Type of Review: Annual Review

Project Title: United Nations Relief and Works Agency (UNRWA): funding basic services and protection for Palestine refugees 2011-15
Date started: March 2012
Date review undertaken: 19 April 2013
## Introduction and Context

What support is the UK providing?
The UK provides predictable multiyear funding to UNRWA. The current funding arrangement is from 2011-2015 (renewing a previous multiyear agreement) and is for a total of £106.5 million, plus an additional £500,000 for evaluation. Of the £106.5 million, £31.5 million is linked to results and progress on reform. The expected payment schedule is. / 2011/12 2012/13 2013/14 2014/15 Total / Core (General Fund) 7,500,000 20,000,000 22,500,000 / (NB 10 million advanced to 2012/2013) 25,000,000 75,000,000 / Reform/Results - 10,000,000 / (reform) 10,500,000 / (reform and results compact) 11,000,000 / (reform and results compact) 31,500,000 / Evaluation 500,000 / Total 7,500,000 30,000,000 33,000,000 36,000,000 107,000,000

What are the expected results?
UNRWA will maintain, and in some areas improve, both efficiency and effectiveness of service delivery. The Agency will maintain its vital protection role. Key results attributable to DFID include: / Results funding – services bought by DFID support – 36,000 children education per year; at least 6,000 pregnant women attending at least four ante-natal appointments each year; over 20,000 households supported by cash-transfers (based on 9% share of total results) and / Policy leverage – UNRWA will implement sectoral reforms based on agreed action plans which will improve the efficiency and effectiveness of health, education and relief services.

What is the context in which UK support is provided?
Summary: / UNRWA provides support to Palestine refugees in five fields of operation (West Bank, Gaza, Jordan, Lebanon and Syria) pending a political resolution to the refugee issue as part of the Middle East Peace Process. It does so in a challenging and highly sensitive political environment - for example during 2012 particular challenges included the November escalation of hostilities in Gaza and the on-going challenge of the crisis in Syria (which has also impacted on UNRWA’s operations in Jordan and Lebanon). The agency is severely underfunded and yet it is facing increased demands on its services as the population of Palestine refugees increases (for example, Gaza, where UNRWA spends over a third of its core budget, has one of the highest birth rates in the world). / Historical context: / The 1948 Arab-Israeli conflict and the formation of the State of Israel resulted in over 700,000 Palestinians becoming refugees. The international community responded to the needs of the newly-formed refugee population by establishing UNRWA via a UN General Assembly resolution in December 1949. The 1949 resolution provided a temporary mandate which, in the absence of a political solution to the Palestinian refugee problem, the General Assembly has repeatedly renewed. UNRWA’s mandate covers both original refugees and their descendants, so the population it serves continues to grow. There are currently over 5 million Palestine refugees registered with UNRWA and this is increasing. The agency relies almost entirely on voluntary contributions for funding. / Today, the refugee problem remains one of the five ‘final status’ issues of the Middle East Peace Process (the others being Borders, Security, Settlements and Jerusalem). Ultimately the UK policy position is that a long term resolution is best achieved through a negotiated two state solution and we continue to work in support of this at a political level. The UK recognises the critical importance of a just, fair and realistic solution to the issue of Palestine refugees as part this. / Pending a political solution, UNRWA’s mandate is to provide basic services (including health, education and relief and social services) to refugees in five fields of operation: the West Bank, Gaza, Jordan, Syria and Lebanon. The relationships between UNRWA, donors, host governments and Palestine refugees are complex and politically sensitive. Although UNRWA has one mandate covering all its operations, how UNRWA applies this varies across each of the five fields (for example, in Lebanon refugees have very little access to government services and as such are highly dependent on UNRWA services). As well as providing basic services, support to UNRWA also plays an important role in fostering regional stability. / Particular challenges in 2012 - by field / UNRWA works in a highly sensitive region and has faced challenges in all of its fields of operation in 2012. / Gaza: The highly restrictive access regime imposed on Gaza has led to a refugee population that is very dependent on UNRWA services. Population growth rates are amongst the highest in the world – for example Gaza has had to increase its education budget in Gaza by approximately US$5 million from 2012 to 2013 to employ new teachers to deal with the increased enrolment. Cuts to emergency food funding in 2013 led to riots and violence against UNRWA premises in Gaza. The escalation of violence between Israel and Gaza in November 2012 both disrupted UNRWA services and created additional needs. / West Bank: Although often perceived as one of the more stable of UNRWA’s operating environments, UNRWA has also faced protests and violence in the West Bank as a result of phasing out some of its Emergency Appeal activities. The Palestinian Authority, which is the other provider of health and education services to the West Bank population (including non-refugees) is struggling with a severe financial deficit and is highly dependent on international aid. / Syria: The most severe challenge in the region during 2012 has been the impact of the Syrian civil war. UNRWA has launched an emergency appeal to meet humanitarian needs as a result of this and the UK has contributed to this, in additional to our core funding which is the subject of this annual review. UNRWA has played an important role in maintaining services to the Palestine refugees remaining in Syria, but it has done so under increasingly difficult circumstances and in many cases continued service provision has been impossible. / Lebanon: The operating context in Lebanon was already difficult – with high dependency on UNRWA services as Palestine refugees have very limited access to Lebanese government services. Camps suffer from high poverty levels and overcrowding as well as frequent security incidents. The already sensitive situation has been compounded by the influx of refugees from Syria, including around 40,000 Palestinians who were living in Syria. / Jordan: Like the West Bank, Jordan is often regarded as a more stable operating environment and the majority of Palestine refugees in Jordan have citizenship. However, the Jordanian government is facing a financial crisis and the sensitivity of the Palestinian issue was highlighted when the Prime Minister announced that the admission of more Palestine refugees (fleeing from Syria) was a “red line”. In this context any attempt to move from UNRWA services to government services would likely cause significant unrest. / Financial challenges / UNRWA is almost entirely dependent on voluntary contributions and its current forecast end of year deficit for 2013 is US$67 million (as of 1 April 2013). UNRWA relies heavily on traditional donors including the EU, European States, the US and Australia. In Europe, many donors have faced domestic financial challenges and in the US, donations were held up in 2012 due to internal political tensions around the Israel/Palestine question. While most traditional donors have managed to maintain their contributions, they are very unlikely to be able to increase them in line with the increased demand on UNRWA services due to population increases. The steps UNRWA is taking to address its dependency on traditional donors are considered further in the risk section below – but financial sustainability remains a severe challenge for UNRWA. In November 2012, at the request of UNRWA, the UK provided a £10 million advance of the 2013/14 core funding to help UNRWA address immediate cash flow issues.

## Section A: Detailed Output Scoring

Output 1: Provide high quality educational services
All results (unless otherwise stated) represent 9% of UNRWA’ General Fund results in 2012. 9% has been applied as this is the estimated DFID share of the programme’s overall core funding (we recognise that actual % share fluctuates depending on currency rates and other donor contributions). / Output 1 score and performance description: Outputs met expectations A / All indicators have been met but not exceeded. On balance, performance was positive and an A score has been assigned because results met expectations. The number of students in basic education and vocational training met the milestones. Progress was also made on reforms with the development of a new training course and the design of a new Education Management Information System (EMIS).
Progress against expected results: / The education programme provides Palestine refugee children and youth with access to quality education and training through 700 schools, ten technical vocational colleges, and two teacher training institutes across its five fields of operation. The results for education are lagged as they are only available at the end of each school year. As such the data for education is relatively unaffected by the on-going humanitarian situation in Syria. 59% of UNRWA’s core funding is spent on education services. / Basic education: Demographic pressures continue to exacerbate strains on already overstretched infrastructure and resources, particularly in Gaza which saw an increase of 5,000 students in the last school year. In Lebanon schools were negatively affected by strikes which saw pass rates in national exams fall from 58% in 2010/11 to 52% in 2012/13. Drop-out rates have been adjusted so they now reflect international standards. These show a slight increase over the last year from 7.4% to 7.6% for males and from 3.9% to 5.0% for females. Lebanon was the only Field Office showing a decline in drop-out rates for both males and females. / Special educational needs: The indicator wording was adjusted and the methodology was updated across all Field Offices so the indicator better measures actual levels of disability. UNRWA are continuing to address the needs of these students and recently adopted a new policy on “Inclusive Education”. The policy sets out how to provide additional support for these students and how to refer them for additional support as well as providing new tools to identify students with special needs. Teachers are being training to use these tools. All new buildings which UNRWA constructs, including all school buildings, meet UNRWA’s new standards to be wheel chair accessible. / Vocational training: The number of students completing vocational training courses continues to increase. These courses provide students with key skills that are relevant to the labour market. 85% of male graduates and 70% of female graduates who completed their studies in 2010/11 are now either employed or are continuing their studies (this figure excludes graduates who are not actively seeking a job). This represents a slight fall on the previous year but continues to exceed the milestone and targets of 83% for males. The milestone of 76% for females was not met. Had Syria employment (which was significantly below expectations due to the local situation) been stable, then employment would have been 73% for females (slightly below the target) and 88% for males (substantially above the target). / Education reform: UNRWA’s education reform strategy for 2011 to 2015 sets out how UNRWA will improve the quality, effectiveness and efficiency of their schools. Two key areas of the reform are the teacher training and the establishment of a system wide Educational Management Information System (EMIS). Teacher training material has been developed and was successfully piloted in every field (except Syria) in October 2012. It was hoped that the training could now be rolled out but there have been delays due to issues with staffing and unions. Good progress is being made on establishing an EMIS. Gaza and Lebanon already have their own EMIS systems but a new agency wide system has now been designed which builds on these. Gaza Field Office will be taking forward the EMIS programme piloting the new system. / Recommendations: / DFID should continue to work with UNRWA on pushing forward the Education Reform Strategy. DFID has supported consultants to work with UNRWA to develop efficiency and value for money indicators for UNRWA’s education programme. UNRWA has committed to incorporate such indicators in its annual reporting on reform. The first report on reform is due by the end of April 2013. This will include baseline data and mechanisms for monitoring value for money. We will continue to support UNRWA to integrate value for money into its reform strategy and to balance quality of service provision with efficiency savings. / Impact Weighting (%): 50% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2: Provide high quality health services
Output 2 score and performance description: Outputs exceeded expectations A+ / All indicators have been met and progress on reforms has far exceeded expectations with much faster roll out of the Family Health Team approach.
Progress against expected results: / 17% of UNRWA’s core funding is spent on health services. Demand for health services remains high alongside the need to focus more on non-communicable diseases which can be expensive. UNRWA has achieved the expected levels of medical consultations along with expected rates of immunisation and ante natal care. UNRWA is implementing an extensive health care reform focussing on adopting the Family Health Team Approach alongside E-health. / The disease profile of Palestinian refugees is shifting with ever increasing proportions of refugees suffering from non-communicable diseases (Diabetes and Hypertension) accompanied by an aging population this is leading to a growing demand for cost intensive secondary, tertiary and long-term care. / Medical consultations: Despite this there was a 9.5% drop in medical consultations over the last year (excluding Syria). Most of the drop was in Jordan and could be due to a change to the Family Health Team Approach but also due to people choosing to access non-UNRWA services. The drop is in line with UNRWA’s reforms which aim to manage demand for health services. This needs to be continued to be monitored through VfM indicators. / Diabetes: The number of diabetes patients rose by 6% over the last year (excluding Syria) and is now at 107,372. This shift is a global phenomenon. UNRWA conducted a clinical audit of their diabetes care in 2012 which showed diabetic control rates for HbA1c at 32% for males and 24% for females, much higher than the <7% recommended by the American Diabetes Association. UNRWA are scaling up their work on diabetes prevention and care through education programmes as well as through the Family Health Team approach. / Ante-natal Care: Demand for antenatal services has declined in all fields with a 6% decline (excluding Syria). This could be due to increased use of other service providers and will be investigated further by UNRWA. Overall 86.5% of pregnant women attended at least four antenatal visits. This varied considerably by Field with the highest rate in Gaza of 94% compared with 77% in Syria. / Health Reforms: Progress on reforms has been much quicker than expected with 33 clinics having now adopted both the Family Health Team approach as well as E-health. In areas where reforms have taken place such as Lebanon the daily medical consultations have reduced from 120 to 80 allowing doctors more consultations time with patients. Waiting times have been reduced and anti-biotics prescription rates have decreased from around 30% to around 20-25%. / Recommendations: / DFID should continue to monitor the progress of reforms and their impact on quality of patient care and should continue to work with UNRWA on efficiency and should look to include some efficiency targets. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Protect the vulnerable
Output 3 score and performance description: Outputs moderately did not meet expectation B / There were mixed results across this output with social transfers achieved whereas microloans underachieved.
Progress against expected results: / Social transfers: UNRWA continue to provide around 290,000 individuals with social transfer payments which represents around 5% of the registered population of refugees. UNRWA no longer collect information on “percentage of social safety net individuals who are abject poor” so this indicator was changed to the “percentage of refugees identified to be poor who receive a social transfer”. This indicator varies across the Field Offices from 21.1% in Jordan to 100% in Gaza which reflects the different contexts. In West Bank there was a fall from 85% in 2011 to 59% which was due to a phasing out of the emergency appeal programme. As a result UNRWA’s programming in West Bank has focussed on core services and supporting the most vulnerable. / Microfinance: Micro finance is not directly supported through DFID core funding. Whilst there have been a number of efforts to move the micro finance to outside of UNRWA to enable the programme to expand this has not happened and as a result the programme is not expanding as fast as expected. Excluding Syria (with only 899 microloans in 2012 compared with 1,652 in 2011) there was a 20% increase in the total number of microloans but this was below the expected increase of 54%. This has been raised at Advisory Committee meetings and whilst most donors are supportive host countries remain concerned and are seeking additional consultation before the micro finance programme is moved outside of UNRWA and expanded. / Recommendations: / DFID should remove the microfinance indicator as it is not funded through the Core Fund but should continue to support the work through Advisory Committee meetings. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 4: Ensure protection of human rights
Output 4 score and performance description: Outputs met expectation A / There was a slight underachievement in the first indicator whereas on the second one good progress was made.
Progress against expected results: / Registrations/Inscriptions: UNRWA continued to rollout the Refugee Registration Information system. In 2012 more than 17 million historic documents such as pre-1948 land deeds, employment records, and birth certificates associated with family files were compressed and electronically stored. This includes 40,000 records for Palestinian Refugees in Syria. The performance of West Bank Field improved from 75% to 92% of new inscriptions/registrations meeting UNRWA standards but is still the lowest across the Field offices with 100% in both Gaza and Lebanon. / Human Rights and Conflict Resolution: In 2011 UNRWA adopted a Human Rights, Conflict Resolution and Tolerance policy. This was followed in 2012 by the development of a toolkit which was tested in Gaza and West Bank. The toolkit is now being adapted, based on feedback from the pilots, and UNRWA is on track to start rolling out training to its 19,000 teachers in 2013. / Gender Based Violence: Although there was no specific indicator on Gender Based Violence (GBV) this was a part of UNRWA’s work on protecting human rights. During 2012 all fields continued work on detecting GBV survivors and providing access to services through the referral systems. The referral system was expanded to all four fields (excluding Syria). There was a twin track approach: building/ consolidating new partnerships and introducing the project to new areas. The capacity of frontline staff was increased with 654 receiving basic training; 463 in-depth training and 626 specialised training. 250 tools and communications events were organised with the community. As a result the number of survivors detected (Dec 2011 to Nov 2012) is 1,512 of whom 1,145 accessed services (counselling, legal aid, medical care and social support). / Recommendations: / DFID should replace indicator 4.1 “percentage of new inscriptions/registrations meeting UNRWA standards” with a new indicator on gender based violence as this better reflects the breadth and depth of UNRWA’s work on protecting human rights and is consistent with the UK’s policy priorities on women and girls. / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y/N / Yes. As agreed between MENAD’s senior statistician there were minor changes to the following indicators: / Outcome indicator 3: "Percentage of graduates working in a job in relation to their training or studying in a relevant field on year later” was changed to “Percentage of graduates employed or continuing their studies among active job seekers” to be more in line with international standards / Output indicator 1.2: “Percentage of children identified as having disabilities”. Although this indicator remained the same field offices were given more guidance on classification of disabilities which led to a reduction in the overall numbers. / Output indicator 3.2: “Percentage of social safety net individuals who are abject poor” was changed to “Percentage of refugees identified (or estimated) to be poor who receive a social transfer.” / 1.2 Overall Output Score and Description: / Outputs met expectation A. The average ratio of achievement across all four outputs was 93%. / 1.3 Direct feedback from beneficiaries / UNRWA have started to incorporate more feedback mechanisms into their work, particularly as part of implementing their reform strategies in education and health: / Education – all schools have a complaints box where staff and students can write down any feedback. These are then forwarded to the Camp Services Officer and headquarters for further action. As part of the reform process in depth consultations are being held with communities. / Health – all health clinics have a complaints box where staff and patients can give feedback. The feedback is collated and sent to the Camp Services Officer and headquarters for further action. As clinics adopt the Family Health team approach UNRWA conducts in-depth consultations with each community. UNRWA are also planning a survey of patients to assess the effects of the move to the Family Health Team approach. As part of this annual review two health clinics were visited and informal discussions were held with patients. “This new system is excellent. The time that nurses and doctors devote to me and my family is much more than before. I hope the change is permanent because it gives me and my family more care.” Amina Diab Ahmad, Rashidieh Clinic Lebanon. / We will continue to encourage UNRWA to continue to improve its engagement with beneficiaries, and to make more quantitative assessments of the direct feedback it receives where possible. In evaluations, we will highlight the importance of including direct feedback from beneficiaries.
1.4 Summary of overall progress / Overall progress has been good with UNRWA continuing to deliver high quality basic services to a growing refugee population people. Progress on education reforms is on track although more recently is beginning to slow down whilst health reforms are progressing much faster than expected with very positive feedback from staff and patients. / This has been in a challenging and highly sensitive political environment - for example during 2012 particular challenges included the November escalation of hostilities in Gaza and the on-going challenge of the crisis in Syria. The agency is severely underfunded and yet it is facing increased demands on its services as the population of Palestine refugees increases.
1.5 Key challenges / The biggest challenges for UNRWA are (i) its financial situation (it has a forecast end of year deficit for the General Fund in 2013 is US$67 million as of 1 April 2013); and (ii) the unstable and political sensitive context in which it operations. These challenges are considered in more detail in the “risks” section below.
1.6 Annual Outcome Assessment / The programme is broadly on track to deliver against its outcome indicators. Education and health reforms are continuing with effects already being shown in health care (reductions in the average number of daily medical consultations per doctor).

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / Yes, the overall project is on-track against financial forecasts. However, UNRWA continues to face severe issues of financial sustainability and in November 2012 (at UNRWA’s request) the UK advanced £10 million of the 2013/14 core funding to help UNRWA address urgent cash flow needs and maintain its service provision. We will continue to work with UNRWA, other donors and hosts to try and put UNRWA on a more sustainable financial footing (for more on this, see Section 4: Risk below). / 2.2 Key cost drivers / Nearly 80% of UNRWA’s General Fund spend is salaries for frontline delivery staff, which is one of the hardest cost drivers for UNRWA to address. UNRWA’s staff unions are strong and well organised and UNRWA is often subject to strike action affecting service provision. We will work with other donors and hosts within the framework of the Medium Term Strategy planning to address both headcount and salary issues, but we recognise that finding a solution will not be easy. / The underlying cost driver is the population of Palestine refugees, which continues to grow. For example, in Gaza (which has one of the highest population growth rates in the world) UNRWA has had to increase the education budget by approximately US$5 million from 2012 to 2013 to employ new teachers as the enrolment rate increases. / 2.3 Is the project on-track against original timescale: Y/N / Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / DFID has funded a study looking at how to best measure and monitor efficiency and value for money in delivery of UNRWA’s health and education services. The study was finalised in April 2013. The study suggests indicators and provides baseline data and targets, which UNRWA has agreed to incorporate in its annual reporting on its health and education reform. This will provide an improved evidence base to assess the efficiency of UNRWA’s service delivery and the value for money of its reforms. / In 2009, UNRWA started an electronic health record system (e-health) which is allowing them to develop a cohort reporting system to improve the quality of hypertension and diabetes management services. / UNRWA conducted a clinical audit on their diabetes care with technical and financial support from World Diabetes Foundation. 1,600 patients were selected (50 from each Field Office). The study found the control rate of diabetes was low(the satisfactory diabetic control for HbA1c is <7% whereas this group was at 28.3% - with 32% among males and 24% among females). Possible reasons were cited as the high obesity rate (64%) and low levels of health education. UNRWA is addressing these concerns through the adoption of the Family Health Team approach which aims to improve health outcomes through focussing on a family rather than a patient They are also scaling up work on health education. The incidence of diabetes is increasing across the region (check data) and this will put an additional burden on already stretched resources and UNRWA health facilities. The move to Family Health Team approach was published in the Lancet. / 3.2 Where an evaluation is planned what progress has been made? / Discussions still underway with UNRWA and other donors to agree an evaluation plan. Progress has been slow as DFID has been trying to develop a joint evaluation plan with UNRWA and key donors. DFID will continue to push this work forward.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium. / 4.2 Assessment of the risk level / The risks identified in the business case risk table remain valid. Two risks identified as “high risk” did occur in 2012: / Risk 5 (Gaza conflict between Israel and Hamas, or re-tightening of blockade) was highlighted last year when the November 2012 conflict impacted on UNRWA service delivery. UNRWA continuation of support throughout the conflict played an important role in mitigating humanitarian consequences. Health centres and food distribution centres were able to remain functioning, and while schools were closed during the conflict itself some education was carried out remotely and they reopened soon afterwards. / Risk 11 (escalation in security situation in Syria leading to temporary or longer terms closure of UNRWA’s facilities and inability to access their beneficiaries) has also occurred. In addition, this has impacted on Lebanon field in particular, which is dealing with an influx of approximately 40,000 Palestine refugees, aggravating an already overcrowded and sensitive situation in the northern camps. We are taking steps to mitigate this risk through the UK respond to the Syria crisis, which includes support to UNRWA’s Emergency Appeal for Syria (covering both maintaining services in Syria, and additional support to deal with the extra refugees in Lebanon). / As described further in the “context” section above, the sensitivity of UNRWA’s role has been highlighted throughout the last twelve months - for example protests and violence in Gaza when cuts were made to the food security programme in early 2013, and strikes and protests in the West Bank in 2012 when UNRWA reduced its Emergency Appeal programme in that field. / The biggest risk to service delivery is the financial situation of UNRWA. UNRWA has a forecast end of year deficit for the General Fund in 2013 is US$67 million as of 1 April 2013. / The political realities of its operating context make it extremely difficult to seriously address sustainability. Until a final solution to the Palestine refugee issue is negotiated as part of the Middle East Peace Process, the provision of services by UNRWA is politically significant and refugees and host countries in particular are highly sensitive to any changes in service provision. Service provision is seen as symbolic as well as practical and is often linked with refugee rights including the right of return. Any attempt to change or reduce UNRWA services usually results in protests and instability in this already sensitive region (e.g. violence against the UNRWA office in Gaza when the food security programme was reduced due to lack of funding in 2013). Even aside from the political sensitivities, the reality is that hosts such as Jordan and the Palestinian Authority are also facing financial crises and would be unable to take on the additional burden of service provision for refugees. / While significant progress has been made on efficiency in the education and health sectors, success on this alone will not solve UNRWA’s longer term sustainability challenge. UNRWA has made significant progress on Resource Mobilisation, but it is unlikely to be able to raise enough funds to meet the increasing demand on services as the Palestine refugee population continues to grow. / Risk table from Business Case / Risk Risk assessment Mitigation strategy / Likelihood Impact / Country level risks[1] / 1 Middle East Peace Process stalls/fails to the point where two state solution no longer viable High Low FCO-led diplomatic activity with parties and with international community / 2 Loss of PA as credible or acceptable partner Medium Medium It’s likely that this would result in more demand on UNRWA services in the OPTs. We will consider alternative service delivery mechanisms / 3 Conflict, civil unrest, settler violence or terrorist threat/ attacks in Gaza, West Bank/East Jerusalem/West Jerusalem raise security threat level, with consequences for both staff duty of care and programme delivery Medium Medium Potential for emergency humanitarian needs – through UNRWA or other organisations. We will continue to monitor the situation / 4 Gradual easing of movement & access restrictions in the West Bank is stalled or reversed, with negative consequences for economic growth, poverty and the fiscal sustainability of the PA Medium Low No immediate impact on UNRWA other than potential increase in logistical costs. We will continue to monitor and support Quarter and UN activity. / 5 Gaza conflict between Israel and Hamas, or re-tightening of blockade Medium High Demand on UNRWA services in Gaza already high due to the declining public institutions. It is unlikely that this will raise massively. The blockade will affect UNRWA’s ability to deliver its programmes and will potentially increase logistical costs. / Continue with diplomatic and development efforts to improve socio-economic conditions in Gaza, including by lobbying Israel for implementation of commitments on movement and access. Continue political lobbying against escalation by either side and the need to respect International Humanitarian Law. / 6 PA fiscal crisis - and UNRWA funding shortfalls - leads to non-payment of salaries, with negative consequences for public services, economic growth, poverty and risk of conflict High Medium Encourage and support PA and UNRWA to continue to raise adequate funds while implementing reforms to reduce external financing needs. / Support UNRWA’s Resource Mobilisation plan / 7 UNRWA fails to deliver Low High More aggressive targeting of specific change via amendments to the Results Compact / 9 Natural disasters impact on area (especially earthquakes) Medium High Refugee camps are old with poor infrastructure. A natural disaster impact on refugees would be devastating. / Conflict Pool is funding support to Palestinian Civil Defence including natural disaster preparedness and response; DFID exploring future support under Security & Justice programme. This will benefit refugees in OPTs / Encourage UNRWA to consider emergency response in its plans and risk management. / Field specific risks (Lebanon, Syria and Jordan only. See risk 3 for Gaza and West Bank, risk 5 for Gaza and Risk 4 for West Bank) / 10 Lebanon – escalation in security situation and worsening of movement & access fro refugees Medium High We will monitor through FCO in Lebanon / 11 Syria – escalation in security situation leading to temporary or longer terms closure of UNRWA’s facilities and inability to access their beneficiaries Medium High There were cases when UNRWA had to close its facilities for one or few days due to violence. We will continue to monitor this through UNRWA and MENAD Regional / 12 Jordan – public sector pay increases, adding pressure on UNRWA to increase salaries for its staff High Medium We will engage with the Jordanian UNRWA representatives on this and continue to raise the issue of affordability and the inability of the agency to match public sector increases
Risk of funds not being used as intended / The 2011 Fiduciary Risk Assessment conducted by DFID found that that there has been a dramatic improvement in UNRWA’s financial management systems since 2009 and that the fiduciary risks of using their systems is now LOW (down from MEDIUM). The FRA used the Public Expenditure and Financial Accountability (PEFA) assessment methodology, in order to benchmark UNRWA’s systems against international standards. The risk of funds being misused is also lowered by the fact that the delivery chain for UNRWA is short – unlikely most UN agencies, it acts as a direct service provider. / UNRWA’s financial report and audited financial statements for the biennium ended 31 December 2011 was published in June 2012. The audit report is not qualified but it does raise matters for attention. The principle concern raised by the Audit report is about the operating deficit and the limited cash position of the Agency. Note 19 to the audit report highlights UNRWA’s dependency on voluntary contributions and the fact that a lack of steady contributions puts a strain on programme activities. DFID is very aware of this. The UK provides multi-year, predictable funding to UNRWA’s General Fund and encourages other donors to do the same. UNRWA reports regularly to the Advisory Committee on its progress with its resource mobilisation strategy. We are also closely engaged with the development of UNRWA’s Medium Term Strategy, which the audit report notes will be key to appraising “whether [UNRWA] should or should not continue to be involved in the array of specific humanitarian services it currently supplies” and therefore may have an impact on future cash outflows and the sustainability of UNRWA’s financial position. / It should also be noted that from 1 January 2012 UNRWA commenced financial reporting in accordance with IPSAS (accrual accounting), moving from the earlier UNSAS (cash accounting) framework. As part of this process it is moving to annual financial reports and audits. The audit for 2012 will be published around June 2013. We view the shift to IPSAS accounting as a positive change which should enable UNRWA to better monitor and assess its financial situation through the recording, on a monthly basis, of assets and liabilities. The shift in accounting does not affect the cash position of the Agency, although there are some key changes to the Agency’s Income Statement. This is due to the registration of assets, the annual depreciation of non-cash assets, the recognition of employee severance entitlements and the exclusion of capital and severance cash payments.
4.4 Climate and Environment Risk / UNRWA are undertaking a range of measures to address environmental issues. They have already introduced measures such as recycling and more efficient lighting. In particular they are piloting a “green building design” in Gaza with funding from Saudi Arabia. This includes using thermal masses, reverse heat exchange and using solar power for electricity. This pilot includes training and knowledge transfer which will be used to help in future projects. / Jordan is one of the most water poor countries in the world. In response the Jordan Field Office has a number of initiatives including: / Design and construction of buildings in an environmentally friendly way; / Piloting using solar water heating systems in health centres and schools; and / Use of grey water expanded to other installations following successful piloting in a few schools.
[1] The likelihood of country risk is kept in line with our assessment. The impact is changed according to our judgment of the risk impact on UNRWA funding

5. Value for Money
UNRWA’s November 2012 Financial Update to the Advisory Committee showed a relatively high spend on “Support Costs” of 13% of the General Fund. It is not clear how much of this is true administrative overhead and how much is attributable to programme. UNRWA is undertaking an Activity Based Costing exercise which will enable it to better understand the cost drivers of its programmes, and the real cost of delivering its services. This exercise has been subject to some delays but is expected to be completed by July 2013. We will include this in the Results Compact as a key deliverable for UNRWA in this funding year. / 5.2 Commercial Improvement and Value for Money / Health reform / The results of UNRWA’s pilot of the Family Health Team approach (as reported in November 2012) have been positive. UNRWA’s initial analysis has identified several potential efficiencies including a reduction in the workload of doctors and improvements in the quality of care. For example, the number of daily medical consultations of doctors has reduced from around 120 to around 80 in pilot clinics in Lebanon and drug prescription rates have fallen by around 5%. Recurrent costs of health reform are relatively low – approximately USD 543,000 across all fields. This is not a net recurrent cost and does not take into account cost savings and efficiencies, which are expected to exceed this amount. UNRWA does need to do more work to quantify these net savings, and to set clear unit cost efficiency baselines and targets. DFID has supported a study by a health economic to develop these and UNRWA has committed to including them in its annual report on reform, due by the end of April 2013. / Education reform / UNRWA has made initial estimates (as of November 2012) that roll out of the education reform strategy across all fields could lead reduction in wastage (money spent on children who then drop out) of approximately USD10 million per annum by 2016, and actual cost savings of around £3.5 million per year. Full details of this calculation have not been provided, but the UNRWA education team has been working with a DFID funded education economist in order to establish indicators, baselines and targets to better quantify and monitor efficiency savings from education reform. These will be included in UNRWA’s annual report on reform, due by end of April 2013. / 5.3 Role of project partners / DFID is a member of UNRWA’s Advisory Committee as well as the Sub- Committee (which the UK is vice-chairing in 2013) and as such works closely with other donors. / 5.4 Does the project still represent Value for Money : Y/N / Yes. The Business Case calculations showing the high net present value for the services UNRWA provides, particularly education, remain valid. In 2012/2013, DFID funded a study by health and education economists who worked with the UNRWA sectoral teams to support them to increase their capacity on Value for Money issues and to establish indicators, baselines and targets against which value for money can be measured. This work will be valuable in increasing the evidence base to show the project represents Value for Money, and in understanding how efficiency might be improved. The results of the Activity Based Costing exercise now due to be completed by UNRWA in July 2013 will also support this. The newly developed Value for Money indicators will be incorporated in the Results Compact/Performance Tranche in order to incentivise UNRWA to take this seriously. We will also encourage other donors who use performance based funding to adopt Value for Money criteria. / There is no alternative mechanism or organisation through which the needs of Palestinian refugees can be comprehensively met. Complementary mechanisms and service providers do exist but UNRWA is the only organisation with the legitimacy and capability of delivering the necessary combination of support. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / There is no conditionality but funding is linked to reform and we are developing a Results Compact/Performance Tranche which will include a focus on reform and value for money. The template this for 2013 is included as Annex A to this review.

7. Conclusions and actions
Overall UNRWA continues to deliver high quality basic services to a growing refugee population. It has been a particularly challenging year due to conflict and instability in the region. UNRWA has made excellent progress on health reforms which are helping to improve both the efficiency and effectiveness of these services. / Actions / Continue to work with UNRWA on implementation of education and health reforms as set out in their reform strategies. / DFID to develop a results compact/performance tranche for future years which will include progress on service delivery, reform, and value for money indicators. / DFID will continue to work with UNRWA and other donors to develop a joint evaluation plan for the period to end 2015. / DFID should consider dropping or amending the microloans indicator as DFID funding to the core fund is not used for this and as such should not form part of the assessment. We would continue to support expansion of the microfinance programme. / DFID should amend the logframe indicators for output 4 replacing the indicator on inscriptions with one on gender based violence, to be discussed and agreed with UNRWA. / DFID should continue to engage in the development of UNRWA’s Medium Term Strategy and in with political colleagues in order to help address UNRWA’s longer term sustainability issues.

8. Review Process
This review was undertaken by DFID’s OPTs Poverty, Hunger and Vulnerability Pillar Lead, who oversees the programme and manages DFID’s institutional relationship with UNRWA and DFID’s Senior Statistician for the MENA region. The review is based largely on: / Discussions with UNRWA throughout 2012 and 2013; / Participation in Advisory Committee and SubCommittee meetings throughout 2012 and 2013, including the documentation and reports presented through these forums; / UNRWA’s Harmonised Results Reports for 2011 and 2012; / The Annual Report of the Department of Health 2012, UNRWA / A variety of field visits to camps including health centres and schools in the West Bank, Jordan, Gaza (limited due to security concerns) and Lebanon (limited due to travel cost and security concerns – but close liaison with British Embassy Beirut lead on Palestine refugee issues) throughout 2012 and 2013. No field visit to Syria was undertaken during this review period due to the security situation.

## Annex 1: Draft Results Compact/Performance Tranche Assessment

UK core support to United Nations Relief and Works Agency for Palestine Refugees (UNRWA) 2012-2015

Results Compact/Performance Tranche Assessment for 2013/2014

Section 1: Delivery against key indicators, including on reform (50%)

Target	Achieved?
Overall score of A of higher in DFID’s Annual Review	Yes

Note: 2013/14 assessment based on 2012 results as presented in UNRWA’s Harmonised Report (published end of March 2013).

Section 2: Progress on value for money (25%)

Target	Achieved?
Develop a coherent set of health and education value for money indicators with baseline data and include these in the 2012 reform report (to be published by May 2013).
Develop targets for health and education value for money indicators up to 2015, with a commitment to report against them in future annual reform reports (by November 2013).

Additional comments on progress on reform/value for money:

Overall assessment – achieved/not achieved.

Section 3: Medium Term Strategy (MTS) (15%)

Target	Achieved?
Draft MTS presented at November 2013 Advisory Committee is: / Developed through a consultative and inclusive process; / Fully costed; / Based on realistic donor income and population projections; and / Addressing key cost drivers, including staff salaries.

Additional comments on progress on reform/value for money:

Overall assessment – achieved/not achieved.

Section 5: Transparency and evaluation (10%)

Target	Achieved?
Activity Based Costing exercise completed by June 2013.
Monthly Financial Reports provided to donors (or available on request).
Successful transition to IPSAS accounting – unqualified audit report received (expected July 2013).
Develop an evaluation plan which is / comprehensive, covering all planned evaluations regardless of funding source; / costed; / reflects medium term evaluation priorities; and / shared with Advisory Committee members.

Additional comments on progress on transparency and evaluation

Overall assessment – achieved/not achieved.

FINAL COMMENTS AND ASSESSMENT