## Sheet1
PROJECT NAME | CROSS CUTTING DISABILITY RESEARCH PROGRAMME
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  | Documents
Contribute to an increase in the effective and sustained social and economic inclusion of disabled people in developing countries, through partners developing policies to incorporate disability within their programmes and research | Number of policy briefs/research papers within bilateral and multilateral donor agencies (DFID, AusAid, GiZ and World Bank) addressing cross-cutting disability issues. | Planned | 0 | 2 | 4 | 8
Achieved
Source
|  |  | DFID/AusAid/World Bank policy briefs and research reports (bilateral and multilateral organisation websites), DFID funded RPC publications and reports (R4D website) |  |  |  |  | Policy briefs are under development; I am contacting DFID re R4D
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
New knowledge is generated and used by policy makers and other stakeholders to improve policies and practices to actively include persons with disabilities at the centre. | No. of examples of research outputs that generate policy-relevant findings which actively affect the inclusion of persons with disability in policies and practices. | Planned | 2 (ABBA, RECOUP) | Research findings evident in at least 5 policy dialogues and decision-making processes - e.g. DFID includes use of research evidence in DFID policy briefings, PRSPS, country strategies, etc. | Research findings evident in at least 15 organisations - policy dialogues, decision-making processes and development programme policies - e.g. DFID includes use of research evidence in DFID policy briefings, PRSPS, country strategies, etc. | Research findings evident in at least 30 policy dialogues, decision-making processes and in development programme policies and implementation e.g. DFID includes use of research evidence in DFID policy briefings, PRSPS, country strategies, etc. | That there is a stable and secure economic and aid-policy environment. Bilateral and multilateral agencies are committed to developing policies and operational modalities and have sufficient financial resources to effectively cross-cut disability in their core programmes. Governments and other key stakeholders in developing countries have resources, infra-structure and political will and commitment to the gender sensitive implementation of appropriate policies, programmes and practices for the social and economic inclusion of disabled people. Research generated effectively informs and is utilised by donor agencies, government and civil society institutions in developing genuinely inclusive policies and programmes.
Achieved
Source
|  |  | LCD Systematic review on disability and poverty. RPC and other research/strategy/ policy documents and TORs for further research programme proposals. DFID policy briefings, country strategy papers and programme calls. Quarterly and annual programme reports submitted to DFID by other stakeholders (including gender analysis disaggregated by sex/age/other variables). |  |  |  |  | Systematic review submitted; draft SHARE future proposal submitted;
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| No. of users, academics and decision makers reporting that they are using, building capacity, and promoting uptake of research results to cross-cut disability in their development policy and practice by end yr 3 and satisfaction with research results | Planned | 2 (ABBA/ RECOUP) | At least 10 target users report use and satisfaction with research results and include disability as a cross-cutting issue in policy and practice | At least 15 target users report use and satisfaction with research results and include disability as a cross-cutting issue in policy and practice | At least 25 target users report use and satisfaction with research results and include disability as a cross-cutting issue in policy and practice - e.g. DFID promotes use of research evidence through cross-cutting guidance in policies, PRSPS, country strategies and calls for proposals.
Achieved
Source
|  |  | Agendas and minutes of meetings held with donors, government official in developing countries, other DFID-funded research centres, international networks, and disabled people’s organisations. Reports (with gender analysis disaggregated by sex/age/other variables) produced by international and in-country cross-cutting and disability-specific NGOs working in the disability sector. Example development programme proposals including disability as a cross-cutting issue. Disability and gender mission statements in policy documents. |  |  |  |  | SHARE minutes submitted;
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
0.25 FTE (Principal Researcher); 3 x 0.2 FTE (Senior Researchers); 0.5 FTE (Project Coordinator)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumption
Programme Management RPC effectively managed and partnerships maintained throughout the 3 yr CCDRP. | Functioning partnerships with up to 4 RPCs with signed and delivered MOUs. | Planned | 0 | 2 | 3 | 4 | That productive collaborative research partnerships are maintained throughout the 3 years with other DFID-funded RPCs. Management, staff and partners share a common understanding of the right to gender equality and the need for gender sensitivity. Management, staff and partners understand the links between gender and disability and incorporate this into their everyday work.
Achieved
Source
|  | Contracts, MOUs, Consortium Advisory Group, management structure of specific research outputs, all disaggregated by gender. | [5 empty] | CAG minutes submitted; All contract/MoUs submitted
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Functioning CAG which advises on and supports CCDRP uptake results | Planned | Inception phase: Members of CAG finalised and gender balanced. | CAG identifies high level uptake channels. | Annual CAG meetings well-attended, gender balanced and constructive. | Annual CAG meetings well-attended, gender balanced and constructive.
Achieved
Source
|  | Attendance records, minutes and resolutions from the meetings. Outcomes from regular contacts with the members of the CAG. Gender monitoring of CAG proceedings. | [5 empty] | CAG minutes submitted;
IMPACT WEIGHTING (%) | Output Indicator 1.3 | hfp | Baseline | Milestone 1 | Milestone 2 | Target (date)
20% | Gender balance and policy and practice on gender and disability maintained throughout. | Planned | Inception phase: Gender Strategy statement developed. | Research teams gender balanced. | Management, staff and partners engage in organisational discussions on gender. | Ditto contribute to discussions on gender equality outside their organisation.
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Mission statements on gender and disability from all partners. Management /staff ideas, discussions, reports on gender monitoring. Partner gender strategies and reports. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Research By end of year 3, research evidence is generated using new methodologies, and policy makers are using research to take concrete steps to cross-cut disability in their core programmes. | No. and quality of partnerships with research community who are undertaking cross-cutting disability research. | Planned | Pre-inception: Quality of dialogue with potential partner RPCs. Inception: Commitment of chosen RPCs to partnerships. | Phase 1: Level and quality of commitment of chosen partner RPCs (up to 4) | Phase 2: Level and quality of commitment of chosen partner RPCs (up to 4) | Phase 3: Level and quality of commitment of chosen partner RPCs (up to 4) | By the end of yr 3, the evidence generated by this research programme will have begun to engage and effect change in including people with disabilities in the policy of donor governments. Research and policy monitoring not destabilised by political intervention, armed conflict or other external crises. That the CCDRP succeeds in attitude and behaviour change in target groups (e.g. policy makers, researchers, academics, etc).
Achieved
Source
Meeting resolutions. Potential and chosen partner perception surveys. Research review document. External evaluation.
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| No. of targeted DFID-funded research programmes including disability as a cross-cutting issue | Planned | 0 | 2 | 3 | 4
Achieved
Source
Evidence papers. RPC research plans, actual research data. Pieces of research available that incorporate disability as a key component / that cross-cut disability. Research cited by other users Reports on DFID-funded research programmes to DFID.
| Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| No of peer reviewed and open access evidence and research papers produced and published. | Planned | 0 | 3 | 6 | 10
Achieved
Source
Evidence papers and policy briefing papers distributed to stakeholders Evidence papers and policy briefing papers available on website and available from other open access sources
| Output Indicator 2.4 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| No. of evidence papers and policy briefing papers actually in use by DFID and other stakeholders. | Planned | 0 | 3 | 6 | 10
Achieved
Source
Evidence papers and policy briefing papers distributed to stakeholders Reference to such papers in DFID/other stakeholder outputs
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
40% | Gender balance and disability analytical framework developed and implemented and data generated by research programmes is dissagregated by sex | Planned | Inception phase: Gender strategy (including analytical framework) developed. | At least 3 research papers reflecting gender analysis | At least 4 research papers with a gender and disability specific theme | Research partners implement gender and disability framework.
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Mission statements on gender and disability from all partners. Management /staff ideas, discussions, reports on gender monitoring. Partner’s gender strategies and reports. Data sets/reports dissagregate results by sex |  |  |  |  | High
INPUTS (£) | DFID (£) | Source | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Research uptake By the end of yr 3, evidence-based knowledge and new methodology on disability and poverty shared with target groups and disseminated widely | Number of CCDRP engagements with policy makers and other key stakeholders on policy options and research evidence. | Planned | Inception phase: Completed draft of Research Uptake Strategy | DPO and CCDRP participation in 5 high-level policy forum | DPO and CCDRP participation in 10 high-level policy forum | DPO and CCDRP participation in 20 high-level policy forum | That the research generated through programme publications, policy briefs, and outputs from workshops, seminars and conferences is effectively and widely accessed and put into practice.
Achieved
Source
Conference presentations and attendance, and subsequent feedback from participants Web-based material demonstrating, constructive discussions, uptake and web-sharing of information and research by others.
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Extent and quality of regular usage of CCDRP webpage (within LCD website) by DPOs, NGOs, bilateral and multi-lateral donors, potential research users (e.g. World Bank, etc.), relevant government ministries in developing countries, academics worldwide, the media. | Planned | CCDRP web page added to existing LCD website | Increase number of total hits | Total hits increase by a further 50% | Fully-functioning webpage effectively used/ contributed to by a wide range of stakeholders.
Achieved
Source
Positive feedbacks, web discussions, information exchange. Quality of information exchange through network user surveys. Actual use of research in policy-making.
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20% | Number of examples of research evidence being used to generate discussion about the need to cross-cut disability and development (amongst academics, DPOs, donors, policy makers, NGOs, development pratitioners, researchers and other stakeholders) | Planned | 0 | 10 (To have established a network of researchers working in disability and development) | 25 (develop relationship with media, examples of policy briefing papers being used by policy makers, donor agencies and development practitioners) | 50 (active and sustainable network of disability and development practitioners; 4 regional dissemination workshops; final international research uptake conference)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Peer reviews/citations Media impact – citations Online development blogs NGO and bilateral/nultilateral citations Dissemination workshops - regional and international |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Capacity building Capacity of research partners and disabled people's organisations to do and use research is strengthened through mutual knowledge exchange. | No. of quality participatory research materials produced by the CCDRP and their partners, for DPOs, universities and other stakeholders which are used to influence programmes, policy, knowledge and practice which includes persons with disabilities. | Planned | None | 5 - (Development of DPO Training manual; involvement of 5 DPOs, universities and other stakeholders) | 10 (Finalise University course on disability and Development, Pilot DPO training manual; involvement of 10 DPOs, universities and other stakeholders) | At least 20 DPOs, universities or other stakeholders use CCDRP materials for policy, advocacy, awareness raising, or programming purposes | Stakeholders have the ability to process the information given and can access the data and information given, and assimilate it. That good working relationships are maintained with partner international disability and development networks and organisations throughout the programme.
Achieved
Source
Research materials (DPO Training manual, Powerpoint presentation on disability and development for university courses) Reports on outcomes of collaborations. Reports from cross-exposure seminars. Feedback (via forms etc)
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
20% | Number of partners - e.g. DPOs, academics, students, field researchers trained or participating in disability issues with approximately equal numbers of women and men. | Planned | 0 | 20 | 50 | 75
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Final reports and feedback from university/DPO research internship exchanges, and intern surveys Attendance lists from field researcher training sessions Creation of course materials Number of lectures/seminars given Inclusion of disability in future curriculum Gender disaggregated statistics from research partners. Equal numbers of men and women participating in training workshops |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)