Type of Review: Annual Review

Project Title: Social Fund for Development (Phase IV)

Date started: Dec 2011	Date review undertaken: Nov 2013 - Jan 2014

## Introduction and Context

What support is the UK providing?
In 2010, DFID committed to provide £100 million over five years between January 2011 and December 2015 to Phase IV of the Yemeni Social Fund for Development (SFD) to improve access to basic services, enhance economic opportunities and reduce vulnerability for the poor.

What are the expected results?
DFID support will enable SFD to meet their overall aim to improve the lives of the Yemeni poor. The main objectives of our support are: / improve access to basic services, such as education and health facilities; / create economic opportunities and improve the business environment; / create employment opportunities for the poor; and / increase the ability of local authorities, NGOs, and communities to manage, monitor and evaluate development programmes. / In total, the programme will: / enable the construction and/or rehabilitation of 9,000 classrooms and 80 health centres / provide access to credit and savings for 100,000 clients / provide employment opportunities for 300,000 poor people / train 7,720 individuals and organisations in project planning / This is a multi-donor supported project and DFID’s contribution equates to 14% of the total budget. Key results attributable to DFID therefore include: / Over 50,000 pupils enrolled in SFD-supported schools / 6,720 households provided with new/improved drinking water / Over 150,000m3 of water stored in protected facilities / 3,360,000 employment days created / To improve the lives of the Yemeni poor / IMPACT / To improve access to basic services, enhance economic opportunities and reduce the vulnerability of the poor / OUTCOME / Community and Local Development Programme: Basic services improved / Small and Micro Enterprises Development Programme / Labour Intensive Works Programme: Reduced vulnerability for the poor / Capacity Building: Stakeholders capable and empowered / OUTPUTS

What is the context in which UK support is provided?
Yemen is one of the poorest countries in the Middle East and poverty is widespread with 47% of the population living on less than $2 a day.[1]Rural areas are home to 73 per cent of the population but 84 per cent of the poor.[2] Remote, widely scattered villages and poor road conditions make access to health and other social services extremely difficult. Educational facilities are also inadequate, both in number and in the quality of teaching materials. / Yemen is the seventh most food insecure country in the world, ranking 72 out of 78 countries in the 2013 Global Hunger Index.[3] More than 10 million Yemenis, or 44.5% of the population, are now food insecure.[4] Yemen imports over 90% of its wheat, making it particularly vulnerable to fluctuations and volatility in global food prices. / Population growth is one of the world’s highest at 3.03% with the current population of 24 million expected to reach 60 million by 2050 (UNFPA). Under this scenario 2.2 million new jobs would be needed, and there would be 14.7 million children in primary school, requiring 490,000 teachers (IRIN Middle East). In addition, estimates suggest that unemployment, and particularly youth unemployment, is high, nearing 70 per cent. There are few viable employment opportunities for the rural poor and generating income through agriculture is difficult as access to markets and arable land are limited and livestock production unsustainable. This has contributed to Yemen’s alarmingly high rates of undernourishment. / People are poor in Yemen because of a lack of income and assets but also because they lack the power to make decisions to improve their lives. This is true at a national and political level, where power is shared among and restricted to a tiny elite; as well as at a local and community level where typically a small group (usually of male elders) makes decisions; and in the household, where the male head traditionally makes decisions and controls resources. Access to and control over resources and opportunities are often determined by tribe or social group, age, race and ethnicity, gender, religion, nationality and displacement status. / Following popular protests and a political crisis triggered by the Arab Spring, Yemen is emerging from a period of unprecedented economic contraction, widespread insecurity and conflict, all of which have exacerbated already alarming rates of poverty and vulnerability. Though the situation is improving, it is still extremely fragile. To help lift poor households out of poverty, the World Bank estimates that the government would need to allocate at least four per cent of its GDP to help fill the gap between the actual spending of poor households and the poverty line.[5] Yet, social spending in 2012 accounted for just 1.9 per cent of GDP and only 0.65 per cent of GDP was allocated to the Social Welfare Fund in 2011.[6] / Yemen’s existing public social protection system consists of programmes that provide income assistance, training, small and micro-credit, public works and community-driven operations. It also includes contributory social security and pensions for public and private employees. There are several government agencies and departments tasked with delivering social protection. The most prominent include the Social Welfare Fund (SWF) and the Public Works Programme (PWP). The Social Fund for Development (SFD) operates as a quasi-governmental organisation, receiving regular funding and loans from the Government of Yemen and from a variety of donors whilst maintaining autonomy and financial control. This is in contrast to the SWF and PWP who work under the oversight and control of the GoY. SFD’s Board of Directors is chaired by the Prime Minister and is comprised of a number of government ministers along with private sector and NGOs representatives. SFD, SWF and PWP are the only Yemeni organisations (in or outside Government) which provide services for poor people across the whole country. / The international donor community increasingly recognises social protection as an appropriate short- and long-term response to poverty and vulnerability in Yemen. The GoY’s ability to provide social security for the poor is ineffective and in much need of reform. In order to achieve these necessary reforms, the GoY needs to address the issue of unsustainable fuel subsidies (currently 37% of the budget) which largely benefits better-off Yemenis and to increase their expenditure on state welfare, currently 0.6% (below the average for other developing countries). / The Transitional Programme for Stability and Development 2012-2014 (TPSD) and the Mutual Accountability Framework (MAF) – against which donors pledged £8 billion of support at the Riyadh Donor Conference in September 2012 - identify support for social protection as a key priority. Donors and multi-lateral agencies have provided support for social protection institutions in Yemen, such as the Social Welfare Fund (SWF) and the Social Fund for Development (SFD), and have increased support for cash transfers, public works programmes and other interventions to protect poor people from both transitory shocks and chronic poverty.
[1] World Development Indicators, 2005.
[2] World Bank, Yemen Overview. Last updated September 2012.
[3] http://www.ifpri.org/sites/default/files/publications/ghi13.pdf
[4] WFP, Comprehensive Food Security Strategy, 2012.
[5] Government of Yemen, The World Bank, and the UN Development Program, “Yemen Poverty Assessment.” November 2007.
[6] Data from Ministry of Finance, Government of Yemen and the World Bank, “Joint Social and Economic Assessment for the Republic of Yemen.” 2012

## Section A: Detailed Output Scoring
All results represent 14% of SFD’s core fund results in 2013. 14% has been applied as this is the estimated DFID share of the programme’s overall core funding.
We recognise that the actual percentage share fluctuates depending on currency rates and other donor contributions.

Output 1: Basic services improved
Output 1 score and performance description: A (Outputs met expectation) / The Community and Local Development Programme (CLD) implements community-based projects in a range of sectors including education, health, water and sanitation, agriculture and rural roads and provides capacity building to local authorities implementing development projects. At 63 per cent, the CLD Programme represents the largest share of the total planned budget for Phase IV. / SFD has met the majority, but not all, of the milestones for 2013 in the CLD programme and, in some cases, exceeded them. The sole exception to this is for rural road construction. / Indicator Cumulative target for this review [7] Cumulative achievements [8] Cumulative achievements attributable to DFID[9] / Number of classrooms constructed or rehabilitated 4,600 5,260 Total 736 Total / Number of pupils benefitting from SFD-supported schools Total: 184,000 / Boys: 103,040 / Girls: 80,960 / Children with special needs: 2,750 Total: 236,700[10] / Boys: 120,980 / Girls: 115,720 / Children with special needs: / 4,335 Total: 33,138 / Boys: 16,937 / Girls: 16,201 / Children with special needs: / 607 / Number of teachers trained Total: 120 / Male: 60 / Female: 60 Total: 1,645 / Male: 201 / Female: 1,444 Total:230 / Male:87 / Female:202 / Number of other educational professionals trained Total: 828 / Male: 468 / Female: 360 Total: 1,009 / Male: 620 / Female: 389 Total:141 / Male: 87 / Female: 54 / Number of health facilities constructed or rehabilitated or equipped 60 108 15 / Number of health professionals trained (sex disaggregated) Total: 1,800 / Male: 900 / Female: 900 Total: 3,445 / Male: 1067 / Female: 2387 Total: 482 / Male:149 / Female:334 / Number of households provided with new/improved drinking water sources 28,800 68,097 9,534 / Volume of improved drinking water stored in facilities (m3) 660,000 1,445,302 202,342 / Number of households provided with new/improved sanitation facilities 15,600 23,134 3,239 / Total km of rural roads built or upgraded 1,095 619 87
Progress against expected results: / Education / SFD has made good overall progress towards its output targets in education, often exceeding them substantially. This can partially be explained by additional earmarked funding from other donors for example, a contribution from the European Union which specifically targeted girls’ education and teacher training. During 2013, projects that were developed in the education sector amounted to an estimated cost of $69.3 million, 88% percent of which were for expanding and improving school infrastructure. During the year, 277 schools were completed and handed over to the Ministry of Education, at a total cost of $54 million. In addition to building 1,481 new classrooms, SFD projects renovated 1,022 classrooms, a much higher number than anticipated because of the need to renovate classrooms damaged during the instability in 2011. SFD reported a continuing strong demand from communities for school infrastructure projects with a pipeline of 295 projects that are ready for implementation but awaiting funding. Lack of sanitation facilities can be an important factor in discouraging girls from attending school. / Health / During the period 2011-2013, SFD built and equipped 108 health facilities in the targeted governorates according to the criteria and standard design set by the Ministry of Public Health & Population (MOPHP). According to SFD, most of these were existing facilities which required support to improve and expand their services. Additionally, there are several facilities (though SFD did not provide a breakdown) that were only provided with equipment. In addition, 3,445 health care service providers were trained, of which 1,456 community midwives (CMWs) received training on community-based maternal and newborn healthcare, and 1,454 physicians, medical assistants and nurses received training on the Integrated Management of Child Health. Some of these health service providers are employed by the Ministry of Health (though this not an SFD requirement) while others provide services privately or work with private health service providers; detailed statistics are not available. / Further SFD investment in building new health facilities is being scaled down substantially at the request of the Ministry of Public Health and Population. This is because of low utilization rates of existing health facilities due to the absence of qualified staff, lack of essential medicines and insufficient operating budgets. Each health facility supported requires signing agreements with the local health authorities to provide operation costs, staff and supervision. / Water and Environment / All of the indicators in the water and environment sector are now substantially ahead of the project targets for 2013. SFD attributes this performance to: community contribution (caused by a higher demand for rooftop water harvesting tanks where the contribution of communities reach 70%); increased attention to the water sector; the events of 2010-2011; donor preferences and an increase in water trucking. We agree with the view expressed in the JDR Aide-Memoire that attention should now turn to improving the sustainability and impact of project interventions through greater efforts to extend the life span and improve the level of service provided by the water and sanitation facilities and services supported by the SFD. / School sanitation however continues to be a challenge, primarily due to insufficient budgets for operation and maintenance. In 2014, the SFD will undertake a pilot project to develop sustainable operation and maintenance systems for existing WASH facilities in 20 schools with the intention of using the findings to develop approaches and tools that can be incorporated into larger-scale programmes in future. Longer-term sustainability will be dependent on budget allocations by local authorities for operation and maintenance, supported by greater involvement and commitment from all stakeholders. In particular, advocacy is required to convince government decision-makers of the importance of these small budget allocations in order to avoid jeopardising the substantial investments already made in the construction of these facilities. / Roads / During Phase IV, 619 km of rural road have been constructed generating 708,000 days’ work and giving 236,435 people better access to the nearest villages or markets. The shortfall in meeting the target is mainly because of slightly slower progress than expected with 38 projects which are very close to completion but which cannot be included here. That said, SFD report that if these projects had been completed they would have reached 75% of the target i.e. 831 km out of 1095 km. Progress in this sector has also been affected by communities demanding other types of projects.[11] / Recommendations: / Education: As discussed at the November JDR and recorded in the Aide Memoire, while all SFD-supported schools are operational, maintenance problems occur after they have been handed over to the Ministry of Education. Although many of the issues are outside of SFD’s direct control, SFD should take additional measures at the design and implementation stage to mitigate these problems. This applies in particular to maintenance of buildings and equipment, and especially the prevalent issues of non-functioning water supply and/or badly maintained or unusable toilets. More attention might be given to the design of water supply and toilet facilities to reduce maintenance issues. / Health: We agree with the Aide-Memoire recommendation that SFD co-ordinate with MOPHP and Local Authorities to enhance performance and ensure ownership, and we will discuss the issue with SFD in order to fully understand challenges and how we can support them. We will monitor this issue through the regular reviews as well as our forthcoming independent monitoring programme. We will also raise this when appropriate in any bilateral contacts with MOPHP. / Water and Environment / Monitoring of the water sector program could be improved through greater attention to the sustainability of project facilities, services and benefits. SFD undertakes a first check once work is complete but has not typically done follow-up visits: they will start to do this in 2014. / Coordination with the other programme units that implement WASH projects or related interventions could also be improved in order to maximise lesson learning and efficient use of limited resources. / Impact Weighting (%): 70 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[7] This represents the total cumulative target since the start of Phase IV, January 2011 through to December 2013.
[8] These figures represent total cumulative results since the start of Phase IV, January 2011 through to December 2013.
[9] DFID attribution rate is calculated as 14% of the overall achievements
[10] Number of students is calculated based on the classroom capacity which is an average of 45 students per classroom
[11] SFD’s CLD Programme operates on a ‘demand-driven’ basis giving local communities an opportunity to decide what interventions they think would be most beneficial to them.

Output 2: Economic opportunities created
Output 2 score and performance description: A (Output met expectation) / The Small and Micro Enterprise Development (SMED) programme aims to strengthen and build the capacity of local microfinance providers and actively promote their entry into the market by creating an enabling environment and encouraging the establishment of new financial service providers. The SMED Programme represents 3 per cent of the total planned Phase IV budget. / Indicator Cumulative Target [12] Cumulative achievements [13] Cumulative achievements attributable to DFID[14] / Number of active borrowers 80,000 60% female 20% rural 94,966 / 59%N/A 13,295 / Total value of outstanding loans (Million YR) No target set 8,451 1183 / Percentage of active borrowers served by microfinance providers that are financially sustainable 50% 63% / All MFIs have less than 5% Portfolio at Risk (PAR) <5% < 4% / Credit bureau legislation / regulation submitted to the government to support positive enabling environment for microfinance Credit bureau legislation / regulation submitted to govt / Code of conduct regarding consumer protection adopted by Yemen Microfinance Network Regulations for credit bureaus has been developed and circulated to MFIs / Final draft agreed and being applied by MFIs
Progress against expected results: / SMED has exceeded its 2003 target reaching 94,966 clients, close to the final end of Phase IV target of 100,000 clients. / 2013 saw intense financing activity by SMED comprising of loans for on-lending, grants for capacity building and grants for business development services (notably the Small and Micro Enterprises Promotion Services - SMEPS). From January through December, 16 projects were implemented amounting to almost USD 7 million. SMED also hired a legal advisor to help the Central Bank of Yemen (CBY) to rewrite the regulations of Mobile Banking to ensure that they are in line with other banking laws. 2013 also saw the establishment of the second microfinance bank in Yemen, Injaz Capital, and SFD, SMED and Injaz are working together to establish a long-term partnership. / The Code of Conduct has been agreed and SMED visits to some of the MFIs confirmed that notices of the CoC are already on display. / A notable achievement is that in September 2013, the Council of Ministers approved the National Micro, Small and Medium Sized Enterprise Development Strategy 2011-2021 which the Ministry of Industry and Trade had been drafting since 2010 in cooperation with SFD and GIZ. / Recommendations: / Internally, DFID will ensure that there are strong linkages between SFD’s work in this area and other parts of the DFID Yemen programme. Coherence with the Wealth Creation pillar’s work, which also supports SMED and SMEPS through the IFC, including results reporting is crucial. DFID will also need to consider the benefits of providing support through both pillars separately as part of the planning of possible support to SFD Phase V. / DFID will also maintain close communication with SMEPS over the evaluation of the impact of the Ultra Poor Graduation Pilot Project in Yemen.[15] / DFID should clarify with SFD the issues around the indicator of rural active borrowers as the explanation provided for non-reporting is not sufficient. / Impact Weighting (%): 5 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[12] This represents the total cumulative target since the start of Phase IV, January 2011 through to December 2013.
[13] These figures represent total cumulative results since the start of Phase IV, January 2011 through to December 2013.
[14] DFID attribution rate is calculated as 14% of the overall achievements-
[15] DFID are providing Innovations for Poverty Action (IPA) with £140,000 to carry out a survey to evaluate the impact of a pilot project to help some of the poorest households in Yemen move out of extreme poverty via micro-finance interventions. At SMEPS’ initiative, Yemen was included as one of several pilot countries in the project undertaken by Ford Foundation and CGAP. The findings will be critical in helping to determine whether this model is effective in Yemen and will help to improve the quality and effectiveness of future poverty alleviation projects in Yemen.

Output 3: Reduced vulnerability for the poor
Output 3 score and performance description: A Outputs met expectations / The Labour-Intensive Public Works Programme (LIWP) was originally established in 2008 to provide short-term, temporary employment (4-6 months) on community asset construction projects to poor rural households facing food insecurity as a result of the global food crisis. In SFD Phase IV, the plan was to provide longer-term, multi-annual support (3-5 years) in order to build greater productive capacity in poor households (as opposed to addressing short-term household consumption needs). However, the 2011 crisis resulted in a significant increase in unemployment and food insecurity and, in response, SFD decided to scale-up the short-term LIWP and postpone implementation of the longer-term LIWP. This enabled SFD to meet the increased demand for cash for work though it also meant that individual households received less cash overall. The LIWP represents 20 per cent of the total planned Phase IV budget. / A score of A has been given due to SFD’s mixed progress against the milestones in the logframe. The number of people directly benefiting from workfare assistance has exceeded the target by a considerable margin as has the number of households benefiting from community livelihood assets. However, the target for total number of days of work created under the workfare assistance programme has not been met. On balance, the number of people benefiting from workfare assistance and number of households benefiting from community livelihood assets have contributed to reducing the vulnerability of the poor in Yemen under difficult circumstances. / SFD plans to resume longer-term LIWP in 2014. / Indicator Cumulative Target [16] Cumulative achievements [17] Cumulative achievements attributable to DFID[18] / Number of people directly benefitting from workfare assistance 300,000 422,550 59,157 / Number of days’ employment created under workfare assistance programme 12,000,000 7,215,612 1,010,186 / Number of households benefitting from community livelihood assets 180,000 507,060 709,88 / Total area of rehabilitated terraces and agricultural land (hectares) No target set 2,878 403 / Number of community projects (by type) No target set None reported / Average length of payment delay (Number of days) 3-5 days 3-5 days
Progress against expected results: / The programme has made good progress both in terms of employment creation and improvement in its operation, including moving forward with developing an operational manual and Information Management System (MIS). To date, 7.2 million employment days have been created under this program (target: 12 m). The number of people directly benefiting from multi-year workfare assistance has reached 422,550 (against target: 300,000) and total area of agricultural land and terraces rehabilitated have reached 2,878. The average monthly disbursement amount for LIWP during the past six months has been around US$4 million of which about 75% has been paid as wages. / Concerns raised at the last annual review that the design of SFD’s short term LIWP was likely to exclude poorer households and also that women who may face physical or social barriers to employment opportunities. In response to the first issue, SFD have reduced the wage rate further to ensure the self-targeting mechanism was working effectively. And they are looking as a priority at creating subprojects that allow for increased female participation. / SFD have articulated their vision of the LIWP which includes a focus on building beneficiaries’ capacity to enhance their employability, contributing to the reduction the impact of the 2011 crisis on poor households and communities and focusing on increasing agricultural productive assets. It is important for SFD and donors to consider whether these objectives are best being met by the LIWP sub-components. / Recommendations: / SFD have finalized their LIWP operational manual and have submitted it to the SFD Policy Committee for approval. The manual is intended to guide staff and stakeholders on the operation of the LWIP. SFD recognise the LIWP manual will be a live document. DFID will share it with in-house LIW specialists and review it in advance of the next joint donor review (likely to be scheduled in May). / DFID will discuss with SFD their overall approach to implementing both short and longer-term (multi-year) public works starting in the coming year including resource allocation, targeting, and objectives / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[16] This represents thetotal cumulative target since the start of Phase IV, January 2011 through to December 2013.
[17] These figures represent total cumulative results since the start of Phase IV, January 2011 through December 2013.
[18] DFID attribution rate is calculated as 14% of the overall achievements

Output 4: Stakeholders capable and empowered
Output 4 score and performance description: B (Output moderately did not meet expectation) / The Capacity Building Programme contributes to SFD’s three other programmes by building the capacity of local entities, including local and central government bodies, NGOs, and community-level groups and committees, who deliver services to poor people and communities. It also strengthens SFD’s own institutional capacity such as support for monitoring and evaluation and programme management. The Capacity Building Programme represents 14 per cent of the total planned Phase IV budget but is the most underfunded programme of SFD’s four, with only 33 per cent of its planned budget covered by donor pledges. / SFD has exceeded the target for the number of village councils that are functioning effectively and the number of private sector individuals trained. However, to fully assess the extent to which stakeholders are capable and empowered, it is necessary to gather more data on the capacity of village councils to implement development programmes independently of SFD’s support. Furthermore, it is moderately not meeting expectations for the number of young volunteers, local authorities and government organisations trained. The score of B reflects this overall assessment. / Indicator Cumulative Target [19] Cumulative achievements [20] Cumulative achievements attributable to DFID[21] / Number of village councils in pilot areas which are functioning effectively[22] 900 2,486 348 / Number of people and organisations trained in M&E, participatory methods, planning or other strategic information management Young volunteers - 1,500 male - 900 female / Government Orgs: 25 / NGOs & coops: 50 / Local Coms: 1,500 / Local authorities: 54 / Priv. sector/indiv: 600 Young volunteers / - 475 male - 485 female Government Orgs: 9 NGOs & coops: 36 Local Coms: 1059 Local authorities: 20 Priv. sector/indiv: 3,917 Young volunteers - 67 male - 68 female / Government Orgs: 1 NGOs & coops: / Local Coms: 148 / Local authorities: 3 Priv. sector/indiv: / 548
Progress against expected results: / As of December 2013, 2,486 village councils in pilot areas are reported to be functioning effectively representing very impressive progress (an increase of over 330 village councils since last year when 2,153 village councils were reported to be functioning effectively). SFD have attributed this performance to an acceleration of its Empowerment of Local Development Programme (ELD) activities during the previous year in 10 districts. These have included community mobilisation and an increase in the provision of training. However it would be helpful to explore in more detail the capacity of the village councils considered to be functioning effectively and how many have progressed beyond the first of the three stages[23] of the Empowerment of Local Development Programme (ELD) plan. / SFD is keen to build on the successes of this increased capacity with ambitious plans to implement developmental activities through NGOs in addition to building their capacities, continue support to the Ministry of Local Administration (MOLA) in its decentralization efforts, and invest part of SFD resources through the Local Authorities (LAs) to implement subprojects and supervise them jointly with MOLA. / Recommendations: / There are no specific recommendations other than the amendments to logframe (mentioned below). / Impact Weighting (%): 5 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[19] This represents the total cumulative target since the start of Phase IV, January 2011 through December 2013.
[20] These figures represent total cumulative results since the start of Phase IV, January 2011 through December 2013.
[21] DFID attribution rate is calculated as 14% of the overall achievements
[22] Defined as those that meet regularly, include broad participation from community members (sex-disaggregated), and execute self-help initiatives.
[23] In the first stage, SFD implements basic services and subprojects; in the second stage, Local Authorities (LAs) and SFD jointly implement subprojects that may serve more than one village; and, in the third stage, LAs implement and manage subprojects, leaving SFD to supervise and monitor the overall activities.

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No / SFD uses the World Bank's Results Framework (RF) as its logframe and in January 2010 all donors, including DFID, agreed to do the same. The Results Framework was reviewed at both the Mid-Term Review meeting in June 2013 and Joint Donor Review mission in November 2013 after which it was updated to ensure that indicators, milestones and targets were still relevant and achievable and accurately reflect the wide range of activities carried out by SFD. Further improvements to the RF will be made with the support of an M&E expert who has started at SFD this month. As our own logframe is a subset of SFD’s, we have started amending accordingly and within the next 3 months we will be making a submission setting out these changes. Once approved, the revised logframe will be the basis for future reporting. / 1.2 Overall Output Score and Description: A (met objectives) / 1.3 Direct feedback from beneficiaries / Due to the challenging security situation in Yemen it has not been possible for DFID staff to collect direct feedback from beneficiaries to verify the information SFD provided in its narrative reports and evaluations. To allow for this in future we are establishing an independent monitoring programme to provide independent verification of our programmes in the field, and to collect a range of information from beneficiaries and the wider population. This is due to begin in 2014 and we anticipate incorporating findings from it in the next and future annual reviews. SFD colleagues welcomed the prospect of independent monitoring of their projects and were positive about the benefits that this could provide for them as well as donors.
1.4 Summary of overall progress / SFD’s work has been particularly important during the transition period by delivering jobs and basic services to people across Yemen. SFD remains one of the few Yemeni development partners who are able to work across the country, in all of Yemen’s 333 districts. The National Unity Government of Yemen has also underscored the critical role of institutions such as the SFD in its Transitional Programme for Stabilisation and Development (TPSD) and has encouraged donors to channel recently pledged funds through SFD. SFD has continued to make strong progress this year with many output indicators exceeding their target values for 2013. / A key milestone was passed with the appointment in August of Mr Abdullah Ali Al-Dailami as the permanent Managing Director of SFD. Mr Al-Dailami had been the acting managing director since the resignation of the previous SFD head (and Deputy Prime Minister) in April 2011 following the start of the Arab Spring. Mr Al-Dailami was selected following an open and transparent competition conducted in line with official SFD procedures. His official appointment marks the end of a period of uncertainty surrounding the leadership of SFD and the process for selecting a new Managing Director. Mr Al-Dailami is highly respected by SFD staff and donors for his personal integrity, pragmatism and commitment to the SFD vision and DFID warmly welcomes his appointment. / 1.5 Key challenges / Phase IV funding gap / The biggest challenge to delivery of SFD’s full Phase IV programme is a shortfall in donor funding. The financing gap for Phase IV stood at $371 million as of December 2013 (with a potential further $100m from the Arab Fund in the pipeline). Should Phase IV not be fully funded SFD will be unlikely to achieve the full planned results. The results attributable to DFID are based on a percentage share of the overall programme determined by our funding (14%, based on the full phase IV budget). We will also continue to encourage Gulf partners to fund SFD. / Security situation in Yemen / As mentioned above, due to the challenging security situation in Yemen it has not been possible for DFID staff to directly assess SFD’s performance against the information provided. DFID maintains regular contact with SFD to track project progress, assess the impact of the political situation, and discuss ways to strengthen delivery of results. It is also moving ahead in establishing an independent monitoring system for the entire Yemen programme. The latter was welcomed by SFD colleagues who were positive about the benefits that this could provide for them as well as donors. / The political and security situation in Yemen continues to be fragile and with an on-going risk of outbreaks of violent conflict and or widespread political unrest. Either of the latter could substantially disrupt SFD’s ability to implement projects. / Reporting outcomes and impact / SFD has a comprehensive information management system and is able to generate an enormous amount of information quickly and easily, for example on number of projects commissioned and their value, total beneficiaries disaggregated by sex, and geographic coverage. However, reporting against targets beyond activity and output level remains weak, particularly with regards to activities such as training and workshops. SFD and its donors should continue to explore ways to measure transformation, behaviour change and broader changes in well-being in communities benefitting from SFD support. / The timeliness of reporting also needs to be significantly improved. For the November Joint Donor Review, the Progress Report was circulated on the last day of the prior working week which did not allow sufficient time for analysis to inform discussion. Progress Reports need to be submitted at least 1 working week in advance to provide maximum value. DFID raised this with SFD who assured us that timeliness would be improved for future reviews. / Maintaining Autonomy / During the review mission, the critical importance of SFD maintaining autonomy was emphasised. The adherence to due process during the recruitment of the new Managing Director was a notable success but SFD needs to resist future attempts from the GoY to steer them in unhelpful directions. Donors, including DFID, should not be exempted since the donor community has been known to press SFD to take up interventions which are not always aligned with SFD core business. DFID will remain in close contact with SFD on this issue and has offered to raise this with relevant line ministries if/when it would be helpful. At the same time, we will want to ensure SFD continues to operate in alignment with our own objectives for supporting them. / Annual Outcome Assessment / As noted above, based on its performance and in light of the considerable security and political challenges, SFD has made very good overall progress during the review period. The programme has created 13.8 million working days to date and the number of direct beneficiaries has reached 3.6 million (2 million female and 1.6 million male). / SFD is already considering the future directions of the programme - in particular the format of the next, fifth, phase - and will take into account the need to align with national development strategies/plans and priorities, to build on its comparative advantages and strengths, and to reflect lessons learned. SFD will be setting out the timetable for the design of the next, fifth phase, and consulting stakeholders over the content, during 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The total cost of the project is $1.126 billion of which DFID has committed £100 million over five years, estimated at $155 million. As of mid-November 2013 SFD had received commitments worth approximately $762 million to fund SFD Phase IV activities including $101 million that is committed, but not yet transferred, by the Government of Yemen. The financing gap for Phase IV stood at $371 million as of December 2013. We understand that the Arab Fund is likely to commit a further $100m shortly. / As of 31 December 2013, DFID has disbursed £59.8 million. We are on track to disburse our committed £100 million by December 2015. Due to an increased rate of project implementation, funds have been brought forward. This means that on current plans DFID will make its final disbursement to SFD, ahead of schedule, in 2014/15. / 2.2 Key cost drivers / Increasing inflation due to the political crisis of 2011, and the resulting increase in the cost of commodities, such as building materials and fuel, increased the overall unit cost of some SFD project activities. However, to keep its unit costs low, SFD has been continuously modifying the standard design of its infrastructure projects in order to come up with low cost designs. Its procurement process follows transparent and competitive bidding in order to achieve maximum value for money. Additional measures include cutting unnecessary administrative procedures and speeding up the transfer of the contractors and suppliers payment requests. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / National data being collected / New data from 3 important national statistical exercises will be crucial in helping SFD to update its geographical targeting, although these are unlikely to have an impact before 2015 at the earliest. These are the National Demographic and Health Survey (data entry scheduled to be completed in January 2014); the Household Budget Survey (activities due to be completed in December 2014) and the Census which is scheduled for Dec 2014 and will produce data in 2015.The World Bank has worked closely with consultants at the Central Statistical Office (CSO) in Sana’a to finalise the HBS questionnaire including designing a module on social protection/assistance. / Service Deprivation index / As mentioned in Section 1.4, SFD has taken various steps since the Mid-Term Review to respond to the 2012 Targeting Review (Oxford Policy Management), in particular revisiting the means by which it allocates resources geographically. The “Service Deprivation Index” is being remodelled so as to ensure that viable indices for both urban and rural areas may be produced from the new census data. The World Bank and DFID will collaborate with SFD’s Monitoring and Evaluation unit to refine this index. / Independent Monitoring / As soon as DFID Yemen’s independent monitoring programme has been established DFID will determine which elements of SFD we wish to monitor. / Where an evaluation is planned what progress has been made? / During the joint donor review mission in November, donors were clear on their preference for a sectoral approach to evaluation as opposed to repeating a full Impact Evaluation on the entirety of Phase IV. This would include the following: / An education evaluation study for enrolment indicators – reporting end 2015 (though SFD need to agree with donors whether to measure the enrollment rate – which requires a household survey - or just measuring the utilisation of services which could be captured from an education facility survey) / A water evaluation reporting in 2013 and 2015 / For rural roads, SFD proposed to capture the time to market annually from the project survey / SFD has hired a consultant who will help revise the M&E manual. DFID has also shared an example of best practice with regard to an evaluation strategy from another programme to support this process. DFID will provide individual level input and technical assistance as requested by SFD, such as reviewing and commenting on questionnaires, other tools, and the evaluation methodology. Concrete steps on how DFID can work with SFD to strengthen their in-house capacity for regular monitoring and evaluation will include revised guidance and templates for narrative and financial reporting to DFID as well as ways in which SFD can improve data analysis. / The International Labour Organisation and UN Economic and Social Commission for Western Asia are currently undertaking a study on SFD’s Labour Intensive Public Works programmes in Hajjah and Taiz. Results are expected in early 2014 and will be shared with DFID.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Given the political transition and challenging economic and security situation in Yemen, the risk to our programme portfolio remains high. However, SFD has a good track record for delivery and has demonstrated that is it able to continue to work in some of the most challenging environments in Yemen despite a number of operating challenges. Identified risks related to SFD are deemed to be manageable.
Risk of funds not being used as intended / At the outset of the project, DFID assessed the fiduciary risk to be of low probability but high impact. The team has implemented a number of internal risk management and mitigation measures to ensure that our funds are used for their intended purposes. This will be supported by the Independent Monitoring programme (see section 1.3) in addition to DFID’s internal Anti-Corruption and Counter Fraud Strategy that sets out key action points to help identify and reduce risks related to our investment in SFD IV. / USAID “Pre-Award Assessment” of SFD / In March 2013 USAID undertook a pre-award assessment of SFD and have subsequently shared the assessment with DFID. The overall risk level for SFD was judged to be low and SFD assessed as capable of providing adequate oversight for US Government funds. The only area identified as high risk was SFD’s lack of an indirect cost recovery (ICR) mechanism and the potential negative impacts this might have for SFD’s long term financial sustainability. This did not however present a risk in terms of diversion of funds. In response to this concern, DFID has encouraged SFD to meet with other DFID partners in Yemen who have expertise in this area. Initial discussions took place with Save the Children in December, and we will be following this up in the coming weeks. / Areas judged of medium risk were procurement concerns about conflicts of interest. SFD is working towards addressing these concerns, by ensuring the procurement process follows Tender Law on declaring conflicts of interest and by drafting an HR manual. Now that DFID is aware of these risks, we will consider how to monitor SFD’s performance in these areas. We understand USAID’s assessment to be quite rigorous and this gives us further strong assurance about SFD’s capacities. / Financial Management / SFD have stringent internal accounting systems and conduct regular external audits. The financial management procedures used are transparent and verifiable and are designed to ensure cost effectiveness and good value for money of SFD operations. The Finance and Administration Unit uses a Financial Manual which sets out organisational structure, disbursement and payment procedures, and job descriptions. A chart of accounts has also been developed specifying the different codes per category of project expenditures. These Manuals have been approved by the Board and donors as effective financial management tools. / SFD has a qualified Internal Audit Department (IAD) led by the Internal Audit Manager, who reports directly to the SFD’s Managing Director. The department is responsible for conducting regular audits for the branches, departments, and units within SFD. The internal auditor follows up on any actions agreed upon with the concerned branches, departments or units. It also coordinates and cooperates with the external auditors. / The World Bank assessed SFD’s financial management procedures during the November review mission and it was concluded that SFD continues to maintain satisfactory financial management arrangements. / Complaint Handling Mechanism (CHM) / SFD is in the process of migrating from a manual, paper-based complaints handling system to an integrated Complaint Handling Mechanism (CHM) which will allow faster complaint resolution and better tracking, monitoring and analyses of complaints. SFD is currently developing and testing a CHM system that will allow simultaneous entry from all 9 branch offices; tracking of complaints; notifications; inter-departmental collaboration; analysis and report-generation. This improved system is expected to enable SFD to manage, respond to and monitor complaints better within its programmes. The new system will also provide real-time feedback to SFD management which will allow them to make mid-course corrections to existing policies and processes. / Well designed and implemented CHMs can enhance operational efficiency by generating public awareness about project activities; providing staff with practical suggestions/feedback that allows them to be more accountable, transparent and responsive to beneficiaries; deterring fraud and corruption; increasing involvement of stakeholders in project activities; and catching problems before they become more serious and/or widespread. An effective CHM that encompasses all program activities under the Social Fund for Development will help the project team reap the above benefits. Information on complaint resolution rates will be included in future Annual Reports and complaints related to fraud and corruption will be categorised as high priority. / SFD Leadership / Due process in the appointment of a new Managing Director was critical for maintaining donor confidence in fiduciary management. Mr Abdullah Ali Al-Dailami, previous acting director of the SFD, was appointed on 21 August 2013 following a rigorous recruitment process. Mr Al-Dailami is clear on the importance of SFD maintaining autonomy from Government ministries. / 4.4 Climate and Environment Risk / SFD Phase IV is likely to have important environmental impacts and benefits. However, the typically small scale of SFD projects is likely to limit any environmental impacts to the locality within which they are implemented. Examples of the likely impacts will be those associated with terrace rehabilitation, reduction in soil erosion, enhancing groundwater recharge, increasing vegetation cover, and reducing siltation in wadis and downstream water structures, as in the case of dams. For urban projects providing stone pavement the positive impacts may include reducing dust and subsequently air pollution, but there may be negative impacts related to the reduction of reducing groundwater recharge. In this case, to mitigate against the lack of ground water recharge, percolation pits are installed. / All project activities are undertaken in accordance with SFD’s Environmental Management Plan (EMP) which has been agreed with all participating donor agencies. At project level the EMP provides guidance on analysing and managing environmental impacts (positive and negative). In some cases an Environmental Impact Assessment is carried out in accordance with Yemeni law. At the time of writing this review, the report of the 2013 annual audit was not available. The Executive Summary of the Environmental Audit 2012 found that the majority of SFD’s projects had a limited negative environmental impact and identified mitigation measures that could be used to overcome these impacts. SFD has held a workshop to discuss the results of the 2012 Environmental Audit with project officers across all sectors and has distributed the findings to branch offices. / Conflict over environmental resources, particularly land and water, are commonplace throughout Yemen. SFD have long practised inclusive and participatory approaches to project identification and design. They have a good track record of conflict mitigation at local levels. This programme will build on this experience and ensure that any potential conflicts resulting from infrastructure interventions are minimised.

5. Value for Money
5.1 Performance on VfM measures / SFD has delivered value for money since the outset of its phase IV programme. We have assessed this using financial data generated by SFD compared to financial forecasts, unit cost analysis, and cost benefit analysis drawing on the original economic appraisal. / The SFD progress report included a unit cost analysis for water supply sub-projects. This analysis confirmed that a number of factors have led to a significant rise in the project cost per capita for rural water supply schemes: ranging from USD 80 per capita in surface water schemes (dam reservoirs) to USD 129 per capita in covered cistern schemes. However, these changes were explained by SFD analysis, noting that significant cost increases were associated with the lower community contribution agreed in 2010; the higher technical specification introduced in 2008 in order to comply with the government’s requirement that all improved water supply systems provide a minimum of 30 litres per capita per day; and continuing inflation in the price of building materials. Fortunately, the increased funds made available for water and environment sub-projects (through the establishment of the water fund and the provision of earmarked grants by KFW and EKN) have counter-balanced the higher scheme costs, allowing greater progress in the water supply sub-sector despite the higher costs and larger development challenges faced recently. / During the review mission in November, donors requested that future progress reports include tracking of unit costs and cost effectiveness for all sectors, with any changes and associated reasons highlighted. / Finally, we also reviewed the original economic appraisal and can compare the cost benefit analysis value for money measures. The economic appraisal focused on the roads, water, education, and labour intensive works components of the SFD project, as the major areas of DFID support. The table below sets out the original estimates of net discounted benefits, alongside the expected output values upon which these estimates were based. The actual output values (children with access to school, km of road built etc.) are drawn from the logframe results set out above. As can be seen from the table below, all targets were exceeded except for kilometres of road built, which underachieved by nearly 50%, while water overachieved by over 100%. We can therefore expect the original estimate of over £90 million of net benefit for the project to remain approximately the same – although the figure may be slightly higher or lower due to discounting. Nevertheless, based on the cost benefit analysis, we can assess that the project has delivered value for money with significant net benefits. / Children with access to school Kilometres of road built Cubic metres of water storage People benefiting from labour intensive works / Estimate 102,000 1,095 660,000 300,000 / Actual 116,000 574 1,200,000 333,000 / Net benefit estimate £m 0 41 43 7 / 5.2 Commercial Improvement and Value for Money / SFD uses established benchmarks to determine costs of suppliers. Procurement specialists are responsible for ensuring cost controls are in place and that consultants are delivering the required level and quality of services contracted. The World Bank is currently revising a Procurement Plan which governs the projects that they contribute funding to. SFD have agreed to share the latest draft with DFID as soon as it is finalised so that we can assess whether it would be beneficial to extend this to UK funded projects. / 5.3 Role of project partners / SFD are responsible for project delivery. Field offices are responsible for recruiting local technical experts or consultants to assist with the implementation of project activities, however all aspects of procurement and project management are managed by SFD field staff. / 5.4 Does the project still represent Value for Money : Yes

6. Conditionality
6.1 Update on specific conditions / There are no conditions attached to this project aside from DFID funds not being used for projects under the Cultural Heritage component of the CLD programme.

7. Conclusions and actions
As of 31 December 2013, DFID has provided £59.8 million to SFD Phase IV to improve access to basic services, enhance economic opportunities and reduce vulnerability for the poor. / Following understandable implementation challenges faced during the political crisis which came close to civil war during the first two years of the programme, SFD’s key programmes have been expanding in terms of fund allocation, types of activities, intervention areas, and target beneficiaries. SFD now handles a multitude of different activities and interventions through a variety of approaches in each sector and across sectors. SFD needs to continuously review and ensure coherence between different approaches and address any issues of duplication or inconsistency (for example, LIW water interventions are fully subsidized while water sector interventions require a high percentage of beneficiary contribution). It also needs to seek out potential efficiency gains through organizational restructuring (for example, terrace rehabilitation is now carried out by the Agriculture and Rural Development and LIW Units; ECD and children with special needs fall under Health and kindergarten under Education). / The appointment of the new Managing Director makes this the right time for SFD to look at all its programs to see where efficiency can be increased through streamlining and at the same time to focus resources on the areas where the evidence of sustainable benefits is strong and SFD has comparative advantage. / Based on this performance, this project scored an A at output level (outputs met expectations). DFID recommends the following action points and will work closely with SFD and other donors to help implement them. / SFD and its donors should consider how better to measure transformation, behaviour change and broader changes in well-being in communities benefitting from SFD support. DFID will seek to work with SFD to establish a clearer line of sight between its activities and the impact on the poor. / DFID will closely monitor SFD’s progress on timeliness of reporting and will also engage with key partners to apply concerted effort towards SFD. / DFID will seek to include, as and where possible, inputs from other advisors within DFID—particularly education, governance and wealth creation advisors—in the consideration of SFD’s fifth phase. We will ensure that multidisciplinary inputs are linked up to those of other donors. / In light of the significant over-achievement of some targets, DFID should discuss with SFD any challenges it faces in planning and forecasting, identify any sustainability issues that may arise (e.g. changes in unit costs or absorption capacity) and agree mitigating measures. / DFID will continue to provide support to SFD to determine feasible means of improving its sustainability. As discussed above, this includes support to the development of an indirect cost recovery system. / DFID will continue to engage with SFD on the targeting work, in particular the revised method for geographic targeting. We will also closely follow the work of the M&E consultant

8. Review Process
This Annual Review was completed by the DFID Yemen Deputy Programme Manager and Social Development Adviser (SDA) as a combined desk-based and field review. The data for the review is based largely on narrative and financial reports provided by SFD as well as data and reports provided during the joint-donor reviews held in June and November 2013. Further supplementary emails containing information on progress were also reviewed. / In addition, discussions were held with key SFD staff including the Managing Director and Donor Relations Manager.