Type of Review: Annual Review

Project Title: DFID – Africa Development Bank Technical Cooperation Arrangement

Date started:	Sept 2007 Date review undertaken: Oct 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The DFID - African Development Bank (AfDB) Technical Cooperation Arrangement (TCA) provides up to £13 million to the AfDB from 2007-2014.[1] The TCA supports the AfDB to improve its organisational effectiveness through the provision of training, technical assistance, capacity building and institutional support. The TCA focuses support on sectors and themes prioritised as strategically important by the AfDB and African member countries. The TCA therefore channels support to infrastructure and regional integration; private sector development; governance; institutional capacity; and climate change adaption and clean energy.
[1] The original project timeframe was from 2007-2012 but in 2011 it was given a no-cost extension to 2014.

What are the expected results?

The AfDB is a critical actor in the development of Africa – both at the continental level and within regional member countries (RMCs). By supporting the AfDB to implement capacity building reforms, the TCA is expected to contribute to poverty reduction in Africa by strengthening the effectiveness of the AfDB, including the African Development Fund (ADF), enabling it to fulfil its role as a regional driver of African economic growth and development. / The results expected from the programme are: / Impact level (Poverty Reduction in Africa) / To contribute to the reduction in the number of people in Sub Saharan Africa living on less than $1.25 PPP. Achieving a reduction from 57.9% in 1999 to 42% in 2015. / Outcome level (AfDB is a more effective, results orientated and responsive development institution) / To increase the percentage of AfDB partners and donors who rate the AfDB’s overall internal effectiveness as ‘very effective’. / To improve AfDB partners’ and donors’ rating of the AfDB’s corporate focus on results from the category ‘Adequate’ to ‘Strong’. / To increase the percentage of AfDB country strategies that are approved with explicit baseline data, monitoring indicators, and clearly defined outcomes to be reached, from 19% to 78%.

What is the context in which UK support is provided?
The AfDB is critical to Africa’s future. It is uniquely positioned to achieve its mission of stimulating economic growth and social progress within its RMCs. As the continent’s leading development financing organisation, the AfDB is well positioned to coordinate cross-border investments into sectors of strategic priority – these include developing the private sector, building infrastructure and achieving regional integration. In addition, the AfDB’s African nature and ownership provides it with unparalleled legitimacy from which to encourage and assist RMCs to consider cross-cutting issues relating to economic and financial governance, gender, climate change and organisational management. / However, a number of key reports including DFID’s Multilateral Aid Review (MAR) in March 2011, have identified that while the AfDB did, on the whole, achieve its objectives, its delivery of strategic priorities was limited by deficiencies in some areas of technical expertise and human resource management. The 2013 MAR update identified that the AfDB continued to represent good value for money for UK Aid and that reasonable progress had been made in areas of identified weakness, including results management and tackling climate change. The update did note further scope though for improvement on gender issues, enhancing effectiveness in fragile states and costs and value consciousness. / The TCA provides a mechanism through which DFID can provide strategic support to ongoing AfDB reforms by directing capacity building reforms that help AfDB address identified weaknesses and deliver its key priorities.

## Section A: Detailed Output Scoring

Output 1: Enhanced Capacity of AfDB to deliver high quality and high priority infrastructure investment
Output 1 score and performance description: / Output score: C (Outputs substantially did not meet expectations) / During the year under review, substantive activities under this output have ceased. This reflects the completion of earlier activities and the approaching end of the TCA project. No further proposals have been developed, owing to concerns about completing these before project completion in light of the slow implementation of earlier activities under this component. / Relevant activities have been undertaken though linked to the Private Sector Development focus of output 5. These include: / Development of a model for assessing the bankability of power projects. This model and related material directly financed by the project will be used to inform project evaluation and TA for public sector energy projects with a view to unlocking private investment in energy sector with public sector interventions; / Private sector capacity development activities have explored public private partnerships in the power sector, including how to deploy innovative financial instruments such as partial risk guarantees; and / Support in project design of budget support and institutional support projects (ISPs) in Cape Verde, Mozambique and the Democratic Republic of Congo, focusing on supporting private investment and financing in the infrastructure sector. These examples have largely been prompted by participation of the project team in Country Strategy Paper (CSP) activities. / As detailed in the 2012 annual review, this output and indicators are not an appropriate measure of this component’s performance. The logframe has not been amended though given the forthcoming end of the programme, winding up of activities across the programme and ongoing evaluation.
Progress against expected results: / Indicator 1.1. The value of national infrastructure investment approvals (millions of Units of Account or UA where the value of 1 UA is approximately equivalent to US$1.50) / Expected Results (Milestone 2013): 2900 million of Units of Account / Actual Results: 1764 million of Units of Account / This figure has been extracted from the AfDB’s 2012 Annual Report. This decline, compared to the previous year (UA 2037 million), reflects an overall decrease in AfDB approvals which is attributed to a number of Bank member countries reaching their prudent borrowing limits and a number of ADF countries having frontloaded resources and exhausted allocations. / Indicator 1.2. Regional infrastructure investment approvals (UA millions) / Expected Results (Milestone 2013): 525 million Units of Account / Actual Results: In 2012, the total amount approved for multinational operations was UA 956.2 million, of which 27.2% was for energy and 26% for transport (totalling UA 508.7 million). This is slightly below the expected result, but represents an increase on 2011 (470 million UA). / Indicator 1.3. Time lapse between approval and 1st disbursement (months) for infrastructure projects / Expected Results (Milestone 2013): 13.5 months / Actual Results: The 2012 Annual Portfolio Assessment Report shows that the average time lapse between approval and first disbursement for all projects was 17 months. This is significantly longer than the expected results, but does represent a sustained improvement over the past 5 years from 23 months in 2008. For projects achieving an initial ‘satisfactory’ appraisal rating the time lapse was much shorter, averaging 14 months, nearer to the Bank’s long term target of 12 months. / Recommendations: The Transport and Information and Communication Technology department should ensure that any future capacity development proposals (developed outside of the TCA arrangement) build on more detailed assessment of internal capacity needs required to deliver their core strategic objectives. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Improved AfDB capacity to define and pursue its governance agenda effectively
Output 2 score and performance description: / Output score: A (Output met expectations). / Most activities under the Governance component have been completed during the year under review. The key activities undertaken through this component in the past 12 months related to the African Governance Outlook (AGO) and the Review of the AfDB’s Governance Strategic Direction and Action Plan (GAP) 2008-12. / In respect of the AGO, the pilot phase across ten countries was successfully completed. Much work has been done to build partnerships and capacity in each of the pilot countries. In addition, the pilot provided substantial learning in the application of the AGO methodology, as a financial governance diagnostic tool, as well as providing analysis of emerging trends in financial governance in Africa. A consolidated publication, entitled the ‘Preliminary Findings of the AGO Pilot Phase’ was produced and disseminated at AfDB’s Annual Meetings. Substantive implementation of the AGO will now take place outside of the TCA. / The Review of the GAP was also completed. This concluded that, at the country level, the Bank’s performance under the GAP had been very strong, with a total of 79 operations approved during the 2008-2011 period, and indicators showing an improvement in public financial management country systems. The Bank also stepped up its operations in fragile states. At the sector level, the review indicated that the GAP’s objective of mainstreaming governance had been partially met. However, the review also noted that the Bank remained committed to mainstreaming governance across sectors and has produced studies and guidance notes on governance in several infrastructure sectors. / Lessons learned from the implementation of GAP have been used to inform the development of a new Governance Strategic Framework and Action Plan 2014-2018 (GAP II). The Bank’s governance work will increasingly focus on supporting the economic transformation of the continent to ensure more inclusive growth and its transition to green growth. Indicative areas for Bank support include: deepening public financial management reforms; creating the environment and incentives for private sector development; facilitating partnerships between the state and citizens to hold government to account; addressing governance issue in sectors, e.g. infrastructure, education and health; scaling up interventions on extractives industries so that revenues from natural resources benefit current and future generations; and contributing to the global governance agenda, especially money laundering, and reducing illegal financial flows. The Bank will also continue to build on its partnerships with other development partners and African organizations which promote good governance in Africa. The development of GAP II represents an increase in the scope of the Bank’s governance ambition in areas that align well with DFID’s priorities. GAPII also reflects well on the lessons learned from GAP in terms of the Bank’s internal approaches to implementation and in particular the need to be clear around roles, responsibilities and integration with the Bank’s broader results management framework. / At regional level, the Bank has also engaged through the TCA in a significant number of Africa-wide initiatives to advance the governance agenda. This has included financing one regional operation (payment systems) and supporting Regional Economic Communities in their efforts to harmonize economic and financial management aspects (for example in tax policy).
Progress against expected results: / Indicator 2.1. AfDB partners’ and donors’ ratings of AfDB strategic focus on good governance / Expected Results (Milestone 2012): ‘Adequate’ rating / Actual Results: Not obtainable / For the 2009 Multilateral Organisation Performance Assessment Network (MOPAN) report (published in Feb 2010), survey respondents were asked to rate the Bank’s mainstreaming efforts in three thematic areas, namely good governance, environmental protection and gender equality. In the final 2012 MOPAN survey respondents were asked about six thematic areas, not including governance. This means that for the period under review, this is no longer a relevant indicator of Bank strategic focus on good governance. / Indicator 2.2. AfDB strategy to support good economic governance in Africa is clear and being implemented effectively / Expected Results (Milestone 2013): Governance Action Plan II approved / Actual Results: As at the time of the review the Bank’s Governance Action Plan II (GAPII) had been drafted and was with wider stakeholders for consultation. It is expected that GAPII will be finalised and approved in November 2013 in line with the milestone. / Recommendations: / The AfDB should ensure that the lessons from the GAP are fully reflected in GAPII finalisation, in particular through development of clear performance indicators linked to implementation of the strategy across the AfDB. This will help to ensure appropriate incentives for implementation at the sectoral level. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Enhanced capability to support climate change adaption and exploitation of low carbon growth opportunities
Output 3 score and performance description: / Output Score: A (Output met expectation) / As the 2013 MAR Update noted, since 2011 the Bank has made real progress under its climate change workstream, in particular with the finalisation of a Climate Change Action Plan (CCAP) which includes more clearly defined objectives and is supported by increased capacity within the AfDB. A recent progress report on implementation of the CCAP in its two years of operation supports this assessment – it identifies significant progress but concludes that continued concerted effort is required, in particular to build the evidence of the impact that new approaches are having at the country level. This lack of evidence at this stage is to be expected given the new approach is still in its early stages of implementation. / As with other components of the TCA, activities are being concluded ahead of completion of the TCA project. During the year under review, work has been completed to finalise the monitoring and evaluation framework for the CCAP and training has been rolled out across the organisation as well as regional and country offices. An integrated training programme to raise awareness of climate change among senior executives has also been undertaken, with a particular focus on adaptation, mitigation and financing. The evaluation of these training opportunities has been extremely positive, although it is too early to assess the results of increased understanding in terms of sustained achievement of organisational objectives. / Activities were also continued to build on the mapping of member country Nationally Appropriate Mitigation Actions (NAMAs) and develop a guidebook on these to support member countries to better understand concepts and support development of NAMAs. The guidebook has been widely distributed to RMCS as well as to the Africa Group of Negotiators (AGNs). To date, nine RMCs have been assisted by the Bank to develop their NAMA frameworks and to submit these to the United Nations Framework Convention on Climate Change (UNFCCC) registry. / Overall the TCA inputs have begun to support some radical repositioning of the Bank both in terms of methods/tools and senior-management recognition of the importance of these. These have not yet translated though into full realisation of the ambitious targets that the Bank has set itself in this area, although project-specific indicators appear on track.
Indicator 3.1. Percentage of new projects classified as climate sensitive which become climate proofed / Expected Results (Milestone 2013): none / This indicator is aligned with AfDB Corporate targets under the Climate Change Action Plan (2011 to 2015). The latest target was for 75% of the portfolio to be climate proofed by 2012. / This climate proofing is being conducted through the Climate Safeguards System (CSS). This is a set of decision-making tools and guides developed by the Global Climate Adaptation Partnership (consultants) and the Bank to screen projects for climate change related risks and to identify appropriate adaptation measures to reduce project vulnerability. Both the CCAP and CSS were developed with TCA support. / To facilitate the mainstreaming process at the country programming level, in 2012 the Bank developed a Guidance Document for Mainstreaming Climate Change in the Bank’s Country Strategy Papers and Regional Integration Strategy Papers (RISPs). Use of the guidance document is expected to enable country/regional teams to design improved climate-resilient strategies that lead to more sustainable investments. During the pilot period of 2011–2012, climate change was mainstreamed into the strategy papers of 16 countries. For an extended pilot period in 2013, the guidance document will be applied in the preparation of CSPs for an additional five countries / Actual Results: 65% (2012 data published in 2013 Annual Development Effectiveness Review). This is slightly behind the Bank’s own ambitious targets, but represents significant effort and progress towards implementing the new approach. / Indicator 3.2. Percentage of energy investment that is clean energy / Expected Results (Milestone 2012): increased by 40% / The AfDB now has a developed Energy Sector Strategy (awaiting approval) to help set and deliver clean energy targets. The ambition for this indicator (if not the specific milestone) will be enshrined as a target to increase the lending volume for clean energy from its baseline (which has not yet been specified). / Actual Results: / From 1995 to 2010, the Bank provided around $2.7 billion in public financing for clean energy – which equates to an average annual spend of $169 million. Between 2011 and 2013, the Bank expects to invest an additional $4.6 billion in improving energy access, with 85% going to clean energy. In 2012 the AfDB approved UA890 million in new loans and grants for energy supply, up from UA420 million in 2011. This equates to just over $2 billion. This shows that although investment is scaling up, significant further progress is required to meet the Bank’s expectations for the 2011-13 period, including testing assumptions about the percentage of approvals which would be clean energy. It does suggest though the bank has exceeded a 40% annual increase against baseline expenditure on clean energy before the project commenced. / Recommendations: Considerable progress is now being made under this component, and logframe indicators, but not all of the AfDB’s own climate change targets have yet been clearly specified or met. The AfDB should continue to reflect on whether this is because of the speed of ambition, capability at implementation levels, the nature and types of instrument, or broader commitment, and consider what is the appropriate response. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 4: Improved AfDB human resources and procurement capacity
Output 4 score and performance description: / Output score: B (Output moderately did not meet expectation) / TCA-funded projects within the Institutional Strengthening component have continued to meet senior management demand for support for capacity building reforms in human resource management, procurement and fiduciary safeguards. The 2013 MAR Update identified the progress that the AfDB has made against specific areas of institutional weakness set out in the original 2011 review. In particular it acknowledged improved systems for measuring the Bank’s contribution to results. It also highlighted the improved cost-effectiveness of project management and swifter project delivery, reflecting efforts in recent years (with support through the TCA) to improve both the speed and quality of its procurement. In practice however, the speed of procurement and other administrative procedures is an area that requires on-going attention, ensuring an appropriate balance with management of fiduciary risk. / There has also been progress in the area of human resource management, as evidenced by the reduction in the staff vacancy rate from 15% in 2011 to 11.7% in 2012. Decentralisation is also moving ahead, with an increase to 36% of operations professional staff based in field offices in 2012 (up from 29% in 2011) and 42% of projects tasked managed from field offices (up from 25%). / The MAR update did identify, however, that progress on strengthening the gender focus as part of the results agenda had not been as expected. Although there is some evidence that gender is being considered in programme planning and results are being disaggregated by gender, a revised gender framework and action plan has been delayed by over two years.
Progress against expected results: / Indicator 4.1. Perceptions of the AfDB’s donors and partners of its effectiveness in managing human resources / Expected Results (Milestone 2012): AfDB rated as ‘adequate’ by survey respondents of the MOPAN 2012. / Actual Results: Adequate / There was a positive trend in stakeholders’ perceptions of the Bank’s human resource management practice. This was rated inadequate in 2009 and adequate in 2012. Survey respondents particularly noted the Bank’s efforts to instil a culture that is transparent and meritocratic. According to the 2012 MOPAN report, procurement and contract management processes and risk management were also considered adequate by stakeholders. / Indicator 4.2. Gender Balance Index (percentage of professional staff that are female) / Expected Results (Milestone 2012): 30% / Actual Results: The share of female staff among professional staff in 2012 was 27%, a decline of 1% from the previous year. / Indicator 4.3. Time elapsed from approval to first disbursement (months) / Expected Results (Milestone 2013): 11 months / Actual Results: 12 months for ADF countries. This represents a slight improvement on the 2009 baseline (13 months) but the milestone has not been met. / Recommendations: The Bank should continue to explore the reasons for continued delay between approval and disbursement and reassure itself that it is taking sufficient and appropriate steps for boosting female representation among professional staff. Any capacity support required to deliver this should be sourced through alternative institutional capacity development resources once the TCA has been concluded. / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 5: Infrastructure, social sector and governance operations contribute to development of dynamic competitive private sectors
Output 5 score and performance description: / Output score: A (Output met expectations) / Activities under this component have represented a significant proportion of overall activities through the TCA during the past 12 months. / The Private Sector Development (PSD) component of the TCA was launched in February 2012 and was originally anticipated to run for 2 years to March 2014. Activities have contributed to the approval in 2013 of a PSD Policy and Strategy which now recognises PSD as a Bank wide priority to which all Bank operations, across sectors, can contribute. As evidenced in the 2013 Annual Development Effectiveness Review, the Bank now places private sector development at the core of its mandate. TCA activities continue to help enhance the PSD capacity of the Bank throughout its operations department beyond the Private Sector Department (OPSM). / At the level of strategies, the TCA has directly contributed to mainstream private sector development into 23 country strategies, out of which 11 have been approved by the Board since project inception. In terms of specific activities, the TCA contribution to Country Strategy Paper (CSP) missions has delivered 11 PSD clinics at which about 80 Bank staff participated. The project has also supported the development of 15 PSD-related Economic and Sector Work approaches (ESWs) by providing inputs during project preparation (e.g. Private Sector profile and opportunities in the Centre Region of the Democratic Republic of Congon). / The TCA has also contributed to mainstreaming PSD at the strategic level, through the development of guidance notes on how better to factor private sector development and operations into country strategies; the paper will be submitted to stakeholders by the end of 2013. At the level of tools, the project has initiated 8 short term assignments (out of 10 planned for the whole project) aimed at developing tools and delivering training on specific topics (Technical Advisory Services). Three have been completed (African Development Finance Institutions, Large Liquefied Natural Gas projects, strengthening off-takers in the power sector). Four are on-going (enhancing value chain competitiveness, fostering PSD through budgetary support, PSD in fragile states, Public Private Partnership in the health sector) and one is about to be launched (Development Outcomes and financial sector development). / In terms of capacity development, the project has produced a capacity development plan, based on extensive consultations, that was approved in January 2013 - implementation is ongoing. The Bank assesses that there is now a critical mass of field and Tunis-based professionals benefitting from coaching/training who are able to design strategies and operations supporting PS and/or enable PS solutions: 250 professionals have received PSD capacity building and 80 have participated in CSP clinics or PSD days. / This component was expected to conclude in March 2014 (at the same time as the rest of the project). The AfDB have now advised that a short no-cost extension will be required in order to complete activities. This will be considered in further detail by both the AfDB and DFID.
Progress against expected results: / Indicator 5.1. Share of public and private operations having private sector development (PSD) impact / Expected Results (Milestone 2013): none (the 2012 original baseline was <10%). The baseline has been reframed. As part of the preparation of the PSD strategy, the Bank conducted a rapid assessment of the operations approved over the past 5 years and their contribution to PSD objectives and PSD impacts. This assessment revealed that over 70% of the Bank’s operations (in terms of financing volume) were targeting one of the 3 PSD pillars of the Strategy. / Actual Results: There has been no reassessment of the percentage of operations having PSD impact since the re-assessment linked to development of the 2013 PSD Strategy. / It will be important to assess the impact of the PSD Strategy in driving an increase in projects with PSD impact. Capturing new sector operations mainstreaming PSD will, however, be challenging. Owing to the sector operations cycle, operations that are identified during the preparation of the CSP will materialise (as a Board approved transaction) up to 18 after the CSP is approved. / Recommendations: / The AfDB should ensure that its new organisational mechanisms for strengthening PSD impact are working effectively, including the PSD Steering Committee. It should also review where PSD skills should be located within the organisation to avoid the risk of this reverting to an OPSM lead. The Bank should also continue to track the effectiveness of its new approaches, including through periodic review of the percentage of its portfolio delivering against PSD objectives. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No. The previous annual review included some recommendations for indicators to be amended. However, since the programme is in its final year with many activities now concluded, and is also going through further evaluation, it was felt that adjusting indicators at such a late stage would not provide sufficient new information to track progress. Design of any future AfDB capacity support interventions (by DFID or others) should draw on the recommendations of the evaluation to ensure they are supported by a robust results framework. / 1.2 Overall Output Score and Description: B (Outputs moderately did not meet expectation) / 1.3 Direct feedback from beneficiaries / No direct feedback from beneficiaries has been obtained for the purpose of this Annual Review. It is expected that the forthcoming Evaluation of the TCA (due end 2013) will include and reflect direct feedback from beneficiaries.
1.4 Summary of overall progress / Overall progress remains uneven across outputs, but the pace of implementation of approved activities has picked up slightly across all components. As at the end September 2013, the total disbursement rate stood at 81% for approved activities, compared with 65% a year before. / Certain components are delivering as expected. Output 2 on the capacity of the AfDB to develop and pursue its governance agenda has progressed well in 2012/13, with a largely positive assessment of GAP implementation and the development of a more ambitious GAPII which draws on the lessons learned from GAPI, including the need for development of clear organisational indicators to ensure take up across the organisation and not just at a country level. / The climate change component (output 3) has also made significant progress during the year and is now achieving expected project results, having failed to meet these at the time of the previous review. This positive movement is identified in the MAR update, although further concerted effort is required to build on this momentum and track actual outcomes from newly implemented approaches and procedures. / The pace of delivery under the Private Sector Development component (Output 5) has also increased. During the past 12 months the TCA has supported successful finalisation and approval of a PSD strategy and translation of this into a number of Country Strategy Papers. It has also supported extensive training and sensitisation across the organisation to this new approach and required skills development. Further focus is required, however, to ensure that the Bank has the right structures and incentives for building on what has been achieved to date as well as measuring impact. / Other components have not progressed as expected. For example, work has continued on the institutional strengthening component (output 4), with broadly positive progress in terms of procurement practice and human resource strengthening, particularly as it relates to decentralisation. This progress has not, however, matched the ambitious targets set out by the AfDB. / In order to ensure that the activities can be completed before March 2014, there has also been a reduction in the number of proposals developed in the past 12 months – which has in part contributed to the increased disbursement rate. This has been particularly the case for the Infrastructure component (output 1) where activities had been slow to implement and were not clearly contributing to achievement of desired results. No remaining funding is allocated to activities under this component and the Bank has not achieved its targets in this area. / Overall, remaining approved activities are on track to be completed before the expected project end date for all components with the exception of the more recent Private Sector Development component. The AfDB have made an initial request for this to be extended, which will be considered further by DFID. / The programme will shortly be evaluated. This should now be the key focus of the project, alongside completion of remaining activities. Given the flexible and somewhat disparate nature of activities under the TCA, the evaluation will be critical for establishing the overall results achieved through the TCA and for making recommendations on how the AfDB can strengthen its organisational approach to and management of capacity development.
1.5 Key challenges / The key programme challenges remain: / a) Slow implementation of TCA-funded projects. As a result of slow implementation, the number of new activities developed during the year under review has been reduced to ensure that only those which could be implemented in full before March 2014 were considered. / b) Relevance and prioritisation of proposals. Not all proposals have been sufficiently clear about their alignment to TCA/AfDB priorities or had clear results, indicators or timelines. The AfDB has gone some way to address this, but the approach could be further strengthened through clearer internal mechanisms for prioritising among proposals building on latest AfDB strategy and internal capacity assessments. / c) Administrative Requirements. The design of the TCA as a standalone fund has placed a considerable administrative burden on AfDB and DFID staff in terms of generating proposals, overseeing implementation and ensuring value for money. This experience should be reflected on during the evaluation to help inform future approaches to the design of capacity development mechanisms. / d) Tracking performance. The flexible nature of the TCA has complicated the measurement of results. This flexibility has meant that output indicators have focussed on levels of change which are outside the scope of the TCA rather than the outputs of discrete activities. Again, the forthcoming evaluation should provide recommendations on how to best manage this tension to ensure useful and proportionate monitoring and results management.
1.6 Annual Outcome Assessment / The intended Outcome of the TCA is that “the AfDB is a more effective, results orientated and responsive development institution.” / The Outcome Indicators are: / % of AfDB partners and donors rating the AfDB’s overall internal effectiveness as ‘very effective’: There was no specific milestone for 2013. The milestone for 2012 was an increase in the percentage of donors and partners who perceive AfDB internal effectiveness to be very effective from 24% in 2009 to 27% in 2012 (as assessed through the periodic MOPAN review). Unlike the 2009 MOPAN survey which scored the AfDB using a 1-5 scale with 5 representing the category ‘very effective’, the 2012 survey used a 1-6 scale, with 6 representing ‘very strong’. Due to this inconsistent scaling, it is difficult for ARD to be explicit in assessing if there has been an improvement on the 2009 result and whether the 2012 milestone has been achieved. / However, the 2012 MOPAN Survey results did show that, on average, 30% of stakeholders perceive the AfDB to be either ‘strong’ (category 5) or ‘very strong’ (category 6) in its organisational effectiveness. On average, 10% of stakeholders perceive AfDB to be ‘very strong’ (category 6). / AfDB partners’ and donors’ ratings of the AfDB’s corporate focus on results: There was no specific milestone for 2013. Within the period since the last MOPAN report (2009) the partners’ and donors’ rating of the AfDB corporate focus on results was expected to have increased from ‘adequate’ to ‘strong’. According to the 2012 MOPAN survey, the AfDB continues to receive an overall rating of ‘adequate’ from these key stakeholder groups (albeit with an increase in the raw score from 3.4 in 2009 to 4.24 in 2012). This improvement is also noted by the 2013 MAR update which acknowledged the continued progress that the Bank is making in terms of results management across the organisation. / % of AfDB country strategies approved with explicit baseline data, monitoring indicators, and clearly defined outcomes to be reached: Within this reporting period the number of AfDB country strategies approved meeting this criteria was expected to increase from 72% to 75%. At the time of the review no updated data on the extent of progress against this indicator was available (as at 2010 this reported figure was 58%).

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / Over 90% of the total TCA budget has been allocated to projects, but there has been slower and lower than anticipated disbursement of funds for certain projects once they have been approved. Both the AfDB and DFID are monitoring budget performance closely and will adjust the total budget and final project disbursements accordingly. / 2.2 Key cost drivers / AfDB staff manage project funds in accordance with AfDB procedures and policy guidelines, including direct procurement of goods and services (including consultancy services) and indirect implementation through grant agreements with recipients. / Key cost drivers include the procurement of technical advice and training. These have been sourced within the budget as reflected in the cash flows of the financial reports. AfDB obtains competitive quotations during its procurement processes to ensure this. / 2.3 Is the project on-track against original timescale: No / The TCA was originally a five year programme from 2007 to 2012. Achievement of TCA results has been challenged by slower than expected implementation of TCA-funded projects, largely due to the time taken to procure support and competing demands for Task Managers. / Following the joint DFID-AfDB Annual Review in March 2011 it was decided that the TCA would support an additional two year project designed to enhance the AfDB’s Private Sector Development Strategy. A no-cost extension to 31 March 2014 was originally agreed to allow this new component to complete. This component is progressing well (see output 5 above), but is unlikely to be fully completed within the new timeframe. The AfDB have therefore made an initial request for this one component to be extended (at no additional cost) beyond March 2014 for consideration by DFID. A decision will be made based on provision of further information on the activities still required to be completed and the timing for this.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / As explored in the 2012 annual review, at the time of design or the TCA, it was assumed that it would help make the AfDB strategic, capable and responsive in delivering pro-poor investments in Africa. The purpose of the TCA was to sustainably enhance AfDB’s capacity to formulate policy and deliver programmes. The TCA programme was intended to contribute to achievement of the MDGs in a range of ways; some components directly (e.g. water) and some indirectly by improving quality of AfDB operations (e.g. institutional strengthening). / In practice, TCA-projects are approved on the agreed understanding that they will not only result in satisfactory outputs but also contribute to the achievement of the higher level outcome: AfDB is a more effective, results orientated and responsive development institution and towards the realisation of impact: poverty reduction in Africa – shorthand for an implicit Theory of Change. However, the programme was designed and approved before Business Cases, including a Theory of Change, was made mandatory. / Given the lack of evidence for the implicit Theory of Change for the TCA, it has been agreed that an Evaluation of the TCA would enable AfDB and DFID to: / Test critical assumptions that the TA provided through the TCA helps AfDB to become a more effective, results orientated and responsive development institution; and / Monitor and evaluate the performance of the TCA as a whole i.e. gather evidence that the TCA is contributing to the reduction of poverty in Africa and demonstrating, for public accountability purposes, that the TCA has used funds effectively and efficiently to deliver results. / 3.2 Where an evaluation is planned what progress has been made? / An independent evaluation of the TCA was commenced in late 2012. DFID (ARD in consultation with IFID) and the AfDB (ORRU in consultation with OPEV, the Bank’s Evaluation Department) jointly developed the Terms of Reference. AfDB (agreed with DFID) considered that the quality of initial outputs from the evaluation were not of the required quality. The contract for the evaluation was therefore terminated. Another independent evaluation is currently being procured by the AfDB, drawing on revised terms of reference, including an enhanced role for quality assurance. This evaluation should be completed in late 2013 with findings contributing to the Project Completion Review.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The overall risk level is unchanged. The key risks remain: / AfDB’s Partnership & Coordination Unit’s ability to effectively coordinate TCA components with their technical colleagues; / DFID and AfDB’s ability to ensure that, beyond effective management, the TCA achieves results; / AfDB’s guidance and control systems remain robust; and / AfDB component leads have the incentive and capacity to deliver quality, timely and cost effective plans that are aligned to their institutional capacity requirements. / The AfDB has continued to strengthen its oversight, including financial management, of TCA proposals and implementation. Since agreements reached at the March 2011 annual review, each approved activity has more clearly identified and tracked the results associated with it. Given that proposals are developed by the various thematic leads within the organisation, it has proved more difficult though to track the overall effectiveness of the TCA across all components. There has not been a systematic way for quality assuring proposals to ensure alignment and relative prioritisation with AfDB strategy nor a robust results management framework for the AfDB capacity development as a whole. This will be explored in more detail through the evaluation and will help to inform future AfDB approaches to capacity development.
Risk of funds not being used as intended / The Bank is rated by all of the four major rating agencies (Standard & Poor, Moody’s, Fitch Ratings and the Japan Credit Rating Agency – all four have regular update reports on the Bank on their websites) to have sound financial management processes in place. The rating agencies’ positive assessment reflects the Bank’s strong financial position (based on sound capital adequacy) and prudent financial and risk management policies. This, together with a positive assessment on its financial systems by the MOPAN 2012, provides external evidence of the Bank’s financial structures, systems and processes. / In particular, the Bank is considered by external reviewers to have good audit procedures. The 2012 MOPAN reported the AfDB as strong in the areas of internal auditing, organisation-wide external audit and its anti-corruption policy. The MOPAN reviewers were less confident about audits at country and project level due to the AfDB using local country auditors, however this does not apply to the TCA given the nature of the project and procurement of activities. / 4.4 Climate and Environment Risk / The TCA focuses on institutional capacity building, particularly through technical assistance, targeted consultancy support, and strategy and systems reform. Direct adverse significant environmental issues will not result from this support. Where appropriate, possible technical assistance programmes will utilise environmentally-friendly communications options, such as video conferencing, over extensive travel. / However, some risks potentially arise during policy implementation in some of the target sectors, most notably infrastructure and private sector development. These risks are manageable through the AfDB environmental safeguard procedure. In addition, a central component of the TCA is to support the AfDB to mainstream climate considerations and climate proofing in the development and approval of its projects. As noted in this annual review, the TCA has begun to support some radical repositioning of the Bank both in terms of climate change tools and senior-management recognition of the importance of these.

5. Value for Money
5.1 Performance on VfM measures / This programme was developed before the requirement for a Business Case. There was therefore no specific baseline assessment of VfM or establishment of VfM indicators. The planned evaluation is expected to explore economy, efficiency and effectiveness throughout TCA implementation. / 5.2 Commercial Improvement and Value for Money / Overall the 2013 MAR continued to rank the African Development Fund as representing good value for money for UK aid. As part of this, the MAR noted the strong consideration that the Bank gives to value for money through its own systems. The Bank has also taken strong steps to keep administrative budget and salary increases under control. / Most of the activities under the TCA are implemented through procurement of consultancy services on a competitive basis using the Bank’s procurement systems. As identified by the MAR, the Bank has effective procurements systems with transparent publication of data. The Bank has also introduced (with TCA support) a number of measures to improve both the speed and quality of its procurement processes in recent years. / 5.3 Role of project partners / The TCA is implemented solely by the AfDB. / 5.4 Does the project still represent Value for Money : Yes / Whilst there are concerns over the length of time taken to implement proposals, including slow disbursement rates, the Bank has an appropriate range of mechanisms for ensuring economy and efficiency at both the approval and implementation stage. The nature of the project, in its flexible delivery of capacity development support, has complicated results measurement (as acknowledged in this report) and therefore the measurement of the overall effectiveness of the project. This will be explored in more detail through evaluation. / Economy: The Bank uses its own effective procurement services to source consultants. It reviews the remuneration of consultants and fixes thresholds according to experience to ensure that the Bank receives value from its suppliers. / Efficiency: The primary responsibility for ensuring efficiency falls to individual Task Managers when developing proposals and determining the scale of input required. Proposals are reviewed by the Fund Manager in the Partnerships and Cooperation Unit (ORRU), prior to submission for approval. The Fund Manager also oversees the progress of each activity and urges Task Managers to improve the performance when necessary. / Effectiveness: The TCA is a Trust Fund specifically for the capacity development of the Bank itself. It has greatly contributed to developing sector policies and strategies, improving corporate services systems, and streamlining some of the key issues such as Governance, Climate Change and Private Sector Development into the Bank’s regular operations. Effectiveness beyond the level of individual activities will be explored through evaluation. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / No conditions have been applied.

7. Conclusions and actions
The progress of the TCA at the Output level is uneven: progress under the infrastructure component has largely ceased, but activities under the climate change and private sector development components have begun to deliver well, creating a strong base for continued progress beyond completion of the TCA project. / The key actions required between now and project end will be (i) delivery of a robust evaluation, which provides more detailed evidence of TCA overall effectiveness and clear recommendations for the AfDB on how to strengthen its approach to organisational capacity development, and (ii) successful completion of remaining activities, including further consideration by the AfDB and DFID on the appropriate timing for completion of output 5. This information will be used to inform the timing and amount of final disbursements under the project.

8. Review Process
This was a desk based review completed by ARD on the basis of information provided by the AfDB. The main sources of information used in the review were the 2012 AfDB Annual Report; the AfDB’s 2013 Annual Development Effectiveness Review; and the 2012 MOPAN Organisational Effectiveness Performance Assessment Report. The review was shared with the AfDB for comment and additional evidence prior to finalisation.