Type of Review: Annual Review

Project Title: Improved Public Financial Management and Accountability

Date started: 02 March 2012	Date review undertaken: October 2013

## Introduction and Context

What support is the UK providing?
Under the project Improved Public Financial Management and Accountability, the UK, through DFID, is providing support to public financial management (PFM) reform at the sub-national and sectoral level as well as to as greater accountability of the national government in Nepal. The project includes two components: / 1. Co-financing of the Asian Development Bank (ADB) managed Strengthening Public Management Programme (SPMP). DFID has committed £2.6 million to the grant component of the programme and £1.6 million to the technical assistance component of the programme. The SPMP has been designed to strengthen PFM reform at the local level, as well as selected accountability institutions at the national level. / 2. Provision of technical assistance to PFM reform at the sector level as well as support to DFID with assessments of fiduciary risks across sectors and at the national level. DFID has contracted Crown Agents to implement this component with a value of £1.8million. / The project started in September 2012 and is planned to end August 2016, but as both components have started with considerable delay this first Annual Review was deferred to November 2013.

What are the expected results?
The ADB SPMP has been designed to strengthen Public Financial Management (PFM) Reform at the local level, as well as selected accountability institutions at the national level in Nepal. In its design the SPMP is directly complementary to the Local Governance and Community Development Programme Phase II (LGCDP II), to which DFID is planning to contribute £70 million. The programme is designed to reduce fiduciary risks for donor funds using Government of Nepal’s systems. It is as such also complementary to the World Bank led PFM Multi-Donor Trust Fund which focusses its support at central level. Specifically the SPMP will support the following components: / (1) local government budget and fiscal management, including support in the areas of fiscal transfers, resource mobilisation, medium-term budget framework; (2) fiduciary risk management at the local government level, including design and implementation of PFM and fiduciary risk mitigation action plans, as well as risk assessment guidelines and tools, complemented by a local level Public Expenditure and Financial Accountability (PEFA) Assessment and Public Expenditure Tracking Surveys (PETS); (3) public procurement reform, with support to E-Bidding and the Public Procurement Management Office; and (4) oversight and accountability capacity building, with support to the National Vigilance Centre (NVC). / The component strengthening sector PFM reform, implemented by Crown Agents, is designed to support DFID sector programmes and help develop and improve sectoral PFM reform plans, support the implementation of such strategies or stand-alone PFM reform activities, all based on thorough diagnostic work and fiduciary risk assessments. / The four headline results of the Improved Public Financial Management and Accountability project are: / A reduction by £6m (20%) in disallowed government expenditures, as measured by external audits (based on current exchange rates and figures in the 49th Report of the Nepal Office of Auditor General 2012). / A 40% increase of own-source revenues of a pilot municipality using the ‘Municipal Administration and Revenue System’ (MARS). / Improved scope, nature and follow up of internal and external audit of local bodies. / Completion of 24 Fiduciary Risk Assessments (FRA) and Annual Statement of Progress (ASP). / The programme will also contribute to the following DFID Nepal Operational Plan Headline Result: Percentage of formal community organisations (District Development Committees and Village Development Committees) that hold Government to account through social audits from 78% in 2009 to 93% by 2015.

What is the context in which UK support is provided?
After decade of civil war ended in 2007, Nepal continues to experience political instability and its people to be afflicted by severe poverty. Nepal is the 16th poorest country in the world ranked by average national income. While the first elections for a Constituent Assembly were held in 2008 and Nepal was declared a Federal Democratic Republic, the Constituent Assembly was dissolved in 2012 due to the inability to finalise the Constitution. Nepal has been without elected Government and without Constitution since. National elections are planned for November 2013. / This deep and on-going political crisis in Nepal has also affected the abilities and capabilities of the public sector, including PFM. Various and repeated PFM assessments at national, sector and local level all point to weak PFM systems and high fiduciary risk, including: weak oversight and scrutiny, badly functioning budget process, problematic implementation of capital spending, gaps in financial reporting, inadequate staffing and capacity. Fiduciary risks and PFM deficiencies tend to be even more evident at the local and sector levels due to even weaker capacities and oversight. It is widely recognised that weak PFM systems contribute to poor governance, undermining poverty reduction and critical state and peace building processes. Moreover, evidence shows that weak PFM systems increase fiduciary risk and provide opportunities for corruption, with corruption itself also undermining poverty reduction. / However, the Government of Nepal has also shown strong initiative in some areas of PFM reform, including the roll-out of the Treasury Single Account System (a so called Integrated Financial Management Information System) to all 75 districts in Nepal, the creation of a PEFA (Public Expenditure and Financial Accountability) Steering Committee bringing together several PFM actors at high political level, developing a new Chart of Accounts and the gradual adoption of accounting and auditing standards according to international standards, development of Strategies for the Office of the Auditor General and the Public Procurement Management Office, development of the national PFM Reform Program (Phase I) and PFM reform strategies in some sector ministries (health, education, local governance). These efforts have also been underpinned by generally sound fiscal management and a professional civil service. The reform efforts have brought some improvements in the area of PFM, including better expenditure controls, transparent budget classification according to international standards, and more comprehensive budget information. / However as severe PFM weaknesses remain, renewed efforts are required to identify critical gaps in the PFM system in Nepal and to accelerate the implementation of risk mitigation measures and crucial reform. To assist and drive these reform efforts, a multi-donor trust fund managed by the World Bank, and co-financed by DFID, has been concentrating on PFM reforms at the central level, working with the Ministry of Finance, the PEFA Secretariat and the Office of the Auditor General as well as civil society organisations. As abovementioned, PFM weaknesses are even more evident at local and sector level due to weak capacities and oversight. Therefore the project Improved Public Financial Management and Accountability was designed to complement the multi-donor efforts at central level, by specifically focussing support to PFM reform at the local and sector level in Nepal. / Accordingly the project Improved Public Financial Management and Accountability has a crucial role in strengthening Government of Nepal’s PFM systems at local and sector level as well as reducing fiduciary risks for DFID’s and other donors’ development funds. It is directly complementary to a large local governance programme (Local Governance and Community Development Programme Phase II (LGCDP II)) with a total value of over USD 1 billion, to which DFID is planning to contribute £70 million. The project also directly contributes to strengthening PFM systems and reducing fiduciary risk in the sectors where DFID provides financial aid, including for example health, forestry, rural infrastructure, and thereby reducing fiduciary risks.

## Section A: Detailed Output Scoring

Output 1: Improved local budget and fiscal management
Output 1 score and performance description: / C – Outputs substantially did not meet expectations / Indicator 1.1: Uniform Village Development Committee (VDC) accounting software used in VDCs / Baseline: 0 / Target: Accounting software developed / Indicator 1.2: Performance indicators and guidelines developed and applied for allocating block grants to Village Development Committees / Baseline: None / Target: Performance indicators and guidelines developed / Indicator 1.3: PEFA Indicator 21: Effectiveness of internal audit / Baseline: TBD (as soon as local level PEFA Assessment has been completed) / Target: TBD (based on baseline)
Progress against expected results till September 2013: / The ADB managed Strengthening Public Management Programme (SPMP) was operational only in August 2013, due to Government of Nepal’s delay in fulfilling one of the first tranche policy conditions. There have also been unanticipated delays in the ADB procurement of service providers (technical assistance) for the sector PFM reform part of this programme. This has contributed to significant delays in starting the project activities and therefore no results are achieved as yet. / Recommendations: / ADB and the Government of Nepal should now accelerate the implementation of the programme. It is recommended that the milestones and outputs are revisited to accommodate the initial delays. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 2: Strengthened sub-national fiduciary risk management at the local level
Output 2 score and performance description: / C – Outputs substantially did not meet expectations / Indicator 2.1: Village Development Committees’ (VDCs) Annual Plans developed through Ward Citizen Forums / Baseline: None / Target: 200 VDCs / Indicator 2.2: Risk-based management audits conducted on VDCs / Baseline: 0 / Target: 5 DDCs, 5 Muns, 50 VDCs / Indicator 2.3: Reduced number of District Development Committees and Municipalities categorized as high-risk / Baseline: TBD / Target: 10% reduction from baseline
Progress against expected results till September 2013: / See progress for Output 1 above. / Recommendations: / Similar recommendations as for Output 1above. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Enhanced public procurement system
Output 3 score and performance description: / C – Outputs substantially did not meet expectations / Indicator 3.1: Procurement plans of ministries published electronically / Baseline: 0 / Target: 3 ministries / Indicator 3.2: National and local government officials trained in public procurement / Baseline: 0 / Target: Procurement officials of 2 ministries, 3 districts trained
Progress against expected results till September 2013: / E-submission module of the e-government procurement system has been rolled out in 13 government procurement entities to date. E-government procurement consultants have been deployed for the development of additional modules. They will also assist the government in achieving outputs 3.1 and 3.2. / Recommendations: / Closely monitor the progress and work to accommodate the initial start-up delays. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Strengthened institutions of oversight and accountability
Output 4 score and performance description: / C – Outputs substantially did not meet expectations / Indicator 4.1: Improved ranking of Nepal in Transparency International's Corruption Perception Index / Baseline: 2.2 score in 2010 / Target: 2.2 in 2012 / Indicator 4.2: % of senior civil servants that comply with submission of asset declaration / Baseline: 63% / Target: 70%
Progress against expected results till September 2013: / Transparency International changed its scoring methodology for its Corruption Perception Index in 2012 and the scale now ranges from 0-100, while before it ranged from 0-10, but this should not have affected country ranking. Nepal’s ranking improved from 2010 to 2012 from rank 146 to rank 139. However, as rankings are per definition relative to the performance of other countries it is more advisable to look at the score achieved. Nepal’s Corruption Perception Index score improved from 2.2 (equivalent to 22) in 2010 and 2011 to 27 in 2012. / Year Score Rank 2010 2.2 146 2011 2.2 154 2012 27 139 / Progress for indicator 4.2 to be updated in the next progress report. / Recommendations: / Similar recommendations as for Output 1 above. It is also recommended that indicator 4.1. is reviewed and improved. / Impact Weighting (%): 5% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 5: Counter Fraud Analysis and Support for Sectoral Public Financial Management Reform
Output 4 score and performance description: / A – Outputs met Expectations / Indicator 5.1: # of Fiduciary Risk Analysis (FRA) and Annual Statement of Progress (ASP) / Baseline: none / Target: 5 FRAs, 3 ASPs / Indicator 5.2: # of reports on Public Finance Management reform in key sectors
Baseline: None / Target: 3 reports / Indicator 5.3: Implementation of sectoral Public Finance Management reform action plans in key sectors / Baseline: None / Target: Public Finance Management reform action plans prepared / Progress against expected results till September 2013: / DFID Nepal has commissioned fiduciary risk assessments for the national systems, the Local Governance and Community Support Programme (LGCDP), School Sector Reform Programme (SSRP), Nepal Peace Trust Fund (NPTF) and the Nepal Health Sector Support Programme (HSSP). The first four have been finalised and are in the process of approval or have been approved, while the latter is available as a final draft. The Forestry Sector was the only sector with an annual statement of progress (ASP) was due this year (2013). This ASP was prepared by the the Multi Sector Forestry Programme itself. As 5 FRAs and the one pending ASP have been prepared, we consider the benchmark of indicator 5.1 to have been met. / Crown Agents were awarded a contract in May 2013 to carry out PFM reform activities in the sectors. A 3 month inception phase came to an end in August and they have submitted the inception phase report as well as PFM reports for 7 sectors, including Health, Education, Local Governance, Rural Infrastructure, Climate Change, Forestry and Security and Justice. With reports on PFM reform in 7 sectors completed, we consider the benchmark of indicator 5.2 to have been met. / Crown Agents will now begin to support selected sector ministries to prepare, refine and implement PFM reform plans. The respective sectors will most likely be the following: Health, Forestry, Peace and Justice, Local Governance, and Rural Infrastructure (maintenance). / Recommendations: / It is recommended that the current logframe along with the indicators is revised. The PFM support to the sectors will be depend on the advice from respective DFID Nepal sector advisers to engage with the sector ministries as well as the actual demands from the respective ministries. / Impact Weighting (%): 40 % / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / The logframe has not been updated as this is the first annual review. As abovementioned, the logframe needs to be updated and the milestones need to be deferred to accommodate the delayed start of the programme. / 1.2 Overall Output Score and Description: / B – Outputs moderately did not meet expectations / The ADB managed Strengthening Public Management Programme has become operational only in August 2013 which has caused significant delays in starting the project activities. The delay was, among others, due to the long time taken by the Government of Nepal to fulfil one of the tranche release policy conditions set by ADB. There have also been unanticipated delays in the ADB procurement of service providers (technical assistance) for the sector PFM reform part of this programme. / Crown Agents were awarded a contract to carry out PFM reform activities at sector level only in May 2013 due to DFID internal procurement delays. / The project Improved Public Financial Management and Accountability has therefore not achieved its milestones for the first year and has thus underperformed slightly. The overall score for this annual review for the Improved Public Financial Management and Accountability project is a “B”, indicating that outputs moderately did not meet expectations. However, it should be highlighted that the first component of the Improved Public Financial Management and Accountability project, the ADB led SPMP, only scores a “C”, which means its outputs have substantially not met expectations. The overall rating of the project is improved by the “A” rating for the second component, the Crown Agent implemented sector PFM reform assistance. / 1.3 Direct feedback from beneficiaries / This has been a light touch desk based review only, as the programme is yet to be fully operational. It is recommended that the next annual review should include as many stakeholders as possible.
1.4 Summary of overall progress / The overall progress has been slow due to delays in starting of the project. It is expected that the project will pick up momentum this year.
1.5 Key challenges / The key challenges in the implementation of the Strengthening Public Management Programme have been to actually start its implementation based on the fulfilment of the ADB tranche conditions by the Government of Nepal and the procurement of the technical assistance completed. There have also been unanticipated delays in the ADB procurement of service providers for the sector PFM reform part of this programme. / The key challenge regarding the second component of the Improved Public Financial Management and Accountability project, the technical assistance for PFM sector reform by Crown Agents, has been the delayed start due to DFID internal procurement delays. / We expect the programme to now focus on the actual implementation of programme activities, as the initial problems have been overcome.
1.6 Annual Outcome Assessment / The outcome of this programme is ‘Enhanced Efficiency, Transparency, and Integrity of Public Finances at the National, Sectoral and Sub-national Level’ The programme is yet to contribute to this outcome.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / DFID has provided funds to ADB for the grant component in 2012, but ADB has disbursed funds to the Government of Nepal only in August 2013. The spend on the technical assistance component has also been slow due to delay of the procurement of the respective service provider. / 2.2 Key cost drivers / The business case expected that costs to DFID were to be significantly reduced due to selection of one service provider to deliver Counter Fraud and fiduciary risk analysis as well as support for sectoral PFM reform. Crown Agents have been selected to deliver these outputs. DFID Nepal followed this strategy even before Crown Agents were selected by joining five Fiduciary Risk Assessments into one contract and therefore making savings in terms of transaction costs and actual spending. / 2.3 Is the project on-track against original timescale: N / As described above, there have been delays in starting the actual programme activities and the project is therefore not on-track against the original timescale.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The originally applied theory of change and assumptions are still valid for in this project and there is no new evidence to challenge the original project design. / 3.2 Where an evaluation is planned what progress has been made? / The project envisages a possible mid-term evaluation, as well as an evaluation led by the Government of Nepal (through the PEFA Secretariat, including the planned PEFA assessment).

4. Risk
4.1 Output Risk Rating: Medium / The overall risk rating of the project is medium. / 4.2 Assessment of the risk level / The risk level remains stable. DFID Nepal has risk registers which are updated and monitored on a regular basis.
Risk of funds not being used as intended / The SPMP is part of the Local Governance and Community Development Programme Phase II (LGCDP II), which is a Government of Nepal and multi donor programme (also co-financed by DFID). The LGCDP II Joint Financing Arrangement has agreed on additional financial scrutiny and risk mitigation measures to reduce the risk of funds not being used as intended in the grant part of SPMP funding. DFID is also funding part of the ADB provided technical assistance for SPMP which will be done through ADB procurement and management procedures. / For the second component supporting PFM reform at sector level as well as DFID with Counter Fraud and fiduciary risk analysis, implemented by Crown Agents, DFID receives monthly invoices and weekly updates from the service provider. The invoices are checked by the programme team and verified by the advisors. / 4.4 Climate and Environment Risk / This intervention has limited direct environmental impacts, but it does provide opportunities to improve the financial performance within the local bodies managing environmental resources.

5. Value for Money
5.1 Performance on VfM measures / The business case stipulates the following benefits from the programme, which still hold true: / The benefits from the programme for GoN include i) improved budget credibility ii) improved revenue collection from local governments and reduced financial mismanagement iii) cost savings in public procurement through the adoption of electronic government procurement (e-GP) and iv) strengthened oversight resulting in reduced corruption. / The benefits for DFID are envisaged to be higher value for money as a single contract to carry out counter fraud and fiduciary risk assessments has been awarded. This will only be evident after the programme has started implementation. / 5.2 Commercial Improvement and Value for Money / The design of the second component of the Improved Public Financial Management and Accountability project, focusing on sector PFM reform and counter fraud as well as fiduciary risk analysis, was such that DFID Nepal would conducts a mini competition from among the existing DFID framework contracts. There was a good market response with 3 bidders from within the frameworks, enabling DFID Nepal to choose the bidder offering highest value for money. / 5.3 Role of project partners / ADB, having a leading role in the SPMP, and Crown Agents have started to implement the project activities. The performance assessment based on the indicators of the logframe is currently pre-mature due to the delays outlined above. / 5.4 Does the project still represent Value for Money : Y / We expect the value for money aspects to be unchanged since the design of the programme and therefore still represent value for money. / 5.5 If not, what action will you take? / Not applicable, see above.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
The ADB managed Strengthening Public Management Programme has become operational only in August 2013 which has caused significant delays in starting the project activities. The delay was, among others, due to the long time taken by the Government of Nepal to fulfil one of the tranche release policy conditions set by ADB. There have also been unanticipated delays in the ADB procurement of service providers (technical assistance) for the sector PFM reform part of this programme. / Crown Agents were awarded a contract to carry out PFM reform activities at sector level only in May 2013 due to DFID internal procurement delays. / The overall score for this annual review for the Improved Public Financial Management and Accountability project is a “B”, indicating that outputs moderately did not meet expectations. However, it should be highlighted that the first component of the Improved Public Financial Management and Accountability project, the ADB led SPMP, only scores a “C”, which means its outputs have substantially not met expectations. The overall rating of the project is improved by the “A” rating for the second component, the Crown Agent implemented sector PFM reform assistance. / Looking forward, the following actions are recommended to improve project performance significantly: / Review and update the logframe and indicators to take into account the initial delays as well as improve the indicators. / Focus on actual project implementation now that the initial problems delaying the start of the programme have been overcome. / To ensure improved implementation progress, it is recommended to put in place a Project Improvement Plan for the ADB managed SPMP component. Even though this would not be mandatory at this stage we believe such a Project Improvement Plan for an initial six months would support implementation progress. While the details of this Project Improvement Plan still need to be decided it should include the following aspects: / Stronger oversight from DFID with regular monitoring of project progress and project improvement plan to be monitored and reported on bi-monthly; / Improved and more systematic communication between ADB and DFID in Nepal; / Improved ADB management capacity for the SPMP, including decentralising project responsibility to Nepal country office if at all possible. / Continued close collaboration with the implementation partners as well as the Government of Nepal. / Conduct more participatory annual review next year (2014).

8. Review Process
This review was a light-touch desk based review conducted by DFID advisers as there had been significant delay in the programme becoming effective and the implementation of most of the programme activities had not begun.