Type of Review: Annual Review

Project Title: Development Research Uptake in Sub-Saharan Africa (DRUSSA)

Date started: 1/10/11	Date review undertaken: 18-21 Sept 2013

## Introduction and Context

What support is the UK providing?
The UK is currently providing £3.7million over five years. This programme will be receiving an additional £1,261,955 over the next 3 years for an additional work programme. As this has just been awarded this is not part of the review but will be considered as part of the next annual review.

What are the expected results?
The DRUSSA (Development Research Uptake in Sub-Saharan Africa) programme aims to improve the capacity of universities in Sub-Saharan Africa (SSA), to contribute research evidence for pro-poor policy and practice. The programme will contribute towards improving knowledge about, and practice of, Research Uptake Management in SSA universities. DRUSSA will do this by supporting universities to improve the accessibility, availability and use of their research, across a range of thematic areas, to improve the livelihoods of children, women and men in Africa and to inform Sub-Saharan and global development policy and practice. / DRUSSA will strengthen the capacity of 24 research-intensive universities in Nigeria, Ghana, Cameroon, Ethiopia, Kenya, Uganda, Rwanda, Zimbabwe, Zambia, Botswana and South Africa by strengthening their research uptake management capacity, and by strengthening their participation in the international development scientific research system. / The programme intends to deliver the following results: / At least 40 staff members from DRUSSA’s 24 partner universities certified as specialist Research Uptake Managers; / At least 85 staff members from Sub-Saharan African universities certified as specialist Research Uptake Managers; / At least 16 M/D.Phil graduates in Science and Technology Studies (specialisation in Research Uptake and Utilisation); / Research Uptake Management embedded in the organisational and institutional practices of 24 universities in Sub-Saharan Africa, by way of engagement with leadership, continuous access to online learning resources and a shared online workspace, and comparative benchmarking of university management structures, process and practices; / Evidence of uptake and utilisation of research systematically documented and shared; / An established, active, engaged and sustainable network of researchers and Research Uptake Management specialists fully engaged in the international development research system and specialising in making research evidence accessible and usable.

What is the context in which UK support is provided?
Demand is growing amongst policy and decision makers for reliable evidence from science, technology and social science research to stimulate sustainable development across a range of development challenges. Quality evidence can contribute to improving better outcomes in, for example, agriculture, health, education, governance, climate change responses, urban and infrastructure development, economic growth and wealth creation. Applying and using evidence in developing countries is constrained by poor access to research information and weak interactions between policymaking and research communities. Evidence use is also affected by local governance and political factors, institutional and organisational barriers. / Research-intensive African universities can play an important role in contributing to the evidence base to address specific development challenges, and to stimulate demand for better, stronger and contextualised evidence. African research institutions’ capacity is a key resource for policy makers and people working in development, but this capacity is under-resourced and under-utilised, and consequently not fulfilling its potential. / There are numerous examples of university-based research that are having an impact on poverty reduction. But there is also evidence of dynamics at these universities that prevent research being effectively disseminated outside the academic domain, let alone being taken up by individuals and organisations that want and need evidence to tackle development problems.

## Section A: Detailed Output Scoring

Output 1: a core of specially trained and qualified university staff who can provide the strategic and operational leadership and expertise for research uptake management in their university
Output 1 score and performance description: / A – outputs met expectation / Indicator Milestone Sept 2013 Actual / 1.1 Number of Masters and PhD awarded in STS Programme Masters and Doctoral candidates of cohort 1 have completed 75% of modules. / Cohort 2 of the RU&IA Masters has completed U Stell academic assessment and selection processes in readiness for 2013 registration. / Candidates informed and DRUSSA bursaries allocated. Master and Doctoral students have completed 6/8 modules (75%) / The invite for applications was launched 2 months ago. The deadline is at the end of September with selection by the end of October in line with the University of Stellenbosch’s processes. DRUSSA bursaries will be announced then too. / There are currently 8 Masters and 6 PhD students funded by DFID. There were 14 applications from DRUSSA partners for the Masters programme and 8 for the PhD programme –applications were received from 12 of the 24 DRUSSA Universities and 11 had a candidate accepted. The minimum academic requirements for the M.Phil programme is an Honours Degree with at least 65% average in the major subjects and CREST are satisfied with the quality of the current candidates. / In addition, there has been demand beyond the DRUSSA programme with an additional 10 students funded by other sources– this includes people funded by the National Research Foundation in South Africa, UNICEF and the Global Environmental Program. These ‘spill-over’ effects are welcomed and CREST is to be congratulated for dealing with this increased demand. However, CREST must ensure that this extra demand does not reduce the quality of the course delivery and student support. CREST is aware that they need to manage this risk and have been sourcing additional supervisors for the students, recognising they do not have adequate capacity. / 1.2 Number of DRUSSA participants completing short courses Minimum of 40 delegates (annually) from DRUSSA partner universities have completed 2 short courses in RU offered each year (disaggregated by gender) 35 participants from DRUSSA universities have completed the 2 courses. This number is less than the target because a number of issues such as changes in university staff and visa issues prevented some participants attending at short notice and o. / Gender rep reflects research offices. 60/40 / 1.3 Number of non-DRUSSA participants completing short course in science communication Minimum of 20 delegates from non-participant university community complete short course in science communication 29 participants from non-DRUSSA universities completed a short course in science communications / The short courses have been delivered in South Africa, Ghana and Kenya. The feedback from participants on the six short courses, collected through a course evaluation questionnaire, has been generally very positive with participants feeling the courses were well prepared, structured and delivered. CREST have been making alterations to future courses to address feedback, such as the request from some to provide more reading ahead of time to help participants prepare and to include more time for discussion and participant interaction. / There has been discussion over whether further quality measures should be added to the short course indicators. The short courses are adapted from the Masters course and the quality of the material is not in doubt. Some indications on how much people are learning would be useful- this could be attained through a very short pre- and post- diagnostic course / The short course programme was designed anticipating that the same participants from the DRUSSA universities would attend every course. There has been about a 60% overlap between the first and second round. It is unsurprising that this is the case given there will be staff turnover and not all participants will be available for the second dates. This lack of continuity presents some problems for the short courses and how they are contributing to organisational capacity, which should be given further consideration. This may in part be addressed by the suggestion to embed the short course training (see below). / The previous annual review recommended that more practical examples be used in the courses. CREST has explained that the courses vary on how theoretical or practical they are depending on the subject. This mix works well if participants complete every course. As the accumulated learning that CREST had hoped for is not consistent across all DRUSSA universities, CREST should consider how future course structures could ensure inclusion of some practical examples and/or participants bringing their own examples to share/work on as part of the course. In addition, it will be important that partners explore how the participants on courses can feed into the University change strand being overseen by ACU. / The logistics of organising short courses for participants from universities across SSA has been demanding, with planning for them commencing 5 months in advance. CREST has been coping well with the logistical and administrative burden, but it has been greater than expected. We would, however, recommend that CREST reviews its planning to ensure are enough time for visa applications I allowed. Organising the regional courses has proved problematic with local logistical issue causing significant problems and requiring more resources to manage these issues. It was hoped that organising courses regionally would enable more people from the host university to attend. Although more people from the university registered, this did not result in these people attending or fully participating in the course. This phenomena has also been observed in other DFID-funded programmes. The policy of not paying per diems does mean that generally people are attending because it is relevant to them. / CREST feel that the benefits of having regional courses are not being realised as hoped and the cost related of them is higher than expected and so they are planning on conducting all future courses in South Africa. This is disappointing but understandable. However, a number of participants suggested at the recent DRUSSA symposium and in subsequent communications with DFID that they would like to see the short courses decentralised with more Training of Trainers to give universities the capacity to embed the training alongside other training, such as that in research methods. The training courses for academics obviously may differ to that aimed at research managers. The programme team should explore the potential for training people to deliver the short courses in selected universities that have shown demand. This could be as part of the next phase of improving institutional capacity. This may require extra resources but this may be worth reallocating resources to from other parts of the programme. / In response to the administrative burden of the short courses and as recommended in the previous annual review, CREST has been exploring the possibility of producing online training courses. CREST currently put much of their course material online so that anyone can access it. However, some material cannot be put online except for access for registered students because of issues around IP. CREST is looking into how training can be broadened and how tele-learning and online resources can be used, but recognise that their capacity is already stretched. / CREST is also exploring whether the Science Communication short course can be accredited by the University of Stellenbosch. This may make the course more valuable for CPD and result in a more certain future for the course beyond DRUSSA. However, if successful in being accredited this could change the business model for delivering such a course as it would require full cost recovery by the university and would not be as simple to run under a programme such as DRUSSA. / Recommendations / CREST must monitor its capacity to teach and supervise the current 14 DRUSSA M.Phil and PhD students and utilise additional resources where necessary to ensure that the increase demand from outside DRUSSA does not diminish the quality offered to those on the programme – especially with an additional intake of students to start in the coming months. / CREST to consider introducing light-touch pre/post course diagnostic tests / CREST to consider whether any alterations to the training curricula need to be made given the lack of continuity of participants and to ensure that planning for course allows time for problematic visa applications. / CREST to consider how future course structures could ensure inclusion of some practical examples and/or participants bringing their own examples to share/work on as part of the course. / CREST to explore how participants on their courses can link up with/support the university change programmes when they return to their own institutions. / The programme team should consider how they can work together to enable the short courses to be embedded in universities (where there is the demand and the capacity). This requires consideration of whether trainers can be trained, how this fits with other institutional support activities and how electronic resources can aid this. Partners should think through the potential barriers and problems. This may have implications for how the budget is allocated. They may wish to consult with other organisations who are supporting Training of Trainers to embed courses in Univerisities (e.g. INASP, IDS and PASGR). / CREST should continue to explore potential for online and remote access learning
Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Strengthened strategic leadership and organisational capacity within DRUSSA partner universities to achieve greater uptake of their research by external users.
Output 2 score and performance description: / A – outputs met expectation / Progress against expected results:
Indicator Milestone 2013 Actual / 2.1 Number of university leaders and senior research managers from DRUSSA partner universities who have completed the University strategic management benchmarking programme, adopted research uptake management policies and strategies for the University and have research uptake implementation plans developed. At least 18 universities have set up cross functional consultation teams and reviewed draft good practice statements developed by all the universities identifying individual priority improvements to policy and practice to strengthen the management and promotion of research uptake. The DRUSSA team have visited 20 universities so far. It was ambitiously hoped to have visited all 24, however elections in Zimbabwe and changes in staff at other universities have meant some visits have had to be rearranged. It is hoped that all 24 will have had a workshop with programme staff by December 2013. / 2.2 Number of universities who have developed or strengthened systems and processes to embed research uptake as integral part of research management At least 18 universities have mapped internal and external research uptake stakeholders, current systems and processes, individual challenges and opportunities, as a result of university research uptake planning visits and workshops. As part of the university campus visits, 20 universities have identified stakeholders and considered their current systems and processes. / 2.3 Number of DRUSSA partner universities who have compiled and make publicly accessible a complete organisational record of their policies, literature, institutional repositories and institutional services focusing on Research Uptake Management At least two universities have compiled and made publically accessible a complete organisational record of their policies, literature, institutional repositories and institutional services focusing on Research Uptake Management. Four universities (Zambia, Fort Hare, Makerere and CPUT) have complied and made public their policies and approaches to Research Uptake. For example, CPUT has published research and innovation blueprint which includes a section on research uptake. / The programme has made good progress in engaging with the 24 Universities. This has involved each university establishing a broad implementation team across their university, with a high level leader and a champion to catalyse action. Of the 24, 20 universities have then prepared for and received a visit by the DRUSSA team, during which they have considered what research uptake is, how it currently operates in their university and how the universities strategies and processes could be improved. Many of the Universities have taken this very seriously, including the VC or a deputy VC in the meeting, and dedicated senior staff time to it. The content and quality of these visits have developed over time. / These workshops and visits were designed and delivered by ACU (WP2) to support participating universities explore in depth their current strengths and challenges in research uptake management within the university. Bringing together a range of staff from across the universities their aim is to support participants understand value of research uptake management and what it means at an organisational level; to support participants take forward discourse, learning and priorities identified from the benchmarking process, in particular to individually assess themselves against the statements of good practice in research uptake management developed at the Leadership Conference; and to begin to develop at organisational level their own framework for strengthening research uptake management. Over 400 participants have taken part. Course/workshop feedback has been very high. / The programme is designed so that universities develop their approach in a way that suits their context. It was clear at the symposium and from discussions with the programme team that some universities were very engaged and have been making very good progress. Predictably this has not the case for all 24 and there is a range of enthusiasm and willingness to engage, as well as ability and capacity to do so – both of which can be affected by the quality of leadership at the university. This is beyond the control of the programme management team and the team are aware of this. However, as the programme team are planning for the next stage, this needs to be factored into future plans and support/guidance activities should be targeted appropriately at universities with different capacity levels. There were discussions at the advisory panel meeting on providing a ‘menu’ of options to allow universities to discuss with programme staff what support or guidance would be most useful for each university in the second half of the programme. This should be explored further by the programme team. DFID is keen that the programme team invest the greatest amount of time and energy into the Universities which are most likely to be able to drive change. We would suggest that Universities which are less engaged could be offered a lighter offer of support and whether support should be removed if a low level of engagement persists for an extended time period. / This first stage has been broadly successful at raising awareness and generating interest; the next stage will require universities to dedicate real resources and will test their willingness and commitment to improving research uptake. / Staff changes at universities, particularly in the senior management team, can seriously affect how activities to improve research uptake are perceived, prioritised and resourced. The programme team is aware of this and have encountered this on several occasions. This is beyond the control of the programme team, however, they feel that the impact of such changes will reduce as the programme becomes more established in each university and can continue working with those engaged despite changes in leadership. / The current trend of ‘federalisation’ of universities being observed in some countries presents a further challenge to institutionalising research uptake as this means the number of people that need to be engaged and committed will increase. However, engaging more people may also help mitigate the risks from people in the implementation teams changing. This needs to be added to the risk framework and the implications for how the programme is delivered considered. Embedding training in some universities – as mentioned above – may help. / Monitoring and next phase / The previous annual review noted that the programme needed to improve how it will demonstrate strengthened organisational capacity by the end of the programme and recommended the logframe be revisited. Whilst the logframe has been improved, a more detailed monitoring tool is required for the team to be able to track progress of each individual university. This would enable the team to ensure their next phase of activities is appropriately targeted, help ensure all people involved in the programme management are aware of progress and help any new team members to become familiar with the status of this part of the programme quickly. / The September symposium was designed as additional support activity to begin to address this to allow universities to start developing plans of action. This was not in the original plan but was developed as a direct response to that gap. / This monitoring tool/table could be developed from the benchmarking data, the university campus visits, the data on who has been trained and the tacit knowledge of the team, which is extensive and should be documented. If further information is required, this could be collected during the next benchmarking activity. / Any official ranking of universities may be unhelpful but the monitoring tool could be developed into something universities could use to track progress themselves and compare themselves to others. It may be useful to have a version available for participant universities to be given annually and one that is more appropriate for internal programme monitoring and planning that is updated more than once a year. / As mentioned, the programme was specifically designed so that universities could develop an approach to research uptake that was most appropriate for their context rather than trying to fit one model to all. This obviously presents challenges to developing a monitoring tool, which inevitably standardises progress, but it could be designed and used to illustrate the range of ways in which universities can approach and embed research uptake. Such a tool could then be used as evidence for progress of the programme and identification of future work (tying it in with the ‘menu’ of options) and possible needs for future funding. The project team will need to be careful they do not end up spreading their resources too thinly and a monitoring tool could help them consider where their resources are best spent. / It seems it would be more appropriate for ACU to develop and use such a monitoring tool since they are more heavily involved in organisational capacity building – although they may want to consult CREST’s expertise as they do so. This could also be aligned with general programme monitoring discussed in section 7 part B. / Other donors / The programme team rightly recognises the risk that other funders becoming interested in this area could start working in parallel to DRUSSA, competing for and reducing the enthusiasm and willingness of universities. DFID and the programme team should work together to explore the intentions of other ‘like-minded’ funders to work in this area to prevent this from happening. / The DRUSSA programme does not provide direct funding to the universities involved but provides advice, training and technical support. This means that those that engage do so because they can see the value in improving research uptake in their universities. However, the lack of direct funding to the universities does still cause some issues with enabling individuals to prioritise this work. In discussions with other donors the potential for funding from other sources to complement DRUSSA’s work could be discussed. / Recommendations: / ACU tailors the amount of time and energy invested in Universities to the degree of engagement such that fully engaged Universities receive more support. / Add University federalisation to the risk framework and consider implications for programme implementation. / ACU develop a monitoring tool (as discussed above) to enable them to keep track of individual universities progress more systematically and to be able to communicate this with those involved or interested in the programme. / ACU and DFID should discuss the DRUSSA programme with other donors/funders. / Impact Weighting (%): 45 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y

Output 3: New contributions to the evidence base about Research Uptake and Impact Assessment in Africa and globally.
Output 3 score and performance description: / A – outputs met expectation
Progress against expected results: / Indicator Milestone 2013 Actual / Research undertaken and publication of documents and reports- specifically Review Report of scholarship on Research Uptake and Impact Assessment Second Draft of Report on Scholarship in RU and IA informs construction of the RU and IA knowledge resource A second draft has been produced and summited to DFID (although there are still chapters missing from this) and a final report is expected to be produced by March. / 10 in-depth case study reports on RU in development research projects at Group of 24 universities 4 case studies selected and process for writing case studies initiated; Second round of nominations for 4 more case studies initiated 4 case studies have been selected and a workshop held in South Africa to initiate the process (although 1 team could not attend because a visa was not approved in time, so will be included in the next round) / Second round call has been sent to Drussa universities and the process of writing will begin in Feb or March. / Development of an operational DRUSSA M&E Framework to inform regular M&E reports Synthesis study of quarterly M&E reports disseminated to DRUSSA internal audiences A synthesis study has been developed and circulated amongst partners – this will be reviewed by the programme manager to ensure most value is gained from this for ongoing monitoring and reporting. / Research A customised version of the research report CREST are producing may be produced as handbook for the short courses. / CREST is completing a journal article on frameworks for institutionalising research uptake in universities. CREST must ensure they are familiar with DFID’s Open Access Policy / CREST has applied to the South African Government’s Department of Science and Technology to become a Centre of Excellence in Scientometrics and Science Policy. If successful (and they are confident they will be), this will result in long-term funding of 10 million Rand per year for 10 years. This will enable them to expand some of the activities they currently do under DRUSSA in the long term. / Case studies The programme team reported that producing the case studies have been a challenge. The criteria were stringent and there had to be two calls before suitable case studies could be selected. The case study teams will work with CREST over the course of 2 years on developing an uptake strategy, delivering this and considering how to evaluate it and assess impact. This is challenging as it is quite new to the participants. It is anticipated that although there will be a second call for cases studies, this will supplemented by case studies drawn from the PhD thesis. It is anticipated that a book featuring these case studies will be produced in 3 years. / In addition to these case studies on specific research projects, the DFID review team would encourage DRUSSA to consider a series of ‘high level’ case studies which illustrate how different Universities have embedded Research Uptake. One approach would be to consider different categories/types of approaches taken by different types of institutions. Such case studies could be a valuable output of the programme since they could inform the Research Uptake approaches of Universities who are not part of DRUSSA. / Monitoring and Evaluation CREST has been leading the partners on developing and internal Monitoring and Evaluation Framework. This Framework is well developed in terms of monitoring, but has not been completed. Once completed and agreed amongst partners this could be used as a basis for future annual reports prior to annual reviews, which would reduce the work of future. / The programme team need to consider how in the next phase they can support universities to develop their own approaches to M&E. / See section 3.2 for further details on evaluation. / Recommendations: / Consider developing high level case studies of how Universities approach embedding of Research Uptake / Ensure that internal M&E is further developed and fully implemented and links with reporting to DFID / Work with universities to develop their capacity to monitor and evaluate their own activities / Impact Weighting (%): 10 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y

Output 4: A Community, Network and Public that is better informed about, and more engaged in, the SSA development research uptake discourse.
Output 4 score and performance description: / B – outputs moderately did not meet expectations / Indicator Milestone 2013 Actual / (1) Number of Community members that have been trained; / (2) Number of user responses on the DRUSSA Coffee Station/DRUSSA Blog and other DRUSSA accounts on SN Platforms / 3) Number of individuals reading DRUSSA-published content about Research Uptake and Research Uptake Management. Implementation Teams at 24 universities; + 600 persons / Members from up to 6 universities' RUM implementation teams are responding on the DRUSSA Blog/Coffee Station and DRUSSA SM platforms. / Up to 24 universities have practiced RUM in 2 media in the RUC 2013 campaign 20 of 24 DRUSSA universities’ implementation teams have received online training as part of each campus visit and this has been supplemented with 2 online user guides sent to implementation team members and available online. / 20 of 24 Leaders/Champions have had training consolidated at the Symposium. / Members from 14 universities’ RUM implementation teams are responding on the DRUSSA Blog/Coffee Station and DRUSSA SM platforms. / 186 of 643 individuals from 24 of 24 universities’ teams read DRUSSA-published content. / The wording of this indicator needs to be clarified (as with some other indicators). If responding is taken to mean visiting this milestone has been met as some of the implementation team from most universities have visited the DRUSSA Blog/Coffee Station (over 12). However, the number commenting/interacting on either is significantly less and overall the figures relating to how well it is being used are disappointing. / 20 of 24 universities have worked to contribute entries to the publication Platform 2013. The publication has been prepared for print, digital media on DRUSSA and university websites, and there is a social media campaign around the launch of Platform 2013 which will commence in late September to late October 2013. / As of mid-September, only 4 DRUSSA universities have put up a dedicated Research Uptake page, but as a result of explanation at the DRUSSA Symposium 19-20 September, the university Leaders are clear about the need for a RU webpage on which to lead their own university’s Platform2013 digital DPS. / Gender breakdown of community members: / F: 190 / M: 383 / Unknown: 69 / Participators, by gender within gender group / % of male participation : 27% / % of female participation : 30% / % of non-gender specified 11% / Number of members of different networks, as well as members of the public, are utilizing these platforms as evidenced by (1) number of visitors and responses on the DRUSSA Blog, / (2) DRUSSA accounts SN platforms Public use of the DRUSSA Blog by 10000 visitors and and 150 registrations for DRUSSA Network. / DRUSSA social networking strategy implemented on 3 social networking platforms. / RU content is shared with 2 international and 1 SSA online networks/sites. / DRUSSA platform/app accepted by 2 RIMA websites. 250 people are registered on the DRUSSA Network. / Public utilisation: / 57227 unique visitors from / 217532 unidentified hits / DRUSSA has a Linked-in, Facebook, google plus and Twitter presence. These are not used frequently. The team are considering using them to target narrow groups of people. / Content has been shared with 4 international networks/sites (R4D, / Communications Initiative Network, / Young Professionals Platform for Agricultural and the Knowledge Brokers Forum) and 5 DRUSSA universities. / Drussa app accepted by WARIMA (www.warima.org)and SARIMA / (www.sarima.co.za) / RU discourse is more visible and engaged as evidenced by the SSA RIMAs, via (1) number of physical events at which DRUSSA is invited to present, and the (2) number of mentions in media of physical events organised by DRUSSA universities, the SSA RIMAs, and international organisations. RU topics and papers included in at least 4 SSA/international research management / conferences/seminars/meetings as a result of DRUSSA presentations/papers Research and innovation management for associated countries (rimi4ac) (EU funded research management capacity building) programme meeting at the ACU in London 9 – 11 October 2012. Audience of +/- 40 people were sub-saharan africa universities’ research managers.8 DRUSSA university representatives) Wellcome Trust african initiative staff, World Health Organisation TDR, Research Africa. / ACU – public relations network conference in Windhoek, Namibia , 15-17 October 2012. 28 DRUSSA university representatives. Audience of +/-100 people was senior staff of commonwealth universities’ public relations/communications divisions. / West African Research and Innovation Management Association (warima) Annual conference, Ile Ife, Nigeria 22-24 October 2012. 17 DRUSSA university representatives Audience of +/- 120 people was senior research managers from west african universities. / Drussa workshop pre-warima conference 21 october 2012. Audience of +/-20 was young researchers and research managers – all from DRUSSA universities. / Poverty and land rights policy (plaas) symposium. University of the Western Cape, South Africa 18-19 november 2012. Audience of +/-55 people was policy think-tank and policy programme managers from SA, UK, South America, North America – all registered on DRUSSA Network. / University of Brighton, IDS, ‘big push forward colloqium 23-25 april 2013. Audience of +/- 120 was development project and programme managers from Asia, S and N America, Africa,UK. 7 registered on DRUSSA Network. / Doclinks summer school, helsinki. 2-5 july 2013. 38 doctoral level researchers whose field work is in sub-saharan africa, 7 from DRUSSA universities – all research Africa-located. ½ day intensive workshop individual research uptake planning for early career researchers.
Progress against expected results: / The DRUSSA coffee station and blog station has not received the level of interaction hoped for. Representatives from the universities usually access the site after training, but generally less than 50% of the team nominated in each university is accessing the site. Discussions on the coffee station are less than hoped. It seems there are a number of reasons for this, some rooted in the current culture of universities which this programme is hoping to alter. The programme team feel that many people do not have the confidence to comment online as they are unaccustomed to doing so in a professional environment and in many universities only a few people are authorised to speak on such online forums. The team have some evidence of emails between participants discussing issues raised on the site offline and they recognise that they underestimated the permission people had to express their own views. / Despite the OSD team’s dedication, the numbers making full use of the site is disappointing. OSD have some suggestions for improving online interaction, including asking the universities to take ownership of the site for discrete periods. It could also be that the sites are used more as the programme matures and peer support and learning is further encouraged however it should be noted that DFID’s experience with other online platforms is that the proportion of people who ever engage is low. Furthermore, our experience suggests that engagement is higher using platforms which participants are familiar with and use regularly – e.g. email. An added advantage of such platforms is that they are free. / We suggest that the programme team should discuss how much resource is dedicated to the current online activities and consider whether resources should be diverted to other more promising areas to ensure the programme is maximising value for money. We would ask the Programme Director to submit a proposal for the future of this area of work within 3 months of this review. / A lesson for future programmes and initiative is to build the online activity more organically around the developing programme and activities, so there is better understanding of the community/audience and their needs before any significant investment is committed. In this case it may have been more suitable for the online activity to grow with the developing community of practice initially through a free group (such as dgroups) rather than constructing something which there is then pressure to fit the community to, and then if necessary develop something bespoke around that community. / The review team felt that OSD have done well to get inputs from 20 Universities for the Platform publication and it is particularly impressive that they have raised the issue of Research Uptake with such high-ranking individuals including many Vice-Chancellors. Furthermore, the annual review team were very impressed by the highly professional formatting of the publication and see that is important for DRUSSA universities to have more practical experience of presenting their research uptake work. However, they had concerns about the style and quality of the writing which did not seem to be appropriate for the policy audience they were targeting. We would suggest that it might be better to focus on a smaller number of institutions but ensure that the outputs model good practice in research communication. / It is encouraging that DRUSSA has presented at a number of conferences and meetings. It would be helpful to get feedback on the outcomes of these presentations – i.e. have they succeeded in influencing people. At present this indicator appears only under WP4 but we would expect that all three lead partners would play a role in promoting the need to integrate Research Uptake into Universities. As the programme progresses we would hope that representation at these meetings would increasingly include representatives from the Universities which DRUSSA is engaging with in addition or instead of staff from DRUSSA lead organisations. / Recommendations: / As the team are developing a better understanding of their target audiences they should review whether the current resource put into producing several newsletters, the blogs and updating and improving the coffee station as well as maintaining presence on a number of social networking platforms should be consolidated and whether resources should be redirected to other activities to improve value for money. The programme manager should report their proposal to DFID by the 10th of January 2014. / Consider whether the Platform publication could be improved by working with a smaller number of institutions and developing a product which is more suitable for a policy audience. / Consider adding an indicator on outcomes/impacts of presentations/discussions at conferences. This does not need to be too in-depth but it would be useful to get some narrative reports on the types of people at these conferences and the outcomes of discussions in order to make a judgement on whether funding conference attendance represents value for money. / Ensure that representation at meetings and conferences is carried out by all lead partners and that efforts are made to increase representation from partner Universities at such events. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? Y

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? / The logframe has been updated since the last annual review although it appears that the process has been protracted and cumbersome. Whilst the outcomes and outputs seem sensible, some of the indicators and milestones require revisiting to ensure that they are suitable for the coming year and to ensure they all have sufficient quality and quantity measures. The logframe should be adjusted in light of recommendations made in this review and to account for a new work package that the programme team will be incorporating. It is suggested that this is done alongside planning for the next phase of the programme (for WP2 and 4) and for the new part of the programme (WP5) and completed by January 2014. We would suggest that one individual is responsible for completing this in consultation with partners so there is consistency and to avoid it being a lengthy process. DFID can provide support and guidance. / 1.2 Overall Output Score and Description: / The overall output score is A. The programme is delivering outputs that meet expectation. / 1.3 Direct feedback from beneficiaries / Feedback from beneficiaries of the programme has been summarised under thematic headings of strengths, challenges and impacts. Note that the feedback is based on a sample of participants and does not necessarily reflect the overall view of all programme beneficiaries. / Strengths / Based on informal discussions and written feedback the symposium participants expressed engagement with the programme and enthusiasm for their current and future research uptake plans. There was general acknowledgment of the experience and efforts of the DRUSSA project team in leading the programme and providing advice and guidance. / The symposium itself provided the opportunity for participants to collectively think and plan for their respective research uptake strategies, providing a ‘conducive environment’. As well as face to face learning the online platform was noted as an opportunity to ‘share experiences and learn’. In summary: / It was noted that the DRUSSA programme in one University has been ‘embraced wholeheartedly’ because of its viability, noting that the programme is the first of its kind in Sub-Saharan Africa. / There is evidence that for some Universities research uptake is being considered as part of the wider institutional research policy. This includes activities such as establishing a specific website platform for research uptake and an implementation team within the university: ‘DRUSSA has challenged the thinking and practice of the participating institutions to be more proactive in innovation and research targeting the needs in society’. / In requesting feedback, participants were also asked about challenges. In summary: / Communication: Need to broaden communication beyond the Coffee Station to focus on direct emails to participants with information and relevant programme material. The online community platform has been established but participants may not have the time to engage with this communication channel. / Monitoring & Evaluation: There needs be further guidance on how M&E will be implemented, including both design and management. Participants also need further practical guidance and support. For example, as well as the toolkits more ‘template driven assistance’ would be valuable. Overall, a long-term evaluation plan for the DRUSSA programme is required, including medium-long term monitoring data from the 24 institutions collected. In addition, measures need to be developed and implemented that ‘attribute systemic changes to the DRUSSA programme’. / Sustainability: It is important to consider planning for the programme’s sustainability beyond 2015, for example considering the potential role of the Association of African Universities. In terms of training, it was also recommend that ‘a generic Module on Research Uptake that can be taught in all partner Universities perhaps within research methodological courses.... is one way that DRUSSA can ensure sustainability and the continued training of a critical mass of researchers, as we build/advance knowledge in this new field’. This points to the importance of building capacity across all University practices, including training researchers who will go on to function as trainers themselves within a University. / The process of attributing impact of the programme will be further identified from the monitoring and evaluation that each University undertakes as well as the independent evaluation for the programme. At this stage of the programme, it is also not possible to assess all impacts as universities are in the stage of writing and implementing their research uptake strategies. For example, one participant noted that the programme has ‘enabled us review our polices and plans relating to research management and uptake which have been laying in limbo for long and embark on the process of formalising and approving them for systematic implementation’.
1.4 Summary of overall progress / Overall the programme is making good progress and is seeing some positive signs as a consequence of the hard work the programme team have put in. The general approach of enabling the 24 universities engaged in the programme to improve their own capacity through support and guidance is challenging but should achieve more sustainable outcomes than may be expected from providing a small amount of budgetary support directly to the universities.
1.5 Key challenges / Some of the key challenges for each output have been discussed above. A further challenge relates to sustainability. The programme team have rightly begun to consider how they can ensure that the changes they are starting to see are sustainable and do not end with the completion of the programme. This is not easy since the universities will be at different stages and it is difficult to know now what support they will need in 2/3 years’ time. / This programme team would like to see research uptake management recognised as a profession in its own right and a long-term professional network established. This would be a step towards making the changes catalysed by the programme more sustainable. Alternatively rooting research uptake within existing research management networks could be also be effective. The aim should be that the principles of and approaches to research uptake should be more embedded in universities and their research activities, whatever it is named. / The programme team have recognised that the development of Research Councils in some of the countries where the DRUSSA Universities are based could provide an opportunity to strengthen the support and incentives for research uptake of high quality research. Whilst working with Research Councils is not part of the DRUSSA programme the team could explore whether there are any opportunities to leverage long-term change for relatively little investment and DFID should consider whether there are any opportunity for DFID or UK Research Councils to support this. / 1.6 Annual Outcome Assessment / Inevitably some individuals will use the skills and knowledge gained through the training more than others and some universities will use the opportunities offered by programme to better effect than others. Therefore the outcome for each organisation is likely to range considerably. The programme team face many challenges in trying to embed research uptake into the culture of such an array of universities; yet they have the ability and have laid the groundwork to make good progress. We hope that the recommendations made in this review will help them to increase the likelihood that they will achieve the sustainable change they are intending to catalyse. / 1.7 Gender / The programme monitors gender by tracking participation in activities. It actively encourages stronger female participation in university teams where it is seen to be weak. When establishing programme teams or governance structures gender is taken into account (e.g developing the Advisory Committee)

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / The project is on-track against financial forecasts and indeed there is an underspend due to currency fluctuations. The ACU as the contract holder are responsible for submitting a proposal on how this underspend could be used. Approval from DFID is required before it can be used for alternative activities. / 2.2 Key cost drivers / Human resources and travel are the key cost drivers. Scheduled workshops and meetings that involve travel are planned ahead as much as possible to take advantage of cheaper fares. The policy within the programme is always to travel economy and to stay in local hotels recommended by partner universities to ensure value for money. / 2.3 Is the project on-track against original timescale: Y / Overall, the project is on-track against original timescales. There are minor timetable slippages but overall the delivery of outputs is to the milestones agreed. For example, not all of the university research uptake workshops have been completed, this is largely down to external factors beyond the DRUSSA team’s control such as the recent Zimbabwean elections.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Since this project was originally designed, there has been growing evidence that Research Uptake requires investment in the ‘demand-side’ as well as support for the supply. This project was designed as a mainly supply-side intervention – supporting Universities to be better producers and communicators of research. Given the emerging evidence on demand-side work, a decision has been taken to extend the DRUSSA programme to include a new workstream focussing on the demand-side (add Quest number). Implementation of this workstream will begin in October this year. / 3.2 Where an evaluation is planned what progress has been made? / It was noted in the project business case and original budget that in addition to project monitoring that an evaluation plan would be developed and an external evaluation undertaken. There appears to be no plans as yet for an external evaluation. This should be discussed by ACU and DFID prior to the next annual review. / The Terms of Reference for the evaluation will need to be developed in collaboration with DFID evaluation advisers to ensure that the evaluation generates reliable evidence that can be used to assess the impact of this programme. A recommendation of this review is to progress discussion on the following aspects of the independent evaluation of the DRUSSA programme: / Agree evaluation aims and objectives / Map the availability and reliability of existing and planned monitoring data / Work with DFID Evaluation Advisers on the evaluation design / Develop a draft project timetable

4. Risk
4.1 Output Risk Rating: / Medium / 4.2 Assessment of the risk level / The risk level has been increased from Low to Medium. The risk level for Output 1 has not changed, the level for Output 2 has been decreased from High to Medium as the programme team now established good relationships with most of the universities and have more experience of managing the existing the inherent risks. The risk level for Output 3 has been raised from low to medium to reflect the difficulties the team have encountered with recruiting and developing the cases study teams. The risk level for Output 4 has increased from low to high to reflect concern over value for money of this work and the need to rethink plans for developing this output. / Risk of funds not being used as intended / As noted in the previous annual review, the programme is led and managed by the ACU. Internal mechanisms to check financial quarterly returns are in place. The ACU also undertakes an annual independent audit. / 4.4 Climate and Environment Risk / Low – travel is kept to a minimum . Materials are on-line. During the courses effort was made to reduce printing and copying costs to a minimum.

5. Value for Money
5.1 Performance on VfM measures / Economy / Meetings where possible are scheduled ‘back-to-back as was evident from the University Symposium/Advisory Committee Meeting as well as a large part of the annual review took place. The universities play an important role in sourcing good local accommodation that offers value for money. The programme does not pay per diems for workshops. / Efficiency / Workshops developed and delivered by ACU were designed to offer value for money and be practical in their outputs. CREST courses must satisfy the University of Stellenbosch quality assurance checks. / The ACU remain an efficient partner to deliver this programme given their experience and existing networks working with Universities across Africa. / (Cost-) Effectiveness / One concern raised by the review team was whether the amount of funds invested in the online discussion platform represented value for money for DFID (see recommendations under Output 4). The team questioned whether a free or low-cost alternative platform may be a more cost-effective means to facilitate discussions and have recommended that the resources dedicated to this be reduced to reflect lower levels of online discussion and sharing than predicted. / The DRUSSA team will be reviewing their past activities to consider where effectiveness could be improved in the next phase. As part of this they should consider alternative uses of the funding for the same ends of strengthening individual and organisational capacity. / 5.2 Commercial Improvement and Value for Money / DRUSSA must have 3 quotes for anything in access of £1000. Consultants must offer VFM with clear outputs. / 5.3 Role of project partners / N/A – DFID is sole funder. / 5.4 Does the project still represent Value for Money : Y / The programme is currently representing value for money- and is strengthening individual and organisational capacity, but VFM needs to be considered in future planning, particularly with reference to Output 4. An evaluation needs to be designed and commissioned to ensure that reliable evidence is collected on the impact of the programme. This will strengthen the assessment of whether the project represents value for money. / 5.5 If not, what action will you take?

6. Conditionality
N/A

7. Conclusions and actions
Recommendations relating to each output are included above. Below are general recommendations relating to the overall programme: / Balance of effort in different activities: We are requesting the programme team to consider the value for money of some communications activities under WP4 and for the programme manager to submit a proposal for the future of these activities by the 10th of January 2014. DRUSSA may propose that funding for these activities should be continued at its present level however a strong justification would need to be made for how this will deliver value for money for DFID. The programme partners may wish to take this opportunity to review the entire programme and to ensure that they feel confident that the balance of efforts across different activities is appropriate to achieve the outcomes they are aiming for. ACU as programme manager should lead this. / Communication between partners: Whilst there are no major concerns about how the partners are working together, communication between partners must be improved. The success of the programme will depend on the partners combining their efforts so that it is more than the sum of the discrete ‘work packages’ /outputs and the synergies are realised. Currently there is a risk this will not happen. This requires better (as opposed to more) sharing of information to ensure that complementary activities are synchronised and that the maximum value is derived from planned and unplanned activities. Communication between partners has focussed on financial issues, developing the logframe and reporting to DFID. There is a need for partners to spend time together focussing on planning the next stage of the programme, taking into account lessons learnt so far. / Programme management: Programme management has evolved at the programme has developed. Now would be an opportune time to ensure that management processes are fit for the next stage of the programme. / Whilst all three partners have agreed to manage their work packages, there is a need for stronger management across the whole programme. The ACU, as the accountable grant holder, is responsible for the delivery of the logframe outputs and must ensure that appropriate systems and agreements are in place to deliver on this and that these are understood by all partners. Given that new partners will be joining DRUSSA as part of the agreed extension, this is an opportune time to consider the nature of the agreements which they hold with partners. In particular, as part of their risk management approach, they should consider how they will respond if partners do not deliver on their outputs. They must ensure that there is adequate programme wide monitoring and that this is then communicated with partners and DFID. This requires the programme manager to be responsible for ensuring that there are plans in place for the next year and more detailed plans for the subsequent quarter. These then need to be regularly monitored with progress communicated to all involved in delivering the programme. CREST has developed monitoring plans (a draft synthesis report) based on the logframe. Once the logframe has been updated to reflect developments and extensions to the programme ACU should use this as a basis for strengthening their monitoring. (This also ties in with the need for a better monitoring tool and for the development of organisational capacity across the universities recommended above.) / The governance of the programme will need revisiting as the work of the programme extends. The advisory board has two good external advisors but should be strengthened further and should also include further representation from the policy community in the countries involved in the programme and the policy arena in Uganda or Ghana DFID can provide further advice/support on this. / Ensuing value for money. The programme team have aimed to provide value for money. However, the team should remain aware of the drive for value for money when considering allocating resources over the next few years. This means avoiding spreading themselves too thinly across too many activities and being prepared to reduce or change activities that are not providing the value hoped for. The programme will have to also consider achieving a balance between providing tangible outputs (such as a toolkit for use across many more universities) and other important outcomes such as altering the culture around research in some universities. The programme team should consult DFID if and when they would like advice on this. / Evaluation – In addition to the existing monitoring activities in place, an independent evaluation of the programme is required. Given the value of the programme and its potential importance beyond the DRUSSA participants, an evaluation would help to draw out the key challenges and successes of the programme. A recommendation of this review is therefore to progress discussion on the aims, scope and timescales of programme evaluation. / Case studies – As mentioned under WP 4, the partners should consider whether case studies could be developed to reflect different models of developing and maintaining research uptake capacity in universities. This could involve taking a small selection of universities from different countries with different characteristics, such as size and sectors that they cover, and exploring their development and lessons learnt. This could be useful for non-DRUSSA universities when considering their development, so active dissemination of this would need to be planned. How this may tie in with an independent evaluation could be explored. / Sustainability - The review team welcome the focus DRUSSA has on sustainability and would encourage them to continue to prioritise this. As discussed above, and by the programme team, the potential for rooting more training within the universities should be explored. The review team can understand the drive to get Research Uptake Management recognised as a profession however they do have some concerns that expertise in Research Uptake Management will need to be firmly rooted in strong research management. We would therefore suggest that the team considers whether getting Research Uptake into the Research Management agenda might be a more sustainable approach than setting up separate support structures.

8. Review Process
The review was carried out by Kate O’Shea and James Rushbrooke from the Evidence into Action team. This involved the following activities: / Attendance at the DRUSSA Symposium, 18-19 September, Nairobi. / Participant of the DRUSSA Advisory Panel meeting - Friday 20th September / Meetings with the DRUSSA team in Nairobi September 21st (ACU, OSD) and 23rd September (CREST). / Informal discussions with symposium participants / Questionnaire (via email) to selected DRUSSA symposium participants / People involved in group discussions, email correspondence or individual discussion: / Mr Vincent Ankamah-Lomotey (Kwame Nkrumah University of Science and Technology) / Professor Shaun Pather, Head Strategic Initiatives, Cape peninsula University of Technology (CPUT) / Professor Pamela Mbabazi, Mbarara University of Science and Technology / Professor Johann Mouton, CREST / Dr Nelius Boshoff, Lecturer, CREST / Dr Sara Grobbelaar, Lecturer, CREST / Diana Coates, Team Leader, OSD / Caite McCann, Information management specialist, OSD / Dr John Kirkland, DRUSSA Director, ACU / Karrine Sanders, DRUSSA Progamme Manager, ACU / Richard Middleton, Commonwealth Scholarship Commissioner, Interim Head of Resources and Planning, Kingston University and consultant to DRUSSA / Nick Scott (ODI) / Ellen Bortei Doku-Aryeetey (University of Ghana) / References: / The following documents were reviewed during the review process / 2012/13 Annual Review / Campus Visit Reports / Benchmarking Summary / Business Case / Risk Analysis / Theory of Change / Logframe / DRUSSA site (www.drussa.net) / Quarterly Reports (Oct-Dec 2011; Jan-Mar 2012; Apr-Jun 2012; Jul-Sept 2012) / Terms of Reference for the Annual Review / Digital Engagement Strategy / M&E Framework / CREST Case Studies