Project Completion Review
DFID Pakistan: Sub-National Governance Programme (SNG)

Title: Sub-National Governance (SNG) programme
Programme Value: £38.1 million (of which £29,199,737.85 disbursed as of 30 May 2018, and a further £951,336 is forecasted for FY 2018. Total expected spend by the end of the programme: £30.2 million)		Review Date: 12-22 March 2018
Programme Code: 202367	Start Date: World Bank (WB) Externally Financed Output (EFO) start: 2012; Oxford Policy Management start 8 April 2013	End Date: 31 May 2018

Summary of Programme Performance
Year	2014	2015	2016	2017	2018/PCR
Programme Score	A	A	A+	A+	A
Risk Rating	Severe	Severe	Major	Major	Major

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202367/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202367/documents/

A. Summary and Overview

The Sub-National Governance programme (SNG) invested £30.2 million over 5 years (2013-2018) to support provincial and district governments in Khyber Pakhtunkhwa (KP) and Punjab improve the delivery of basic services, in particular, health and education. The programme worked to strengthen provincial and district level public financial management (PFM), planning and performance management capability to enable efficiency savings and ensure a more productive and needs-based allocation of resources for improved basic service delivery. In addition to operating with provincial Governments, the programme worked in 12 districts: 6 in KP and 6 in Punjab.

SNG has four outputs:
1. Public financial management and planning systems improved: supporting the delivery of reforms to the budget process, including evidence-based budgeting, transparency, allocation and execution.
2. Devolved systems, processes and budgets better focused on service delivery: facilitating the transition to new local government systems and structures, and supporting the development and alignment of Annual Development Plans (ADPs) around population needs.
3. Innovation supports sustainable service delivery: establishing the District Delivery Challenge Fund (DDCF) to finance innovative service delivery pilots, and rolling out Geographical Information System (GIS) technology to improve evidence based policy making.
4. Strategic oversight of delivery improves performance in priority areas: building the capacity of units in the centre of government to track performance of key priority areas and remove obstacles to delivery.

Oxford Policy Management (OPM) was the lead implementer for the programme, working across all outputs, and managed Coffey International to deliver on the Innovation Challenge Fund (output 3). The programme separately financed the World Bank (2014-2016) on three Externally Financed Outputs (EFOs) and provided a conditional grant to the government of KP (2012). Towards the end of the programme two additional contracts were signed, one with Sarhad Rural Support Programme (SRSP) on school reconstruction and another with Delivery Associates (DA; 2016-2018), to support the delivery of output 4 in Punjab. Overall the programme is assessed as having demonstrated very good value for money (VfM) and the performance of the contract with OPM is particularly commended.

Key achievements (2017-18)
Output 1: Public financial management and planning systems improved
- Strong inroads made in enhancing the PFM capacity of KP and Punjab governments, and embedding learning. Overarching PFM Reform Strategies in KP and Punjab have set clear priorities for reform and oversight and implementation mechanisms have been established to enforce them.
- Budget transparency index scores have substantially improved in both provinces, with citizens’ budgets now regularly published and year end reports published for the first time by the Government of KP (GoKP) in 2017, marking an important step towards improved accountability.
- Revenue generating capacity has increased and efficiency savings made in both provinces, through better planning and processes. In Punjab, SNG supported the Finance Department to save PKR 1.820 billion and establish a tax survey identifying 25,000 additional taxpayers. In KP an SNG-funded tax survey piloted in 3 districts identified the potential for tax collection on services at almost 10 times the revenues currently collected.
- Planning processes are more robust, improving budget preparation and credibility, with efforts in place to look more at the quality and accountability of the process going forward. In KP, alignment between the ADP and Integrated Development Strategy priorities (IDS) has increased from 75% (2014/15) to 94% (2016/17). In Punjab, ADP formulation was amended to include a mandatory consultation process with all stakeholders.

Output 2: Devolved systems, processes and budgets better focused on service delivery
Roll out of needs-based budgeting is an important step towards improved efficiency, transparency and accountability in district budget preparation and allocation. In Punjab, the needs assessment process for primary healthcare budgets identified issues of inadequate budgeting, resulting in an increase in non-salary budgets in 4 districts over the review period. In KP, pre-budget consultations led to over 330 developmental projects (worth PKR 593 million) prioritised and incorporated in district ADPs for 2017-18.
- SNG-supported calculation of Provincial Finance Commission (PFC) Awards is a major achievement for improved equity and empowered local government. In Punjab, the share of ADP allocated to poorer districts increased from 16% to 36% through the process. District Education Authorities (DEAs) received a 19% increase in transfers and District Health Authorities (DHAs) a 37% increase. In KP, health facility budget tracking led to a 41% increase in allocations to health budgets in 6 focal districts given the identification of funding gaps. These increases were within the overall budget allocations to the provinces concerned.
- Instrumental TA provided during the review period to the rules, regulations and guidelines defining the nature of local government transition.

Output 3: Innovation supports sustainable service delivery
SNG’s challenge fund pilots from round II were scaled up vertically and horizontally and effectively demonstrated their ability to improve service delivery in a sustainable manner. In Punjab, 7 pilots directly benefited 1.5 million people (over 50% women) and in KP, 7 pilots benefited 1.6 million people directly and indirectly, both on health and education outcomes.

Output 4: Strategic oversight of delivery
- Special Monitoring Unit (SMU) and Strategic Support Unit (SSU) both successfully unblocked reform challenges in the priority sectors. DFID’s education and health teams have confirmed a number of instances whereby heightened attention on specific reform agenda items has expedited delivery in both provinces.
- While the SMU in Punjab was established from the Government of Punjab’s own budget (and consequently appears more sustainable), the SSU in KP was funded with DFID support and was not fully institutionalised. The SMU was mentored using international deliverology expertise while the SSU focused on learning from doing. The two delivery units have had different approaches from the beginning with the Punjab SMU focusing on targeted reforms in a few sectors and the KP SSU focusing on the wider priorities of the Chief Minister.

Operating context and challenges
An assessment of the programme’s progress must be made in the context of the operating environment. The country’s political economy, dominated by a narrow business and political elite, has contributed to exclusionary economic policies and the marginalisation of the poor. Whilst the bureaucracy functions, there is a need for better strategic capacity and more focus on results, inclusion and accountability. While the level of need is high, internal resource generation is low. Therefore, pushing forward governance reforms to promote transparency and accountability are as much a political, as a technical endeavour. It also reinforces the necessity of establishing formal structures, processes and checks and balances for the raising, allocating and managing of public finances to counter the informal influences of the political landscape.
The programme was designed following the 2010 18th Amendment to the Constitution, which involved the transfer of significant federal powers to the four provinces, including enhanced provincial responsibilities for delivering basic services, and the formation of local governments. While the devolution of provincial powers moved forward (including around basic services), the formation of local governments (including the devolving of authority and responsibility for basic services) lagged. It occurred only in 2015 in KP and 2017 in Punjab, and even then there remained discrepancies between theory and practice and the nature of local government devolution differed across the two provinces. This resulted in the delayed implementation of output 2 and differences in the pace and nature of the roll out of activities in the two provinces.

Assessment of sustainability
SNG led reforms are at different stages of institutionalisation along the spectrum of ‘demonstration’ (programme leads on reform implementation), ‘replication’ (government takes over leadership/scales up reform, with some programme support) to ‘adoption’ (full government ownership and lead; reforms embedded through legislative/financial/organisational means) - see annex I. This process takes time and the short period of implementation in some areas naturally affected their level of progress. It will be important that a future programme identifies the differing advancement of SNG-initiated reforms, to ensure that SNG investments and government progress is not lost.

The elections, scheduled for mid-2018, could pose a threat to the sustainability of some programme activities. With an election comes the potential for a high turnover at the top of provincial and district governments, the key beneficiaries and partners in this programme. SNG has worked hard in its final years to institutionalise the reforms it has supported and ensure the transfer of learning and ‘ways of working’ to a broad audience. However, there are likely to be setbacks, particularly in those areas which have been built upon relationships (such as the SMU in Punjab and SSU in KP), or where activities are in their early stages, in particular the devolution of powers to local governments. These challenges are balanced by the opportunities which the new provincial governments may provide and SNG II shall be well-timed and well-placed to avail of those new opportunities.

Assessment of Inclusion
SNG, in particular the TA team, made deliberate efforts to ensure that the inclusion objectives of the programme (that the poor, women and vulnerable groups are included and supported through the reforms) were realised in practice. Some positive examples include:
- The development of the first Punjab Women’s Development Policy 2018, now approved by the provincial cabinet. This is a major milestone.
- The needs-based PFC Award formula for transfer of funds to new local governments in KP and Punjab, promotes equalisation/equity among districts and genders by taking into account issues of population, per-capita expenditure and fiscal needs in different districts – ensuring the poorest districts are adequately resourced.
- Local needs-assessment and provincial pre-budget consultations in both provinces broaden engagement beyond the educated elite.
- Dedicated page on women and girls in citizens’ budgets.
- Training of provincial and district government officials on improved planning processes, including gender-sensitive and pro-poor development planning.

These inclusion achievements are to be commended and this targeted focus should aim to be more ambitious in the next iteration of the programme. The programme will need to continue to interrogate its methods (i.e. online polls vs. more traditional media) and channels of engagement (universities vs. local community centres/markets) as consultation processes mature. It will also be important that an emphasis is put not just on the participation of women, the poorest and vulnerable groups, but substantive, quality engagement that follows through to implementation.

Overall Output Scoring

Log frame output	Punjab	KP
Output 1: Public financial management and planning systems improved (30%)	A
1.1 Institutional capacity of government departments in public finance	A	A+
1.2 Improvement in Provincial Open Budget Index (OBI) score	A+	A+
1.3 Availability of resources to finance services	A	A
1.4 Strengthened provincial planning processes	A	A+
Output 2: Devolved systems, processes and budgets better focused on improved service delivery (30%)	A+
2.1 District budgets based on evidence of peoples’ needs	A	A+
2.2 Improved flow of funds to districts and service delivery units	A+	A
2.3 Strengthened capacity of local governments to deliver services	A+	A+
Output 3: Support innovative experiments, some of which sustainably improve service delivery (30%)	A+
3.1 Service improvement pilots are evaluated and successful pilots are adopted by provincial governments	A+	A+
3.2 Government uses GIS to monitor and plan quantity and quality of services	A	- [1]
3.3 Rectification of construction flaws in schools	-	A
Output 4: Strategic support improves performance in priority areas (10%)	B
4.1 Support to equip the SMU with the knowledge and skills in the ‘delivery’ approach	B	-
4.2 SMU builds the capacity of departments to effectively implement roadmaps	A	-
4.3 Ensure transition towards the 2018 vision for selected roadmaps	B	-
4.4 Progress in priority sectors monitored and assessed against established timelines	-	A
4.5 Stocktake routines to keep political leadership informed on the status and issues of progress in priority sectors	-	A
4.6 Knowledge management routines established and Strategic Support Unit's sustainability options agreed with government	-	A
4.7 SSU's sustainability options discussed and agreed with the government	-	B
[1] KP GIS activities were rolled out in previous years

Overall programme score (2017-18): A+

In the final year of the programme SNG consistently met and exceeded expectations against the logframe. Particular emphasis was placed on implementing the exit strategy (June 2017 to May 2018), which involved extensive measures to transfer knowledge, documentation and ownership of key processes and structures to provincial and local government. However, not all reforms have been fully institutionalised and further investment and TA support will be needed under SNG II (in particular around the newly devolved local government structures and processes), to safeguard SNG investments in the long term. The area that continues to receive mixed performance scores is output 4 on delivery units in both provinces. In both provinces, the delivery units were mentored or supervised by strong personalities and these relationships worked well: however, this also puts into question the sustainability of these units once these relationships are not there in the post-election administrations. Delivery units are not a solution for all governance challenges and work best under specific conditions including very strong political involvement; a relentless focus on targeted results; strong and reliable data collection and use; and dedicated teams to identify and remove bottlenecks in the delivery of results. There was strong performance on delivering roadmap goals in both provinces; the logframes did not allow for the complete assessment to be reflected in the ratings. Issues of ‘defining success’ and getting the balance right between plugging gaps vs. building long term capacity continue to create challenges for assessing performance.

Section C on ‘theory of change and progress against outcomes’ provides an assessment of the overall impact of the programme. The conclusion is that there is a high likelihood of improved access to, and satisfaction with, government health and education services, given: increase in pro-poor and sector-targeted allocation levels; improved prioritisation and efficiency of these allocations; combined with effective performance oversight of funds disbursed. However, the extent and nature of the impact cannot be accurately assessed, given there is no indicator data available at outcome and impact level.

The lessons learnt and recommendations for future programming are outlined below and developed within section B.

Lessons learnt
Overall
SNG has demonstrated that supporting provincial and district governments to better raise, allocate and manage their resources has clear spill over benefits for basic service delivery. For example, the SNG-supported needs based intergovernmental fiscal transfer formula in Punjab contributed to a 37% increase in budget allocations for health and 19% for education. In KP SNG’s support for their equitable resource distribution formula meant that the poorest districts received increases in funding. Such advances can then in turn be capitalised on by DFID Pakistan’s basic service programmes, which can focus on the quality, equity and efficiency of the public investment.

Using an ‘adaptive programming’ approach throughout the programme lifecycle enabled SNG to improve how, and on what, it worked. Capitalising on its own technical expertise and using its close relationship with provincial governments, it was quick to identify emerging reform priorities and learn from its own delivery experience to course correct and adapt. For example, SNG effectively adapted phase II of its challenge fund to learn from its experience in phase I. As a result, it was able to achieve better results and sustain its contribution to the government.

Cross-DFID partnership is not a given and requires significant effort to leverage and sustain. Over the course of the programme there was a lot of information sharing by SNG with other teams and some good examples of advisory and implementing partner relationships. However, there have been areas of (perceived) overlap and missed opportunities. Suggestions for future programming are developed in the recommendations section.

Technical level
SNG ‘worked politically’, regularly balancing the technical and political, to drive forward reforms. SNG recognised the importance of working politically to build ownership, sustainability and long term buy-in, both within the bureaucracy and with senior politicians. It relied on its experienced team and strong linkages with government to understand the operating context and where it did and did not have traction for reform. SNG, on occasions, delayed the ‘technical’ to spend time building political buy-in, particularly at the beginning of the programme. This combination of strong constructive relationships, politically aware engagement and flexible technical assistance put SNG in a position to effectively shape and accelerate reforms, as opportunities arose and political appetite increased. But the centrality of government buy-in to drive forward and embed reforms was clear in the case of Punjab, which lagged behind on its reform agenda until a change in finance minister. Punjab’s Chief Minister’s support was fundamental to the effectiveness of the deliverology approach that Delivery Associates provided technical assistance on.

Establishing formal guidelines, strategic plans and processes and making budgetary documents publicly available helps lock in reforms for the longer term, making reforms less easy to reverse, when political conditions shift. For example, budget transparency reforms have become mandatory in provincial governments and have now been taken on at a national level, with Pakistan joining the Open Government Partnership. As public expectations shift in terms of what they can expect from the government, for example the publication of citizens’ budgets and end of year expenditure, the government will find it harder to backtrack.

Closer coordination between demand and supply side interventions was needed. Whilst SNG focused on the creation of forums for dialogue between government and citizens (i.e. budget consultations and presentation of citizens’ budgets) there was not a commensurate effort by SNG to ensure that civil society could productively engage in these forums to strengthen the accountability process. Whilst there were efforts to make linkages between SNG and DFID Pakistan’s AAWAZ programme[2], (and a willingness to partner by AAWAZ), these never fully materialised. Weak local governments, long standing suspicions around community level engagements and weak incentives for stakeholders were some of the reasons for this limited coordination between implementing partners, which provide lessons for the upcoming programmes to address.
[2] DFID Pakistan’s demand side programme working in all districts across KP and Punjab to strengthen citizen voice and government accountability.

Peer to peer exchange visits can improve dialogue, learning and synergies between provinces.

The push for ‘institutionalisation’ in the exit strategy was unrealistic for nascent community level reforms that require behavioural change, which challenge existing social norms.

The success of the SNG challenge fund (in particular round II) lies in its approach that ensured the provincial governments ‘adopt’, not just ‘endorse’, the pilots. The challenge fund allowed district level service delivery departments to: a) demonstrate their capacity to the senior layers of bureaucracy, which is often questioned under local government devolution; b) test-out technology-driven high risk innovations using ‘big data’ to ensure efficiency gains were made through better planning and allocation; and c) demonstrate results in pilots, for which, theoretically, the provincial governments had funds but avoided investing due to high risk. The result: wide-scale adoption and scale up by district and provincial government.

Avoiding mission creep and overstretch in delivery units needs to be closely monitored. During implementation both delivery units were burdened, at times, with the management of ad-hoc special initiatives. While this was managed well, it required close supervision and support to implementing teams by DFID. In Punjab, for example, DFID and DA, through working together, were able to support SMU in prioritising additional dedicated staff for the roadmaps. Another important concern is keeping the inherently political nature of these delivery units in mind as while this high-level political involvement provides drive for reform, it also creates friction with line departments due to increased accountability. It requires considerable political acumen on the part of bureaucrats and advisers to navigate the reform process.

Programme management level
SNG’s choice of indicators made it hard to measure overall impact and outcome. These included data sources which were not revised frequently enough to be viable indicators for the purposes of programme monitoring – i.e. out of sequence with the Annual Review cycle. This was a recommendation arising from several of the Annual Reviews but not resolved. The chosen indicators had no data available for 2017/2018 and several had a time-lag of two years. While the unsuitability of the outcome indicators was flagged in the 2015, 2016 and 2017 Annual Reviews and in the Mid Term Evaluation Report, the problem was never rectified.

The commitment, dynamism and experience of the technical assistance (TA) team was a significant contributing factor to the success of SNG. This is also a testament to a strong recruitment process. It also helped that several in the TA team came from the civil service, bringing not only local networks, but importantly, a nuanced understanding of local structures and ways of working. However, the TA team was also staffed with those from a private sector or academic background, bringing a diversity of views to the table. The result observed by the review team: strong constructive partnerships between the contractor and provincial and local government.

It is important to get a balance in the logframe between ‘product’ outputs and those that address the issue of the quality and credibility of these products. There was a heavy emphasis in SNG’s logframe on indicators focused on the production of documents rather than the quality and impact of those products and their institutionalisation. For example, on Open Budget Index (OBI) indicators, it would have been useful to assess also the ‘completeness of documentation’, rather than just the publication of documents, or track government ownership and leadership on key budgetary processes. Additionally, demand side assessments such as community score cards, control districts and perception surveys, may have helped capture the perception and/or impact of the reforms themselves.

Measuring success: challenge fund pilots should be assessed through their sustainability and impact on long term government policy, not just through completion. Although SNG pilots did meet the test of sustainability and responsible exit, especially in phase II, the logframe does not adequately capture it. Over the years, it focused primarily on managing and closing the funds rather than their contributions to effective service delivery. SNG decided to not continue with challenge funds after round two in order to evaluate the lessons from the first two rounds. During the next phase of SNG, DFID should also consider pre-programme consultations with all stakeholders to ensure that there is a clear understanding about the programme’s scope of work.

Phase II of the project should also consider building in sustainability indicators to track the progress of key initiatives supported through phase I.

DFID’s investment in delivery units needs to be managed, implemented and monitored more effectively as part of the SNG programme. The two units were managed through separate logframes, which were poor quality, in part due to changes in strategic vision by the SMU and a resistance to some of the original indicators, and not linked to the overall logframe for the SNG programme. In addition, whereas DFID’s provincial health and education programmes leveraged the political clout of the delivery units to unblock reform obstacles regularly, the contribution was not assessed, linked or reported through the SNG programme in a structured and regular manner. Greater coordination between the different strands of TA working on health, education and governance reforms could have resulted in a clearer sense of which organisations had achieved what, and given rise to opportunities for further synergies.

In Punjab, the ambition in the exit strategy to transition all roadmaps was unrealistic for nascent roadmaps like water and waste management given the limited timeframe of the contract. There is a need to keep the focus on a smaller number of roadmaps rather than spreading too thinly and sustainability measures need to be based on on-the-ground realities and achievable in the stipulated time.

Recommendations for future programing
The ‘How’
Invest in local government, who are at the coal face of decentralisation and improved service delivery. Capacity at the lowest levels of government remains particularly weak and further work is needed. It will be important to establish what reforms have been embedded and which have not, and the local capacity to deliver them, before pushing forward with further reforms.

Accountability, oversight and sustainability mechanisms should be integrated into the programme from the start. Policy and budget preparation requires an oversight and accountability dimension to be able to fully assess the overall effectiveness and credibility of the management of public finances. Whilst the oversight and accountability angle is harder to sell to governments and requires building trust, it should be part of the conversation from the beginning and planned into logframes.

1. Ensure incentives and structures to partner across DFID sector and governance programmes is built in from the outset. This could include:
  1. Mandating the development of a framework for partnership in the inception phases of the new AAWAZ II and SNG II programmes, which could be monitored in future Annual Reviews.
  2. Using DFID convening power to regularly bring together implementing partners working on similar thematic or regional areas for ad hoc deep dives.

Consider indicator choices carefully. (1) Measurability: Avoid those with a time lag and which are not easily and/or regularly assessed. (2) Programme processes vs. Government actions: explore gearing more indicators towards government actions and behaviours, rather than the programme’s own processes and products, to help build in sustainability. It may help to have a more developed theory of change on how institutionalisation occurs, to enable charting the desired progression of reforms.

Better define what success looks like for DFID’s investment in the delivery units. Given that the value of DFID’s investment in delivery units is not limited to the SNG programme, it is important to take a broader perspective on defining success. This could consider a number of factors including: buying access, unblocking ‘tangible’ reform blockages and long and short-term investment in capacity building. Finally, regularly review the balance of DFID investment in delivery units versus priority departments’ own monitoring capabilities. Whereas delivery units no doubt effectively fill an urgent gap, it is important to ensure a balance between plugging gaps and building long term capacity.

SNG II should build on the success of phase II of the Challenge Fund. The methodology for phase II has shown strong results. In the next generation of programming, the challenge fund should continue to ensure selected innovations are in line with government priorities to increase the probability of scale up and to avoid a distortionary effect in the allocation of government resources. The innovations should also try to use e-solutions, where possible, to capitalise on efficiency gains and build on the success of these types of interventions in round II.

The ‘What’
Integrate demand-side accountability. Future programming should consider having a more incorporated demand side component, even if it has to be managed separately. Ideally the demand side function would sit within the programme – perhaps in SNG II there may be opportunities to explore this through the Challenge Fund - but where that is not possible it is important that efforts are made to incentivise joint working (see recommendations on cross-DFID partnership).

Pivot from preparation and transparency to execution and oversight. Work with internal and external audit and provincial parliamentarians and concentrate on the rigour of execution reporting to improve the overall credibility of the budget cycle. SNG has done a lot of very good preparatory work, but it is important to now focus on the quality of its implementation.

Focus on the sharp end of PFM. Concentrate on those areas of PFM that are more sensitive but impactful. SNG1 built a critical mass of relationships; it is now time to leverage these though many of these shall change with new administration, especially in Punjab. For example, consider engaging on areas that begin to address potential mismanagement and wastage within the system: such as government procurement and fraud units and departmental performance and expenditure reporting. On tax, the focus should be on ‘tax for development’ objectives, which require a closer look at ‘tax for what’ and ‘tax mobilisation how’ to avoid regressive implementation and to maximise pro-poor allocation.

Needs based budgeting should be part of a process, which should include community monitoring of activities and government reporting back to communities on performance against expenditure throughout the year. In addition to AAWAZ, consider linkages to democracy programming at the local level as engaging citizens in budgetary processes and holding elected officials to account is vital.

Follow up actions required:

(All recommended actions completed prior to PCR approval. Team considering how to apply lessons learned into SNG II). [3]
[3] Actions included asset disposal, implementation of recommendations from Internal Audit, the external audit of OPM, implementation of the exit strategy, and PCR lesson learning and recommendations for SNG II.

Acronyms List

AR	Annual Review		OBI	Open Budget Index
ADP	Annual Development Plan		OPM	Oxford Policy Management
BHU	Basic Health Unit		P&D(D)	Planning and Development Department
BTR	Budget Transparency Reforms		PFC	Provincial Finance Commission
CDIP	Consolidating Democracy In Pakistan		PFM	Public Financial Management
CFU	Corporate Finance Unit		PHC	Primary Health Care
CSSF	Conflict, Stability and Security Fund		PHFMC	Punjab Health Facilities Management Company
DA	Delivery Associates		PITB	Punjab Information Technology Board
DDCF	District Delivery Challenge Fund		PKR	Pakistani Rupee
DDP	District Development Plan		PLSM	Pakistan Living Standards Measurement
DEA	District Education Authority		PMRU	Performance Management Reform Unit
DFID	Department for International Development		PPA	Partnership Principles Assessment
DHA	District Health Authority		PRA	Punjab Revenue Authority
DLI	Disbursement Linked Indicators		PPIF	Punjab Population Innovation Fund
DMU	Debt Management Unit		RHC	Rural Health Centre
EFO	Externally Financed Output		SDG	Sustainable Development Goals
FATA	Federally Administrated Tribal Areas		SDPF	Strategic Development Partnership Framework
FD	Finance Department		SMU	Special Monitoring Unit
FMIS	Financial Management Information System		SNG	Sub-National Governance programme
GIS	Geographical Information System		SSU	Strategic Support Unit
GoKP	Government of Khyber Pakhtunkhwa		SRSP	Sarhad Rural Support Programme
GoP	Government of Pakistan		TA	Technical Assistance
GoPb	Government of Punjab		TPU	Tax Policy Unit
IDS	Integrated Development Strategy		VC/NC	Village Councils and Neighbourhood Councils
IDU	Internal Delivery Unit		VfM	Value for Money
KP	Khyber Pakhtunkhwa		WB	World Bank
NFC	National Finance Commission		WBI	World Bank Institute
OBB	Output Based Budgeting

## B: DETAILED OUTPUT SCORING

Output Title	Public Financial Management and planning systems improved
Output number per LF		1	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

Indicators	Milestones 2018		Progress
1.1. Institutional capacity of government departments in public finance	Punjab	Performance management system for at-least one specialized unit (Tax Policy Unit, Debt Management Unit & Corporate Finance Unit) established and implemented.	A: Met. Performance management system developed and implemented for Debt Management Unit (DMU), with the first performance review due to be completed in June 2018.
	KP	Government initiates implementation of PFM Reform Strategy	A+: Exceeded. Government approved and launched provincial PFM Reform Strategy in July 2017. First-year action plan (2017/18) of PFM Reform Strategy prepared and being implemented by the Finance Department (FD). By March 2018 implementation of 45% of strategic interventions was ongoing with support from SNG and other donors.
1.2 Provincial Open Budget Index (OBI) score	Punjab	At-least 50% of the Budget Transparency Reforms (BTR) institutionalized by FD, GoPb. / BTR Assessment Checklist and Manual developed and officials trained	A+: Exceeded. Finance Department institutionalised and adopted 66% of the Budget Transparency Reforms (BTR): 1. Citizens' budgets; 2. Debt bulletins; 3. Medium Term Fiscal Framework; 4. Year-end reports. / Institutionalising initiatives include: / i) revision/updating of Punjab’s Budget Manual, to reflect budget transparency measures; / ii) development and handing over of checklist, guidelines/toolkit, and a manual on BTR; / iii) training of Finance Department officials on BTR
	KP	Open Budget Index (OBI) Score sustained at 66	A+: Exceeded. OBI score of 66 sustained and budget transparency reform initiatives maintained. End of Year report published for the first time in 2017 (for FY 2015/16)
1.3 Availability of resources to finance services	Punjab	Revenue mobilization plan developed and shared with government for implementation	A: Met. Medium-term revenue mobilisation strategy developed. GoPb has submitted a formal request to the World Bank to obtain a loan/Technical Assistance of US$100 million to support implementation of the plan.
	KP	Government approves recommendations on revenue enhancement for implementation	A: Met. Government approved revenue mobilisation proposal and its main recommendation on revising indexation of existing tax rates based on inflation trends.
1.4 Strengthened provincial planning processes	Punjab	ADP Formulation Strategy approved by Planning & Development Department. Also, duration of planning cycle lengthened to strengthen planning process	A: Met. The ADP Formulation Strategy FY 2017/18 and FY 2018/19 approved by P&D Department and Chief Minister. Planning cycle lengthened by three months and new process now in use.
	KP	P&D Department capacity to monitor reforms and execution of development budget at decentralised levels enhanced	A+: Exceeded. Quarterly expenditure review mechanisms institutionalised across all districts under deputy commissioners. / SMS-based expenditure tracking system developed and operationalised at Village and Neighbourhood Council level (VC/NCs)

Summary
This output focused on improving the PFM and planning systems of the provincial governments of KP and Punjab through supporting reforms to the budget process, including evidence-based budgeting, transparency, allocation, revenue generation and execution. Overall the pace of reform in both provinces has differed. In Punjab, progress on PFM has been faster due to the leadership of the Minister and the Secretary of Finance. Reforms of Punjab’s planning system are however at a less mature stage, but momentum for reform accelerated towards the end of the programme, under a supportive bureaucratic leadership. In KP, SNG started from a lower base on PFM and planning, but the approval of a PFM Reform Strategy and shrinking fiscal space focused political attention and over the review period 45% of strategic interventions of the Reform Strategy were ongoing. Both provinces made substantial progress in the areas of budget transparency and improved revenue generating capacity.

Key Points
SNG has made strong inroads in enhancing the PFM capacity of the GoKP and GoPb, initiating the institutionalisation of PFM reforms and embedding learning. Achievements include:
- Both provinces drafted and launched updated PFM Reform Strategies, focused on reform priorities, along with implementation and oversight mechanisms. In the case of Punjab, the Finance Department’s Fiscal Policy and Reform Unit now has the mandate to oversee and coordinate reform and in KP (following the 2017 launch) an oversight ‘dashboard’ along with working groups and action plan has been put in place.
- In Punjab, the government has also strengthened critical PFM and planning capabilities through the creation of specialised units in Finance and P&D, funded with government resources and with their own regulatory, performance management and organisational systems.
- In KP, the government has recently rolled out an internal audit policy (June 2017) – the first of its kind in Pakistan - and set up a number of internal audit units across its departments, along with a ‘provincial internal audit cell’, intended as a policymaking, regulatory and coordinating body. Audits have recently begun.

Budget transparency has been improved in both provinces with a greater number of budget preparation and oversight documents produced and published.
- Both provinces have begun publishing citizens’ budgets, enabling a broader population (including journalists and civil society groups) to understand the key promises of the budget in a simplified form. Pre-budget consultations have become mandatory and the GoKP has established online and SMS-based opinion polls (with over 1.5 million responses) to gather feedback ahead of finalising the budget. These are critical steps towards facilitating improved accountability.
- SNG also supported the production of mid-year and year-end budget reports and medium term fiscal frameworks (KP published an End of Year report for the first time in 2017 for FY 2015/16). Whilst SNG was heavily involved in drafting and providing TA in the first iterations, the provincial governments have increasingly taken the lead.
- To institutionalise these reforms, budget transparency has been included in Punjab’s regulatory framework; guidelines have been drawn up for the GoKP; and Pakistan has become a member of the Open Government Partnership. But full institutionalisation will require a legislative base and commitment to fulfilling the OGP National Action Plan, which will have a number of fiscal transparency and PFM objectives if approved.
- The challenge ahead will be to concentrate on the quality of the budgetary documents produced, institutionalise their production and ensure mid & year end reports are systematically released to the public, even if they highlight shortcomings in the provincial governments’ performance.

Both provinces have been supported to improve their revenue generating capacity, and make efficiency savings, with the potential to increase it further still.
- In Punjab, SNG supported the Finance Department to increase its fiscal space, realising a saving of PKR 1.820 billion. This included through the identification of 25,000 new taxpayers (using a tax payer survey) and GIS-based analysis to define urban areas for Capital Value Tax.
- In KP, SNG supported the GoKP to establish the provincial tax agency and supported a tax survey pilot in 3 districts, which is planned to expand to the entire province. The survey confirmed that the potential tax on services is almost 10 times the revenues currently collected. The GoKP has also approved a revenue mobilisation plan, which will be implemented in part through a new $50 million World Bank programme on revenue generation. The KP Revenue Authority has gone from zero contribution to the provincial revenue in 2014, when it was established, to providing 56% of all provincial revenue collected in 2016-17 – SNG has played a major role in this.
- Going forward, it will be important to work with the provincial tax agencies to ensure that the implementation of revenue generation strategies is not regressive and that revenues generated are productively reinvested in the provincial budget.

Planning processes are more robust, improving budget preparation and credibility, with efforts in place to look more at the quality and accountability of the process going forward.
- In Punjab, the ADP formulation was changed to place heavier emphasis on strategy to inform the allocation and include a mandatory consultation process. The production of departmental annual reports is now mandatory and 20 out of 34 units prepared, published and disseminated their reports for the last fiscal year. The P&D department has also developed (but not yet rolled out) an ADP Performance Tracking Index, to incentivise and institutionalise a quality budgetary process. Finally, policy guidelines and templates have been used to lead a process of policy formulation in over 10 GoPb departments.
- In KP, SNG supported the GoKP to better align the annual ADP with the medium term Integrated Development Strategy (a medium term planning and policy framework first introduced under SNG in 2013), to ensure resource allocations meet overarching priorities. The GoKP has invested in improved expenditure tracking mechanisms, including quarterly expenditure reviews and an SMS based expenditure tracking system for the VC/NC level. The GoKP recently approved financing[4] to sustain all governance and planning reforms introduced during SNG's lifespan.
  [4] Financing has been secured through Investment, Innovation, Research and Reforms Wing of the P&D Department who have initiated a project document to ensure funding of PKR 360 million.

Assessment of sustainability and responsible exit
With much of the work in its early stages of implementation, it is hard to fully assess how institutionalised reforms have been, but it is clear that the groundwork has been laid for longer term reform. From meetings with the review team it is also clear that there is support among top civil servants for the reforms. The sustainability test will come in the next iterations of the budget cycle under a new administration and how far the guidelines, manuals, processes and rules are operationalised and abided by.

Sufficient time and resources are needed to consolidate, embed and transfer ownership of reforms. The programme developed an exit strategy for June 2017 to May 2018 to systematically transfer ownership and embed reforms. While progress has certainly been made, what is clear is that this is a lengthy process, which requires several iterations of the processes in question and which cannot be measured in terms of simply documents produced, but government actions taken.

Lessons learnt and recommendations for future programmes
The groundwork for reform can be laid in the absence of high level political and/or bureaucratic will, but launching and embedding reform cannot. SNG invested heavily in the early years of the programme in building relationships, working politically, and establishing the technical base for reforms. This combination of strong constructive relationships, politically aware engagement and flexible technical assistance put SNG in a position to effectively shape and accelerate reforms, as opportunities arose and political appetite increased. But the centrality of government buy-in to drive forward and embed reforms was clear in the case of Punjab, which lagged behind on its reform agenda until a change in finance minister.

Establishing formal guidelines, strategic plans and processes and making budgetary documents publicly available helps lock in reforms for the longer term, making reforms less easy to reverse, when political conditions shift. For example, budget transparency reforms have become mandatory in provincial governments and have now been taken on at a national level, with Pakistan joining the Open Government Partnership. However Pakistan needs to now show its commitment by signing and implementing the national action plan under OGP. As public expectations shift in terms of what they can expect from the government, for example the publication of citizens’ budgets and end of year expenditure, the government will find it harder to backtrack.

Peer to peer exchange visits can improve dialogue, learning and synergies between provinces. During the programme, SNG arranged exposure visits to Punjab and Sindh with the GoKP to share experiences and exchange lessons on specialised units, revenue mobilisation reforms and devolution. The result was a more effective and healthy competition and collaboration between Punjab and KP.

Recommendations for future programming
Sustainability should be built in as an objective from the beginning, with indicators geared towards government actions and behaviours, rather than just the programme’s actions on reform. It may help to have a more developed theory of change on how institutionalisation occurs. Charting the progression of reforms from initial ‘demonstration’ (with heavy programme involvement) to ‘replication’ (where the pilot/initiative is scaled and/or applied with grater government ownership) to ‘adoption’ (where there is full financial, technical and organisational ownership of the process and product).

Accountability and oversight mechanisms should be integrated into the programme from the start. Focus on policy and budget preparation is important, but a programme needs to be assessing quality and budget execution to be able to assess the overall effectiveness and credibility. Whilst SNG has made significant headway in reforming preparatory processes within provincial (and district) government, it has only been towards the end that there has been an emphasis on the implementation and execution of these processes. Whilst the execution and accountability angle is harder to sell to governments and requires building trust, it should be part of the conversation and plan from the beginning and planned into logframes.

Output Title	Devolved systems, processes and budgets better focused on improved service delivery
Output number per LF		2	Output Score	A+
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

Indicators	Milestones 2018		Progress
2.1 District budgets based on evidence of peoples’ needs	Punjab	Evidence based budgeting adopted by the newly established District Health Authorities in all 6 SNG districts	A: Met. Evidence–based budgeting used in development of primary healthcare budgets (FY 2017/18) in all six districts. Evidence gathered through pre-budget needs-assessment consultations, ‘big data’ from challenge fund health projects and improved reporting systems. / In early stages of implementation but on track to adoption if commitment remains.
	KP	Six district budgets (FY2017-18) prepared based on needs	A+: Exceeded. Six focus districts prepared FY 2017/18 budgets using processes designed to gather and assess needs. / The GoKP was also supported by SNG to provide District Development Plan (DDP) guidelines to help districts prepare medium-term development plans. An inter-governmental devolution support committee has been established to embed implementation of the DDPs.
2.2 Improved flow of funds to districts and service delivery units	Punjab	The PFC makes recommendations to Government for regular PFC Award, under Provincial Local Government Act 2013 on the basis of evidence of fiscal needs.	A+: Exceeded. PFC Award recommendations agreed – under leadership of Finance Minister – including an equity-based formula for regular transfers to local governments. / In April 2018 the Government of Punjab approved the PFC Award, which will now formally be notified within the 2018-19 Budget. This replaces the ‘interim PFC Award 2017’ and will run for 5 years.
	KP	Facility based budgets prepared for 219 service delivery units in 6 focus districts	A: Met. SNG supported district government to introduce facility-level health budgets, covering 219 health service delivery units (172 Basic Health Unit (BHU) 28 Rural Health Centre (RHC) and 19 civil hospitals) in focal districts. The service delivery units are now visible on the FMIS, enabling the GoKP to better track how funds are disbursed. The result, a 41% increase in health budgets in 6 focal districts given the identification of a gap in medicine funding.
2.3 Strengthened capacity of local governments to deliver services	Punjab	Capacity gaps of local government (District Health Authorities (DHAs)) identified and a detailed action plan is developed for addressing capacity constraints on a prioritised basis.	A+: Exceeded. Diagnostic study conducted by OPM on transition to the new local government system. Action plan developed to address issues and recommendations identified to fully operationalise local government DHAs. / Additionally, the Challenge Fund provided 7 district level grants, many on health, further reinforcing the government’s understanding of needs and allocation of resources.
	KP	Government initiates reforms/amendments in the local government system based on an institutional assessment of VC/NCs and district stocktakes	A+: Exceeded. Following institutional assessments of the VC/NCs and districts the GoKP initiated several policy actions (led by chief minister), including: / development of government-owned action plans to remove systematic bottlenecks and undertake second-generation reforms; / an SMS-based expenditure tracking system introduced to track performance of VC/NCs; / district expenditure review mechanisms established.

Summary
This output took a top-down and bottom-up approach to facilitating the transition to new local government systems and structures and supporting improved planning and PFM capacities so that they are better focused on delivering against the population’s needs. SNG supported the provincial governments to establish a series of rules, regulations and guidelines to support the transition to local government, whilst working with districts on assessing needs.

The nature of the provincial-local government arrangement is different in Punjab and KP. The GoKP established Village and Neighbourhood Councils (VC/NCs) in 2015 and devolved30% of the development budget to local governments (i.e. district, tehsil and VC/NC levels[5]). The GoPb created District Health Authorities (DHAs) and District Education Authorities (DEAs) in January 2017 to manage budgets and deliver services. These reforms are in their early stages and there remain questions as to district governments’ ability to effectively absorb, manage and equitably allocate their resources to deliver quality services.
[5] Of this 30%, the division between district, tehsil and VC/NC is 30:30:40 respectively

Key Points
SNG’s support to the roll out of needs-based budgeting is an important step towards improved efficiency, transparency and accountability in district budget preparation and allocation.
- In Punjab, the needs assessment process for primary healthcare budgets identified issues of inadequate budgeting, resulting in an increase in non-salary budgets in 4 districts, helping finance service delivery improvements in areas including: allocation of medicines, maintenance of medical equipment and training for birth attendants.
- In KP, district level pre-budget consultations involved elected local representatives and demand side actors (including from DFID-supported programmes) such as AAWAZ, Alif Ailaan, EVA-BHN and local civil society organisations. According to SNG, on average over 60% of projects in approved district ADPs (2017-18) are from the needs identified through the exercise.

SNG support to the calculation of PFC Awards is a major achievement for improved equity and empowered local government.
- In both Punjab and KP SNG supported the provincial governments to establish an equitable formula for the transparent and regular transfer of funds to local governments. The result: more funds transferred to poorer districts (see graph, for Punjab example).
- In Punjab, the share of the ADP allocated to poorer districts increased from 16% to 36% of total ADP. Additionally, under the Award DEAs received a 19% increase in transfers, DHAs 37% and municipal local governments 164%.
- In KP, SNG’s support to the GoKP on an equitable resource distribution formula and fund flow mechanism was linked to needs-based budgeting and expenditure reporting of health and education service delivery units. The result, evidence of better tracking of expenditure and improved efficiency and prioritisation of allocation.

Capacity of local government (particularly at the lowest levels) remains weak, but SNG has made in-roads on capacity development and oversight and was instrumental in defining the nature of the local government transition.
- In both Punjab and KP, SNG engaged heavily on advising on the drafting of rules, regulations and guidelines to facilitate the transition to the newly devolved structures (in collaboration with DFID’s education programme technical assistance team).
- They have also supported the establishment of expenditure tracking, (such as through the design and roll-out of FMIS software across all local councils in Punjab) and performance management (through the Performance Management and Reforms Unit (PMRU) in KP. KP’s PMRU assesses the performance of districts (and the province) against a set of Key Performance Indicators, which are published online and are the makings of an important accountability function.
- SNG has also invested in capacity building of local government, training 337 district government officials and 287 local government political representatives in planning, budgeting, and the local government system under their District Training Plan in KP alone.

Sustainability and exit
Given the new systems of local government only came into place in 2015 and 2017 in KP and Punjab respectively, the majority of reforms remain in their early stages and are not yet self-sustaining. It will take several years and iterations of the budget cycle to really embed reforms, such as the district level needs assessments, and ensure they move from a theory of participation and accountability to the substantive practice. Similarly, there is only so much that formal training can do, and it will take time for the capacity level of local government authorities to improve. Finally, these reforms fundamentally alter the power dynamic between provincial, district and local government officials and there may still be push back against reforms – especially with elections potentially ushering in new governments, combined with the historical fluidity of local government reform, with 3 different forms of local government trialled in less than 20 years. However, the review team judges that SNG have done what they can, in the time they had, with the annual output milestones they had, to build in sustainability for the future and it will be to the next iteration of the programme to embed it.

Lessons Learnt
Closer coordination between demand and supply side interventions was needed. Whilst SNG focused on the creation of forums for dialogue between government and citizens (i.e. budget consultations and presentation of citizen budgets) there was not a commensurate effort by SNG to ensure that civil society could productively engage in these forums to strengthen the accountability process. Whilst there were efforts to make linkages between SNG and DFID Pakistan’s AAWAZ programme, (and a willingness to partner by AAWAZ), these never fully materialised. A consequence, in part, of no in-built structural incentives for implementing partners to systematically collaborate and share information.

The push for ‘institutionalisation’ in the exit strategy was unrealistic for nascent community level reforms that require behavioural change and which challenge existing social norms. District level consultation takes time and while the review witnessed clear enthusiasm among local civil society and local authorities, there remains much work to move from theory to practice. This means ensuring that participation, when it occurs, is substantive and inclusive, and that typically marginalised voices of women, youth and other vulnerable groups are treated and heard equally.

The commitment, dynamism and experience of the technical assistance (TA) team were significant contributing factors to the success of SNG. It helped that many in the TA team came from the civil service, as not only did they have local networks, they had a nuanced understanding of local structures and ways of working. However, the TA team was also staffed with those from with a private sector or academic background, bringing a diversity of views to the table. The result observed by the review team, was strong constructive partnerships between the contractor and provincial and local government.

Recommendations for future programming
Focus on demand-side accountability. Future programming should have a more integrated demand side component built in, even if it has to be managed separately. Ideally the demand side function would sit within the programme, but where that is not possible it is important that efforts are made to incentivise joint working. For example through: (a) establishing a common indicator; (b) ensuring overlap of districts; (c) ensuring sufficient resources put aside to implement; and (d) having regular and structured information exchange – including at steering committee level.

Needs based budgeting should be part of a process, which should include community monitoring of activities and government reporting back to communities on performance against expenditure throughout the year. In addition to AAWAZ, consider linkages to the Conflict, Stability and Security Fund (CSSF) Consolidating Democracy in Pakistan (CDIP) programme at the local level, as engaging citizens in budgetary processes and holding elected officials to account is an important part of the electoral cycle and effective on civic education.

Output Title	Support innovative experiments, some of which sustainably improve service delivery
Output number per LF		3	Output Score	A+
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Service improvement pilots are evaluated and successful pilots are adopted by provincial governments	Punjab – All of the round 2 pilots closed, audited and financial reports delivered. / Knowledge products produced and used for stronger dissemination. / KP - Round 2 assessment completed and pilots’ handed over to the Health Department	A+: Exceeded. In Punjab - All of the round 2 pilots have been closed and audited. Knowledge dissemination effectively done, including: developing a documentary, a brochure and a position paper on how to use the challenge fund function effectively. / The lessons learnt effectively communicated to government and donor community through a high profile workshop, leading to the lessons being picked up by GoPb and used to design a challenge fund for Punjab Population Innovation Fund (PPIF). / In KP, round 2 pilots were completed, handed over to the Health Department and scaled up by the GoKP through government project approval processes (PC-1 and allocation in ADP). 1 pilot was picked up for Federal level scale-up.
3.2 Government uses GIS to monitor and plan quantity and quality of services	Punjab - GIS intervention evaluated and key lessons shared with government / KP – N/A	A+: Met. In Punjab, GIS technology cells introduced in all SNG districts. Strong documented evidence available on its effective use to improve quality and quantity of service delivery in the target districts. Evidence of government scaling GIS cells vertically and horizontally.
3.3 Rectification of construction flaws in schools	KP - Rectification work completed and handed over to the Education Department	A: Met. In KP, 190 schools rectified and handed over to the Education Department of GoKP.

Summary
This output provided support to innovative experiments, both in Punjab and KP to improve service delivery, with a focus on education and health. This was successfully achieved through a combination of challenge fund grants and support to GIS cells targeted at selected districts in the two provinces, but later scaled up both horizontally and vertically.

Key Points
SNG’s challenge fund pilots were scaled up vertically and horizontally, and effectively demonstrated their ability to improve service delivery in a sustainable manner (Annex III). In both provinces, the scaled up pilots made effective use of e-technology to establish big data, which could be used for better planning and resource allocation, resulting in efficiency gains at the district level.
- In Punjab, 7 pilots directly benefited 1.5 million people (over 50% women) through improved service delivery in health and education. Overall, 6 pilots were endorsed by the GoPb for adoption. However, the government scaled up 2 health pilots itself from round II through a commitment of £11 million, estimated to benefit 1.8 million children and 1 million expecting mothers.
- In KP, 7 pilots benefited 1.6 million people directly and indirectly on health and education outcomes. All pilots were recommended by GoKP for adoption. However, 2 health pilots from phase II were practically scaled up by the GoKP through the allocation of funds in the ADP and approved PC-1. GoKP committed £5 million to these with an estimated benefit to 17% of the provincial population.
- Learning lessons from phase I, round two challenge funds proved to be more successful in terms of scale up, government commitment and sustainability.

SNG’s GIS support to selected districts in Punjab and KP was scaled up both vertically and horizontally.
- In Punjab, the district officials are actively making use of SNG supported GIS technology to make responsive decisions (based on location and gender-disaggregated data). Examples include use of GIS to better target citizens through the Integrated Ambulance Service in Hafizabad and telemedicine in Sheikhupura. The government has successfully adopted the GIS model, as piloted by SNG in selected districts, and scaled up GIS cells to the rest of the province. SNG’s district level interventions have been scaled up, using government funds, to create provincial hubs, including establishment of GIS cells in the Planning and Development Department, Education, PMIU and Punjab Information Technology Board.
- In KP, there is evidence that GIS cells are successfully influencing district level decisions around service delivery, especially health and education. Building up on SNG’s pilot, GoKP is now rolling out GIS interventions to 12 more districts through a PC-I provision (£0.6 million). For vertical scale up, a provincial-level GIS Hub is also in place within the P&D Department, which confirms that SNG pilots in districts successfully demonstrated value and have been scaled up vertically and horizontally.
- It is important to note that the GIS component also led to closure of the implementing partner in KP province for about three months. However, once DFID and OPM were able to explain the usage to Government, the matter was resolved and the partner was allowed to restart its work.

SNG met its target to rectify construction flaws in 190 schools in KP, despite slow progress reported in last year’s Annual Review.

In the early part of the SNG Programme, DFID earmarked £9 million financial aid package for the Government of KP to support reconstruction of damaged infrastructure in remote areas, as defined by the Post Crisis Needs Assessment of 2010. This was a package of support through conditional grants – an expenditure model in which government and donor money was channelled through communities to construct missing health and education facilities. Following the disbursement of the first tranche of £2.5 million in 2013, DFID discovered gaps in management and construction controls.

Continuous audit of Conditional Grants was carried out by Deloitte Pakistan in 2015 which highlighted certain gaps in the construction in its report entitled "Schools’ Survey Report”.
According to the survey, a total of 540 schools were picked that needed construction repairs. 161 schools were rectified by OPM under the SNG Technical Assistance component. The remaining 379 schools were reconstructed through an Accountable Grant of £950,000 with Sarhad Rural Support Programme (SRSP). This work was delivered with the required quality standard and within a very ambitious timeline of ten months by SRSP, thus minimising the reputational risk for DFID. These schools are now handed over to the Government of KP. The Elementary and Secondary Department has subsequently introduced their own conditional grants model, amounting to £51 million, to provide for missing facilities in schools in KP.

Sustainability and exit
Given that SNG completed the challenge fund and district level GIS cells in years 3 and 4 of the programme, the programme completion review is a good time to assess the sustainability of these interventions. There is strong evidence, both in Punjab and KP, that round II grants were replicated and adopted. Government ownership and commitment to use GIS for effective planning and monitoring is already evident in both provinces. The SNG handover has also been responsible with efforts made to institutionalise learning. Focus has been placed not only on knowledge products and training government, but also on securing government buy-in through establishing action plans.

Lessons learnt
The primary success of the SNG challenge fund (in particular round II) lies in its approach that ensured the provincial governments ‘adopt’, not just ‘endorse’, the pilots. SNG learnt this during phase I, which led to it opening up phase II to district level government departments. The challenge fund allowed district level service delivery departments to: a) demonstrate their capacity to the senior layers of bureaucracy (some pilots were scaled up provincially and nationally), which is often questioned under local government devolution; b) test-out technology-driven high risk innovations using ‘big data’ to ensure efficiency gains were made through better planning and allocation; and c) demonstrate results in pilots, for which, theoretically, the provincial governments had funds but avoided investing due to high risk. There is consensus that the challenge fund approach to engage district level government proved to be a huge success (e.g. the Health and Nutrition Innovation Fund under the DFID health sector programme adopted this model).

The success of challenge fund pilots should be assessed through their sustainability and impact on long term government policy at the appropriate level (local or provincial) and not just through their completion. Although SNG pilots successfully met the test of sustainability and responsible exit, especially in phase II, the logframe does not capture it. Over the years, it focusses primarily on managing and closing the funds and did not capture their contributions to effective service delivery. This should be addressed in how challenge fund outputs are assessed in the logframe for SNG II. Phase II of the project should also consider building in sustainability indicators to track the progress of key initiatives supported through phase I.

Recommendations for future programming
SNG II should build on the success of phase II of the Challenge Fund. The methodology for phase II of the challenge fund has shown strong results. In the next generation of programming, the challenge fund should consider exploring fewer, but bolder themes for exploring innovative solutions. The selected innovations should be in line with government priorities to increase the probability of scale up and to avoid a distortionary effect. The innovations should also try to use e-solutions, where possible, to capitalise on efficiency gains. Phase II of the programme should also focus on collaboration with academia. E.g. Lahore University of Management Sciences or Ghulam Ishaq Khan University.

SNG II should be designed with stronger links with other sectoral DFID programmes, not just at the design level, but also throughout the implementation phase. During the implementation phase, DFID Pakistan should use its convening power more effectively to bring together various suppliers working on similar thematic or regional areas. Proposed ways to improve on this could include: a) developing common logframe indicators that more than one programme can contribute to and b) articulating and understanding the added-value of interventions that look similar on paper, through stronger engagement between implementing partners.

Output Title	Strategic support improves performance in priority areas
Output number per LF		4	Output Score	B
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
PUNJAB / 4.1 Support to equip the SMU with the knowledge and skills in the ‘delivery’ approach	13 ‘activity focussed’ indicators are part of the logframe with weak links to the output. The reviewers exercised their own judgement to summarise them as follows: / Institutionalise a strong organisational structure within SMU / Equip SMU with the required skills (trainings, communication strategy roadmap routines)	B: Partially met Note: On the basis of the logframe, it is not possible for the reviewers to assess the performance without making their own assumptions. / SMU is staffed and DA supported performance management system is in use / DA has supported SMU in a number of tools including communication approach, digital dashboards and training dashboards which are ready to be taken up / SMU staff is beginning to lead stocktakes but not yet independently
4.2 SMU builds the capacity of departments to effectively implement roadmaps	Note: The selection of indicators is not strong. / Stakeholder mapping for each roadmap is complete / Leadership development programme executed to build capacity at department level	A: Met. Stakeholders mapping for each roadmap was developed and is regularly updated. Leadership development programme was conducted to build knowledge in other departments in GoPb. 6 mini projects (from different sectors) developed at the end of the programme were nominated by Chief Secretary. Performance of these projects is shared with the Chief Secretary on a monthly basis.
4.3 Ensure transition towards the 2018 vision for selected roadmaps	SMU leads delivery of water and solid waste management roadmaps with no TA support. Internal Delivery Unit (IDU) leads Secondary Health and SMU plays a role on performance RAG (Red/Amber/Green) rating.	B: Partially met Chief Secretary led stocktake routines are in place. However, only Health Department (through IDU) has demonstrated capacity to take forward the approach on its own. Water and Waste Management are still in nascent stages and not ready for a complete handover due to lack of capacity in departments
KP / 4.4 Progress in priority sectors monitored and assessed against established timelines	Collection of information to update status of progress on regular basis and identify issues, if any, for resolution	A: Met. SSU conducted regular spot checks, meetings with the prioritised departments, DFID sector programmes and other key stakeholders, leading to informed policy recommendations for the Chief Minister.
4.5 Stocktake routines to keep political leadership informed on the status and issues of progress in priority sectors	Two rounds of stock takes presentations with political leadership in 6 priority sectors	A: Met. SSU successfully facilitated the stocktakes in 6 priority reform areas with sufficient evidence of unblocking obstacles especially in Local Government, Education and Health.
4.6 Knowledge management routines established and SSU's sustainability options agreed with government	Periodic reports prepared	A: Met. Monthly sector wide reports for priority areas produced on selected initiatives.
4.7 SSU's sustainability options discussed and agreed with the government	Initiation of dialogue with government on various feasible options for SSU sustainability	B: Partially met. The dialogue was initiated and the government is exploring options. However, no agreed plan currently exists on sustaining the unit in the long run (e.g. notification) or commitment from GoKP to support the running costs (salaries) associated with the unit through a recurring budget.

Summary
This output took a top down approach to provide the Chief Ministers of Punjab and KP access to ‘special delivery units’ as a mechanism to expedite delivery of priority reform agendas. These delivery units undoubtedly offered pace, momentum and continuity to the provincial reform agendas, including DFID’s sectoral investments in Health and Education. However, despite several outputs having met expectations set in the logframe, the overall output is nonetheless scored ‘B’ to reflect the seriousness of challenges around this output’s theory of change and measurability.

Delivery units in Punjab (SMU) and KP (SSU) cannot be compared in their design, progress and implementation. Whereas the two units are servicing the same purpose, they differ in their size, structure and experience.
- In Punjab, DFID provided technical assistance to SMU through a third party, Delivery Associates. It was established in 2013, and has over 17 staff members. The SMU model relies heavily on ‘delivery experts’ that are programme management specialists, with strong data analysis, problem solving and stakeholders management skills. Whereas the SNG programme provided technical assistance to SMU through DA, there are also other contractors working exclusively on specific primary health and primary education roadmaps. The SMU staff members are completely paid through funding from the GoPb.
- In KP, DFID funds the costs of 9 local consultants who run SSU as sector specialists and lead on various roadmaps. The SSU was established in 2015 and is not yet notified as a government unit/department. It is a small set up which is entirely supported by DFID at the moment. Whereas the SNG platform is used to transfer the funds to SSU, the output is directly managed by DFID and not through OPM.

Key Points
SMU and SSU both successfully unblocked reform challenges in the priority sectors. Building on the recommendation from the last AR, both delivery units have made progress in documenting considerable evidence in this regard. DFID’s education and health teams have confirmed a number of instances whereby heightened attention on specific reform agenda items has expedited delivery in both provinces.

With DA support, the SMU did support the achievement of significant successes on the secondary health roadmap, and Sir Michael Barber (DA) played a key role in supporting regular stocktakes for all the roadmaps. In Punjab, DFID’s support goes beyond the SMU. The SMU roadmap teams actively support line departments by designing and implementing interventions, setting up data systems, reporting data and running check-in routines which keep the line departments accountable for progress during stocktakes. However, the effort has only produced substantial results with the health and education departments at the time of the review and there are sustainability challenges with the water and waste management departments. This is unsurprising given that the water and waste management roadmaps are so much newer than in health and education: experience from the older and highly successful roadmaps suggests that programmes need significant long-term investment and a slower ‘incubation’ period before they can realistically bed down, garner buy-in, and deliver real change on the ground.

SMU did not demonstrate success in facilitating the capacity building of prioritised departments, which is important for long term sustainability of the prioritised reform agenda. On the other hand, SSU was not expected to do this as part of their logframe objectives.
- In Punjab, part of the challenge with the DA contract was a change in leadership for the SMU which led to a shift in the partnership between DA and the SMU. This also had an effect on the strategic direction set out for the unit overall. As a result, the logframe had to be reviewed line by line and adapted in light of the new context. In an attempt to gain consensus, a number of changes were made to the logframe including, for example, removing indicators to test perceptions about the capacity of departments to handle roadmaps independently.
- In Punjab, there is evidence that the health department (through the Internal Delivery Unit) has improved capacity to take a leadership role in the coming years. It is evidenced by data systems, where staff are able to use data to support established routines driving accountability within the department. The transition is not currently sustainable on water and waste management. This is due to a number of reasons, including the newness of the roadmaps and weaker line department capacity. There is a risk to the sustainability of these roadmaps as sufficient long term capacity was not assessed. The review team judges that the objectives, as outlined in the project documents, were quite ambitious and did not make a distinction between results for newly vs. long-established roadmaps.
- In KP, unlike Punjab, the capacity building of partner departments (e.g. Local Government, Education, and Health) to monitor and report their own performance during the programme life-time is not considered part of the programme objectives. This is a major design weakness, which brings into question the sustainability of the DFID investment, and should be actively addressed in the future. Whereas initiatives like SSU can provide a temporary impetus, this approach is not sustainable unless coupled with complimentary and balanced investment in strengthening the respective government department’s own internal capacities.

Sustainability and exit
SMU and SSU both face sustainability challenges of different natures. The review team considered this from two angles: a) sustainability of the delivery units as organisations; and b) the sustainability of technical investment made in them through DFID. As an institution, SMU is more established than SSU. Given that the staff are paid by the GoPb through a PC-1, it can sustain itself in the foreseeable future. However, in terms of its capacity to deliver, it demonstrates early promise to sustain, without DA, on health and education, but not on water and waste management. SSU, on the other hand, currently cannot sustain itself without donor support on both fronts.
- In Punjab, the review team also concluded that the DA contribution was largely focussed on ‘individuals’ and not on the ‘institution’. This presents additional sustainability challenges to DFID’s investment in SMU’s capacity. For example, DA investment is focussed heavily around the Head of SMU position and individual roadmap leads within the SMU. Over the course of its support, DA adapted its approach and delivered tailored ‘deliverology’ training to a wide set of civil service partners, as well as their targeted support to the IDU in the Primary & Secondary Health Department to broaden the base for its capacity building efforts. However, the challenge with the focus on specific individuals is that whenever positions become vacant, handovers are often ineffective and the learning, therefore, is not passed on. This indicates institutional gaps which are equally important to be addressed. There was also evidence that DA was regularly used as an extension of SMU rather than capitalising on their role to build capacity. This was partly driven by the fact that DA started out its contract when the previous Head of SMU had left the job and there was a long gap. As a result, DA ended up providing bridging support instead of focussing on their main intervention objectives.
- In terms of its exit strategy, DA produced a number of deliverables in collaboration with the SMU, including an overarching transition plan, transition plans for each individual roadmap that they work on, and a knowledge hub where relevant trainings, tools and roadmap documentation are housed. However, capacity from SMU to take them forward independently is yet to be tested.
- In KP, sustainability is a much bigger challenge. Despite acknowledging the contribution of the unit, the GoKP did not allocate funds for it through its recurring provincial budget. This brings into question government’s commitment to the sustainability of the unit. Whereas there is an argument to continue support the GoKP on this, it should come in the form of technical assistance to SSU and departments delivering the prioritised reforms/roadmaps. It should also be made conditional on further commitment from the GoKP through a formal notification of the unit and agreeing to pick up the staffing costs itself.

Lessons learnt
DFID’s investment in delivery units needs to be managed, implemented and monitored more effectively as part of the SNG programme. The two provincial units were managed through separate logframes, which were insufficiently specific and not linked to the overall logframe for the SNG programme. In addition, whereas DFID’s provincial health and education programmes in Punjab and KP leveraged the political clout of the delivery units to unblock reform obstacles regularly, the contribution was not assessed, linked or reported through the SNG programme in a structured and regular manner. Greater coordination between the different strands of technical assistance working on health, education and governance reforms could have resulted in a clearer sense of what organisations had achieved, and given rise to opportunities for further synergies.

In Punjab, the ambition in the exit strategy to transition all roadmaps was unrealistic for nascent roadmaps like water and waste management. Whereas sustainability is a priority at the time of programme closure, it should also be based on on-the-ground realities and achievable in the stipulated time to avoid doing harm to the momentum built through the investment to-date.

Avoiding mission creep and overstretch in delivery units needs to be closely monitored. During implementation both delivery units were burdened, at times, with the management of ad hoc ‘special initiatives’. While this was managed well, it required close supervision and support to implementing teams by DFID. In Punjab, for example, DFID and DA, through working together, were able to support SMU in prioritising additional dedicated staff for the roadmaps

Recommendations
Better define what success looks like for DFID’s investment in the delivery units. Given that the value of DFID’s investment in the delivery units is not limited only to the SNG programme, it is important to take a broader perspective on the definition of success. This could consider a number of factors including influencing at the highest levels of government, buying access, unblocking ‘tangible’ reform blockages, long-term/short-term investment in capacity building. Better clarity in-house between programme teams will result in better management of the delivery unit level logframes. In addition, with a strong relationship built with SMU and SSU, DFID Pakistan is already lobbying for making stocktakes more inclusive. Whereas gender is effectively covered in the stocktakes, there is more that can be done on disability, modern slavery and minorities and plans on this should continue to prioritised.

Regularly review the balance of DFID investment in delivery units versus priority departments’ own monitoring capabilities. Whereas delivery units no doubt effectively fill an urgent gap, it is important for DFID Pakistan to regularly assess the balance between plugging gaps and building long term capacity. In case the balance is not maintained, the development assistance to delivery units could potentially lead to a distortionary effect and undermine long term institutional capacity building. SNG II could consider introducing a ‘mentoring scheme’ whereby civil servants from the prioritised departments are invited to join SMU for a short deputation. During this period, the technical assistance provided through DA could be used to strengthen the capacity of SMU and the departmental staff at the same time by working on stocktakes together. This will also improve the relationship between SMU and the priority departments.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Impact		“More stable democracy in Pakistan”
Indicators		Milestones	Progress
World Bank Institute (WBI) Worldwide Governance / Government Effectiveness / Government Control of Corruption		No target as no data available	Baseline (2013): a) -0.79[6]; b) -0.96[7] / 2016 result: a) -0.64; b) -0.86 (improvement)
Bertelsmann Transformation Index[8] - Government Capability		No target as no data available	Baseline (2012): 3.81 (rank: 110 out of 129) / 2016 result: 3.9 (rank: 106 out of 129)
Outcome	“Poor people in Punjab and Khyber Pakhtunkhwa report that services are better meeting their needs”
Indicators	Milestones		Progress
Household satisfaction with basic health and education services / [Note: Indicator captures government and private sector facilities for education (primary, middle, and high), and basic health care.]	Punjab	No target as no data available	Baseline (2012/13 - data 2010/11): a) Basic Health Unit (BHU) = 29%: b) schools = 63% / 2017 result (data for 2014/15): BHUs=66%; schools=96%
	KP	No target as no data available	Baseline: a) BHU = 45%; b) Schools = 94% / 2017 result (data 2014/15): BHUs = 50%; schools = 93%
Access to improved health and education services:[9] / Immunisation coverage for children below five years of age / Net enrolment rate (girls in primary education)	Punjab	No target as no data available	Baseline (2012/13 – data 2010/11): a) 65%; b) 73% / 2017 result (data 2014/15): a) 70%; b) 67%
	KP	No target as no data available	Baseline (2012/13 - data 2010/11): a) 76%; b) 60% / 2017 result (data 2014/15): a) 83.3%; b) 60%
[6] Revised by PCR reviewer based on WBI online statistics from - 0.81 (in logframe) to – 0.79.
[7] Revised by PCR reviewer based on WBI online statistics from – 1.00 (in logframe) to -0.96.
[8] Bertelsmann Stiftung’s Transformation Index (BTI) analyses and evaluates the quality of democracy, a market economy and political management in 129 developing and transition countries.
[9] Indicator and milestones revised July 2016 in response to a change in available data sources.

Key Point
It is very hard to assess the impact and outcome of this programme, against the logframe indicators, given that there is no data available for 2017/2018 across any of the indicators. Several of the indicators also have a time-lag of two years, so data reported in 2017 is actually for 2014/15. While the unsuitability of the outcome indicators was flagged in the 2015, 2016 and 2017 Annual Reviews and in the Mid Term Evaluation Report, the problem was never rectified.

Both the outcome and impact indicators were overly ambitious for a 5 year programme and as largely composite indicators, too dependent on other external factors to allow a credible attribution by the programme and/or any one donor or intervention. For example, the World Bank Institute impact indicator for “improved democracy in Pakistan” is a composite of 10 indicators, all of them aggregate indicators, including one of SNG’s other impact indicators, the ‘Bertelsmann Transformation Index’. In the case of the outcome indicators, both from the Pakistan Social and Living Standards Measurement Survey (PLSM),[10] the statistics include data from districts not covered by the programme.
[10] Methodology and sampling of PSLM was changed during the programme and logframe indicators updated to reflect this. The data for immunisation and net enrolment is also triangulated with provincial education and health databases.

Therefore, in the absence of credible indicators, an assessment of whether the outcomes have been met has to be done on the basis of qualitative judgement of the programme’s own evidence, assessed against the theory of change. The diagram below sets out how the programme’s outputs have worked from the top down and bottom up to cumulatively deliver towards the outcome. The conclusion is that: there is a high likelihood of improved access to, and satisfaction with, government health and education services, given increase in pro-poor and sector-targeted allocation levels, improved prioritisation and efficiency of these allocations, combined with more performance oversight of funds disbursed. However, the extent and nature of the impact cannot be accurately assessed.

Outputs to outcome assessment

Outcome
Support to planning and policy design to improve the capacity of provincial governments to deliver upon reforms.
- Punjab: ADP formulation amended to strengthen emphasis on strategy to inform the allocations and include a mandatory consultation process.
- KP: Alignment between ADP and Integrated Development Strategy priorities (IDS – mid-term planning framework) increased from 75% (2014/15) to 94% (2016/17).

Reforms to PFM at provincial and local level improve how governments allocate and generate resources, ensuring more funds get to where there’s greatest need.
- Punjab: Under new PFC Award, share of ADP allocated to poorer districts increased from 16% to 36% of the total ADP. Additionally, DEAs received 19% increase in transfers and DHAs 37%.
- KP: Health facility budget tracking established, enabling GoKP to better track disbursements. The result, a 41% increase in allocations to health budgets in 6 focal districts given the identification of funding gaps.
- Overarching PFM Reform Strategies in KP and Punjab set clear priorities for reform.

Needs-based assessments and expenditure tracking at district level begin to enable a better prioritised and efficient allocation of local resources, according to need.
- Punjab: needs assessment process for primary healthcare budgets identified issues of inadequate budgeting, resulting in an increased non-salary budget in 4 districts, which has helped finance service delivery improvements in areas including allocation of medicines, maintenance of medical equipment and training for birth attendants.
- KP: Pre-budget consultations led to around 333 developmental projects (worth PKR 593.315 billion) prioritised and incorporated in district ADPs 2017-18.
Innovations in sector service delivery (in particular health), have created efficiency gains, freeing up funds and ensuring a more productive allocation of resources.
- Punjab: Scale-up of e-vaccination pilot will benefit 1.8 million children annually and Rural Ambulance Service will support c. 1 million expectant mothers annually.
- KP: Innovation pilots directly and indirectly benefited 1.6 million people in six SNG focus districts (48% poor and women).

Provincial and district oversight and programme delivery support mechanisms improve performance and measure and track expenditure, improve the quality of implementation.
High likelihood of improved access to, and satisfaction with, government health and education services for the poor in Punjab and KP.
1.1
1.4
2.2
2.1
2.3
2.3
3.2
3.1
2.3
1.1
1.4
2.2
2.3
4.1
Top-Down
Bottom-up
Outputs

Outcome contribution to impact: ‘More stable democracy in Pakistan’

While governance literature has shown that improved transparency and accountability of government (through improved PFM and planning processes) and improved service delivery are aspects that can support an improvement in democracy,[11] there are many other factors involved. Additionally, impact at this level should be measured in terms of decades, rather than years. Therefore, no assessment can be made at this stage of the programme’s contribution to progress towards impact, aside from a confirmation that the progress towards outcomes is on track, as outlined in the diagram above.
[11] See evidence section in SNG Business Case appraisal section.

The programme’s theory of change (ToC) is summarised below. There have been no major changes to the ToC over the past year, nor during the lifetime of the project. A mid-term evaluation of the programme (Nov 2014 to Feb 2015) noted that the ToC was “ambitious” and that the instruments to test it were “somewhat blunt”, both conclusions remain valid.

Sub National Governance programme
Theory of Change

More stable democracy in Pakistan through increased trust in Government
Improved access to, and citizen satisfaction with, government health and education services
Increased funding and efficiency savings for basic service delivery, targeted to the needs of the population
Reforms to PFM, planning and performance monitoring at provincial and district-levels

Outputs

Impact
Outcome

?

There have been no major changes to the logframe in the past year. However, there have been changes over the course of the programme. The logframe was updated in 2015 and in 2016 to reflect recommendations made in the previous annual reviews. The focus of the revisions was to ensure that indicators were sufficiently ambitious, proportionately weighted, and included a focus on the institutionalisation and consolidation of reforms. However, despite repeated recommendations to reform the overall outcome indicators, given problems with the source and validity of its link to outputs, this was not done.

Recommendations for future programming (on impact/outcome/output indicators)
Consider indicator choices carefully. (1) Measurability: Avoid those with a time lag and which are not easily and/or regularly assessed. (2) Programme processes vs. Government actions: explore gearing more indicators towards government actions and behaviours, rather than the programme’s own processes and products, to help build in sustainability. It may help to have a more developed theory of change on how institutionalisation occurs, to enable charting the desired progression of reforms.

Important to get a balance in the logframe between ‘product’ outputs and those that address the issue of the quality and credibility of these products. There was a heavy emphasis in SNG’s logframe on indicators focused on the production of documents and less on the quality and impact of those products and their institutionalisation. For example, on Open Budget Index (OBI) indicators, it would have been useful to assess also the ‘completeness of documentation’, rather than just the publication of documents. Additionally, demand side assessments such as community score cards, control districts and perception surveys, may have helped capture the perception and/or impact of the reforms themselves.
## D: VALUE FOR MONEY

The total allocated budget for SNG was £38.1 million over six years, of which approximately £29. 2 million was disbursed as of 30th May 2018 and a further £951,336 is forecast to be spent during the current financial year, bringing the total expected spend by the end of the programme to £30.2 million.

The key driver of costs in SNG was technical assistance by OPM, amounting to £23.2 million, split between programme staff (76%) and short term consultants (24%). These, in addition to the costs of the DDCF, GIS technology, the Continuous Audit of Conditional Grants and the School Rectification, make up 83% of the budget. There was a no-cost extension to extend the programme to 31st May 2018 from 13th September 2017. All budget allocations and actual spend are outlined below.

Component	Delivery Partner	Budget	Actual Spend
Technical Assistance	Oxford Policy Management (OPM)	£23,860,600	£23,207,790.33
KP Financial Aid	Government of KP	£9,000,000	£2,500,000
Schools Rehabilitation Accountable Grant	Sarhad Rural Support Programme (SRSP)	£1,686,259	£746,621
SMU	Delivery Associates (DA)	£2,100,000	£1,804,548.99
Externally Financed Outputs	World Bank	£1,318,000	£1,318,000

The VfM assessment conducted by the OPM team indicates provincial governments have allocated an additional £751.25 million to health and education over the life of the programme (until January 2018). On the basis of past execution rates, it was estimated that this would translate to £624.03 million additional funds being spent by districts to increase health and education services for citizens by the end of the current fiscal year.

OPM, in their VfM assessment, calculate that 10% of these results could be attributed to the programme. This would mean that £75.13million of increased allocations over the life of SNG until programme closure and £62.4million increased utilisation of funds by the end of the fiscal year. This translates to:
- For every £1 invested by DFID through SNG the programme has already achieved £3.15 worth of increased allocations to health and education in Punjab and KP.
- For every £1 invested by DFID in SNG until closure, the SNG programme will achieve an estimated £2.62 worth of increased utilisation of health and education resources in Punjab and KP until the end of current fiscal year.
- For every £1 collectively invested by DFID and the provincial governments of Punjab and KP to SNG and related reforms until programme closure, the SNG programme is estimated to achieve £1.59 worth of increased utilisation of health and education resources.

The DFID team worked with Delivery Associates (DA) to create a new VfM monitoring framework in 2017 for the Delivery Associates component. This report is due at the end of April.

Economy

Based on evidence available, the sourcing of high quality and cost effective inputs met or exceeded expectations. For example:

- The average cost of TA for the programme decreased. The majority of this can be attributed to more technical assistance being delivered by the OPM team and a decrease in national consultant fees.
- Significant economies were achieved in 2016 through the co-location of the Islamabad SNG office with OPM’s Islamabad office and transfer of most of the previously centrally located programme management capacity to Lahore and Peshawar. There have been significant savings in rent/utilities and in the cost of support staff.
- SNG adopted a district cluster hub approach for programme execution districts operating the programme through four district hub offices rather than 12 district hub offices which led to cost savings.
- GIS was handed over to the government in year four, ahead of schedule, reducing operation costs for this component.
A testament to the effective cost-saving management of the programme’s resources is that the project was able to continue for a further 8 months at no additional cost.

Efficiency

SNG met or exceeded the output objectives of its year 5 work plan, in line with the allocated budget. Key to the efficiency of the TA team achieving their outputs on government uptake and institutionalisation was their strong working relationships with government and their ability to be flexible and adapt to respond to government needs.

SNG funded TA has also enabled the GoKP and GoPb to achieve their own efficiency savings. In 2015 alone, SNG achieved allocative efficiency savings of £7 million in KP from improved budgetary management. While in Punjab efficiency savings of £8 million were realised for 381,977 flood-affected families, in addition to £4 million efficiency savings from the Punjab education payroll audit. This was equal to a saving cost ratio of 35.3[12] i.e. every £1 investment led to £35.3 savings.
[12] It is assumed that the total spend which led to efficiency savings and tax surveys cost an equal amount of £424,773.

DFID Pakistan took action quickly to avoid inefficient use of resources. For example, the financial aid component of the programme to the KP government was not delivered efficiently so DFID stopped the delivery of this component. DFID Pakistan then contracted Sarhad Rural Support Programme (SRSP) through an accountable grant to reconstruct schools which had been built to a low quality. This was delivered successfully within an ambitious timeframe.

Effectiveness

The effectiveness of SNG can be judged on how progress is achieved against key milestones. The programme has scored A+ for 3 out of its 5 years of operation against output indicators, indicating that it is effectively achieving (and exceeding) objectives with the funds available. However, issues with the logframe’s outcome and impact indicators, make a final assessment of overall effectiveness challenging, given that data is not available.

The following results indicate that the programme effectively delivered against key objectives:
- On improved budget transparency, the provincial Open Budget Index score in KP reached 66 and in Punjab the OBI score was increased by 18% from the baseline to 65.
- On improved devolved processes, all six focal district budgets in KP were prepared based on needs. In Punjab, evidence based budgeting has been adopted by the newly established district health authorities in all 6 SNG districts through SNG support in evidence based budgeting, execution and reporting systems for primary health care.
- On improved innovative solutions to service delivery, the service improvement pilots in Round II in KP have been scaled up by the Health Department through a provision of PKR 782 million. In Punjab, all rounds of the District Delivery Challenge Fund (DDCF) were completed, benefitting over 1.5 million people and with a wide-reaching government uptake. In addition, SNG has supported the government to establish and implement its own challenge fund (the Punjab Population Innovation Fund – PPIF), based on learning from the DDCF.
- On capacity building, the SMU has increased in capacity including in delivery planning, relationship management across government and ability to identify risk plans and take corrective actions. The ongoing coordination of the roadmap delivery has contributed to outcomes in Education, Health, Water and Clean Cities.

However, long term effectiveness may be undermined if progress is not sustained. It will be important for the future programme to assess and identify those reforms which continue to need support (particularly given there will be a gap before implementation of the new programme), before moving on to new areas of work.
Equity

The project positively impacted the governments’ budgetary allocations to the poorest citizens and those who rely on public services. In particular, through the PFC Award calculations and the district delivery challenge fund, which impacted over 1.8 million beneficiaries, 50% of whom were women.

The poorest, women and girls were included in various planning and resource allocation processes supported by SNG. For example, in KP GIS Cells produced maps/reports for service delivery monitoring with sex-disaggregated data feeding into needs-based planning and contributing to the preparation of district ADPs. In Punjab there was an exclusive page on women and girls in the Citizen’s Budget.

E: RISK

Given the complexity of the operating environment, and political economy of reform in KP and Punjab, the risk of the programme was rated high. The risk level remained severe in 2014 and 2015 but changed to major in 2016 and 2017 due to better risk management.
The programme managed its risks well during implementation – putting in place robust mitigations and reacting appropriately when risks were realised.

An overview of key risks featured throughout the programme, and their mitigation, is outlined below.

Fiduciary risk: Conditional grants
- In 2014, it was found that some of the monies spent by government on school construction component was not used according to plans and actually ended up building low standard school buildings. DFID took action, reported the issue to fraud unit and stopped the non-sector budget support.
- Fraud unit advised DFID to follow up on all the construction that had taken place and completed the survey on the construction quality of school facilities built under these grants. DFID ensured that the findings were followed up and addressed through an accountable grant agreement with SRSP. This was monitored closely and schools were completed and handed back to the government once the quality was improved and assured.

Delivery risk: Uncertainty and delays of devolution
- Progress towards devolution in each province was delayed, slowing implementation. However, the delivery risk was mitigated by investment into preparatory technical work that could be capitalised on when the situation changed.
- How power was devolved in each province differed. At times this was challenging, but the delivery risk was mitigated through strong engagement of local government and other relevant departments to understand the different approaches.

External risk: Security and conflict
- The security situation was a continual challenge for programme operations. In particular, areas of KP were restricted for DFID staff, reducing DFID’s ability to conduct some monitoring visits. However, to mitigate this, meetings with government officials were held in easier to reach locations. In 2016 OPM was blocked from operating for three months; however strong and proactive engagement meant this was a comparably shorter time compared to other organisations.
- Security incidents also occurred in Punjab close to government buildings and in certain locations. Robust partner security plans and information networks were established and precautionary actions taken.

Delivery risk: High turnover and transfers of government officials
The high turnover and transfer of government officials was a difficulty throughout the programme. Each time a counterpart would change the SNG TA team would have to form new relationships, which risked slowing progress. Consistent communication and strong government engagement were important mitigating factors.

Sustainability risk: Political ownership and programme gap
- Sustainability was considered as a risk throughout the programme and mitigated through promoting greater government ownership and matching capacity building with technical assistance. However, this remains a risk as the programme comes to a close just ahead of elections, which could lead to a turnover of key government partners and reforms. It is also an opportunity, as the new programme will start just as the new government is establishing itself and staffing key posts.
- Mitigating actions include DFID maintaining government relationships as best as possible in the intervening period.

Update on Partnership Principles
The SNG programme is part of the wider aid relationship between the UK and Pakistan, which is based on an assessment of the government of Pakistan’s commitment to the UK’s four Partnership Principles: Poverty reduction and attainment of SDGs; respecting human rights; strengthening financial management and accountability; and strengthening domestic accountability. 58% of DFID funding in Pakistan currently goes through government channels, therefore it is important that both governments are clear what is meant by adherence to the principles and what constitutes a breach leading to a change in DFID funding or programming.

There remain some challenges to improvement against the principle of strengthening public financial management and accountability, including prioritisation of PFM reforms, the need to pass key PFM legislation, and limited legislative review of budget proposals. Despite this, DFID Pakistan’s assessment throughout the programme has been that the government has demonstrated a reasonably credible commitment to the Partnership Principles. DFID Pakistan regularly conducts the Partnership Principles Assessment (PPA) with the Economic Affairs Division at the federal level and the text is shared every six months. The last PPA assessment was in February 2018 with the same result. Therefore throughout the life of the programme it was judged that DFID could continue the partnership as agreed, including the short-lived financial aid component.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

SNG started in April 2013 and ends on 31 May 2018. This followed a no-cost extension to extend the programme beyond its initial 13 September 2017 end date. SNG has two commercial contracts with OPM and DA. The contract with OPM was extended to 31 May 2018 from the original contract end date of 30 September 2017. The second with DA ended on 31 May 2018.

Delivery against planned timeframe
The VfM report analysis conducted by the team assessed that all deliverables for Year 5 had been met or moderately exceeded the work plan without exception and in line with the allocated budget and timeframe.

Oxford Policy Management
Delivery against the work plan was monitored and reported regularly, including on a monthly basis using DFID-OPM meetings and dashboard reports. In the inception phase DFID had more regular communication with OPM, with OPM providing short weekly updates. Assessed as a high risk programme, this was initially considered necessary to give DFID greater oversight. After the inception phase OPM provided monthly updates and a quarterly report to DFID. After two years, formal reporting was delivered quarterly, along with an end of year report. Quarterly progress reports were conducted to monitor the logframe milestones. These reports were accompanied by regular discussion with DFID at the provincial and central level. The quarterly Steering Committee meetings in each province were organised by the OPM SNG team but chaired by senior officials in government. This was regarded as an important forum for decision-making or for solving specific challenges.

The programme remained on track throughout, according to milestones, despite challenges noted below:
- Due to the political situation the SNG team were unable to enter KP for three months in 2016 as the Pakistan government restricted all SNG operations. This was a relatively short time in comparison to other organisations and was responded to well by the SNG team.
- The high turnover of government counterparts meant the SNG team had to constantly reengage and build new relationships with government officials.
- The introduction of a new devolved government system was delayed.

Delivery Associates
To-date Delivery Associates has met all targets on its deliverable-based payment contract. Delivery Associates also had a mandate to provide technical support on the tax roadmap to the GoPb. The initial work was completed however the tax roadmap could not be launched in Punjab as the Finance Department did not want to take a roadmap approach. After a series of consultations between DFID Programme Team, Commercial Team and Delivery Associates a partial payment (against progress made) was paid.

Performance of Partnerships
Performance of technical assistance by OPM
OPM consistently delivered on the programme outputs and objectives and effectively responded to recommendations raised, in particular through the Annual Reviews. The team have built strong relationships with government departments through regular and consistent communication, maintaining relationships and providing additional assistance, when it contributed to the programme objectives and they had the capacity. The team have been particularly responsive to requests from DFID and supportive of the DFID review process and proactively shared challenges and lessons learnt.

Performance of the Challenge Fund
Coffey were subcontracted by OPM to manage the Challenge Fund, which they did until its closure after Round 2. However, they continued to manage and monitor the performance of the grantees and the pilots for the preparation of the scale up by government until the end of the project. In addition, a lessons learnt document on the Challenge Fund experience was produced in late 2017. Coffey performed as expected against their terms of reference. The Challenge Fund exceeded expectations, with many initiatives being extended and taken up by government.

Performance of Delivery Associates
The management of the Delivery Associates contract has changed throughout the programme (between being DFID or OPM led). In the last two years they were directly contracted by DFID. Having a separate partner for the SMU component meant that OPM could continue having strong relationships with provincial government without also having an additional monitoring capacity. DA completed quarterly reports, mid-term and yearly reviews. DA submitted quarterly reports on time, however monthly updates were not as consistent. The quality of reporting improved over the last twenty months.

The influence Delivery Associates provided through their most senior representatives was considered a benefit. However, challenges around defining and measuring success for SNG have hampered the overall assessment of performance. There were also challenges related to staff turnover, in particular, the new (Government-appointed) Head of SMU who joined in the first quarter of 2017. Some activities, including training of SMU staff and on-going support, were put on hold and a revised work plan was later agreed between DFID, SMU and DA. As a result, a deliverable on a perception survey of SMU was removed from DA’s contract, leading to a contract reduction of £66,441.

Performance of the SRSP in the school reconstruction component
SRSP have provided timely reports and were successful in achieving challenging milestones within the timeframe. DFID contracted SRSP through an accountable grant in September 2017 to rehabilitate and reconstruct incomplete schools, following the closure of the financial aid component to the GoKP. SRSP provided fortnightly progress and financial reports and the DFID team held weekly phone calls to monitor progress and troubleshoot any challenges.

DFID performance and coordination with other programmes
There was a high level of ambition for SNG to be a cross-cutting programme with strong linkages written into the BC, in particular on health, education and demand side governance. Whilst efforts were made at DFID and implementing partner level, the practice never met the original theory.

Factors contributing to challenges around partnership with AAWAZ on demand side governance included:
- Incomplete geographic overlap: while they covered some of the same districts (such as Haripur which was a successful example of collaboration), for the most part they did not overlap.
- No formal, and evaluated, mechanisms in either programme for collaboration (i.e. indicators, joint activities, joint monitoring, or subcontracting arrangements).
- The SNG and AAWAZ did not have joint forums for discussion with provincial and district governments but conducted their steering committees separately.

In short, opportunities were missed (or simply not set up correctly) to more substantively bring the supply and demand side programmes together and ensure that as work on systems strengthening and expanding government outreach was supported under SNG, activities were being closely coordinated to enable citizens to effectively engage with the information available (i.e. citizens’ budgets) and in the forums available (needs based budgeting consultations). This inter-relationship between supply and demand side governance is fundamental to effective subnational governance and will require close attention under SNG II. The teams are considering incentivising collaboration between the contractors by creating shared indicators across both programmes and adding the need for joint working to tender Terms of Reference.

There have been some good examples of partnership on health and education, but also issues of duplication. Partnership on education included through the delivery unit work on the education roadmap; collaboration on the development of bylaws and rules around the newly created DEAs in Punjab; and on the Challenge Fund service delivery pilots. The quality of the OPM TA team was emphasised as a valuable asset. However, on the challenge fund, concerns were raised regarding duplication with existing DFID education programming in this area. In health, the round II pilots that worked closely with district government seem to have been widely supported and one of the innovation pilots from SNG is now being scaled up by the DFID Health Team. However, more could have been done to maximise incentives for, and substance of, the partnership across the sectors. Recommendations for future programming are outlined in the PCR summary section.

Asset disposal and value obtained by DFID

Throughout the programme 1090 assets were obtained. An assessment of the value of each asset was conducted in order to decide what would bring the best Value for Money for DFID. Assets which have a long life-cycle and are high value are proposed to be retained for the future SNG programme. Assets which are within government buildings or have limited life-cycles will be transferred to government ownership, to continue the strong relationship and allow for resources to continue to be used to support the sustainability of the programme. Overall the current proposal is that 536 will be transferred to NGO’s from other DFID programmes, 45 will be retained for SNG II, 425 will be transferred to government and 84 will be disposed of.

Spot checks have been conducted throughout the programme life cycle. A random spot check was conducted during the review period in Islamabad on 22 March 2018, which was satisfactory. A spot check was also conducted in Lahore and Hafizabad districts during the previous annual review period.

Quality of Financial Management
The programme has demonstrated strong financial management controls for partners, with continuous monitoring. Invoicing quality and control mechanisms have been maintained throughout. Overall the quality of forecasting was adequate. The closure of the Financial Aid component resulted in an underspend of £6.5m under this component. Continuous negotiation by DFID with OPM and the flexibility of OPM enabled cost efficiencies to be achieved. Significant efficiency savings were also achieved under the accountable grant with SRSP for school rehabilitation and this work was delivered against a very tight timeline (of eight months) with continuous reviews ensuring adequate resource allocations, resulting in £746,621 spent against a budget of £950,000. Similarly, efficiency savings were also achieved under Delivery Associates (DA) component through continuous monitoring.

The final audit for the programme for 2017/18 is due to be conducted and finalised by September 2018.
Date of last narrative financial report	September 2017
Date of last audited annual statement	March 2017

G: MONITORING, EVIDENCE & LEARNING

Monitoring
DFID’s monitoring mechanisms for the SNG programme included: (1) monthly, quarterly and annual progress reports (including a dashboard of indicators); (2) regular (as possible) field visits; (3) independent evaluations (i.e. mid-term evaluation); (4) quarterly steering committee meetings in each province with key government beneficiaries; (5) regular and frank engagement with implementing partners and programme stakeholders; and (6) access to the OPM knowledge management system, which includes evidential documents against each of the logframe indicators and work plan deliverables. In addition, to look at the progress of conditional grants and for verification of fund flows, DFID deployed Deloitte to conduct a Continuous Audit following the 2017 Annual Review.

Finally, as part of SNG’s exit strategy (June 2017-May 2018), regular reporting has been provided against ‘exit strategy actions.’

This PCR was conducted between 12 to 22 March 2018 by Clara Barnett (Governance Adviser, DFID DRC) and Sana Zia (Acting Head of CSSF, Pakistan), with support from the DFID Pakistan programme and advisory team. The PCR was based on an assessment of a range of evidence including:
  1. Desk-based documentation review: Government documentation (i.e. budget products); SNG programme reporting documentation; budgetary statistics; internal communication; external statistics; and graphs reflecting a more equitable distribution of provincial funds (as part of assessing the ‘leave no one behind’ dimension of the programme);
  2. Field Visits to districts in both Punjab and KP to conduct interviews with beneficiaries from provincial and district government and civil society;
  3. DFID staff and implementing partner interviews.

Evidence
A baseline evaluation of the programme was conducted during inception and a mid-term evaluation of the programme was completed in 2015. Both reports assessed the programme against its theory of change and original assumptions. SNG regularly gathers evidence of performance as part of quarterly and annual reviews. There have been no major changes to the evidence base relating to this programme.

The development of a VfM framework for SNG allowed the programme to establish, test and validate the link between activities and outputs and outcomes. The VfM framework explores in detail issues of economy, efficiency, effectiveness, and equity as well as learning and adaptation.

Learning
SNG has produced an extensive amount of high quality learning documentation – in the form of policy briefs, case studies, videos and guidelines - and conducted a series of training and lesson learning seminars, to ensure that knowledge has been captured and transferred to the relevant stakeholders throughout the course of the programme’s life cycle.

Lesson Learning
DFID’s key lessons learnt from the programme are captured in Section A and throughout the output sections.

Progress on recommendations from annual reviews for this programme
Overall, there has been a very high level of responsiveness to Annual Review recommendations by the implementing partners and DFID team. SNG has also demonstrated flexibility in its
implementation as new challenges, opportunities and priorities arose.

Recommendations from the early years were tackled and the focus shifted from current implementation to future sustainability. At the beginning of the programme, key recommendations included: the need to invest in more political engagement; applying flexible programming in light of delays in the roll out of devolution; and the importance of prioritising equity and gender objectives. These recommendations were taken on board and did not repeat themselves in the later years of implementation. Recommendations in the later years of the programme focused instead on issues of sustainability, responsible exit, prioritisation and lesson learning. These were responded to well, with extensive work done on exit planning over 2017/18 and the transfer of knowledge. The progress against the 2017 AR recommendations are outlined in the table below.

However, two recommendations were consistently raised and not fully met over the course of the programme: the first was the need to review the logframe indicators for outcome and impact level and the second to improve coordination across DFID programmes. On the first, the responsibility to make changes lay with DFID and it appears that while there was internal discussion, it was ultimately decided not to make substantial changes. On coordination, again while efforts were made, they never were able to overcome the lack of structural incentives to partner.

All recommendations from the last (2017) Annual Review were adopted with the exception of the revision of indicators to better measure contribution to improved service delivery, which will be considered when developing indicators for SNG II.

Annex I: Pilots under SNG Challenge Fund

Summary of Punjab projects

Har Zindagi E-vaccination (HZ): This project aimed at enhancing the coverage and completion of child immunization cycle by deploying innovative use of technology to make each child traceable. The key innovation under the HZ project has been the redesigning of the immunization card, to make it more intuitive for low-literate users and improve its functionality by adding a Quick Response (QR) code and an electronic memory card so that the unique child ID of each card can be digitally scanned by the vaccinator’s smartphone and data transferred. Har-Zindagi with its green vaccination passport has replaced the old yellow slip and the monitoring only application. Punjab Information Technology Board has received approval of a PC-I under which 4 million cards are being produced and vaccinators’ phones are being replaced.
Beneficiary Counts – 100% females
23,000+ new born registered

Beneficiary Counts – 100% females
Over 8,000 emergency pick-ups
With 7,162 critical cases

Integrated Ambulance Service (IAS): this project aimed at filling the gap of timely availability of medical service for Emergency Obstetric and Neonatal Care (EmONC). The pilot has developed a GIS enabled ambulance dashboard which is managed centrally by the DCO office and located through GIS mapping covering the entire rural area of Hafizabad. The integrated ambulance service (IAS) piloted in District Hafizabad provided a door step service to expectant mothers. The maximum response time within rural Hafizabad was just under 14 minutes and the pilot served over 8,000 women. The Government of Punjab has now scaled up the model across Punjab and will be adding 450 new ambulances.

Tele Medicine/Diagnosis (TMD): This project aimed at filling the gap of a doctor at remote Basic Health Units (BHUs) by equipping them with key diagnostic facilities and connectivity with a remote doctor. The equipment has the capacity of being solar powered and works on simple GPRS to connect to a consultant sitting at a senior district hospital. The results of the tests are immediately sent to the consultant and patient can engage with the consultant in real time over video connectivity. The government has started to adopt and scale up the intervention in parts – 1,000 portable ultrasound machines have been provided to Lady Health Workers at BHUs to target ANC scanning, while Vehari and Hafizabad districts have scaled-up across the districts. The road map team is keenly following the developments. Another key element is the disease pattern data supporting needs based planning and budgeting.
Beneficiary Counts – 62% females
87,836 patients
Over 14,900 ANC Scans

Teemardar – Medicine Inventory Management (TM): The TM pilot has automated the medicine inventory management system to reduce pilferages, improve availability, maintain visible inventory and create data for informed procurement and distribution of medicine at district level. The pilot is designed to integrate with the work of district planners to provide evidence based needs assessment of medicine requirements. Additionally, the pilot has created display spots of the inventory for public view to increase transparency. Finally, by tracking the exact use of medicine the pilot has developed a disease patterning in the district that will inform planning and budgeting. The inventory management component of the project has led to controlling pilferage, transparency, better monitoring and evaluation and efficient service delivery. Similarly, Electronic Record Management (ERM) has resultantly improved patient record, disease records and patient disease history. The PC-I has been developed for a province wide scale-up.
Beneficiary Counts – 60% females
1.3 million patients served

Summary of KP projects

Three round 1 pilots boosted children's scores in basic numeracy and literacy tests. The attendance rate also increased, while drop-out rates declined. The successful models (Broad Class and Science Camps) are being streamlined into new initiatives of the Education Department. Beyond this, the Broad Class model also informed the design of a British Council-funded education project.

The Integrated Disease Surveillance and Response System (IDSRS) pilot delivered a workable model for checking outbreaks of communicable diseases and is replicable across the country. It has started influencing the way immunisation is being done at provincial level by creating a cadre of entomologists who carry out vector surveys in districts to identify high-risk points for communicable diseases, to share the results of their work with district authorities, which in turn enables immunisation campaigns to target high-risk areas, thus mitigating the risks of outbreak. The IDSRS core team (i.e. Project Director and Project Coordinator) are supporting the National Institute of Health and Public Health England to roll out the IDSRS model across the country.

The D-Talk pilot has delivered an effective model to prevent and cure diabetes at a time when 17% of the country’s population is suffering from the disease. The Provincial Task Force on Diabetes – an offshoot of the pilot – has started holding awareness sessions in medical colleges to ensure that doctors and paramedics make screening for diabetes routine in their work. The D-Talk model was selected by the International Diabetes Federation for presentation to the International Diabetes Congress in 2017.