Project Completion Review

Title: Building Core Systems in the Government of Sierra Leone
Final Programme Value £ (full life): £25m	Review Date: August 2018
Programme Code: 205192	Start Date: 10 February 2016	Final End Date: 31 August 2018

Summary of Programme Performance

Year	2016	2017	2018
Programme Score	A	A	A
Risk Rating	Severe	Major	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5284320.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5628014.xls

A. Summary and Overview

Description of programme and what it has achieved

The Building Core Systems programme was designed to improve the Government of Sierra Leone’s ability to spend public money wisely, increase its capability to raise domestic revenue to reduce aid dependency, and promote accountability to stop corruption.

It focused on five areas of public financial management (PFM): budget credibility, wage bill and payroll control, public procurement, revenue mobilisation, and macroeconomic management.

In 2.5 years the programme achieved a more accurate and clean payroll, better control of spending and arrears, better revenue forecasts, a streamlined and more accurate budget formation process, and informed plans to reduce tax exemptions and waivers to increase revenue collection, enhanced transparency in government procurement, and a new PFM Reform Strategy for the next five years.

There were three components to the project:
1. Supporting health workers’ salaries through performance-based aid. This component of the programme was discontinued after 2016.
2. Providing expert technical assistance (TA) to support the Government to implement its reforms.
3. Diagnostics and monitoring, including a major Public Expenditure and Financial Accountability (PEFA) assessment.

Specific achievements include:
Budget planning process revamped so that there is enough time to involve all stakeholders, budget ceilings are now based on more reliable data and forecasting, and they take a medium term view. This was evidenced in the 2018 supplementary budget.
- Strengthened budgetary controls, with the Ministry of Finance’s information and communications technology department supported to develop an automated system for spending departments to request funds electronically so that they cannot spend if there is no budget.
- Cleaned up payroll systems to remove ghost workers (i.e. fake records) and duplicate records, improve ability to detect these in future, and identify those of retirement age. Employees are now being encouraged to retire once they reach retirement age, creating room for jobs for the growing number of young people. This is all captured in a high quality payroll management strategy that was recently approved by Cabinet.
- Built the capacity of key staff through training in Excel and specialist financial software. Training led to skills being enhanced and put into practice.
- Stronger and more transparent procurement systems. Systems in the Ministry of Finance have been re-established so that senior leadership has more oversight over procurement, leading to some contracts representing poor value for money (VFM) not being approved. Full details of 55 contracts above the national competitive bidding threshold published to improve transparency.
- Progress towards reducing tax exemptions and waivers, and increasing revenue. Influenced policy recommendations to the Minister of Finance via his Special Committee on tax exemptions and waivers, including on which to remove and how they should be administered.
- New Public Financial Management Reform Strategy in place based on robust evidence from high-quality, comprehensive Public Expenditure and Financial Accountability (PEFA) assessment.

Lessons learned over the lifetime of the programme:

- Where there was openness to reform, our support helped to catalyse action, although commitment to reform varied across departments. Policy dialogue between DFID and the Government worked very well where objectives were aligned.
- It is vital to have a technical assistance team that can balance the need to build strong relationships with the need to understand the politics of Sierra Leone and have difficult conversations with government counterparts. This paid off in the form of close collaboration leading to success in implementing stretching reforms.
- A flexible programme is important in an unpredictable context to efficiently achieve objectives. Technical advisers need to remain focussed on achieving outputs and outcomes, rather than holding focus at the activity level. The programme was able to align to the emerging priorities of the Ministry of Finance, as the technical advisers had the flexibility to respond to requests from government counterparts.This helped strengthen the relationship and deliver on the major reforms planned.

## B: DETAILED OUTPUT SCORING

Output Title	Well-developed and well-executed national budget
Output number per LF		1	Output Score	B
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Budget data and monitoring	The automated budget execution process (commitments and purchase orders without manual public expenditure tracking forms) has been rolled out.	Not met due to delays in complementary investments.
	Configuration for new Integrated Financial Management Information System (IFMIS) includes provision for changes in allotment controls to complete the automation and streamlining of the budget execution process. / This will be evidenced by documentation agreed at technical level in Ministry of Finance (MOF) (recognising the final configuration may not be agreed because of length of time it may take to procure the new or upgraded IFMIS).	Met

Provide supporting narrative for the score

Although this output scored a B overall as performance did not fully meet expectations, over the lifetime of the programme progress was made to move towards a more automated, streamlined budget process with stronger controls. This is vital to improve the credibility of budget execution.

In the last year, the technical advisers completed a database that will automate the process for line ministries requesting funds from the Ministry of Finance. This database will provide an immediate solution until the new comprehensive upgraded IT system (IFMIS) can take over in the next few years. The Ministry of Finance has tested the database, and although the rollout was held up by delays to the procurement of ICT equipment for line ministries, they aim to introduce it in 2019.

The specification document for the longer-term comprehensive upgraded IT system (IFMIS) was prepared with support from the technical advisers in 2017, and this is the basis for ongoing negotiations with the IFMIS vendor. This includes plans to reconfigure allotment controls which means the second milestone was met.[1]
[1] Currently allotment controls, which cap spending against different chart of account codes within IFMIS, are set at a detailed level of the chart of accounts. Capping expenditure at a less detailed level will allow ministries, departments and agencies (MDAs) greater flexibility within their own budget allocations whilst still providing the MoF with sufficient oversight.

Lessons identified this year linked to this output and recommendations for future programmes

Even when there is genuine buy-in and the reform will make jobs easier, it is not uncommon for reforms that depend on procurement of ICT equipment to be delayed by unforeseen glitches and inefficiencies.

Systems and automation are also only the first step. Whilst they are crucial to better controls in the long-term, they must be complemented by change management strategies to incentivise behaviour change and ensure systems are being used properly, working alongside internal and external auditors.

Output Title	Better processes and increased capacity for management of the public sector wage bill
Output number per LF		2	Output Score	A
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	Y ↑

Indicator(s)	Milestones	Progress
Wage bill data and capacity for analysis increased. Data purity for the payroll is significantly enhanced as evidenced by:	99% of National Social Security Insurance Trust (NASSIT) numbers included and correct	Exceeded. 99.4% and results have already been used to remove duplicate workers from the payroll.
	99% of basic bank account numbers (BBANs) included and correct	Met. 98.4%
	Employee Assignment Coding Blocks are recorded correctly to match the Budget Book	Met – 60,000 have been corrected which makes budget execution reports accurate for the first time.
	Ministry of Education data (from DFID teacher payroll cleaning exercise) on NASSIT and work location discrepancies of teachers has been used to update 90% of the data on the system.	Met
	Report that highlights employees who have achieved retirement age as per NASSIT number is published. / NASSIT contribution for retired subvented agency staff, consultants and civil servants are stopped. / Employee files for all the employees who have left GoSL jobs due to retirement, termination, death and resignation have been properly deactivated.	Met.

Provide supporting narrative for the score

Technical-level support to review and add data to the wage bill has exceeded expectations in delivering a cleaner payroll with fewer ghostworkers, generating savings for the the government in paying wages and salaries.

Approximately 1,100 social security (NASSIT) numbers have been corrected on the system and over 15,000 bank account numbers (BBANs) added. NASSIT numbers are used as the unique identifier for government employees and need to be correct in order to identify dual employees. 204 cases of dual employees have been detected since the NASSIT data clean up, building on the 400 identified last year. These employees are no longer being paid twice. Correcting NASSIT numbers has also ensured employees pay the right contribution to their pension and receive a pension. Correcting bank account data means government employees including teachers and health workers are being paid more promptly and efficiently. These reforms are essential ahead of the IT system (IFMIS) upgrade so that clean data is entered to the system.

The programme has supported workforce management by persuading the government of the benefits of encouraging staff to retire once they reach retirement age. The technical advisers produced a report showing to the number of staff who should have, or were shortly due to retire, and setting out the benefits of enforcing the retirement age in particular in creating jobs for the growing number of unemployed graduates and generating savings in further pension contributions. As a result of this the government encouraged people over retirement age to retire, which has created space on the payroll. These files, and those of other departing civil and public servants, have been properly deactivated so that their files cannot be used to create new ghost employees.

Lessons identified this year linked to this output and recommendations for future programmes

Maintaining a clean payroll is not a one-off exercise: it requires continual effort to ensure new recruits’ data is entered accurately and changes to existing employees’ data are captured. DFID and others supporting the government on public financial management need to support a coherent approach to continued implementation of the payroll strategy, under the oversight of the Cabinet.

Output Title	Better processes and increased capacity for revenue policy, coordination and collection
Output number per LF		5	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	Y ↑

Indicator(s)	Milestones	Progress
Revenue data and monitoring	Pilot analysis in a major sector to highlight the impact of the tax policy and suggested changes to the policy (sector report produced); agreement from Director of Revenue and Tax Policy Department (RTPD) on the proposed changes (if implemented would lead to increased tax revenue).	Met
	Continue relationship building between National Revenue Authority (NRA) and tax policy department of MOF (as demonstrated by example of data sharing and joint working on exemptions policy).	Met

Provide supporting narrative for the score
In the last year, analysis provided by the technical adviser through this programme has had a significant impact in shaping Sierra Leone’s approach to tax exemptions at the very highest level of government, and tightening up waivers in order to generate more domestic revenue.
Following the election in April 2018, political attention on tax exemptions and waivers increased markedly and the Government set up an independent committee to give policy advice to the Minister of Finance and President. The programme technical adviser was asked by the committee to provide a paper to inform these policy recommendations. This paper included an in-depth analysis of the potential impact of tax exemptions and waivers in the tourism sector, and a framework for analysis of exemptions and waivers. It drew on previous DFID-funded work on tax exemptions that was completed over 2016 and 2017, thus enabling DFID to get even greater value from this earlier work when political interest in this issue had increased. The technical adviser’s inputs formed the basis of the committee’s recommendations to the Minsiter of Finance and President and ensured this issue will receive attention at the very highest level of Government (rather than Director-level as reflected in the logframe milestone).
The relationship between the National Revenue Authority and the Ministry of Finance’s Revenue and Tax Policy Department has improved, partly due to project activities and partly due to changes in senior staff at the NRA. The programme team created the foundations for this in 2017 by initiating data sharing initiatives, which improved relationships at the technical level. Another welcome development is the establishment of a revenue steering committee involving both ministries, departments and agencies (MDAs) which is meeting monthly.
Lessons identified this year linked to this output and recommendations for future programmes

Tax exemptions and waivers are a highly politically sensitive issue in Sierra Leone and elsewhere. This highlights the need to be flexible and target our assistance towards areas where there is both the political will to drive reform, and large gains to be made.

Output Title	Increased capacity to implement and monitor PFM reforms
Output number per LF		6	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Technical capacity demonstrably improved; Budget Bureau Director and RTPD Director can rely on staff for technical analysis on specific topics.	20 MOF staff trained on advanced Excel with at least 40% of them passing the final exam / 16 MOF staff trained on use of Tableau (an IT software) with at least 40% of them passing the final exam.	Met.32 trained on Excel and 50% passed the exam (16 staff) / 15 staff trained on Tableau and 33% passed the exam (5 staff)
	Strengthened capacity of RTPD and NRA to analyse impact of exemptions and waivers.	Not met.
Implementation plan for PFM reform developed, tested and approved by Government.	2017 PEFA finalised and quality assured by the PEFA Secretariat.	Met
	A well-defined PFM Reform Strategy developed (short, usable format that has positive feedback from PFMRU and other departments in MOF).	Met
	Improved reporting of government commitments under the PFM reform act to ensure stronger implementation (template on transparency commitments drafted and filled out 2nd quarter of 2018).	Met

Provide supporting narrative for the score

Technical capacity in the Ministry of Finance has been improved, in particular in relation to key IT skills. The programme technical adviser undertook a comprehensive Excel training course for carefully selected staff in the Budget Bureau, Accountant General’s Department and Internal Audit whose jobs rely heavily on Excel. Their managers had nominated them to attend: this made sure that only those in need of the skills participated, and the results fed into performance management. 50% passed the stretching exam after the course and therefore qualified for Tableau training. Tableau is the software package rolled out in 2016 by the programme which brings all budget and wage bill data together from the various databases and presents it in user friendly dashboards. Using Tableau allows Ministry staff to get on demand figures easily and in a well-presented way. Feedback from Directors using Tableau has been extremely positive. They are now using it without support, reducing over-reliance on external technical assistance, saving time and improving the accuracy and quality of advice to the senior management in the Ministry of Finance. Both the Budget Bureau and Accountant General’s Department reported finding hidden talents among staff and concluded they must give these staff more complex analytical work to do now they have proved they are capable through the training and exam results.

Given the challenges in gaining traction in 2016 and 2017 on reforms to tax exemptions and waivers, further efforts to build the capacity of NRA and RTPD to assess their impact were deprioritised. Instead support in the final year has focused on informing the committee on tax exemptions and waivers. The analysis previously undertaken by the BCS team in this area is extensive and remains relevant.

An implementation plan for PFM reform has been developed, tested and approved by Government. A Public Expenditure and Financial Accountability (PEFA) assessment was carried out in 2017, and completed in 2018. A PEFA provides a standardised, evidenced-based assessment of PFM performance and is the most commonly used international assessment tool for PFM (see pefa.org). The PEFA was finalised in time to feed into the Government’s new PFM Reform Strategy for 2018-2022, and the programme technical adviser played a leading role in the development of this. It is vital to have a Strategy that is well thought out, grounded in evidence, and reflective of government priorities in order to guide the efforts of both donors and ministries. The technical adviser navigated complex competing views from stakeholders to help the Government produce a document that has buy-in across the board. The technical adviser also ensured that the Strategy is concise, clear and presented in a user-friendly way so that stakeholders can see at a glance what the strategy focusses on and what the priority areas are. The Strategy sets the framework for the successful implementation of the PFM Regulations, which were laid before Parliament in June 2018.

Lessons identified this year linked to this output and recommendations for future programmes

Training courses, if done well, can result in essential skills being absorbed and put into practice and can unearth hidden talent. But the style of training is important. Exams are an important part of testing that skills have been absorbed and should be factored into any training course. Attendees must also be genuinely committed to participating throughout the course and have the support of their managers.

DFID’s new PFM programme should take these lessons into account in capacity building efforts. It should also consider whether it is appropriate to resume capacity building support around analysis of exemptions and waivers based on the findings of the independent committee.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The programme has performed well against outcome indicators, making steady progress in payroll reforms and developing evidenced based strategies for PFM reform. The change of government has brought additional momentum to revenue mobilisation, payroll management and arrears clearance. The new government has also finalised the PFM strategy and PEFA exercise, with support from this programme. It is expected the IMF programme will be agreed this year, following a positive IMF Mission in September / October and the Government is on track to meet the prior conditions required for a new programme. In terms of reducing arrears, the new Government reduced the stock of unpaid cheques from 1.3 trillion Leones in March 2018 to 1.07 trillion by June 2018. A decision was taken in June to audit all arrears to be sure what needed paying. There is still good evidence that budget credibility has improved.

We expect further outcome level results in time, especially as a number of donors, including DFID, are continuing to support these priority reform areas. There is generally a time lag between outputs being achieved and their effects leading to outcome success, and even more so with impact. It is therefore not surprising that the impact level indicator has not been met due to the time lag as well as the fact that impact level results are driven by factors far beyond the scope of the programme.

Impact target	Result
Annual rate of real non-iron ore GDP growth is above 4.5%	3.6%[2]
Poverty headcount (national poverty line) is below 41%	No data
Outcome target for end August 2018
Unpaid cheques are below 700 bn Leones by end August 2018.	GoSL made progress on this indicator but then decided to conduct an audit to verify all arrears before making further payments.
Total revenue (excluding from extractives) increases by 212 billion Leones compared to same period (Jan - June) in 2017, if the logging ban stays in place. The target should be 309bn Leones if the logging ban is lifted because this will generate more revenue; the uncertainty around the ban contributes to uncertainty around the target.	Met – revenue collected was 224 bn Leones above the same period last year. The logging ban remained in place.
Total workforce in July 2018 does not significantly exceed total workforce in July 2017 (i.e. it is within 5%).	Met – the total workforce is 1% lower in July 2018 than July 2017
Agreement reached with IMF and a credible ECF programme is in place.	The IMF and GoSL are aiming to take a programme to the Board in late November 2018.
[2] 2017 data from the World Bank Sierre Leone Economic Update, June 2018

Summarise the programme’s theory of change and major changes to it in the past year

The theory of change supposes that technical assistance and financial aid will support and incentivise the Government to deliver a set of actions and reforms across various areas of public financial management. These actions are captured in the programme outputs, which articulate processes that should become embedded in the Ministry of Finance. Collectively these processes will deliver the outcome level results, which measure of the strength of the institutions and their ability to manage public finances for improved service delivery. The ultimate impact is therefore the result of improved service delivery: reduced poverty and increased GDP.

The evidence from implementation of this programme supports the theory of change in terms of the contribution of technical assistance to developing and embedding systems and processes, but does not fully hold in terms of the contribution of financial aid to incentivising reforms. The 2017 PEFA provided evidence that the BCS support was relevant as it targeted a number of the areas of weakness identified. Financial aid did help drive forward reforms at the time, but these were not always sustained and the assumption that it was critical for our continued policy dialogue with Government did not hold.

Explain major changes to the logframe in the past year

The programme had been due to finish in December 2017 but was extended to August 2018. This was to prevent a gap in support before DFID’s new PFM programme came on stream in September 2018 and ensured support was in place to capitalise on the reform momentum of the new government post-elections. This required the logframe to be updated to reflect the later end date, and add a sixth output: increased capacity to implement and monitor PFM reforms. The third and fourth outputs, on macroeconomic management and procurement were discontinued for the final eight months because the programme was not working in these areas during the period.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

2016 and 2017
The financial aid component was designed so that DFID only disbursed funds when targets had been met, so there were no payments if results were not delivered. Similarly the TA component was a 100% milestone-based payment by results contract so ASI was mandated to deliver high-quality outputs against an agreed milestone schedule in order to be paid. All milestones were met on time and to a high quality, in many cases exceeding what was required for payment. The TA part of the programme represented extremely good value for money. This was due to the programme building in flexibility and an emphasis on sustainability.
- On flexibility, a flexible team structure limited the need for additional inputs and enhanced the efficient use of existing inputs. Rather than focus solely on their own work streams, team members’ varied skills were actively used to fill gaps in other work streams. As well, 15% of working days were flexible so that the team could respond to emerging MOF priorities. This built confidence within MOF and helped facilitate the planned reforms. It also ensured that reforms were able to complement each other, and have a holistic impact on core systems.
- On sustainability, each output had a solid plan for how the reform would continue beyond the life of the programme. Continuing to keep two technical advisers in place until the new DFID programme is running also safeguarded some of the reforms. This will allow the value from the programme to continue for years to come if it is successful (although it is too soon to tell this).

The Business Case listed “take up of TA advice by the Government of Sierra Leone” as one measure for effectiveness of the programme. The following examples of actions taken are all a result of advice provided under this programme:
- MOF re-organising how senior managers meet and discuss pertinent issues on a weekly basis to enhance efficiency in problem solving;
- re-establishment of the ECMC, improving the way contracts are approved and enhancing VfM through procurement;
- changing the budget calendar for the 2018 process;
- bringing the subvented agencies[3] on the MOF payroll.
  [3] Subvented agencies are independent agencies of government that receive subsidies from the budget to cover at least part (or often all) of their expenditures.

2018
The programme was extended from 31 December 2017 to August 31 2018. This was to allow two carefully designed technical assistance roles to continue, and the PEFA to be completed. Retaining the technical advisers in the Ministry of Finance between the end of this programme and a new DFID PFM programme allowed DFID to contribute to emerging needs in the Ministry of Finance, keep abreast of the latest reforms and influence how reforms are executed.

In terms of economy, rates paid for the consultants were extremely competitive. Feedback from counterparts in MOF has been positive, indicating that their support has been efficiently delivered. As well, the PEFA was delivered exactly to time and the PEFA Secretariat assured its quality.

There has also been good take up by Government of the technical advisers’ advice, indicating effectiveness. Examples are:
- Government acted on the programme’s technical advisers’ advice to encourage public and civil servants above retirement age to retire.
- DFID, through this programme and our revenue programme, effectively influenced the government across its lifetime to significantly reduce tax exemptions and waivers. Government issued an executive order with the aim of reducing these. The programme’s work on the issue stepped up in 2018 and has fed into the Government’s Special Committee making decisions on waivers and exemptions. The technical assistance team ensured the analysis from the revenue programme was also fed in, further enhancing value for DFID’s money.
- The new Public Financial Management Reform Strategy has a focus now on higher level strategic issues and is articulated in a concise and usable format. There is agreement across the Ministry of Finance on this Strategy.
- The PEFA has been accepted. The Ministry of Finance have published the report on their website and approval is being sought to publish it on the PEFA secretariat website. The PEFA fed into the Strategy.

E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The principle driver of risk in this programme was financial aid. This is why risk was assessed as severe in 2016 and dropped after that the decision was taken to stop the financial aid component. DFID continually monitored the key areas identified in our fiduciary risk assessment and provided an annual statement of assurance on these. In addition, engagement on PFM reform through our TA and the development partners working group was targeted at addressing some of the key weaknesses in the PFM control environment. The financial aid component was stopped when the risk the government was not genuinely committed to reform rose above our risk appetite. The TA component remained within our risk appetite due to prioritisation of reforms where there was Government buy-in and technical advisers ability to work poitically and build relationships with government officials. Risk was assessed as moderate in 2018 because we had just two technical advisers working on very carefully selected reforms and the consultants had proven track records of building successful relationships in difficult environments.

Update on partnership principles

DFID monitors the Government of Sierra Leone’s (GoSL) commitment to the UK’s Partnership Principles on an on-going basis. The assessment in July 2017 concluded that the environment was not compatible with the continuation of financial aid. The most recent update was done in June 2018. There is evidence of credible commitment to each of the four partnership principles.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

The partners over the lifetime of the programme have been the Government of Sierra Leone, Adam Smith International (ASI) and two technical advisers contracted through Ernst & Young. Government partners had an optimism bias and this presented challenges for the programme. Ultimately two of the four payment-linked targets were not met and so only half of the financial aid was disbursed. Lack of credible commitment to reform resulted in DFID stopping the financial aid component.

ASI was a good partner to work with on this programme. ASI flagged risks early and discussed mitigation strategies with DFID. ASI proactively managed the programme, advising on areas to scale up and down on, as well as being responsive to DFID and Government needs for adjustments to the programme. ASI worked to a milestone-based contract making forecasting easier. Where there were delays to outputs being met, ASI communicated this early and this helped keep DFID forecasts accurate. The vast majority of milestones were completed on time.

The two technical advisers procured through Ernst & Young were also good partners, engaging in regular dialogue with DFID to manage risks and communicate achievements. The procurement mechanism was a framework that allows DFID to procure specialist expert advisers quickly. There were some issues with the management arrangements of this mechanism which were raised with DFID’s procurement and commercial department and DFID centrally is reviewing this.

Date of last narrative financial report	June 2016
Date of last audited annual statement	November 2016

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Monitoring in 2018 involved regular meetings between DFID and the technical advisers to review trackers for each adviser outlining tasks, associated Ministry of Finance actions required to deliver against each output, and a traffic light system to communicate easily to DFID and Government when something was off track. DFID also met with the counterparts in the Ministry of Finance to discuss the progress, add pressure where necessary and get feedback on the work they were doing alongside the technical advisers. Feedback was consistently positive. Discussions with Ministry of Finance staff led to some adjustments to the work programme, for example focusing more time of one technical adviser on the new PFM Reform Strategy relative to revenue work based on trends and needs in the Ministry at the time.

Evidence

The PEFA has generated a wealth of evidence on PFM systems in Sierra Leone and the technical advisers have ensured this is reflected in the new PFM Reform Strategy. The next DFID programme will build on this so that it works in the areas of greatest need (i.e. where there is buy-in and potential for high impact).

Learning

Lessons learned over the lifetime of the programme:
- Where there was openness to reform, financial aid helped to catalyse action, although commitment to reform varied across departments. Policy dialogue between DFID and the Government worked very well where objectives were aligned.
- It is vital to have a technical assistance team that can balance the need to build strong relationships with the need to operate politically and have difficult conversations with government counterparts. This paid off in the form of close collaboration leading to success in implementing stretching reforms.
- A flexible programme is important in an unpredictable context to efficiently achieve objectives. Technical advisers need to remain focussed on achieving outputs and outcomes, rather than holding focus at the activity level. The programme was able to align to the emerging priorities of the Ministry of Finance, as the technical advisers had the flexibility to respond to requests from government counterparts.This helped strengthen the relationship and deliver on the major reforms planned.

Progress on recommendations from annual reviews for this programme

Recommendation	Progress
Ensure the PEFA is completed on time and to a high standard. It will be subject to a review by the PEFA Secretariat in Washington DC.	The PEFA was completed exactly to time and the PEFA Secretariat issued a certificate of quality assurance (the PEFA check).
Two TA positions to be filled, running from January to August 2018.	This was done and the TA provided support on key areas including payroll and tax expenditures.
DFID needs to continue to lead and shape the PFM Donor Working Group. The group should continue to develop joint messages on PFM for Heads of Mission to take up with the GoSL.	This was done. Joint messages are agreed and passed on after each meeting. DFID successfully handed over the Chair of the Group to the World Bank.
GoSL and DPs should ensure that the Payroll Strategy forms the basis for all interventions in the wage bill reform area.	The TA working with PFMRU ensured that the Payroll Strategy underpins the payroll aspects of the PFMRS. This included raising the profile of manpower planning in the PFMRS.
The PFM Working Group must put a spotlight on procurement and influence the EUs approach to procurement reform to ensure their TA helps to institutionalise recent changes to the way procurements are made.	The PFM Donor Working Group has yet to focus in on procurement due to competing priorities. However, a former BCS TA consultant is now leading the EU work on procurement, ensuring continuity of BCS reforms.
DPs should discuss progress of the ECMC with senior officials in MOF to ensure it is still operating.	This has been one of the PFM Donor Working Group’s joint messages and is being followed up with the new GoSL. ECMC is still meeting.
The TA should ensure that fiscal risk templates are being completed regularly and help institutionalise use of the different instruments.	Departments are collating information for the 2019 fiscal strategy statement which reports on fiscal risk. So this is happening.
DFID and the GoSL should work with the World Bank to ensure World Bank-led reforms to rollout systems to automate revenue administration are accelerated.	DFID and GoSL have put pressure on World Bank to accelerate these reforms and more efficiently solve problems. There is some limited evidence of improvements.