To :	Judith Herbertson	From: / Ext: / Date: / CC:		Jo Simpson / 2561 / 30 October 2013 / Asyia Kazmi / Lynn MacAulay / Atif Rafique / Saiqa Kanwal / Mahvesh Adil

## The Pakistan Education Task Force Annual Review
## Issue
How to approach the 2013 Pakistan Education Task Force (PETF) Annual Review.
Recommendation
I recommend that you approve the Annual Review (Annex A) and overall score of A.
Information
1. The PETF programme was approved in 2009 (total budget £2 million) to address the poor delivery of public education through supporting political leadership to champion reform and move bureaucracy to focus on results and outcomes. The Task Force was mandated by the Pakistan Prime Minister to bring the best international and national educationalists and other renowned experts, including Sir Michael Barber, around a common agenda. The initial component under PETF concluded in 2011 with the high profile March for Education campaign and engagement with the Government of Baluchistan to develop an education action plan. Between 2011 and 2012, PETF did not fund any additional activities but the budget line was kept open by DFID Pakistan to maintain flexibility to fund standalone activities as the education programme scaled up through the 2011 Operational Plan framework
2. At the start of 2013, two additional projects were approved under PETF:
- Support to the second phase of the effective education budgets initiative (EBBI) implemented by the Institute for Social and Policy Sciences (ISAPs). The objective is to generate evidence based debate and demand for effective utilisation of the education budget in Pakistan (total budget £270,000). The first phase was supported under the Strengthening Education in Pakistan programme which was subsequently closed down.
- Support to The Citizens Foundation (TCF) to develop the toolkit ‘TCF in a box’. Recognising the proven success of the TCF model across Pakistan, the objective of this project is to develop a primary school franchise model for low cost education providers (total budget £108,860).
1. An Annual Review of PETF was last undertaken in November 2010 by an independent team which scored the programme a ‘C’. The Annual Review identified gaps between the concept and the design of the project, particularly the limitations of the log frame which did not include criteria which allowed the team to capture the major achievements of PETF. However, the team recommended PETF continue as a much needed platform to focus political and policy attention on education, a no cost extension of £0.8 million (bringing the total value to £2.8 million). However, in reality the log frame was not revised and no new activities undertaken until EBBI and TCF were funded in early 2013. In addition, no Annual Review was conducted in 2011 and 2012; although in retrospect this should have happened. The last entry on ARIES is therefore the 2010 Annual Review.
2. The Innovation and Outreach Team undertook an internal desk based Annual Review in May 2013 to monitor progress on EBBI and TCF. The original PETF programme was designed and implemented before the new business case process therefore it was proved difficult to complete the review in the new Annual Review format. Given competing demands on the team, they were also directed by the Head of Basic Services to be proportionate when conducting the Annual Review. In the absence of an updated overarching log frame, the team used the two separate log frames for EBBI and TCF to evaluate progress and a generic template rather than the new Annual Review template[1].
  [1] This was adapted from the format used for the ‘Strengthening Education in Pakistan’ project completion report; which was also designed prior to the new business case process and had no overarching log frame.
3. The 2013 Annual Review was presented to the DFID Pakistan Programme Board in August, recommending EEIB score an A+ and TCF an A. It was met by a mixed reception and received various comments to strengthen the text. These included: (a) link the Annual Review to the log frames for the two activities; (b) provide more description on outcomes / impact; and (c) provide more detail on TCF and sustainability. The minutes of the Programme Board state that the Annual Review was not approved and request the Team to come back to the Board with the revised document (Annex A).
Advice
Given the recent change in the Programme Board modus operandi (which mean that Annual Reviews which score an A or above can be signed off by the relevant Group Head) and the need for proportionality, I recommend that you approve the revised Annual Review at Annex A with an overall A score.

I also recommend that the team move to a project completion report in early 2014 and consider developing an overarching logframe for the programme to form the basis for the review.

Jo Simpson
Deputy Head and Programme Manager of Basic Services Group