Girl Hub: Independent Annual Review

For the Department for International Development

August 2013

Annual Review

Project Title: DFID/Nike Foundation Girl Hub Project (Aries project number 20186)
Project start and end dates: 1 December 2009 to 31 May 2014
Date review undertaken: 2 May to 19 July 2013
## Introduction and Context
What support is the UK providing?
The Department for International Development (DFID) and the Nike Foundation are working together in a strategic collaboration called Girl Hub to break the cycle of inter-generational poverty through investment in adolescent girls. / DFID is contributing £12.8 million (£11.6 million cash and £1.2 million in in-kind). The Nike Foundation is contributing £9.1m (in kind and cash). The Project (Girl Hub) started on 1 December 2009 and will end on 31 May 2014. / This Review is of the DFID global grant agreement to the Nike Foundation for the Girl Hub project. To date the DFID global grant has been used to fund Girl Hub activities in Rwanda, northern Nigeria and Ethiopia as well as globally (led from Girl Hub London). Since November 2011, Girl Hub Ethiopia has been funded separately by DFID Ethiopia (with a separate business case and logical framework), so the work in Ethiopia is not part of the review.

What are the expected results?
The outcome of the Project as set out in the logical framework is that “social communications, evidence and partnerships drive action for girls at scale”. This outcome has changed since the last DFID Annual Review to focus on the immediate effect of the Project on partners’ policies and programmes, rather than longer-term changes in attitudes, which has been moved to the impact level of the logical framework. / The current logical framework sets four key outputs for delivery: / Girl Hub catalysing role established and effective / Branded social communications activated and sustained / Research and girl-centred participatory monitoring and evaluation (PM&E) generates real-time, robust evidence and insights. / Girl Hub organisational development implemented / Output level indicators, with associated milestones, were set for May 2013 and 2014 (the end of the project extension). One outcome level milestone was set for 2013 of the number of additional girls attending girls’ groups at least once a month in Nigeria and Rwanda. / The details of the output indicators and milestones are set out in section A of this review.

What is the context in which UK support is provided?
Focusing on girls and women has been a priority for DFID since the DFID Strategic Vision for Girls and Women was launched in 2011. It says: / “If we reach girls, in particular, early enough in their lives, we can transform their life chances. Giving girls greater choice and control over decisions that affect them helps break the cycle of poverty between one generation and the next. It enables us to stop poverty before it starts.[1]” / The Nike Foundation focuses exclusively on adolescent girls and has a similar approach. They describe their mission as “unleashing the girl effect”. Many other donors and development actors also subscribe to the theory and there is much evidence to support the approach.[2] / In 2010 DFID and the Nike Foundation established a new organisation called Girl Hub. Girl Hub’s aim was to produce ideas backed up with evidence on the best way to unlock the potential of girls and then provide advice to donors and governments on how to turn these ideas into action through their policies and programmes. Girl Hub would not run large-scale programmes itself; rather the aim was to influence other organisations that did. This included providing advice and support to DFID programmes so that these made the most of opportunities to have an impact on girls. The social communications element of the programme would complement these efforts to influence mainstream programmes. An important element of this work is the development of “brands” that inspire, motivate and encourage girls to make the most of the new opportunities for girls provided by the policies and programmes of others. / Beyond DFID and the Nike Foundation there is support for the approach: in both Rwanda and Nigeria there are a number of non-government organisations (NGOs) that are similarly committed. The review team also found strong support for the approach from the Government of Rwanda. / When Girl Hub was first set up the priority was to establish headquarters in London, country offices and to get these up and running and working effectively. The original programme document for Girl Hub under‑estimated the amount of work involved in this, and it has taken longer than envisaged to establish country offices with the required complement of staff. Some countries have been easier to work in than others. It has been easier to operate in Rwanda than northern Nigeria, particularly since the deterioration in the security situation there. / Although the approach of Girl Hub rests on “catalysing” and influencing other organisations, this review, like the last annual review, found that Girl Hub has been more successful where it has done things itself. In Rwanda, for example, there has been greater progress in the development of the Ni Nyampinga brand, and dissemination of it through a magazine and radio show, than in influencing other development programmes. / This Review also reinforced the finding of the last annual review that there is a need to ensure that work across all outputs is pursued with equal energy and balance and that attention in one of the areas does not dominate at the expense of other work.
[1] DFID 2011: A New Strategic Vision for Girls and Women: Stopping Poverty Before it Starts. DFID. Available at: http://bit.ly/1bcGnMd. See also DFID 2012: The Strategic Vision for Girls and Women One Year On. DFID, July 2012. Available at: http://bit.ly/12y26JQ.
[2] For the evidence base there is an abundance of sources, see for example Bruce, J. 2007: Reaching the girls left behind: targeting adolescent programming for equity, social Inclusion, health and poverty alleviation. Paper prepared for Financing Gender Equality; a Commonwealth Perspective, Commonwealth Women‘s Affairs Ministers' Meeting, Uganda, June 2007. Available at: http://bit.ly/18es864. Lloyd, C. & Young, J. 2009: New Lessons: The Power of Educating Adolescent Girls. Population Council. Available at: http://bit.ly/1dx3BJG.

## Section A: Detailed Output Scoring
Output 1: Girl Hub catalysing role established and effective
Output 1 score and performance description: A – outputs met expectation / Output 1 is focused Girl Hub’s influencing of “scale partners” (e.g. donors, international organisations) so these partners increase the impact of their programmes on girls. / It is not straight forward to attribute changes in other organisations programmes directly to Girl Hub activity. Girl Hub is operating – particularly within DFID – in an enabling policy environment and is as much a consequence as a cause of the increased momentum and interest in ensuring that girls are a priority in country strategies and the full range of projects that make up the strategies, and not just those designed to specifically target girls. / There is also widespread acceptance beyond DFID of the case for investing in girls, so Girl Hub is often working with organisations that are already convinced of the merits of building a focus on girls into their programmes.[3] / However, it is the judgement of the review team that Girl Hub and the Nike Foundation have contributed to ensuring that a focus on girl-centred programming has been maintained in DFID and other partners. / Progress against expected results / Indicator one: Quality of Girl Hub's influence as a catalyst in activating others to integrate girls into their work / Indicator one assesses how effective Girl Hub has been in influencing other organisations. The means of verification is a questionnaire – called the Qualitative Assessment Scorecard (QAS) – about Girl Hub’s engagement with other organisations. Questions are answered using a four point scale (“strongly agree”, “agree”, “disagree” or “strongly disagree”) and an aggregate score is used overall to measure achievement against the indicator. / The QAS provides a snapshot of the quality of Girl Hub’s engagement with partners and other organisations they seek to influence. The focus is on the qualitative aspects of the output rather than the numbers of items delivered. The individual QAS reports set out the justification for the aggregate score. / The QAS is undertaken every three months. Girl Hub staff complete the questionnaires, sometimes with outside facilitation, and the views of outsiders are included. The review team checked with external stakeholders to ensure that Girl Hub had not inflated their performance. / The review team found that the QAS incorporates inputs from external stakeholders, and that Girl Hub staff are aware and critical of their performance. For example there are cases where staff decided that their performance has declined during the year. / The questions in the QAS are: / Has Girl Hub influenced high level (global and/or national) champions (e.g. religious leaders, political leaders and other opinion formers) to create political space at national and global level? / Has Girl Hub engaged with scale partners with influence over strategies, policies, programmes and budgets? / Have scale partners responded positively to Girl Hub’s catalysing role [based on self-assessment scorecards/interviews with 2-3 key scale partners]? / Have scale partners invited or accepted staff capacity building initiatives by Girl Hub? / Has Girl Hub provided remote or in-country support for strategy, policy or programme review, design or delivery? / Is there evidence that scale partner strategies, policies and programmes have changed as a result of the Girl Hub influence? Do these changes reflect a girl-centred approach? / How has Girl Hub enabled effective follow up after evidence and energising? / Milestone / 'A score of 3 = “disagree” or better achieved in assessments of quality of integration of adolescent girls' priorities (cumulative from baseline). / Achievements against indicator one / QAS 1[4] QAS 2 QAS 3 QAS 4 / Girl Hub London Agree/disagree Agree Agree Agree / Rwanda Agree Agree Disagree / Nigeria Agree Disagree Disagree / Girl Hub London: / Girl Hub met high-level champions to generate support at a global level. Girl Hub London has also engaged with scale partners such as DFID, with influence over strategies, policies, programmes and budgets. / The Nike Foundation and Girl Hub took part in the 2012 London Family Planning Summit. With Restless Development, the International Planned Parenthood Federation (IPPF) and others, Girl Hub used disaggregated data to high light the scale of the problem for adolescent girls and young women. This contributed to girls being included in the summit mission statement and outputs. / Girl Hub has so far consulted 250 adolescent girls and 25 technical partners on the post-2015 Girl Declaration. This contributed to the Declaration including the voices of girls and having wide ownership and support. Kathy Calvin, Melinda Gates, Barbara Bush, Naveen Rao (Merck for Mothers), Nyaradzayi Gumbonzvabda (General Secretary of World YWCA) and Chelsea Clinton (Clinton Foundation) have championed the work and raised its profile. / Girl Hub has shared its SenseMaker® pilot work with Progressio, Save the Children, Plan International, Action Aid, Christian Aid and Women Kind. / Girl Hub worked with DFID, OECD DAC and ODI to co-host a technical workshop on social norms and adolescent girls during 2013. The event brought together 40 experts to discuss research and global indicators to measure shifts in the social norms affecting adolescent girls. The workshop was preceded by a two-week online discussion convened by Wiki-gender and Wiki-child.[5] / Girl Hub supported DFID in the development of the business case for the DFID funded Global Girls Research Initiative (GGRI), including convening a meeting of over 60 international girl experts to identifying gaps and priorities relating to adolescent girl research and commissioning 5 technical review papers. / Feedback from stakeholders and participants at these events highlight the contribution that Girl Hub brings to such events, particularly the creative and innovative approaches used to communicate ideas.[6] The GGRI meeting experienced a high level of demand showing that there is interest among experts in sharing lessons and developing joint strategies.[7] A member of the review team took part in the GGRI meeting and can confirm that the meeting generated useful discussions regarding filling the gap in global knowledge on empowering adolescent girls. / Girl Hub has been approached by DFID departments and country offices beyond their current focal countries (Rwanda, Nigeria and Ethiopia) for support. In the Democratic Republic of Congo (DRC) Girl Hub worked with DFID to develop a pilot project focusing on adolescent girls. Support provided included: analysis & appraisal of the evidence base for different approaches to innovating and influencing and the necessary scale and scope of a pilot programme; contributions to the theory of change and logical framework; comments on proposals for pilot/innovation funding; and examples of innovative programming on girls economic empowerment from elsewhere. / Girl Hub staff were consulted during the design of the Girls Education Challenge Fund (£330 million) and are continuing to support this having been asked to share Girl Hub’s learning with successful bidders from the private sector at the launch this year. Girl Hub is co-managing the design of the Direct Assets to Girls Incubator programme. / During interviews a DFID adviser stated that Girl Hub “had more flexibility than DFID in the present business case funding environment, so they’ve been able to provide seed funding for background papers and to bring together policy actors, alongside their own technical inputs, to move this research initiative forward [we] have very much valued this collaboration and the financial and technical support.”[8] / Girl Hub has also applied to be a member of the UK Gender and Development Network. / Girl Hub partners recognise what the Nike Foundation and Girl Hub have done to make adolescent girls a priority for development organisations. However, the distinction between what the Nike Foundation does and what Girl Hub does is not always clear, particularly at the country level.[9] / Some concerns have been raised about Girl Hub’s main message – the Girl Effect (http://www.youtube.com/watch?v=1e8xgF0JtVg) – and the original Theory of Change which focused on the girl and her ability, given the right support, to act as a catalyst for her own development and that of her community. They raised concerns that the evidence that underpins this message is weak and that empowering girls also requires changes in the wider enabling environment that all too often prevents girls from reaching their full potential. For them, motivating and inspiring girls, and providing opportunities are not enough: the attitudes and behaviour of others also need to change.[10] / Girl Hub’s revised theory of change (figure 1, p.42) has taken some of these concerns into account. It emphasises the links between the different programme strands of advocacy, programming, brand development and evidence and the work to change the wider enabling environment and social norms that impact on girls. Girl Hub’s Monitoring and Learning Plan (2013) sets out how the theory of change has been developed drawing on evidence generated in the project to date. This has not yet been widely disseminated and the report of the supporting theory and evidence is not yet publicly available. / The review team noted that nearly 1.5 million people have viewed the Girl Effect film online. A similarly captivating visual message is now needed that includes the importance of the enabling environment for girls’ empowerment. / Girl Hub Rwanda: / For the last three QAS exercises Girl Hub Rwanda gave themselves scores of ‘Agree’, ‘Agree’ and ‘Disagree’ for indicator one, output one. / A strategic plan for influencing policy change has been prepared and a Girl Centred Practice and Strategy team with two technical experts on girls’ programming has been established to turn the plan into action.[11] This should help strengthen the links between the three work areas of knowledge and research, branding and communications and catalysing and influencing. As the team has only recently been created and recruited, it is too early to assess the impact of the team. / The review team held discussions with Government and other non-government organisations (NGOs) and found that there was knowledge and awareness of Girl Hub’s work and that this had been effective at getting girls built into a range of programmes and policies, and involving girls in policy and programming discussions in Rwanda. / Girl Hub Rwanda brought girls together to contribute to the following policies: / The National Adolescent Sexual Reproductive Health and Rights Policy (ASRH) – the ASRH Strategic Plan now includes a number of Girl Hub recommendations.[12] / The National Youth Policy – Girl Hub ensured that girls’ thoughts and suggestions were fed directly into the policy drafting process with a group of girl representatives attending the national stakeholders’ validation meeting.[13] / The Family Promotion Policy – Girl Hub convened vulnerable girls and parents of vulnerable girls separately to review and provide feedback on the draft. These are being considered for inclusion in the final document. / A girl journalist from the Ni Nyampinga magazine and radio show was part of the Rwandan delegation to the Commission on the Status of Women in March 2013.[14] Girl Hub Rwanda also ensured the voices of girls were represented in the ‘MY World’ survey that was designed by the UN as part of the post-2015 development framework consultation process. A key finding was that violence against girls emerged as a significant issue for older girls and this will contribute to ensuring action is taken to include this issue in follow-up action. The team was able to include information on this in briefings for meetings between President Kagame and the UN Secretary General, at which the post-2015 priorities for development were discussed.[15] / The Minister of Youth and ICT has supported the appointment of 15,000 Ni Nyampinga Ambassadors across Rwanda. Each girl will be elected by her peers to represent them in the national youth council and will be a member of the local village committee. Girl Hub is working with the Ministry on this initiative and is developing a digital interactive platform with the Praekelt Foundation to connect and support these girls.[16] / The 12+ programme is providing opportunities for Girl Hub to strengthen their relationship with DFID as well as the Rwandan government.[17] The Girl Hub consultant on the 12+ programme has worked with DFID on the design of the programme (discussion with DFID Rwanda 30 October 2012). The programme has now been successfully included in the Health Sector Strategic Plan and a number of consultation workshops were held during the year, which brought together different ministries alongside girls and Girl Hub staff to redesign the national 12+ scale-up.[18] / The success Girl Hub has enjoyed in Rwanda is in large part due to the constructive political environment. It is a small, relatively homogeneous (linguistically) country, with strong political leadership, a relatively high literacy rate and a strong commitment from the government to the country’s development. The same features – the enabling policy environment – that make development efforts more generally effective apply equally to the work of Girl Hub. Access to ministers is easy and they engage easily and often with development partners. The review team was able to meet ministers and senior Government staff at quite short notice all of whom were aware and supported the work of Girl Hub. In addition, when Girl Hub was first set up in Rwanda, it was offered and used temporary accommodation in the Presidential Offices alongside the Imbutu Foundation. / Girl Hub Nigeria: / For the last three QAS exercises Girl Hub Nigeria gave themselves scores of ‘Agree’, ‘Disagree’ and ‘Disagree’ for this indicator. / In their latest QAS highlighted the impact Girl Hub has had on DFID Nigeria in the last quarter. They have now moved to make an impact beyond DFID but scored themselves lower than in the last QAS as they are starting in a new field and have yet to change the quality of systems at scale in the area of ‘safe spaces’.[19] / In Nigeria examples of outputs include: / In four northern states 17,160 girls participated in safe spaces through the Programme for Reviving Routine Immunisation in Northern Nigeria / Maternal and Neonatal Child Health (PRRINN/MNCH), for which Girl Hub provided technical support and assistance. This support consisted of a workshop for programme staff in February 2012. This Programme has now established young women’s support groups that provide adolescent mothers with maternal health guidance and support.[20],[21] / Other DFID funded programmes include targets for reaching adolescent girls through safe spaces partly as a result of Girl Hub Nigeria, including: Mobilizing for the Millennium Development Goals (M4D); Voices or Change (V4C); Girls Education Programme (GEP3); and the Nigerian Stability and Reconciliation Programme (NSRP). Over the next four years 1.23 million girls are expect to be reached. It should be noted, however, that DFID Nigeria has set a country level target for safe spaces programmes, which has probably made a more significant contribution than the work of Girl Hub. / In 2013 Girl Hub Nigeria, Girl Effect University (a training programme that has been developed by the Nike Foundation for delivery to its partners[22]) and the Population Council organised a meeting for safe space practitioners. The aim was to exchange knowledge and experience about safe spaces and create an informal “community of practice” that would continue to exchange ideas with each other. The review team discussed this event with the Population Council and other participants. This is one of Girl Hub’s activities that is most valued by external stakeholders. The Girl Effect University facilitated participatory learning event that girls were included in. Without Girl Hub and the close relationship with the Nike Foundation, the Girl Effect University may not have supported this. / Girl Hub has also emphasised the importance of communications and messaging for young people and the Voices for Change (V4C) programme now has a major communications component influenced in part by Girl Hub Nigeria and London. / Feedback from DFID stakeholders in Nigeria confirms the added value of Girl Hub, particularly regarding communications and safe spaces. DFID feedback is that Girl Hub Nigeria was successful in forming partnerships with DFID programmes and encouraging them to focus resources on adolescent girls. A key strategy employed that has a positive impact on the understanding of DFID staff regarding the realities faced by adolescent girls is their ‘Girl led journeys’. Staff are taken to villages to spend time with girls as they go about their daily lives. Feedback to the review team from DFID staff that have taken part was positive. / Feedback to the review team from the Voices for Change programme (V4C) has highlighted Girl Hub’s role in supporting the communications element of their work. There are, however, concerns about the approach taken so far to the development of the “brand platform”. The current security situation in the North remains a cause for concern and V4C commented that the branding and communications approach would need to be sensitively adapted and implemented in northern Nigeria so it does not exacerbate tensions.[23] / Girl Hub is not only working with donors and NGOs. In recognition of the role traditional leaders play in determining the lives of girls, Girl Hub Nigeria hosted a religious roundtable with a number of state and local level Imams from northern Nigeria in August 2012. They have produced a draft strategy and write-up of the roundtable work.[24] / Indicator two: Level of new national and global scale partner resource allocations for girls due to Girl Hub influence. Number of major investments secured disaggregated by DFID and non DFID scale partners. / Milestones: / DFID Global: +1 (Global Girls' Research Initiative) / DFID Rwanda: +1 (12+ Scale Up) / Achievement against indicator two: / Girl Hub has met this milestone: / Five background papers completed and disseminated (2013) and an international experts workshop conducted (October 2012) in contribution to the Global Girls' Research Initiative (GRRI). The DFID business case not yet complete. / 12+ scale-up business case approved December 2012. The Programme is at bid stage. / Recommendations / DFID guidance for outputs, indicators and targets is that they should be realistic and achievable rather than aspirational. The first indicator for output 1 is focused on the quality of engagement of Girl Hub with DFID and non-DFID “scale partners”. The second indicator measures the response of ‘scale partners’ to this engagement over which the Girl Hub has had little or no control. We therefore recommend that indicator 2 is revised to focus on the contribution that Girl Hub makes to scaling-up resources rather than the quantity of resources eventually allocated. For example, a target could be set for the number of programmes Girl Hub will engage with and contribute to that have the potential to unlock the potential of girls, and the nature of the influence they would bring to bear. / The UK Gender and Development Network is an important sounding board for the work of Girl Hub and has been critical of their approach in the past, in particular the need to change wider attitudes and behaviours towards girls. The revised Theory of Change developed by Girl Hub answers many of their concerns and we recommend that the revised Theory of Change be disseminated to the gender and development community. The original Girl Effect film was praised for reaching and convincing a wide audience of the merits of the girl effect. We further recommend that a similarly convincing video should be made that highlights the importance of changing the attitudes and behaviours of wider society. / We recommend that Girl Hub develops in each country an influencing strategy that sets out who they want to influence, why they are targeting this individual/organisation/group in terms of the results they expect to achieve and how this links to the other areas of their work. This will enable Girl Hub to focus their influencing and catalysing work where it has the most potential to have an impact. In the absence of a strategy there is a risk that they will be drawn into opportunistic and reactive work, responding only to the latest opportunity. / Impact weighting and risk / Impact weighting: 35% / Revised since last Annual Review? Yes. The output has changed since last annual review (previously “partners innovate and deliver results for adolescent girls at scale”) and the impact rating has been revised (from 25% to 35%). / Risk: Medium / Revised since last Annual Review? Yes, the risk has been reassessed against the new output.
[3] See for example, Plan International 2009: Because I am a Girl. The State of the World’s Girls 2009. Available at: http://bit.ly/1fZe562.
[4] Dates for QASs: London: QAS 1 13th of July 2012, QAS 2 24th of September 2012, QAS 3 December 2012, QAS 4 February 2013. Rwanda: QAS 1 July 2012, QAS 2 11th December 2012, QAS 3 18th of March 2013. Nigeria: QAS 1 August 2012, QAS 2 December 2012, QAS 3 March 2013.
[5] Progress Report, April 2012 – 2013.
[6] Girl Hub London, Quarterly Scorecard (QAS) Exercise, December 2012. The review team heard similar feedback about the events organised in Nigeria by the Girl Effect University. See paragraph 46 on page 6.
[7] Ibid.
[8] London office Quarterly Scorecard (QAS) Exercise, December 2012.
[9] Ibid and February 2013.
[10] London office Quarterly Scorecard (QAS) Exercise, December 2012 and Grosser and van der Gaag, 2013.
[11] Girl Hub Rwanda, QAS Exercise, FY13, Quarter 3: results report 26 February 2013.
[12] Girl Hub Rwanda ASRH Policy Process Documentation 2013, and independent review team interviews with MoH officials.
[13] Girl Hub Rwanda National Youth Policy Process Documentation 2013 and interview by independent review team with Minister of Youth and Influencing Technology.
[14] Independent review team interview with the girl who participated in the delegation to CSW.
[15] Independent review team interview with UNICEF, Kigali.
[16] Progress Report April 2012 – 2013 and independent review team interviews with Ministry of Health Officials and with Minister of Gender.
[17] The 12+ programme aims to improve knowledge and life skills among young girls. It includes training and mentoring to develop self-esteem, leadership, social capital health and personal finance. In 12+, approximately 600 10-12-year-old girls from four districts in Rwanda meet weekly in youth centers and schools for training modules and activities focused on topics such as puberty, HIV, delaying sexual debut and financial literacy. Older mentors lead each group of 25 girls through the mixed-method, 18-week pilot program and facilitate additional “learning journeys,” which include visits to local banks and health centers.
[18] Girl Hub Progress Report April 2012 – April 2013.
[19] “Safe space” is a term for an area or forum where either a marginalised group are not supposed to face standard mainstream stereotypes and marginalisation, or in which a shared political or social viewpoint is required to participate in the space.
[20] Girl Hub Progress Report April 2012 - April13.
[21] Independent review team interview with Fatima Adamu, PRINNN/MNCH consultant.
[22] Girl Effect University (GEU) is a mobile university that provides 2-4 day courses to people involved in girl-focused programming. GEU participants bring their own programme design questions to the workshops, so learning is tested and ready to be applied upon return to work. Participants are also linked to a global network of GEU alumni, coaches and experts who serve as a resource in their work with adolescent girls. GEU is supported by the Nike Foundation, the Bill and Melinda Gates Foundation and the World Bank. It has a permanent 8 person team based at the Nike Foundation HQ in Portland, OR at the Nike Foundation. This team works with a team of consultants who are hired specifically to deliver the workshops in-country facilitators, etc). GEU serves the Nike Foundation and Girl Hub priorities.
[23] Review team interviews with V4C staff.
[24] Review team interview with Girl Hub Nigeria lead on engagement with Imams and verification interview with DFID senior gender adviser.

Output 2: Branded social communication activated and sustained
Output score and performance description: A (output met expectation) / The Review Team concluded that a score of A was justified for output two. This assessment was not arrived at without some difficulty, given that Girl Hub Nigeria has not managed to activate and sustain its branded social communications platform. Performance in Nigeria, however, has been balanced by better performance in Rwanda, where good progress has been made against the indicators and milestones, in some cases exceeding the milestones. / Girl Hub Nigeria did support a 13-week radio show in May 2012 – Carbin Kwai – designed to reposition girls in the public discourse and provide a platform for community dialogue. This was broadcast on government stations, Radio Kano and commercial station Freedom Radio and reached an estimated audience of 5 million. / In Rwanda, Girl Hub launched Ni Nyampinga magazine. This is produced by girls for girls and is Rwanda’s largest media publication (90,000 copies per issue). Research indicates that each copy is being shared with five others and that girls are forming Ni Nyampinga clubs. Seventeen trained girl journalists and photographers provide the content and messages are reinforced by the Ni Nyampinga radio show (60 to date) which is broadcast nationwide through 8 radio stations. / Progress Against Expected Results / Indicator one: Number of citizens reached by branded communication strategies and technologies (disaggregated by age and sex, socio-economic group, geography). / Milestones: / Rwanda: 135,000 girls reached with Ni Nyampinga magazine. / Nigeria: Brand platform is launched and May 2014 targets are defined. / Achievements against indicator one: / Girl Hub Rwanda: / Every three months, 90,000 copies of Ni Nyampinga magazine are distributed across each of Rwanda’s 30 districts. A survey of awareness and readership of the magazine among 3,005 people (of whom 700 were girls aged 13-19) found that awareness of Ni Nyampinga magazine was 31% among all respondents. Of the girls in the survey aged 13 to 15, awareness was 39%, and of girls aged 16 to 19, awareness was 43%. Of the total respondents who were aware of Ni Nyampinga magazine (918 people), 81% of girls aged 13 to 15 (231 respondents) and 80% of girls aged 16 to 19 (255 respondents) had read the magazine. The survey of readership also revealed that each magazine can be read by up to 5 girls, and that girls often read the magazine in groups. / It is not possible to conclude with absolute certainty that Girl Hub has achieved the milestone of a reach of 135,000 girls by May 2013, as the survey was not representative of the population of Rwanda as a whole, nor of adolescent girls in Rwanda. The data sets do not allow the reviewers to produce absolute numbers. However, given the fact that readership among girls often takes place in groups, we can conclude that it is likely that this milestone has been met and has probably been exceeded. / Girl Hub Nigeria: / Girl Hub has not launched its brand platform, magazines or other branded social communication products to date. There are three reasons for this: 1) the deteriorating security situation in northern Nigeria entailed the relocation of the office from Kano to Abuja, with associated disruption to its work; 2) it proved harder than expected to find creative partners in Nigeria that had a good understanding of the environment in northern Nigeria, where the girls that Girl Hub Nigeria wanted to work with live; and 3) it proved more difficult to recruit staff than was the case in Rwanda, with the office only became fully staffed during this review. / We note that the risks of not achieving this milestone should have been at least partly known when the delivery date was agreed in September 2012. Insecurity was explicitly recognised as a risk in the logical framework (dated September 2012). However, the assumption that good quality creative talent would be available to help develop and test the brand was not recognised and the Girl Hub team has found it hard to find a local creative partner that is sufficiently sensitive to the cultural and social values of the north. / Girl Hub Nigeria has not met this milestone. However, noting that a number factors including the challenging operating environment in Nigeria were not within Girl Hub’s control, we conclude that Girl Hub should not be penalised for not achieving this milestone, especially given the success in Rwanda. Girl Hub must learn from this experience and ensure all risks are adequately factored into work plans and target results. / Indicator two: Number of repeat visits (country specific) (e.g. website hits, radio programme repeat listens, number of teenage magazines repeat purchases). / Milestones: / Rwanda: 50% repeat (more than one issue) Ni Nyampinga magazine readership; 50% repeat radio show listeners. / Nigeria: 80% repeat consumers of Girl Hub Nigeria local brand. / Achievement against Indicator two: / Girl Hub Rwanda: / 61% of those people who had read the Ni Nyampinga magazine (671 people of the sample) had read it more than once. Repeat readership is marginally higher among girls aged 13 to 15 and 16 to 19 years old. Though overall repeat readership of the magazine is low, we conclude that Girl Hub Rwanda has exceeded the target for this milestone. / 57% of respondents (581 people of the sample) who had ever listened to the Ni Nyampinga radio show said that they had listened to one to two shows, 22% said that they had listened to three to four shows while 7% said that they had not listened to the show during the specified period. Repeat listens are higher for girls aged 13 to 15 and girls aged 16 to 19. We conclude that Girl Hub Rwanda has exceeded the milestone. / Girl Hub Nigeria: / Because of the delay in launching the brand, no branded social communications are currently in circulation in northern Nigeria. Therefore, no loyalty and retention of the branded products has been developed. We can conclude that Girl Hub Nigeria has not met this milestone, but should not be penalised in the overall score for this output for the reasons set out in paragraphs 63-4 of this review. / Indicator three: Quality of social communications content relevance and reach assessed through QAS. / Milestone: / A score of 2=Agree or better achieved in assessments of quality of social communications content, relevance and reach (cumulative from baseline). / Achievements against indicator three: / QAS 1 QAS 2 QAS 3 QAS 4 / Girl Hub London - - - - / Rwanda Agree Agree Agree / Nigeria Disagree Disagree Disagree / The milestone is an assessment of the quality of the social communications work. The assessment is made by the Girl Hub team, with inputs from to outside stakeholders where possible, and is based on the aggregate reply to the following questions: / Has the process of social change communications development been built on locally relevant knowledge (including a focus on the bottom 40%)? / Has social communications platform building come out of Girl Hub evidence/insights? / How effective has Girl Hub been in building trust in its social communications platforms? / How effective has Girl Hub been in tailoring its social communications work to changing context and need? / To what extent have (unintended) risks been considered in social communications platform building? / How many people have been reached over time? / Is Girl Hub reaching the people (girls and gatekeepers) we need to reach (including the poorest 40%)? / What conversations and changes have been sparked by social communications, either about girls or between girls themselves? / How do girls relate and react to the Girl Hub social communications platforms? / Is there an emerging collective identity around the Girl Hub initiated local brand? / Are social communications products saleable and sustainable in terms of their target, cost and funding, and involvement of implementing partners? / Girl Hub London: / There is no milestone for the Girl Hub Global team based in London, though they have engaged in supporting the development of social communications at a global and country level, including supporting creative excellence, setting standards and supporting insights work, which seeks to ensure that social communications are built on locally relevant knowledge. Girl Hub acknowledges that more work needs to be done to ensure that poorer girls are being reached by the branded communications. / Girl Hub Rwanda: / Girl Hub Rwanda has met this milestone. Girl Hub comments that the Ni Nyampinga brand has resonance and staying power. The team indicated that a significant amount of time had been spent in planning, and while this was seen as valuable, there were some questions related to whether Ni Nyampinga work had been delayed as a result. / Girl Hub is continuing to develop its approach to branded social communications based on insights and audience feedback to ensure it remains culturally relevant. Direct feedback on the concept and content of the magazine is positive. There is a high demand for the magazine from schools, parents and the Ministry of Education. The Rwanda Education Board and Ministry of Education acknowledge the relevance of the magazine for Rwandan girls. Evidence of this can be seen in the spontaneous forming of Ni Nyampinga clubs, including in refugee camps. / Two girl Ni Nyampinga journalists were awarded the Ulrich Wickert Award for Child Rights in the international category for the story “Sugar Daddies Prey on Female Students Headed Home for Holiday in Rwanda.” This described the ways in which young Rwandan schoolgirls become susceptible to predatory, older men who offer rides and gifts in exchange for sexual favors.[25] / The independent review team met girls who were involved in the production and also girls who had read the magazine and Rwandan officials who confirmed the relevance and resonance of the Ni Nyampinga brand. / Girl Hub Nigeria: / Girl Hub Nigeria has assessed itself as not having reached this milestone. This is because the brand platform has not been delivered. The review team agrees with this assessment; although we conclude that the reasons set out in paragraphs 63-4 mitigate this. / The review team has concluded the strong performance in Rwanda offsets the underperformance in Nigeria overall to justify the final mark for this output. / Background on Girl Hub’s approach to branded social communications / The emphasis that Girl Hub places on development communication is based on a belief in its potential as a catalyst and driver of social change. It enables the sharing of knowledge and promotes dialogue among target groups to build awareness and commitment, and changes in attitudes that can lead to increased demand for and take up of services.[26] / The use of branded social communications in development is a new approach, which draws on techniques and approaches that have been refined in marketing and communications. A social brand is the condensation of a set of interrelated ideas, values, aspirations and associations and their attachment to something tangible: a product, an event, a publication, a radio programme, an institution, a person or group of people. The potential of social brands to contribute to social change lies in their ability to consolidate ideas and values and act as a reference point for their audience. In doing so, they provide a route to understanding and – it is argued – transforming individual attitudes, ambitions and behaviour. If social brands that inspire people, raise expectations and create new levels of ambition are deployed alongside increased opportunities there is the possibility of creating among girls a rising tide of expectations and ambitions and the girls then making the most of the opportunities to realise these ambitions. Thus the thinking behind social brands is seen as enriching the theory of change that underpins the approach of Girl Hub. / Girl Hub’s approach to branded social communication is to create a “movement” owned by the girls themselves, rather than providing a top-down, donor-owned and branded communications programme, as has often been the case in other development initiatives. Girl Hub develops the social brands so they have a “life of their own” and do not depend on continued external funding to survive. The brands are developed alongside advocacy and campaigning to build a broad-based understanding of the need for and momentum for change. This includes senior decision makers, practitioners in development, to gatekeepers at community level and girls themselves. Qualitative research is used to ensure that the social brand is relevant and understood by everyone and in particular resonates with girls themselves. / At a global level, Girl Hub has built awareness and understanding of the approach. This includes continuing the development of the Girl Effect platforms (www.girleffect.org) to generate broad reach and ownership of the central message that girls are agents of change and the cost of excluding them is high. These platforms and social media have reached an audience that is quite a lot larger than those reached by more conventional communications approaches.[27] / The 2012 report of the Independent Commission for Aid Impact (ICAI) contained a number of findings and recommendations concerning communications, including: / The need to include qualitative indicators of the effectiveness of communications on attitudes towards girls and their perception of their role and place in society. / The danger of magazines being of little use to girls they cannot reach, cannot read or do not have safe places to engage with peers to discuss. / The difficulty of reconciling a simple message with the complex social problems faced by girls. / The lack of measures to assess the impact of Girl Hub’s communications work. / Since the ICAI report, Girl Hub has revised its logical framework and introduced management improvements that to some degree address the ICAI’s findings and recommendations. This independent review makes further recommendations that will increase the understanding of and impact of Girl Hub’s communications work. / Findings and Recommendations / There is poor understanding and some scepticism of brand-led communications within DFID / The reviewers found that some people in DFID were sceptical about, or had difficulty understanding, Girl Hub’s approach to and use of branded communications. Girl Hub staff also recognise this as a problem, especially at headquarters levels. Branded social communications is an important element of the Girl Hub theory of change and it is important for the approach that underpins it is fully understood in DFID. / Recommendation / Girl Hub should develop a clear set of messages that set out how branded communications can contribute to development. In particular these need to set out how branded social communication can change the attitudes and behaviour that are an obstacle to realising the potential of the girl effect, and go beyond presenting the arguments for the girl effect. / The approach to social brands in Nigeria carries risks that need to be more fully assessed / Girl Hub places importance on the social brand being properly designed and tested. Girl Hub argues that releasing a brand before it is ready risks long-term and possibly irreparable damage to the integrity and impact of the brand. In short, a brand that doesn’t work cannot be repaired: doing it right is more important than doing it on time. So when it proved difficult to produce the brand to the original timetable, quality rather than speed was the priority. Because of this, the first indicator and milestone, which focused on speed rather than quality, was missed, and the milestones for indicators two and three could not be assessed. / In addition, several of the partner agencies and programmes interviewed by the review team voiced concerns about the risk of a backlash against girls which they were not sure had been given sufficient consideration in preparing the brand platform. The inequalities between the north and south of Nigeria, and the attendant social and political tensions that have the potential to become violent are well known. So the risk of a brand not working is not just that the impact will be reduced, but could also inadvertently fuel social and political tensions that then become violent. Furthermore, government services are particularly poor in northern Nigeria. Even if the brand were successfully launched, there is a risk that expectations would be raised without an equivalent improvement in access to services. In this environment, it is especially important that the social brand that is developed is appropriate for the north of Nigeria. / The difficulty experienced so far in developing the social brand for northern Nigeria and the risks of doing so raise the question of whether an approach using brands is feasible. / Recommendation / Given the difficulties and risks of developing a social brand relevant for northern Nigeria, the review team recommends that Girl Hub undertake a review of its approach to social brands in Nigeria. This review should consider the risks of the approach and include strategies to mitigate these risks. In particular, the approach should be fully sensitive to the risks of conflict, in line with the new DFID guidance on conflict sensitivity in business cases. It should draw on the conflict expertise available within DFID and its other programmes in Nigeria. This review and its conclusions should be submitted for approval to DFID Policy Division who will need to draw on advice from advisers within DFID, both centrally and in Nigeria. / The evidence of progress with and the impact of branded social communications is weak / While it is clear that in Rwanda in particular, the reach and uptake of branded social communications has been significant, the evidence of its impact on girls’ self-image and confidence, and their standing within society, is weak. Furthermore, the surveys of readership of Ni Nyampinga did not enable firm conclusions to be reached on whether the milestones had been met. / A quantitative evaluation of work in Rwanda completed in May 2013 shows early encouraging signs. To some extent, the absence of impact evidence is understandable given that Girl Hub has only been in operation for a little over two years. However, it is the impact on girls and the perceptions of others in society that has the most potential to make a powerful case for Girl Hub approach to social brands. / Recommendation / Girl Hub should gather stronger evidence on the impact that social brands have on the perceptions, confidence and agency of girls and how others see them. This will entail discrete studies of perceptions and attitudes linked to the distribution and use of the social brands already being used. Given the progress with the development of the social brand in Rwanda, this work should initially be undertaken in Rwanda. / Girl Hub Rwanda should review the methodology being used to assess progress, in particular readership and repeat readership of Ni Nyampinga and ensure that it will enable firm conclusions to be reached about performance. In particular, the sampling frame needs to be representative of the population, and of the readership. / It is unclear how branded social communications will reach the bottom 40% of girls / A clear objective for Girl Hub’s branded social communications, in supporting programmes, is that it reaches the bottom 40% of girls. In countries with nascent media markets, this can be one of the most difficult objectives for communications to achieve. If Girl Hub is to have greater impact, then its communications must seek to reach the poorest and most vulnerable girls, many of whom will have low levels of literacy and be less able to access media or services. / Girl Hub has begun to tackle this issue and has conducted research in Girl Hub Ethiopia (the ‘Last Girl Strategy’) and Girl Hub (‘Vulnerability Mapping’) which has established the different categories of vulnerability of girls. This work needs to be continued and ensure that it assesses the access that the poorest girls have to media and how to ensure that these elements of the programme reach them. / Recommendation / Girl Hub should assess the degree to which the branded communications products are reaching poorer girls. Surveys of readers should be disaggregated using indicators for household wealth and be compared to the population at large. This quantitative data should be complemented with qualitative studies that assess the barriers that poor girls face in getting access to media (both print and broadcast) and strategies developed to overcome these barriers. / Impact weighting and risk / Impact weighting: 35% / Revised since last Annual Review? Yes, increased from 25% to 35%. / Risk rating: Medium, but in the case of Girl Hub Nigeria, this risk should be assessed as medium/high. There is some likelihood that branded social communications may not launch effectively in the coming year.
[25] See http://bit.ly/122sjSH. The Ulrich Wickert Award for Child Rights is awarded by Plan International Germany. The Ulrich Wickert Award for Child Rights is awarded to journalists whose writing represents the rights of children and girls in a detailed, balanced and understandable fashion and that encourages/stimulates engagement with the content. The award is made possible through the support of Ulrich Wickert, a prominent German journalist and broadcaster.
[26] Thusong Service Centre. "The Government Development Communication Initiative: A Response to Democratic Communication and Citizen Participation in South Africa" http://www.thusong.gov.za/documents/policy_legal/gdc.htm
[27] For example, the Girl Effect channel on YouTube has 18 videos and 5,852 subscribers have viewed the channel 4.5m times, and the most popular video has been viewed 1.4m times. In contrast, DFID’s YouTube channel has 194 videos, 943 subscribers who have viewed the channel 576,000 times, and the most popular video has been viewed 72,000 times.

Output 3: Research and girl-centred participatory monitoring and evaluation (PM&E) generates real-time, robust evidence and insiGirl Hubt
Output 3 score and performance description: B - Outputs moderately did not meet expectation. / Although Girl Hub Rwanda and Nigeria have conducted a number of PM&E activities and accompanying discussions with girls, not all were participatory (in particular the baseline survey in Nigeria). The review team has concluded that because the milestone specifically requires that the PM&E and accompanying discussions were participatory, the milestone against indicator one has not been met. Although we conclude that they have met the milestone for the second indicator, the review team notes that it was met by publishing five issue papers commissioned by the London office rather than drawing on their in-country research and PM&E work. No knowledge product based on in-country PM&E work has been widely disseminated and the quality of their knowledge products is mixed. This has been confirmed by feedback from external stakeholders. / Girl Hub lacks the capacity to undertake research that will stand up to scrutiny from development practitioners including those working for DFID. A reliance on external consultants, with varying degrees of experience in social research to plug their own capacity gap and conduct the work has led to knowledge products being produced that are of mixed quality. A number of their knowledge products do not include a methodology and description of participants. This makes it impossible to assess the usefulness (or indeed enable use) of the products, determine whether the most marginalised girls are being reached and understand how participatory and empowering the activity was for girls. The capacity and quality issues have also meant that knowledge products have not been effectively distributed in order to inform the work of other stakeholders. / Girl Hub was possibly too ambitious with the milestone in that it takes time for many organisations to publicly release their reports. However, the review team believes their research and PM&E activities need to be more grounded in good research practice. The fact that the Girl Hub is now piloting SenseMaker®, a participatory story collection research instrument, combining qualitative and quantitative analysis, in Rwanda and Ethiopia is a very positive step in this direction.[28] The innovative use of SenseMaker® has led to research participants engaging constructively and positively. In Rwanda and Ethiopia the SenseMaker® approach has led to a stronger strategic and programmatic focus on violence against girls and women. / The review team believe that the lack of strategic thinking around their research and PM&E activities has hindered a cohesive presentation to an external audience concerning exactly what Girl Hub are aiming to achieve with this output and how they aim to do it. For example, in their Annual Progress Report no clear sense is given of the different types of activities that informed their knowledge products, the methodologies employed and the aims of the activities / knowledge products produced. A mapping of their activities, methods and aims as well as an articulation of how the activities and methods tie in with their wider strategic aims would be useful. / Indicator one: Number of adolescent girls participating in PM&E and accompanying discussions / Milestones: / Rwanda: 1,500 girls participating in PM&E and accompanying discussions / Nigeria: 600 girls participating in PM&E and accompanying discussions / Achievements against indicator one: / The milestone has not been met. In Rwanda 1,487 girls have participated in research and PM&E activities and we note that Girl Hub Rwanda has performed satisfactorily again this milestone. These activities include ethnographic studies, interviews, co-creation workshops and surveys, as well as involving girls in supporting data collection. The Girl Research Unit Initiative has been established and has completed three rounds of training girls to conduct peer-to-peer research. The fourth was scheduled for the first two weeks of August 2013. It is important to note that each training round also includes field research. / In Nigeria 1,800 girls involved in the baseline survey as key informants. The baseline survey was conducted to explore girls’ perceptions of themselves and other people’s perception of girls in northern Nigeria, and to provide baseline indicators for Girl Hub Nigeria’s Monitoring and Learning framework.[29] However, the baseline survey was not participatory, so a key quality indicator for this milestone was not met. The review team is of the view that unlike the difficulties in achieving the milestones for output 2, the operating environment in Nigeria is not a mitigating factor in the qualitative standard for the milestone not being met. / Participatory Insights work involved a further 167 girls. 60 girls were involved in a media mapping. Ruby Pseudo research involved a further 550 girls in participatory research in Rwanda, Ethiopia and Nigeria. The breakdown by country is unclear. / Indicator two: Number of Girl Hub knowledge products published on website/other forums / Milestone: / 5 knowledge products published and available on the website and/or in other forums. / Achievements against indicator two: / The milestone has been met. A list of knowledge products delivered by Girl Hub during the review period was provided to the Review Team and can be found at Annex 2. However, only five papers commissioned by the London office are available online and these do not draw on Girl Hub driven insights from research and participatory monitoring and evaluation activities in Rwanda, Nigeria or Ethiopia. No results from the Girl Hub country PM&E activities have been widely disseminated. However, results have been presented to stakeholders in different forums, including presentations. / Indicator three: Quality of knowledge products (content and reach/sharing/demand) / Milestone: / A score of 2 = Agree or better achieved in assessments of quality of knowledge products and knowledge sharing (cumulative from baseline) / Achievement against indicator three: / QAS 1 QAS 2 QAS 3 QAS 4 / Girl Hub London Disagree Agree/Disagree Agree/disagree Agree/disagree / Rwanda Strongly disagree Disagree Agree / Nigeria Agree Agree Agree / The indicator has not been met. Girl Hub London in particular recognises that although a number of knowledge products have been produced there are significant issues around procurement and quality, which have caused delays, and have had knock on implications for meeting deadlines. The review team conclude that the knowledge products, particularly those based on PM&E activities with girls, are of mixed quality. The presentation of methodologies and results lacks clarity and detail. / External stakeholders confirm this conclusion and say that it is rare that Girl Hub has brought radically new insights to the table. Some also feel that Girl Hub is not effectively communicating and using the research and insights they have, and that the best use is not being made of the data they have. They feel that Girl Hub need now is to provide practical ideas on how to design and deliver programmes to unlock girls’ potential, rather than repeat the messages about the thinking behind the girl effect. The “why” has been answered, and people now want to know the “how”. / With the recent increase in staff capacity Girl Hub has organised an increasing number of activities aimed at feeding girls’ views and experiences into their work and that of others. Now more needs to be done to better present, disseminate and learn from the evidence generated from Girl Hub’s own research and PM&E activities. / Recommendations / Girl Hub should review the milestones for 2014 for output 3 to include an assessment of the quality of the research papers published on the website and the level of uptake and readership using downloads and forums to assess the level of interest in the publications. / Girl Hub should strengthen the links between their in-country participatory research work (e.g. the Sensemaker® work) and the work they publish on their website. This will entail ensuring that the in-country participatory research work is of hiGirl Hub quality and is can be used in synthesis studies that can then be put on the central website. At least half of the 2014 target of 10 knowledge products to be published on the website should comprise papers that draw on the in-country participatory research, rather than simply be background papers drawing on the work of others, as they do at present. / Impact weighting and risks / Impact weighting: 20% / Revised since last Annual Review? Yes, impact rating reduced from 25%. / Risk: Medium / Revised since last Annual Review? No
[28] See http://www.sensemaker-suite.com for details of the method, software and how it can be used.
[29] The research was conducted using a stratified random sampling approach to select and interview 4,300 respondents across Kano (1,500), Kaduna (650), Jigawa (650) and Sokoto (1,500) states. Respondents to the survey were young girls (10–19 years), young boys (10 –19 years), parents and men (20 – 45 years). Data was collected through face--‐to--‐face Interviews between October 22 and November 12, 2012.

Output 4: Girl Hub organisational development implemented
Output 4 score and performance description: A - Outputs met expectation / Indicator 1: Girl Hub offices established and resourced / Milestone: / Development plan for Girl Hub agreed with DFID and the Nike Foundation. / Achievement against milestone: / The milestone has been met. All actions in the ICAI management responses have been completed (with the publication of this report). Girl Hub has taken the recommendations made by ICAI very seriously. A further internal audit was undertaken and an action plan is in place to address all issues identified. This has been reviewed and verified by the review team. The review team are also producing a paper on options for the future of the strategic collaboration, which will help DFID and Girl Hub to assess the future of Girl Hub. / Indicator 2: Quality of the Girl Hub organisational development process / Milestone: / A score of 2 = Agree or better achieved in assessments of quality of Girl Hub’s organisational development (cumulative from baseline) / Achievements against milestone: / QAS 1 QAS 2 QAS 3 QAS 4 / Girl Hub London Strongly disagree Agree / disagree Agree Agree / Rwanda Disagree Disagree Agree / Nigeria Strongly disagree Strongly disagree Disagree / The milestone has been met in Rwanda and London, but has not been met in Nigeria. The review team noted the external challenges to management in Nigeria in particular the deteriorating security situation and the difficulty of recruiting permanent staff. Taking these into account and the improvement in Nigeria in the third quarter, the review team concludes that overall this milestone has been met. / The QAS questions that informed the QAS score were: / Has Girl Hub demonstrated the impact of bringing together the Nike Foundation and DFID culture and capability to add up to be greater than the sum of their parts? / Has the Girl Hub office been established and effectively/sustainably resourced? / Has Girl Hub created a safe environment where girls can convene? / Are systems and policies in place (governance, child protection, strategic planning, Human Resources, travel, low carbon, financial management, VFM, asset register etc.) / Country led development: Do Girl Hub country offices set strategy at country level? / Has Girl Hub assessed and responded to risks? / The pattern of gradual improvement reflects the growing emphasis placed on management during the year. Since the ICAI review Girl Hub has made good progress installing robust systems of management and procedures. Some of the country operations have experienced greater management challenges than others. / Nigeria is a particularly challenging environment in which to work and the team in Nigeria has had to deal with a deteriorating security situation, difficulties in establishing Girl Hub as a legal entity and identifying and recruiting a full team of staff. These challenges have now largely been overcome, but have demanded a considerable amount of the Country Director’s time since arrival in post at the beginning of 2012. The recent positive developments – the recruitment of 7 new staff, development of policies and procedures and clarification of duty of care arrangements with DFID – have improved staff morale, which is reflected in the improvement in the QAS 3 score. / Girl Hub is strengthening its performance management and learning and development policy for staff. Girl Hub London and Rwanda have developed monitoring and learning plans and a key strategy for supporting organisational development and learning is the quarterly QAS process. Rwanda and Nigeria have each completed three QAS processes and the London office has completed four. This process also monitors progress against milestones under each indicator in the logical framework. / Girl Hub has developed policies and procedures, the lack of which was noted by the ICAI review in 2012, including – critically – those for child protection. A child protection policy is now in place, although it has not yet been tested against a particular event. Girl Hub has also developed terms and conditions, salary scale and travel and expenses policies. / Additional findings / Beyond the internal management of Girl Hub, the ICAI review and the 2012 DFID Annual Review heightened the lack of clarity over the institutional arrangements and exact nature of the relationship between DFID, the Nike Foundation and Girl Hub, and the institutional future of Girl Hub. / The ICAI review observed: / “Our interviews within and outside DFID revealed a lack of understanding over where the boundaries lie between Nike Inc., Nike Foundation, Girl Hub and DFID... / Planning for Girl Hub did not include sufficient planning for long-term sustainability or an exit strategy. The idea of Girl Hub becoming income- generating through consultancy services was proposed in the planning documentation but does not appear to have been developed. / The option of DFID country offices or other donors funding additional Girl Hubs has not been ruled out; neither does it appear to be actively sought. / We also heard differing views about Girl Hub’s long-term structure: should it be spun off as a separate entity; should it be franchised out to other donors; should it be wound down; or should it be brought within DFID? The implementation of a new structure of governance provides an opportunity for DFID to consider the options for Girl Hub’s future.” / The ICAI review went on to recommend: / “Girl Hub, DFID and the Nike Foundation should ensure that… the roles and influence of each organisation are transparent and accountable. / DFID should assess the options for Girl Hub's future in the light of the evidence to date. DFID should form a clear and agreed forward plan within the next six months. For example, should Girl Hub be spun off as a separate entity, franchised out to other donors, brought within DFID or wound down? This plan should also include an assessment of whether and on what basis further national Girl Hubs should be established.” / The 2012 DFID Annual Review picked up this concern and observed: / “DFID and Nike Foundation have started to consider the broader nature of the DFID-Nike Foundation collaboration beyond the Accountable Grant. A DFID-Nike Foundation Senior Strategic Collaborative Group has been established to provide direction, leadership and decision-making. Over the coming months, this group should consider options for the future model of the collaboration including to maximise its added value. In addition, the Nike Foundation restructuring has implications for the location of the Girl Hub in Nike Foundation and the project governance arrangements. At the next meeting of the DFID-Nike Foundation Senior Strategic Collaborative Group, Girl Hub governance arrangements should be approved and Principles of Partnership agreed which should clearly establish the roles and influences of each organisation.” / The 2012 DFID Annual Review went on to recommend: / “DFID-Nike Foundation Senior Strategic Collaborative Group should approve Girl Hub governance arrangements and agree Principles of Partnership which should clearly establish the roles and influences of each organisation. Clarity should be reached on the role of the Girl Hub in taking forward Accountable Grant objectives vis-à-vis Nike Foundation’s core work. / DFID-Nike Foundation Senior Strategic Collaborative Group should consider options for the future model of the collaboration including to maximise its added value.” / The independent review team found that although the Senior Strategic Collaborative Group has been established and new governance arrangements have been agreed and documented, these do not provide clarity over the respective roles of DFID, the Nike Foundation and Girl Hub. / The Girl Hub Strategic Collaboration Governance Overview paper says: / “The Girl Hub Country Directors report to the Nike Foundation General Manager for Global Initiatives based in London who oversees the implementation of the global Accountable Grant overall, including submitting annual budgets/reports and quarterly reports to DFID. The Nike Foundation General Manager for Global Initiatives, together with the Girl Hub Country Directors, are part of the Nike Foundation Leadership Team. The Leadership Team undertakes annual strategic planning for the Girl Hub (and other Nike Foundation initiatives). The Leadership Team presents Girl Hub annual strategies and budgets to the Nike Foundation Board and the Girl Hub Board of Trustees for approval.” / It appears from this that the Nike Foundation and Girl Hub are so closely linked that they are essentially two parts of the same organisation. Although Girl Hub has an independent legal status in the UK and in Rwanda, which enables it to directly employ staff and issue contracts, the Senior Management of Girl Hub are clearly an integral part of the Nike Foundation. Furthermore, the Accountable Grant Arrangement is between DFID and the Nike Foundation rather than between DFID and Girl Hub. / Options for the institutional future of Girl Hub, which would resolve the continuing lack of clarity over the respective roles of DFID, the Nike Foundation and Girl Hub, have been considered in a parallel review undertaken at the same time as this annual review. DFID, The Nike Foundation and Girl Hub will be considering the options and agreeing a way forward. / The Theory of Change has been more fully developed and sets out the theoretical links between the different strands of Girl Hub activity: advocacy and advice on mainstreaming girls into regular programmes; influencing the official policy environment for girls; working on the wider enabling environment for girls (the cultural and social barriers); and inspiring and motivating girls directly (through the branded communications). / This now provides an opportunity to put the theory into practice and to integrate these activities more closely in the country programmes so that maximum synergy between them is achieved. / A useful further development of the Theory of Change would be to set out the thinking behind the individual programme components. Currently this is based on the hypothesis that the three programme components of strong evidence in support of the girl effect, influencing the wider environment, and inspiring and motivating girls can in combination achieve more than they can alone. A refinement of the Theory would be to set out the hypothetical pathway by which branded social communication can inspire girls and the assumptions behind the strategy to influence other larger development actors. / Recommendations / Subject to the response of DFID, The Nike Foundation and Girl Hub to the review of the options for the future of Girl Hub, output 4 should be expanded to include indicators and milestones that track progress against the conclusions that DFID, The Nike Foundation and Girl Hub reach on the institutional future of Girl Hub. / Each Girl Hub country programme should develop a strategy to harmonise and align the work of the three programme outputs so that the different audiences for each output receive a common message that is tailored for them. For example, a thematic push on education could comprise: / A set of recommendations and provision of advice to mainstream education programmes on how to increase girls’ attendance and performance at school. / Engagement in policy to identify opportunities to improve the policy environment for girls’ education. / A parallel “education special” theme launched through the brand vehicles and targeting adolescent girls. / A research theme focused on girls’ education. / A campaign to work with families, communities and teachers to identify barriers and enlist their support and involvement in getting girls to school. / Country programmes would need to decide on a limited number of themes they would pursue in a particular year, and then align all Girl Hub resources behind these themes. / Impact weighting and risk / Impact weighting: 10% / Revised since last Annual Review? Yes, this is a new output. / Risk: Medium/High / Revised since last Annual Review? Yes, this is a new output.

## Section B: Results and Value for Money.
Progress and results
Has the logical framework been updated since last review? / Yes. The logical framework has been revised with an additional output focused on management, and revised indicators and milestones to bring it into line with DFID guidance that outputs, indicators and milestones should be realistic rather than aspirational. / Overall Output Score and Description: A Outputs met expectation / Following the 2012 DFID Annual Review the project was marked as B – moderately not meeting expectations, but the review team at the time observed that “with a recently strengthened Nike Foundation management team in place, and groundwork laid, we are confident overall in the current direction of travel. The project is now well positioned to make strong progress in the coming year.” / Since then, the ICAI review recommendations have been implemented, management has been strengthened, particularly in Nigeria where they now have a full team in place. The logical framework has been revised to bring the outputs, indictors and milestones in line with DFID guidance. There has been good progress in some output areas, in particular the output on branded social communications, and a new and comprehensive theory of change has been developed and is now in use. The project is now well placed to make continued good progress for the final year of implementation. / Direct feedback from beneficiaries / The review team held interviews principally with DFID staff and partners in country who work with Girl Hub. Some interviews were held with direct beneficiaries – girls in Rwanda involved in safe spaces work and who were also aware of or involved in the production of Ni Nyampinga, but these were necessarily limited in scope. / The feedback from Girl Hub partners in country was positive, and in some cases even enthusiastic. Particular credit was given for the ability of Girl Hub to respond quickly and deploy resources to make the most of opportunities to influence policy that arose at short notice. There was also appreciation from partners of the development of the “community of practice” in Nigeria, not just for the content but also for the innovative and participatory way in which the “Girl Effect University” ran the event using a range of creative approaches they had not experienced before. The guided learning journeys were also welcomed as a way to bring policy makers and programme managers closer to the reality of girls’ lives and reveal to them the challenges they face in overcoming the multiple obstacles to unlocking their potential. / Girl Hub has also started using genuinely participatory approaches to getting feedback and engagement of girls in the programmes. The SenseMaker® work in particular places girls much more at the centre of interpreting and developing solutions to the challenges they face. And the involvement of girls in the production of the branded communication vehicles is of high quality. The next step is to go beyond those directly involved in the production and ensure that the audience is fully engaged in assessing and responding to the content. / Summary of overall progress / Set against the difficulties in Nigeria, there has been good progress elsewhere in 2012/13, particularly the branded social communications elements in Rwanda. There are also some good examples of Girl Hub having traction over a wider policy agenda. Taken together, along with the fact that the outputs and indicators and milestones are more realistic and include a management output on which good progress has been made the review team has concluded that the project should be marked at A – meeting expectations. / The failure to reach the milestones for output 2 in Nigeria is a cause for concern, given that the milestones were set in September 2012 and the risk of not meeting the milestone might have been apparent at that stage. However, the review team is of the view that some of the factors that contribute to the challenges of achieving progress in Nigeria are outside Girl Hub’s control. The difficulty of travelling to northern Nigeria, the bureaucratic delays in registering Girl Hub Nigeria as an independent entity, the lack of good quality creative agencies with a footprint in and understanding of the North, and the difficulty of getting good quality staff were to a degree outside Girl Hub Nigeria’s control. This suggests that a strategy is needed to respond more effectively to the external operating environment in Nigeria. This could entail refocusing effort on areas where Girl Hub can have an impact that is less dependent on overcoming some of the external frustrations. / A remaining area of concern is that the good progress in social branding and communications is not matched by the progress in wider policy and programme influencing, and in the research and evidence gathering. This is partly because this work (especially in Rwanda) is largely in-house or contracted directly, so it has been possible to deliver the outputs. It is also because Nike Foundation support for the project has been strongly focused on this output and has created momentum and energy behind it. The recommendation that Girl Hub country programmes develop a strategy to harmonise and align the work of the three programmatic outputs is intended to help ensure the programme does not become a branding and communications-only vehicle. / Annual Outcome Assessment / Outcome: Social communications, evidence and partnerships drive action for girls at scale / Indicators: / Number of girls attending girl groups outside the home and church/mosque at least once per month / Number of policies (e.g. in health, family planning, education, jobs, entitlement to assets and inheritance) that explicitly recognise girls (Rwanda, Nigeria state level) / Build recognition of adolescent girls into the post-2015 development framework / Progress against outcome: / The outcome has been revised to bring it into line with DFID guidance. Three indicators have been established, only one of which (indicator one) has a target and milestone for 2013. This indicator focuses on the additional number of girls recruited into safe spaces programmes. / The second indicator (policies recognising girls) was to have a baseline and target set in November 2012. This does not appear to have been done. Establishing targets and milestones for indicator two needs to be done as a matter of urgency so that the project completion report can assess progress against the outcome. / The third indicator (recognition of girls in post-2015 development framework) has a baseline of little or no recognition, with a target of girls being included through consultation, evidence and advocacy. / In Rwanda the Girl Hub has not directly aided the creation of safe spaces/groups for any girls to date. However girl groups are organising organically around the magazine Ni Nyampinga and the Girl Hub is in the process of learning more about these groups. (Girl Hub Progress Report April 2012- April13) / Under this outcome the logical framework does not address the specific targeting of marginalized girls. However, the business case for the scale-up of the Rwanda 12+ programme noted a concern that the pilot had not reached such girls. Girl Hub commissioned a vulnerability mapping for the 12+ Programme (Turatzine, Cyrille, 2013) in order to define the bottom 40% of girls and how they can be reached. The 12+ programme scale-up aims to target girls who are vulnerable and both in school and out of school and will target those communities with higher numbers of vulnerable and disadvantaged girls. (Business Case for the 12+ Programme DFID Rwanda October 2012) / In Nigeria 17,160 girls in 4 northern States have participated in safe spaces through the Programme for Reviving Routine Immunisation in Northern Nigeria and Maternal and Neonatal Child Health for which Girl Hub provided technical support and assistance, consisting of a workshop for programme staff in February 2012. This programme has now established young women’s support groups that provide adolescent mothers with maternal health guidance and support (Girl Hub Progress Report April 2012- April13). / On the third indicator, Girl Hub Rwanda collaborated with UNICEF to implement the MY World Survey and hold discussions to elicit girls’ opinions on their priorities for a post-2015 agenda. This work is feeding into a Girl Declaration being developed by Girl Hub and the Nike Foundation.[30] The UN resident representative presented the Girl Declaration concept note and MY World Survey results to the UN Secretary General when he visited Rwanda. UNICEF particularly welcomed the MY World Survey contribution by Girl Hub, which provided a good example of how age and sex-disaggregated data can reveal problems that might otherwise remain hidden. For example, for older adolescent girls, violence against girls emerged as a more significant issue than it would have done had the data not been disaggregated by age. Girl Hub Rwanda had also pushed for girls to be included in the post-2015 agenda with the Office of the President and through other forums such as during International Day of the Girl discussions. The review team independently verified this through interviews with UNICEF. / Recommendation / The review team recommends that the milestone for outcome indicator one is revised to take account of the project’s aim of targeting poorer girls. For example, the target for May 2014 should be expanded to include the qualification that at least 20% of the girls attending are from the poorest 40% of households.
[30] http://www.girleffect.org/2015-beyond/girl-declaration/.

Costs and timescale
Is the project on-track against financial forecasts? / Total Grant Allocation £12.8m / Cumulative Spend to date £8.9m / Forecasted spend 2012-13 £6.36m / Expenditure to end April 2013 £4.37m / Forecasted spend to end May 2013 £5.13m / Forecasted underspend to year end £1.23m / The project is not on track against the financial forecast. There is an under-spend of 19% against the annual budget. This is due to a combination of weaknesses in budgeting and forecasting, the delay in launching the brand platform in Nigeria and the delay in the start of 12+ Programme in Rwanda. The review team noted that improvements have been made to budgeting and forecasting over the last year. A no-cost extension from May 2013 to May 2014 has been approved by DFID. / Following the DFID Annual Review recommendation last year, the Accountable Grant to the Nike Foundation is now provided in arrears, based on actual spend; and budget and spending actuals are now aligned with the logical framework. These are all positive developments that are expected to contribute to a better performance on forecasting and spending in the next year. Actual expenditure has varied by no more than 5% from forecast expenditure in the last three quarters. / Key cost drivers / Key cost drivers have been, as in the past review periods, administration and management related costs and brand and communications related expenses. ‘Operations’ which are management overheads, were 28%. A main cost item titled ‘Girl Hub’, which was 15% of the actual spend, also features overheads related expenses. The high management costs were attributed to Girl Hub’s technical assistance heavy operation model, and the organisation being a recently established start up and not yet having internalised economies of scale in some programme components. / Ni Nyampinga (radio and magazine) costs constituted 26% of the total expenditure during the review period. Communications related professional fees were 14% of the total budget for last year (2% of the DFID grant). / According to Girl Hub’s 2013 financial year budget submission to DFID (which including DFID and Nike Foundations funds), salaries and wages were 26% of the budget. ‘Wage-related expenses’ amounted to 54% of the budget, including professional fees paid to contractors as well as the above mentioned salaries category. / Is the project on-track against original timescale? / The project is not on track against the original timescale. The original end date of the Accountable Grant Arrangement was 31 May 2013. Following the previous DFID Annual Review a no-cost extension was granted by DFID to 31 May 2014. / In the review period Girl Hub has strengthened its programme management and made reasonable progress on some of their initiatives on brand development, advocacy and influencing. If sustained, we can expect a stronger performance towards achieving the project outcome by the end of the programme.

Evidence and evaluation
Assess any changes in evidence and implications for the project / The review team is not aware of any new evidence that has emerged during the review period that challenges the rationale underlying ‘the girl effect.’ / During the review period, Girl Hub’s Theory of Change was further articulated, clarifying a results chain and unpacking the assumptions, thereby strengthening the internal logic. The Theory had originally focussed exclusively on the girl as a change agent. The revised Theory of Change recognises the importance of the enabling environment and establishes links between Girl Hub’s work to build demand for service and their work to influence the supply of services for girls through advocacy, brand development, research and evidence. / There is a growing evidence base to suggest that providing girls and young women with access to economic assets and developing their skill sets may improve their ability to generate an income, increase savings, support school attendance, and increase their sexual health knowledge.[31] There is evidence of how social marketing can change non-product behaviours.[32] However there is as yet limited evidence on the impact of social marketing on the change that Girl Hub aims to achieve (increased self-confidence and value) and how this leads to socio-economic benefits for girls and their communities. This is where Girl Hub wants to test their approach and contribute to the evidence base. / While implementation to date does provide conclusive evidence for this Theory of Change, there is some preliminary, narrow-base and country-specific evidence emerging from the Quantitative Survey (May 2013) of Ni Nyampinga. Of the respondents in the survey who had read the magazine,[33] 70% reported that it had changed their confidence to ‘a great extent’ and 72% reported it has changed their self-worth. It is not yet known whether this type of change is translating into other social and economic benefits. / Where an evaluation is planned what progress has been made / There is no evaluation planned. Alongside this annual review, the review team is producing a report considering options for the future collaboration between DFID and the Nike Foundation beyond May 2014. Subject to DFID and Nike Foundation’s response to this report and the proposals for the institutional future of Girl Hub, there is a good case for an independent evaluation of Girl Hub’s approach. This is due to the innovative nature of the collaboration and in particular the incorporation of social branding as a tool to promote social change. / Recommendation / Subject to the conclusions on the future of Girl Hub, DFID should consider commissioning an independent evaluation of Girl Hub’s approach, in particular to document the evidence or the impact of social branding in changing attitudes and behaviour relating to adolescent girls.
[31] Dickson and Bangpan, ‘Providing Access to Economic Assets for Girls and Young Women in Low and Lower-Middle Income Countries: A Systematic Review of Evidence’, 2012. Commissioned by DFID.
[32] Social marketing evidence base is huge, particularly on health related interventions, HIV, family planning, malaria, etc. There is enough evidence to demonstrate which types of interventions of social marketing offered cost effective means. Social marketing interventions have produced strong and broad ranging evidence of impact on product behaviours, particularly condom, oral contraceptive, and insecticide treated net use. Evaluations of non-product behaviours have found social marketing to be effective in increasing abstinence and fidelity, and several preventive child health behaviours, including handwashing. Chapman and Astatke, ‘Review of DFID Approach to Social Marketing, Annex: 5 Effectiveness, Efficiency and Equity of Social Marketing’, PSI Research Division, 2003.
[33] 671 respondents including boys and girls.

Risk
Output Risk Rating: Medium / The overall output risk is medium, with three out of four outputs assessed to be of medium risk, and the fourth (output 4) medium/high. This review recommends that output 2 should also be rated medium/high for Nigeria, as there is a higher risk of delivery given the lack of progress for Girl Hub Nigeria over the review period and that changes in the security situation are beyond Girl Hub’s control. / Assessment of the risk level / The original project memorandum for Girl Hub identified some risks and mitigating actions. These are reflected in the assumptions of the logical framework. Through the QAS processes, Girl Hub teams review and assess risks quarterly. Reviewing the QAS over the last year, the key external risk and uncertainty that affects delivery is insecurity in focus countries. / In addition to these risks, the following assumptions underpin the theory of change: / Girls can build social and economic assets through Girl Hub interventions / Branded communications can amplify behaviour and attitude change / Branded communications can be designed to reach the most disadvantaged 40% of girls / The remaining risks are more within the control of Girl Hub and can be mitigated to a significant extent by having the right policies and systems in place. Girl Hub has spent considerable effort on this during the review period. Operationalizing an effective monitoring and learning system which will underpin organisational learning and strengthen the evidence base and reviewing the Ni Nyampinga magazine distribution strategy to reach girls not in education are examples of mitigating measures. / There fact that branded communications has not been tested as part of an international development strategy creates uncertainty. The proposed independent evaluation of Girl Hub’s approach would enable firmer conclusions to be reached on the effectiveness and impact of the approach and demonstrate whether the approach provides value for money. / Risk of funds not being used as intended / The previous DFID Annual Review rated this risk as high. This was because: Girl Hub budgets did not show sufficient detail and did not separate DFID income; a low level of understanding among Girl Hub staff of DFID financial rules and procedures at the time: and the Nike Foundation’s annual audited accounts did not show the DFID grant as a separate item of income. In the review period, significant progress has been made to address these issues. Girl Hub global budgets and spending actuals are now at a sufficient level of detail and separate the grants from DFID and the Nike Foundation. Due to the constraints of the US general accepted accounting principles (GAAP) the Nike Foundation audited statements still do not show the DFID grant as a separate item in the accounts. As an alternative, the Nike Foundation now provides an auditor’s certificate to DFID. Audit discharge has been performed for 2010, 2011 and 2012. / DFID have shared with the Nike Foundation and Girl Hub their guidelines on salary levels, travel and subsistence, consultancy fee rates. DFID grant money can only be used in line with these guidelines. This has been set out in an accountable grant amendment letter, as was recommended by that previous Review. Significant effort has been made to familiarise Girl Hub staff with these guidelines. / Recommendation / In light of the progress, it is recommended that this risk is changed from high to low. / Climate and Environment Risk / Air travel by staff and consultants is considered to pose the highest risk. Recommendations made in past reviews have been taken on board. Girl Hub has put in place an Emission Offsetting Policy and engaged their travel company and a carbon retirement broker to implement a carbon retirement scheme. Calculations were done and reported based on travel between June 2011 and June 2012. Video conferencing facilities have been purchased in order to reduce the need to travel. / Girl Hub Rwanda has also been using environmentally friendly materials in the production of the Ni Nyampinga magazine. / As a way of contributing to positive externalities for the environment, Girl Hub can use environmental messaging and content for the Ni Nyampinga magazine and radio show with the aim to increase awareness of issues such as climate change and climate friendly action and the importance of preserving natural resources. A wide variety of issues are covered in the magazine and on the radio show and both would provide convenient platforms for this.

Value for money
Performance on value for money (VFM) measures / Girl Hub was set up before the DFID requirement to write a business case and no value for money indicators were set at the outset of the project. The previous DFID Annual Review noted that Girl Hub Ethiopia’s work on developing value for money metrics could guide future reviews. It concluded that ‘when unit costs are available, it is recommended that DFID benchmark Girl Hub’s work against other organisations delivering in this area’. / Girl Hub has recently developed a draft Value for Money Framework, setting out a strategy to assess value for money and includes metrics for unit costs that can be used for trend analyses in the future. The strategy indicates that ‘a consistent VFM analysis over the life of accountable grant is likely to be difficult’. / This review has found that although some unit costs are emerging, these are not yet consistent and uniform across Girl Hub offices and operations. Girl Hub has not yet developed a consistent indirect costing methodology for unit costs. There are some unit costs set at design stage of some programmes, for instance regarding Girl Hub Ethiopia programme and for 12+ Programme in Rwanda. Better value for money data will allow more rigorous assessments in future reviews. / The assessment carried out by the review team looked at the following aspects of value for money during the review period and concluded: / Theory of Change: the internal logic was strengthened and the results chain linked to the evidence base. The assumptions in the theory of change, particularly the relevance of branded social communications to the most disadvantaged girls and whether this approach will reach them, need to be fully tested. / Economy and programme management improvements: significant improvements were made both in terms of cost savings and putting policies and systems in place. / Efficiency: some unit costs are emerging, though they are not consistent across all programmes, and are currently on the high end. A commonly used efficiency indicator is the ratio of management costs to total costs. An indicative benchmarking exercise indicates Girl Hub costs to be high compared to some programmes. / Effectiveness: it is difficult to judge VFM at this stage, but some worthwhile benefits can be evidenced already. / Equity: there are plans to address this, but overall the interventions have not yet reached the most disadvantaged girls. Producing disaggregated data on the most disadvantaged girls should be a priority area for Girl Hub because this will strengthen the evidence base in Girl Hub focus countries and beyond, which will improve the value for money assessment. / Economy / Girl Hub has put considerable effort into this aspect of VFM in the review period. It is reported that an estimated £1 million was saved through adjusting salary structures, policy on per diems, more competitive procurement, negotiating preferential rates with suppliers and reducing travel and entertainment costs. The review team were provided with evidence on this, for instance Girl Hub Rwanda tracked savings secured through negotiating all contracts in the past 6 months. Further savings are estimated due to the recent office relocation of Girl Hub London into Nike offices – a significant saving as 9% of total spend during the review period was for rental for all Girl Hub offices. / In terms of procurement, a working draft policy is in place and is being reviewed with country offices inputs. The policy largely references Nike Foundation rules, with the DFID guidelines on spending added on. In practice, this has caused some confusion and trainings have been held for staff at London and at country offices levels. Girl Hub is required to receive approval from the DFID project manager for procurement over £50,000, and country directors can approve spend up to $25,000. Contracts worth over $25,000 require a competitive process of seeking 3 quotes. / Considerable effort has also been made to put various systems and policies in place and improve existing ones, as discussed in the section of this report titled ‘role of Project Partners’ above. / Efficiency / As explained above, the development of unit costs consistently across Girl Hub programmes is in progress and it is not yet possible to come to a definitive conclusion on Girl Hub’s performance against this VFM metric. / Which cost efficiency indicators can Girl Hub use? / Even for programmes where results are considered ‘hard to measure’, these metrics should be identifiable and reckonable. The starting point is configuring budgeting, monitoring and evaluation, and management information systems to be able to generate the information. Examples of unit costs are: / Cost per girl reached through direct interventions / Cost per girl reached through direct interventions vs. benchmark per capita cost of similar intervention(s) elsewhere / Number of people reached with communications campaigns (by medium) / Ratio of programme to management costs of social communications products / Ratio of programme costs to total costs and/or management costs to total costs / Cost per person reached with communications campaigns (by medium – benchmarked regionally where possible / Number of people responding to communications campaigns’ messages/calls to action (by medium) / Cost per person responding to communications campaigns’ messages/calls to action (benchmarked where possible) / Cost per person engaging in participatory monitoring and evaluation / Unit cost of training per mentor / To increase cost efficiency, the use of new media should also be considered in addition to the traditional media channels. Particularly Nigeria is on a growth curve of new media and subscriber numbers are likely to increase, without any significant cost increases. These scale effects will result in falling unit costs. Such scale effects are not so prevalent in traditional media because markets are likely to be more saturated in subscriber numbers. / In the absence of unit costs, we looked at a commonly used efficiency metric: the ratio of management costs to total costs. / Management costs to total costs / A review of DFID guidance and reports from similar non-government organisation (NGO) and UN programmes show that in the absence of set unit costs, a cost efficiency proxy that is often used is the ratio of administrative costs to total costs, or programme costs to total costs. Similarly, Girl Hub’s draft VFM Framework proposed ‘ratio of programme to management costs of social communications products’. During the review period, administrative costs as a percentage of total costs for Girl Hub were at least 28%[34]. This ratio puts Girl Hub towards the high end on a spectrum of trusts and challenge funds studied for comparison which had on average of 20-25%[35]. This ration is however comparable to some Population Council programmes in Kenya (33%) and Ethiopia (33%)[36], although these are service delivery programmes working with disadvantaged girls. Girl Hub’s management costs did not compare favourably to UN agencies which typically charge 7-10% to DFID for management costs. Girl Hub high administrative costs were attributed to the organisation being a recently established start up and not having internalised economies of scale in some programme components yet. / One difficulty encountered during the review was identifying which costs were administrative and which were programmatic. For instance, Girl Hub’s budget forecast for the 2012/13 financial year was divided into wage and non-wage related expenses categories. Wage related items also included professional fees to consultants, which might all have been programme related. Further, the current budget coding structure does not adequately support the VFM analysis needs. Going forward, Girl Hub should further clarify reporting and budgeting so as to allow accurate identification of administrative and programme costs. / Ni Nyampinga costs / The cost per magazine printed for issue 5 was $4.31 (£2.70) (based on 87,895 copies printed) and cost per reader was $1.51 (£0.95) (based on estimated reach of 250,413 readers). A similar concept of social marketing was explored for comparison. Shujaaz is a popular comic book (monthly) and radio programme (on various radio stations daily) in Kenya, implemented by Well Told Story (WTS, a social enterprise). This is a brand that Girl Hub is familiar with, and has explored as a model. It aims to promote governance and accountability in the pre-elections period. Shujaaz magazine averaged a print run of 700,000 per issue during 2012. Their research suggested 10 reads per comic over an average lifespan of up to a year. The current reported cost per issue per reader is $0.05. WTS was funded with $1.1 million over 2 years from the United States Agency for International Development (USAID). Currently 40% of Shujaaz revenue is derived from private sector sources and they expect this percentage to increase. / In this comparison, it is important to consider quality. Ni Nyampinga magazine is of high quality and a ‘high-end product’, as stakeholders and the Shujaaz team observed. That high quality comes at a cost. Key questions are whether the additional cost is required to achieve and sustain impact or whether there are more cost–effective options? Girl Hub should also consider whether commercial advertising can decrease costs while maintaining the integrity of the brand. These are considerations for sustainability of Ni Nyampinga going forward. / In terms of radio, estimates on the reach of Ni Nyampinga vary. Using the estimate of 200,000 provided in Girl Hub’s VFM report and the total radio costs for the 2012/13 financial year (£216,777), the cost per listener is £1.08. This is high when compared to both Girl Hub Ethiopia’s planned Yegna radio show (£0.39) and the Story Story in Nigeria, which was implemented by the British Broadcasting Cooperation (BBC) World Service Trust (£0.28). However, both of these programmes reached a higher audience than Ni Nyampinga radio; 10m and 20m respectively. Cost per listener for Ni Nyampinga is likely to fall as the audience increases. / VFM Measures from Girl Hub Ethiopia and 12+ in Rwanda / As explained above, the Girl Hub Ethiopia Business Case established unit costs that can be used for their VFM analyses. Other Girl Hub offices are not yet using these. Girl Hub’s brand development model is very context specific and costs have varied between countries at different stages. ‘Cost per participant in monitoring and evaluation’, estimated at £110 by Girl Hub Ethiopia, can be used by other Girl Hub offices. However, it should be noted that this is remarkably high, which is attributed to the resource intensive processes of the chosen methodology using the SenseMaker®. / Benefits and Overall Effectiveness / It was not possible at this stage of implementation to quantify benefits. Therefore, a qualitative assessment is provided based on: / Review of project documentation, progress reports and Girl Hub QAS results. / Feedback from DFID and Girl Hub staff (UK and overseas); one to one and group interviews; NGO partners in countries where Girl Hub operates and elsewhere in Africa (including Plan, Care, Population Council); Government officials (Rwanda); and beneficiary girls (Rwanda). / An online survey completed by 33 members of DFID, Girl Hub and Nike Foundation staff. / On this base, while it is difficult to judge with certainty at present, the review team concludes that some worthwhile benefits have already been delivered. / Private benefits to direct and indirect beneficiaries / Overall, positive feedback was received from girl beneficiaries of Girl Hub in terms of the private benefits to them from mentoring and training (in magazine and radio journalism, research methods). Self-forming Ni Nyampinga clubs all around Rwanda, including in refugee camps, were noted by stakeholders including by government officials who have plans to tap into these to link them up with services. Although preliminary and narrow-base at this stage, a recent quantitative survey on the Ni Nyampinga brand showed that 70% of magazine readers reported increased self-confidence and worth. / Benefits through research and learning / Some feedback received during the review was that the quality of some of the research and knowledge products created by Girl Hub are not yet at a level expected from them at the outset. There were accelerated efforts during the past year of implementation both in research and participatory monitoring and evaluation (PM&E), and the examples are the 5 systematic reviews commissioned (Girl Hub London), baseline surveys (Nigeria), Ni Nyampinga qualitative and quantitative research in Rwanda. A National Attitudes Survey is starting in July in Rwanda. In terms of uptake of research, positive feedback was received from UN agencies and NGO partners in Rwanda, Nigeria and Kenya who gave specific examples of Girl Hub reports and data presentations that they frequently use and refer to. / PM&E implementation and findings have not yet contributed to supporting the wider evidence base to a significant extent. Setting up of M&E systems is underway, at a more advanced stage in Rwanda than Nigeria. Some important initiatives have started namely seconding an M&E expert to Ministry of Health (Rwanda) and the Girl Mapping Platform/Girl Effect Grid (Rwanda and London). / One aspect of learning in relation to VFM is learning from mistakes and discontinuation of failures. Although this is mentioned in Girl Hub’s draft VFM Framework, the review team have not come across or been given examples of this type of learning from failures. Documenting what has not worked and why, would provide a good case to present for VFM. / Benefits though policy level influence / In Rwanda, Girl Hub has enjoyed high–level access and support from key political figures and government departments. They were described as ‘a key player’ in the sphere of girl and youth issues. In Nigeria, access and perceived influence were less clear. Rwanda appears to have been an easier place to operate in this sense and Girl Hub Rwanda’s senior management have taken full advantage of the more welcoming attitude and advanced groundwork on gender and girls’ issues. During the review, we met several Rwandan Ministers and other high level officials who confirmed that Girl Hub provided useful girl-focussed inputs and reviews into national policies, namely the Adolescent and Reproductive Sexual Health (ASRH) Policy, National Youth Policy and Family Promotion Policy. In addition, Girl Hub Rwanda is represented on many technical working groups on gender and youth issues. / Some international NGOs working on girls and youth issues observed that Girl Hub are ‘making a lot of noise’ and contributing significantly to awareness raising on girl issues at country and global level, through there was some confusion as to whether it was the Nike Foundation or Girl Hub who was being credited with this. At country level, Girl Hub identity (independent from the Nike Foundation) appeared to be more visible, but at global level the distinction was less clear to the stakeholders. During the past year, significant influencing efforts were focussed on the post-2015 development agenda. For instance in Rwanda a Girl Hub info-graphic summary of the responses of 30,000 girl to the “MY World” Survey was included in the brief for the UN Secretary General during his visit to Rwanda in May. / The ICAI Review in 2012 observed that ‘Girl Hub’s main impact to date has been in helping DFID to integrate girls’ needs into its mainstream programming and strategy.” The stakeholders interviewed as well as the survey respondents agreed with this to a large extent, noting that Girl Hub helped and supported DFID (through technical inputs during programme design, and participating in tender evaluations for girl programmes) rather than directly influencing strategy. As one put it: ‘DFID did not need influence, they were already committed to the girls agenda.’ / Benefits through mobilising and leveraging funding for girls / In terms of catalysing investment and resource allocations for girls, beyond DFID funding commitments, there has not been significant progress. It appears that Girl Hub has not focussed influencing efforts on other donors so far. They can be attributed a reasonable level of direct influence on DFID programming at country level. Examples of this are the 12+ Programme in Rwanda and incorporating safe spaces components in some of the large-scale programmes of DFID Nigeria. As regards DFID’s global programmes, the Girl Hub logical framework presents the related milestone as the GGRI, which is at design stage. / In terms of leveraging funds from developing country governments, the Government of Rwanda have promised to take 12+ approach and programme to scale beyond the programme duration, however there are no firm budgetary allocations or similar initiative that could be considered as evidence at this stage. / Socio-economic benefits that can be accrued through development and poverty reduction impacts (such as support of a demographic dividend, education or economic empowerment) of Girl Hub programmes are unknown at this stage. / Equity / Girl Hub’s draft VFM Framework argues that Girl Hub values ‘effectiveness and equity over economy and efficiency’. In the review period, there has not been a significant progress on extending programme benefits to disadvantaged groups of girls. The 12+ pilot, which involved 600 girls, did not reach those groups nor can we be sure of the reach of the Ni Nyampinga magazine at this point (as the Ni Nyampinga Qualitative Research done by 2CV showed). The Ni Nyampinga team are continuously reviewing their magazine distribution strategy to extend its reach beyond the urban and relatively better off readers. For example by identifying a diverse set of distribution outlets to capture girls out of school. / The 12+ programme in Rwanda has incorporated strategies to reach the poorest 20% of girls. Girl Hub Ethiopia developed a reach strategy, which defined ‘invisible girls’ to ensure that benefits will reach the different groups of girls to give the greatest returns. They aim to collect disaggregated data on ‘invisible and vulnerable’ versus ‘connected’ girls. This will contribute to the evidence base locally and internationally and ensure a higher return on the investment by providing better value for money. / Commercial Improvement and Value for Money / In the review period, there were considerable efforts by Girl Hub to improve procurement performance across the programme. A working draft of a procurement policy is in place and largely references Nike Foundation procedures. DFID issued guidance, which outlines the expenses – such as marketing, advertising, and first/business class air travel – that cannot be paid for using the DFID the central grant. Girl Hub is now working with DFID procurement department to further develop the procurement strategy and this support has been valuable in increasing VFM. / Girl Hub budgets and financials separate the DFID and the Nike Foundation contributions to Girl Hub. The problem encountered here is that two separate sets of principles seem to be applied to funds from the two contributors to the Girl Hub budget. As was the case with benefits, which were assessed overall and not in relation to contribution, the same is applied for overall costs. If DFID is not ‘buying’ certain outputs from the Girl Hub collaboration, which they are not, then costs and benefits should be shared. All monies should be used to maximise the programme benefits, and charging certain expenses to a different source of income is not going to take away the problem. The accounting rule here (as in separating the income streams and expenses) is not relevant. ‘Opportunity cost’ argument stipulates that the expenses that were not allowed for DFID funding and therefore covered from Nike Foundation funds, could be used for programmes and increase Girl Hub’s effectiveness. The review team was informed that the general principle that Girl Hub London applies on this is to spend as much as possible of the DFID Central Grant, within the limits set by the DFID guidelines. In addition, in some instances seeking DFID approval was going to cause delays to activities, so in the interest of speeding up delivery, Nike Foundation funds were used, an example being the Girl Effect Grid. / Girl Hub’s efforts to improve their procurement performance during the year have been extensive, particularly in terms of increasing Girl Hub London staff understanding on DFID financial rules and procedures. Procurement training and exercises have been held for staff (e.g. for exercises on allowable costs, and procurement role plays). At the country level, the internal audit process helped familiarise staff with allowable expenses in particular and DFID procurement rules in general. Girl Hub Rwanda held a procurement workshop in January 2013, which covered contract management and avoidance of fraud. Girl Hub Rwanda also has developed vendor lists and agreed corporate rates with various service suppliers (transport, accommodation, hiring of event venues), which saves on procurement time and reduces transaction costs. / Recommendation / DFID rules governing procurement by partners should be rolled out to cover all Girl Hub funding. / Role of project partners / There has been good progress since the ICAI Review on putting new systems in place and strengthening existing ones. / An external consultant, who visited each Girl Hub country office, carried out a comprehensive internal audit plan. The country offices have submitted periodic progress reports to the Nike Foundation Senior Management Team. The reports include asset registers, insurance, security, IT, human resources, financial and operational controls, budget management. More specifically, the following has been achieved in the review period: / Girl Hub Employee Handbook was completed / Girl Safeguarding Policy is in place and is supported by designated Girl Safeguarding Officers in each office / A procurement policy should be in place by the beginning of 2014 (a working draft is in place) / Girl Hub staff in London and country offices have been trained in procurement / Strategic Workforce Planning is under way and milestones agreed at country levels / Budget management and project records have been strengthened / A VFM Framework has been drafted / A carbon-offsetting scheme was chosen and reporting is being done on an annual basis / An anti-bribery policy is in place / The Girl Hub logical framework was revised to include organisational development as one of the outputs (output 4). The progress on this is also covered in the section of this report covering this output. / According to the Girl Hub’s draft VFM Framework, as a result of collaboration with DFID on the Girl Hub, the Nike Foundation is also trying to demonstrate more awareness of value for money and internalise such measures in their operations. An example of this was that Nike Foundation identified 4 key performance indicators and has applied these to 2013/14 budget decisions. / Finally, the previous annual review found that ‘understanding of the role and work of the Girl Hub within DFID is inconsistent’. This review has found that this challenge still exists, however there were efforts to address this through periodic meetings of Senior Strategic Collaborative Group, as well as a Girl Hub display at the DFID London offices. Given that communications is one of their strengths, the Nike Foundation and Girl Hub could take the lead in communicating more effectively the role and work of Girl Hub to DFID. / Does the project still represent Value for Money (VFM)? / It is not possible to say with certainty, but the indicators are positive. / The previous Annual Review also concluded that it was not possible to judge whether the project represented value for money. There is no baseline to use as a comparator so we have taken on board the following consideration in assessing VFM: / The improvements made, particularly in the Economy aspect of VFM (cost savings and strengthening of programme management) / A qualitative assessment as to the benefits delivered from the Girl Hub experience thus far / The draft VFM Framework identifies which VFM metrics Girl Hub can work on going forward / Further efforts are need to consolidate budget and reporting systems to enable consistently calculation of unit costs / We conclude that although it is still not possible to say definitively that the project is good value for money the indicators are that it possibly is. However, further data is needed to confirm this impression. In reaching this conclusion, the review team would like to highlight: / A full and fair VFM assessment cannot be made using available data / Our assessment is based on what the team does know / Further information is needed and the review team recommends that steps are taken to collect this information. A table with recommendations on further data needed to have a definitive VFM assessment is on page 38. Further attention should be given to this issue in the final year of the project.
[34] This was the percentage of Operations (overheads) line item, however there are overheads factored in some of the other line items of spend, such as ‘Girl Hub’, which was 15% of the spend in the review period. This was discussed under key cost drivers in the Annual Review Template.
[35] A benchmarking study of Africa Enterprise Challenge Fund (Bester, 2010) showed that development funds (trust funds, matching grant funds, challenge funds, etc) commonly have management costs at around 20-25% of total costs.
[36] Bruce and Menon, The Cost of Reaching the Most Disadvantaged Girls, Population Council, 2012.

Conditionality
Update on specific conditions / There are no specific conditions

Conclusions and actions
The recommendations of this Annual Review are summarised below. / Output 1: Catalysing and influencing / DFID guidance for outputs, indicators and targets is that they should be realistic and achievable rather than aspirational. The first indicator for output 1 is focused on the quality of engagement of Girl Hub with DFID and non-DFID “scale partners”. The second indicator measures the response of ‘scale partners” to this engagement over which the Girl Hub has little or no control. We therefore recommend that indicator 2 be revised to focus on the contribution that Girl Hub makes to scaling-up resources rather than the quantity of resources eventually allocated. For example, a target could be set for the number of programmes Girl Hub will engage with and contribute to that focus on unlock the potential of girls, and the nature of the influence they would bring to bear. Action: DFID and Girl Hub. Timing: By December 2013. / The UK Gender and Development Network is an important sounding board for the work of Girl Hub and has been critical of their approach in the past, in particular the need to include in the approach work to change wider attitudes and behaviours towards girls. The revised Theory of Change answers some of their concerns and we recommend that the revised Theory be disseminated to the gender and development community. The original girl effect video was praised for reaching and convincing a wide audience of the merits of the girl effect. We further recommend that a similarly convincing video should be made that highlights the importance of changing the attitudes and behaviours of wider society. Action: Girl Hub London Office. Timeframe: By February 2014. / Girl Hub should develop in each country an influencing strategy that sets out who, they want to influence, why they are targeting this individual/organisation/group in terms of the results they expect to achieve and how this links to the other areas of their work. This will enable them to focus their influencing and catalysing work where it has the most potential to have an impact. In the absence of a strategy there is a risk that they will be drawn into opportunistic and reactive work, responding only to the latest opportunity. Action: Girl Hub Country Offices. Timeframe: by April 2014. / Output 2: Branded social communications / Girl Hub should develop a clear set of messages that set out the contribution that branded communications can make to development. In particular these need to set out how branded social communication can change the attitudes and behaviour that are an obstacle to realising the potential of girls, and go beyond presenting the general arguments in favour of the girl effect. Action: Girl Hub. Timing: By December 2013. / Given the difficulties and risks of developing a social brand relevant for northern Nigeria, the review team recommends that Girl Hub undertake a review of its approach to social brands in Nigeria. This review should consider the risks of the approach and include strategies to mitigate these risks. In particular, the approach should be fully sensitive to the risks of conflict, in line with the new DFID guidance on conflict sensitivity in business cases. It should draw on the conflict expertise available within DFID Nigeria and its other programmes in Nigeria. This review and its conclusions should be submitted for approval by DFID Policy Division who will need to draw on advice from conflict advisers within DFID, both centrally and in Nigeria. Action: Girl Hub Nigeria and DFID Policy Division. Timeframe: By November 2013. / Related to recommendation 4, Girl Hub should collect stronger evidence on the impact that social brands have on the perceptions, confidence and agency of girls and how others see them. This will entail discrete studies of perceptions and attitudes linked to the distribution and use of the social brands already being used. Given the progress with the development of the social brand in Rwanda, this work should initially be undertaken in Rwanda. This evidence could be used in support of recommendation 4. Action: Girl Hub Rwanda. Timeframe: By April 2014. / Girl Hub Rwanda should review the methodology being used to assess the readership and repeat readership of Ni Nyampinga and ensure that it will enable firm conclusions to be reached about performance. In particular, the sampling frame needs to be representative of the population, and of the readership. Action: Girl Hub Rwanda. Timeframe: By December 2013. / Girl Hub should assess the degree to which the branded communications products are reaching the most disadvantaged girls. Surveys of readers should be disaggregated using indicators for household wealth and be compared to the population at large. This quantitative data should be complemented with qualitative studies that assess the barriers that poor girls face in getting access to media (both print and broadcast) and strategies developed to overcome these barriers. Action: Girl Hub Country offices. Timeframe: by January 2014. / Output 3: Research and girl-centred PM&E / Girl Hub should review the milestones for 2014 for output 3 to include an assessment of the quality of the research papers published on the website and the level of uptake and readership using downloads and forums to assess the level of interest in the publications. Action: Girl Hub London. Timeframe: November 2013. / Girl Hub should strengthen the links between their in-country participatory research work (e.g. the Sensemaker® work) and the work they publish on their website. This will entail ensuring that the in-country participatory research work is of high quality and is used in synthesis studies that can then be put on the central website. At least half of the 2014 target of 10 knowledge products to be published on the website should comprise papers that draw on the in-country participatory research, rather than simply be background papers drawing on the work of others, as they do at present. Action: Girl Hub London and country offices. Timeframe: By May 2014. / Output 4: : Girl Hub organisational development / Subject to the response of DFID, the Nike Foundation and Girl Hub to the review of the options for the future of Girl Hub, output 4 should be expanded to include indicators and milestones that track progress against the conclusions that DFID and the Nike Foundation reach on the institutional future of Girl Hub. Action: DFID, Girl Hub and Nike Foundation. Timeframe: November 2013. / Each Girl Hub country programme should develop a strategy to harmonise and align the work of the three programme outputs so that the different audiences for each output receive a common message that is tailored for them. For example, a thematic push on education could comprise: / A set of recommendations and provision of advice to mainstream education programmes on how to increase girls’ attendance and performance at school / Engagement in policy to identify opportunities to improve the policy environment for girls’ education / A parallel “education special” theme launched through the brand vehicles and targeting adolescent girls / A research theme focused on girls’ education / A campaign to work with families, communities and teachers to identify barriers and enlist their support and involvement in getting girls to school / Country programmes would need to decide on a limited number of themes they would pursue in a particular year, and then align all Girl Hub resources behind these themes. Action: Girl Hub country offices. Timeframe: February 2014. / Outcome / The milestones for outcome indicator one (number of girls attending girl groups outside the home and church/mosque at least once per month) should be revised to take account of the aim of targeting the most disadvantaged girls. For example, the target for May 2014 should be expanded to include the qualification that “at least 20% of the girls attending are from the poorest 40% of households”. Action: Girl Hub London. Timeframe: November 2013. / Evaluation / Subject to the conclusions of DFID and the Nike Foundation on the future of Girl Hub, DFID should consider commissioning an independent evaluation of the Girl Hub approach, in particular to document the evidence or the impact of social branding in changing attitudes and behaviour relating to adolescent girls. Action: DFID. Timeframe: Commission evaluation in time to commence work in May 2014 and report by the end of the next phase of support to Girl Hub. / Risk of funds not being used as intended / It is recommended that this risk be changed from high to low. Action: DFID. Timeframe: Immediately. / Value for Money / DFID rules governing procurement by partners should be rolled out to cover all Girl Hub funding. Action: Girl Hub. Timeframe: by December 2013. / Girl Hub should clarify reporting and budgeting so as to allow accurate identification of administrative and programme costs. Action: Girl Hub. Timeframe: December 2013 / Further attention is given to developing VFM measure in the final year of the project. A table with recommendations on what further data is needed to arrive at a definitive VFM assessment is on page 38. Action: Girl Hub. Timeframe: December 2013.

Review Process
This annual review was undertaken by a team of 6 independent consultants from 2 May to 22 June 2013. A review of key literature was undertaken. Visits were made by 3 members of the review team to the Girl Hub offices in Rwanda and Nigeria. An online survey of DFID, Girl Hub and Nike Foundation staff was undertaken. Interviews were also conducted with DFID, Girl Hub and Nike Foundation staff, external stakeholders in the UK and overseas and programme participants and beneficiaries in Rwanda. DFID and Girl Hub provide feedback on this report and their comments have been considered by the review team. A list of organisations consulted and documents reviewed is provided at annex 2. The results of an on-line survey of DFID, Girl Hub and Nike Foundation staff are provided at annex 3.

Table 1: Table of Proposed Value for Money Measures
Target Outcome/ Output	Achieved (Benefits)	Quantifiable benefits	Cost (For FY 2012-2013) if available	Current assessment of VFM inc. quantitative measures where available (and which of the 3 Es)	Recommendations for future VFM Measures / (and which of the 3 Es)
Outcome
Social communications, evidence and partnerships drive action for girls at scale					Percentage changes in (disaggregated) societal attitudes towards issues on which the branded communications platforms have campaigned (EFFECTIVENESS). / Percentage of girls/ boys/ people attributing changes in attitudes to girls as a result of social communications (EFFECTIVENESS).
Outputs
1. Girl Hub catalysing role established and effective			$461,679		A review conducted for DFID looking at influencing efforts in the health sector concluded that ‘a full quantitative cost-effectiveness analysis of influencing is likely to remain impractical, but more attention should be given to the costs involved and the alternatives that may be available.’[1] GIRL HUB can focus on understanding and documenting the total costs and cost- efficiency of its influencing efforts. / Cost per £ scale partner investment (EFFICIENCY)
2. Branded social communications activated and sustained			$ 1,441,440	Cost per person reached through communications (broken down by medium) (EFFICIENCY). [2]	Cost per girl reached through direct interventions vs benchmark per capita cost of similar intervention(s) elsewhere (EFFICIENCY). / Number of people reached with communications campaigns (by medium) (EFFICIENCY) / Ratio of programme to management costs of social communications products (EFFICIENCY). / Cost per person reached with communications campaigns (by medium); benchmarked regionally where possible (EFFICIENCY). / Number of people responding to communications campaigns’ messages/ calls to action (by medium) (EFFICIENCY) / Cost per person responding to communications campaigns’ messages/ calls to action; (benchmarked where possible) (EFFECTIVENESS)
3. Research and girl-centred PM&E generates real-time, robust evidence and insights			$874,472		Cost per person engaging in Participatory M&E. (ECONOMY) / Unit cost of training per mentor (ECONOMY) / Systematic and periodic qualitative analyses, particularly through Sensemaker (EFFECTIVENESS)
4. Girl Hub organisational development implemented			$1,971,888	Ratio of programme costs to total costs and/ or management costs to total costs. (EFFICIENCY) / Cost savings through scale economies, salary structures etc (ECONOMY). Reportedly up to £1 m during the review period.	Programme Processes (ECONOMY): / A Girl Hub model that will involve DFID funding will have to be benchmarked against DFID Procurement Standards. A comprehensive approach to this aspect of VFM will involve: / Competitive procurement (ensuring competition in all aspects to keep costs down and reduce excess), / Scale economies (negotiating preferential rates with suppliers), / Salary structures and per diems, / Exploring opportunities for cost sharing with other Girl Hub programmes (to avoid additional tendering/ procurement time, achieving a cost and time saving)
[1] Clarke J et al, ‘DFID Influencing in the Health Sector, A Preliminary Assessment of Cost-Effectiveness’, ODI, Nov 2009, p.xii.
[2] Available to a limited extent currently. We have Ni Nyampinga magazine costs based on issue 5 (issue 7 is about to be released and issue 6 costs not available at the time of writing). Radio costs are also only indicative as figures for reach vary significantly. This review used the reach figures from the Girl Hub VFM Framework Internal Report. Further, a comparison to similar examples from the region was provided (details above).

Annexes

Annex 1: Theory of Change

Figure 1: Theory of Change
Annex 2: List organisations and documents consulted during the review

Organisations consulted during the review

DFID
Nike Foundation
Girl Hub
Minister of Youth and Information Technology, Rwanda
UNICEF, Rwanda
CARE, Rwanda
Minister of Gender, Rwanda
Plan International, Rwanda
FHI 360, Nigeria
Association of Youth Documentation and Innovation, Nigeria
Population Council, Kenya
Search for Common Ground, Rwanda
Voices for Change (V4C), Nigeria
Population Council, Nigeria
Mercy Corps, Nigeria
Population Council, Nigeria
Girl Hub Rwanda Advisory Committee
Well Told Story, Kenya

Bibliography

Bruce and Menon, The Cost of Reaching the Most Disadvantaged Girls, Population Council, 2012.
Clarke J et al, ‘DFID Influencing in the Health Sector, A Preliminary Assessment of Cost-Effectiveness’, ODI, Nov 2009.
Dickson and Bangpan, ‘Providing Access to Economic Assets for Girls and Young Women in Low and Lower-Middle Income Countries: A Systematic Review of Evidence’, 2012. Commissioned by DFID.
Grosser and van der Gaag (2013) ‘Can girls save the world?’ in Aid, NGOs and the Realities of Women’s Live, edited by Wallace, T., Porter, F. Ralph-Bowman, M. Rugby: Practical Action Publishing.
ICAI (2012) Girl Hub: a DFID and the Nike Foundation Initiative, ICAI Report No 5, London: Independent Commission for Aid Impact (ICAI) (http://icai.independent.gov.uk/wp-content/uploads/2010/11/ICAI-Girl-Hub-Final-Report_P1-5.pdf - accessed June 5th 2013).
Thusong Service Centre. "The Government Development Communication Initiative: A Response to Democratic Communication and Citizen Participation in South Africa" (http://www.thusong.gov.za/documents/policy_legal/gdc.htm).
## DFID Business Cases:
DFID Kenya (February 2013), Business Case for Adolescent Girls Initiative – Action Reach Programme.
DFID (2013?) Strategic Case: Direct Assets to Girls (DAT-G) Incubator.
DFID DRC (16 June 2013) La Pépinière: DFID DRC’s Programme for Adolescent Girls.
DFID Ethiopia (2012?) Business Case and Intervention Summary, Girl Hub Ethiopia.
DFID Rwanda (October 2012), Business Case for 12+ Programme, DFID Rwanda.
## Girl Hub Knowledge Products:
2CV (January 2013), Exploring the Impact of Ni Nyampinga and opportunities for development,
Ball Cooper, L. and Fletcher, E. (2013) Reducing Societal Discrimination against Adolescent Girls, Paper Commissioned by Girl Hub, February 2013. http://www.girleffect.org/resources/2013/3/reducing-societal-discrimination-against-adolescent-girls/
Blanc, A., Melnikas, A., Chau, M. and Stoner, M. (2013) A Review of the Evidence on Multi-Sectoral Interventions to Reduce Violence against Adolescent Girls, Paper Commissioned by Girl Hub, February 2013. http://www.girleffect.org/resources/2013/3/a-review-of-the-evidence-on-multi-sectoral-interventions-to-reduce-violence-against-adolescent-girls/
Calder and Huda (2012) Adolescent Girls Economic Opportunities Study, Rwanda, Development Pathways, commissioned by the Nike Foundation and the Girl Hub Rwanda.
DFID and Girl Hub, Adolescent Girls: Expert Meeting. Technical Experts’ Meeting on Adolescent Girls, October 2012.
DFID NN Gender Progress Report, internal report, February 2013.
Fusion Consulting (March 2013), Baseline Survey Report, Girl Hub Nigeria.
Girl Hub (2012) Insights: The Story of Northern Nigerian Adolescent Girls.
Girl Hub (April 2011) Media Mapping Survey report, Girl Hub (date?).
Girl Hub After-Action Process Documentation: Adolescent Sexual and Reproduction.
Girl Hub After-Action Process Documentation: National Youth Policy Post Game Wrap up Report, January 2013.
Girl Hub Nigeria (2012) Girl Hub Northern Nigeria: Religious Leaders Round Tables, May 2012.
Girl Hub, (n.d.) Exploration of Cultural Context for Branding Platform for Girls in Northern Nigeria.
Hallman, K., Stoner, M., Chau, M., and Melnikas, A.J. (2013) Review of Control-Comparison Interventions on Girls and Health in Low and Middle-Income Countries, Paper Commissioned by Girl Hub, February 2013. http://www.girleffect.org/resources/2013/3/a-review-of-control-comparison-interventions-on-girls-and-health-in-low-and-middle-income-countries/
Health and Rights Policy (ASRH&R) Post-Game Wrap up Report, January 2013.
Iscale (April 2013) Political and Social Influencing Related to the Advancement of Girls’ Well-being in Rwanda.
Kawo, A. (date unknown) Exploration of Insight’s: Teenage Girls in Kano, Communication Support Kano.
Lloyd, C. (2013) Education for Girls: Alternative Pathways to Girls’ Empowerment.
Ni Nyampinga Issue 02, January 2012.
Paper Commissioned by Girl Hub, February 2013. http://www.girleffect.org/resources/2013/3/education-for-girls-alternative-pathways-to-girls-empowerment/
Population Council (2013) The Adolescent Experience In-Depth: Using Data to Identify and Reach the Most Vulnerable Young People: Rwanda 2010. New York: Population Council. Produced in collaboration with the Nike Foundation and the Girl Hub.
Population Services International / Rwanda (April 2012) 12+ - Final Program Evaluation Report April 27, Submitted to Girl Hub and the Nike Foundation.
Quisumbing, A. and Kovarik, C. (2013) Investments in Adolescent Girls’ Physical and Financial Assets, Paper Commissioned by Girl Hub, February 2013. http://www.girleffect.org/resources/2013/3/investments-in-adolescent-girls-physical-and-financial-assets/
Restless Development / Bell & Payne Consulting (2011) Girl Hub: State of Girls in Rwanda http://www.restlessdevelopment.org/file/girlhub-01062011-pdf.
Ruby Pseudo and the Nike Foundation (April 2013) Understanding Teen Girl Culture: a youth culture study, Girl Hub.
Strategic Research Ltd (January 2012) Girl Hub Communications Baseline Study Report, Girl Hub Rwanda.
The Girl Hub (DRAFT) Girl Safety Toolkit: A Resource for Practitioners.
TNS (May, 2013) Ni Nyampinga Quantitative Research. Draft Report, The Girl Hub.
Training resources and research Group (date?) Parental perceptions on Girl Hub 12+ approach pilot Program Baseline survey in Huye, Ngoma, Kicyukiro and Musanze districts in the Republic of Rwanda.
Turatzinze, Cyrille (February 2013) Vulnerability Mapping for 12+ Programme.
Zhen Goh (2012) Girl Hub Rwanda: 12+ programme narrative analysis report, prepared by Cognitive Edge Pte. Ltd.
## Girl Hub Organisational documentation:
Desai, P. (2013) Focus Group Report, Girl Hub Nigeria Stakeholders, March 2013
Desai, P. (2013) Girl Hub Nigeria Feedback from DFID Stakeholders Questionnaire, April 2013
Desai, P. (2013) Girl Hub Nigeria Monitoring and Learning Strategy, April 2013
Desai, Philly (April 2013) Feedback from DFID Stakeholders Questionnaire, Girl Hub Nigeria
Draft Girl Hub Trustee Pre-Read – May 2013
Girl Hub (2012-2013): Quality Assurance Scorecard Exercises: London: QAS 1 13th of July 2012, QAS 2 24th of September 2012, QAS 3 December 2012, QAS 4 February 2013. Rwanda: QAS 1 July 2012, QAS 2 11th December 2012, QAS 3 18th of March 2013. Nigeria: QAS 1 August 2012, QAS 2 December 2012, QAS 3 March 2013
Girl Hub (2013) Annual Progress Report April 2012 – April 2013
Girl Hub Accountable Grant Project Memorandum
Girl Hub Country Plans, January 2013
Girl Hub Governance and Strategic Planning Arrangements
Girl Hub logical framework, revised September 2012
Girl Hub Monitoring and Learning Plan, March 2013
Girl Hub Nigeria, Baseline Summary, March 2013
Girl Hub Trustee Meeting Presentation, October 2012
Girl Hub, Table of Evidence of Deliverables, April 2012
SSCG Meeting; March 2013
## Finance & Operational Documents:
Budget by logical framework
DFID financial report
DFID Project Progress Reporting Template
Game Plan – Quarterly Financial Review Q1-Q3 FY13
Girl Hub Anti-bribery and Corruption Policy
Girl Hub Audited Accounts
Girl Hub DFID central grant procurement approval template (required for procurement worth more than £50,000)
Girl Hub Emission Offsetting Policy
Girl Hub Employee Handbook 2013
Girl Hub Governance and Strategic Planning Arrangements
Girl Hub Guidance on Expenditure of the DFID Global Grant
Girl Hub Internal Audit Status May 2013
Girl Hub Monthly Management Reporting Pack – April 2013
Girl Hub Procurement Policy
Girl Hub Procurement training deck
Girl Safeguarding Policy

Acronyms

AGI	Adolescent Girls Initiative (World Bank)
ASRHP	Adolescent Sexual and Reproductive Health Policy (Rwanda)
CBO	Community Based Organisation
CHASE	Conflict, Humanitarian and Security Department (DFID)
CSW	Commission on the Status of Women
DFID	Department for International Development
DHS	Demographic and Health Survey
ESSPIN	Education Sector Support Programme in Nigeria
GEP3	Girls Education Programme
GEU	Girl Effect University
GHR	Girl Hub Rwanda
GHN	Girl Hub Nigeria
GLLJ	Girl Led Learning Journeys
GPI	Global Press Institute
HLP	High Level Panel
HSSP	Health Sector Strategic Plan (Rwanda)
ICAI	Independent Commission on Aid Impact
IDG	International Day of the Girl
MDG	Millennium Development Goals
M&L	Monitoring and Learning
MoH	Ministry of Health
MYICT	Ministry of Youth, Information, Communication, Technology
NF	The Nike Foundation
NN	Ni Nyampinga
NSRP	Nigerian Stability and Reconciliation Programme
NYP	National Youth Policy (Rwanda)
NGO	Non-Government Organisation
ODI	Oversees Development Institute
OECD/DAC	Organisation for Economic Co-operation and Development / Development Assistance Committee
PM&E	Participatory Monitoring and Evaluation PRINN/ MNCH Programme for Reviving Routine Immunisation in Northern Nigeria / Maternal Neonatal and Child health
PUSS	Permanent Under-Secretary of State
QAS	Qualitative Assessment Scorecard
SoS	Secretary of State
ToC	Theory of Change
V4C	Voices for Change
VFM	Value for Money
Annex 3: Findings from on-line Survey
## Introduction
This section presents the findings from a survey of selected DFID, Girl Hub and the Nike Foundation staff member’s experiences and views of the Girl Hub. The survey examines relevance, effectiveness of the Girl Hub’s social communications, knowledge products and its role as a catalyst. It also explores the extent to which DFID has learned and been transformed by the Nike Foundation to deliver a more girl-focused approach, as well as looking at value for money and staff opinions on future models.
The survey was developed in consultation with DFID and Girl Hub. The survey was anonymous and administered by an independent consulting firm, Social Development Direct, using the online survey tool Survey Monkey.
In total, 33 staff members responded to the survey – a response rate of 28 per cent – including 9 staff from DFID, 19 from the Girl Hub and 3 from the Nike Foundation. Most respondents were based in the UK, with the rest based in Rwanda (4 responses), Nigeria (3), Ethiopia (2), Tanzania (1), Kenya (1) and the United States (1). Caution should be exercised in interpreting differences at the country and organisation level due to the low response rate.
## Key findings on Girl Hub’s work
As an average score out of 5, respondents scored various aspects of the Girl Hub’s work as follows:
4.7 / 5	Relevance of Girl Hub strategies / programmes to the context in the countries they operate
4.1 / 5	Effectiveness of Girl Hub’s social communication as a means to generate dialogue among target groups
3.9 / 5	Successfulness of Girl Hub as a catalyst in activating others to take a girl-centred approach
3.5 / 5	Effectiveness of Girl Hub’s knowledge products in generating robust evidence and insights
As might be expected, Girl Hub and Nike Foundation staff consistently scored the various elements of their work higher than DFID staff (see Annex 1), although there were some surprising elements in the detail. For example, the lowest scores for the effectiveness of Girl Hub’s social communication were provided by Girl Hub and Nike Foundation respondents, rather than DFID staff.
For many of the questions, there were also a high proportion of ‘don’t know’ responses, particularly among DFID staff, suggesting that opinions are still forming and people remain open-minded about the effectiveness of the Girl Hub.
Relevance
Overall, respondents provided the most positive comments and scores on the Girl Hub’s relevance. Both DFID and Girl Hub staff highlighted the value of Country Offices tailoring programmes and strategies to the needs of girls in country. As one DFID respondent observed, “Girl Hub strategies in country are relevant as each Country office takes into account the context of the specific girls and their environment, therefore programmes and strategies are designed to meet the specific needs of specific girls.” Although respondents placed strong emphasis on the need for context-driven strategies, a few also highlighted that despite the variation between different country offices there was a strong underlying message uniting all Girl Hub work:
“Our strategies and programmes in country vary depending on the context (for example our work in Rwanda is different and can happen at a different pace from what we are able to do in Northern Nigeria due to the security context) but all centre around the belief that changes need to be made at the level of the girl (to allow access and agency over resources), the structural environment (to make girls visible in legal and development agendas for example) and the consciousness of the girl and her wider society to increase her value and self-esteem” (Girl Hub).
Several Girl Hub respondents mentioned the emphasis placed on trying to understand what girls need and on insights, monitoring and learning: “we are triangulating those insights with what we know from the political landscape and what works for girls. We will always learn and evolve.” Respondents also valued the central role of girls in co-designing programmes which helped ensure their relevance to girls’ needs: “girls are at the centre of all strategizing”.
Branded social communication
Respondents also rated Girl Hub’s social communication work highly: “Will take some time, but already the conversation has started. If followed through, could be revolutionary” (Girl Hub). Several respondents noted that it is too early to be able to tell whether Girl Hub’s branded social communication has been effective or not, having only just launched in Ethiopia and only been around for a year in Rwanda. However, respondents noted that “early indications are better than anticipated” (DFID) and “research shows that girls and boys both engage positively with the brand platforms” (Girl Hub).
“If you look at the comments on Facebook or the mobile responses relating to Yegna or the discussions that take place between NN ambassadors and girls on the ground, dialogue is definitely being generated. The proof will be further down the line when we look at whether the brands are stimulating debates in homes and in communities.” (Girl Hub)
Several respondents observed Girl Hub offers a unique (but as yet largely untested) way of amplifying girls’ voices through its branded social communications: “This means that girls are given a voice and opportunity to unleash their potential and be part of the solution to ending poverty” (Girl Hub). For example, one Nike Foundation respondent observed,
“Where the communication has been well managed and target audience feel they 'own' it, it has been successful and created healthy conversation. Yegna launch and media coverage is unprecedented in Ethiopia and general insights indicates it feels relevant locally and is perceived as a breakthrough in perception of adolescent girls (as leaders, singers etc).”
Girl Hub staff noted how their qualitative research on Ni Nyampinga shows that it is “absolutely connecting with, inspiring, and provoking conversation with both girls and those around them.” Another respondent observed that Ni Nyampinga “has been effective in opening dialogue amongst girls and their parents/guardians.” A DFID respondent also commented that policy makers have been influenced to use the brand names, for example the Ministry of Health Rwanda for the 12+ programme.
Although respondents were generally excited by the early indications that the branded social communication was sparking dialogue and inspiring girls, they identified the following areas for further work over the next couple of years:
      1. Using M&L frameworks to understand how these products develop and whether attitudinal and behavioural changes are happening within girls and wider society
      2. Convincing stakeholders to see branded social communication as having development outcomes for girls
      3. Analysing whether the branded social communication is successful at reaching the most vulnerable girls
      4. Continued efforts to integrate ownership of girl-centred models in-country to keep the momentum and local support alive.
Girl Hub’s role as catalyst
Respondents identified several examples of how Girl Hub have catalysed others to take a girl-centred approach, both at the country level and in terms of influencing DFID operational and business plans to target girls separately from women (see Box 1 below). Respondents from DFID, Girl Hub and the Nike Foundation all acknowledged that the record was “a bit mixed – maybe this is a time issue?” and “there is still much more we can do as we go forward”. For example, one Girl Hub respondent observed, “there are some examples in country, but they are thin and it feels as if the entire catalysing highlighted the need to communicate more closely to DFID and other partners what Girl Hub can offer, while ensuring that there is capacity to turn ‘inspiration into action’:
“We have a great and willing partner in DFID and we could do more here if we clearly communicated what our offer is. I feel there is still a major comms piece to DFID to show them what we are able to do - I think this would inspire them and make the partnership more approachable if people knew how we can work together to do more for girls. We should also be thinking about how we can work with other partners to catalyse them into taking a girl centred approach. We are a good catalyst and have the ability to inspire people but we need to have capacity to follow this up and learn whether this inspiration is turning into action, i.e. what impact are we having?”
Examples of Girl Hub’s catalyst role
- “DFID's gender strategy has an explicit focus on adolescent girls (this was not previously the case) - Secretary of State is mentioning adolescent girls as a priority in speeches
- Girl Hub analysis of the quality of country bids influenced the Bilateral Aid Review (SR 2010 influencing £40 billion aid allocations and improving results commitments for girls and women)
- DFID has invested in some significant new scale programmes, especially in Girl Hub focal countries (e.g., 12+ in Rwanda, Adolescent Girls Research Initiative in Kenya, Zambia girls programme (DFID+ Pop Council), safe spaces investments in Nigeria, End Child Marriage Programme (Finote Hewat) in Amhara, Ethiopia)
- DFID is planning more global initiatives focused on adolescent girls, as a result of collaboration with Girl Hub London e.g. GGRI, building assets of girls in humanitarian settings, Economic Assets for Girls Incubator
- High level focus on girls e.g. PM family planning summit in June 2012
- Girl Hub and the Nike Foundation brought pazzaz and statistics to the youth lunch at the event (generating a lot of interest), and importantly we worked with Government partners in country e.g., Minister of Health in Rwanda to equip them to speak out in support of an adolescent focus in family planning - this has had a positive knock on effect in getting support of Ministry officials for the 12+ programme.
- Girls getting on the post-2015 agenda: high level advocacy with the High Level Panel and the Women Deliver conference in Kuala Lumpur (May 2013)
- USAID and AUSAID have both expressed interest in our approach - through we have not yet found a way to work with them (we explored this in depth with USAID in 2011)
- Gates and World Bank collaboration on Girl Hub U/G-School
- SenseMaker: Girl Hub's pilot programmes are sparking interest from DFID and its PPA partners, with potential to elevate girls' voice and understanding of their priorities
- There are fewer examples yet of mainstreaming of an adolescent girl lens across core development policies beyond health and education sectors e.g. economic development, climate change. But we are starting to see opportunities in Ethiopia and Rwanda.” (Girl Hub, UK-based)
(As highlights by Girl Hub survey respondent)
Knowledge products
Overall, the least effective aspect of Girl Hub’s work so far appears to be its knowledge products. Although one DFID staff member rated the knowledge products highly, the rest either scored it ‘2 out of 5’ or were not aware of any knowledge products. Girl Hub and Nike Foundation staff also scored the knowledge products lower than various other elements of their work.
Reasons provided by respondents for the lower score (in comparison to other aspects of Girl Hub’s work) include delayed starts in monitoring and learning, coupled with a need to disseminate products more widely. As one Girl Hub respondent acknowledged, “I think we can improve in this area to ensure that our knowledge products are widely received and supported and adding new insights to the field.”
Some of the comments provided also suggest a need to inject a level of rigour into some of the more innovative research methodologies used:
“Though they provide insights, I do think some methodologies used by Girl Hub wouldn’t stand up to rigorous scrutiny, though they are exciting and innovative.” (DFID)
“The quality has been mixed. Some of the insights work has been experimental and undertaken by people who do not have a development background (e.g. Ruby Pseudo) - and one can question the methodologies used and whether the insights are more broadly valid. However, other work has been excellent. The five published GGRI papers, for example. The SenseMaker pilot work has been path-breaking and is already generating more robust evidence.” (Girl Hub)
Extent to which DFID has learned and been transformed by the Nike Foundation
On average, respondents scored 3.6 out of 5 for the extent to which DFID has learned and been transformed by the Nike Foundation to deliver a more girl-focused approach.
Several respondents pointed to examples of new commitments to girls, saying “the top of DFID now ‘gets girls’”. However, there was some doubt from all staff (both DFID and Girl Hub/Nike Foundation) about the extent to which DFID had been transformed to deliver a more girl-focused approach. One Girl Hub respondent observed, “Currently, it feels like there are pockets within DFID who have learned from Girl Hub/Nike Foundation in terms of gaining a deeper understanding of adolescent girl issues and an interest in working in a more innovative way but this isn't widespread - nor would I say it's transformative at this stage.”
5 out of 7 DFID respondents said their attitude to the role of adolescent girls in development had changed over the last five years. These respondents said they were now more aware of the specific needs of adolescent girls – “a strategically important group”. However, two respondents noted that a focus on adolescent girls is not new: “Has been on the agenda for as long as I’ve working on gender and development, including for child insights and women’s rights organisations”.
4 out of 7 DFID respondents said that the Girl Hub had influenced their thinking and technical approach. Most DFID staff who responded to the survey appreciated the opportunity to learn more about brand and communications, as well as how to “communicate the issues of girls better and most of all putting the girl first, and in the heart of everything I do”. However, one person noted that the Girl Hub’s technical approach was not always clear and there was a need for a more holistic approach: “sometimes naïve about how policy and programming for adolescent girls fits in with wider development issues and different contexts”.
Value for money
Just over half (54.2 per cent) of respondents thought the Girl Hub’s work had provided value for money, while a small proportion (8.3 per cent) thought it did not (see Figure 1). The rest (37.5 per cent) did not know and thought it was “too early to tell” and “the work that Girl Hub does is difficult to measure / value”.
Figure 1: Do you think that the Girl Hub's work has provided value for money?
Number of respondents
Although one DFID respondent noted that “my sense is that they don’t really consider value for money in the same way that DFID staff are required to,” most respondents (DFID, Girl Hub and Nike Foundation) noted that value for money concerns were now being taken “extremely seriously”. According to several Girl Hub respondents, the organisation has worked hard over the past year to prove that its work provides good value for money, including sharpening up procurement processes and general spending oversight: “Girl Hub as an organisation is very conscious of VFM and vast improvements have been made in our finance department over the past year to allow this work to happen”.
Several respondents noted that the Girl Hub model had high initial costs, as “working with the private sector on social communications work is expensive”, but that the costs will come down with time:
“While more expensive than typical development interventions up front, the comms products are building brands that will have long-term equity. The incremental cost of impact for new work under the brands becomes lower and lower and they reach millions.”
“It is important not to fixate on unit costs in measuring VFM - Girl Hub is doing something different and the costs are high at the start because of the experimental nature of the work. The costs may come down over time.”
There was a sense that Girl Hub was doing something highly innovative and evidence of behaviour and social norm change will take time. For example, one DFID staff member observed, “Girl Hub was set up in Ethiopia with a clear value for money framework. To date we can only assess against cost economy and cost efficiency - which audit shows are good. It is too early to measure VFM with regard to effectiveness or equity, so we should be careful about making VFM judgements without using a clear framework and metrics.”
## Future models
Most respondents said the current Girl Hub strategic collaboration is a feasible and sustainable model in terms of empowering adolescent girls to scale. A few said they were unsure and needed further evidence. For example, one DFID respondent said, “I remain on the fence. Need to see more of Girl Hub’s work and results”. One DFID respondent was less convinced: “No - very reliant on huge DFID investment; not a model that builds country ownership & capacity; too heavy on international consultancies; not delivering VFM nor is it sustainable or scalable in its current form.” However, due to the low response rate from DFID staff, it is not possible to draw any firm conclusions about DFID staff opinions on whether the current Girl Hub model is feasible and sustainable.
A few DFID respondents highlighted the early ‘creative tension’ in the partnership and the need to continue working on this.
“I don't know. It seems to be a pretty uncomfortable relationship. Maybe that's a creative tension that brings out the best in both parties or maybe there isn't added value in forcing DFID and the Nike Foundation to be bound so closely?” (DFID)
“There is still confusion about the nature of the Nike Foundation partnership - it feels like Girl Hub is owned by the Nike Foundation but does some work for DFID - I think the partnership needs to become more balanced in the future if it is to be sustained.” (DFID)
Girl Hub respondents were generally more positive about the partnership and the combined impact of the strategic collaboration. For example:
“The developmental reach of DFID combined with the Nike Foundation's approach is truly original and has already been very impactful. Opposites often attract and in many cases produce beautiful things. Girl Hub is one of them” (Girl Hub).
“Taking the best of brand/innovation and DFID influence and expertise has been an amazingly powerful model and it feels like having been through the pain barrier of combining ways of working, now is the time to capitalise!!” (Girl Hub)
However, there was recognition amongst several of the Girl Hub respondents that while the current model is an appropriate one for the short-medium term, there are benefits to opening up the Girl Hub partnership to a wider set of partners in the long-term:
“The current Girl Hub collaboration is a feasible model and has been sustainable in the short-term. In addition to partnering with DFID in the future, it would be good to consider additional partnerships with World Bank, etc to continue to bring work to scale in other contexts.” (Girl Hub)
“Other partners need to come into this if we are to achieve scale and unleash the girl effect. DFID contributes less than 5% of development aid. There needs to be much more action and capacity building by others from the private and public sectors.” (Girl Hub)
“Eventually there should be an exit strategy or hub should be set up as social enterprises” (Girl Hub)
Survey Graphs (by Organisation)
How relevant are Girl Hub strategies / programmes to the context in the countries they operate?

Number of respondents
Score from 1 (not at all relevant) to 5 (very relevant)

How successful do you think the Girl Hub have been as a catalyst in activating others to take a girl-centred approach?

Number of respondents
Score from 1 (not at all successful) to 5 (very successful)

How effective do you think the Girl Hub’s social communication has been as a means to generate dialogue and interaction among target groups?

Number of respondents
Score from 1 (not at all effective) to 5 (very effective)

How effective do you think the Girl Hub’s knowledge products have been in generating robust evidence and insights?

Number of respondents
Score from 1 (not at all successful) to 5 (very successful)

As an organisation – to what extent do you agree that DFID has learned and been transformed by the Nike Foundation to deliver a more girl-focused approach in development programmes?

Number of respondents
Score from 1 (strongly disagree) to 5 (strongly agree)

Do you think that the Girl Hub's work has provided value for money?
Number of respondents
Endnotes