Type of Review: Annual Review

Project Title: DFID Zimbabwe Pro-Poor Growth Programme

Date started:	24 September 2013

Date review undertaken: 25 September – 18 October 2013

## Introduction and Context
What support is the UK providing?
Up to £13.54 million until 2015 to: / Provide support to rural businesses with grants and loans and the provision of business development support services. / Increase access to affordable finance for the economically active poor, with a particular focus on empowering women and, in doing so, help to reduce gender based violence. / The programme is being delivered through four interventions: / £2 million for the Zimbabwe Agricultural Development Trust (ZADT), a trust which includes the $15 million Create fund, which provides support to financial institutions to on-lend to agricultural market intermediaries that benefit small-scale farmers / £2 million to help strengthen the microfinance sector through establishing the Zimbabwe Wholesale Microfinance Facility (ZMWF),a trust which will provide wholesale funds to MFIs and other microfinance organisations, including SACCOs, which in turn will provide credit and other microfinance to their clients; introducing a microfinance act and regulations; and mainstreaming HIV AIDS/ Gender issues into the microfinance provider business models / £1.54 million to the Agro Initiative Zimbabwe (AIZ), a facility to encourage innovative ideas in agriculture and agro-processing, providing grant funds and technical assistance to grow the ideas / £8 million to the Africa Enterprise Challenge Fund (AECF), a programme of the Alliance for Green Revolution in Africa (AGRA). AECF is an Africa-wide challenge fund, and the DFID funding contributes to the Zimbabwe window of the AECF. / The interventions are supported by other donors and implemented in part by consultants and donors: / ZADT. Donor partners- SNV (Netherlands Development Organisation), Hivos (Humanist Institute for Development Cooperation), DANIDA; implementers - SNV and Sabi Consulting / ZMWF. Donor partners-Hivos, DANIDA, GIZ (German Agency for International Cooperation); implementers – Zimbabwe Microfinance Wholesale Facility (ZMWF) Zimbabwe Association of Microfinance Institutions (ZAMFI), Hivos / AIZ. Donor partners – Nduna Foundation, Delta; implementer TechnoServe / AECF. Zimbabwe Window (round 2, 3 and beyond) Donor partners - Soros Economic Development Fund (SEDF) in R2 only, SIDA, AusAid. Implementer - KPMG IDAS

What are the expected results?
The four programme components have the following expected results, based on the business case (2011) and subsequent amendments following the 2012 review. / ZADT – The primary outcome of the intervention is improved access to finance for intermediaries in the rural agriculture and food value chains. This is expected to lead to improved input supplies and market access for small producer commodities; contributing to an increase in smallholder productivity, incomes, employment opportunities and ultimately to improved livelihoods of poor rural families. / The outcome as at December 2015 is measured in terms of the following indicators: / 400 intermediaries borrowing from the participating banks / 80,000 beneficiaries linked to intermediaries / 10% annual growth in intermediaries’ income / Average of $200 increase in beneficiary incomes. / At the output level, as at December 2015, the fund will: / Provide 50% of intermediaries applying to the facility with appropriate capacity building that lowers their business risk and allows access to funds / Experience no greater than 5% loan defaults by intermediaries / Target to ensure that 70% of beneficiaries are women-owned / Develop 4 tailored financial products for beneficiaries / Commit 97.5% of the available funds to intermediaries within 12 months. / ZMWF – The main outcomes of the intervention are expanded access to financial services for the economically active poor, especially women and a reduction in Gender Based Violence / Intimate Partner Violence, through capitalisation of MFIs. / At the output level, as at 31 December 2015, ZMWF will, on a cumulative basis for the programme as a whole: / have provided financing to a number of microfinance providers that have attained operational self sufficiency / enabled 18,000 economically active poor people to access financial services, 70% of whom to be women / A microfinance act and regulations approved into law and enacted, influenced and enabled by ZAMFI (Zimbabwe Association of Microfinance Institutions) / A number of innovative microfinance products introduced into Zimbabwe by 3 microfinance providers / MFIs mainstreaming HIV/ AIDS and gender issues and providing 500 of their clients with training, with an impact on reported GBV and HIV prevalence. / AIZ – The primary outcome of DFID funding, for technical assistance and seed capital over four years, combined with corporate sponsorship, is to enable AIZ to award prizes to 21 grantees that demonstrate the potential to generate outgrower/contract farming opportunities. / At the output level, by December 2015, it is expected that AIZ will generate: / 4,200 sustainable jobs/opportunities / £2.3 million incremental small farmer revenue / £2.87 million income for the grantees. / It is anticipated that the scaling up of some of the pilots will occur within the program timeframe, and the implementing partners would hope to help raise additional finance for the most successful models to enable additional growth opportunities. / AECF– In March 2013, AECF’s Zimbabwe Window logframe results were substantially reduced, with formal approval still to be sought from both AusAid and DFID. The justification for this important change was to ensure the targets are realistic. DFID have not yet approved these changes. However, as the revised AECF figures have been incorporated into the most recent consolidated DFID logframe, our analysis is based upon the figures in the most recent logframe. The primary outcome of AECF’s Zimbabwe Window aims to provide aims to provide 30 project (down from 34) grants/no recourse loans totalling $22 million (down from $27 million) by the end of 2014 that contribute to the rehabilitation and regeneration of agri-businesses and rural financial markets. / Thus, at the output level, by December 2014, it is expected that AECF will benefit: / 200,000 poor, rural households (down from original logframe target of350,000 households) by at least $75 (down from $100) per household per year / generate 5,000 direct jobs in businesses and related supply chains over the course of the programme. / The Pro-Poor Growth Programme logframe, and the individual component logframes for ZMWF and AECF, have been revised (although the latter has not yet been endorsed by DFID). The Review team has used the milestone targets from these documents to assess programme delivery. AECF provided the Review team with both the contracted logframe and the revised logframe to allow a comparative assessment.

What is the context in which UK support is provided?
Zimbabwe experienced a decade of sustained economic decline at the start of the New Millennium. There was a 50% decline in GDP between 1998 and 2008, in large part caused by economic policies and a significant deterioration in the business climate. Together with the effects of hype-inflation that reached two quintillion percent in October 2008, this resulted in the abandonment of the domestic currency and the adoption of a multi-currency framework in Zimbabwe. Family level food security, whereby rural family members delivered basic foodstuffs to those family members living in urban areas (estimated at its peak to amount to 1.5 million metric tonnes annually and three times higher than commercial farm maize sales) collapsed when government decreed in 2004 that all maize sales should be to the Grain Marketing Board. This restriction was relaxed in 2009. Together with the erosion of purchasing power, caused first by hyper-inflation and second by the dollarization of transactions, this has seriously impacted on the ability of food deficit households to purchase sufficient food. / Zimbabwe’s Human Development Index (HDI) ranking has had the steepest fall of any country – it fell from 130th out of 174 countries in 1998 (in bottom 25%) to 173rd out of 187 (in bottom 10%) countries in 2011. On measures of empowerment, women fare badly in Zimbabwe. They face significant barriers to accessing affordable finance, levels of gender based violence (GBV) are high and women are disproportionately affected by HIV. / Despite a return to positive economic growth following currency reform in 2008-09 and the advent of the Government of National Unity following the 2008 elections, the rural economy remains depressed through a combination of limited agricultural financing, input/output market constraints and diminished service industries. The Reserve Bank remains technically in default and banks are still greatly under-capitalised. With the wiping out of Zimbabwe Dollar bank accounts as a result of dollarization, domestic savers are reluctant to deposit funds in banks and potential foreign investors have little incentive to bring external funds into the Country. Lack of liquidity and high perception of risk are critical barriers to the economically active poor’s ability to access finance that would help them to start or grow their businesses and better cope with shocks. / DFID’s intervention aims to contribute to and help to consolidate emerging donor efforts to revitalise the agricultural sector and to catalyse private sector innovation in Zimbabwe, drawing on a proven track record of support to business challenge and prize funds and to create two sustainable trusts (agricultural development and wholesale microfinance) that can provide focused products and finance that directly or indirectly encourage income growth for small farmers.

## Section A: Detailed Output Scoring

Output 1:
Commercially viable business ideas to demonstrate clear poverty impact especially for women / Score: Score: A (profitability and sustainability indicator on track, underperformance on women-owned business target)
Measures: / Indicators from output 1 and output 4 have been swapped to include one gender indicator under output 1 and the enabling environment indicator under output 4. We do not believe this arrangement is helpful; and propose the gender indicator should be moved to Output 4 / The existing weighting (40%) remains appropriate for this output. / Number of MFIs borrowing from ZMWF that have attained operational self-sufficiency (OSS) – exceeded / 9 loans have been disbursed up to September 2013 and ZMWF reports 6 MFIs are close to, or have achieved, operational self-sufficiency. However these OSS measures are misleading. They are being achieved through a combination of very high on-lending rates and reduced overheads, despite small loan portfolio sizes, due to ZMWF’s limited capital base. As such, ZMWF is unable yet to fully address the overall aim of the fund which is to rebuild and recapitalise the MFI sector. / Number of projects including agribusinesses that are profitable and sustainable – evidence of a portfolio approach for AIZ and AECF which, in aggregate, achieves reasonable viability and risk metrics to achieve results / It is too early to indicate definitively what proportion of funded projects will be sustainable. / ZADT does not have a financial viability indicator, though we recognise that CREATE does monitor its financial performance closely. However, compared with the 39 loans that have been fully repaid, 12 (31%) have been rolled-over and a further 5 (13%) have required top-ups. This suggests that there may be issues with the financial sustainability of about 45% of the loans to businesses receiving finance from the fund within the first year of support. However, the banks do take full responsibility to return the funds to ZADT whether the end-borrower pays them back or not. This design feature sets it apart from a challenge fund in that ZADT has effectively transferred its credit risk from intermediaries to the banks (who rely on their credit reputation as a fundamental part of doing business). In order to influence the risk bank risk appetite, ZADT offers to take on 50% credit risk in select instances where the expected positive development impact outweighs heightened credit risk. To date, of the 8 loans guaranteed by ZADT, the Review team understands only one - Leoford Investments - is under stress and is being discussed. Any losses would be shared equally with the bank and ZADT; and ZADT should be able claim its loss from its insurers. / AIZ estimates incremental revenues by prize-receiving business to have reached £1.6m ($2.5m) by end September 2013. In discussion with TechnoServe it appears that ‘incremental income’ reported for Origen and Peak Trading is actually be the gross income earned by smallholders – rather than isolating the additional income resulting from the PPG intervention. From an evaluation perspective, it is important to isolate the net effect of the intervention. Working with TechnoServe, we would discount Origen and Peak Trading by 70% and 60% respectively (to isolate net revenue) which would revise the estimate of total incremental revenue down from $2.5m to $1.1m. TechnoServe have been prudent in including no economic benefit for the Mubatsiri market information service. Even including these revisions, the project comfortably exceeds targets. / KPMG assess the profitability of projects 36 months after receiving the AECF grant. At the end of 2012 this figure was 37.5% - slightly below the logframe target of 40% in August 2013 (interpolating between a target of 30% in 2012 and 50% in 2015). In addition, by August 2013, 30% of AECF repayable grants had been repaid on time or within 12 months of due date. This performance falls below the logframe target of 40% repayment by August 2013. These indicators suggest that AECF has a slightly higher risk profile than was anticipated in the log-frame and most businesses receiving support are cash-constrained. If this were not the case, it would be legitimate to question the additionality performance of the AECF. / The challenging operating environment in Zimbabwe makes the sustainability of any business uncertain. The ‘traffic light’ analysis of the AECF and AIZ suggests that: with 42% and 50% respectively of projects in the ‘green zone’; 53% and 42% in the ‘amber zone’ respectively; and 5% and 8% in the ‘red zone’ – a reasonable balance between the goal of financial sustainability and having the appetite for risk (which is essential in order to justify the use of public aid money for private organisations) is being found by both mechanisms. Although most businesses which the AECF is supporting are cash-constrained, the risk of default is considered to be medium only, provided Zimbabwe does not slip back into economic collapse. / Percentage of women owned businesses accessing financial services – under performance / Neither the AIZ nor the AECF have any gender targets in their logframes. This reflects the design of the programme; 70% of the programme funding delivered through programmes with no formal gender focus, this was acknowledged by DFID following the 2012 review. Both AIZ and AECF have made some effort during the year to address this issue, however it is difficult to address retrospectively. Technoserve developed a proposal which was submitted to the World Bank’s Gender Innovation Lab initiative aimed at mainstreaming gender equality into subsequent AIZ competitions (bid unsuccessful, but some aspects may still be built into AIZ work under the PPG – eg enhanced M&E); AECF – disaggregation of results by gender in line with DCED requirements, AECF at a global level have considered running a women only funding window) / An SNV verification exercise in June 2013 revealed that 32% of Fund beneficiaries are women, undershooting the target of 50% of women receiving capacity building and credit support as detailed by the official 2012 logframe. ZADT previously proposed an additional global logframe indicator to better reflect their performance in addressing the needs of women owned businesses, as the above indicator focuses more on ZMWF performance. The wording proposed is “Percentage of female headed household beneficiaries linked to borrowing value chain intermediaries”. Proposed revised target is 30% by 2015, 20% in 2013 and 10% in 2012. / To date ZMWF has disbursed $50,000 to the Women’s Development Savings and Credit Union (WDSCU), the entire amount has been distributed as loans to its members (an average loan $416) all beneficiaries are women. As such, although actual loan disbursements are low the milestone for this indicator has been exceeded. Approximately 99% of WDSCU historical loans are made to women borrowers. This indicator has been re-worded in the new logframe to “percentage of loan contracts financed through ZMWF wholesale loans signed by women.” On this basis, the Nathan Report found that 73% of ZMWF loans to MFIs go to women borrowers out of a total 4208 loans to MFI clients.

Output 2:
Appropriate financial products accessible to value chain actors
Score: A / Measures: / At 30% the weighting for this output remains appropriate. New product development and organisational self-sufficiency are key attributes of a long term financial sector intervention. / Number and types of financial products – being achieved and potentially exceeded, / The PPG logframe specifies a target of 2 financial products by December 2013. / In addition to grant finance, PPG has been offering one financial product to date – a short term loan ranging from 1 to 36 months duration. Short-term loans alone are not an appropriate financial product to recapitalise the agricultural sector. To this end PPG partners are beginning to experiment and pilot initiatives to more effectively serve the market; / ZADT has introduced a 50% guarantee in its engagement with qualified banks as an incentive to provide under-collateralised borrowers with finance. A guarantee is a useful complement to the 11.5% loan, but it is not a product in its own right. The guarantee is being extended to 75% and this is significant; because the banks have indicated an appetite to accept up to 25% of loans on an unsecured basis. ZADT is also planning the introduction of an unsecured value chain product; and is experimenting with, a group lending product, currently benefiting more than 400 banana and tea growers in Honde Valley. / ZMWF provides information on new and innovative microfinance products to its MFI clients. ZMWF is engaging with three MFIs to introduce new microfinance products based on assessed needs of their clients. MOUs have been signed with MicroKing to introduce a loan for dairy production and with Quest Finance for a cassava production loan. MicroKing has begun rolling out the dairy product (with its own funding) and Quest Finance are due to release the cassava product to market before December 2013. The selection criteria for engaging with MFIs include openness to new products. ZAMFI has provided four sensitisation events for MFIs on innovative products, including mobile banking, agricultural value chain finance and micro insurance. This represents good progress, given that ZMWF only began lending in 2012. / Productive utilisation of disbursed funds: a mixed picture / The 2012 Review focused on different definitions of ‘productive utilisation’. This Review adopts a more pragmatic approach and assesses simply whether programme support is reaching the intended beneficiaries (low-income smallholders) and encouraging eligible activities (i.e. productive agriculture). / During the project visits, the Review team saw more than one instance where CREATE funding had been absorbed either totally or mainly to finance the working capital of the intermediary with either none or limited benefit to the target population of smallholder producers linked to the intermediary[1]. The counterfactual here would be allowing this type of business to fold completely with all future benefits accruing to smallholder producers, regardless of extent, being foregone. / Similarly, it appears that that the large majority of end-beneficiaries of ZMWF funding are using their micro-loans for short term working capital for trading activities rather than productive investments. Only few MFIs are able to offer loans for productive enterprises. / Both the CREATE fund and ZMWF should pursue proposals to actively address the tension between the need to recapitalise businesses (and MFI’s) who’s financial assets have been wiped out post dollarization, and the need to ensure that intermediaries engage in smallholder focused value adding activities and that a proportional amount of this value is passed onto the end beneficiary. / The Review team has confidence that AIZ funds are being used to benefit the intended beneficiaries. The AECF funds too are clearly impacting upon the livelihoods of many low-income rural people. Clearly some of the project beneficiaries are not in the target group – principally for the mobile-enabled financial services and for the Yelo Egg broiler project – although it is challenging and possibly unrealistic to target fund beneficiaries with pin-point accuracy using a private sector development approach. / Operational self sufficiency of the funds: only with further funding / The measure has been re-worded in the revised logframe to “Operational self-sufficiency for ZADT and ZMWF”, and the definition of OSS provided in the 2013 Aide Memoire. / OSS will be achieved in ZADT when additional funds are provided to the programme, provided loans are repaid. It is expected that operating costs will remain relatively flat compared to funds under management, which attract an arrangement fee charged to banks. DANIDA’s planned further injection of funds could provide a significant boost to the self-sufficiency of ZADT; although the Review team urges CREATE to monitor closely the early-warning signs of a potential future repayment problem (roll-overs and top-ups) and ensure these are not realised; even though CREATE is well protected from losses through risk sharing with the banks and its insurance policies. / ZMWF has fewer funds to work with, and interest income at 11% is insufficient, even if the wholesale funding is totally absorbed, to cover current operating costs. Again, further capital injections would have a large positive impact. The Nathan Report finds that ZMWF is unlikely to increase its level of OSS at the current level of funding. A sustainability analysis found that $4.98m at 8.94% yield or $4.03m at 11% or $3.41m at 13% will enable ZMWF to cover its operating costs. While this may be the case in so far as the facility itself is concerned, the extent to which these funding levels will support the needs of MFIs to recapitalise and the needs of their clients for productive loans needs to be determined; and should be subject to further analysis.
[1] With a small sample of projects visited, it is not possible for the Review team to estimate the magnitude of this problem amongst all 109 CREATE funded projects but this suggests that issues reoccurring in the small sample could be fairly widespread.

Output 3:
Financial and technical support to agribusinesses with innovative and inclusive business models
Score: A+ / Measures: / Weighting of 20% for this output remains appropriate. / Number of agribusinesses supported –exceeded for AIZ, AECF and Create / AIZ has already approved support through grant awards, in three annual rounds (4 in 2011, 8 in 2012 and 5 in 2013), to 17 enterprises (100% attributable to DFID funding). AECF, which has also progressed through three rounds of the Zimbabwe window, has contracted 31 enterprises, which is slightly above the revised logframe target (8 of which [27%] are attributable to DFID fuunding). The ZADT is supporting 109 businesses with the CREATE fund, which exceeds the logframe target (milestone 1 in 2013 is 80 intermediaries), 14 of which (13%) are attributable to DFID funding. / As it currently stands this logframe indicator measures the performance of the AECF and AIZ only, with an aggregate performance of 25 agribusinesses against a target of 15 agribusinesses. It is proposed that the logframe be amended to include CREATE Fund numbers and that the target be increased accordingly. / Incremental agribusiness revenues – exceeded for AIZ, unclear for ZADT, AECF below target / During the Review, ZADT claimed that an average 39% increase in intermediary turnover as a result of the credit facility; based on a sample. / AIZ’s expected outcome measure is £2.87 million, equivalent to the global result under this output measure. AIZ reports that $2.5m of cumulative incremental business revenue has already been earned by AIZ winners, which is far in advance of the logframe target of $137,000 at milestone 1 (December 2013). Working with the Review team TechnoServe identified two projects where the AIZ project was attributing gross smallholder income to the AIZ intervention, rather than the net increase in smallholder income which can be attributed to the project. The impact of applying reasonable discount factors to estimate net incremental revenue figures for the PEAK Trading and Origen project figures is to reduce our estimate of cumulative incremental business revenue from $2.5m to $1.1m. / A case study of the significant difference between gross and net revenue impacts / The benefit of the AIZ PEAK Trading project is not the total payment to smallholders for agricultural commodities paid for by PEAK Trading (as TechnoServe claim) but rather the difference in smallholder revenue between the previous buyers – compared with the new, higher, prices paid by PEAK Trading. This is not a nebulous definitional issue, it is the difference between quantifying the benefit from DFID funding of $300 a tonne (the gross PEAK Trading price for maize at present) or the more realistic benefit figure of $100 a tonne (the difference between the PEAK price and the $200 a tonne which smallholders were receiving before the project). / Reducing the total farmer benefit figure by 60% (from $221,207 to $88,842) takes account of the difference between gross and net impacts. / AECF quantifies incremental project benefit which can be attributed to their interventions. These currently total net benefit of $4.2m, which equates to $26 per beneficiary per year. This is considerably lower than the target that has been already revised downward to a benefit per person of $50 in 2012 and $75 in 2014. / The logframe targets for this indicator, in 2013, 2014 and 2015 are £137,000; £629,000 and £2.9m respectively – this indicator only captures the performance of AECF and AIZ. It is proposed that this indicator include the performance of the CREATE fund and that the targets are adjusted upward to reflect this as well as increased stretch in performance. It is also important to ensure that any increase in agribusiness revenue is attributable to the project (rather than, for instance, commodity price inflation or improved performance in a part of the business which should not be attributed to the intervention. / Days and types of technical assistance provided to agribusinesses – exceeded / SNV has provided capacity building support for 27 of their 109 loans, 22% of the total. The project visits also revealed that SNV had procured effective capacity support for smallholder beneficiaries. In other cases, the Review team met intermediaries that were in urgent need of technical support that had not yet been forthcoming. SNV has also assisted 29 intermediaries to prepare their business plans who are awaiting the results or are yet to submit applications to the banks. / The logframe target is for 420 days of technical assistance provided to agribusiness by December 2013. AIZ has already provided 840 days of TA to date. The types of TA include capital raising, market linkages, financial modelling and extension support. Grantees highlighted the support AIZ TA provided – in the form of business planning and the application process itself - in graduating from AIZ to AECF support. Project visits also revealed a significant amount of encouragement and non-technical support for entrepreneurs. Although the logframe does not include any indicator of the quality of TA, our impression from project visits was that AIZ TA is high quality and highly-valued by the grantees. / AECF does not measure days of TA as part of their logframe, as there is no TA facility within the AECF. However, in reality, an increasing volume of AECF support, as part of their ongoing portfolio management, is being used to support grantees that are facing challenges to their businesses. As the supply of relatively straightforward, large projects suitable for AECF funding with minimal ex ante support declines – a process now apparent from the R3 in 2013 – the case for more active support on the demand side of the challenge fund becomes increasingly compelling; (and also a review of the requirements for the Fund Manager to visit all AECF project quarterly, which in some cases, absorbs significant resources without adding sufficient value to justify the exercise).
Output 4:
Enabling environment for business and microfinance
Score: B / Measures: / As mentioned in the discussion under output 1, the Review team propose that the gender indicator should be moved to Output 4. / The 10% weighting for output 4 is sufficient to emphasize the importance of ensuring that the enabling environment facilitates the development of microfinance and the PPG’s gender focus. / Number of regulations supporting the growth of the financial sector – on track / The Bill was laid before Parliament on 31 August 2011, and was passed and signed into law in June 2013, before the recent elections. ZAMFI led the MF sector dialogue on the draft Bill; organising meetings country wide and gathering and synthesising members’ views and communicating the amendments proposed by the sector to Parliament. These were to: extend the annual licence requirement to an indefinite period licence, which could be revoked by CBZ; reducing the Micro Finance Bank (MFB) capital requirement of $5m; including MFB customers under the depositor protection scheme; and addressing contract resolution issues. The amendments were agreed by Parliament but, due to an administrative hiatus, were not incorporated into the Bill before it was signed into law. ZAMFI is now working with the Ministry of Finance to include these in the 2014 Finance Bill. / 2. The number of GBV/ IPV reported to the police and local traditional leaders– output indicator data not available[2] / ZMWF is the only one of the four programme components that is required to address GBV/IPV. ZMWF adopted the IMAGE model from South Africa, of training MFI clients on Gender GBV and HIV to influence women’s economic empowerment and decision making. The model in Zimbabwe was applied at three MFIs - WDSCU, Zubo (women’s group affiliated to WDSCU) and MicroKing. The training was targeted at women clients and excluded males, community leaders, opinion leaders, police who could play a critical role in behaviour change towards reporting of GBV issues. The training left out the staff and management of the MFIs, who need to be sensitised on gender issues and buy in to this agenda. / The Nathan Report on ZMWF points to possible proxy indicators for reporting on GBV. The report noted that some of the MFIs reached with training had reported that the performance of their clients had been affected by their experiences of GBV in the last year. Some of the positive outcomes of the training included: awareness among MFIs clients of the social and cultural practices that lead to GBV and increase vulnerability to HIV; improved household relations as a result of communication skills gained through training; about 22% of trained MFI clients went for voluntary testing while 7.9% developed a positive attitude towards living with HIV.[3] All these are intended benefits of the gender, HIV/AIDS and Women empowerment training. / 3. Number of females in decision making positions in beneficiary enterprises – off track / At the MFI level, consultation with ZWMF indicated that most of the MFIs it is supporting are led by women. However, it was not possible to understand the gender composition of their boards and the positions that women occupy in those boards. / Regarding end beneficiary enterprises, ZMWF reported reaching 73% females and 28% males with loan facilities. A close analysis of some of the outcomes of the ZMWF training in GBV and HIV shows potential proxy indicators for decision making. About 80% of the MFI clients who received training reported contributing to decision making at the household level while 60% made decisions about household spending and 31% jointly made decision with their husbands. / ZADT which focuses on lending to enterprises focusing on agricultural value chains indicated that there are relatively fewer women in leadership position among the businesses. ZADT had set a target of reaching 50% of women small holders receiving loans 2013. It has managed to achieve 32%.[4] One of the major reasons for failure to reach the target was that most of the activities supported by businesses fall in the category of “male domain”. This suggests the need for gender sensitization of ZADT staff and the businesses that they support, so that they understand how women participate in agricultural production at the household level which is invariably linked to value chains. In this way there would be broader understanding of the various integral roles that women play and the value of building women leaders would be clearer. / AIZ and AECF do not have any specific WEE targets. Given that both these programmes are integral to value chain development where women play a host of roles, it is recommended that both organisations have suitable targets in their logframes. Overlooking gender roles runs the risks of excluding parts of the value chain and thereby undermining potential growth and profit margins in all the businesses. When these are escalated, they end up constraining growth at national level.
[2] Findings for this output indicator are mainly informed by findings of the comprehensive Nathan Evaluation of the ZMWFT (Sep 2013), consultation with ZMWFT staff and partners, review of PPG planning and monitoring tools (PPG Business Case, Institutional Self-Assessment Report and Log frames) and field data from ZMWFT beneficiaries. Review of ZADT project planning and monitoring tools as well interviews with ZADT staff and partners also informs review findings
[3] Nathan ZMWFT Evaluation Report, September 2013
[4] Inception feedback meeting at DFID and ZADT self-assessment Report.

## Section B: Results and Value for Money
1. Progress and results
Has the log frame been updated since last review? / Yes, but in a way which has caused a degree of confusion amongst project partners. Each of the four components of the programme has a separate logframe. Since the last review, two of these have changed. In one case, the ZMWF, these logframe changes have been agreed between DFID and the Trust following a normal process. In the other case of the AECF, KPMG informed DFID that significant changes to logframe targets had been made by KPMG, communicated to AGRA but not formally to AuzAid and DFID. These changes to the Zimbabwe Window need to be formally communicated to donors for their ratification. / The reason for the lowering of targets is to increase their realism and the likelihood of the programme reaching them. The revised targets were informed by the actual experience of competitions in the field. Whatever the justification for these significant changes, the process by which they were quantified and communicated to DFID (as a minority but still significant investor in AECF-Z, but by far the largest financier of AECF), should have been more transparent and consultative. As a consequence DFID has not yet endorsed these changes to the AECF logframe. The AECF FM has been fully transparent in his response to the Review team’s questioning on this issue. / Table 1: Changes to the AECF logframe targets for 2014 / Indicator Original logframe target Revision March 2013 Change / No. poor rural households benefitting from AECF-funded projects 350,000 200,000 -42% / Average benefit received per household per year $100 $75 -25% / Total value of benefits received in final year $35m $15 -57% / Total value of cumulative benefits received $100m $40m -60% / Annual impact ratio (benefit per $ disbursed to projects by AECF) 1.26 0.8 -37% / Cumulative impact ratio (benefit per $ disbursed to projects by AECF to date) 3.57 1.63 -54% / In response to the above, during the course of 2013 the targets for the OP headline results (economic opportunities) and the ‘We Wills’ (access to finance) have been modified. The global PPG logframe is still to be updated to reflect these changes, for the purposes of this review; / the previously approved logframe (2012) has been used as the ruler against which the review team have assessed programme performance at an output level / the updated OP headline results and ‘We Wills’ are used to gauge performance at the outcome level. / It will be necessary to adjust the PPG global logframe to reflect the changes agreed as a part of the results refresh. / Table 2 below outlines the changes to key indicator targets in line with this result refresh process and actuals achieved as at September 2013, indicating that DFID Zimbabwe is broadly on track for both economic opportunity and access to finance. / Table 2: Proposed Changes to Key Outcome indicators for the PPG Programme / Indicator Milestone 1 / (Dec 2013) Milestone 2 (Dec 2014) Milestone 3 / (Dec 2015) / Economic opportunities / ‘OP headline results’ ¹ (target) 66,000 79,000 86,000 / OP headline results (actual as at September 2013) 77,386 / Old PPG logframe targets (2012) 56,083 ­­108,641 129,642 / Proposed revision to PPG logframe targets (2013) 56,000 58,182 64,612 / PPG attributable as at September 2013 55,784 / Access to finance / ‘We wills’ ¹ (target) 20,000 25,000 29,000 / ‘We Wills’ (actual as at September 2013) 22,070 / Old PPG logframe (2102) 10,688 9,865 29,591 / Proposed revision to PPG logframe targets (2013) 6,500 12,000 18,000 / PPG attributable as at September 2013 4,247 / Notes: / 1. The ‘OP headline results and we wills’ are based on DFID financial years (i.e. April to March each year) rather than calendar years. / 2. Contributing to these outcomes, in addition to the PPG, is the PRP programme, which includes 17,823 A2F beneficiaries and 21,602 economic opportunity beneficiaries. All of whom are also counted as economic opportunity beneficiaries and additional non-A2F economic opportunities. / 1.2 Overall Output Score and Description: / The analysis suggests mixed performance against the logframe – an aggregate score of A is proposed. / Output 1 (40%): Commercially viable business ideas to demonstrate clear poverty impact especially for women) A / Output 2 (30%): Appropriate financial products accessible to value chain actors A / Output 3 (20%): Financial and technical support to agribusiness A+ / Output 4 (10%): Enabling environment for business and microfinance B / There are instances where data has not been available and /or it is too early to tell. There are also instances where programmes have reported under spend / disbursement against budget, this is due in part to the fact that this review was conducted in late September / early October 2013 and several of the milestone targets are set against a December timeline. In such instances implementing partners have provided comfort around progress made to date and the likelihood of achieving milestones. / Direct feedback from beneficiaries / Please see appendix 1 for detail. / Summary of overall progress / Please seen appendix 1 for detail / 1.5 Key challenges / All four programme components are piloting different approaches to pro-poor growth in a post crisis scenario. These mechanisms are being used in an environment for which they were not specifically designed and there is clear evidence that ZADT, ZMWF and AECF need to adapt their business models to better suit the needs of their clients. A key input to any redesign is programme wide value chain analyses of key agricultural sectors, particularly at primary smallholder producer levels, that take into account the totality of household resource use, production and cash flows and the differing roles of women and men along value chains. / Direct and untargeted subsidies, including the on-going voucher and agricultural input subsidy programmes, can badly distort markets. As long as these persist, programmes such as PPG, will struggle to achieve their objectives. At the same time, financial and product markets can work better for the poor through providing more indirect subsidies, such as BDS and technical support for producers. / Recent improvements in monitoring the AECF are applauded. AIZ monitoring is less rigorous and there are some specific weaknesses in the approach. However, TechnoServe are attempting to monitor results accurately. Elsewhere, monitoring and verification of results is weaker; though ZADT is now implementing a detailed M&E programme. The programme components and their partners should greatly strengthen knowledge management, learning and networking. / All of the grant recipients and smallholder farmers face an uncertain time based on whether the rains fall in a way that provides for good quality harvests. The weather patterns in Zimbabwe appear to be impacted by climate change-related volatility, with longer droughts and heavy rains. / The uncertain political and economic landscape following the elections, remain an overarching challenge. / ZADT- The challenges facing ZADT are as follows: / ZADT was designed as an Inclusive Business Fund for smallholder farmers in order for them to work with companies over time, recognise agriculture as a business, improve performance, learn to bank and invest and eventually be ready to borrow directly from banks. The provision of loan finance to intermediaries, who then provide inputs and other services including finance for capex to smallholders for irrigation on credit (and the provision of direct credit to smallholders as ZADT is now piloting), does not guarantee that these positive results can be achieved. It is necessary for there to be a full understanding of the link between the intermediary and smallholders. In addition, an appreciation of the totality of household production, resource use and understanding of the roles of men and women is necessary to anticipate the development impact of this intervention. / Allied to this, ZADT needs to facilitate the inclusion of smallholder producers into mainstream financial services through the partner banks or other mechanisms so that, over time, smallholders become bankable in their own right, and not through intermediaries for whom credit management is not their core business. / The financial product to date has been essentially a short-term working capital loan for intermediaries; and does not address the agricultural production cycles or needs of producers to invest in capital assets to improve their production in agricultural production. The review recognizes that it was the initial focus of ZADT to gain experience and acknowledges that CREATE does now offer longer tenures (up to 36 months) that includes an element for capital investment. However, ZADT the fund now needs to begin to develop and offer distinct loans for production and capital investments and explicitly link recoveries to revenue streams though the use of appropriate bullet and balloon payments. / For the ZADT model to work, high levels of technical support at producer, intermediary and bank levels are needed. The benefits of this approach were evident among smallholder banana growers that the review team visited; however intermediaries reported that they feel ZADT has little to offer them in way of capacity building support and ZADT reports that there has been no demand from intermediaries for TA. The current process whereby the capacity building needs of intermediaries is established by banks (and passed to SNV), as well as by SNV, for subsequent follow-up, may not be delivering the technical support that meets the needs of intermediaries. The levels of competence at the two banks visited - NMC and FBC - are higher than had been expected. / SNV appears to be seen as the public face of ZADT. ZADT needs to make clear to banks, intermediaries and smallholders the roles and responsibilities of its various components, including SNV. / ZADT needs to continue to work with the banks to harmonise its borrowing rates with those of the market and, as market conditions allow, address the factors that will allow it to leverage its resources so that current customers can “graduate” to become full customers of the banks. / ZMWF– The recovery process of the MFI sector is still at early stages and the wholesaler has only been disbursing for a little more than a year. While the wholesaler has conducted appropriate assessments and priced its loans for risks at the MFI level, its performance and growth are constrained by the level of available and funding and the capacity of the MFIs. In their attempts to recover, MFIs have not had the resources to (re)-instate products to provide efficient and appropriate products to clients, especially those in productive enterprises that need a grace period. In addition the wholesaler is disbursing in relative small tranches which limits the ability of MFIs to disburse and to grow their portfolio. The wholesaler in turn is limited by the size of the fund to on-lend; hence it builds its own operating margins through interest payments from MFIs as loans are disbursed. If the wholesaler had a larger fund and some early stage operating costs, it could enable the MFIs to instate products and systems for productive enterprises and to scale up. / The ZMWF final design and early implementation focuses more on its protecting capital than revitalising the sector (collateral, loan terms, disbursements and repayment schedules). This results in MFIs unable to build capital or create products to meet needs of clients in productive enterprises. Clients are largely stuck with trading loans at high interest rates and are limited in their ability to undertake loans to productive enterprises or build assets for themselves or in their businesses. Although the revised collateral and interest rate policies should contribute to some improvements in lending, ZMWF continues to be constrained by its small capital base and needs to focus more on the task of rebuilding the sector. In doing so, it will need to take greater risks, while the programme component overall has to address the sector’s serious capacity and skills constraints. / AIZ - Is a successful intervention in the sense that it is likely to generate 21 effective and impactful projects by 2015. The challenge for TechnoServe is to scale up the intervention to have an impact beyond the directly-supported projects. Fundamental to achieving this aim is for TechnoServe to communicate their experiences with AIZ much more clearly and prominently. / AECF–The challenge facing AECF is that there are significant signs that the supply of good quality, leveraged projects which can respond to competitions in Zimbabwe is limited and may be drying up. If this analysis is correct, AECF-Z must either adapt or risk becoming increasingly less relevant to Zimbabwe. An approach which responds to this challenge is likely to involve a transition from a somewhat passive fund-management model to a more developmental engagement that is active before, during and after competitions. The risk with this approach is that it requires a higher magnitude of technical input than the current model. This may not be compatible with the current fee structure of the AECF. The AECF has a mandate to seek systemic change which also requires a clearer understanding of market systems and a central focus on scaling-up the impact from some 30 projects to other businesses in agricultural sub-sectors. / 1.6 Annual Outcome Assessment / The programme calls for improved access to financial and business development services for agricultural value chain actors, SMEs and entrepreneurs, with outcome indicators that measure the number of jobs and opportunities created, the average income generated per new job opportunity, and the growth of agribusiness and financial sector in Zimbabwe. / All four components have made progress since inception, and are managed by dedicated and professional teams. In the case of ZMWF and ZADT, progress has been slow compared to original plans and this is partly due to a risk-averse approach and institutional challenges with the delivery platforms. The inability of AECF to meet all its outcome targets in the timescales envisaged reflects the weakness of the external environment and the relatively limited scope to flex their model of delivery. / Two of the four programme components report that the outcome targets, reflected in their logframes, are broadly on target. The Review team have attempted to critically review the way that programme partners report their results. From a results reporting perspective, the targets and performance figures presented below reflect the performance of the programmes components in total, DFID attribution (according to contribution) is then apportioned accordingly in the global log frame. / ZADT (DFID attribution current 13% / forecast 3%[5]) – A total of some $11.5 million (target 97%) million has been disbursed to 109 intermediaries (end 2013 target is 80), who report that 26,000 smallholders are linked to their businesses. The Fund Manager has reported some 63,000 beneficiaries are now linked to intermediaries (target 30,000), although this figure – an average of 600 per intermediary – appears to be very high, has yet to be verified and is not consistent with the numbers observed at the small sample of projects visited. On the basis of SNVs own verification exercise (7,000 from a sample of projects), it is very likely that a significantly lower number of smallholder farmers are linked to intermediaries than that reported by the intermediaries themselves or the Fund Manager. Intermediary turnover is reported as having grown by 39% (based on a sample of 19 intermediary businesses) and smallholder revenues by $250 as a result of the loans (targets 10% and $100). The Review team does not understand how these figures can be derived with any certainty, as the first wave of loans has yet to mature. / Reported output level results include: 22% of beneficiaries have received TA/CB support (target 30%); 32% of beneficiaries are women (target 50%); there has been only one financial product developed, namely the current loan product with a term of up to 36 months, with a second – unsecured supply chain finance – in development and a pilot ; and loan defaults are 0% (target 20% for 2013) although since many loans have been extended beyond their original term or have yet to mature and are measured at the intermediary rather than beneficiary level, it is too early to assess this indicator. / ZMWF (DFID attribution 100%)–its outcome is “expanded access to financial services for the economically active poor, especially women and a reduction on GBV/IPV, through capitalisation of MFIs”. ZMWF is moving towards this outcome in terms access to finance (much less so with regard to GBV/IPV as discussed in the detailed output review above); though its progress is hampered by the funds available, and need for MFIs to provide collateral in conjunction with the capacity of the MFIs in disbursing productive loans. / AIZ (DFID attribution 100%) – The job opportunities target at the first milestone have already been exceeded, with 821 jobs opportunities compared to 700 targeted. Smallholder incremental revenues also above target. / AECF (DFID attribution 27%) – The AECF Zimbabwe Window outcome is to contribute to the rehabilitation and regeneration of agribusiness and rural finance market systems in ways that benefit the rural poor. Its measures assume that the market system improvements and investments stimulate the effectiveness of private sector, government and donor interventions, and this is yet to occur at significant scale. / The AECF-Z Window is delivering good results, but these are significantly below the outputs envisaged. Outputs are being impacted by the very high risk profile around grant investments and slower than expected implementation. There is an inherent tension between trying to generate broad impact (i.e. large numbers of beneficiaries) and deep impact (i.e. significant change per person). As the figure below illustrates, using data from the 19 AECF projects (each project represented by a blue diamond) for which results exist, projects with a broad impact tend also to have a very small impact per person. Conversely, the projects which generate sufficient benefit per person to materially change household well-being tend to reach fewer beneficiaries. The statistical analysis below suggests that this inverse relationship between benefit breadth and depth is not particularly strong, but it does hold at a general level. The danger is that the very high breadth targets (originally 350,000 households now revised to 200,000) will incentivise the programme to select projects which spread a relatively limited benefit across a very large number of beneficiaries. / Households benefitting / Households Benefitting / Net Benefit per person (US$)
[5] Assuming 1) forecast fund growth to $35m by 2015 and 2) DFID contribution remains unchanged

2. Costs and timescale
2.1 Is the programme on-track against financial forecasts: / DFID allocation of funding to implementing partners in now broadly on track. / ZADT – ZADT is now using DFID’s funding from the beginning of 2013, as expected; and has drawn down all but £100,000 of DFID’s contribution. / ZMWF – The target for active loans in 2013 was 6731; currently 4208 are being on-lent to clients of MFIs. This is due to the value of loans to MFIs and the moratorium on lending during the first quarter of 2013 so that ZMWF would address the recommendations of the 2012 Annual Review; particularly the collateral and interest rate issues. Loans in excess of $1.5 million in total have been approved in 2013 under new collateral and interest rate structures; and it is possible that the number of loans to MFI clients will be close to the target by year end. / AIZ –is provided under an accountable grant arrangement and spending is somewhat behind target (£639,669) against a budget of £965,742. Spend to date has been complicated through the co-funding arrangement with Nduna (essentially, DFID funding to date has been spent on TA for the first round winners, and it is only for the second round that DFID funding is actually going into grants).Spend is expected to pick up in 2014 primarily through heavier TA and paying out of third round awards. / AECF –Disbursements to grantees are very significantly behind schedule. As a result of the mixed response to R3 of AECF-Z there is some doubt whether it is worth progressing with a fourth round of competition. / 2.2 Key cost drivers: / Project costs / All projects are impacted by the foreign currency risk where DFID contributions are denominated in pounds sterling, whereas most pass-through costs, comprising grants, prizes, loan instruments etc. are denominated in US$. This is causing projects to act with some caution in ensuring there is adequate management over the risk that the pound significantly deteriorates against the US$. / ZADT – Consulting costs are expensive in the Zimbabwean environment, but essential for the provision of TA/CB at smallholder producer, intermediary, and bank levels (where needed). This places an onus on ZAD/SNV to ensure it delivers high quality support. While we found evidence that this is the case among smallholder producers, the picture was very mixed at the intermediary level. / Costs of monitoring and evaluation are quite high, reflecting the need to collect nationwide information on use of funds and impact. / ZMWF – There has been concern that MFI interest rates to their clients are too high. Interest rates to borrowers can only decrease when significantly more funding is provided to the Apex (and a clear message is provided to MFIs to reduce interest rates) and/or DFID insists that the Apex make this a requirement for access. ZMWF has recently introduced a staggered interest rate policy under which MFIs are allowed to charge a maximum of 60% p.a. on the first loan cycle and 45% p.a. and 35% p.a. for the second and third cycles respectively. All loans issued in 2013 have clauses that limit the rate the MFI can charge on loans funded by ZMWF funding. However, this approach is financially feasible for MFIs only provided they keep their overheads down and do not invest. In the long run, MFIs can only reduce on-lending rates sustainably as they enhance their skill base and build scale. / ZMWF management costs are subject to Zimbabwean inflation and cost of living. The market for locally qualified consultants in specialised areas is not large, and occasionally international resources must be used. The cost of provision of TA is similar to that of management; and inevitable under the current conditions. / AIZ – Consulting costs absorb almost all of non-prize expenditure and can be expected to increase in the coming year as projects are implemented. It will be critical to ensure a clear linkage between the cost and quality of TA and the expected benefit of the TA. TechnoServe has a good model of using relatively low cost, but skilled, volunteers to provide TA. / AECF – Key cost drivers of the AECF-ZW are average project size and funds awarded per project, the percentage approval rate by the Independent Investment Committee and the length of time that each project is contracted and monitored. Another cost driver is the project scope “creep”, where additional burdens are placed by donors after implementation commenced. Extra funding has been provided to ensure more robust M&E through the introduction of the DCED monitoring approach. For grantees, cost drivers include the costs of doing business in Zimbabwe, and the associated risks and uncertainties in the environment. / 2.3 Is the project on-track against original timescale: / All projects are behind track on project expenditure, as detailed above.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Generally it is too early in most of the subprojects to determine changes in evidence. / ZADT – has started to gather evidence and report against the logframe indicators for each of its outputs; and it has commenced implementation of its M&E programme. Early findings appear to be encouraging, although these are drawn from a sample of projects. As the M&E programme completes its first assessments, and the first loans fully mature (enabling intermediary and smallholder benefits to be measured more accurately), a more comprehensive and reliable picture can be expected to emerge; enabling ZADT to assess its performance with greater clarity and certainty. / SNV has concluded a study on impact of improved access to credit on the agricultural value chains. The study sought to explore the usage and effectiveness of similar revolving credit facilities and suggest possible ways of improving the effectiveness of the CREATE Fund. ZADT reports that the findings of the study have been discussed by the Board during a strategic planning session and some recommendations are already being implemented, whilst new strategies have been crafted. / ZMWF– ZWMF has moved on substantially since the least review. At that time, $50000 had been disbursed and $1.360m has been disbursed since the start of the project. / AIZ–AIZ should be supported to expand its activities – both in terms of getting closer to the ideas generation part of the pipeline and also upscale implementation activities. Monitoring should include a clearer focus on attributable change. / AECF–The major change has been the embedding of the DCED monitoring process. This is an important initiative because, whilst not quite the panacea for monitoring, the rigors of the DCED process requires a careful elaboration, analysis and monitoring of the results chains. This would benefit the whole PPG. / 3.2 Where an evaluation is planned what progress has been made? / No overarching DFID evaluation of the PPG programme has been planned. / ZADT– A DANIDA review of the programme is scheduled for May 2014. / ZMWF– The Nathan Evaluation on ZMWF was completed at the beginning of the review period and is being reviewed by the ZMWF and its donors; however it is too early to say what changes will be made following the evaluation. / AIZ–An internal evaluation in January 2013 for the 2011 grant winners illustrates TechnoServe’s desire to understand and improve their on-going support for winning projects. / AECF–AECF has been subject to AusAid and DFID annual reviews since inception.

4. Risk
4.1 Output Risk Rating: / The overall risk continues to be rated as high because the risks of operating in Zimbabwe continue to be high. In light of this it is proposed that the PPG programme’s risk rating in DFID Zimbabwe’s Monitoring Strategy be reviewed and that the programme’s individual monitoring plan be adjusted appropriately. / 4.2 Assessment of the risk level
The original business case and 2012 review identified a large number of risks that that could threaten the successful delivery of the intervention along with the corresponding mitigating actions to minimise these risks. We have reviewed and updated these risks now that elections have been completed; and we have adjusted the probability and impact scores for a number of risks (generally upwards). We also recognise conditions can change rapidly in Zimbabwe and with little warning, thus further complicating any assessment of risk. / Based on this assessment, while all the risk identified can occur and will almost universally have significant impacts on the programme, we believe the key risks that PPG needs to guard against at the present time, are: / Political interference, / The new government economic policy framework, / Occupation of land/ projects on disputed land, / The weak law and order climate, / Quality of proposals for funding and or response of programme components (specially, AECF, ZADT and ZMWF), / Weak gender focus of PPG, and / Risk of seizure of bank accounts. / Findings and revised mitigation strategies are set out in appendix 2. / Table 1: Risk Matrix Summary – Changed assessment of risks shown in [square brackets] / IMPACT / H M L / PROBABILITY H 1, 3, [12] 11 / M [6] 5, 9 [13] / L 2, [4], 7, [8], 10 / Risk of funds not being used as intended / The risk that funds are not utilised as intended is low, given strong governance and adequate financial procedures in each project component and the high reputation of partners. There are some outstanding issues that need to be addressed. / ZADT– The risks are low, with professional services provided for all fiduciary processes, including at trustee, board and management levels. The CREATE fund is well protected against losses due to loan defaults because loans from banks to intermediaries are either collateralised, the risks are shared between the banks and the Fund and the Fund’s exposure is insured. / ZMWF–The risks are considered low, with professional services provided for all fiduciary processes, including at trustee, management and payment agent levels. / AIZ–AIZ has recognised that the main risk to funds not being used as intended relates to use of prize money by the grant recipient. The risk is mitigated by providing the money in instalments, separate project bank account, regular monitoring visits, and expert assessments of the systems and accuracy of financial and project reporting. / AECF–The implementing agent has introduced a monitoring system against four major criteria, project financial viability, development impact, AECF reputation and reporting from the grantee, to ensure that funds are used as intended. / 4.4 Climate and Environment Risk / ZADT - The project encourages loans where sustainable agricultural practices are used or introduced, including use of climate adapted seed and organic fertilizers against inorganic; and sustainable wood lots. It is likely that increased farming activity will result from lending activities, but farming activities are at historically low levels. A constraining factor will be access to water supply, which appears to be a constant issue for small holders wishing to expand; and, although ZADT is supporting intermediaries and smallholders who are focusing on water management, the Fund (and banks) will need to focus increasingly on water use and conservation; as well as sustainable land use and environmental management, as set out in the Fund’s Business Plan. / ZMWF - As an on-lender to the MFI sector, ZMWF is unlikely to know the impact on the environment of activities funded by the MFI. Given the size of loans made by the MFIs, individually they are likely to not have a significantly harmful impact, although in total they could, especially if loans are to purchase harmful products. ZMWF should reconsider this risk and assess against the policies of the MFIs it makes loans to. ZAMFI and GIZ recently conducted training on environmentally conscious microfinance. ZMWF could liaise with ZAMFI about developing a compact/MOU on standards among MFIs. / AIZ - Requests an impact assessment from all would-be grantees. Judges are mindful of these impacts in the selection of the winners. AIZ carries out environmental assessments as part of grant due diligence. / AECF - Recognise that agriculture can have an adverse impact on the environment but it is already impacted by climate change, which compromises low technology farming. Adaptation through new technologies and better management techniques is a positive outcome in this situation. AECF carries out due diligence on this issue before grant award.

5. Value for Money
5.1 Performance on VFM measures / Of the four projects, only the AECF has attempted analysis of VFM using the ICAI recommended 4 E’s approach. Because none of the sub-programme management contracts were awarded under a DFID-run competition, a VFM economy opportunity was foregone or the process left to others. The existence of other donors and in the case of ZADT and AECF significant donors closer to the projects, DFID’s influence on VFM discussions is more limited. The following, albeit with the above caveat – represent opportunities for VFM over and above those found by other VFM audits. / The review team have assessed each programme component using the DFID VFM Framework scoring methodology; and the markings are provided in the table below; together with comments on the scores for each component. At this stage of programme implementation it is not possible to undertake estimates of VFM at the “Effectiveness” and “Equity” level. / Table 3: VfM Scoring on scale of 1[poor] to 5[excellent] / Economy / (Unit costs) Economy / (Procurement) Efficiency TOTAL / ZADT 3 4 2 9/15 / ZMWF 4 3 2 9/15 / AIZ 3 4 4 11/15 / AECF 2 3 2 7/15 / ZADT - The ZADT intervention is broken down into 2 main channels – the Fund (managed to date by Sabi Consulting but now moving in-house to the Secretariat), and the provision of technical assistance and training to current and potential beneficiaries (managed by SNV). For donors wishing to contribute to the programme the split in contribution is a predetermined 80% CREATE Fund: 20% Technical Assistance (TA) and M&E.). From an efficiency perspective, while disbursements are now more satisfactory, loan terms and conditions and disbursement profiles do not fully match the needs of smallholder producers and intermediaries to enable them to maximise returns; the Trust is in the process of reorganising the previous top heavy management and governance structure, but this is yet to be completed (2). Fund management costs are included in the 11.5% overall interest charged to access funds, this rate is significantly below the market average which keeps unit costs low [4]. Procurement of bank partner services and TA appears to be satisfactory (3). / ZMWF – ZMWF follows Hivos procurement procedures which does ensure sound practices; however the skills that have to be purchased are rare in Zimbabwe or they have be sourced in the region or internationally. / It continues to be too early to make a full effectiveness, efficiency and economy assessment; however preliminary rating of 2 for efficiency and 3 for unit costs seem reasonable. HIVOS-based procurement processes are viewed as satisfactory, yielding a score of 4. / AIZ - From a VFM perspective overall overhead costs are relatively high (35% of budget), this drives the unit cost score of [3]. The cost of TA provision to beneficiaries is relatively low (at $270/day), and includes the subsidy provided through the use of volunteer consultants, efficiency score is a [4]. Procurement of a vehicle following a formal procurement process and coming in under budget drive the procurement score of [4]. / AECF - DFID supports the AECF at an Africa wide level, with funding for the programme coming centrally from DFID UK as well as various country offices providing funding to specific country windows. AECF has overall been rated as providing VFM from DFID’s perspective[6]. Reflecting the initially slow disbursement of funds via the AECF Zimbabwe window, results achieved to date have fallen short of key milestones indicating a moderately efficient delivery of services to beneficiaries [2]. Management fees are in the mid-range of the spectrum for a six year Fund (the combined KPMG IDA and AGRA management fee totals 20% of funds provided over the 6 years) this drives the unit costs score [2]. KPMG’s procurement cycle conforms to international procurement standards [3] / 5.2 Commercial Improvement and Value for Money / DFID is at a distance from the decision-making relating to procurement under the sub-programmes, resultant from its decision to fund existing initiatives. There is evidence that local procurement practices on the four sub-programmes are of an acceptable standard. / ZADT – The selection of participating banks was based on a competitive bidding process, although the selection of banks was hindered as a number are proscribed. SNV provides good quality processes around the selection of consultants and local capacity builders. SNV withholds a percentage of the contract based on the need to demonstrate the quality of the deliverables. However, unit costs should not be the sole VFM measure, especially of TA. / ZMWF – the purchase of goods and services is carried out through competition and there are procedures, including separation of duties in the procurement process, based on purchase limits set by the ZMFW board. / AIZ – grant prizes are paid in tranches based on meeting performance targets. AIZ uses relatively low cost, but high quality volunteers to supplement the core of paid advisers. / AECF –the grant control procedures ensures that funded projects stay on budget at a line item level, with approvals for variations made requiring justification. Changes above 20% require the approval of the investment committee. Checking of invoices includes assessment of grantee financial control and spot checks of accounting records and vouchers. / 5.3 Role of project partners / As lead donors, DANIDA should be requested to provide VFM audits of ZADT; and AusAid of AECF (Africa-wide). The findings of this annual review in relation to VFM will be discussed with donor partners. / 5.4 Does the project still represent Value for Money / The VFM assessment is based on observation and documentation provided during the course of the review; and should not be relied upon as definitive. Apart from AECF, who have provided a properly documented appraisal in the 3 E’s framework, the assessment of the other programme components have not been carried in accordance with DFID standards. / 5.5 If not, what action will you take? / We believe DFID should require a full VFM appraisal of the PPG both to assess the programme against its standards and to provide learning for future programming. The managers of all four programme components should receive guidance and training to enable them to provide a 3 E’s VFM appraisal of their projects and a plan to address VFM deficiencies.
[6] DFID Research and Evidence Division, January 2011

6. Conditionality
6.1 Update on specific conditions N/ A

7. Conclusions and actions
The actions are aimed at providing positive recommendations on all four programme components and for DFID. This is in two parts; the first being a commentary on the recommendations from the 2012 AR as set out in the Review team’s TORs (appendix 3); and the second being the recommendations arising from this review. / Overall, the review notes that a majority of the recommendations of the 2012 have been implemented or are in progress. We have included those recommendations held over from the 2012 review that are still relevant for each programme component in appendix 3. / Regarding 2013 recommendations: / ZADT should: / Complete the reorganisation of ZADT with the aim of having a Board of Trustees and Investment Committee, and Secretariat with strong competence in banking and financial services, agribusiness and agriculture at smallholder level. / Re-assess supply chains already analysed to ensure full understanding of the roles of smallholders and women play in order to develop financial and technical support products that meet these requirements; taking into account of the findings of the recent SBA study. / Continue to analyse needs of intermediaries and smallholders for TA; and empower a pool of qualified service providers to deliver this support, through a competitive, transparent bidding process. / Prepare for potential leverage of its funding to increase impact (greater efficiency/effectiveness) and potentially increase its appetite for risk, if and when bank liquidity and financial market conditions improve. Consideration should be given to starting to harmonise current subsidised rates with market rates and explore with banks the possibility of blending CREATE funds with those of the banks to make second and subsequent loans, so that ZADT is able over time to graduate its clients to its partner banks. / Conduct a study to determine how ZADT can use its leverage with banks and links with ZMWF to enable smallholders to directly access financial services. Supporting smallholder groups to form financial cooperatives and generate scale for banks to engage with; and making use of digital phone technology to reduce transaction costs, are possible options to consider. / As part of a strengthening the delivery focus of the M&E programme, implement independent reviews of the 109 companies that have received loans to: establish the number of smallholders linked to funded intermediaries; the extent to which this number has changed as a result of the funding; and measure the scale of benefits attributable to project funding. Use the findings of this review to either adjust the targets or revise the approach to reach the agreed results. / Develop a VFM plan / ZMWF should: / ZMWF to keep its revised collateral and interest rate policies under review and adjust these as market conditions change. In particular, the evidence shows that a properly functioning MF sector does not need interest rate restrictions; but should set interest rates based on assessments of risk and local market conditions. This allows the sector to grow; and naturally weeds out those MFIs that cannot effectively compete for business, / The Nathan Evaluation has provided a model and calculated the levels of funding for ZWMF to be sustainable, but this does not take into account the expansion needs of the sector if client outreach is to be scaled up. The model needs to be revised on this basis; and presented to donors (DFID +others) for funding. In doing so, ZMWF should revise its business strategy and balance its needs to protect its capital base, with those of MFIs to rebuild their businesses and asset base and MFI clients to undertake productive micro and small enterprises. / Using the current OSS framework of small MFIs does not address programme goals - scale at the MFI level is essential. ZMWF needs to develop a revised OSS model with its MFI partners based on an active client base of at least 20,000 active clients and offering a range of products at market based interest rates. / Any growth will be constrained by current skill levels; the wholesaler is an inappropriate vehicle for this purpose. The MFI sector, led by ZAMFI, should develop a strategy to rebuild the sector’s skills present this to the donors for funding, including the institutional vehicle, separate from but linked to ZMWF and ZAMFI, for delivery. / The process of revising the roles and responsibilities of ZMWF governance and management structures need to be completed so that they are clear and development as well as banking focused. / Finalise and operationalize the 2012 recommendation of an effective gender equity monitoring and evaluation strategy / The programme managers should provide a VFM Economy and Efficiency plan / AIZ should: / Proceed with its proposal to extend activities down to the ideas generation end of the pipeline / Improve the monitoring of project impacts to ensure that the incremental benefits are correctly attributable to AIZ interventions. / Develop clear proposals to scale-up the impact of the AIZ, which includes a much stronger emphasis on communicating the results of AIZ to the wider business community in Zimbabwe. / AECF should: / Review AECF-Z in the light of the response to R3 to assess the differences in modus operandi which are required to allow the Fund to achieve its objectives. This review should include issues relating to the role of the fund manager; technical capacities of the KPMG team; fees and likely outcomes. / Review the fund-management focus of KPMGs activities – so that these are driven by the needs of the Programme and projects rather than administrative process (such as the quarterly visits to all projects which may represent poor value for money). / Discuss the rationale for the proposed changes to the AECF-Z logframe with DFID. In particular, the likelihood of achieving even the revised figures (particularly the $75 incremental benefit per person) and the trade-off between the extent of benefit per person and the number of beneficiaries should be discussed and agreed with DFID. / Support the dissemination of more effective monitoring processes (largely based upon refinements of the DCED Standard) throughout the PPG programme. Support DFID by strengthening the quantification of economic contributions and ensure that the results reported to DFID reflect the 25% contribution to AECF-Z funding that is made by DFID. / Adopt an approach which has a much greater emphasis on scale up and replication, most obviously through exploiting the demonstration effect of supporting successful projects in Zimbabwe. / Keep a clear focus on the pro-poor and gender objectives of PPG and incorporate this ex-ante into the design of future AECF-Z windows. / DFID should intensify its current monitoring strategy in the project management of the PPG Programme. This should involve: / Taking a more active role in the practical implementation of the four different components to develop an informed view of the implementation of the Programme. DFID should continue to use the Programme quarterly meetings and regular individual meetings to assess implementation of recommendations for improvement and ensure they have a specific focus which will add value to the programme. / DFID should engage constructively with the ZADT and DANIDA and offer support, in the form of a review of the 109 current projects to guide the work of the new CEO; / DFID has significant leverage on the AECF and should actively engage in re-thinking the approach in Zimbabwe to ensure the Fund remains relevant to the context in which it operates. / Continue to visit projects funded by PPG outside of the Annual Review cycle to gain an appreciation for the project beyond the Review process and allow improvements to be proposed and implemented out with the yearly review cycle. / Ensuring ZADT, AIZ and ZMWF complete VfM assessments and implement VfM plans. / Ensuring all four programme components undertake gender audits and take steps to increase gender awareness within the management teams and funded projects. / Deciding whether to accept the changes in logframe proposed by the programme components, including establishing common understanding and measurement of economic opportunities across all four components. Consider the other changes to the logframe proposed by this Review. / Support the diffusion of ‘best practice’ from one part of the PPG Programme to another; / Support the programme components to work together more effectively, where this makes sense for the PPG Programme.

8. Review Process
The review was carried out over a 2 week period in-country and a further 2 weeks of analysis and report writing. The review team from Coffey International Development comprised: Jeremy Swainson, Team Leader; Jonathon Mitchell; Sharda Naidoo and Neddy Matshalaga, Independent Consultants; and David Mollatt, Economic Adviser; Sam Coope, Social Development Adviser; Angie Dhlakama, Programme Assistant; and Nyasha Mayanga, Programme Manager - DFID Zimbabwe. The work of the review included technical meetings with all sub-programme managers, and field visits in Harare, the Eastern Highlands and Bulawayo/ Matabeleland.