Type of Review: Annual Review

Project Title: Strategic Impact fund for the Occupied Palestinian Territories

Date started:	22/12/11	Date review undertaken: 27/11/13

What support is the UK providing?
The Strategic Impact Fund (SIF) aims to generate new evidence, new pilot studies and new ways of working to strengthen the quality of the OPTs programme. The UK will provide £1 million to finance at least 12 small projects over 4 years to achieve this aim.

What are the expected results?
The project will help DFID and its partners to deliver high quality programmes which will improve the lives of Palestinian people and contribute to a two state solution, as measured by year on year improvement in the Palestinian Programme portfolio quality score. This will be achieved through the generation and use of new evidence, new pilot studies and new ways of working, with at least 75% of interventions in these fields meeting or exceeding expectations in delivering strategic impact. The project will produce at least: / 6 high quality studies which strengthen the evidence base for DFID, Palestinian Authority and other partner projects, ensuring projects stay relevant and effective in a fast-moving political and economic environment, and leading to better value for money and reduced risks to project delivery / 3 pilot projects that assess and develop innovative approaches to project delivery and which are taken forward by DFID/other partners to increase the returns on investment / 3 influencing activities which bring together key development actors working to support Palestinians in order to improve harmonisation and coordination of development activity and leverage development outcomes beyond that which a single actor can deliver alone.

What is the context in which UK support is provided?
The context in which this support is provided is fragile with regular changes to the political and operating environment. For example: / In August 2013, direct negotiations restarted between Palestinians and Israelis for the first time in three years, brokered by US Secretary of State John Kerry. Secretary Kerry has announced that all ‘final-status’ issues – core issues central to a peace agreement - will be on the table: Jerusalem, borders, security arrangements, settlements and Palestinian refugees. As part of the process, Israel has agreed to release 104 long-serving Palestinian prisoners and the Palestinians are expected to refrain from upgrading their membership of UN agencies. / The economic and fiscal outlook of the OPTs as a whole has deteriorated substantially in the past 12 months. Economic growth in the West Bank and Gaza declined from an average of 11% in 2010-11 to 6% in 2012 and has fallen further in 2013 (3% in Quarter 1). Unemployment remains persistently high, especially youth unemployment which hovers at around 1/3 in the West Bank and ½ in Gaza. / The Palestinian Authority (PA) has very limited control over its income given the unpredictable nature of aid flows and the fact that tax revenues (around 2/3 of its total revenue) are transferred to the PA via Israel, which collects on the PA’s behalf. Both sources of finance are vulnerable to political leverage (for example in response to Hamas/Fatah reconciliation, and Palestinian action at the UN). / The situation in Gaza is particularly fragile and a future humanitarian crisis cannot be ruled out. Movement and access restrictions on Gaza are estimated to be depriving the Palestinian economy of nearly £1.3 billion a year and more than one third of Gaza’s workforce, including over half its youth, is unemployed. Recent actions by Egypt to close the smuggling tunnels across the border have made the situation even more precarious / Clearly DFID support needs to be ready to respond to these and other major changes. In order to maintain the ability to respond effectively to the changing political and humanitarian/developmental situation on the ground, and to continue to deliver development objectives effectively, the Strategic Impact Fund (SIF) supports targeted inventions aimed at addressing emerging risks, opportunities and issues within and across projects, which cannot be easily incorporated into our on-going projects or carried out by others. These interventions fall into three main areas: strengthening the evidence base for DFID and partner projects; supporting innovation; and improving DFID’s influencing ability with donors and the wider community.

Section A: Detailed Output Scoring

Output 1: Strengthened evidence base for DFID, Palestinian Authority and other partner's programmes and policies / Indicator: Number of high quality new studies disseminated within time frame agreed in proposal form / Milestone 2013: 4 / Delivered: 2
Output 1 score and performance description: / C Outputs substantially did not meet expectation
Progress against expected results: / Two studies have been implemented / ODI – research into links between economics and conflict in the Occupied Palestinian Territories (OPTs) / This project seeks to explore the links between the intensity of conflict (between 1987 and 2009) and various economic indicators. The outputs were to be three technical economic papers and three non-technical short policy briefings, along with the dissemination of key findings to Palestinian and Israeli policy makers, donors, NGOs and international academics. The project has faced a number of problems over the past year: / - Initial findings from the data analysis were unexpected. As a result, the team had to run extra analysis and checks to ensure the methodological integrity of the analysis. / - The team encountered difficulties in collecting Israeli trade and tariff data due to lack of cooperation from Israeli ministries. Alternative sources were found but this delayed the delivery of the second paper. / Nevertheless, three papers (on public sector jobs, trade and settlements) have been produced this year. The three non-technical briefs will be combined into one final policy brief summarising the entire research project. The latest revised work plan indicates that all outputs will be delivered within the overall timeframe of the project. The team has started to explore possible arrangements for the dissemination events and envisages that these could be held promptly after the production of the policy brief. / Occupied Palestinian Territories (OPT) Evaluation / This project is reviewing the DFID Palestinian team’s progress against the current Operational Plan in order to strengthen the evidence base to help inform the next Operational Plan. The first output for this project was to deliver a clear baseline situation report of the DFID Palestinian programme and present a detailed methodology including an evaluation matrix. A draft Stage One report was submitted to DFID on the 10th October 2013 for comments and the final report was delivered in December 2013 and was within the agreed timeline. This report formed the starting point for Stage two of the project and Stage 2 fieldwork commenced mid-January 2014. Project is currently on track to meet its next target. On completion results will be shared with the Palestinian Authority and will be made publically available to ensure it meets the full output requirement. / Issues: / Despite the data collections issues related to the ODI paper, the quality of studies delivered under this output has been high. The issue has been a shortage of proposed studies to deliver the output milestone. There have been several studies that would normally have been identified as priorities for the SIF that have been completed as part of the inceptions phases of other programmes. Examples include political economy analyses on accountability and private sector development have been undertaken as part of the Taajabwob and Palestinian Market Development programmes. / Recommendations: (To note these recommendations apply to all outputs) / Reduce the total amount of expected projects from 12 to 6 and revise the budget down to £500,000 to reflect this. / To ensure flexibility within the project the three current outputs should be incorporated into one main output with three indicators. / Ensure pillar engagement in SIF by incorporating SIF into Pillar operating plans with aim for each pillar to have one project in 2014. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: High quality innovative pilots conducted for scale up / Indicator: Number of innovative pilots conducted / Milestone 2013: 2 / Delivered: 1
Output 2 score and performance description: / C Outputs substantially did not meet expectation
Progress against expected results: / One innovative pilot project has been completed. / Deployment of emergency preparedness and response officer-UNRWA / Using SIF funding, UNRWA recruited a six-month Emergency Preparedness and Response (EPR) consultant to work with each field office to develop a risk register linked to emergency preparedness checklists which could be adapted to field-specific identified risks. This work had started at the time of the last Annual Review, but was completed this year. / Four risk assessment and risk profiling exercises were conducted and five risk registers with early warning capability were established for all UNRWA’s fields of operations. Four workshops were conducted with field offices to introduce methodology and tools and ensure UNRWA staff ownership of the process going forward. Four focal points in four field offices received training in emergency preparedness and response methodology and tools. Four training of trainers sessions were conducted for field staff and a Roadmap was developed to support and synchronize implementation of EPR plan with wider planning processes. Unfortunately simulation exercises could not be conducted with field offices due to travel constraints, mainly the rapid deterioration of the security situation in Syria. To compensate, area office level emergency preparedness and response training was given instead and over 50 staff from West Bank, Jordan, Lebanon and Syria attended. / The project was completed on time, within budget, and met all achievements in the log frame. The consultant has given UNRWA recommendations for scaling up the project and these are currently being reviewed. / It was disappointing that only one pilot project was completed within the year although this was in part due to lack of suitable proposals early in the project and steps were taken last year to try and address this. However this year has seen a significant increase in the amount of proposals being put forward. Nine have been submitted. Of these, three were rejected, one was deemed more suitable to another DFID project and five are currently being reviewed and there is an expectation that at least two of these will be implemented in the first quarter of 2014. / Issues: / A lesson learnt from the UNWRA project is that clear delivery mechanisms need to be identified (at least in principle) for successful pilots to be scaled up. DFID should ensure such pilots are part of ongoing dialogue discussions. / Again, quantity rather than quality has been an issue with this output. A limited number of feasible projects were received which impacted on the delivery of this output milestone. / Recommendations: / Reduce the total amount of expected projects from 12 to 6 and revise the budget down to £500,000 to reflect this. / To ensure flexibility within the project the three current outputs should be incorporated into one main output with three indicators. / Ensure pillar engagement in SIF by incorporating SIF into Pillar operating plans with aim for each pillar to have one project in 2014. / Raise awareness of the programme by advertising and discussing with stakeholders and partners / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthened influencing across donor and wider community / Indicator: Number of specific influencing activities which take place to bring together different actors / Milestone 2013: 2 / Delivered: 0
Output 3 score and performance description: / C Outputs substantially did not meet expectation
Progress against expected results: / Although no direct influencing activity took place, the SIF project showed that it had the potential to be a useful influencing instrument. / The work conducted by the deployment of the emergency preparedness and response officer brought together a number of different actors in a workshop setting, for example actors from the different UNRWA field offices, actors from National Authorities and other in country partnerships. Here the contractor was able to influence how other organisations think about how they can better coordinate emergency preparedness activities in UNRWA’s field of operations. / DFID, as Donor Co-Chair of the Security Sector Working Group, has been encouraging progress on good governance in this sector. This has involved influencing other donors to appreciate the importance of addressing governance weakness and working with the Palestinian Ministry of Interior to understand how it might strengthen management and civilian oversight of the security sector. This resulted in UNOPS submitting a SIF proposal on this issue and this is currently being explored. / Issues: / Quantity has been an issue with this output, although it has shown that SIF can be a potential influencing instrument. / Recommendations: / Reduce the total amount of expected projects from 12 to 6 and revise the budget down to £500,000 to reflect this. / To ensure flexibility within the project the three current outputs should be incorporated into one main output with three indicators. / Ensure pillar engagement in SIF by incorporating SIF into Pillar operating plans with aim for each pillar to have one project in 2014. / Closely integrate SIF with the new DFID Jerusalem Influencing Framework to ensure the most joined up approach / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / The log frame was changed to reflect a recommendation in the 2012 Annual Review. / The target for Output 2- Number of innovative pilots conducted, was reduced from 4 to 3 over the life of the programme, therefore the 2013 milestone was changed to 2. It was believed that four studies were over ambitious for this period and that it would allow for any delays or projects that had not been taken forward / 1.2 Overall Output Score and Description: / C– Outputs substantially did not meet expectation / 1.3 Direct feedback from beneficiaries / The overall message from project partners is positive. In general they have found DFID and SIF relatively easy to work with. However there could be more flexibility from DFID when unforeseen problems occur and feedback on technical papers needs to be provided in a timelier manner. / Some specific examples are provided below: / “DFID was a very easy and nimble interlocutor… Funding was availed quickly, DFID was supportive and accessible, but did not micromanage, and reporting and feedback requirements were very reasonable.” UNRWA / “The application was a smooth and effective process. We were able to get a common understanding with DFID on the objectives of the research project and in fact the project idea grew out of consultations with the DFID office in Jerusalem. The key was to have a very responsive and committed economic adviser. The key to the success of any such project is also an open and effective communication throughout the project cycle to deal with new issues as they emerge. This communication worked great until the economic adviser left his post.” ODI / We have intentionally included the feedback from ODI as they can also be classed as beneficiaries of the reports as they have an interest in the results.
1.4 Summary of overall progress / Overall Output Score : C / The project is producing useful research which is improving the evidence base in the OPTs. It has also demonstrated that discussion related to the application for funds can be used to influence and work with other donors and agencies to improve the lives of the Palestinian people. Some work has been delayed due to unforeseen difficulties (such as access to data). Other pressures have included the dramatic change in the political landscape over the past year: the resumption of direct Israeli-Palestinian negotiations has made some work very much more sensitive and has increased the demands on the time of key DFID staff members. It is essential that SIF is flexible enough to respond to such pressures. / The number of proposals coming forward has increased significantly this year from 2 to 9. We expect to see a couple of these come online in the early part of 2014. The major challenge to delivery of output milestones has been the number of quality proposals for consideration. We have been rigorous in our appraisal of projects to ensure quality. SIF will only ever be as good as the proposals that are received; it is important that action is taken to encourage even more proposals in the year ahead.
1.5 Key challenges / The political landscape over the following year may continue to change and increase the demand on the time of key DFID staff and further staffing changes over the next quarter could also have an impact on SIF as it requires Pillar and Technical Leads to play an active role in both promoting the fund and giving technical inputs. / Pillar leads have also commented that they believe SIF does not form part of their own Pillar Strategy and see it more as an add on, therefore SIF work tends to fall down their list of priorities at times of intense work pressure. SIF has to date not been well integrated into the core pillar strategies and the recent identification of influencing priorities. As a result, we have missed the opportunity to think more strategically and encourage proposals that will build the evidence base for future programmes or answer questions in a rapid and responsive manner. Pillar leads are now working more closely with the project officer to help source ideas and translate them into projects. / Most of the interventions being proposed to the SIF are brought about by Pillar Leads. Given the demand on their time, some consideration must also be given on how the SIF Fund can be advertised amongst the donor community to ensure update and should be more closely integrated with the new DFID Jerusalem Influencing Framework. / Another challenge is to ensure beneficiaries are aware of the good work being done under the SIF, this could perhaps be done by more target marketing or publishing work on the gov.uk website and ensuring dissemination of findings are done in a timely manner and to appropriate audiences. / To ensure high quality scale up of pilot projects, we also need to ensure that mechanisms to enable scale up of the pilots are clearly articulated and realistic before project commences.
1.6 Annual Outcome Assessment / The Outcome calculation for 2013 is 100%, giving the project an Outcome Score of A. / Although the amount of projects being implemented has been disappointing and resulting in the project getting an Overall Output Score of C, the quality of the projects implemented have been good therefore giving an outcome calculation of 100% and an Outcome Score of A. / SIF has continued to generate new evidence this year. Two new studies have been produced. It was disappointing that there was no new innovative pilot project although this was in part due to lack of suitable proposals early in the project and steps were taken last year to try and address this. However this year has seen a significant increase in the number of proposals being put forward. Nine have been submitted. Of those submitted three were rejected, one was deemed more suitable to another DFID project and five are currently being reviewed, there is the expectation that at least two of these will be implemented in Q1 of 2014. The fund has also proved to be a useful forum for influencing work across the donor and wider community and steps should be taken to closely integrate SIF with the new DFID Jerusalem Influencing Framework.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / No. / £ Thousand / Original Budget Committed Spend to date Balance / UNRWA 56 56 0 / 2012 56 56 / ODI 100 91 9 / 2012 50 50 / 2013 50 41 9 / GDSI 100 39 61 / 2013 100 39 61 / Total 256 186 70 / Total SIF budget 1000 / 2011 140 0 0 140 / 2012 286 106 106 180 / 2013 286 150 80 136 / 2014 288 0 288 / Unallocated 744 / To date only 3 proposals have been implemented which has meant that the project is off track against original budget forecasts, expenditure did not take place until 2012 and poor take up in the early stages of the project has meant only £256k has been committed to date, leaving an unallocated budget of £744k. / It is realistic to expect that another three proposals will be implemented before the end of the project bringing the total amount of proposals implemented under the SIF to 6, half the original target on the logframe, therefore it is recommended that the overall budget be reduced to £500,000 to reflect this expectation. / 2.2 Key cost drivers / The key cost drivers of SIF are consultancy rates and admin costs. Proposals are required to demonstrate how these cost drivers compare to the market. / 2.3 Is the project on-track against original timescale: N / No, the project is off track against the original timescale. It became live in December 2011 but the actual funding of submission took place August 2012. This and the lack of initial proposals have meant it is off track. In 2013/14 there has been an increase in the number of proposals being put forward although these have been slow in coming to fruition and the concern is that this pattern may continue into the next financial year. Recommendations have been made in this annual review to address these concerns.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no new evidence currently available which challenges the project design or rational. If anything the project continues to improve the availability of evidence in OPTs at a time of great uncertainty. / Moreover, as the DFID OPTs team prepares to undertake its Country Poverty Reduction Diagnostic and refresh its operational plan, this programme could be more useful in terms of piloting new approaches and building an evidence base for future areas of support. / 3.2 Where an evaluation is planned what progress has been made? / There is good existing evidence that additional research and evidence can help to improve the quality of programmes. It is judged that this Annual Review is sufficient at this present time and an Evaluation will take place at the end of the project.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium / 4.2 Assessment of the risk level / Progress on this project has been slow due to lack of initial ideas. This year has seen an increase in the amount of proposals being put forward and although not all have been implemented through the SIF some have been taken forward through other DFID projects, for example the political economy analyses on accountability and private sector development have been undertaken as part of the Taajabwob and Palestinian Market Development programmes, or have been rejected as similar work was being done elsewhere. Going forward the SIF will still be reliant on Pillar Leads to promote and utilise the fund and should be introduced as part of their current objectives to ensure milestones can be met and that fresh ideas will continue to be harnessed. / A degree of risk will always exist with this programme as it is intended to build evidence for other work and pilot new approaches in a small scale but scalable manner. This is one of the more manageable ways in which the OPTs team can take the risks needed to deliver in a fragile environment.
Risk of funds not being used as intended / Very low, since all spending is made against invoices provided by a reputable organisations and partners. / 4.4 Climate and Environment Risk / The rapid design and implementation of potential SIF funded projects presents a risk that climate/environment screening can be overlooked or inadequate within the time available. It is important to ensure that within overall SIF management arrangements that adequate resources (financial and human) are built in to undertake rapid climate/environmental screening and monitoring of interventions. / As far as is possible, priority is given to recruiting nationals or consultants based in the region/country so that air travel and associated carbon emissions can be minimised. / These risks have not changed from the original business case so it has been judged that there is no positive or negative impact.

5. Value for Money
5.1 Performance on VfM measures / SIF provides an opportunity to improve value for money by: developing innovative approaches to maximise project outcomes relative to costs; providing evidence to ensure our projects remain appropriate and effective in a changing environment; leveraging input from others to deliver greater impact and reducing duplication. / 5.2 Commercial Improvement and Value for Money / Since SIF provides various implementing organisations with the opportunity to propose and implement projects, each organisation can implement the project according to its procurement procedures as long as they are consistent with DFID VFM. Some partners like UNRWA agreed with DFID that they would pay the expenses of the project until it finished, and DFID after receiving the narrative and financial report supported with all the documents, paid them on accrual basis. / The main cost driver is consultant fees. We have endeavoured to ensure proposers use local consultants in order to keep costs low. For example one of the proposals currently under review and expected to be implemented in early 2014 have reduced their budget by engaging more local consultants rather than using international. The consultants employed to carry out the OPT Evaluation were selected through the Global Framework Agreement to ensure they could demonstrate their capacity to deliver high quality evaluations at competitive rates and VFM and some of the consultants working on this project are local. / The daily rate under the ODI intervention is below the market rate and was negotiated by DFID Jerusalem. To ensure further economies of scale it was also decided to contract the three research papers at the same time. Additional analyses and data collection has required a project extension but this has been kept within the existing cost envelope. / 5.3 Role of project partners / UNRWA-Deployment of Emergency Preparedness Officer: / The project was cash in kind support to hire an external consultant. Cost efficiencies were gained by placing the incumbent in Jerusalem under the direct supervision of the HQ Emergency Officer, with direct access to the West Bank field Office. UNRWA covered the cost of travel to and from Gaza and Jordan although the majority of communication was done through email, video and telephone therefore reducing costs. / ODI - Research into links between economics and conflict in the OPTs / The researchers’ daily rate is slightly below the market rate (given the researchers’ expertise and competence) because the research is of particular interest to them. In addition, ODI’s administrative fee has been reduced from the usual 20% to 10% and applies only to the cost of the researchers. This compares favourably to the industry’s practice for such research projects. ODI brings to the table great experience in managing relatively complex contracts involving multiple transactions, and their editorial and online communications services which may be important to enhance the outreach of the research’s findings. / The cost per paper has been kept as low as possible. Firstly, there have been low data collection costs due to the team’s extensive knowledge of data in the OPT context as well as good access to the data sources. And secondly, there have been economies of scale from the three research projects being produced together; data collection is done more efficiently together for all data sources by the same research assistant; the international advisor can contribute more effectively since the research pieces are interrelated; and the research findings can be disseminated together as one package. / GDSI – OPT Evaluation / The supplier contracted to carry out the evaluation was contracted through a mini competition under the Global Evaluation Framework Agreement (GEFA). Under GEFA there are 27 pre-qualified service providers who have demonstrated their capability to deliver high quality evaluations at competitive rates and VFM. The supplier will use local contractors to help carry out the work and will revise their work plan at the two stages to ensure minimum travel costs and expenses. / 5.4 Does the project still represent Value for Money : Y / Yes. It is providing evidence to ensure our projects remain appropriate and effective in a changing environment; it also delivers value for money as it reduces the need for separate project management, implantation and monitoring arrangements and has the capacity to leverage input from others to delivery greater impact. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not Applicable

7. Conclusions and actions
SIF is not yet delivering to its full potential. This year has seen an increase in project applications and a number of useful pieces of work coming online. However, the success of the programme depends on staff sourcing high quality and strategic applications and supporting the projects throughout their lifetime. It also depends on greater up take from other donors and agencies. / Despite this, we have seen three distinct pieces of work – research into links between economic indicators and conflict, emergency awareness preparedness, and an evaluation of the OPTs programme. This work will help to boost the evidence base for DFID and other donors. Delivering it through SIF has been cost-effective and efficient and has added an element of flexibility to the OPTs programme. To get the most out of this programme in the next year, the following recommendations should be taken on board and be incorporated into a Project Improvement Plan which should be monitored on a regular basis throughout the next review period; / Reduce the total amount of expected projects from 12 to 6 and revise the budget down to £500,000 to reflect this. / To ensure flexibility within the project the three current outputs should be incorporated into one main output with three indicators. / Ensure pillar engagement in SIF by incorporating SIF into Pillar operating plans with aim for each pillar to have one project in 2014. / Raise awareness of the programme by advertising and discussing with stakeholders and partners

8. Review Process
Review submitted by: Gillian Mitchell (SIF 4 project officer) / Date: 29/01/14 / Information sources: / Direct feedback from partners / Direct feedback from DFID Staff involved in the interventions / Business Case and Log frames for the 3 implemented interventions / Proposals and decisions for rejected interventions / Proposals for interventions being currently reviewed