Type of Review: Annual Review

Project Title: Support to Government of India for National Secondary Education Programme (Rashtriya Madhyamik Shiksha Abhiyaan)

Date started: November 2012 Date review undertaken: November 2013

## Introduction and Context
What support is the UK providing?
DFID is supporting the Government of India’s (GoI’s) flagship Secondary Education programme, Rashtriya Madhyamik Shiksha Abhiyan (RSMA). RMSA seeks to expand access and improve the quality of provision across India. / DFID is providing £ 80 million to GoI (2012/13 and 2015/16); £60 million in grant aid and £20 million in technical co-operation. Grant funds are pooled with the World Bank which is providing approximately £300 million as a concessional loan. Pooled funds pay for school buildings, teacher salaries; teacher training; science equipment; school improvement grants. / DFID is the sole provider of technical assistance to RMSA. Support is being delivered through the Technical Cooperation Agency (TCA). Technical support is focused on accelerating the implementation and effectiveness of RMSA. Key areas of support are: learning measurement, management information systems, planning and budgeting, teacher management and school improvement.

What are the expected results?
The expected impact of the project is improved better educated and employable youth. / The expected outcome is more girls and boys benefit from good quality education (regardless of social background). / DFID financial assistance of £60 million is estimated at 6.1% of the total incremental cost of the program. (Total incremental cost includes the financial assistance from the World Bank). On this basis the results attributed to DFID are calculated as: / 0.61 million additional students enrolled in secondary schools of which 0.47 million completers / 650 new schools set up and 7000 additional classrooms. / 6000 teacher recruited and 70,000 additional teacher training days delivered. / National Secondary Learning Assessment System established / Enhanced and amalgamated Management Information System in place (Unified District Information System for Education - UDISE).
What is the context in which UK support is provided?
Technical Context / In 2013, DFID graduated from 23 years support to basic education. For the last ten years DFID has been a partner in GoI’s Sarva Shiksha Abhiyan (SSA) national basic education programme. This has put India on track to achieve MDG 2 and 3. Mass primary provision in India has meant the greatest returns to education are increasingly derived from secondary graduation - raising demand for secondary schooling. Unfortunately, state secondary education in India is a bottleneck rather than a bridge to higher studies or the workplace. Mass secondary education is under invested and of poor quality. / Secondary education, particularly for girls is a critical intervention with potential for big multiplier effects and inter-generational dividends (DFID 2011). It is where a number of important development benefits accrue including: poverty reduction (Aslam, et al 2010; Rose & Dyer 2008) health and reproductive choice (Dreze & Murthi 2001) and environmental sustainability (World Bank 2010; Bangay & Bloom 2010). There is real concern that without a secondary education that expands life chances, challenges gender and caste discrimination and equips future generations for sustainable development India’s much vaunted demographic dividend will not materialise. / Enrolment data provided by MHRD (Ministry of Human Resource Development) at the second JRM present an encouraging picture (Figure 1). However, some caution must be taken in using this data as it is a composite figure incorporating higher secondary education and is a comparison across two data sources. / Figure 1: Enrolment Trends in Secondary Education / RMSA is DFID India’s largest education intervention within a complementary education portfolio which seeks to address impediments to access and learning from both the demand and supply side (ii) support teachers and schools to be agents of change (iii) strengthen system efficiency through capacity building (iv) build evidence on learning outcomes and through research to inform reform. / While secondary education currently has less political profile than primary and higher education – GoI has increased the RMSA budget year on year since inception i.e., 2009-10. Over the last year (the first of DP support) GoI financing has grown by more than 10%. However, with the slowdown in economic growth and the need to find additional resources to finance the food security act may slow the pace of financing. It is also important to note that government aided schools are now eligible for certain types of support under RMSA, such as teacher training. This is a positive policy outcome, however the implications of this expanded coverage in terms of financing will need to be adjusted in the next budget cycle. / DPs monitoring of RMSA is done through joint review missions (JRM) held twice a year. A field based visit in January and a desk review in July / August.Securing accurate data on education in a country as large and diverse as India has always been challenging. This year the National University of Education, Planning and Administration (NUEPA), the guardians of education data amalgamated the primary and secondary data management systems to form the Unified District Information on Schools and Education (UDISE).This is a welcome development, though inevitably has caused some disruption. While all States have engaged with the process significant anomalies are evident in the quality of data emerging from UDISE. / Implementation Context / As with its predecessor, SSA - RMSA is a complex flagship programme dealing with both Centre and State process, the programme management is gradually bedding in. The aide memoire for the first Joint Review Mission (JRM) of January 2013 identifies the twin issues processing of financial flows from the centre and provision of evidence of expenditure/utilisation from the state as productive areas for improvement. The second RMSA JRM notes the good progress and particularly the ‘positivism and progressiveness’ shown by MHRD in addressing recommendations from the first JRM and more widely in moving the programme forward. The constructive nature of the DP – MHRD relationship is particularly important to note and augers well for the future. / DFID Technical Cooperation Fund (TCA) is being led by a consortium headed by Cambridge Education with regional staff provided by IPE Global. The Central office of the TCA is based in the National Centre for Education Research and Training (NCERT), Delhi. State based engagement is organized from five regional hubs in Bhopal, Mysore, Bhubneshwar, Shillong and Patna. The TCA has been provided space in Regional Institutes of Education, NCERT’s outreach institutions and within the National Open School in Patna. he TCA completed its inception period in September 2013. This contains a detailed theory of change, logframe and workplan. Strong collaboration has led to a demand driven work programme which was passed by GoI steering committee. The TCA has a mandate and is fully operational. The TCA has already delivered some important outputs including: two need assessment reports (i) teacher management and (ii) planning and budgeting as well as a review of ICT issues with education management systems. The TCA has also managed to bring all the key state and central apex bodies together to develop implementation plans based on partnership. Overall the TCA has created a firm platform to influence and accelerate RMSA implementation.

## Section A : Detailed Output scoring

Output 1: Strengthening planning and management to better deliver quality secondary education
Output 1 score and performance description: ‘A’+ (moderately exceeded expectations) / The implementation arrangements for delivering and monitoring the RMSA programme are in place. These include: adoption and use of Financial Management and Procurement Manual (FMPM); the use of e-procurement and constitution of School Management Development Committees. The TCA is also supporting MHRD in streamlining the process for appraising annual workplans and budgets. / The two Joint Review Missions (JRMs) held thus far have focused on administrative processes. It is encouraging to note that action has been taken on a number of important recommendations. The second JRM specifically noted that the manuals and guidelines developed to govern operationalization of the programme are being used. It also complimented positive action on previous JRM recommendations including: MHRD providing states with indicative budget allocations to states (including state share); an increase in the monitoring and management, evaluation and research (MMER) allocation from two to four percent - enabling recruitment of staff and monitoring institutions to strengthen financial management and transparency. / The technical cooperation agency (TCA) funded by DFID is the primary provider of technical support to the whole RMSA programme. The TCA has a mandate to work in five priority areas which support output one: Learning Assessment, Teacher management, School performance management, Data management and use, Results focused planning. The detailed workplan on this mandate has been approved by the first project steering committee meeting of the TCA held in September 2013. / Progress against expected results: / National Achievement Survey for grade 10 conducted: 2012/13 is on track. The sample survey is underway. Results are due for release by June 2015. The TCA has produced a report on the state of preparedness of NCERT on undertaking this task around which capacity building support is being mobilised. / Teacher Attendance rate: Baseline not established. MHRD has moved away from systematically tracking this issue on the basis that teacher employment is a state based issue. Experience suggests the most reliable measurement of teacher attendance comes from unannounced visit surveys. These are periodically done by bodies such as the World Bank. While DFID should continue to monitor teacher attendance – the lack of annual data in this area would suggest this indicator should be replaced with a metric better suited to annual review. / Proportion of RMSA of government and aided teachers receiving in-service training. Proportional As figure two indicates there is room for improvement on in-service education delivery. Provisional UDISE data for 2012/13 suggests that 75% of teachers are suitably qualified to teach at secondary level. 11% of teachers have no professional qualification. However head teacher training, critical for school improvement is progressing at a faster pace. It is also encouraging that government aided schools have now been incorporated into RMSA and are now eligible to engage in RMSA funded training programmes. Overall support to teacher education is also being provided through the TESS I programme. TESS I reports strong demand for its school leadership modules. / Fig 2: Status of Teacher Education Support 2009 -2013 / Source: MHRD presentation to 2nd JRM / Proportion of schools with School Management Committees (SMC) formed: No baseline established: Noting the importance of community involvement in school management MHRD have made formation of school management committees a pre-requisite for receiving RMSA funding. This is a positive step. As a consequence all RMSA schools have a SMC. However, the second JRM noted variation schools with constitutionally effective SMCs. Given the importance of the SMCs the Mission recommended that this issue is examined in detail. This issue is to be picked up in the third JRM. In light of these changes this indicator should be replaced in a revision of the RMSA logframe. / Recommendations / DPs secure agreement from MHRD on a mutually acceptable results framework document(RFD) at the earliest / DFID TCA supports strengthening of the new national assessment structures – in particular improved communication and support for data use. / DFID recalibrate and align its logframe to a combination of the agreed RFD and the indicators contained within the TCA logframe. / Impact Weighting (%): 40% / Revised since last Annual Review? No / Risk: Low

Output 2: Schools are given the resources to needed to deliver quality education
Output 2 score and performance description: ‘B’ (moderately did not meet expectation) / Progress against expected results / 2.1 Number of grade 9 & 10 teachers disaggregated by gender. Baseline 1.3 million (SEMIS) – no milestones established. UDISE indicates that as of 2010 there were 831,000 male and 487,000 female secondary teachers. Figures indicate a slight increase. It is likely that the secondary teacher provision is better than these figures indicate. This is because UDISE numbers are likely to be under representative as the expansion of RMSA schools has been largely achieved by expanding elementary schools. Teachers who teach in these upgraded schools who teacher across grades are commonly recorded as primary school teachers and thus the expansion in teacher time/ numbers available at secondary level is likely to be underestimated. / Provisional UDISE data indicates as of 31st March 2013, 45% of the target for recruitment of new teachers has been met. As figure 3 indicates there are major differences in teacher recruitment by state. Current data disaggregated by gender has not been issued in the RFD submitted to the JRM. / Figure 3: Teacher Recruitment against Annual Work Plan and Budget Submissions / Source: MHRD presentation to 2nd JRM / It is clear from state visits, the two JRMs and the activities of the RMSA’s sister programme the national teacher mission that major efforts are being made to employ new teachers – commonly teacher costs constitute the largest budget request component within the AWPB plans. Recruitment of teachers is however complex and political involving both levels of compliance against the national sixth pay commission and requirements around filling employment quotas against various societal categories – scheduled caste, scheduled tribe etc. / From information available it can be concluded that the overall numbers of teachers are improving at the expected rate. However, this needs to be seen in the context of a rising number of schools and students and significant challenges in raising overall competency and morale levels amongst teachers. In this respect the DFID funded TCA is working on key areas of teacher management including guidance on contracting, sustainable financing and rationalisation of teacher deployment. The issue of sufficient numbers of suitably qualified, competent and motivated teachers is central to overall RMSA success. It should also be noted that while RMSA will be influential the scope for action in many of these areas lie outside the immediate remit of the programme. / 2.2 Proportion of schools with a complete set of infrastructure components: Baseline - pucca classroom 22%, library 53% Integrated science lab 21%, computer lab 22%. The Results Framework Document (RFD) issued by MHRD indicates that the proportion of schools with all ten infrastructural components has moved from 1.8% in 2010 to 2.0% in 2011/12. This is a modest improvement and still leaves a large majority of schools without a full complement of specified inputs. Judging from the projected logframe milestones established by MHRD, acceleration of civil works is required to meet the targets. It is clear from field visits and data provided at the JRM that there has been a strong push in the provision in educational infrastructure (see figure four). This is particularly evident in the increase in additional classrooms – the most common practice to facilitate expanding elementary schools to junior secondary schools. On a national level school build is keeping pace with student growth – however the situation is localised and varies both between and within states. / Norms and standards for civil works have been prescribed and detailed guidelines developed. While civil works does score well, concern was raised in the JRM on the quality of completion and that rooms designated as computer, science labs did not have adequate electric points or drainage facilities to function as such. State governments were also vocal in that the CPWD Schedule of Rates used by RMSA as costing norms were not sufficiently flexible to reflect the differing levels of building cost across India’s diverse terrain. Encouragingly, MHRD have accepted this point and from next year will accept civil works costing based on state norms. The DFID funded technical support unit has been commissioned to do a comprehensive review of civil works practices. / 2.3 Proportion of students with adequate numbers of toilets (by gender): Data on toilets has been removed from the new RFD. Data on urinals is provided and is shown to have dropped from 82.5% to 33.2% - it is not clear if urinals should read as toilets – nor the reason why such a dramatic fall in provision is recorded. / Figure four shows data submitted by MHRD detailing completion of civil works against sanctioned activity. This was explained at the JRM as the time taken for state governments submit utilisation certificates to denote completion and a recent hold on civil works to enable processing of the backlog in work. / Figure 4 : Overall Progress against Approvals 31.3.2013 / Source: MHRD presentation to 2nd JRM / 2.4 Proportion of RMSA schools with full allocations of qualified subject teachers: Base line 20%. The percentage of schools with a full complement of qualified teachers is shown to have increased to 34% in 2010 to 34.2% in 2012. This is a moderate increase. At secondary level performance is not simply a function of overall numbers of teachers but also access to subject specialism. This is still an area of concern. Major subject specific shortages were reported - science (12% of required teacher strength), maths (12%) and English (19%). It is not unusual to have within any one area both over supply and shortage of subject teachers by school; typically with urban schools being overly endowed and rural ones suffering shortage. The issue of teacher rationalisation and deployment as an aspect of overall workforce management is critical. DFID’s TCA is providing support in this area. / Recommendations / DPs secure agreement from MHRD on a mutally acceptable RFD at the earliest / DFID TCA supports strengthening of the new UDISE / DFID TCA complete the sanctioned review of civil works process (JRM 1) / DFID recalibrate and align its logframe to the agreed RFD and TCA logframe / DP’s promote per teacher norms for RMSA allocation to teacher costs. / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk: Medium

Output 3: Children regardless of background regularly attend and complete secondary education
Output 3 score and performance description: B (moderately did not meet expectation) / Progress against expected results / 3.1 Elementary to Secondary transition rate: Baseline 83% milestone 89%. Figures provided by MHRD indicate that the transition rate has moved from 91.3 % to 101.7% in 2010/11. Data indicates that this milestone has been achieved – the trend is clearly positive and supported by data and observation. However, some caution is needed with figures provided. A reported figure of 101.7% is a statistical anomaly as it suggests that there are more children in grade IX than were enrolled in grade VIII the previous year. Normally it would be expected that the figure would be less than 100% since not all children transit to secondary education (and indeed some who start grade VIII will not complete it). Possible explanations could be that there are children who were not counted in the grade VIII figures as they were in schools not included in the DISE dataset (such as private unaided schools) but then attended a secondary school which was in the SEMIS dataset or that there are a large number of repeaters in grade IX. / 3.2 Gross completion rate at secondary: Baseline 58% in 2013. This has been removed from the RFD issued by MHRD. The DPs have officially requested that this be re-instated in line with the RFD agreed in the WB Project Appraisal docoument / loan agreement. / 3.3 Share of Scheduled tribe and Scheduled Class completers: Baseline Schedule caste 16.8% and Scheduled Tribe 6.03%. Expected milestone 17.8% and SC and 7% ST. While data on ST and SC total enrolments has been included, data on completers has been omitted from the MHRD RFD. For both SC and ST enrolments the proportions remain static at around 8%. Access to secondary education for minority groups particularly students of the scheduled tribes and Muslim faith children remain a major concern. / Recommendations: / DPs secure agreement from MHRD on a mutually acceptable RFD at the earliest. / DFID recalibrate and align its logframe to the agreed RFD and TCA logframe. / The revised DFID logframe includes an indicator on children with special needs (cwsn) in line with DFID HQ efforts to focus and capture progress on cwsn. / Impact Weighting (%): 30% / Revised since last Annual Review? This is the first Annual Review / Risk: Medium

Section B : Results and Value For Money
1. Progress and results
1.1 Has the log frame been updated since last review? / No: This is the first year of DFID support – the review is against the original logframe. There is a need to revise the logframe to: align to the new RFD (when agreed) and to better capture the impact of DFID TC support. / Monitoring progress on RMSA is particularly challenging given: (i) the initial PAD documentation including baselines for the programme was based on the then most available data from SEMIS 2008; (ii) the ‘teething problems’ resultant from the recent consolidation of primary and secondary education data bases into UDISE; (ii) the unilateral revision by MHRD / NUEPA of the original RMSA Results Framework Document (RFD). MHRD and DPs are currently in discussions on how to resolve this issue. It is important to emphasise that the creation of UDISE – and its conducting of an annual school based census will considerably strengthen the capacity of GoI and DPs alike to robustly monitor progress. It should also be noted that DFID technical support is playing an important role in building capacity in this crucial area. / 1.2 Overall Output Score and Description: ‘A’ / Overall Output Score / Output achievement under RMSA is moderate in meeting expectations on most fronts. The TCA has made an impressive start – building strong relationships of trust at both centre and state. This has been evidence by a number of direct requests for assistance to support important undertakings such as MHRDs ICT in education conference. / The second JRM made particular note of the constructive leadership being provided by the joint secretary and directors of RMSA. In combination this augers well for the future. However, challenges with data collection make it impossible to provide accurate progress against the original logframe. Secondary data analysis and field observation does provide evidence of increased of progress on intended goals – enrolment, equity, and efficiency – though meaningful learning remains a longer term challenge. Establishing a robust programme of periodic and diagnostic learning assessment will be crucial to meeting this challenge. / 1.3 Direct feedback from beneficiaries / Beneficiary feedback was obtained through JRM, engagement with central, state, district and school level government officials involved in the implementation of the RMSA programme. The TCA support directly provided through DFID has been widely praised by MHRD, the World Bank and the institutions with which it works NUEPA and NCERT.
1.4 Summary of overall progress / Given DP engagement in RMSA is in its first year, overall progress within RMSA is satisfactory and in many ways compares favourably with DFIDs experience with SSA at the same juncture. Transition rates have increased from elementary to secondary. The government is committed to closing the gaps between social groups, particularly for girls. Most importantly the government is strongly supportive of efforts to address learning outcome issues in line with broader 12th plan commitments. / The RMSA budget has increased year-on-year since inception in 2009 – with allocation for 2013-14 being some 25% higher than the previous. The graph (Figure 5) below presents the budget estimates of the central share of funds over the years of programme implementation to date. / Despite encouraging progress considerable challenges remain both in retaining children in school and delivering demonstrable improvements in children's learning levels. These are long term, systemic challenges that require prolonged and sustained effort. / Budgeted expenditure (BE); revised estimates (RE); actual expenditure (AE)
Figure 5: Budget Allocations under RMSA, 2009-10 to 2013-14 / Source: MHRD presentation to 2nd JRM / 1.5 Key challenges / The key challenges include: / Further strengthening financial planning and budgeting (building on substantive progress already made) – particularly ensuring a closer match between promised commitments and actual disbursements and the timeliness of financial processing. / To encourage better collaboration between SSA and RMSA and the teacher education mission in planning and implementation. / To come to agreement on a RFD in the short term and to build capacity in education management systems and promoting a culture that uses data to inform planning and implementation. / To institutionalise a cycle of national assessment at the secondary level using IRT methodologies and to strengthen the dissemination and accessibility of findings thereby encouraging data use. / To broker support on teacher management, school leadership and school performance standards and school improvement (working with HMG partners) / Availability of funds: Union Cabinet approval for 2013-14 falls short of MHRD’s own projected requirement on two counts; the first being expansion of the programme to Government aided schools and second, MHRD’s endeavour to clear up committed liabilities carried over from previous years.
Annual Outcome Assessment / The annual outcome assessment is graded as ‘A’ (met expectations). / The RMSA is developing well as an effective sequel to the Sarva Shiksha Abhiyan (SSA) at the elementary stage. That RMSA was launched ahead of the culmination of SSA’s first eight year cycle is indicative of the Government’s resolve to tie-up smooth arrangements for transition of universalised elementary education to well organised secondary education. The Government’s decision to emphasise, in the initial phase of RMSA, focussed attention to installation of infrastructural and institutional arrangements exemplifies its eagerness to ensure a qualitative approach to quantitative expansion. / In terms of outcome indicator on enrolment of students in secondary level, 34.6 million children were enrolled in 2012-2013 as against total enrolment of 28.3 million in secondary (Grades IX and X) level in year 2009-10. Provisional 2012-13 U- DISE figures suggests the national gross enrolment ratio at junior secondary level is 69% - with 34,643,915 children enrolled out of whom 18,321,796 are boys and 16,322,119 girls. Transition rates from Class VIII-IX are reported at 91% nationally a very encouraging figure, however, there are 15 states including Bihar, Madhya Pradesh and the North Eastern States with transition rates below this. Data suggests that there are approximately one million repeaters at junior secondary level undermining the efficiency of the system. / On Gender parity index in enrolment (in schools supported through RMSA programme), it is reported as 89 girls to every 100 boys enrolled at junior secondary level. This scenario puts India off track on gender MDG 3. MHRD is committed to addressing this imbalance. It is also an area where DFID, through a complementary conditional cash transfer programme is making an important contribution. / For number of SC and ST girls per 100 boys, the percentage of Muslim, SC and ST enrolment to total enrolment stands at 9.06 %,18.24% and 8.42% respectively. Overall ST and Muslim children are particularly under represented at secondary level. It is likely but not possible to currently verify that children from these groups under perform in learning assessment. / MHRD report that 76 % of habitations are served by a Secondary education facility within 5 Km as per the Annual Work Plan and Budget (AWP&B) 2013-2014 as against 68% in 2012-2013. A total of 9,636 schools were sanctioned by March 2013 out of which 8,605 schools are functional. 61% of the new schools were set up in low income states of Bihar, Chattisgarh, Jharkhand, MP, Odisha and Uttar Pradesh. / Teacher and teacher management issues remain a concern. However, many of the levers for change in this area are outside the direct remit of RMSA management. Only two thirds of the 633,760 sanctioned posts have been filled (UDISE provisional 12-13). Teacher training support remains a concern with only 19 % of the approved financing for induction support being utilised.

2. Costs and timescale:
2.1 Is the project on-track against financial forecasts: Yes / The project is on-track against financial forecasts. In line with the agreed financial arrangement, DFID disbursed its first tranche of £20 million for FY 2012-13 against the semi-annual interim unaudited financial report (IUFR). The second tranche of £20 million is scheduled for disbursement in December 2013. This will be released after reconciling our last year’s disbursement with the audit reports of FY 2012-13. Any discrepancies between them will be adjusted in making our second tranche disbursement. Subject to timely approvals from the government partners, the projected spend will be achieved. If MHRD approvals are not secured there is a risk of underspend of upto a £1 million in the financial year. / The procurement of the technical cooperation agency (TCA) through competitive tender was efficient and the TCA were operational as per agreed timelines. However, the inception period for the TCA was extended by three months to accommodate MHRD decision making on the TCA mandate and workplan. The TCA implementation work plan was approved by the Project Steering Committee in September for the period October,’13 –Mar,’14. / 2.2 Key cost drivers / The key cost drivers of the programme include (i) construction and renovation of school buildings; (2) salaries for additional teachers; (3) training for teachers and school heads; (4) books and science equipment; (5) small grants for community-run school management committees and (6) technical support through the jointly selected technical cooperation agency (constitutes 17.5% of the total project allocation). / 2.3 Is the project on-track against original timescale: Yes / The project is on-track as per the original timescale. The secondary education programme was launched by GoI in 2009. The World Bank and DFID agreed to pooled support with GoI for the period 20012/13-2016/17. DFID’s financial aid support will end by December 2015 timed with the closure of DFID I’s financial aid support to GoI.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The fundamentals justifying DFID support remain. Indeed there is growing concern that without addressing secondary education issues India’s vaunted demographic dividend could end up as a disaster – potentially contributing to social unrest. / A result framework document (RFD) was agreed between GOI, state governments and development partners at the outset at the programme level and formally signed off in the loan agreement. This framework included a full range of performance indicators (dis-aggregated by social group and gender) with annual milestone targets and data sources from which targets would be monitored. Regretably, MHRD have unilaterally revised this and in certain cases removed indicators without explanation. This poses challenge in monitoring progress against envisaged results. DFID along with World Bank is currently trying to resolve this issue with GoI. / DFID constantly monitors evidence as generated from central government published data sources, project management information system, six-monthly joint review missions with government and donor partners, and through independent reports. DFID is also contributing to the evidence base through both the TCA and World Bank trust fund commissions. / 3.2 Where an evaluation is planned what progress has been made? / Following the successful procedures of SSA, third party monitoring of implementation performance has been agreed upon by GoI by contracting independent monitoring institutes. / The DFID funded TCA contract has its own evaluation and performance monitoring procedures and is subject to performance reviews as detailed in the contract. / In addition DFID India education team are commissioning an impact evaluation of the technical cooperation component of the Education Portfolio. / A joint DFID / World Bank third-party end of project (EoP) evaluation will be initiated to feed into the project completion reporting exercise.

4. Risk
4.1 Output Risk Rating: Medium/ / 4.2 Assessment of the risk level / A comprehensive assessment of the FM arrangements and implementation readiness of RMSA was carried out through a Fiduciary Risk Assessment (FRA) in March 2011 (refer table below). This concluded that (a) the programme is expected to focus significantly on civil works in the initial few years of the DP financing. Also the arrangements for execution are variable across states; (b) several states have opted for new societies for programme implementation. This would result in their needing to establish new fiduciary systems and learning that may have been gained from years of SSA implementation may not be fully utilized; and (c) systems for implementation of the programme e.g. staffing for the FM function, arrangements for accounting and reporting, audit etc. are being set-up. / Table: Highlights of PFMA Risks: Good Practice Principles & Risk Rating / GPP 1: A clear set of rules govern the budget process. S/ H / GPP 2: The budget is comprehensive. L / GPP 3: The budget supports pro-poor strategies. M / GPP 4: The budget is a reliable guide to actual expenditure. H / GPP 5: Expenditure within the year controlled. H / GPP 6: Government carries out procurement in line with principles of value for money and transparency. S / GPP 7: Reporting of expenditure is timely and accurate. S/ H / GPP 8: There is effective independent scrutiny of government expenditure. H / Risk Rating Nos. of benchmark / Low Risk (L) 2 / Moderate Risk (M) 2 / Substantial Risk (S) 5 / High Risk (H) 6 / Overall risk rating S / The bilateral MOU was signed in November 2012, the annual statement of progress (ASP) for FRA is now due. The ASP exercise will check if the identified fiduciary risks are being adequately managed and planned reforms or safeguards are being implemented. It will also identify any new fiduciary or corruption risks or changes in circumstances in completing ASP on FRA in line with DFID guidelines and standards.
Risk of funds not being used as intended / The Programme expenditure and accounting follows the Financial Management and Procurement Manual (FMPM) that has been prepared in consultation with states and the Bank. This covers procedures for planning/budgeting, funds flow, accounting and internal controls, staffing and capacity building, and audit. / Development partners (DP) reimburse expenditure compliant with the FMPM guidelines. DPs jointly monitor RMSA’s financial management systems based on the review of GOI’s Financial Management Reports (FMRs), Audit Reports, JRM documentation, IPAI reports on concurrent reviews, manual and GOI’s external website. / The first set of audit reports is expected end October 2013. These will be analysed by the DPs. Issues of concern will be discussed with MHRD for resolution and any discrepancies adjusted through subsequent DP disbursements. / MHRD is urging all states to develop Financial Management Information Systems – an electronic repository where all budget heads from the school level upwards would be aggregated as per the annual work plan, and expenditure will be booked against them at the school, district and state levels. Information on financial transactions will be uploaded and consolidated regularly for public access to ensure greater accountability of expenditure. States are at the early stages of developing such systems. / The Fiduciary Risk related to the TCA contracted to Cambridge education is adjudged low. A milestones based contract with the technical agency drives progress and disbursements in arrears against invoices. / 4.4 Climate and Environment Risk / The climate and environmental issues in the RMSA are judged to be high /medium (varying from state to state according to natural hazard zoning). The main area of environment risk is associated with civil works. / An environmental assessment was undertaken by the development partners in preparation of financial support. This covers (i) environmental principles during site selection, design and construction; (ii) operation and maintenance of the school buildings; and; (iii) environment, health and safety aspects. The assessment informed an Environmental Management Framework (EMF) for RMSA which provides a set of measures/guidelines, which would help in preventing, minimizing and/or managing various environmental, health and safety concerns faced during planning, design construction and maintenance of secondary schools. This is monitored by the Bank. / Currently civil works is predominantly focused on upgrading existing schools – so issues of appropriate school siting are limited. The major concern is in school design and build quality particularly in earthquake / cyclone prone areas and in high population density areas where additional storeys are the only options for school expansion. / Ultimately supervision of school construction lies with state authorities. The DFID supported TCA fund is managing a comprehensive review of civil works covering school siting, spacing, design and build supervision.

5. Value for Money
5.1 Performance on VfM measures / DFID support is deemed value for money though aforementioned data challenges preclude detailed quantitative attribution. A revised logframe which pays greater cognisance to the impact (particularly systems improvement and policy influencing impact) derived from the TCA will enable a more detailed analysis of this area to be conducted in future reviews. / 5.2 Commercial Improvement and Value for Money / The DFID funded Technical Support Agency (TSA) was selected through OJEU competition and an output based contracting arrangement was negotiated in the year 2012 for better VfM. Specific and measurable milestones with target dates are agreed with TSA and are monitored on regular basis. A proper inventory is maintained for all the items procured from DFID funds. / Procurement under Financial Aid is managed by respective state implementation agencies adhering to the standard GOI procurement standards. States have introduced e-procurement system and all procurement plans are uploaded on their official RMSA website; Electronic accounting software (TALLY) is used in most states for financial management; Procurement and Financial Management specialists on behalf of the DPs review the procurement plans and ensure that all procurement practices are in compliance with the standard practices set out in the Financial Management and Procurement manual prepared by the GOI with input from DPs. The Ministry of Human Resource Development at the national level has developed online software to monitor progress of procurement contracts in excess of Rupees 1 million. / 5.3 Role of project partners / RMSA is a partnership between National and State governments and two development partners (DPs): The World Bank and UK’s DFID. 94% of funding requirements of the programme are funded from India’s own resources, with the balance being provided by the donor partners. DP’s support to RMSA is provided through a sector wide approach (SWAp). / DFID is the sole provider for technical assistance to the RMSA programme. The TCA impact exceeds expectations having built strong and trusting relations in a short period of time as evidenced by MHRD actively approaching DFIDs technical support unit for a number of high profile event and sensitive areas of support. / DPs participate in the Joint Review Missions and review status of the progress and issues. Two such reviews have taken palce since the inception of the support of DPs to RMSA. / DPs contribute to programme planning, implementation, monitoring and evaluation, including financial management/procurement capacity of states and districts and agree on actions to support the weaker states. / 5.4 Does the project still represent Value for Money : Y/N : Yes / DFID’s financial contribution is adding value to RMSA by: / Improving the technical quality of GOI programme management and design and strengthening monitoring and evaluation arrangements; / Supporting quality improvements advocating for and working with GoI on delivering a unified data management system and learning assessments surveys at grade X for remedial action. / Providing policy advice which is sensitive to and understanding of India’s machinery of government in education; / Sharing international experience; developing exemplars and helping to boost the confidence and capacity of the GOI and State staff machinery responsible for programme implementation. / 5.5 If not, what action will you take? / Not applicable.

6. Conditionality
Update on specific conditions / Financial reimbursements are not tied to, nor conditional on, particular aspects of programme implementation, but are based on GoI expenditures and implementation of the programme in line with its broad design. / Disbursements are based on Interim Unaudited Financial Reports (IUFRs) covering the current fiscal year, and programme expenditures reported in the IUFRs aresubject to confirmation/certification by the annual audit reports of all implementing agencies and States. Discrepancies between the programme expenditures reported in the IUFR and those reported in the Consolidated Report on Audits are to be adjusted in subsequent disbursements (to be recovered from or reimbursed to GoI through the next disbursement).

7. Conclusions and actions
In Nov 2013 DFID will complete a year’s support to RMSA. Progress is broadly as expected – with DFIDs technical support proving to be particularly valued. / Action items for 2014 include: / Revise the DFID logframe to better capture progress of both delivery and TC support / Finalise and strengthen data and results monitoring processes / Establish formal light touch governance mechanisms for the TCA / Accelerate the work of the TCA particularly at state level. / Support and strengthen delivery and use of learning outcome assessment at central and state levels

8. Review Process
The annual review (against the original RMSA logframe) was completed by the DFID education team including members that participated in the 2nd Joint Review Mission. Reference was made to available government and independent reports, In particular the 1st and 2nd Joint Review Missions (JRM) held in January 2013 and July 2013 respectively informed this review. Aide Memoires and associated documents are available at http://mhrd.gov.in/rashtriya_madhyamik_shiksha_abhiyan .