Annual Review – post April 2018

Title: Special Development Fund 9th Replenishment
Programme Value £ (full life): 18,000,000		Review Date: 15/11/2018
Programme Code: 204675	Start Date: 29/11/2017	End Date: / 01/07/2022

Summary of Programme Performance
Year	2017
Programme Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204675
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204675

A. Summary and Overview (1-2 pages)

Description of programme

The 9th replenishment of the Special Development Fund (SDF 9) will contribute to economic and social development in the Caribbean’s poorest countries through support to core sectors that contribute to the achievement of the Sustainable Development Goals (SDGs): transport, education, water and sanitation, agriculture, climate change/environment and inclusiveness – leave no one behind, jobs and prosperity.

DFID will contribute up to £18 million (including up to £4.5 million as a performance based tranche for 2020) towards the replenishment of SDF 9, running from 2017-2020. The SDF is the Caribbean Development Bank’s (CDB) concessional mechanism (soft loans below market rates, grants and technical assistance) supporting the most vulnerable and poorest people in the Caribbean region.

The SDF supports projects with a focus on basic social infrastructure such as roads and electricity, vocational training centres and schools, agriculture and climate change resilience (e.g. flood and hurricane protection) as well as support to poverty reduction through its Basic Needs Trust Fund (BNTF), which has focus on local vulnerable communities and gender equality. SDF has grant funding “set asides” for Haiti ($45 m), the Basic Needs Trust Fund (BNTF $45 m), disaster responses ($3 m) and regional collaboration ($4 m).

The CDB is expected to deliver both direct development results through the SDF 9 and internal reforms agreed as part of the SDF replenishment negotiations. These reforms, if implemented as planned, should strengthen its efficiency and effectiveness leading to improved performance during the SDF 9 period and beyond. The Bank has outlined the expected development outputs and results offer for the SDF 9 period 2017-2020. Examples include:
[note] Source: Replenishment of the Resources of the Special Development Fund Unified (SDF 9) Resolution and Report of Contributors, draft May 2016.

- 222 km of roads built or upgraded,
- 198,900 students benefiting from improved educational facilities and provision,
- 285 small businesses benefiting from credit,
- 248,768 beneficiaries of community citizen security interventions and
- 18,400 households with access to improved sanitation and water supplies

Summary supporting narrative for the overall score in this review

The CDB performed well across the vast majority of indicators in the logframe, but also against many indicators in the results framework which have not been selected for the DFID logframe. For those indicators selected for the DFID logframe, only three indicators failed to meet their targets, whilst many exceeded expectations. This paints a promising picture of progress compared to previous years.

One reason for that may be the CDB’s speedy response to Hurricanes Irma and Maria, which devastated the region in 2017. The CDB, through the SDF, provided several rapid response grants and loans which are likely to have helped improve some figures, such as speed of disbursement. However, these Hurricane response loans and grants have been excluded from other calculations, such as projects with gender mainstreaming, because they do not have gender markers.

Even so the Bank successfully delivered outputs across various sectors and is undertaking several efforts to improve efficiency and effectiveness, including the long-awaited roll-out of a new system designed to improve CDB’s ability to measure, monitor and report on results throughout the project/loan life cycle and improve the timeliness of decision-making (PRISM). This and other reforms are helping the CDB improve the speed and effectiveness of its delivery and allowing it to better serve its borrowers.

The Bank’s performance has improved significantly in 2017 but this must not distract it from the further work which needs to be done to improve its operations, for instance in relation to PCR completion.

Recommendations for the year ahead

The main challenge of the year ahead will be to consolidate the progress made in 2017 and to continue improvement in areas where the targets get more challenging in future.

Recommendations for the year ahead concentrate on two main ideas. DFID, through engagement at the Board and from London, should:

1. Maintain pressure on the CDB to improve performance in remaining areas of underperformance
  1. PCR completion remains disappointingly low and as one of the three indicators in the DFID agreed Performance Improvement Plan it is important for the Bank, and DFID, that performance improves dramatically and quickly.
  2. Other targets, such as administrative expenses per $million disbursements only marginally missed the target. However, DFID should continue to encourage better performance

1. Monitor the appropriateness of targets
  1. Approvals supporting environment, renewable energy/energy efficiency and climate change substantially exceeded the target range in 2017. This was put down to an exceptional year supporting the Hurricane response, but DFID should closely monitor the performance and ensure that target for this indicator remains appropriate in the context of the wider portfolio.
  2. Indicators such as portfolio performance rating for implementation have been consistently above target levels for several years, which reduces their value. DFID should explore with the CDB the possibility and desirability of getting further information on the breakdown of projects rated satisfactory, good and excellent. This will enable more detailed analysis of the strengths and weaknesses of the CDB’s portfolio and help inform improved policy making.

There are also several broader issues identified in the risk section, mainly the speed of spending on the Disaster Response set aside and the possible impact of a resultant reallocation of funds. The SDF 9 Mid-Term Review is the primary opportunity to engage on these important issues and DFID should work proactively to consider the best way forward.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Project Outputs
Output number per LF		1	Output Score	A
Impact weighting (%):		30	Revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
1.1 Students benefiting from improved physical classrooms (Performance Tranche Indicator)	Planned: 20,000, Achieved: / 23,599	Target moderately exceeded
1.2 Land improved through irrigation, drainage, and/or flood management (hectares - cumulative)	Planned: 0, Achieved: 0	No planned achievement in 2018
1.3 Energy: Conventional or renewable power generation capacity installed (MW- cumulative)	Planned: 1.50, Achieved: 1.54 (of which 0.04 renewable)	Target moderately exceeded
1.4 Households with access to improved sanitation and water supply (number - cumulative)	Planned: 14,800, Achieved: 14,514	Target moderately not met

Provide supporting narrative for the score

The Bank exceeded targets for two out of three indicators where they planned to deliver outputs in 2017. The fact that they over-achieved by 17% on 1.1 more than offsets the fact that 1.4 was missed by only 2%. Overall this merits an A.

Indicator 1.1 Students benefited from the construction or upgrading of 247 classrooms with additional educational support facilities such as bathrooms, administrative spaces, and facilities for the disabled. As a result, the bank has moderately exceeded expectations for indicator 1.1.

Indicator 1.2 The bank did not plan to complete any projects in land improvements in 2017, and no projects from 2016 overran.

Indicator 1.3 In March 2017, a 1.5 MW energy generator was installed in Montserrat, providing reliable power to over 3,500 residents. In addition, the CDB financed the provision of solar panels for a number of hinterland communities in Guyana which are too remote access the electricity grid. This contributed to the additional renewable energy results reported in 2017 (40MW). The CDB is working to promote sustainable energy in the region through the Caribbean Sustainable Energy Roadmap and Strategy.

Indicator 1.4 During the year, 12,794 m3 of water capacity was installed in seven BMCs and 157.8 km of water supply lines installed/upgraded in six BMCs. As a result, the quality of life of 14,514 households was improved through access to safe and reliable water and sanitation facilities. The facilities are being fully utilised as designed and are meeting the needs of residents in the beneficiary communities. Whilst the 2017 figure is slightly lower than expected this is an area in which the CDB has performed strongly over the years, with the Bank well over half-way to meeting its 2015-2019 targets.

Lessons identified this year, and recommendations for the year ahead linked to this output

The CDB has performed reasonably well across output 1 in 2017. The challenge will be to keep this up in future years. The targets in the logframe are based on CDB forecasts and project pipelines which become less certain further into the future. To ensure that targets remain reasonable DFID should ensure a strong working relationship with the CDB results lead. However, any revisions to the targets should be thoroughly justified and not simply amend initial forecasts which were not correct.

Output Title	Strategic focus
Output number per LF		2	Output Score	A+
Impact weighting (%):		20	Revised since last AR?	Yes – since SDF 8 PCR

Indicator(s)	Milestone(s) for this review	Progress
2.1 Approved projects with a gender-specific or gender mainstreamed rating (as a % of total projects)	Target: 76%, Achieved:76%	Met
2.2 Approvals supporting environment, renewable energy/energy efficiency and climate change (as a % of total financing)	Target:16%-24%, Achieved: 71%	Substantially Exceeded
2.3 Technical Assistance (TA) approvals supporting private sector development and PPPs (as a % of total TA financing)	Target: 4%-8%, Achieved: 7%	Met
2.4 TA approvals supporting regional cooperation and integration (as a % of total TA financing)	Target: 40%-50%, Achieved: 47%	Met
2.5 Financing directed to less developed BMCs (% 3 year average)	Target: ≥51%, Achieved: 82%	Substantially Exceeded

Briefly describe the output and provide supporting narrative for the score

The CDB has either met or substantially exceeded every indicator under this output. On balance this warrants an A+. The use of ranges for these indicators makes sense across the period of replenishment as the makeup of the portfolio will inevitably fluctuate over the years, driven by many factors including project demand.

Output 2.1 The CDB agreed stretching targets which go beyond those in their corporate results framework during the development of the SDF 9 logframe, the e target, for 2019, in the CDB’s corporate results framework is a mere 40%. This target excludes Immediate Response Loans, which do not have gender markers. The focus on disaster response and speedy disbursement means that it is reasonable for these loans to not include gender markers.

The CDB has also introduced a new indicator, “Projects reporting on gender results during implementation” to monitor effective supervision of gender results and activities, as well as effective integration of gender design features into project implementation plans. DFID should consider adding this to the logframe.

The CDB also reports disaggregated data on various indicators, including “MSMEs benefitting from credit”, “teachers and principals trained” and “beneficiaries of road projects”.

Output 2.2 The CDB has substantially increased its approvals supporting environment, renewable energy/energy efficiency and climate change. At 71% this is now well above the 16-24% target agreed in the logframe (and even further above the 8-12% target in the CDB’s Corporate Results Framework) and above the baseline of 10.5%, increasing from 39% in 2016 and 22% in 2015. There are two main reasons for this:

1. The catastrophic 2017 Hurricane season severely impacted many of CDB’s BMCs.   During the period, CDB approved loan and grant financing totalling $104 mn to three BMCs geared at rehabilitation and reconstruction efforts, much of this work supported environmental goals. This is exactly what DFID has been advocating, by encouraging the Bank and Borrowers to “Build Back Better”.
2. A significant increase in borrowing activity in the energy sector with the approval of two relatively large loans ($55 mn) linked to energy efficiency projects.

This is a very broad indicator and DFID may wish to consider pushing for more specific indicators in the next iteration of the results framework. DFID should also seek to understand the implications of this increase, whether funds are being diverted from other areas such as Regional Cooperation, which declined in 2017, or whether there are simply more cross cutting projects.

Output 2.3 In 2017 the CDB approved a few initiatives to boost private sector development including:

1. A new private sector policy and strategy: the policy and strategy will include a framework to guide the Bank’s support for interventions in the sector, with a focus on achieving competitiveness within the Region’s private sector. A range of modalities and activities will be used that include both sovereign and non-sovereign operations, as well as lending and TA programmes.
2. The establishment of a cultural and creative industries fund: Given the significant growth potential of the creative sector, an initial contribution of $2.6mn was approved to support, innovation and emerging business opportunities in the cultural and creative industries, which mainly comprises MSMEs. This Fund will provide non-reimbursable grants to related projects and/or activities at the national, sub-regional and regional levels.

The CDB performed well in 2017, meeting the target set. However, as the target becomes more stretching in years to come it will be important that the CDB also expands its work. The new strategy is a step in the right direction.

Output 2.4 At 47% the proportion of TA approvals supporting Regional Cooperation and Integration (RCI) was comfortably within the target range. RCI projects are broad and varied, for instance, one of the largest contributions in 2017 was a grant allocation from CDB’s Special Development Fund (Other) by the Government of Mexico aimed at strengthening and supporting the CCRIF SPC (formerly Caribbean Catastrophe Risk Insurance Facility), which provides parametric insurance coverage for government risk to Caribbean and Central American countries.

Output 2.5 in 2017 the CDB directed 82% of financing to less developed BMCs. This is computed as a three-year average so was not unduly affected by the 2017 hurricane season. However, it is well above the target level. The CDB defines its less developed BMCs in line with CARICOM’s Revised Treaty. These countries are Belize, Dominica, Grenada, Guyana, Haiti, Montserrat, St. Kitts and Nevis, Saint Lucia, and St. Vincent and the Grenadines.  Of these Haiti is by far the largest recipient, as it is of the entire SDF, which somewhat boosts these figures. In 2017, the SDF committed over $25m in grant resources to Haiti.

 It is encouraging that the SDF is directing such a large percentage of its resources to the poorest members of the bank. This is what we would expect of the Bank’s concessional fund.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID should ask the Bank to consider the treatment of Immediate Response Loans and Rapid Response Grants in its results framework. There is currently inconsistency, with them being counted in the figures such as speed of disbursement, but not gender mainstreaming This could be done as part of the next results framework which will come into effect in 2020.

Approvals supporting environment, renewable energy/energy efficiency and climate change increased substantially in 2017. It is unclear if this was a one off, due to the reasons set out above, or if it is an indication of a broader shift. Progress should be closely monitored and the appropriateness of the long term 16-24% target assessed at the next annual review if the score does not return to normal

Output Title	Operational quality, effective portfolio performance and resource allocations
Output number per LF		3	Output Score	A
Impact weighting (%):		30	Revised since last AR?	Yes – since SDF 8 PCR

Indicator(s)	Milestone(s) for this review	Progress
3.1 Portfolio performance rating for implementation (% rated excellent to satisfactory)	Target: 90%, Achieved: 99%	Moderately Exceeded
3.2 PCRs prepared/completed within two years of project completion (%)	Target: 50%, Achieved: 36%	Substantially Not met
3.3 Average time taken from appraisal mission to approval (months)	Target: 3.5 months, Achieved: 1.6 months	Substantially Exceeded
3.4 Average time taken from approval to first disbursement (months)	Target: 8 months, Achieved: 8.0 months	Met
3.5 Average length of project extension (months)	Target: 30 months, Achieved: 26 months	Moderately Exceeded

Provide supporting narrative for the score

The CDB has generally performed well across output three; only indicator 3.2 not meeting the target and three of the five indicators performing better than the target. On balance this warrants an A.

Output 3.1 The CDB once again exceeded the target for portfolio performance under implementation, with 99% of operations rated excellent to satisfactory. Since 2013 this score has never been below 95% and has been either 99% or 100% in all other years. It is good to see that the CDB is consistently exceeding its targets, but this begs the question “are the targets too easy?” Given known concerns about the implementation of CDB projects DFID should endeavour to understand firstly, what makes a project “satisfactory” and secondly, the breakdown of projects achieving different ratings from satisfactory to excellent. This can be achieved by asking the CDB and by asking for publication of more detailed information as part the next iteration of the CDB’s Strategic Plan and Results Framework which will take effect in 2020.

Output 3.2 The CDB failed to meet the target of 50% of PCRs completed within two years of project completion, with only 36% of reports complete. This is a traditional area of weakness for the CDB and one which they acknowledge could erode the benefit of the self-evaluation system. It is also an area which DFID has incorporated in the performance tranche agreement, an acknowledgement of the importance of evaluation.

One key reason for the low level of report completion was the diversion of resources to support the response to the devastating Hurricanes Irma and Maria which hit the region in 2017. This is somewhat understandable but performance must improve in future years.

We have been informally told that the CDB will hire consultants to complete the PCR backlog caused by the hurricanes. This is acceptable as a one off to get back on track however it must not become the norm. Self-evaluation should be carried out by Bank staff with knowledge of the project and CDB systems, and can be complemented by independent evaluation carried out by consultants.

This target becomes rapidly more challenging over the course of the SDF 9 period, reaching 95% in 2020. The CDB must take strong action if this target is to be met.

Output 3.3 In 2017 the CDB cut its time from appraisal to approval to 1.6 months, well below the 3-month target. This was in large part due to the rapid response to Hurricanes Irma and Maria. DFID has long encouraged the CDB to operate more quickly and it is good to see that they are able to do so in times of need. This must now be mainstreamed to become the norm, and DFID should use its existing channels of influence, including the Board, to encourage this.

Output 3.4 The CDB met the 2017 target of months between approval first disbursement. This was a vast improvement on 2016, where disbursement took 32.2 months. This was again helped by rapid disbursements to cope with the hurricanes and the use of advance payment as a disbursement modality for investment loans and TA loans.

Output 3.5 Project extensions have been a major issue for the CDB over the years. In 2017 the average length of extension fell to 26 months, exceeding the target. This is a step in the right direction. The percentage of projects under extension also fell. There is still work to be done in the realm of project planning to ensure that projects are given the appropriate planning at the design stage.

Lessons identified this year, and recommendations for the year ahead linked to this output

The portfolio performance rated excellent to satisfactory remains well above the 90% level. This indicator is therefore not particularly informative when it comes to monitoring long term changes in CDB projects. DFID should explore with the CDB if it is possible to get a break down of project ratings across the categories which will provide more detailed information on changing portfolio performance over time. This will enable more detailed analysis of the strengths and weaknesses of the CDB’s portfolio and help inform improved policy making.

CDB once again failed to meet the target for PCR completion. This is worrying given that the target gets increasingly challenging over the course of the SDF 9 period. This is also a performance tranche indicator so DFID should strongly encourage CDB to improve performance in this area and closely monitor performance, for instance through check-ins on progress in year against the performance tranche indicators.

Output Title	Organisational effectiveness of CDB (administration and human resources)
Output number per LF		4	Output Score	A
Impact weighting (%):		20	Revised since last AR?	Yes – since SDF 8 PCR

Indicator(s)	Milestone(s) for this review	Progress
4.1 Administrative expenses per million US$ of project disbursements (3-year average) $000s	Target: Below 167, Achieved: 168	Moderately Not met
4.2 Ratio of professional staff to support/administrative staff	Target: 1.60:1, Achieved: 1.78:1	Substantially Exceeded
4.3 Vacancy rate at management and professional levels (%)	Target: ≤8%, Achieved: 4%	Met/Exceeded
4.4 Staff in management positions who are women (%)	Target: 40%-50%, Achieved: 44%	Met

Provide supporting narrative for the score

Again, the first year of the SDF 9 period has seen the CDB perform well, three of four targets were met or exceeded and the only target which was not met was missed by the smallest of margins. This improved performance warrants an A score.

Output 4.1 Administrative expenses per million US$ of project disbursements were marginally over the target, at $168,000. Internally the CDB’s only target is to reduce administrative expenses below the 2014 baseline of $181,000. The target in the logframe to reduce administrative expenses below the 2015 baseline, of $167,000, is more challenging. This is higher than in other MDBs, but this would be expected due to the CDB’s unique size and geography.

Output 4.2 The CDB have made excellent progress in improving the ratio of professional staff to support/administrative staff over the last 12 months, increasing from 1.55 to 1.78. This exceeds the target for 2017 and the increasingly challenging target to 2020. The jump can be explained by the Bank’s commitment to leverage technology in its support services, but it remains to be seen if this a one-off jump relative to the longstanding average of around 1.5 or will be consolidated in future years.

Output 4.3 The CDB continue to maintain a low vacancy rate at management levels. Given the small size of the CDB it is important that it maintains a low vacancy rate as it has little room to carry gaps in staffing, particularly at a senior level.

Output 4.4 The Bank has highlighted that indicator 4.4 is not intended to represent a quota, but rather check that adequate consideration is given to gender equality at managerial levels when recruiting or considering promotions. At 44% compared with 42% recorded in 2016 shows a slight increase, remaining within the target range for 2017.

Lessons identified this year, and recommendations for the year ahead linked to this output

The CDB predicts in its draft 2019-2020 Work Programme and Budget that Administrative expenses per million US$ of project disbursements will fall below $130,000 by 2020, this is far below the target in the Results Framework. Depending on what is finally agreed by the Board DFID should consider adopting this more stretching target in the logframe.

The CDB has performed well across output 4 indicators this year. It is important that this progress is now consolidated. DFID should continue to encourage the CDB to continue to improve in these areas; for instance, by monitoring the CDB’s administrative expenses against the projections in the Work Programme and Budget. DFID should also use the opportunity to input into the CDB’s next Strategy to push for more stretching targets.
C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

The programme’s theory of change and any major changes in the past year

The theory of change for SDF 9 combines both the resources provided for the SDF 9 replenishment and the ongoing engagement with the CDB, through the Board and other channels. It has not changed over the last year and is set out below:

Input
Outputs
Key Assumptions
- Financial contribution
- Policy engagement during negotiations and delivery
- Other development partners provide resources
- Clients continue to engage positively with SDF projects and demand remains high
- Reform led from HQ in Barbados has an impact on ways of working in-country and at HQ
- Reforms are relevant, and do improve the Bank’s ability to deliver results through speedier and more effective project processes
- Projects are resilient to risks arising in country
CDB organisational and operational outputs e.g.

Around $350 m of concessional funding to SDF countries including $45m to Haiti

CDB joins International Aid Transparency Initiative (IATI)

Eradicate poverty and achieve the Caribbean Sustainable Development Goals
- The Bank is capable of having a sustained impact on the sectors and policy areas it programmes in
- There is the political will and capacity in partner countries to ensure bank projects have a sustained impact
- The UK is successful in influencing the shape of SDF 9
- The Bank implements and monitors the agreed organisational and operational changes

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Due to the lack of an annual survey on impact level indicators (Proportion of population below the national poverty and indigence lines % in SDF eligible BMCs) it is not possible to say if the region is on track to.

The outcome level the results are encouraging, with most targets being hit. The only outcome indicator to fall short of its target was net enrolment in primary education, at 88.1% versus an 89% target. This is slightly concerning given that the target increases over the SDF 9 period.

Many of the other indicators are already close to meeting or above the target levels, for instance the Proportion of population with access to improved sanitation (% urban, rural) which at 87.1% and 82.8% respectively is already above the targets of 82% and 80.5%.

Looking forward the SDF will continue to deliver projects and programmes committed to improving outcomes and impact in eligible countries.

Explain major changes to the logframe in the past year

Over the last year, the SDF logframe has been reviewed and updated to reflect DFID’s priorities for the replenishment and the CDB more broadly.

Output 1 has been refocused on the outputs of CDB projects, bringing it in line with internal guidance and the logframes of other multilaterals and MDBs. This enables DFID to score the CDB on if it achieves the results that it sets out to in its projects.

The use of range targets for output 2 acknowledges that there the Bank should maintain a balanced portfolio and that it is rarely possible to precisely hit targets for priority sectors.

Output 3 has been rationalised with indicators which measured similar things being dropped and indicators in other priority areas have been added under output 4. This structure brings the CDB logframe in line with the logframes of other IFI special funds.

Describe any planned changes to the logframe as a result of this review

There are no changes to the logframe planned as a result of this review.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year

The overall VfM statement in the SDF 9 Business Case was “The limited analysis possible suggests that the SDF represents VfM in addressing the development needs of the region, particularly in promoting economic development and resilience in the smaller and poorer members where other MDBs do not operate and given the limited capacity of DFID to manage projects directly.”

In its first year, and in keeping with the statement in the Business Case, SDF 9 has made commitments across several sectors which promote economic development and resilience in eligible countries, including Environmental Sustainability, Climate Change and Sustainable Energy, Regional Cooperation and Private Sector Enabling Environment. The themes of SDF 9 grants can be seen below.

The SDF also contributed a significant amount of funding very rapidly following the devastating Hurricanes, Irma and Maria, which hit the Caribbean in September 2017. This included $200,000 emergency relief grants to Anguilla, Antigua and Barbuda, the Bahamas, British Virgin Islands and Guyana. This fast disbursing finance was most welcome given the circumstances and was not something that DFID could have done directly. The SDF also provided further support through concessional loans to countries rebuilding from the hurricanes. Many of these were countries where DFID does not work, such as BVI, but which were desperately in need of grant and/or concessional support following the Hurricanes. The ability of the SDF to provide this finance quickly and effectively greatly enhances its VfM offer. The downside of this is that SDF 9 spent more than 50% of its Disaster Response allocation in the first year of operations and would not be able to provide similar support were equally devastating Hurricanes to hit again before the end of the SDF 9 period. This is explored further in the risk section.

The SDF has long focused on the smallest and poorest members, for instance 2017 so $24.1m committed to support Haiti, which is 53.6% of the total SDF 9 allocation. SDF 9 also saw a one-off transfer of $40m to the Basic Needs Trust Fund. This Fund contributes to poverty reduction in targeted communities by providing infrastructure and livelihood enhancement services nationally and regionally. The BNTF supports many of the smallest and poorest countries in the region, as indicated by the proposed BNTF 9 allocations shown.
DFID’s focus on VfM through the SDF replenishment process is beginning to percolate through the CDB as a whole. For instance, the Draft Work Programme and Budget documents have begun to measure CDB performance against the four E’s, economy, efficiency, effectiveness and equity, accompanied by a narrative report. The Draft Work Programme and Budget for 2018/2019 introduced this and it will be continued in future iterations. These are indicators which are measured in the Development Effectiveness Report as a matter of course, and some are included in this Annual Review, but it is nonetheless positive to see the CDB begin to articulate their VfM offer more clearly. The next step will be set more stretching targets. The forthcoming revision of the CDB’s Strategic Plan is a good opportunity for the Bank to articulate its approach to VfM in a key document, and set targets.

Overall SDF 9 continues to in promote economic development and resilience in the smaller and poorer members where other MDBs and DFID do not operate as per the VfM statement in the Business Case. In addition, the ability of the SDF to quickly and effectively disburse funds to countries devastated by the 2017 Hurricanes enhances the SDF’s Value for Money offer. This offer is further enhanced by the changes it is stimulating across the CDB, helping the Bank to better articulate the ways in which is achieves Value for Money.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

As discussed above, the SDF 9 has a unique VfM offer which means that it should continue from a VfM perspective.

Looking forward there is another opportunity to push the CDB to programme the SDF in alignment with DFID priorities at the SDF 9 Mid-Term Review in 2019. This will be an important opportunity to consider the needs in priority areas such as Disaster Response and the case for reallocating funds.

As regards the wider portfolio, the CDB has a geographic and technical remit which greatly complements the work of DFID Caribbean. Delivering through the SDF allows DFID to reach a wider range of countries than it would have otherwise been able to as well as operating in a variety of sectors, including infrastructure, health and education.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The SDF 9 Business Case identified risk across six categories:

- External Context – The Business Case states that high debt levels in SDF countries could affect the levels of grant vs loan project undertaken by the SDF. These debt levels remain elevated and the risk remains live. The other significant element of external context for the SDF in 2017 was the exceptionally severe hurricane season. This led to SDF 9 committing more than half of its Disaster Response allocation. There is now a risk that if there are equally severe hurricanes in future years the SDF will not be able to respond. To mitigate this risk the CDB committed to review the allocations at the Mid-Term Review. This is welcome, but reducing the allocations for other priorities risks a loss of outcomes in these areas.
- Delivery of Outcomes – SDF 9 performed well on its delivery of outputs, and there was also some progress at the outcome level. The Bank has also made progress in speeding up internal procedures, though the extent to which this is due to the exceptional hurricane season rather than being a permanent change remains unclear. However, the delivery of outcomes relies on more than just an effective CDB and borrower capacity remains a challenge. The CDB is working hard to boost capacity, for instance through the creation of a Regional Procurement Centre which will build the procurement capacity of staff in borrowing member countries.

Safeguards- The Business Case assessed the CDB as having generally adequate safeguards policy and systems. The recent Central Assurance Assessment concurred with this assessment. However, it also identified a risk around safeguarding, whereby the limited oversight of the delivery chain in SDF projects can mean that CDB does not become aware of issues relating to projects it finances. This can mean that it does not get the opportunity to utilise its powers under its Framework for Integrity, Compliance and Accountability. Internally, ICA carries out mandatory training and awareness sessions for management and staff cover all wrongdoing including sexual misconduct. The Head of ICA attended the recent “Putting People First” summit to learn more about how the Bank can improve in this area. Earlier in the year the SoS wrote to the Head of the CDB setting out DFID’s expectations of the CDB, and other multilateral partners.

Operational – The Business Case ascribed a low probability to operational risks. One of the mitigating actions was to push for the Bank to “strengthen its operations in Haiti”, which receives the most support from the SDF. The Bank has just opened an office in Haiti which should help to improve its local knowledge and relationships in country.

Fiduciary – The Business Case identified minor/moderate fiduciary risks, noting that fraud on certain projects is always a risk. The CDB has established and is expanding its Office for Integrity, Compliance and Accountability which seeks to strengthen the Bank’s processes and procedures to tackle fraud. ICA will be independently assessed within the first five years of its operations, by 2021 at the latest. DFID should take note of this review and respond as appropriate.

Reputational – The Business Case assessed there to be a low reputational risk, whereby CDB projects could be subject to fraud or high-profile mismanagement. This remains a minor risk given the progress above. CDB also has risk mitigation systems in place to manage reputational issues.

The main challenge for the SDF is to consolidate its strong performance in 2017, which was boosted by the response to Hurricanes Irma and Maria. As targets in the logframe become more stretching this could prove difficult. There is a risk that performance could slip back to previous levels. The Bank is seeking to do so by implementing new systems such as PRISM. Overall the risk rating for SDF 9 is minor.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues

The CDB’s recipient executed delivery model means that it carries out little direct procurement on SDF projects. The Bank provides oversight to ensure that procurement is carried out in accordance with the Bank’s procurement guidelines and the terms of the relevant financing agreement between the recipient and CDB. Further details on the CDB’s procurement process can be found in the 2018 Central Assurance Assessment, which found that despite good policies and procedures the CDB is lacking in expert staff capacity to engage in every project. Limited internal resource means the CDB must work to improve the capacity of its borrowers. It has recently opening a regional procurement expertise centre in Jamaica in partnership with the World Bank.
[note] Vault ID 31063886

DFID has deposited the first two Promissory Notes of £4,500,000 each as per the agreed schedule.

Date of last narrative financial report(s)	30/05/2018
Date of last audited annual statement (s)	30/05/2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

The Bank has good sources of evidence, including the Annual Development Effectiveness Reviews, the Annual Report, and the SDF Annual Report. Data collection however continues to be weak in borrowing countries where capacity remains weak overall. The Bank aims to conduct self-evaluations on all projects, which are verified regularly through its independent evaluation department. No DFID specific evaluations were conducted during the reporting period.

The CDB continues to struggle to complete PCRs, a lesson that has not been learnt in previous years. That said, the Bank has acknowledged that failing to complete PCRs “hinders the learning process and weakens the self-evaluation system as information which could have been used to improve the implementation of ongoing projects and the design of future projects is not incorporated in a timely manner.” This needs to kick start improvement over the remainder of the SDF as targets become increasingly challenging.

Evidence

The CDB’s Office of Independent Evaluation (OIE) is the main source of independent evaluation and evidence within the CDB. In 2017 it completed an evaluation of the Bank’s policy-based operations for the period 2006 to 2016. It included case studies of policy-based lending in Barbados, Grenada, Jamaica, and St. Vincent and the Grenadines. Overall, there was evidence of continuing demand for this lending instrument; achievement of most of the agreed prior actions; and some progress on expected outcomes. This evaluation is of limited relevance to the SDF, which makes few PBLs.

The CDB’s Office of Independent Evaluation also sponsored the engagement of Caribbean Evaluators International, the regional association of professional evaluators, with the International Development Evaluation Society. This resulted in a signed memorandum of understanding between the two organisations, representing a further step towards professional capacity development in the Region.

As for evidence of the impact of the SDF, the key point for this is the Mid-Term Review which will be carried out in 2019. DFID will engage proactively with the review and discussions of reform to the SDF.

Learning

The first year of SDF 9 has seen good progress against many indicators; one contributing factor was the Bank’s speedy response to Hurricanes Irma and Maria.

However, the hurricanes also posed a problem for the SDF. SDF 9 was significantly smaller in size than both SDF 8 and SDF 7 before it. The UK halved its contribution to SDF 9, which was significant given that it is one of the largest donors. The value of the Disaster Response Set-Aside was not increased between SDF 8 and SDF 9.

The exceptional nature of the response the Hurricanes Irma and Maria meant that the CDB committed more than half of the entire Disaster Response set-aside in the first year of SDF 9. This means that the CDB’s capacity to support future hurricane responses is constrained.

To get around this the CDB must be flexible; the President has already indicated that there will be a reallocation of funds at the Mid-Term Review. This is welcome and DFID will engage constructively in the discussions. However, there are risks that reallocation of funds will mean that SDF 9 is unable to support planned projects in other areas.

This hurricane season highlighted the need for the CDB, and region more broadly, to focus on resilience and risk transfer mechanisms. The UK Caribbean Infrastructure Fund (UKCIF) is an important project in this regard, helping the CDB fund critical economic infrastructure including: bridges; renewable energy; ports; water; and sea defences that will increase productivity and resilience to natural disasters and climate change and increasing DFID’s influence within the Bank.

Progress on recommendations from previous reviews

Recommendations from the SDF 8 PCR included:

We should continue to closely monitor progress on representation of women during the next replenishment including by incorporating it in the project logframe for the UK’s contribution. – this was included in the logframe for SDF 9

We should ensure that we have a broader set of results indicators in our logframes for the SDF programme to measure operational delays. We should support the operational initiatives described above and monitor progress. – Changes to the logframe are covered in section C and DFID continues to encourage the CDB to implement initiatives to enhance operational efficiency, such as PRISM. Indicators in the SDF 9 logframe show improvement in 2017

The indicator for completing PCRs for projects completed in the last 2 years should be included in future programme monitoring and we will pay close attention to annual results for this over the next 3 years and DFID should raise it again as an issue should the Bank not be making satisfactory progress - this was included in both the performance tranche and SDF 9 logframe, though progress has been slow.

Although the percentage of projects under implementation rated as satisfactory or highly satisfactory was ahead of target, it should be noted that in general the results for this area of the Bank’s own Results Framework “Operational processes and practices, and portfolio performance” were not good, with 5 of its 8 indicators failing to meet targets. We should pay close attention to this area when we manage our future SDF funding – paying particular attention to project extensions and ensuring that we include indicators for both the proportion of projects with extensions and for the percentage of projects with extensions of 36 months or over which can be monitored year on year and raised with the Bank at various fora as appropriate (including annual meetings of the Bank and the SDF). – to maintain a succinct logframe it was decided that only one indicator on project extensions would be used. However, the progress against the other indicator is referenced in the narrative. Both have improved in 2017.