Type of Review: Project Completion Review

Project Title: Tanzania Revenue Authority –Tax Modernisation Project

Date started: 01/02/2010	Date review undertaken: 22/11/2013
Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
Under a Memorandum of Understanding between DFID and the Tanzania Revenue Authority (TRA), DFID provided funding to a multi-Development Partner (DP) basket to support the implementation of the TRA’s Tax Modernisation Programme (TMP) under its Third Corporate Plan (2008/09 to 2012/13) –CP3. The support marked a continuation of DFID’s funding for TRA’s TMP under its Second Corporate Plan (2003/04 to 2007/08).

What were the expected results?
Impact/Goal: The stated impact of the programme was to enable the Government of Tanzania to improve revenue collections in order to achieve MKUKUTA goals of higher growth, poverty reduction and good governance. This was to be assessed by an increase in the tax revenue to GDP ratio from 14.5% in 2008 to 20.3% in 2013. / Outcome/Purpose: The stated purpose of the programme was to support the establishment of an efficient and effective tax administration that provides high quality customer services with fairness and integrity. / This was to be assessed through a number of indicators covering the i) level of annual tax collected versus its target ii) average time taken to clear goods at ports, border posts and airports iii) time taken to register taxpayers iv) level of revenue realised from audits/revenue collected v) level of perceived corruption and vi) the cost of collection as a % of revenue. / The programme’s outcome/purpose was to be achieved through a range of supporting outputs targeted at: / Increasing revenue collection in a cost effective way through broadening the tax base; increasing levels of compliance; improving the tax structure; and better monitoring and controlling of the cost of revenue collection; / Improving the efficiency and effectiveness of TRA by integrating its operations; / Providing high quality and responsive customer service; / Strengthening the efficiency of tax enforcement with a fair, equitable and transparent application of tax laws; / Improving TRA staff competence, motivation, integrity and accountability. / The above impact, outcome and outputs were drawn from TRA’s M&E framework for CP3.

What was the context in which UK support was provided?
The Government of Tanzania established the Tanzania Revenue Authority (TRA) in 1995 as a semi-autonomous agency with the objectives of increasing revenue collection; improving tax policy making; broadening the tax base; and responding to the serious fiscal problems arising from the gap between stagnant revenues and rapidly growing expenditures, which had resulted in an increase of the fiscal deficit from 5% in FY 1994 to 7.9% in FY 1995. / The creation of TRA had an immediate impact on collection efficiency, and actual tax revenue collected increased by 26% in the first year of operation. However, despite these commendable improvements, collection performance stagnated between 11 and 12% of GDP from FY 2000 to FY 2006 – some way below the sub-Sahara African average. As a result, the GoT asked TRA to launch a second generation of reforms to make TRA more investor and taxpayer friendly, strengthen its operational efficiency, and enable TRA to further boost revenue collection. Responding to this request, in 2003 TRA developed its second five-year corporate plan consisting of 70 major initiatives to be implemented in FYs 2003/04 – 2007/08. Five DPs (DFID, The World Bank, the IMF, the EU, and DANIDA) supported the preparation and implementation of the plan. / The reforms of the second corporate plan substantially improved the revenue collection system. Tax yield more than doubled from TShs 1.4 trillion in 2003/04 to TShs 3.4 trillion in FY 2007/08, raising the tax/GDP ratio to 14.5%. Broadening the tax base substantially increased the fairness of the tax system, as the number of registered taxpayers increased from 190,000 in July 2003 to 381,000 in March 2008. Despite these improvements, further reforms were required to consolidate results achieved and reach still higher revenue targets to effectively support public service delivery. / Thus the GoT developed its third corporate plan, spanning five years 2008/9-2012/13 and requested DP support from year two to foster the mobilisation of domestic resources; reduce the taxpayer compliance burden; improve the investment climate and facilitate cross-border trade; continue to improve the quality of services offered to taxpayers; and install a culture of transparency and integrity among TRA staff. / DFID’s impact, outcome and output objectives to support CP3 are detailed earlier. Alongside DFID’s support to a basket fund with DANIDA, which directly supports CP3, a number of other DPs were active in providing non-basket financial aid and/or technical assistance. These included the World Bank, Investment Climate Facility, IMF and IMF AFRITAC EAST, JICA, Korea International Cooperation Agency, Norway Tax Administration, TradeMark East Africa and the US Treasury. / The programme has been implemented by the TRA with strong support from its highly capable senior management. Up to the 30th June 2013, the programme end-date, 93 of the 98 major performance initiatives had been completed to achieve a 95% implementation performance rate. The remaining 5 initiatives which are at different stages of implementation have been rolled over into a new fourth Corporate Plan. / Approach to assessing scoring: / The approach taken to assess the scoring of indicators is as follows: / Green: consistently good performance in the interim years and the end of programme target was met; / Yellow: significant under-performance in the interim years although the end of programme target was met; / Red: under-performance throughout the duration of CP3 with an unmet end of programme target.

## Section A: Detailed Output Scoring

Output 1: Increase Revenue Collection in a Cost Effective way
Output 1: final score and performance description: / Final result: A – output met expectations. / The output was composed of a number of indicators detailed below. Strong performance has been seen in relation to the broadening of the tax base with registrations for Taxpayer Identification Numbers (TIN) and VAT quadrupling and trebling respectively over the programme duration, whilst more large taxpayers now account for 80% of revenue generation. However liquidity problems in some major parastatals impacted negatively on the collection of revenues, including the collection of arrears causing some under-performance – particularly so on the collection of arrears from large taxpayers. / Registered taxpayers by Department, disaggregated into TIN, VAT and Large Taxpayers: There has been substantial progress year-by-year in TIN and VAT taxpayer registration, although there has been an under-performance in relation to large taxpayers: / TIN 2008 Baseline: 398,080. 2013 Target: 800,682. 2013 Actual: 1,611,520 / VAT 2008 Baseline: 9,036. 2013 Target: 14,553. 2013 Actual: 21,362 / Large Taxpayers 2008 Baseline: 370. 2013 Target: 450. Actual: 432 / Revenue Collection Performance by Department, disaggregated into the Domestic Revenue Department (DRD), Customs and Large Taxpayers. Progress has been mixed throughout the programme period with DRD outperforming milestones in many years whilst general under-performance has been seen for the Customs and Large Taxpayer departments. This is attributed to lower than expected revenue performance from major parastatals which faced liquidity problems over the duration of the programme: / DRD 2008 Baseline: 104%. 2013 Target: 100%. 2013 Actual: 102% / Customs 2008 Baseline: 97%. 2013 Target: 100%. 2013 Actual: 94% / Large Taxpayers 2008 Baseline: 105%. 2013 Target: 100%. 2013 Actual: 97% / Number of taxpayers accounting for 80% of total Large Taxpayer Department revenue. Whilst a moderate under-performance was seen on milestones for the interim years of the programme, the actual end of programme target was achieved. : / 2008 Baseline: 39. 2013 Target: 50. 2013 Actual: 56 / Amount of previous year’s arrears collected/total amount of tax arrears at beginning of the year, disaggregated into the DRD and Large Taxpayer Departments. Although the end of programme target was met for the DRD, there has been a general significant underperformance across both departments in the interim years and particularly so for large taxpayers. For large taxpayers, most of the arrears were from major parastatals such as the Tanzania-Zambia Railway Authority (TAZARA), Air Tanzania Corporation (ACT) and Precision Air, all of which have faced liquidity problems: / DRD 2008 Baseline: 63%. 2013 Target: 65%: 2013 Actual: 65%. / Large Taxpayers 2008 Baseline: 100%. 2013 Target: 95%. 2013 Actual: 58%
Recommendations: Whilst the results on taxpayer registrations are encouraging, there is a need to delve beneath these numbers to analysis the number of active taxpayers. These statistics should also be monitored. The impact of poor parastatal performance on revenue collection remains a significant problem and TRA’s new Corporate Plan should seek to see how this can be addressed, in conjunction with the fourth Public Financial Management Reform Programme (PFMRP IV), supported by DFID. / There are issues of funding and staff numbers within TRA that need to be addressed. A full staffing review that leads to better focusing of staff resources in higher yielding areas to help increase revenues would be helpful. This should be encouraged under CP4. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Modernisation of TRA operations
Output 2: final score and performance description: / Final result: B – output moderately did not meet expectations. / The output was composed of a number of indicators below and its performance score was the lowest of all output areas. Performance on VAT e-filing met its target but under-performed in interim years. The implementation of e-filing, however, marks an important step towards improving the integrity of taxpayer returns whilst reducing transaction processing times and providing geographical convenience for taxpayers. It also helped reduce errors vis-à-vis the filing of paper returns and helped to stem opportunities for corruption by reducing face-to-face time. Performance on the timeliness of VAT refunds and transactions processed by ITAX has been disappointing. Generally, it should be noted that given the wide array of modernisation initiatives under CP3, the selection chosen for the DFID log-frame is narrow and thus doesn’t reflect good progress on modernisation initiatives in other areas for example the implementation of electronic tax payments through mobile phone devices. / % of large taxpayers that submit their VAT returns electronically. Whilst the end of programme target was met, there has been under-performance across the interim milestone years. It is noted that experience suggests that unless e-filing is the only option, a number of businesses will prefer to use manual filing potential due to reluctance to change internal control processes. The sustainability of the performance of this indicator is therefore questionable and a 100% target is deemed to be unrealistic in the context where there are other options to file. / 2008 Baseline: 67%. 2013 Target: 100%. 2013 Actual: 100% / % of VAT refunds made within a month. Under-performance has been seen on this indicator across the years. The level of accuracy of VAT return claims is not as high as it could be and hence a significant proportion of claims continue to require either desk audits or verification at the taxpayers’ premises. Both are time consuming processes and combined with the internal TRA administrative and approval processes, continue to contribute to lengthy timescale and hence the missed target. / 2008 Baseline: 72%. 2013 Target: 90%. 2013 Actual: 85% / % of transactions processed by ITAX. This indicator has generally under-performed. ITAX, the current domestic tax system has not been as robust as expected given that modules on debt management, audit and refunds have not operated efficiently. However going forward into CP4, acquisition of a new integrated domestic tax administration system will assist in improving this indicator: / 2008 Baseline: 50%. 2013 Target: 100%. 2013 Actual: 84%
Recommendations: None beyond the plans set out to tackle these challenging areas in CP4. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Provide High Quality and Responsive Customer Service
Output 3: final score and performance description: / Final results: B – Outputs moderately did not meet expectations. The output was composed of a number of indicators detailed below. Areas of good performance have been seen across this output particularly in relation to enhanced taxpayer awareness and TRA’s response times on taxpayer queries. However, progress on improving customs clearance times has been very disappointing, particularly at the port in Dar Es Salaam. Given that customs clearance is a major reform initiative and once improved has the potential to generate substantially more revenue, the overall output is scored as a B to reflect its heavier weighting/importance. / % of customs clearance made within 24 hours. Underperformance, including on interim years and substantially for the DSM Port has been seen on this indicator. Customs performance remains far below expected service levels due to a plethora of issues including i) the process of customs declarations by TRA uses a centralized data processing office (CDPO) which in theory is an excellent concept as it should result in more efficiency, more effective and consistent checking and it separates the processing officer from the importer or exporter. However the unit only works office houses plus Saturday mornings. This impacts hugely and negatively on clearance times. Where centralised units are employed (e.g. South Africa, UK) they operate 24/7 on a shift basis. Another process challenge is that some consignments are checked at two stages, instead of one, which also greatly contributes to clearance times whilst adding to the costs of importing. Also to note that there has been due to the delay of the implementation of major initiatives within CP3 including a new customs system, cargo management system and risk management system. Once these systems are successfully implemented, improvements should be noted in cargo clearance times across ports: / DSM Port 2008 Baseline: 58%. 2013 Target: 100%. 2013 Actual: 41% / Airport 2008 Baseline: 91%. 2013 Target: 100%. 2013 Actual: 75% / % of declarations subjected to scanning or physical verification: Significant under-performance has been seen on this indicator, particularly at the port. In Tanzania, there are three channels that declarations should be passed through – the i) green channel: cleared without detailed document verification or physical inspection ii) the yellow channel: subjected to detailed document verification with the deferred option of physical inspection and iii) red channel: detailed document verification and mandatory physical inspection. The current ratios for risk channelling are considerably outside of accepted norms. To take a snapshot of the period 27 Dec 2012-28 Feb 2013, 15% through green versus 60-70% international norm; 67% through yellow versus 20-25% international norm; and 18% through red versus 5-10% international norm. The high level of these targeted interventions imply weaknesses in the risk management system and also distrust on declarations: again taking a snapshot as an example, agent import statistics show widespread non-compliance with 47% of the over 37,000 declarations checked between July and August 2012 have their customs rates uplifted and 29% being reclassified: / DSM Port 2008 Baseline: 85%. 2013 Target: 40%. 2013 Actual: 92% / Airport 2008 Baseline: 43%. 2013 Target: 20%. 2013 Actual: 45% / % of taxpayer awareness on tax education programmes: There has been consistent over-performance on this indicator through the programme duration: / 2008 Baseline: 70%. 2013 Target: 80%. 2013 Actual: 94% / % of written enquiries attended to within 7 days: There has been consistent over-performance on this indicator through the programme duration: / 2008 Baseline: 74%. 2013 Target: 95%. 2013 Actual: 96%
Recommendations: Reforming the customs business processes is one of the key challenges going forward. TRA has been searching for a long term and permanent solution to address shortfalls in its current ICT system (ASYCUDA ++) and has now procured a new bespoke customs system. Going forward, the implementation of this system and broader customs modernisation process should be a focus in TRA’s CP4. Based on international experience, the new customs system has the potential to generate efficiency gains of up to 2% of the value of imports i.e. at around $280 million per annum at current Tanzanian trade volumes. Risk management (indicator ii) is one of the many challenges that the new system seeks to tackle. The currently high channelling ratios require significant human resources to physically check declarations and documents and this approach is unlikely to provide value-for-money. In addition, there are also the costs incurred by traders. There is also the need for TRA to switch to a 24/7 shift operation to ensure that the new customs system generates the claimed increased trade facilitation. / As highlighted in an independent VfM audit on TRA’s procurement of the new customs system, it will be essential to ensure that the necessary project management skills are put in place for a successful roll-out. This may require non-TRA technical assistance. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 4: Promote Voluntary Tax Compliance
Output 4: final score and performance description: / Final results: A – Outputs met expectations. The output was composed of a number of indicators detailed below. Voluntary compliance levels in terms of taxpayers filing returns on time have fared well, despite the indicator having not met its target. Where taxpayers have not filed on time, TRA has performed well in following-up. / Average number of days taken to identify stop-fliers i.e. TRA’s speed in following up with taxpayers who fail to make a return on time. TRA has generally performed well on this indicator although the need to follow-up on so many stop-fliers is a drain on TRA resources. / DRD (Direct taxes) 2008 Baseline: 14. 2013 Target: 10. 2013 Actual 10 / DRD (Indirect taxes) 2008 Baseline: 5. 2013 Target: 5. 2013 Actual: 5 / Large Taxpayer Department 2008 Baseline: 3. 2013 Target: 3. 2013 Actual: 3 / % of taxpayers filing on time. A key measure of voluntary compliance is the % of taxpayers who file returns on time. In the 2012 DFID annual review, it was deemed that the target of 100% was unrealistic – a figure not achieved anywhere in the world. The target should therefore have been revised in previous annual reviews. Most countries can achieve, for VAT and PAYE compliance rates approaching 80%. TRA’s achievement of 85% for the end of the programme, through its credible and considerable efforts at taxpayer education, is deemed to be commendable However this indicator has been scored as under-performing on the basis of both not having met the target and that the actual end of the programme, performance was below the 2008 baseline. / 2008 Baseline: 90%. 2013 Target: 100%. 2013 Actual: 85%
Recommendations: TRA needs to continue with a clear strategy to raise compliance levels consistently. New ICT systems, such as e-filing (as planned under CP4) should help but must be accompanied by sufficient taxpayer education initiatives. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? N

Output 5: Enhanced staff performance management system
Output 5: final score and performance description: / Final results: A – Output met expectations although the integrity indicator has not been rated for reasons cited below. The output was composed of a number of indicators. TRA has performed well in related to its gender target on increasing the number of women in management/decision making positions. Although the indicator that attempts to capture the performance on integrity is not rated, there are a number of significant steps that TRA has been taking during CP3 to enhance integrity with the aim of reducing corruption. / Number of integrity cases handled by TRA’s Internal Audit Unit. TRA’s Internal Affairs Unit has expanded in size and is working well with many initiatives expected to make an impact on TRA integrity. During CP3, an Ethical Climate Assessment was conducted with its findings and recommendations presented to TRA’s Management Ethics Committee and Board of Directors. Further to this, Ethics Committees were established in 36 districts, 9 customs border stations and 11 Dar Es Salaam tax centres. TRA’s Internal Affairs Department has also conducted district level training on ethics and anti-corruption related reforms. However, this indicator is not rated as it does not give a credible/clear picture on the trajectory of improvements or deteriorations in integrity and/or the effectiveness in handling integrity cases. Indeed, it was determined in the 2012 annual review that a reduction in the number of integrity cases could either mean no corruption or during investigation. Furthermore, no target was also assigned for the 2013 end-programme point / 2008 baseline: 21 2013 Target: None stated. 2013 Actual: 11 – Not rated. / % of objectives met as per TRA Service Level Agreements. Low performance is attributed to the fact that targets were put in place on the assumption of particular systems being available. However, these systems were not established on time and hence manual operations have continued. Key systems have now been automated with effect from September 2013: / 2008 baseline: N/A. 2013 Target: 100%. 2013 Actual: 89% / % of female employees in management positions: / 2008 Baseline: 9% 2013 Target: 30%. 2013 Actual: 33%
Recommendations: Improving integrity in TRA will be critical going forward. Under CP4, strong focus should be placed on developing, disseminating, implementing and enforcing the Internal Affairs Department’s new Anti-Corruption Policy and Strategy. As part of this, it will also be essential to ensure that credible indicators are devised to measure performance improvements in improving integrity and reducing corruption. The implementation of modernised systems (i.e. e-filing and the new customs systems) should also reduce opportunities for corruption, whilst TRA has also mentioned plans for a scheme for tax consultants and tax agents, whereby they would only be issued with licences following mandatory training on ethics and professional standards. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? No / 1.2 Final Output score and description: / A – Outputs met expectations. / The overall output score is an A, calculated by three outputs scoring an A and two scoring a B. TRA has performed well in implementing CP3 with many targets being met and some significant areas of over-performance being achieved. However, there are three key performance related issues to note. Firstly, a few of the milestones and targets (extracted from TRA’s own M&E framework) are deemed to be aspirational (for reasons cited) rather than realistic i.e. output 2 indicator (i) and output 4 indicator (ii). This optimism bias is often seen across public sector programmes as a means to help drive performance. In these cases, targets for the programme were set beyond the reach of most and for some targets, all countries – not just Tanzania. Secondly, performance on some indicators during the life of CP3 has been inconsistent although end of programme targets have been met. These indicators have been scored green or yellow in cases where there has been significant under-performance in interim years. Keeping a watchful eye on consistency in these performance indicators to ensure that their results are sustainable will be important going forward. Thirdly, the indicators chosen for monitoring represent a narrow set compared to the wide range of initiatives under CP3. In future monitoring of TRA programmes, it would be useful to capture as a measure the % of initiatives implemented in the plan period to provide a broader sense of the pace of modernisation.
Direct feedback from beneficiaries / Direct feedback was obtained from TRA on areas where the rationale for under-performance was still unclear. This was deemed to be a sufficient approach to minimise transaction costs, noting that many discussions have taken place on the performance and challenges encountered under CP3 during the design process for CP4. This design process included a wide range of stakeholders from the district level all the way up to the TRA Board level. Direct feedback from taxpayers to complete this PCR was not obtained due to the high transaction costs that this would entail.
1.4 Overall Outcome score and description: / The outcome of the project was to provide an effective and efficient tax administration system which promotes voluntary compliance by providing high quality customer services with fairness and integrity through competent and motivated staff. Performance was assessed against a range of indicators culminating in an overall score of A – outputs met expectations. Despite revenue collection challenges, particularly from major parastatals, TRA only marginally missed its annual revenue target – by the equivalent of £52.8 million out of a total targeted £3.1 billion target – or phrased differently by 1.7%. Performance, as mentioned previously, on customs clearance times has been disappointing due to the slow roll-out of systems. However, success has been seen in areas such as the time taken to register taxpayers, which has supported the broadening of the tax base, and taxpayers perceptions of TRA’s fight against corruption. TRA’s costs in collecting revenue, a measure of its efficiency and organisational VfM, have not fallen by the targeted amount – by 1.1% rather than 1.7% but the performance trajectory is in the right direction. / Total annual tax revenues collected by TRA in relation to its annual revenue target. According to the economic forecasts during the Global Financial Crisis in 2008, the global recovery was expected to be slow-paced. Despite the expected positive signs of economic recovery in Tanzania, the impact of the global recession to various economic sectors resulted in sluggish revenue collection performance from the FY 2009/10 onwards. Despite this, it seems that milestones and targets were not revised and it is to be noted that TRA despite not meeting these ambitious targets did demonstrate resilience on revenue collection particularly during the crisis years of 2008/09 to 2010/11. It is also noted that revenue forecasts are generated by the Ministry of Finance and, as assessed in various independent studies, these forecast are often not seen to be highly reliable/accurate due to weaknesses in revenue forecasting capacity: / 2008 Baseline: Tsh 3465.8 bn. 2013 Target: Tsh 7871.4 bn. 2013 Actual: Tsh 7739.3 bn / Average time taken to clear goods at sea ports, border posts and airports. Refer to earlier explanation for output 3 indicator (i) on the slower than expected roll-out of modernisation systems: / DSM Port 2008 Baseline: No baseline detailed but data is 14 days in 2010 2013 Target: 5 days. 2013 Actual: 9 days / Airport 2008 Baseline: No baseline data detailed but data is 6 days in 2010. 2013 Target: 2 days. 2013 Actual: 3 days / Time taken to register taxpayers on TIN and VAT: / 2008 Baseline: 7 days. 2013 Target: 2 days for both TIN and Vat. 2013 Actual: TIN 1 day, VAT 2 days / Total revenue realised from audits/revenue collected: / 2008 Baseline: 12%. 2013 Target: 10%. 2013 Actual: 11% / Corruptions perceptions index. This indicator is taken from an infrequently conducted survey and measures the perception of stakeholders who consider TRA to be successful in fighting corruption: / 2008 Baseline: 9%. 2013 Target: None. 2013 Actual: None. Missing data in the interim years. However data points available suggest there was an improvement in the index from 9% in 2008 to 34.5% in 2010 and then a fairly commendable 43% in 2012. / Cost of collection as a % of revenue. The lower than expected revenue yield had a bearing on the average cost of collection. In the case of collecting taxes, it can be very cost effective to collect 80% of revenues from large taxpayers (at a cost of under 1%) but the marginal cost of collections is much higher. It is also noted that service improvements can be costly but yield little revenue aside from reducing private business costs: / 2008 Baseline: 3.8% 2013 Target: 2.1%. 2013 Actual: 2.7% / TRA managed to implement 95% of its planned major initiatives under CP3. This has been driven by its dedicated strong leadership, professional and accountable staff, the automation of operations and continuous efforts on capacity building. However, evidence from the log-frame highlights under-performance in reaching some of its targets, including in key areas such as revenue generation and customs clearance. Taking into account earlier comments on aspiration, rather than realistic target setting, the progress that TRA has made in implementing CP3 and in reaching or making good progress towards reaching its targets is commendable – an observation made by independent expert consultants when conducting the 2012 annual review. / Impact and Sustainability / The stated impact is tax revenue as a % of GDP. The results and evidence base suggests that whilst the impact target of 20.3% for 2013, again deemed to be highly aspirational over a 5 year timeframe, has not been met (2013 actual: 16.1% versus the Sub Sahara African average of 17%), strong progress has been made in reform areas which bodes well for this ratio going forward. Revenue is now considerably above the levels at the start of the project, showing a consistent upward trend year by year. This has been supported by a broadening of the tax base with strong increases in registered tax payers and; the automation of processes and modernisation of systems which are translating into steady improvements in voluntary compliance. CP3 has therefore considerably improved the function of tax administration and the benefits generated are likely to be sustained. However, challenges to ensure sustainability include a continued focus on capacity building/skills upgrading; continued introduction of modernised and more efficient systems; and improving integrity and taxpayer education. Ensuring that tax policy, led on the Ministry of Finance, is favourable and particularly tackling the issue of exemptions will also be important for sustainability and indeed the achievement of tax revenue to GDP targets. / In essence, capacity building of this type of nature should be viewed as a long-term process. TRA’s continued commitment, as reflected in the development of its fourth Corporate Plan (2013/14 to 2017/18) is therefore highly encouraging. CP4 attempts to address many of the on-going challenges identified under CP3. Reform initiatives are classified into 4 areas: i) Financial – with a focus on improving operational efficiency and increasing domestic revenue collection ii) Customer – with a focus on being a prompt, technology enabled proactive partner iii) Internal processes – with a focus on simplifying registration, assessment and payment processes, enabling administrative improvements and improving effectiveness in collection, accounting, audit, investigation and objections and iv) Learning and innovation – with a focus on improving strategic HR capacity, enhancing good governance and increasing ICT outreach and availability.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: / Yes. The MoU between DFID and GoT/TRA, signed in January 2010, committed DFID funding of £8 million between the 1st February 2010 and the 30th June 2013. In total, £8 million was disbursed in accordance with the agreed yearly profile detailed in the MoU. / 2.2 Key cost drivers / The programme was developed in 2009 without the key cost drivers being identified as this wasn’t required at the time. / 2.3 Was the project completed within the expected timescale: / Yes. CP3 had a total of 98 major initiatives. Up to the end of June 2013, 95 had been completed – a performance rate of 95%. The remaining 5 initiatives, which are at different stages of implementation, have been rolled over and incorporated into TRA’s fourth Corporate Plan which commenced on the 1st July 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / The programme was developed in 2009 without a written Theory of Change as this wasn’t required at the time. / TRA implemented 95% of its planned initiatives, a commendable performance. However some of the output indicators declined rather than approved. This would suggest that if a Theory of Change had been written, it would have had gaps which could have been filled with evaluations. / Also as mentioned previously, evidence suggested that a few of the programme’s targets which were drawn from TRA’s own M&E framework, were aspirational rather than realistic. DFID log-frame targets should have been adjusted to account for this optimism bias but this never happened. However in assessing DFID’s support for TRA’s fourth Corporate Plan, measures will be taken to ensure that log-frame targets are moderated to a realistic level of achievement. / 3.2 Set out what plans are in place for an evaluation. / No comprehensive evaluation of CP3 has been planned aside from TRA’s own CP3 Implementation Completion Report already available. However in the design for DFID’s support to CP4, currently underway, measures are being put in place to conduct independent mid-term and end-term evaluations. These should reflect long-term performance on tax modernisation efforts, including under CP3.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended / DFID funds were channelled through a multi-DP basket mechanism to TRA, which then used its systems to contract in technical assistance, goods and other services to implement the programme. / The Controller and Auditor General’s independent annual audits have issued unqualified/clean audit opinions for TRA’s Revenue Statements and Financial Statements throughout the duration of CP3. These / audits have captured a range of aspects including an assessment on whether the internal control system and accounting policies are appropriate to the circumstances of the TRA and that they have been consistently applied and adequately disclosed in the preparation of financial statements; an assessment of whether reasonable precautions have been taken to safeguard the collection of revenue; and an assessment on whether TRA has complied with the provisions of the procurement law and its regulations. / Furthermore, TRA was awarded the 1st prize for Best Presented Financial Statements for both 2010/11 and 2011/12 by the National Board of Auditors and Accountants in quality and conformance to the International Financial Reporting Standards (IFRS) under the Government institutions category. / In addition, TRA has also provided semi-annual Financial Reports on the programme’s implementation which have been discussed in the joint TRA-DP (including DFID representation) Joint Steering Committee. A special independent value-for-money audit, requested by DPs, was also conducted on the TRA’s purchase of a new customs system. This audit concluded that TRA had correctly followed international competitive tendering processes, consistent with World Bank guidelines, and had exercised the appropriate level of due diligence throughout the process. / Throughout the duration of CP3, the World Bank also provided their ‘no objection’ process on procurements. / On the basis of the above, evidence suggests that funds were used for their intended purposes. / 4.3 Climate and Environment Impact / The programme was developed in 2009 with the then required Environmental Screening Note (ESN) and as such there was no requirement to assign categories for risks, impacts and opportunities. However, there was no substantive change in the ESN assessment over the course of the programme. The programme therefore did not have any direct climate and environment impacts and there were limited climate and environment risks. However, as the programme helped improve revenue generation, this will have indirectly had a positive impact by supporting spending on environmental services such as water and sanitation. TRA has also introduced electronic filing and payment systems which have helped reduce taxpayer transport needs and thus carbon emissions. During the course of the programme, TRA also started to implement the Government’s policy to introduce a special excise duty on the imports of motor vehicles greater than 10 years old. This should also have helped to reduce carbon emissions

5. Value for Money
5.1 Performance on VfM measures / The programme was developed in 2009 without specific VfM measures being identified. However, the following VfM proxy measures, categorised under the economy, efficiency and effectiveness framework, can be identified to assess VfM performance. / Economy / Consultancy fee rates and compliance with procurement guidelines/procedures: To ensure VfM, TRA has prepared annual Procurement Plans throughout the duration of CP3. The World Bank has also applied its ‘no objection’ process to procurements to ensure both compliance to guidelines/procedures and VfM. At the time of the review, only one VfM audit on the procurement of a new customs system, was available – the results from which are outlined in section 4.2. / Efficiency / The cost of revenue collection can be used to assess TRA’s operational efficiency and thus its ability to provide VfM from a broad organisational point of view. This is also an indicator from the logframe at the outcome level. During CP3, cost collection as a % of revenue fell from a baseline of 3.8% in 2008 to 2.7% in 2013, therefore suggesting that efficiency gains had been made. / The implementation success rate of the programme can also be used to assess VfM. With 95% of initiatives implemented in the given timeframe, this is deemed to be highly commendable capturing TRA’s leadership, drive and operational efficiency. / Effectiveness / The effectiveness of the programme can ultimately be measured by the amount of additional revenue raised by TRA. Revenue increased from a 2008 baseline of Tsh 3465.8 billion to Tsh 7739.3 billion in 2013 – a 123% increase in just 5 years. In GBPs, this increase is equivalent to £1.7 billion, over 67 times the total investment from DPs (£25.3million from DFID, DANIDA and the World Bank). / Other supporting indicators, contained in the logframe, can also be used as they provide proxies for reduced compliance costs which are critical to delivering programme benefits. These include: / Average time to clear goods: As detailed earlier, there have been reductions in the number of days to clear goods at both the DSM port and airport but 2013 targets in both cases were missed. The poor results, at the port in particular, is an area on which the programme has not delivered VfM in a critical area. TRA attribute its lack of success here to the slow implementation of major initiatives such as the establishment of a new customs systems. / 5.2 Commercial Improvement and Value for Money / For indirect spend delivered via partner funding: / TRA, through its CP3 initiatives, have been taking active steps to improve their internal cost management with targeted efficiency gains reflected in their monitored cost of collection ratio. Initiatives have included the roll-out of major electronic systems across their work areas, in order to make the organisation modernised and more cost-effective. / Despite having clear plans in place, TRA has faced the widely known challenges of procuring through GoT systems thus resulting in execution delays. Whilst the World Bank’s ‘no objection process’ adds a degree of robustness to help ensure VfM, it has also unfortunately led to execution delays. / DFID has, alongside other DPs, continued to press VfM messages and TRA has shown a good degree of receptivity. / 5.3 Role of project partners / Achieving value-for-money lies at the core of TRA’s agenda, with the organisation showing both a good degree of understanding and commitment to the concept. More recently, they have demonstrated a strong receptivity to VfM auditing as evidenced by the independent audit on the new customs systems. Their ambition to drive lower their costs of collection, as evidenced by their continual monitoring of this statistic, reflects their efficiency drive. In addition to costs, they have focussed sufficiently on quality during CP3 particularly in relation to the quality of their taxpayer services – again, a core objective that has been regularly monitored. / A challenging issue which must be addressed by TRA going forward relates to staffing as modernisation and automation processes implies a reduction in staff numbers. A full review of staffing and structures is needed to better focus resources on higher yielding revenue areas, and thus deliver more VfM as an organisation. / 5.4 Did the project represent Value for Money : / Yes –The programme scores an A overall. The PCR demonstrates that TRA has performed well in implementing CP3 taking forward a plethora of wide ranging and challenging initiatives. However,, under-performance has been seen on targets in major areas such as revenue collections and customs improvements and these should be focal areas going forward into CP4. The collective DP (DFID, DANIDA and the World Bank) financial investment of £25.3 million to the basket fund which supported the implementation of CP3 has helped to generate a £1.7 billion increase in revenue – a multiple of 67 times – to finance essential public services.

6. Conditionality
During CP3, there were no concerns raised about the four partnership commitments that apply to financial aid.

7. Conclusions
A strong, efficient and equitable tax system is a crucial enabler for Tanzania’s development objectives, helping to mobilise more resources to address MDG service delivery issues and provide much needed supportive infrastructure for economic growth. Tax revenues provide an important ‘social contract’ between the state and citizens, encouraging the latter to exert accountability. Furthermore, an efficient, equitable and transparent tax system supports private sector development by lowering compliance costs and providing financial certainty to support investment decisions. Longer-term, increased tax revenues are necessary to reduce Tanzania’s reliance on foreign aid. / DFID and other DPs has responded well to Tanzania’s tax challenges by supporting a clearly identified need to assist TRA in modernising tax administration through the implementation of CP3. This has been of good value-for-money. The IMF has commended DP support for tax administration as “excellent over the past decade”. / The problems with the ambition level of milestones and targets in the DFID logframe (drawn from TRA’s M&E framework) have been detailed earlier. One of the key lessons going forward into CP4 is that whilst a DFID log-frame should ideally draw on TRA’s own M&E framework, it will be essential to ensure that milestones and targets are moderated to what DFID deems to be a realistic level of ambition, an observation also noted by the UK’s Her Majesty’s Revenue and Customs (HMRC). This will help better assess the genuine performance of the programme. Other key lessons to note are i) the continual need to ensure access to high quality technical assistance to implement TRA’s ambitious programmes and ii) the need to ensure that DP inputs – financial and/or technical – are coordinated to maximise synergies and avoid any contradictory messages.

8. Review Process
This PCR was conducted by DFID Tanzania’s Economic Adviser and Programme Officer for the Results and Aid Effectiveness team. It was largely desk based, drawing on a range of reports including TRA’s Implementation Completion Report of its Third Corporate Plan (2013); previous DFID Annual Reviews; the independent VfM Audit on the new customs system; the independent assessment on TRA’s procurement plans (2012); various Tanzania NAO reports on TRA. Consultations also took place with TRA on areas where the rationale for under-performance was unclear.