Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Building Empowerment and Accountability in Malawi (BEAM)
Programme Value: £24,957,729		Review Date: 31/03/2016
Programme Code: 200469	Start Date: 7/12/2010	End Date: 30/11/2017

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	NA	A	A+	A+	A
Risk Rating	NA	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
BEAM is a portfolio programme combining different projects contributing to the overall outcome. This Annual Review covers the fifth and penultimate year of operation of the Building Empowerment and Accountability in Malawi (BEAM) programme. From featuring 14 components in its original design, the programme has gradually been rationalised and was this year able to focus on the three components that deliver the greatest contribution to the BEAM objectives: the Tilitonse civil society governance fund, the Kalondolondo score-carding programme, and the support to Public Financial Management (PFM) reform through the World Bank’s PFM Multi-donor Trust Fund (MDTF). For the remainder of the programme it will primarily cover the Tilitonse civil society governance fund.

Performance has varied across the components. There has been strongest progress in the outputs supporting civil society’s ability to monitor service delivery and demand accountability and also good progress in investigating and prosecuting high-level corruption cases. Slowest progress has been seen in strengthening public financial management.

Tangible results in civil society’s ability to influence the quality of service delivery have been achieved at local levels, resolving specific service delivery problems. Influencing change at a systemic level continues to be more challenging. However, investment in a more issues-based approach that brings different actors together to influence policy-making has had some positive results in influencing the draft legislation on local governance, mining and access to information.

The quality of monitoring and governance arrangements in the different components has been variable and the lack of strong results framework in PFM has meant a reliance on measurement of outcome type indicators.

Summary of recommendations for the next year

- Risks need to be carefully managed in some areas – notably in 1) the setting up of a new civil society foundation to continue the TIlitonse grant fund work and 2) the implementation of the new IFMIS due to be procured.
- Any continuation of DFID Malawi support to PFM should be results-based and contingent on a strong monitoring framework. It should also be brought under a new Public Sector Reform Business Case.
- Documentation of lessons learned and sharing and dissemination of results to be prioritised in closure of Kalondolondo project and continuation of Tilitonse.
- The logframe should be amended to reflect that the support to Tilitonse will be the primary activity for the remainder of the project.
- A number of lessons learned are captured for taking forwards in future programming covering ensuring clarity in agreements (contracts, MoUs), governance arrangements and reducing programme management for DFID.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-200469/
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4429218.xlsx

Outline of the programme

The Building Empowerment and Accountability in Malawi (BEAM) programme was launched under a Programme Memorandum in 2010. It combines work on the ’demand side’ of governance - supporting citizen and community based projects that promote better information, monitoring and influencing of Government policies and programmes – with work on the ‘supply side’ – supporting selected Government or quasi-Government institutions to improve service-delivery and increase transparency and accountability. The total UK commitment to BEAM is £24,957,729 from December 2010 to November 2017. This includes a 17 month cost extension to the value of £4.5 million which was approved in June 2015. This was to facilitate a two-year contract extension with DAI/HTSPE which implements the Tilitonse component and therefore to provide sufficient time for Tilitonse to be established as an independent Malawian foundation as recommended by the Tilitonse board.

The expected impact of the programme is ‘more accountable, responsive and inclusive governance in Malawi able to support progress on off-track MDGs.’ The outputs are:

1. Civil society fund strengthens local organisations’ ability to promote access to information and monitor and influence policy
2. Government public financial management policies, procedures and practice strengthened
3. Capacity of National Integrity System assessed and civil society and Anti-corruption Bureau (ACB) capacity strengthened (not assessed in this review as activities completed in 2014)
4. Civil society community based monitoring strengthened

Since the launch of BEAM in 2010, the context has changed several times. In its first year, the programme operated in an environment of sharply declining governance with President Bingu Wa Mutharika’s government increasingly limiting the independence of accountability institutions and restricting the ability of citizens to exercise rights and freedoms. This changed with Bingu Wa Mutharika’s sudden death in April 2012 and transfer of power to Vice President Joyce Banda. As Head of State, Banda moved quickly to address concerns around economic management, political governance and human rights. Increased space for civil society and more freedom for the media to speak out returned, and relative stability ensued. However, during 2013 Banda’s leadership was increasingly being questioned and her position was weakened by the revelation of grand scale fraud and corruption involving public finances, popularly known as Cash-gate. Malawi held tripartite elections in May 2014 and Peter Mutharika emerged as the winner of the presidential ballot. The new government made a strong commitment to Public Sector Reform, including reforming the public finances. Addressing the weaknesses in the public finances however has been slow. There has however been a relatively strong commitment from the Government of Malawi to follow through on Cashgate corruption issues. This is in the context of deteriorating corruption indicators across the board (see accompanying data sheet), creating a very difficult environment within which to make progress on improving accountability of public resources.

BEAM is a portfolio programme which originally brought together a total of 14 planned components. Some components were in-design at its approval stage, some were short extensions to existing projects, and others were still to be fully defined. Throughout, BEAM has had to adapt to the changing circumstances while staying committed to achieving the overall impact of the programme. By the start of the current annual review period, the BEAM portfolio had been rationalised to concentrate on its three main components:

Component	Description	Contributing to output	Operational dates
Tilitonse	A multi-donor Civil Society Governance Fund (Tilitonse) combined with an Independent Impact Evaluation Agent (IIEA). The fund aims to strengthen civil engagement to support efforts to achieve greater public accountability and faster progress on development outcomes while at the same time contributing to the institutional development of civil society organisations (CSOs). This is a £19,654,267 programme with a DFID contribution of £13,617,857.	1	23/02/2011 – 30/09/2017
Kalondolondo	An Accountable Grant to a consortium of Plan Malawi, CONGOMA and ActionAid for a community based monitoring programme. The purpose is to ensure community participation in planning and budgeting processes at local district and national levels so that plans and budgets are more evidence based and reflective of the real needs of rural service users. The programme is solely funded by DFID with a budget of £2,480,015.	4	01/09/2011 – 31/03/2016
Public Financial & Economic Management (PFM) Reform	Contribution to a World Bank managed PFM Multi-donor Trust Fund (MDTF) supporting the Malawi Government’s Public Financial and Economic Management (PFEM) Reform Plan. The target budget for the PFM MDTF is $40 million and DFID’s contribution is £5,174,000. Contributing to the PFEM Reform Plan objectives but outside the MDTF, DFID has also a Cash-gate related forensic audit and is supporting investigation and prosecution of the corruption cases, with a total contribution of £1,251,664.	2	01/07/2011 – 30/06/2016

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome for BEAM is “Greater citizen voice and participation in governance with improved management of public resources”. It is measured by four indicators which combine results from the three main BEAM components, as set out in the table below. The project is on track to achieve the outcome of voice and participation, with considerable examples of improved management of resources at a local level. Improvements in public financial management at a national level have been insufficient to date. Significantly more progress is needed in getting the basics right.

		Milestone 2015	Result 2015
1	Improved scores in relevant Public Expenditure and Financial Accountability (PEFA) indicators	Improved PEFA scores in the four areas: / PI- 26 and 28 (external audit) / PI – 21 (internal audit) / PI – 22 (accounts reconciliation) / PI – 10 (budget transparency)	PI 26 and 28 – Both improved from D+ to C / PI 21 – Improved from D+ to C / PI 22 and 10: Not achieved
2	Number of documented cases of influence at national and decentralised levels on government and non-government actors achieved by BEAM programme partners / Tilitonse / Kalondolondo	Tilitonse – 1000 / Kalondolondo – 187	975 / 158
3	Number of people supported to have choice and control over their own development and hold government to account	250,000 (Tilitonse only)	642,169 / (cumulative 900,088)
4	Quality of cooperative activity (Tilitonse) / Extent to which cases demonstrate a strategic approach to partnerships / % of funded project respondents that say they have a ‘strong’ working relationship with Government officials / # of cases that demonstrate improved collaboration between CSO/citizens, government stakeholder and/or private sector actors	Most > ¾ if cases / 50 (Open call 1) / 25 (Thematic call) / 50 (Open call 2) / 7 (of 12) and 2 (of 5 CBOs)	IIEA Endline survey data not complete – Final report due June 2016.

- Outcome indicator 1 - Improvements were seen for 3 of the 5 of the Public Expenditure and Financial Accountability (PEFA) indicators (PI 26,28,21) being measured at outcome level above. PI-10 and PI-22 were not formally assessed. However based on World Bank Aide-Memoires and Government of Malawi (GoM) progress reports, PI-22 was not achieved because the main GoM bank account (MG1) has still not been fully reconciled. Budget transparency indicators both for PI-10 and PI-24 although not assessed during the Mid-Term Review (MTR) of the Financial Reporting and Oversight Iimprovement Programme (FROIP), have not been achieved because the published GoM data does not reach the standard set in the PEFA framework. The DFID logframe does not include key PEFA indicators (18,20,25) measuring payroll controls, compliance with rules and accounting, recording and reporting which were assessed in the World Bank MTR of the FROIP programme. These three have all deteriorated. As that report says “it is a common knowledge that PIs 18, 20 and 25 are fundamental to any PFM system such that achievements or improvements in others cannot compensate for their deterioration.”
- There was progress in terms of documented cases of influence at national and decentralised levels. The target was narrowly missed, partly as a result of the phasing out of a number of CSO grants in 2015 (Outcome indicator 2).
- Outcome indicator 3 substantially surpassed the target. This was as a result of the specific window of support to community based organisations under Tilitonse that more directly reach out to ordinary citizens and the mass media campaign by the Centre for Multiparty Democracy which reached large numbers of people.
- No data is yet available for Outcome indicator 4

Overall output score and description

The output score of the programme is A on the basis that:
- Output 1 with an impact weighting of 45% scored A+
- Output 2 with an impact weighting of 33% scored B
- Output 4 with an impact weighting of 22% score A

Output 1: Output 1 ‘Civil society governance fund strengthens local organisations’ ability to promote access to information and monitor and influence policy’ scored A+
The achievement of the milestone for Output indicator 1.1 exceeded expectation with Tilitonse grantees developing 207 information products against a milestone of 180. For Output indicator 1.2, a total of 1,281,937 have been informed about their rights to public services, less than the planned the milestone of 1,550,000. Output indicator 1.3 was below expectation achieving 498 representations to duty bearers against a milestone of 600. For Output indictor 1.4, a total of 23 innovative practices developed by Tilitonse grantees were adopted by other CSOs or agencies outside Tilitonse, against a milestone of 20.

Output 2: Government public financial management policies, accountabilities, procedures and practice strengthened’ scored B. The progress against the Public Financial Management (PFM) milestones fell short of expectation. However there was good progress on investigating and prosecuting high-level Cashgate corruption cases. The National Aufit Office (NAO) audit reporting is not on track and the legislative proposals (last year’s milestone) are yet to be tabled in parliament (Indicator 2.1). There has not been an improvement in the PI 24 (in-year budget reporting) and the score for annual financial statements (PI 25) has deteriorated since the last PEFA assessment (Indicator 2.2). There has been some progress in terms of the procurement of an Integrated Financial Management Information System (IFMIS). The GoM has now reworked a fully funded IFMIS budget and now (awaiting budget resubmission to the Bank before the WB can a no-objection) but the process is delayed (Indicator 2.3). Indicator 2.4 (scale and nature of Cashgate cases established) has met expectation and the progress in Cashgate investigations (2.5) has exceeded expectations with successful plea bargaining having been undertaken and five more convictions obtained.

Output 4: Civil society community-based monitoring strengthened’ scored A
Cumulatively 90,638 people have participated in Kalondolondo score-carding, exceeding the milestone of 50,000 for Output indicator 4.1 by 80%. In terms of Output indicator 4.2, there have been 57 instances where the allocation of resources has changed as a result of the programme, against a milestone of 35. For output indicator 4.3, 174 agreements have been recorded between service providers and service users to improve service delivery, against a milestone of 100. While the cumulative totals for these three indicators are significantly higher than the targets, given the annual results for the programme in 2015 and the triangulation with monitoring of reports and field visits, this output is judged to have scored an A and not an A+ as a simple reading of the figures above might suggest.

Key lessons

National versus Local
The Tilitonse shift to funding more community based organisations (CBOs) from a focus on national CSOs/ NGOs has been successful at the local level with examples of tangible results in improving service delivery at service centres. Local organisations’ performance has positively compared to that of national Civil Society Organisations (CSOs) with much greater experience and capacity. The limitation of this approach is the reduced capacity to influence at a national level. Across the Tilitonse results framework, the indicators for informing and engaging citizens at a local level have surpassed expectations as a result of this shift. However the indicators for influencing policy and delivery, based on formal social accountabiltiy tools, have generally achieved less than was expected as some of these national level grants phased out. This shift to CBOs is countered to an extent however by the support to coalitions of organisations at national and local level around specific issues, namely mining, access to information and monitoring of local governance funds These have had promising results and some CSOs who have received grants under this thematic window have reportedly performed better working in coalitions than when they received individual grants under the first or second Open Calls.

Breadth versus depth of score-card monitoring
The Kalondolondo brand is well-known across the country and widely cited very positively. Its presence across all districts in the country has enabled it to address issues at scale, different from many other community score-card initiatives. This has enabled comparison between performance in different regions and at a national policy level. For example, comparing the performance of the regional Water Boards has created peer pressure for improvement and the Light-a Health-Centre Campaign resulted in the Ministry of Energy donating solar systems across the country. Although community assessments do result in action plans that are monitored by local actors, the geographical breadth and the addressing of different issues each year does mean that there is not ongoing monitoring of specific service delivery over time, making it difficult to sustain influence and track change. Lack of sectoral expertise (for example in health) could also limit their effectiveness. The limited investment in documentation of the Kalondolondo approach could affect the sustainability of the outcome.

Monitoring and communication of results
Both Kalondolondo and Tilitonse could pay more attention to communicating and disseminating results from investment. An out-of-date website in the Tilitonse case and absence of one in the Kalondolondo case make it difficult to access information about what has been achieved and lessons learned. Tilitonse has been focusing on getting internal information systems in place at the expense of communicating externally. Capturing results from community initiatives is challenging. Greater investment in monitoring and evaluation capacity in the case of Kalondolondo would have been beneficial. The lack of monitoring and evalution capacity in FROIP continues to be an issue.

Media
Effective use of the media at national and local level has been a critical factor in supporting citizens to demand accountability from duty-bearers. The Kalondolondo project has been particularly adept at using national media to highlight local issues and get positive responses. The response of the Central Region Water Board to the severe water quality problem in Dwangwa is directly related to the extent of the media coverage achieved.

Commitment to Public Financial Management (PFM) reform
There continues to be a lack of high-level commitment to improving Public Financial Management. Without this, it will continue to be difficult to make real progress in the way the public finances are managed in practice. The bulk of the PFM project is now focused on procurement of a new IFMIS system (i.e. a technical and therefore a partial solution). The political and human dimensions that are inherent to the weaknesses in public financial management controls need to be paid more attention. While the current IFMIS is outdate, its replacement is only part of the solution. It is suggested that a more coordinated and problem-driven approach by donors could provide more pathways for improvements.

Key actions and recommendations (Capturing all recommendations detailed in the report)

Future civil society foundation
Tilitonse donors and the Board should draw up a risk matrix for the process of setting-up of the new foundation and mitigation measures by June 2016. Risk areas include handover of knowledge, systems, and processes; fiduciary risks; insufficient engagement of the Secretariat team; communication to the public, conflict of interest mechanisms and institutional memory of some board members and mechnaisms for donor engagement on strategy that need to be managed.

Tilitonse
- Tilitonse should significantly increase dissemination and communication of results, case-studies and lessons learned. This should be part of a lesson-learning and influencing strategy (influencing other CSOs as well as duty-bearers). This should include improving the website and ensure that all case-studies, project briefs, grantee profiles are linked from the Grants Management Information System (GMIS) to the website for public access.
- The Board should urgently take a decision about how the outcomes and impact of Tilitonse will be measured for the extension phase and ensure swiftly actioned to avoid what will be significant gap in the monitoring and evaluation once ITAD completes its current work in June 2016.
- Tilitonse should build on experiences to date supporting communities of practice and lesson learning around issues to increase sharing of experiences and strengthen linkages between CBOs and CSOs.
- Tilitonse should consider whether it needs additional technical governance support within the team or within its mentoring network to support technical capacity of the grantees in working on governance programming

Kalondolondo
- DFID to engage with the final evaluation of the project (commenting on Terms of Reference, selection of consultants and draft report) to ensure a quality output.
- The consortium led by Plan Malawi should allocate additional technical capacity to ensure effective documentation of lessons learned during the final stages of the project.

Public Financial Management
- DFID to remain continuously engaged with the Government of Malawi on strengthening Public Financial Management. If insufficient progress is made, a review by the World Bank in March will likely recommend the project is not extended beyond June 2016. If an extension is agreed, DFID should request that this be on the basis of Performance by Results.
- The MDTF donors should carefully manage the risks associated with the IFMIS procurement and implementation. DFID has communicated clearly to the GoM the risk of losing DFID’s funding for IFMIS, if funds are not committed prior to 30th June 2016. The GoM has now addressed tthe IFMIS funding gap both by reprioritising funds from within the FROIP budget and by confirming their its own funds to fill the gap. Even if funds are committed before the end of June, it is highly unlikely that the procurement process will be complete by then. Given this, an extension to the project, even if only limited to oversight of IFMIS implementation could be considered.
- If the FROIP project continues beyond the scheduled end date of June 2016, it is recommended that DFID revise the PI 24 which focused on in-year budget reporting and replaces it with PI-25 that relates to accounting and financial reporting throughout the year. This will mean changing the outcome and output indicator to PI-25 in the coming year.
- FROIP donors should take the lead to improve donor coordination on PFM issues, take a more problem-driven approach and rationalise engagement with the Government of Malawi given the transaction costs the Ministry of Finance incurs in dealing with multiple donors individually.

Anti-corruption
- Core investigating and prosecuting agencies (ACB, Directorate of Public Prosecutions, Malawi Police Service and Financial Intelligence Unit) should institutionalise inter-agency coordination and collaboration mechanisms in investigations and prosecutions, so that future effective coordination is not depending on individuals.
- ICAR consultants should strengthen mentoring and on-the-job training for staff within the ACB, DPP and Fiscal Police to broaden and deepen expertise within the state institutions.

Programme management issues
- As Tilitonse will be the majority component of BEAM from here on, DFID should realign its annual review timing with the Tilitonse annual report cycle which is produced in April. It is recommended that a very light-touch annual review is carried out in August/September 2016 to to align with the Tilitonse reporting period on the DFID system for the next annual review. This will also allow for capturing of the final Kalondolondo reports and evaluation.
- The weightings of the different outputs of the BEAM log frame should be revised to reflect the remaining components after the light-touch annual review. Additional indicators shoudl be added under Output 1 to capture more of the investment in Tilitonse.

Learning for future programming
- DFID to learn from the challenges associated with reporting in a portfolio approach log frame in future programming and consider alternative ways of capturing complexity of results.
- DFID to ensure sufficient budget allocated for monitoring and evaluation in future accountability programming.
- In future programming, DFID should consider a limited budget to support some operating costs in the Law Enforcement Agencies, within the limits of existing restrictions around providing financial aid to public bodies in Malawi, and adapt the delivery mechanism to reduce DFID management time for this component.
- DFID should avoid requesting additional parallel reports with different templates from partners, which appears to have stretched capacity and resulted in inconsistencies in data. Rather DFID should focus on ensuring partners’ own reports are the best quality possible and that the information reported is robust.
- In future, DFID should explore ways of reducing DFID project management time for supporting law enforcement agencies though for example a single accountable grant or contract.
- DFID to ensure MoUs exist with the respective GoM institution in all cases where technical assistance is being provided. Provision for periodic revision should be built into the MoUs to allow for the work to be responsive to the context.
- DFID to ensure clear lines of accountability with Accountable grantees in all programming and ensure effective project governance arrangements are in place.

Has the log frame been updated since the last review?
The BEAM log frame was updated in November 2015 to reflect changes to the programme context as recorded in Quest document number 5333587. The revised log frame was approved by the BEAM SRO on 17th November 2015. Revisions included minor adjustments to the weighting to adjust for the now zero weighting of Output 3; addition of milestones to reflect the extension of the Tilitonse, Kalondolondo and ICAR projects. Impact, outcome and output indicators themselves remain unchanged.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Civil society governance fund strengthens local organisations’ ability to promote access to information and monitor and influence policy (Tilitonse)
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone for 2015	Progress
1.1 # of information products developed in funded projects	180	207
1.2 # of people informed through funded projects about their rights to public services	750,000 men / 800,000 women / 1,550,000 Total	498,107 men / 780,624 women / 1,281,937 Total (cumulative)
1.3 # of representations based on monitoring initiatives made to traditional leaders, officials responsible for public service delivery	600	573
1.4 # of practices and issues promoted by CSO grant partners that are adopted by other CSOs and development actors	20	23

Key Points
The achievement of Indicator 1.1 for 2015 exceeded expectation, partly as a result of the increase in the number of grants to CBOs. Information products included radio shows, publishing of leaflets, posters, manuals, translated copies of Local Development Fund guidelines into local languages and printing of t-shirts. While the latter are appreciated by citizens, the strategy of printing t-shirts for communicating messages is limited, if not part of a multi-pronged communication approach.

The number of people informed about their rights (Indicator 1.2) did not meet the target. A total of 133,929 people have been informed about their rights to services. People are infomed using a varietry of different methods, including for example community meetings and radio programmes. This is a cumulative result of 1,281,437 missing the target by 17%. This was due to fewer CSOs carrying out mass-media campaigns that were captured under this indicator than in the first year of the project. There is a strong overlap between this indicator and outcome indicator 3 which also measures numbers of people informed about public services. Outcome indicator 3 conversely very substantially exceeded the target. The numbers are not added together to avoid double reporting although combined, this indicator and Outcome 3 can be considered to be both met.

This indicator (Indicator 1.3) captures the # of representations to officials made based on formal social accountability tools (e.g. score-cards, service charters) which are generally used by national level civil society organisations, many of whose grants phased out in 2015. Increased funding to CBOs during the period of this annual review has resulted in increased representation to officials at a local level - however these are not captured in this indicator. They are generally based on community meetings rather than formal accountability tools and are captured under another indicator in the Tilitonse logframe which measure the “Number of dialogue initiatives aimed at influencing service delivery behaviour policies, strategies and resource allocations”. Achievements have substantially exceeded the target in this indicator with 276 dialogue initiatives achieved against a target of 80 (Quest 5374904).

There have been five examples of innovative practices this year adopted by other organisations giving cumulative total of 23 (Indicator 1.4). For example KADEC and NAYODE developed simplified and customized project score-cards. Rumphi Residents Association went on an exchange visit to KADEC where they learnt how to track development issues using the simplified score-card system. They adopted and incorporated this system into their own programming. Another example is the adoption by Genesis Manja Othandiza of a tool kit used by Water for People to build capacity of Water Management Kiosks.

To date Tilitonse has provided grants to 74 civil society organisations in Malawi. Of these, 26 grants have been provided to CBOs – a funding window which ran initially from August 2014 to August 2015. Despite capacity constraints of local organisations, in many cases the results from these direct grants to CBOs have had greater impact at local level than previous grants to larger CSOs. Both the Secretariat and the Board were positively surprised by the performance of the CBOs. 75% of those that received grants have had their grants extended. The legitimacy and embeddedness of local organisations in their community are seen to be key factors in success.

The Tilitonse Secretariat have shown their ability to be adaptive and learn by doing. Initial capacity development to CSOs was provided through traditional training approaches. Given disappointing results and given the pressures to support a larger number of small and dispersed community based organisations, they switched to a mentoring approach. This has increased the cost of the capacity building component but has had good results. The support on project cycle and financial management was greatly appreciated by local and national grantees visited as part of this annual review. There is limited technical governance capacity within the secretariat and the majority of capacity development has focused on project management rather than on technical governance issues.

Tilitonse has also adapted its approach to try and embed political economy analysis and Theory of Change thinking into grantees project design. CSOs/CBOs were initially daunted by the jargonistic and academic language. Tilitonse adapted their engagement with grantees, simplifying language and complementing workshop sessions with mentoring. The Polical Economy Analysis (PEA) “reports” produced have been used primarily to influence decisions around which thematic areas to fund. The researchers however have also been used to mentor grantees on technical governance issues related to service delivery.

Learning between grantees has increased, with Tilitonse facilitating some learning events (e.g. on mining) and bringing different organisations together working on similar issues from different regions. One CBO visited in the north of the country as part of this review considered this connection with others to have been critical . There is scope to do more on learning and joint working, particularly given the lack of immediate linkages between potentially isolated CBOs and the challenge CBOs have influencing national level decision-makers.

The thematic financing windows have however brought local and national organisations together around more focused issues. They have resulted in more coalition-building between organisations around mining, local governance and access to information. There has been positive influencing of draft legislative bills (Mines and Minerals Bill, Local Governance Bill, Access to Information Bill) and effective collaborative working between CSOs and the government. In the case of local governance, the Tilitonse-funded coalition also brought in other organisations that were not Tilitonse grantees into the group.

Summary of responses to issues raised in previous annual reviews

- The revised Tilitonse log frame was approved on the 2nd November 2015 by the Tilitonse Board. The delay from what was originally recommended (April 2015) was as a result of needing to wait for the final decision on the extension of Tilitonse until September 2017. The BEAM selection of a few Tilitonse logframe indicators still results in a reductionist view of progress as can be seen with indicator 1.3 above.
- Progress has been made on the GMIS with all board members now having access to all case study documentation and reports on the management system. There is still need for progress on disseminating of lessons learned more broadly, including through the website.
- The anti-fraud policy is now widely disseminated with both radio jingles and messages on TV. The website also carries information on fraud policy and how to report fraud. As recommended by legal advisers, grants agreements carry clauses on how fraud will be treated and that partners are bound to pay back in the event of fraud. M&O associates who are managing the finances have brought on board more people to support the carrying out of frequent checks and invetistgations.

Recommendations

- Tilitonse should significantly increase dissemination and communication of results, case-studies and lessons learned. This should be part of a lesson-learning and influencing strategy (influencing other CSOs as well as duty-bearers). This should include improving the website and ensuring that all case-studies, project briefs, grantee profiles are linked from the GMIS to the website for public access.
- The Board should urgently take a decision about how the outcomes and impact of Tilitonse will be measured for the extension phase and ensure swiftly actioned to avoid what will be significant gap in the monitoring and evaluation once ITAD completes its current work in June 2016.
- Tilitonse should build on experiences to date supporting communities of practice and lesson learning around issues to increase sharing of experiences and strengthen linkages between CBOs and CSOs.
- As part of the establishment of the new foundation, the Board should consider the need for in-house technical governance capacity.
- DFID Malawi should revise the logframe to reduce the overlap between Outcome indicator 3 and Output indicator 1.2 and amend Output indicator 1.3 to capture different kinds of representation already being measured by the Tilitonse project.

Output Title	Government public financial management policies, accountability, procedures and practice strengthened
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Independence of the National Audit Office	NAO Audit reporting on track	Not achieved: NAO audit reporting is not on track. The expectation was that legislation would already have been passed at this stage. The project has developed the technical legislative amendment proposals but the presentation to parliament has been delayed. Presenting, discussing and approving the proposals is mainly a political process which donors can only seek to influence.
2.2 Quality and timeliness of in-year budget reports	Improved PEFA PI 24 score	Not achieved. In-year budget reports (PEFA Indicator 24) has not been achieved because the published GoM data does not reach the standard set in the PEFA framework.
2.3 IFMIS roll-out and update	IFMIS operational in local and national local government	Not achieved. A decision was made to buy new application and procurement is in progress. If the World Bank maintains its oversight role over the procurement process, the indicator will be achieved. However, project is scheduled to end in June 2016 and there is a risk the procurement may not be completed before that date.
2.4 Scale and nature of Cashgate fraud and corruption established (covering April to September 2013)	59 case files (cumulative) handed over to investigation agencies	Achieved: 59 case files were handed over to investigation agencies in May 2015.
2.5 Progress of Cashgate investigations	A number of high-level facilitators and end beneficiaries are convicted and asset recovery mechanisms (international and domestic) are used more effectively to recover stolen assets.	Achieved: 5 more convictions obtained including those of two major facilitators – Oswald Lutepo and Leonard Kalonga. Asset recover efforts are underway with a joint-agency taskforce in place.

Key Points

Independence of the National Audit Office
Legislative proposals that would increase the independence for the NAO have been developed but still not tabled in parliament. It is hoped that these will be tabled in June 2016. Proposed amendments seek to address the political, financial and administrative angles of NAO independence. The project was designed to develop the technical proposals and in that regard the project has achieved its objective. DFID and other donors are continuously seeking to influence political and technical stakeholders such as members of the Public Accounts Committee and Senior Civil Servants to move the legislative process forward.

As of 30 January 2016, further amendments were being made to the 2014/15 financial statements by the Accountant General before being handed over to the NAO for auditing. Statutory deadline for submission of financial statements to the National Audit Office was 31 October 2015 and completion of 2014/15 audit was by law required to be by 31/12/2015. Government requested more time of up to April 2016 to submit FY2014/15 financial statements to the Auditor General. The audit will not be completed before 30th May 2016. The Treasury is currently awaiting audit opinions for the FY 2012/2013 and 2013/14 financial statements. They were submitted to the Auditor General by the Ministry of Finance in September 2015. The delay in the provision of audit opinions is an indication of the ongoing capacity challenge faced by the Auditor General’s office.

Quality and timeliness of financial reporting:

The log frame indicator refers to PEFA Indicator 24 which relates to in-year budget reports. A formal PEFA assessment is only due in 2016 and as this indicator was not reviewed by the World Bank’s mid-term review an assessment was done internally by the DFID advisor. Not all statutory reports are currently being published. The quarterly reports are published well outside the 8 weeks after the quarter they relate to and the quality of information is not sufficiently detailed to allow analysis of budget performance. The quarterly reports have limited data showing aggregate levels for revenue, recurrent expenditure, development expenditure and donor contributions. It is not possible to view expenditure performance at Vote/ministry level and therefore it is not easily comparable with estimates. Based on the PI-24 criteria it is fair to assess PI-24 at level D because of the poor quality and late release.

The World Bank however in its mid-term review of FROIP (September 2015) did assess PEFA Indicator 25 which refers to the quality and timeliness of annual financial statements. This had declined from a C+ in 2010/11 to a D+ in 2014/15. As of January 2016, the financial statements from 2014/15 (due at end of October 2015) had not been presented to the auditor general. The Government of Malawi proposes to present these in April 2016. The financial statements for 2012/13 and 2013/14 were only presented to the auditor general in September 2015.

IFMIS roll-out and update
The evaluation of bids for the procurement of a new IFMIS system has been completed. An agreement was reached (02/03/16) to reallocate resources from lower priority items within the FROIP budget to bridget the funding gap. A World Bank no-objection should now be forthcoming to allow the procurement process to proceed. Further delays need to be avoided. Donor funds are only available in the MDTF until June 2016 when the FROIP is scheduled to end. If no contract is put in place for securing the IFMIS package by June 2016, donor resources will no longer be available to the GoM for the IT package. If this were to occur, DFID will request refunds of its uncommitted funds in the MDTF in accordance with agreement with the World Bank.

Overall performance of FROIP

The World Bank mid-term review show that while there have been some improvements in internal and external audit (both internal and external audit PEFA Indicators met their target of a C); there are still fundamental challenges in the basics of Public Financial Management. These include accounting and reporting as noted above, payroll controls and overall compliance with rules – and sanctioning for lack of compliance. The ongoing backlog of unreconciled items continues to undermine reporting. The backlog of the bank reconciliation from 2010 to 2014 has now been contracted out to independent auditors and the Accountant General’s office is handling January to December 2015 themselves. The subcontracting is in line with the World Bank’s MTR recommendations

With regards to audit, there is now additional technical and human resource capacity in the National Audit Office to undertake statutory audits. On internal audit, Independent Audit Committees are now active and have started holding Controlling Officers to account by scrutinising and following up audit reports. However they still have challenges to be fully functional due to funding challenges.

An ongoing problem appears to be lack of clarity about where the leadership and drive for PFM lies in the Ministry of Finance. A GoM PFM Action Plan existed but expired in June 2015 and has not been renewed and is not being monitored. While it was primarily a short-term plan, many of the actions from the action plan are still relevant.

Donor coordination around PFM continues to be weak and there are a number of projects beyond FROIP. There is no effective sector-wide group that is discussing PFM issues across the sector rather than progress of individual projects. Poor donor coordination and numerous demands for bilateral meetings, is making engagement with donors very transaction-heavy for the Government of Malawi.

Anti-corruption
A total of 59 case files – each relating to a different company – were handed over to the Malawian law enforcement agencies in 2014 and 2015. These case files have formed the basis of the Cashgate investigations and continue to be used to pursue those believed to have been responsible. To date, there have been 11 Cashgate-related convictions, of which 8 have been sentenced. Approx. K200m of assets have been recovered, representing 2-3% of the roughly K8bn stolen during Cashgate (Baker Tilly, Sept 2015). While still relatively low, asset recovery actions are ongoing and more than K1.5bn is currently under scrutiny for recovery.
[note] The figure for total losses in the Baker Tilly reports rises to over K15bn when taking into account non-Cashgate related fraud.

The technical assistance that has been provided to the Anti-Corruption Bureau (ACB) and the Directorate for Public Prosecutions (DPP) has resulted in a number of important advances in taking these cases forwards. The DPP described the support on prosecutions as “the difference between success and failure”. Guidelines for prosecutors on plea bargaining were adopted in May 2015 and these have since led to a number of guilty-pleas. This is viewed both by the ACB and the DPP as a major step forward in addressing such cases.

Inter-agency cooperation between the DPP, Financial Intelligence Unit (FIU), the Fiscal Police and the ACB has improved from a low base, although there is still scope for improvement. Joint investigations are now happening between the ACB and the Fiscal Fraud Unit with support of the DFID funded technical assistance (TA), and joint prosecutions between the ACB and the DPP.

There is evidence of the TA’s transferring skills and knowledge to the teams in the ACB and the DPP, primarily through mentoring and on-the-job learning. There is scope to widen and deepen that mentoring to a broader group of people. Resource constraints within both these institutions have been an obstacle for basic operations at times, such as costs of fuel to carry out investigations. The embedded TA has helped to identify specific additional technical gaps – e.g. digital data recovery and civil litigation - which DFID has responded to. The flexibility of the individuals and of the BEAM programme to respond to unforeseen needs has been crucial.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID requested a number of times that the World Bank carries out a PEFA assessment during 2015. This was originally planned for August 2015. Given that the PEFA framework was being revised, it was then decided to wait until the new framework was launched. A PEFA assessment is now planned for February/March 2016 and the assessment will be led by the World Bank.

After DFID and other donors successfully lobbied to have a World Bank technical expert stationed in Malawi in the last financial year, DFID has led the demand for more outcome/impact based reporting from the Programme Management Unit, moving away from reporting on activities. PMU have started to report on outcomes and impact, but the quality of reports is not yet satisfactory. There is currently no M and E capacity within the PMU and no monitoring and evaluation framework. This is a serious concern which has not been addressed. There are regular monthly PFM donor coordination meetings under the World Bank Chair. These meetings are also informing discussions at the Heads of Mission level and Group on Financial and Economic Management (GFEM) meetings. The MDTF donors have also been demanding greater transparency in the way the World Bank is using the Trust funds. For example, contributing donors have played a much greater role in scrutinising the Project Work Plan resulting in removal of non-core activities from the budget. While the result of this has been positive, it has been transaction heavy for DFID.

As per the recommendation from last year’s annual review, the log frame was revised to include an indicator capturing the work being carried out by the International Centre for Asset Recovery (ICAR) to support the ACB and the DPP on Cashgate investigations.

Recommendations

- The MDTF donors should carefully manage the risks associated with the IFMIS procurement. DFID should communicate clearly to the GoM the risk of losing DFID’s funding for IFMIS, if funds are not committed prior to 30th June 2016. The GoM should ensure the funding gap is filled both by reprioritising funds from within the FROIP budget and by allocating additional funds to fill the gap. Even if funds are committed before the end of June, it is highly unlikely that the procurement process will be complete by then. Given this, an extension to the project should be considered, even if only limited to oversight of IFMIS implementation. (An extension to the project is currently contingent on the GoM making sufficient progress against the mid-term review targets. If this progress is not achieved, an extension limited to oversight of IFMIS procurement and implementation could be considered).
- If the FROIP project continues beyond the scheduled end date of June 2016, it is recommended that DFID revise the PEFA Indicator 24 which focused on in-year budget reporting and replaces it with PI-25 that relates to accounting and financial reporting throughout the year at outcome level. The DFID Governance team should explore devising output indicators relating to the PFM work that are more attributable to the World Bank’s proposed workplan by June 2016
- FROIP donors should take the lead to improve donor coordination on PFM issues, take a more problem-driven approach and rationalise engagement with the Government of Malawi given the transaction costs the Ministry of Finance incurs in dealing with multiple donors individually.
- Core investigating and prosecuting agencies (ACB, DPP, Malawi Police Service, and FIU) should institutionalise inter-agency coordination mechanisms, so that future effective coordination is not depending on individuals.
- ICAR consultants should strengthen mentoring and on-the-job training for staff within the ACB, DPP and Fiscal Police to broaden and deepen expertise within the state institutions.
- In future programming, DFID should consider a small budget to support limited operating costs in the Law Enforcement Agencies, within the limits of existing restrictions around providing financial aid to public bodies in Malawi, and should adapt the delivery mechanism to reduce DFID management time for this component.

Output Title	Capability of National Integrity System assessed and civil society and ACB capability strengthened
Output number per LF		3	Output Score	N/A
Risk:		Medium	Impact weighting (%):	0%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

The programme areas that contributed to this output were Support to the National Integrity System, Support to the Civil Society Platform and Institutional support to ACB. These were completed by the end of the 2013 Annual Review with a final score of B. This output no longer carries any impact weighting.

However, DFID received an evaluation for the final support to ACB in June 2015, within this AR period.

The programme areas that contributed to this output were Support to the National Integrity System, Support to the Civil Society Platform, and Institutional Support to ACB. These were completed by the end of the 2013 Annual Review with a final score of B.  This output no longer carries any impact weighting. However, in June 2015, (i.e. within this AR period), DFID received an independent evaluation for the final package of support delivered to the ACB between March 2013 and March 2014, of which the first six months was funded by DFID and the second six months was funded by the Royal Norwegian Embassy.

While the independent evaluation noted that the majority (>90%) of the project’s planned activities were completed or partially completed, it highlighted a number of concerns with regard to how the project was conceived and implemented which limited its impact. It noted that some of the activities undertaken were not linked to changes in performance, or were modified in such a way that they were no longer beneficial; that technical and financial reporting by the ACB was often inconsistent, raising concerns about the proper use of DFID funds; and that poor budgeting meant that some activities were underfunded while the project as a whole underspent. The evaluation made a series of recommendations centred on improving both DFID’s oversight of funds provided to the ACB and the ACB’s capacity to manage those funds and report against progress, in the event of any future support.

DFID has not provided any financial assistance to the ACB since November 2013, when all funding through Malawi’s public financial management systems was frozen in the wake of the Cashgate revelations. Since November 2013, DFID support to the ACB has taken the form of an embedded technical assistant, with additional procurements of hardware and short-term expertise undertaken directly by DFID. This model has delivered significant success, as outlined above, and will be built on and developed as part of DFID Malawi’s forthcoming anti-corruption programme, with efforts made to reduce the DFID project management time required to manage multiple contracts.

Output Title	Civil society community-based monitoring strengthened
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	22%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number of people participating in score-carding	50,000 (cumulative) / 20,000 (annual)	96,037 (cumulative) / 19,267 (annual)
Number of instances where the allocation of resources within district and sector budgets has changed as a result of the score-carding process	35	57
Number of agreements between service providers and communities to jointly improve service delivery	100	174

Key Points

Communities better informed about their entitlements and service standards
Indicator 4.1: Number of people participating in score-carding
96,037 people have participated in score-card processes since the project began in 2012, nearly double what was targeted. The annual achievement marginally missed the milestone - 19,267 out of a planned target of 20,0000. The project has been active in 25 districts across the country, working in collaboration with local district-based civil society organisations. The extent and quality of the follow-up of score-card assessments has unsurprisingly varied depending on the local partner organisation. Access to funding to carry out follow-up activities has not necessarily been the influencing factor. Commitment and activism by the local partner has been more important.

The Kalondolondo project featured in the media on a non-sponsored basis 89 times in 2015. Given the focus on assessing piped water and electricity services this year, many of the media articles were in relation to these services. There was also media coverage however of follow-up of commitments from assessments in previous years such as use of Local Development Fund (LDF) funding to rehabilitate school blocks in Lilongwe Urban. The project has very effectively used the media (print, radio and television to shine a light on specific problems. The media spotlight on the water quality in Dwangwa for example prompted a high-level response from the Central Water Board and some relatively prompt action.

Responsiveness of government
Indicator 4.2: Number of instances where allocation of resources has changed as a result of score-cards
There were a total of 34 instances of allocation of resoources being changed as a result of the scorecards in 2015 leading to a cumulative total of 57 since the project began. A number of these were related to actions taken by the different water boards in response to issues raised. For example the Southern Region Water Board (SRWB) increased the price it pays to buy water from the Mpira Water Trust. (MPWAT) from Mk40 to MK80 per kilolitre following the assessment. The Central Region Water Board (CRWB) allocated MK7million to procure pipes to replace old pipes at Dedza trading centre area, the replacing exercise is being done in phases after user complained of poor quality water due to rusty pipes. And the Northern Region Water Board (NRWB) allocated funds to construct a water storage tank at Chikale scheme in Nkhatabay to reduce dry outs due to interruptions caused by electricity that affects water pumping. The storage tanks will act as a short term measure in cases of normal blackouts which will improve water availability to supply the area. Youth friendly health service (YFHS) assessments have resulted in the construction of a YFHS centre at Chinteche Rural Hospital, and the opening of two new YFHS centres in Mwanza district. And the Local Development Fund secretariat allocated an extra MK38million to Lilongwe City Council for completion of unfinished projects under LDF urban window in Lilongwe city after the Kalondolondo assessment revealed that the majority of the project’s still remain incomplete over one year after the expiry of construction period.

Communities and service providers working together
Indicator 4.3 – Number of agreements between service providers and communities to jointly improve service delivery
A cumulative total of 174 agreements have been agreed between service providers and communities to jointly improve services. In 2015, the number achieved was 46 against an annual target of 40. A total Four National Stakeholder Meetings were held during 2015 related to 1) Electricity; 2) Delivery of piped water; 3) Local Development Fund Teacher’s houses scheme and 4) Youth Friendly Health Services Programme. The outcome both of these stakeholder meetings and of district interface meetings were formal agreements on actions to be carried out in response to service issues raised. The project design has largely relied on partners to monitor and follow-up on these agreements, with mixed results (see below).

After initial resistance from the Water Boards to engage with citizens, an important result of district interface meetings was the agreement by the Water Boards to work with Water User Associations and to work with chiefs on catchment area protection. In general it has been challenging to get service providers to sign formal agreements given concerns that they may not necessarily have the resources to follow through.

The following are some of the examples of agreements between service providers and communities to jointly improve service delivery capture in Kalondolondo quarterly reports.
- Citizens agreed to take responsibility of reporting cases of water facility vandalisms, thefts and broken pipes in order to avoid water wastage from broken pipes so that the water service providers may in turn be able to repair vandalized materials and maintain a good quality service as well as holdvandal’s to account.
- Citizens led by community leaders and supported by Water Boards to safeguard catchment areas and water sources for water boards in order to reduce drying out of reservoir dams due to environmental degradation.
- The communities and the service providers agreed to form Water User Associations in 3 districts in Dedza, Ntcheu and Nkhotakota specifically to create consumer contact groups to improve working relationship with water boards.
- In Mulanje at Mpiyama village, communities and SRWB agreed to working together through GVHs and water committee to revive communal taps which stopped working some years ago by first selecting new committees, training by SRWB and councilors and chiefs to formulate by-laws of guiding communal taps from individual interference even if the tap is on his or her plot
- Communities agreed to use the tip-off anonymous number which was shared with communities in Mangochi, Dedza and Kasungu to report meter by-passing to the Electricity Supply Cooperation of Malawi (ESCOM)

While the cumulative totals for these three indicators are significantly higher than the targets, given the annual results for the programme in 2015 and the triangulation with monitoring of reports and field visits, this output is judged to have scored an A and not an A+ as a simple reading of the figures above might suggest.

Score-card assessment follow-up
The design of the project relied on the local partner organisation to follow-up on actions arising from score-card assessments with limited role for the Kalondolondo project team itself. Limited budget for this has resulted in mixed performance in terms of sustained action around specific problems, with the level of engagement of the local organisation being an important factor. Given the focus on different service issues each year, it has also been difficult to maintain engagement around a particular service, beyond solving the immediate problems raised by the score-card assessment. This has not facilitated monitoring of improvements over time.

Monitoring and capturing results
The capacity of Kalondolondo to capture and analyse results is partly dependent on the capacity of the local partner organisations to report them. It would appear from field visits that there is greater richness of results than what is documented by the project. The role of the project in empowering citizens to question service quality through the provision of information, in fostering better working relationships between communities, councils and service providers to help solve local problems, and in helping to identify additional local resources to solve specific problems is only weakly captured in reports to DFID.

Insufficient budget and resources for monitoring and follow-up (since design) has been a challenge. For example, there is limited capacity to monitor whether agreements made by service providers, or jointly between service providers and communities are followed through. This problem is compounded by the fact that the project regularly moves on to monitor different issues (see “breadth versus depth” above).

The lack of a database or website which publishes data, results, and partner reports and captures media coverage has been hindered further learning or snowballing of influence.

Summary of responses to issues raised in previous annual reviews (where relevant)

Kalondolondo project was originally scheduled to finish in October 2015.  A no-cost extension was given to allow for final activities to be completed and documentation of lesson learning and evaluation to be properly captured.

Kalondolondo has shortened the gap in some cases between the initial score-card process and the follow-up meeting with District Councils to ensure actions are agreed and implemented in good time. For example when Kalondolondo conducted assessments of Girls’ self-boarding, they carried out immediate follow-ups and DFID participated in the follow-up meetings.

DFID carried out a due diligence assessment (DDA) of Plan Malawi and the Kalondolondo project (Quest # 5318960) which was completed in November 2015. It raised a number of concerns about the management set-up of the project with unclear lines of accountability and a poorly functioning board. The project closure in March 2016 provides limited time to make progress on the DDA recommendations. DFID will consider the lessons learned in future programming.

The BEAM log frame was updated to include milestones for 2015 and end of project targets for May 2016.

Recommendations

- DFID to engage with the final evaluation of the project (commenting on Terms of Reference, selection of consultants and draft report) to ensure a quality output.
- The consortium led by Plan Malawi should allocate additional technical capacity to ensure effective documentation of lessons learned during the final stages of the project.
- Given the Kalondolondo project was extended until March 2016, and it was decided that efforts during the last quarter should focus on documentation, lessons learned and evaluation of the project rather than carrying out new score-card assessments, the end of project targets in the DFID log frame should be revised accordingly.
- DFID should avoid requesting additional parallel reports with different templates from partners, which appears to have stretched capacity and resulted in challenges in documenting data. Rather DFID should focus on ensuring partners’ own reports are the best quality possible and include robust data.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

As the BEAM programme is based on a Programme Memorandum and not a Business Case, specific cost drivers were not identified and therefore cannot be assessed. However, the following items have accounted for the majority of the expenditure:

Tilitonse:	Grant funding to sub-grantees. The cost of capacity building doubled from 7%-15% of the total budget (pre-extension) as additional support was provided to mentor community based organisations with grants reducing from 80% to 71%.
Kalondolondo:	Implementation of score-cards, including capacity building of grantees and hosting of interface meetings after assessment
PFM MDTF:	Procurement of IT hardware/software. Technical Assistance to DPP & ACB, usables. Given reallocation of additional resources away from other budget lines, the IFMIS procurement now amounts to 51% (from an originally 28%) of the FROIP project.

VfM performance compared to the original VfM proposition in the business case

The BEAM programme was designed and approved prior to the introduction of the business case format and therefore has no established VfM metrics.

Assessment of whether the programme continues to represent value for money

Although the BEAM design lacks VfM metrics, considerable effort is put into ensuring the programme delivers value for money. In its original design, the programme was envisaged to comprise 14 components. While this provided flexibility, the administrative burden and impact on the clarity of delivery were considerable. The portfolio was rationalised in 2014 to focus on the three main components that deliver the greatest contribution to the BEAM objectives. Below are some of the key VfM considerations for individual components.
A new MoU in November 2015 meant renewed cooperation between the donors and a new contract was signed with DAI to continue with Tilitonse. Savings of £172k were achieved through this negotiation with the service provider providing 120 days of pro-bono technical and back-stopping support. As the lead donor for Tilitonse, DFID is leveraging funds worth £5.8 million from other donors with its £13.6m investment. The fund manager was recruited using the OJEU process with financial criteria increased to emphasise the desire to see good value for money, and the competitive grant making process allows the fund to ‘test the market’ and select those partners that are best placed to deliver results and value for money.
[note] Irish Aid contributes EUR 2,550,000  and the Royal Norwegian Embassy NOK 46,000
Kalondolondo has been set up on the basis of a direct grant to a consortium of established CSOs who in turn operate through local CSOs who receive small sub-grants on a non-competitive basis. The 2013 ICAI report on Empowerment and Accountability noted that Kalondolondo had delivered significant development impact for modest expenditure and suggested that this model might deliver better value for money than competitive grant-making for local interventions. In 2015, VfM is likely to have been impacted negatively by delays in implementation and reduced numbers of assessments and activities. This was as a result of financial reporting capacity challenges and delayed disbursements from Plan Malawi to the project.
DFID was the first donor to contribute to the PFM MDTF and has helped mobilise approximately £8 million from other donors. Beyond that, the delivery of value for money in the PFM MDTF is largely dependent on World Bank procurement procedures and the institution’s ability to provide oversight for performance in the PFM reform process. An in-country PFM specialist was brought in in 2014 which has helped strengthen oversight. For example, the World Bank has continually challenged the inclusion by the Government of Malawi of overly expensive and non-core activities for the reform process in work-plans and budgets. The budget is currently being re-prioritised to help meet the funding gap for the procurement of the new IFMIS system. The procurement process itself is being overseen and quality assured by the World Bank on the basis of International Competitive Bidding, following the World Bankprocurement rules. The value-for-money of the procurement will ultimately depend on it being effectively implemented.
[note] The EU contributes EUR 7m, Germany EUR 0.4m, Irish Aid EUR 0.5m and the Norwegian Embassy NOK 15m.
The technical assistance on investigating and prosecuting corruption cases is considered good value for money given the results achieved in securing convictions, addressing impunity and strengthening Government capacity. In monetary terms, the asset recovery of £200,000 to date is still relatively small, but an additional £1.5 million has been identified for potential recovery. DFID has pushed hard for VfM in technical assistance contracts. They have all been output-based and the TA for digital data and civil litigation were put out to limited tender.

Quality of financial management

By the end of FY2015/16 BEAM is largely on track to achieve full spend against its budget. Only the four components which remain live have an outstanding balance. Of these, only Kalondolondo will have money left over after closure. There is also relatively small sum of unprogrammed funds amounting to approximately £560,000. These funds were added to cushion BEAM when the July 2015 cost extension was agreed, the main reason being that additional donor contributions to the Tilitonse contract extension were not yet confirmed at that point.

The following table shows the budget by component. The shaded cells are components which are now closed.

Component	Budget	Expenditure to date	% of budget spent	Balance
Tilitonse	£13,171,505.00	£10,113,134.06	77%	£3,058,370.94
Evaluation Agent	£446,353.00	£353,765.83	79%	£92,587.17
Kalondolondo	£2,466,517.00	£2,244,345.00	91%	£222,172.00
PFM (including Cash-gate follow up)	£6,345,664.00	£6,063,418.10	96%	£282,245.90
Unprogrammed	£559,570.75	£0	0%	£559,570.75
Appraisal and Design	£144,228.42	£144,228.42	100%	£0.00
Support to Local Government Elections	£1.00	£0.00	0%	£1.00
Civic and Voter Education for Local Government Elections	£410,000.00	£410,000.00	100%	£0.00
Monitoring and Evaluation	£3,702.83	£3,702.83	100%	£0.00
Support to Good Governance Fund	£67,713.85	£67,713.84	100%	£0.01
Grant for Story Workshop	£130,792.00	£130,792.00	100%	£0.00
Grant to MEJN	£95,642.55	£95,642.55	100%	£0.00
Grant to CHREAA	£53,420.15	£53,420.15	100%	£0.00
Grant to Union for the Blind	£48,111.95	£48,111.95	100%	£0.00
Anti-corruption Bureau	£550,000	£550,000	100%	£0.00
Advisory and management support	£3.00	£0.00	0%	£3.00
Grant NIS	£421,503.50	£421.503.50	100%	£0.00
NAO	£43,000.00	£43,000	100%	£0.00
Total	£24,957,729.00	£20,742,778.35	83%	£4,214,950.76

The quality of financial management has varied amongst components.

The Tilitonse Secretariat has continued to demonstrate a good grip on financial management as evidenced by increasingly accurate forecasts. Uncertainties around the extension at the beginning of the year – both in terms of the amounts and duration - made this a challenging task but the team has managed the situation well, ensuring grants were either terminated or extended at the right points in time. The high risk fiduciary environment has continued to require attention and the team has worked effectively with the Audit and Finance Sub-committee to ensure adequate controls remain in place and fraud cases are dealt with. The 2015 audit was unqualified.

While Kalondolondo’s budget with DFID is in Pound Sterling, the programme has benefitted from the significant depreciation of the Malawi Kwacha over the past 12 months given programme activities and staff costs are budgeted for in the local currency. As a result of these savings, the programme was able to carry on without making regular quarterly requests for funds for part of the year. On the same basis, Kalondolondo also requested a 7 month no cost extension to enable it to deliver additional results for the budget already agreed with DFID. A key learning point from this experience was the need for Kalondolondo to inform DFID earlier and be more transparent about the savings made as a result of forex fluctuations. A Due Diligence Assessment of the programme also highlighted areas for improvement on financial management capacity. This DDA informed DFID’s decision to grant only a 3 month no cost extension to enable to programme to close in a responsible way.

Date of last narrative financial report	Tilitonse: January 2016 - Quarterly report for Oct-Dec 2015, / Kalondolondo: January 2016 – Q’ly report Oct-Dec 2015 / WB MDTF: The last Quarterly report for FROIP was for period ending 31 December 2015.
Date of last audited annual statement	Tilitonse: 31st March 2015. / Kalondolondo: 31st March 2015 / WB MDTF: June 2015

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

During the review period the overall risk level for BEAM has remained unchanged, however, there has been changes within individual components and some risks have materialised and become issues the team is now managing.

In terms of the civil society components, there has been the risk that space for civil society shrinks as tensions grow between Government and CSOs. DFID is monitoring this carefully. Fragmentation of civil society through for example cooption of key civil society leaders, rather than repression, is more of an issue. In this regard, the Tilitonse and Kalondolondo approach of bringing coalitions of organisations together is one mitigating approach.

Fraud and corruption risks in Malawi are high for all partners. Fraud concerns and cases have been followed up closely by the BEAM programme manager and DFID’s Counter Fraud and Whistleblowing Unit in the UK. No new frauds by BEAM downstream partners have been reported since April 2015, when there were 3 CBOs that reported cases of ineligible expenses. Of these, 2 have repaid the funds whilst Tilitonse is claiming back funds from the remaining organisation. The two that have repaid are currently undergoing the normal grant closure process.

The future of Tilitonse and its transition to a Foundation was a commonly agreed upon goal for the donors. The Tilitonse project has been extended until 2017 to provide time to establish the new foundation. However, there are considerable risks associated with this process that need to be carefully managed. There is a considerable risk of loss of DFID investment if the learning, evidence, processes, procedures and systems that have been established (with considerable effort and expense) under Tilitonse is not taking forward into the Foundation. The parallel process decided upon to establish the foundation compounds this risk.

A decision was made to carry out a DDA of Kalondolondo in August 2015. This exposed some challenges especially with regards to their governance structure. DFID has clarified with the consortium that Plan International is accountable to DFID directly. A decision was taken to extend the project until end March 2016 to effectively wind up partnerships with downstream partners and focus on lesson learning, documentation and evaluation.

On the PFM work, there is considerable risk regarding whether there is will from the Government to follow through with fiscal reforms and in the procurement of a new Financial Management System. The GoM, in consultation with donors, has just revised the IFMIS procurement budget to cover the funding gap. The on-going process of procuring of an IFMIS software package is being quality assured by the World Bank. As at 20 February 2016, the GoM was waiting for a “No Objection” from the WB to award a contract. This component of BEAM comes to an end in June 2016. There is a risk that even if funding is secured that the impending deadline could affect the quality of implementation of the new system. There was also a risk that the Technical Assistants placed in the DPP and ACB would not be effective or find their feet quickly enough. However they have proved to be able and competent TAs and have worked very well with both the DPP and ACB.

Outstanding actions from risk assessment
- DFID to continuously monitor government and civil society relations and use influence to protect against closing space for civil society. The situation should be carefully monitored given the current context.
- DFID to remain continuously engaged with the Government of Malawi on strengthening Public Financial Management. If insufficient progress is made, a review by the World Bank in March will likely recommend the project is not extended beyond June 2016. If this occurs, the risk of procurement of the IFMIS system is likely to be too high to proceed. If an extension is agreed, DFID to request that this be on the basis of Payment by Results.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Generally, Tilitonse has delivered well against the agreed timeframe with most of the key activities implemented within agreed timelines. However, towards the end of the first phase, Tilitonse extended some of the project grants because they could not complete all agreed activities on time. This necessitated continued implementation stretching into second phase of the programme. The impact of this has been the extension of the Impact Evaluation for 6 months because some of the projects were part of the sample for the case studies.

Kalondolondo has also performed well on a general scale. There were delays in release of funding from Plan Malawi to the project in the third quarter, which delayed delivery by two months. The complexity of the work around water and electricity assessments also meant that Plan Malawi sought an extension beyond the original project closure of October 2015. The project has been extended until 31st March 2016.

DFID financial support to the PFM MDTF will come to an end in June 2016. A full PEFA assessment is planned for 2016 to determine the extent to which project outcomes have been delivered. Apart from the procurement of IFMIS, the FROIP project is within its planned timeframe. Both Baker Tilly and ICAR work delivered to agreed timeframe. ICAR work has been extended by 6 months from Jan-June 2016 to allow further work to take place, with new baselines and indicators set. DFID is currently developing a new anti-corruption programme and is proposing to continue this support as part of the new programme

Performance of partnerships

We are working proactively to strengthen donor relationships under Tilitonse to ensure that efforts to reach consensus on the management of the fund and its transition to a local foundation do not have an adverse effect on delivery.

On the Kalondolondo programme, the performance of the consortium of Plan Malawi, ActionAid and CONGOMA has not been very effective in ensuring proper oversight and guidance of the programme. As a result, some administrative issues were not effectively addressed such as staff contracts and this affected the morale of the staff. With our interventions, staff were given contracts to the end of the programme. The Consortium did not communicate with DFID sufficiently in 2015 about challenges within the governance and administration of the programme.

On the PFM MDTF, the Government is still relatively weak in implementing agreed upon reforms and making appropriate decisions to enable the delivery of impact. In addition, there are leadership gaps at a political level that are limiting progress of the project. There is need for better coordination by both government and donors if they are to minimise duplication. During implementation, DFID have learnt that contributing funds to World bank Trust Funds requires much closer involvement and oversight by contributing donors. The World Bank has been weak in supervising the GoM Programme Management Unit and this has affected the quality of project management and project reporting.

The Anti-Corruption work which is placing TA within the office of the DPP and the ACB has increased capacity within those organisations and provided a confidence in pursuing Cashgate suspects. There has been no overarching managing agent for the law-enforcement work which has meant DFID Malawi has had to manage 6 different contracts to date (Baker Tilly/RSM; ICAR; Integrated Security; Maravi Risk Management; FTS; Cooley). With exception of Baker Tilly/RSM and ICAR, all contracts have been worth less than £100k. This has been very transaction heavy for DFID Malawi. With regards to ICAR, their lack of presence in country has meant a lot of the administration and agreeing results to be reported against has fallen to the in-country Technical Assistants - distracting them from the technical work we are paying them to do.

DFID does not have a Memorandum of Understanding with the Government of Malawi institutions to whom we are providing technical assistance (DPP and ACB). This is a matter of concern and can result in lack of clarity about roles and responsibilities of the TAs and the receiving GoM institution.

- In future, DFID should explore ways of reducing DFID project management time for supporting law enforcement agencies though for example a single accountable grant or contract.
- DFID to ensure MoUs exist with the respective GoM institution in all cases where technical assistance is being provided. Provision for periodic revision should be built into the MoUs to allow for the work to be responsive to the context.
- DFID to ensure clear lines of accountability with Accountable grantees in all programming, ensure effective project governance arrangements are in place and ensure delivery plans reflect clear contract management procedures.

Asset monitoring and control

DFID maintains registers of assets purchased by BEAM implementing partners who in turn are responsible monitoring assets purchased by down-stream partners. With the exception of the PFM MDTF, capital investment is modest. The BEAM programme manager carried out physical checks on assets regularly during field trips to projects, performing spot checks including going through asset registers.

With the closure of Kalondolondo component, comprehensive assessment of the assets was undertaken and the state of these assets has been determined. Generally most assists are in good condition and recommendations have been made on how to dispose of them.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

In November 2013, DFID froze all funding through the Government of Malawi’s system and there is currently no financial aid provided through any of the BEAM components. However, support has continued to some quasi-state institutions such as Malawi Human Rights Commission and the Malawi Council of the Handicapped and similar institutions through enhanced control measures including opening of dedicated accounts for the projects. The World Bank has formally agreed that no DFID funds will be disbursed through GoM accounts, even though the PFM MDTF arrangements in principle allow this. On this basis, the use of the Partnership Principles does not apply in the detailed management and monitoring of any part of the BEAM programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is no evaluation planned for the BEAM programme as a whole, largely because the numerous components included in BEAM since its inception would make it challenging to provide a single, coherent assessment of achievement. An impact evaluation has been contracted for the Tilitonse Fund and is carried out on an on-going basis by the Independent Impact Evaluation Agent (ITAD). This evaluation is due by June 2016. The extension to the Tilitonse fund does not include an extension to the contract of the Independent Impact Evaluation Agent (ITAD). Given this, there is currently no plan for how the project will be evaluated in 2017. There is some budget available to address this gap.

The Tilitonse Board needs to urgently take a decision for how the 2 year extension will be evaluated and put that plan into action.

Plan International is carrying out an evaluation of the Kalondolondo component as this project winds up, Learning from this evaluation will help inform DFID design of future programming.

A World Bank mid-term review was carried out in September 2015 which has helped inform this annual review.

This is a portfolio programme and the DFID BEAM log frame draws from the different results of the component parts. This has resulted in quite a complex log frame that risks missing key result areas, as it draws only from selected indicators from the Tilitonse and Kalondolondo programmes, which in turn both have quite complex log frames themselves.
DFID to learn from the challenges associated with this portfolio approach in future programming and consider alternative ways of capturing complexity of results.

Monitoring progress throughout the review period

This annual review was led by the new DFID Malawi Senior Governance Advisor, in collaboration with members of the DFID Malawi Governance and Security team and input from the BEAM programme partners. In addition to reviewing reports and documentation, as part of the review process team members visited a number of Tilitonse and Kalondolondo project sites in the north of the country during a one-week field trip in November 2015 (Quest #5350474). Additional project sites for both Kalondolondo and Tilitonse were visited in the centre of the central region, close to Lilongwe (Quest 5374893). Interviews were also held with key stakeholders (see table below). The review was peer reviewed by the DFID Malawi Health Advisor and (Results Advisor) and quality assured by the Governance Team Leader before being submitted to the DFID Malawi Head of Office. Programme delivery partners were consulted on a draft of the review for fact-checking purposes.

We have received feedback from a variety of stakeholders and beneficiaries.
Beneficiaries at local levels have appreciated how Tilitonse and Kalondolondo projects have brought different actors together to resolve problems. Young people and women in two projects spoke about how the support was helping them to have a voice and challenge the chief’s power in a positive way. The Water User’s Association in Dwangwa said the support from Kalondolondo had been “very important” for them to be able to challenge the Central Water Board.

The Malawi Human Rights Commission appreciated the oversight by the Tilitonse secretariat. They said the Project Cycle Management approach was useful and that the Secretariat had provided “constant collaboration without being overbearing”. A number of others appreciated the trainings that had been provided and the opportunities for learning from other organisations as a result of networking meetings (e.g. on mining issues)

Both the ACB and the DPP were extremely positive about the technical assistance support that has been provided and provided concrete examples of where they thought it had made a substantial difference. This included new ways instituted for doing investigations, plea-bargaining having been put in place, benefitting from the information/ knowledge as a result of the TA’s international networks, mentoring and learning on-the-job. In the words of the DPP, “it has meant the difference between success and failure” with regards to the Cashgate cases.

Meetings and project visits

Meetings were held with the following people
Who	Institution
Reyneck Matemba	ACB
Mary Kachale	DPP
Nick Staite and Alan Bacarese	ICAR
Kalondololondo team	Kalondolondo
Tilitonse team	Tilitonse
Tilitonse Board (Irish Aid, Norway, DFID, Zione Ntaba)	Tilitonse
Daniel Yaw Domelevo	World Bank/ FROIP

Project site visits

Organisation/ site	Location	Project
DCA/ CCJP	Dowa district	Tilitonse
FOCCAD	Nkhotakota	Tilitonse
Karonga Debating Club – Nyungwe Ward	Karonga rural	Tilitonse
Church and Society Livingstonia Synod – Karonga Coal mine	Karonga rural	Tilitonse

Dwangwa Water Users Committee	Dwangwa, Nkhata Bay	Kalondolondo
Chitipi primary school	Lilongwe rural	Kalondolondo
Nkhoma Hospital	Lilongwe rural	Kalondolondo
Msiro Primary School	Mzuzu peri-urban	Kalondolondo
Lwezi Health Centre	Nkhatabay rural	Kalondolondo
Chintheche Health Centre	Nkhatabay peri-urban	Kalondolondo
Munkhokwe Water Kiosk	Nkhatabay rural	Kalondolondo

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process