## Logframe Revised 2017 (hidden)
Smart Guide
|  |  |  | DFID FUNDING 8.5M GBP |  |  |  | BRIDGE YEAR
PROJECT TITLE | Western Region Coastal Foundation (WRCF) | [8 empty] | Assumptions
IMPACT | Impact Indicator 1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2020)
Improved stability and inclusive development prospects in Western Region | Average poverty rates in the Western Region coastal districts | Planned | Poverty incidence: 21.9% (Western Region, GLSS 2012/13) |  | 16.1% | The survey will not be done this year | 17.05% | The survey will not be done this year | 17%
|  | Achieved | n/a |  | 17.9%
Source
GLSS (2012/13 and 2020) and Citizen Perceptions and Socio-Economic Survey (CPSES, 2016 and 2018/19). Data collected semi-annually.
| Impact Indicator 2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Citizen perceptions of local political stability, development equity and economic prospects in the Western Region | Planned | The baseline was condcuted in 2016 using the Ciitizes Perception and Socio Economic Survey |  | Baseline was conducted in 2016 | 22% positive perceptions of local political stability 21% positive perceptions of development equity 11% positive perceptions of economic prospects | 23% positive perceptions of local political stability 22% positive perceptions of development equity 12% positive perceptions of economic prospects | 24% positive perceptions of local political stability 23% positive perceptions of development equity 13% positive perceptions of economic prospects | 24% positive perceptions of local political stability 23% positive perceptions of development equity 13% positive perceptions of economic prospects
|  | Achieved | 21% positive perceptions of local political stability 20% positive perceptions of development equity 10% positive perceptions of economic prospects |  | 21% positive perceptions of local political stability 20% positive perceptions of development equity 10% positive perceptions of economic prospects | 42.6% positive perceptions of local political stability 38.6 % positive perceptions of development equity 25.3% positive perceptions of economic prospects
Source
Afrobarometer (2014 and 2020) and Citizen Perceptions and Socio-Economic Survey (CPSES, 2016 and 2018/19). Data collected semi-annually.
OUTCOME | Outcome Indicator 1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19) | Assumptions
Expectations managed and met and constructive relationships between communities, government and industry built | # of people acquiring jobs or receiving an increased net income as a result of investments undertaken or influenced by the Foundation (disaggregated by sex / youth) | Planned | 0 | 0 | 50 | Total of 432 people will have improved income/jobs -42 graduates to get jobs with industry (20% of 210 students from Technical Institutes) -390 Beneficiaries of Aquaculture | Total of 998 people will have improved income/jobs . 259 TVET graduates acquire jobs (70% of 370 students who graduate in 2018) 450 Beneficiaries of Aquaculture receive increased incomes 108 industry personnel (60% of the180 industry employees trained in 2017) 49 vegetable farmers receive increased income (80% of 62 farmers trained in 2017 60 vegetable farmers will receive increased income (60% of 100 famers trained in 2018) 72 Beneficiaries of climate change adaptation and livelihood enhancement (60% of the120 people trained in 2017 and 2018) | Total of 1142 people with improved income/jobs 37 TVET graduates acquire jobs (10% of 370 students who graduated in 2018 but could not find jobs the same year) 181 TVET graduates acquire jobs (70% of 259 students graduating in 2019), 36 Industry employees (20% of industry employees trained in 2018) 120 industry personnel with improved income (60% of 200 industry employees trained in 2018) 500 Beneficiaries of Aquaculture, 80 Vegetable farmers with improved income (80% of 100 beneficiaries from in 2019) 20 Vegetable farmers (20% of the 100 farmers trained in 2018) 144 Beneficiaries of climate change adaptation and livelihood enhancement (60% 240 people trained in 2019 will have improve income/jobs) 24 Beneficiaries of climate change adaptation and livelihood enhancement (20% of the 120 2018 beneficiaries who will adopt in 2019) | 2622 | National Political stability is a key condition for WRCF success and it is important that political economy for development within the OGP sector does not deteriorate. Sudden policy changes may affect WRCF. Macroeconomic conditions such as continued growth of the GDP, low and stable inflation, and stable exchange rate are key for Improved equitable socio economic development and Improved Stability. In addition, it is assumed that security from exogenous events (outside of issues related to OGP sector) in the Coastal Districts does not deteriorate, especially domestic terrorism and cross-border insecurity. Significant weather events, such as flooding and droughts may have adverse impacts on the WRCF programme. Any negative environmental impact direct or indirect from OGP sector may affect success. Any incident or accident posing a safety or security risk to affected communities may affect success. Other investments or actions in the region do not undermine investments undertaken or influenced by the Foundation. Traditional/cultural practices do not prevent benefits to women and other marginalised groups. The pound has recently lost value against the cedi, and may adversely affect the programme's ability to fully achieve targets.
|  | Achieved | 0 | 0 | 264 4 lead fish farmers and 4 farm hands/farm who helped in pond digging and pond management will receive direct income . This gives a total of 20 people with financial benefit from the acquaculture in 2016. For the Jubilee partners livelihood project influeneced by WRCF, an avaerage of 1 person is engaged per acre of farm to clear land, cultivate and weed . A total of 244 people have been employed and have received increased income | Total of 272 -36 TVET graduates -238 Aquaculture -68 with jobs, 170 with improved incomes , 126 of which are fish farmers, 8 smokers, 3 hatchery operators , 10 fishmongers, 13 restaurants and traditional caterers, 10 transporters
WRCF and scale-up partner intervention monitoring and reporting systems., cross-checked with Citizen Perceptions and Socio-Economic Survey (CPSES) data.
| Outcome Indicator 2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| [VfM] Activity fund leverage: Non-DFID of funding WRCF supported interventions ($ per year, cumulative target) convert to dollar at $1.30 /£ | Planned | N/a | $0 | £240,000 ($312,000) | £560,000 ($728,000) CSLP, Oil&Gas Capacity Building Project ( TVET) | £1,300,000 ($1,690000) | £3,000,000 ( $3900,000) | £5,100,000 ($ 6,630,000)
|  | Achieved | N/a |  | WRCF and Coastal Sustainable Landscapes Project (CSLP) signed a memorandum of understanding (MoU) to support ‘climate smart agriculture’ interventions.The CSLP programme has been renewed with budget of US$6.5million over 5 years. This would help towards leveraging non-DFID funds for the Foundation’s activities | Leveraged $3m worth of welding equipment Oil & Gas Capacity Building Project Project . $1m of CSLP budget on climate smart agriculture
Source
Report from the resource mobilisation and private liaison monitoring, WRCF accounting systems
| Outcome Indicator 3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Level of stakeholder engagement in Dialogue Structure (disaggregated between government and industry) determined by percentage of stakeholders who honour invitations to attend conversations at a certain level/year | Planned | N/a | 0 | CAC Level : Government: 65% Industry: 50% District Level Government: 65% Industry: 50% | CAC Level Government: 75% Industry: 55 % District Level Government: 75% Industry: 50% | CAC Level: Government:75% Industry: 60% District Level Government: 75% Industry: 60% | CAC Level Government: 80% Industry: 65% District Level : Government:80% Industry:60% | CAC Level Government: 80% Industry: 65% District Level : Government:80% Industry:60%
|  | Achieved | N/a | 0 | CAC Level : Government: 70% Industry: 55% District Level Government: 72% Industry: 50% | CAC Level Government 94% Industry 83% District Level Government : Industry : | CAC Level Government Industry District Level Government : Industry : | CAC Level Government Industry District Level Government : Industry : | CAC Level Government: Industry: District Level Government: Industry:
Dialogue Structure monitoring
| Outcome Indicator 4 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Community satisfaction with dialogue outcomes | Planned | N/a | 15% | 20% | 25% | 35% | 50% | 50%
|  | Achieved | N/a | 22% | 21.2% | 42.5%
Source
Semi-annual Dialogue Structure surveys/CPSES Survey
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19) | Assumptions
Coastal Foundation provides locally owned, sustainable platform for coordinated development in Western Region coastal districts | Effective operations of locally owned Foundation (including compliance with Ghana legal and regulatory framework) | Planned | N/a | Board registered and launched, HR plan developed, Branding and communication plan developed, resoure mobilzation plan developed | WRCF Boards continues to function in compliance with ToRs. Establishment of Foundation financial management system and banking capabilities. Resource mobilization strategy revised. | WRCF Boards continues to function in compliance with ToRs. Operationalise Financial management system. Resource mobilization strategy revised. Establishment of business plan | WRCF Boards continues to function in compliance with ToRs. Operationalise the business plan | WRCF Boards continues to function in compliance with ToRs. Transfer of WRCF programme assets to the Foundation. | The foundation is a fully functional and sustainable entity | Active and growing oil and gas, power and extractive industry Central government’s role in policy making can enable the WRCF to function. WRCF will be an actual and perceived impartial, independent body. WRCF is recognised as a common platform to bring industry players and stakehloders together, and is not seen as duplicative or competitive with others. OPG , power, extractive industry and Government will be willing to participate in the WRCF governance structure
|  | Achieved | N/a | Achieved | The PIC and IRMC meetings registered 80% and 100% attendance respectively. • The Governing Board was able to hold its meeting on 9 August 2016.. • Separate financial management system for WRCF (non-DFID) funding from resource mobilisation and related activities in place • The WRCF Resource Mobilisation strategyhas been revised to reflect changes to the logframe and expanding efforts to target donors, development partners, and foundations/grant making institutions, to fund operations and activities/interventions. | • 4 meetings of the Board one of which was an extraordinary meeting focused on feasibility of the Foundation. • Key decisions of the Board: Approved the cost benefit analysis, reviewed the draft business plan and approved Terms of Reference for feasibility study of the Foundation • Part of the Foundation’s financial reporting has been migrated to QuickBooks and is operational.
Source
Programme management monitoring. Board minutes.
| Output Indicator 1.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Effectively engaged staff for locally owned Foundation | Planned | N/a | Staff Assessment | Staff Performance Plans | Staff Performance Plans developed Staff Technical Assistance capacity developed | Staff Performance Plans administered . | Foundation employs staff directly | Foundation is independently managed and operational
|  | Achieved | N/a | Achieved | WRCF has established learning and development plans for staff members and for team capacity development. All WRCF staff plus Grant implementing partners participated in training to understand DAI’s Code of Ethics and Business Code, and Preventing Harassment policy. WRCF achieved 100% compliance with this DAI requirement. | • Programme team developed Individual Performance Plans to guide their work streams. • Programme team participated in three workshops on project management, data coding, and gender
Source
Programme management monitoring, WRCF HR Manual
IMPACT WEIGHTING | Output Indicator 1.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
30% | [VfM] Operational sustainability: Non-DFID funds raised to pay for WRCF operations | Planned | N/a | 0 | £30,000 ($39000) | £150,000 ( $195,000) | £360,000 ($468,000) | £560,000 ( $728,000) | £ 1.1m ($1.3m)
|  | Achieved | N/a |  | Ghana Gas has pledged to make an initial grant donation towards coordinating the management of the ROW project. • Vitol Foundation has also pledged £15,000 in cash for study on Oil impact of marine fisheries | $228,975 worth of contract signed, with additional $123,150 negotiated waiting for signature. The funds received to date is $ 178,251 for the aspects of the contract delivered
Source
Resource mobilisation report, WRCF accounting systems
INPUTS (£5.7M) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  |  |  | RISK RATING
| 15% contract value - £1,264,263 | [8 empty] | Mojor-: [Key risk relates to willingness of stakeholders to contribute to operational funds]
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19) | Assumptions
Independent and inclusive dialogue structure promotes transparency, responsiveness and collective action on local development issues | % of issues raised by the CAC to other stakeholders which are responded to by the next CAC meeting | Planned | n/a | n/a | 50% | 50% | 55% | 60% | 60% | Stakeholders are willing and able to respond to issues raised in dialogue process. Commitment to dialogue and follow-up by each partner. The fact that not all community aspirations can be addressed will not discourage participation in the dialogue process. Community expectations will fall within ‘reasonable’ limits. 'Consultation fatigue' amongst residents and stakeholders does not undermine engagement with the dialogue process.
|  | Achieved | n/a |  | 82% of the issues raised by CAC to other stakeholders have been responded to | 75% of the issues raised by CAC to other stakeholders have been responded to
Source
CAC meeting minutes
| Output Indicator 2.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| # of Western Region coastal district residents engaged in the Dialogue Structure : disaggregated by sex / youth | Planned | 0 directly reached 0 indirectly reached | 21,600 ( 30.8% of the end target) directly/uniquely reached 86,400 indirectly reached | 18,000 (25.6% of the target) directly/uniquely reached 72,000 indirectly reached | 21,900 (31.2% of the end target) directly/uniquely reached 87,600 indirectly reached | 8,700 ( 12.4% of end target) directly/uniquely reached 34,800 indirectly reached | all 70,200 people directly reached 280,800 indirectly reached | 70,200 directly reached 280,800 indirectly reached
|  | Achieved | n/a | 35,000 (49.9% of end target) directly/uniquely reached 140,000 indirectly reached | 29,971 (42.6%) of the end target) directly/uniquely reached | 23,655 directly reached
Source
Reports from Conversation Managers
IMPACT WEIGHTING | Output Indicator 2.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
30% | Level of interest shown by participants –evidenced by level of repeat participation | Planned | N/a | N/a | 10% | 25% | 35% | 35% | 35%
|  | Achieved | N/a | N/a | 24 | 32.6% repeat participation
Source
Reports from Conversation Managers
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  |  |  | RISK RATING
| 25% contract value - £2,107,105 | [8 empty] | Minor/mod Some outputs depend on external factors including sustained community interest and engagement
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19) | Assumptions
WRCF pilots and / or supports stakeholder led socio-economic development interventions | Number of pilots supported by WRCF | Planned | N/a | 0 | 2 Cassava Aquaculture | 2 Youth skills for employment- (TVET) Trainer of Trainers Welding , Climate Smart Agriculture -Pond Side vegetable farming) | 2 | 2 | 8 | Market expandsion at natural growth rate is not disrupted by exogneous events or endogenous events (including legal and regulatory changes). New market entrants or new technologies/products do not disrupt market system. Vested interests do not disrupt or block market system interventions.
|  | Achieved | N/a | 0 | WRCF has supported 3 pilots : Fish,Cassava , GG ROW | Two pilots were supported . These are TVET and Climate Smart vegetable farming
Source
Monitoring and Reporting
| Output 3.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| # of people acquiring skills for employment as a result of training undertaken or influenced by the Foundation (disaggregated by sex / youth) | Planned | 0 | 0 | 50 | Total of 593 210 students from technical institutes, 180 Industry employees, 9 welding instructors from Technical schools, 3 instructors from RMU, 9 mechanical instructors with improved skills in TVET 62 Vegetable farmers 100 farmers in Aquaculture, 20 people trained in climate change adaptation and livelihood enhancement | Total of 870 220 students, 150 students from RMU and 200 industry employees with improved skills in TVET 100 Vegetable farming, 100 farmers in Aquaculture, 100 people with skills in climate change adaptation and livelihood enhancement | Total of 699 259 students with improved skills in TVET 100 Vegetable farming, 100 farmers in Aquaculture, 240 people with skills in climate change adaptation and livelihood enhancement | 2212
|  | Achieved |  |  |  | Total of 986 702 students from technical institutes, 23 Industry employees, 119 farmers in Aquaculture, 12 welding instructors from Technical schools, 130 Vegetable farmers
| Output Indicator 3.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
IMPACT WEIGHTING | Number of interventions being scaled up through WRCF support and technical assistance | Planned | 0 | 0 | 0 | 3 CSLP Climate change, Aquaculture and TVET | 3 | 3 | 9
20% |  | Achieved |  |  | 0 | Three (3) interventions have been scaled up. These are CSLP climate change sensitization, Aquaculture and TVET
Source
Monitoring and Reporting
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  |  |  | RISK RATING
| 55% contract value - £4,635,630 | [8 empty] | Moderate [Key risk relates to potential to attract co-investment required to scale inverventions and achieve outcome targets].
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19) | Assumptions
Evidence generated and communicated to enhance stakeholder learning and inform programming | # of knowledge management products for internal relection or external learning (stakeholders locally, regionally and internationally) per year | Planned | 0 | 3 Economic Opportunity Assessment | 3 Case study on MSDP, Catfish manual, Revised PEA, Revised Resource Mobilisation Strategy, Dialogue Structure economic analysis, CPSES baseline report | 4 Dialogue Case study, Marine scoping studies, Aquaculture scale up strategy , dialogue satisfaction survey report | 3 TBC | 3 TBC |  | OGP companies see value in WRCF products. There is sufficient flexibility in the programming of OGP companies, government and other agencies for them to adjust in response to WRCF evidence.
|  | Achieved | 0 | 6 EOA, PEA, Gender, Climate change, Evaluability, Dialogue, Resource Mobilisation strategies | Catfish Manual Revised , PEA revised, Resource Mobilization starategy revised , CPSES Baseline report completed | 8 Knowledge products have been produced. These are 2 Dialogue Case studies, Marine scoping study, Aquaculture scale up strategy , Dialogue Satisfaction Survey Report, Paper on Implications of Infrastructure Investments on Land and Livelihoods, Cassava Test Harvesting Report on Jubilee Livelihood Diversification Project, and Report on Understanding Contraints to Female Participation in Tech Education
Source
Monitoring and Reporting
| Output Indicator 4.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| # of communcations and outreach activities conducted per year | Planned | 0 | 2 | 3 Short videos of WRCF impact by community residents Foundation website established Annual Learning Forum | 4 success stories, WRCF Documentary, Annual learning forum, pictorial booklet | 5 | 5
|  | Achieved | 0 | 2 WRCF awareness-raising session with House of Chiefs WRCF launch and other publicity events | 2 short videos completed, Foundation Website established | The following were produced: WRCF video documentary; Annual Learning Forum held in collaboration with Chamber of Commerce; Success stories written; pictorial booklets of climate change produced and printed in collaboration with CSLP; and climate change pictorial posters
Source
Programme Management monitoring
IMPACT WEIGHTING | Output Indicator 4.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
5% | Number of plans developed to address community issues facilitated by WRCF | Planned | N/a | Validation workshop | 0 | 1 community initiated plan. A community plan will be developed for Teleku Bokaso in Ellembelle district | 2 | 3 | 6
|  | Achieved | N/a | Validation workshop | TVET Concept note drafted, WRCF has held a meeting with the District Assemblies in the 6 districts to influence their development plans with the issues emerging from the dialogue; • The Coastal Implementing Partners Meetings have led to an MoU signed between WRCF and CSLP to support ‘climate smart agriculture’ interventions, as stated in output one | A community development plan, initiated by Azuleloanu, with support from WRCF
Source
Programme Management monitoring
INPUTS (£ ) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  |  |  | RISK RATING
5% contract value - £421,421
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19) | Assumptions
Effective grant management | Establishishment and utilization of effective grant management and accounting systems | Planned | N/a | Accounting systems in place for accountable grants | Establishment of grant management system TAMIS Staff training and utilization of grant management system | WRCF Programme complies with grant management system | WRCF Programme complies with grant management system | WRCF Programme complies with grant management system | Transition to locally owned grants management system | No legal or regulatory environment changes that impact the programme. No significant inflation / currency valuation adjustments.
IMPACT WEIGHTING |  | Achieved | N/a | Achieved | • TAMIS grant management is up and running and the current grants have been capture in TAMIS. 2. Staff training and utilization of grant management system • Finance/Operations Manager, Dialogue liaison Officer and the Chief Operation Officer have been trained in the TAMIS grant module | WRCF complies with its Grant Management System, which is the DAI TAMIS system
5% |  | Source
Programme Management monitoring, WRCF accounting systems
INPUTS (£ ) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) |  |  |  |  | RISK RATING
| 0% contract value | [8 empty] | Minor
INPUTS (HR) | DFID (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
Improved Community Resilience to Climate Change and Environmental Risk | Number of people with increased awareness of climate and Environmental Risks | Planned |  |  | The climate change output was created in 2017 | 3000 people with increased awareness in climate change | 3000 people with increased awareness in climate change | 2000 people with increased awareness in climate change | 8000
IMPACT WEIGHTING |  | Achieved |  |  |  | Total of 3269 3,139 participants at climate change sensitization through the dialogue platform 130 vegetable farmers
10% |  | Source
INPUT ( £) | Output Indicator 6.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Number of people benefiting from Climate Resilience or Environmental Risk Mitigation | Planned |  |  |  | 0 | 200 | 400 | 400
Source

## LogFrame Revised 2018
Smart Guide
|  |  |  | DFID FUNDING - £8.5m |  |  |  | BRIDGE YEAR
PROJECT TITLE | Western Region Coastal Foundation (WRCF) Log frame (Sept 2018) | [8 empty] | Assumptions
IMPACT | Impact Indicator 1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2020)
Improved stability and inclusive development prospects in Western Region | Average poverty rates in the Western Region coastal districts | Planned | Poverty incidence: 21.9% (Western Region, GLSS 2012/13) | N/A | 16.1% | The survey will not be done this year | 17.05% | The survey will not be done this year | 17%
|  | Achieved | N/A | N/A | 17.9% | N/A |  | N/A
Source
GLSS (2012/13 and 2020) and Citizen Perceptions and Socio-Economic Survey (CPSES, 2016 and 2018/19). Data collected semi-annually.
| Impact Indicator 2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Citizen perceptions of local stability, development equity and economic prospects in the Western Region | Planned | The baseline was condcuted in 2016 using the Ciitizes Perception and Socio Economic Survey | N/A | Baseline was conducted in 2016 | 22% positive perceptions of local political stability 21% positive perceptions of development equity 11% positive perceptions of economic prospects | 42.6% positive perceptions of local political stability 38.6 % positive perceptions of development equity 25.3% positive perceptions of economic prospects | 45% positive perceptions of local political stability 43% positive perceptions of development equity 30% positive perceptions of economic prospects | 45% positive perceptions of local political stability 43% positive perceptions of development equity 30% positive perceptions of economic prospects
|  | Achieved | 21% positive perceptions of local political stability 20% positive perceptions of development equity 10% positive perceptions of economic prospects | N/A | 21% positive perceptions of local political stability 20% positive perceptions of development equity 10% positive perceptions of economic prospects | 42.6% positive perceptions of local political stability 38.6 % positive perceptions of development equity 25.3% positive perceptions of economic prospects
Source
Afrobarometer (2014 and 2020) and Citizen Perceptions and Socio-Economic Survey (CPSES, 2016 and 2018/19). Data collected annually.
OUTCOME | Outcome Indicator 1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
Expectations managed and met and constructive relationships between communities, government and industry built | % of TVET graduates and economic intervention beneficiaries with incresed income (disaggregated by sex / youth) | Planned | N/A | N/A | N/A | N/A | 80% (160 people) of directly trained TVET beneficiaries (minimum of 10% women and 90% youth) and 30% (18 people) of econnomic beneficiaries increase income | 80% (320 people) of directly trained TVET beneficiaries and 40% (160 people) of indirect beneficiaries (students /apprentices) and 30% (30 people) of econnomic beneficiaries increase income | 80% (480 people) of directly trained TVET beneficiaries and 40% (160 people) of indirect beneficiaries (students /apprentices) and 30% (48 people) of econnomic beneficiaries increase income
|  | Achieved | N/A | N/A | N/A | N/A
Source
WRCF and scale-up partner intervention monitoring and reporting systems., cross-checked with Citizen Perceptions and Socio-Economic Survey (CPSES) data.
| Outcome Indicator 2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| WRCF facilitates government, industry and technical institutes to adopt industry training standards and international accreditation in oil and gas related programmes | Planned | N/A | N/A | N/A | N/A | N/A | x5 oil and gas related programmes adopt standards and accreditation (welding, electrical/ electronics, mechanical, hydraulics, instrumentalization) | x5 oil and gas related programmes adopt standards and accreditation (welding, electrical/ electronics, mechanical, hydraulics, instrumentalization)
|  | Achieved | N/A | N/A | N/A | N/A
Source
Report from the resource mobilisation and private liaison monitoring, WRCF accounting systems, monitoring reports
| Outcome Indicator 3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| Sustainable foundation established and functioning | Planned | N/A | N/A | N/A | N/A | Foundation is able to cover 30% of its operational cost | Foundation covers 100% of its operational cost | Foundation covers 100% of its operational cost
|  | Achieved | N/A
Source
Semi-annual Dialogue Structure surveys/CPSES Survey
| Outcome Indicator 4 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
| VFM - Activity Fund Leverage: Non-DFID funding for WRCF supported interventions | Planned | N/A | N/A | £240,000 ($312,000) | £560,000 ($728,000) CSLP, Oil&Gas Capacity Building Project ( TVET) | £1,300,000 ($1,690000) | £3,000,000 ( $3900,000) | £5,100,000 ($ 6,630,000)
|  | Achieved | N/A | N/A | WRCF and Coastal Sustainable Landscapes Project (CSLP) signed a memorandum of understanding (MoU) to support ‘climate smart agriculture’ interventions.The CSLP programme has been renewed with budget of US$6.5million over 5 years. This would help towards leveraging non-DFID funds for the Foundation’s activities | Leveraged $3m worth of welding equipment Oil & Gas Capacity Building Project Project . $1m of CSLP budget on climate smart agriculture
Source
Semi-annual Dialogue Structure surveys/CPSES Survey
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Target (2015-19)
An independent, self-sustaining, open and inclusive dialogue platform for communities, government and industry established | WRCF MoU for funding executed (Government, Industry and donors) | Planned | N/A | N/A | N/A | N/A | x1 MoU signed | x1 MoU Funding commitment secured | Funding for the dialogue for at least one-year cycle
|  | Achieved | N/A | N/A | N/A | N/A
Source
Signed MoU documents with Government, Industry and/ or donors
| Output Indicator 1.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of CSR interventions informed and influenced by WRCF dialogue data to address community needs | Planned | N/A | N/A | N/A | N/A | 5 | 10 | 15
|  | Achieved | N/A | N/A | N/A | N/A
Source
Programme management monitoring, quarterly reports
| Output Indicator 1.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19) | RISK RATING
| Non-DFID funds raised to sustain the dialogue | Planned | N/A | N/A | N/A | N/A | £100,000 (committed by Jan 2019) | £400,000 (committed by end of November 2019) | £500,000 (total committed by end of November 2019) | Major-: [Key risk relates to willingness of stakeholders to contribute to operational funds]
|  | Achieved | N/A | N/A | N/A | N/A
Source
Resource mobilisation report, WRCF accounting systems
| Output Indicator 1.4 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of relevant data sets collected and disseminated to partners as a result of community dialogue | Planned | N/A | N/A | N/A | N/A | 3 | 3 | 6
|  | Achieved | N/A | N/A | N/A | N/A
Source
Programme management monitoring, quarterly reports
| Output Indicator 1.5 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of Western Region coastal district residents engaged in the Dialogue Structure (disaggregated by sex -50% male and 50% female and youth - 50% under the age of 30 years old) | Planned | 0 directly reached 0 indirectly reached | 21,600 ( 30.8% of the end target) directly/uniquely reached 86,400 indirectly reached | 18,000 (25.6% of the target) directly/uniquely reached 72,000 indirectly reached | 21,900 (31.2% of the end target) directly/uniquely reached 87,600 indirectly reached | New 2,610 directly reached Indirectly reached 10,440 | New 2,610 people directly reached 10,440 indirectly reached | 66,720 directly reached 266,880 indirectly reached
|  | Achieved | N/A | 35,000 (49.9% of end target) directly/uniquely reached 140,000 indirectly reached | 29,971 (42.6%) of the end target) directly/uniquely reached | 23,655 directly reached
Source
Dialogue data
IMPACT WEIGHTING- 40 % | DFID (£)
INPUTS (£) | 40% of contract value -£3.4m
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
Community livelihoods improved through Industry CSR support for economic development interventions | No. of OGPs and other funders commiting finance above £25,000 ($32,500) for scaling-up livelihood and economic development initiatives | Planned | N/A | N/A | N/A | N/A | 1 | 2 | 3
|  | Achieved | N/A | N/A | N/A | N/A
Source
CAC meeting minutes, WRCF accounts, partner contracts
| Output Indicator 2.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of beneficiaries trained on new aquaculture, CSA and other economic development practices supported by industry | Planned | N/A | N/A | N/A | N/A | 60 | 100 | 160 | Market expanssion at natural growth rate is not disrupted by exogneous events or endogenous events (including legal and regulatory changes). New market entrants or new technologies/products do not disrupt market system. Vested interests do not disrupt or block market system interventions.
|  | Achieved | N/A | N/A | N/A | N/A
Source
CAC meeting minutes, monitoring and quarterly reports
| Output Indicator 2.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of relevant economic development publication reports produced and shared with stakeholders | Planned | N/A | N/A | N/A | N/A | 2 | 3 | 5
|  | Achieved | N/A | N/A | N/A | N/A
Source
CAC meeting minutes, monitoring reports and quarterly reports
IMPACT WEIGHTING- 25% | [8 empty] | 8
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
25% contract value - £2,107,105
IMPACT WEIGHTING - 20% | DFID (£)
INPUTS (£) | 10% of contract value - £0.85m
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
Community TVET skills enhanced by facilitating dialogue and coordination with public and private educational and training institutions using a self-sustaining revenue stream to generate funds derived from industry | No. of people trained on TVET skills related to the O&G sector and allied industries - disagregated by students and artisans and industry employees (90% male, 10% female) | Planned | N/A | N/A | N/A | N/A | 200 | 400 | 600
|  | Achieved | N/A | N/A | N/A | N/A
Source
Monitoring and Reporting
| Output Indicator 3.2 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of Oil & Gas related courses supported by industry | Planned | N/A | N/A | N/A | N/A | 3 | 4 | 7
|  | Achieved | N/A | N/A | N/A | N/A
| Output Indicator 3.3 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19)
| No. of instructors trained to industry standard in OGP skills | Planned | N/A | N/A | N/A | 12 | 20 | 30 | 62
|  | Achieved | N/A | N/A | N/A | 15
Source
Monitoring and Reporting
| Output Indicator 3.4 |  | Baseline | Inception (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Milestone 4 (2019) | Cumulative Target (2015-19) | RISK RATING
| Total finance secured from industry and other donors to support skills development | Planned | N/A | N/A | N/A | N/A | 200000 | 600000 | 800000 | Moderate [Key risk relates to potential to attract co-investment required to scale inverventions and achieve outcome targets].
|  | Achieved | N/A | N/A | N/A | £215,000 ($280,000)
Source
WRCF accounts, Monitoring and Reporting
IMPACT WEIGHTING - 40% | DFID (£)
INPUTS (£) | 50% contract value - £4.25m

## Indicator definitions
Indicator | Definition | Milestone explanation
Impact Indicator 1
Average poverty rates in the Western Region coastal districts | Following the 'Progress out of Poverty' Index (PPI) Ghana methodology for calculating consumption poverty, combined urban and rural areas, using the new definition of poverty and the 2005 national poverty line of $2 a day, deflated using the national poverty line (Schriener, 2015, p.150). Baseline figures from GLSS 2012/13 Poverty Profile in Ghana for the Western Region. Milestones 1 and 3 calculated using the project administered Community Perceptions and Socio-Economic Survey, which incorporates the same GLSS questions on consumption poverty. In 2013, the GLSS figure of 21.9% represents the whole western region. The WRCF Citizens perception and socio economic survey which was conducted in 2016 covered the 6 coastal districts with a poverty rate of 17.9%. Two years after, the CPSES projected that poverty rates in the six coastal districts of Western Region will be around 17.1%. This will be assessed through a Citizens Perception and Socio Economic survey which will be conducted by WRCF in 2018. | Milestones and targets are based on a linear 14-point reduction in prevalence of household consumption poverty at the $2 a day level over the life of the programme, as was seen in the Western Region from 2005/06 to 2012/13. % of TVET graduates who apply their skills in the Oil and Gas industry value chains and allied industries as a result of training undertaken and/or influenced by WRCF and % of economic intervention beneficiaries with increased incomes are targeted at the $2 a day level, meaning that households formerly below the poverty line which benefit from WRCF supported interventions will be raised above it. Projections have been quite conservative as WRCF may not significantly affect the poverty levels of citizens in the 6 coastal districts with its interventions . WRCF will conduct Citizens Perception Survey in 2018 using the same indicators used in 2016 to assess and compare the level of poverty incidence in the six coastal districts between 2016 and 2018.
Impact Indicator 2
Citizen perceptions of local stability, development equity and economic prospects in the Western Region | This indicator measures how local citizens perceive stability in the six coastal districts. It estimates how social, economic and political stability/security is improving, deteriorating or unchanged. Baseline questionnaire incorporated questions relating to perceptions of local stability, development equity and economic prospects. An index was defined to incorporate / aggregate findings for the purpose of the logframe, with more disaggregated data provided in the baseline report and follow-up survey reports. - Local stability is an unweighted aggregate of responses to CPSES questions from Sections 8 and 9 (Perceptions of security in the community, political involvement and corruption). - Development equity is an aggregate of responses to CPSES questions 7.24-7.34 (Openness, effectiveness, and fairness of local government, traditional leaders, INGOs, and the oil and gas industry). - Economic prospects as an unweighted aggregate of responses to the questions 7.6-7.12 (How would you describe the present economic conditions in this country / your community / personally, and compared to 12 months ago?) | The Citizens Perception and Socio Economic survey which was conducted in 2016 by WRCF is used as the baseline for this indicator. The baseline figures for this indicator in 2016 are as follows: 21% positive perceptions of local political stability 20% positive perceptions of development equity 10% positive perceptions of economic prospects. The dialogue satisfaction survey which was conducted in September 2017 included questions that looked at the citizens perception of these indicators. It is acknowledged that WRCF makes minimal contibution to these perception indicators and therefore the projected positive perception of citizens on these indicators are moderate. In 2017, the same indicators were assessed using the same questions with the following results: 42.6% positive perceptions of local political stability, 38.6 % positive perceptions of development equity and 25.3% positive perceptions of economic prospects. The same set of questions will be part of the 2018 Citizens Perception Survey to assess changes in citiens perception in 2018 following all the development efforts by Government, Industry and Development Partners.
Outcome Indicator 1
% of TVET graduates and economic intervention beneficiaries with incresed income (disaggregated by sex / youth) | WRCF faciliates the provision of TVET skills to Instructors of Technical Institutes, employees of companies and artisans who wish to enhance their skills to improve their chances of providing goods and services to the oil and gas value chain. The instructors and the mastercraftmen are expected to pass on the skills to students and apprentices. WRCF has baseline figures regarding household incomes of its pilot beneficiaries.It has also undertaken an assessment of the effect of its pilots on the quality of life of its beneficiries including changes in household incomes,and productivity. WRCF plans to engage industry to scale-up its economic interventions by securing funding for WRCF to expand the economic inerventions, or the company may also apply the lessons and best practices from WRCF interventions without WRCF being the main facilitator. In both cases WRCF will track changes in income for beneficiaries and apply attribution based on its contribution to the increased income. Measurement of the indicator This indicator will track % of student graduates who are working at any level of the oil & gas value chain and allied industry; and those who benefit from Economic Development Initatives. It will also count artisans or self-employed who have graduated from WRCF TVET training and are doing activities which require the new skills they have acquired from WRCF training. WRCF has baseline information for all trainees regarding the type of work they do and their current incomes. Any difference in the type of job and income earned at the time of measurement could be attributed to WRCF training, holding other factors constant. This indicator will count graduates who are doing full-time jobs, part-time jobs and inernship with Oil & Gas related industry, directly trained-including artisans, training instructors, and employees of industry. Indirectly trained refers to students who are trained by the instructors who received training from WRCF and apprentices who are trained by the mastercraftmen who recieved training from WRCF. | In 2018, WRCF will track 2017 graduates of WRCF TVET training; along with those benefitiing from Economic Development Initiatives who are engaged in activities and services related to oil & gas and allied industry . In 2018, it is estimated that at least 80% of persons who recieved WRCF training (directly trained-including artisans, training instructors, employees of industry) should be undertaking activities related to oil and gas or should enhance their expertise to take up higher skilled jobs. It is expected that, at least one industry will commit to provide funding for scale-up or adopt the best practices of WRCF pilots for scale-up. At least 30% of those who benefit from WRCF facilitated industry led economic intervention will increase their incomes in 2018.
Outcome Indicator 2
WRCF facilitates government, industry and technical institutes to adopt industry training standards and international accreditation in oil and gas related programmes | In order to strength training standards in the TVET sector, WRCF is facilitating the government, industry and technical institutes to adopt industry training standards and adopt international accreditation certificates in oil and gas programmes. | By the end of Nov 2019, WRCF aims to facilitate x5 oil and gas related programmes (indicatively - welding, electrical/ electronics, mechanical, hydraulics, instrumentalization)
Outcome Indicator 3
Sustainable foundation established and functioning | One of the expected outcomes of the WRCF programme is to establish a sustainable foundation which is self financing to be able to deliver services to the citizens of the six coastal districts of Western Region. In order for the foundation to be sustainable, it needs to secure funding to cover all of its cost by the end of Nov 2019. A combination of resource mobilisation effort for TVET, dialogue and economic intervention is expected to generate the needed sustainable funding for the foundation. | By the end of 2018, the foundation is expected raise funding that will be able to cover 30% of its annual cost. By the end of Nov 2019, the foundation wil cover 100% of its total cost.
Outcome Indicator 4
Activity fund leverage: Non-DFID funding leveraged for WRCF supported interventions (£ per year, cumulative target) | This indicator refers to the value of services undertaken by other organisations with WRCF input or support. The value attributed to WRCF depends on the extent of WRCF influence or contribution. The original business case expected that the WRCF would be able to leverage £16m of external funding in addition to the £8.5m provided by DFID. Resource mobilisation will include direct funding of the programme by a third party including industry and donors as well as leveraged funding through stakeholder projects influenced by WRCF. Leveraged funding is calculated as the value of all development projects from stakeholders where WRCF significantly influenced one or more of the following: identification, design, technical assistance during implementation, monitoring and results of performance, and/or communications, based on evidence supplied by partners on project value and WRCF influence. | Following a realistic growth curve, it is anticipated that WRCF will be able to raise 40% of the target amount in the first five years of the programme. In 2018, WRCF intends to leverage £1,300,000 through the Oil and Gas Capacity Building Project and other CSR interventions which will be influenced by WRCF activities. The Oil and Gas Capacity Building Project is a $58,000,000 World Bank project worth of modern equipment to train students, employees of extractive industry and the private sector in extractive industry relevant skills. WRCF is facilitating optimal use of the equipment for skills development. The leveraged amount depends on how much work WRCF executes with the use of the equipment in a particicular year.
Output Indicator 1.1
WRCF MoU for funding executed (Government, Industry and donors) | This indicator refers to the number and type of Memorandum of Understanding (MoU) signed with funding commitment and disbursement to sustain the dialogue platform beyond DFID funding. With the reduction in funding from DFID from 2018, it is expected that stakeholders such as Government, Industry and donors who see value in the WRCF services provided by the dialogue platform will contibute funding for its sustainability. | In 2018, WRCF expects to sign and execute an MoU with the Petroleum Commission (PC). The PC, as the regulator of Oil and Gas production, will impress upon the Oil and Gas Companies to express commitment to provide funding for the WRCF dialogue.
Output Indicator 1.2
No. of CSR interventions informed and influenced by WRCF dialogue data to address community needs | WRCF provides support for effecitve planning and implementation of Industry CSR and/or Government development projects. The support is provided mainly in the provision relevant data from the dialogue to inform the decision of the companiies to decide what, where and how to plan and implement CSR in the coastal communities. WRCF also uses TVET dialogue to support implementation of skills related to CSR . | In 2018, it is planned that WRCF will inform or influence the planning and implementation of x5 CSR projects which can be in community development, economic intervention or skills development.
Output Indicator 1.3
Non-DFID funds raised to sustain the dialogue | This indictator refers to funding of the dialogue operating costs that does not come from DFID. The expectation is that this will largely come from Oil and Gas Companies through the PC. Annual operating costs are currently £400,000, with these costs including: salaries, transportation, fuel and utilities, involved in the day-to-day running of the dilogue. Targets have been set based on a realistic growth and success of resource mobilisation to cover operations cost, and on the need to partially fund operational costs in 2018 and fully fund operational costs in 2019. From 2020, the dialoue will become fully independent in which case it is approximated that total cost of operations will decline by one-third as the project will be fully localized. Therefore WRCF projects total cost of operations will decline to £200,000. | It is expected that DFID will fund all project operational costs in 2015, 2016 and 2017. From 2018 onwards, increasing resources will be leveraged to cover an increasing percentage of annual operating costs to cover the entire operating cost of the final project year in 2019. In 2018, it is projected that an amount of £80,000 will be committed through the MoU with PC with an additional £400,000 commitment in 2019.
Output Indicator 1.4
No. of relevant data sets collected and disseminated to partners as a result of community dialogue | As part of the effort by WRCF to make effective use of industry CSR and Government development projects, WRCF will analyse the data from the dialogue, and disaggregate the data into themes that are of relevance to different stakeholders. These reports will be shared with industry and government to inform planning and implementaion of interventions in the communities. The reports will include the profile of OGP CSR projects across 100 coastal communities, community perception/ satisfaction with industry CSR reports, community perception of Government development projects, impact of oil & gas operations on the livelihood of coastal residents, and OGP and Government response to community concerns/needs. | In 2018, it is planned that 3 of such thematic analyses will be produced and disseminated to WRCF partners. These data sets will include: CSR Profile Report, Satisfaction with Industry CSR report, and Community Issues and Priorisation Report
Output Indicator 1.5
No. of Western Region coastal district residents engaged in the Dialogue Structure (disaggregated by sex -50% male and 50% female and youth - 50% under the age of 30 years old) | Engaged' refers to Individual residents in the Western Region who attend any of the levels of conversations. Numbers indirectly engaged are household members of those involved in the conversations. This gives an indication of the category of people reached by the dialogue. To avoid double-counting, infomation is recorded for all participants on whether they have ever attended a Dialogue Structure conversation before, and whether they have attended another conversation this cycle. Monitoring system will track type of people involved, including according to education, gender, age and employment status. Indirect reach assumes each participant spreads the message to 4 people i.e. the average household size.About 50% of the indirect reach will be attained through media. | In 2018, It is expected that 2,610 new people from all the 100 communities will be directly reached/ engaged across all conversation levels namely: Community, District, and Tradtional Authorities. Because all the 100 communities have had comversations in the past (2015-2017), it is expected that most of the people (70%) who will attend 2018 conversations will be repeated.
Output indicator 2.1
No. of OGPs and other funders commiting finance above £25,000 ($32,500) for scaling-up livelihood and economic development initiatives | WRCF plans to enagage industry to scale up its economic interventions by providing funding for WRCF to expand the economic inerventions. The external organisation from industry may also apply the lessons and best practices from WRCF interventions without WRCF being the main facilitator. This indicator will track the number of organisations and funding received to expand or replicate the best practices of WRCF pilots in the Economic Development output. WRCF could provide the OGP which scales-up the pilots with survices such as identification or design of an intervention, technical assistance during implementation of the intervention, monitoring and results/performance measurement of an intervention, and communications/publicity. | In 2018, it is planned that at least x1 oprganisation will either commit to provide funding over $32,000 for scale-up or adopt the best practices of WRCF pilots for replication.
Output Indicator 2.2
No. of beneficiaries trained on new aquaculture, CSA and other economic development practices supported by industry | As part of the scale-up of the economic interventions through third party funding, new people will be trained on theory and practice of the interventions ()aquaculture and CSA). In order to avoid pitfalls in the implementation, new beneficiaries will be trained on the best practices and lessons from the WRCF pilots which can include technical and managerial training. | In 2018, it is planned that 60 people will receive training in the application of new knowledge for efficient implementation and management of economic interventions through funding from the private sector or Government.
Output Indicator 2.3
No. of relevant economic development publication reports produced and shared with stakeholders | As part of documenting results, lessons learnt and good practices of WRCF pilot projects, relevant reports and publications will be produced and shared with stakeholders in the private and public sectors to inform programming. The development reports include evaluation reports of the aquaculture and Climate Smart Agriculture Pilots, success stories, best practices of livelihood enhancement and recommendation for scale- up of economic interventions. | Two of the development reports from the economic development interventions will be produced in 2018
Output Indicator 3.1
No. of people trained on TVET skills related to the O&G sector and allied industries - disagregated by students and artisans and industry employees (50% male, 50% female, 90% below the age of 30) | This indicator refers to individuals who receive direct training from the WRCF TVET programme. The trainees include instructors of Technical Insitutions, students of Technical Insitutions who acquire enhanced training from the Instructors who received skills upgrading training facilitated by WRCF and artisans trained to improve proficiency at work and improving their chances of acquiring jobs in the Oil & Gas value chain. | It is expected that at least 100 individuals will receive skills upgrading training in 2018
Output Indicator 3.2
No. of Oil & Gas related courses supported by industry | This indicators measures the number of courses that are supported by industry. These courses include welding, mechanical, fabrication, electrical,hydraulics and instrumentalisation. WRCF facilitates the skills development training through funding from the private sector. | WRCF started the faciliation of training for welders in 2016. It is expected that 2 more courses (electricals and instrumentation) will be added to welding in 2018
Output Indicator 3.3
No. of instructors trained to industry standard in OGP skills | The TVET needs assessment conducted by CPI in 2016 revealed gross inadequacies in the skills of the instructors of Technical Training Institutions. As part of the sustainable model for employable skills development in the Technical Training Institutions, WRCF is facilitating upgrading of Instructor competencies through competency based training. Individual instructors who receive direct training from the WRCF TVET programme will be included in the milestone target. | It is estaimated that a total of 62 instructors of Technical Training Institutions will receive training from WRCF by the end of 2019. 15 instructors were trained in 2017. The number of instructors to be trained in 2018 is estaimated to be 20.
Output Indicator 3.4
Total finance secured from industry and other donors to support skills development | WRCF is leveraging on industry funding for the skills development training. A pipeline of funding sources for the skills develoment has been drawn-up to engage industry for the funding the WRCF TVET programme. | In 2018, WRCF has planned to receive £200,000 from industry to support its TVET programme.