Type of Review: Annual Review

Project Title: United Kingdom International Search and Rescue (UKISAR) Deployment Support Programme (203423)

Date started:	November 2012
Date review undertaken: November 2013

## Introduction and Context

What support is the UK providing?
The UK will provide £434,681 over a three period (November 2012 to March 2015) through the UK Fire and Rescue Services to support the training and standby costs of UK International Search and Rescue (UKISAR) teams provided by UK Fire and Rescue Services (former fire brigades). This support will ensure that UKISAR is ready to deploy for sudden onset emergencies, providing lifesaving support in the immediate aftermath of major disasters. / This funding will provide 24/7 availability of a trained, experienced UKISAR team, equipped to the necessary international standards. UKISAR will be able to draw on 260 fully trained responders, along with a medical support team, to deploy teams of between 45 and 68 personnel in response to sudden onset emergencies – especially earthquakes. / To complement UKISAR activities the UK will provide an additional £85,000 over 2 years (June 2013-March 2015) to support Fire AID activities overseas. They will work with local government agencies, communities and fire & rescue services to provide much needed equipment, accompanied by training for trainers and assistance with emergency response strategies. This will form part of a sustainable local initiative, involving civil society and local policy makers to make maximum impact. / Total cost of the project will be up to £519,681.

What are the expected results?
The expected results are that teams of international standard (INSARAG) search and rescue personnel, all serving professionals with UK Fire and Rescue Services, are fully trained, equipped and ready for very rapid deployment, enabling DFID to rescue victims of overseas disasters, help to co-ordinate local rescue efforts and to contribute to wider international rescue capacity. / The size of such a UKISAR deployment typically will be up to 60 to 70 personnel drawn from the 15 Fire and Rescue services. The UKISAR deployment frequently includes rescue dogs, and is equipped to provide a “medium” rescue response as classified by the United Nations, i.e. the capability to rescue victims from collapsed buildings constructed from steel reinforced concrete. If necessary, the UK also has the capacity to provide a “heavy” search and rescue deployment, i.e. the capability to rescue victims from collapsed steel framed buildings - the maximum rescue capability that can be effectively deployed internationally in disasters. / UK support will continue to enable a “medium”, or if necessary “heavy” deployment to be drawn from the 15 UK Fire and Rescue services; staffed, trained and equipped to the necessary standards of expertise and readiness to ensure a timely and appropriate UK response and 24/7 standby. / The results of UK support to Fire AID will be a strengthened and extended network to make best use of expert volunteers and trainers; a website established to give recognition to UK donations and encourage wider membership; together with a database to track good quality, redundant UK equipment available for donation to fire & rescue services in DFID target countries. This assistance will help support preparedness for fire and other risks, vital for preventing and responding to disasters and conflict.

What is the context in which UK support is provided?
DFID wishes to maintain a capacity to send UK International Search and Rescue (UKISAR) teams to overseas disasters, especially to areas hit by earthquakes, for example Haiti in 2010 and New Zealand and Japan in 2011. Long before these recent examples, successive British governments have been committed to helping international search and rescue responses to large-scale overseas disasters. Consequently HMG’s capability and commitment in this field is substantial, both as a UK response and as part of the international search and rescue network operated under UN auspices. UK Search and Rescue Teams are highly respected internationally, and are trained and certified to the highest international standards overseen by the International Search and Rescue Advisory Group (INSARAG). / UKISAR personnel are provided from 15 UK Fire and Rescue Services from across the UK, with the overall coordination and oversight being provided by the Chief Fire Officers Association (CFOA) group, through CFOA National Resilience. The UK is an Active Member of INSARAG, with the UK Fire and Rescue Service providing the necessary technical representation at the INSARAG meetings. / The 2010 independent Humanitarian Emergency Response Review (HERR)[1] chaired by Lord Ashdown, concluded that; DFID should retain its existing search and rescue capability, although it should be more selective in where UK search and rescue teams are deployed. Decisions to deploy should take into account the effect of distance between the UK and the disaster zone on the life-saving value of deployment in the critical early hours of response. / DFID support to UKISAR is needed to ensure the personnel are staffed, trained and equipped in a state of readiness for rapid and effective deployment for the UK’s international response to sudden onset emergencies. These international requirements are additional to those required by for domestic UK response, and would not be appropriate or possible to be covered by existing national/county level Fire and Rescue Service budgets. / UK fire services donate high quality fire and rescue equipment to developing countries. However, due to concern about terrorism and misuse of ‘trojan’ vehicles it is now riskier for UK fire services to provide redundant equipment overseas. To help address this problem, DFID will support Fire AID in its efforts to match the availability of high quality, second-hand fire fighting and crash extrication equipment donated by UK fire services, with well-researched needs in destination countries working in partnership with local people. These donations will be accompanied by top-quality training for trainers and will form part of a sustainable local fire prevention, injury reduction and road safety strategy.
[1] Humanitarian and Emergency response Review (HERR), 2010

## Section A: Detailed Output Scoring

Output 1: Current frameworks and processes are used to develop and deliver operational training to ensure the competence of all operational staff. This will include acquisition, developmental and maintenance of competence training.
Output 1 score and performance description: A
Progress against expected results: / Progress is assessed against the following output indicators: / Number of staff completing technician acquisition and maintenance course (Year 1 target – 220 staff trained): In 2012/13 National Resilience delivered a central training programme to meet a range of core training needs, and in total 791 course places were delivered. However, as some people attended more than one course, these central records do not show how many individuals received training, or how many benefited from DFID funded training, this data would need to be gathered from individual fire service brigades. / Number of staff completing specialist and technical support acquisition and maintenance courses (Year 1 target – 40 staff trained). Target met – details below: / UK ISAR Structural engineer has completed EU Technical experts (September) and FEMA structural specialist courses (November). / Sector medic course completed by 45 personnel. / Trauma Risk management course delivered in June 2013 and attended by 23 personnel. / Specialist slinger/signaller and appointed persons courses delivered Dec 12 and attended by 16 personnel. / Command support communications course delivered to 21 personnel. / 8 Medical Team members and canine handlers have undertaken a specialist veterinary care course with the Military Veterinary school (Nov 13). / Specialist international modules continue to be delivered. / UKISAR Strategic advisory module 1 delivered at DFID (Sep 13). Further module delivery planned throughout 2014. / Number of national training exercises completed that include full deployment cycle (Year 1 target – 2 national exercises successfully completed) - All UK ISAR personnel are required to participate in a national exercise annually to maintain international readiness: This year a large number of personnel participated in national and international exercises. For 2012/13 there were 9 major UK exercises, plus the following UK ISAR only national and international exercises: / Exercise type Interaction with international teams / Exercise Tusker, UK / November 2012 The main outcomes from the exercise were designed to introduce the UK ISAR concept of operations to new team members commencing with the alert and going through all phases including full deployment and operation of the team in an overseas environment. It was also used to introduce the new INSARAG coordination and assessment methodology and to field test the structure and processes prior to world wide implementation. Personnel and teams attended the exercise from Belgium, USA, Australia, Switzerland, Sweden and the United Arab Emirates. / EU field exercise, Denmark 2013 The team deployed a medium team of 45 personnel to an EU exercise in Denmark. This exercise tested our response under the EU Civil Protection Mechanism, and was designed to give teams the opportunity to test European cooperation in the realistic environment of a functional field exercise, to test the integration of functions and experience the operational and political complexity of international disaster response. / Teams from Iceland, Estonia, and Czech Republic. / UN earthquake simulation, Poland, 2013 Earthquake scenario with teams from Germany, Spain, Poland, Russia, Belarus / INSARAG earthquake simulation exercise Switzerland 2012/13 Held in Kriens, Switzerland the exercise was based around an earthquake scenario and involved teams from 15 countries being tested on team processes including assessment, coordination, safety, security, logistics, command, and information management. Six personnel represented the main components of the team. / EU field exercise, Italy 2013 Heavy deployment with Estonia, Hungarian and Austrian USAR teams. / Exercise Poacher, UK / Planned for Feb 2014 Full heavy deployment exercise in preparation for INSARAG external classification planned for 2014 / UK ISAR participation at these events helped to both develop the skills of personnel, foster professional relationships and maintain UK search and rescue influence at the strategic level. / Recommendations: / UKISAR personnel have undertaken a broad range of training this year, including national and international training exercises. / DFID should review indicators (particularly 1.1 and 1.2) and milestone targets with UKISAR. Currently, it is not easy to measure exactly how many staff have benefited from DFID funded training. National Resilience Centre can provide the numbers of courses delivered centrally, and UKISAR have said that it would take a large data collection exercise involving all participating UKISAR brigades to determine an accurate figure of total UKISAR staff trained. / Impact Weighting (%):29 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: The UK ISAR heavy equipment cache is maintained at a constant state of mission readiness and complies with general requirements as determined by the INSARAG guidelines. This includes planned and agreed maintenance, R&D and asset refresh programmes.
Output 2 score and performance description: A
Progress against expected results: / Progress is assessed against the following output indicators: / The UK ISAR Medical Team (UMT) is able to deliver the required level of effective medical care in support of UK ISAR deployments. Includes charges applied for maintenance, logistics, drug turnover and staff costs – (Year 1 target – Equipment needs addressed and readiness maintained) : / Work has been completed on the review of medical equipment levels, type and suitability. Weight and volume have been reduced by approximately 60%, and UKISAR are now renegotiating deployment, training and servicing costs based on the new equipment scales. / DFID funding has allowed financing of all medical equipment, servicing, turnover, storage and staff costs. Plus procurement of 2 x medical lite giving sets, 2 x medical training packs and 1 x medical manikin which has improved training delivery. UKISAR are currently planning to procure essential advanced trauma monitoring equipment. / The UK ISAR team has a mission ready complement of logistical support, coordination, administration, IT, communications, sanitation, accommodation, showering, food, and water, with appropriate maintenance and storage arrangements – (Year 1 target – support arrangements and equipment readiness maintained): / UK ISAR has established a logistical and equipment working group to carry out an overarching review of all equipment carried for deployments. DFID funding has helped procure equipment that reduces weight, and volume but maintains operational effectiveness and capability. This has included lighting, generators, breaking in tools. In addition the command support tentage and satellite communications have been upgraded. Further work will identify other areas of priority equipment spend. / The UK ISAR team has a mission ready complement of operational equipment including, shoring, breaking, confined space, hot cutting, working at height, technical search, lifting and moving and hydraulic rescue components – (Year 1 target – Equipment readiness maintained): / UK ISAR works to a three year asset refresh strategy and planned equipment maintenance programme under the DCLG long term capability maintenance programme. The strategy takes account of original contract life, manufactures life forecast and most importantly life prediction based upon nature and frequency of use, defect history and progressive wear and tear. Development of the asset refresh requirements has enabled a planned programme of implementation and ensures that UKISAR have all operational equipment stored within West Sussex FRS in a guaranteed mission readiness state. / Recommendations: / UKISAR has not provided a comprehensive list of equipment for deployment during the reporting year, due to no UKISAR deployments having taken place. However, we recommend that a revised list should be provided at least once a year for audit purposes, even if there have been no deployments. All other targets have been met. / Impact Weighting (%):29 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: UK ISAR makes an effective contribution to the development of INSARAG governance and methodologies to improve international urban search and rescue assistance.
Output 3 score and performance description: A
Progress against expected results: / UK ISAR make effective contributions to international, regional, national and technical meetings, that lead to improved guidance and processes (Year 1 target – continued improvement of INSARAG guidance and governance processes). / UK ISAR has representation on the three main INSARAG working groups covering operations, training and advanced medical support. These groups develop policy and guidelines for all international search and rescue teams worldwide, which allows the UK to be at the forefront of new design and delivery. Representatives also attend and support the INSARAG strategic meetings aimed at the political (donor) level of the International steering group, and regional (Africa, Middle East and Asia) levels, as well as the annual Team Leaders meeting. / A UKISAR team member took over the chairmanship of the INSARAG Operations working group (OWG) earlier this year. The OWG has been established to review the coordination methodology of assessment, search and rescue operations. The creation of the OWG was a direct result of feedback gained from various field operations culminating in a recommendation from the Haiti earthquake international debrief for INSARAG to form a specific group to develop an improved coordination methodology. The OWG has worked to produce a series of outputs, the most significant being the production of a new handbook, which will form part of the 2015 INSARAG guidelines. A huge amount of research, background work and testing was completed by the OWG and UK ISAR during its 30 month work cycle leading to the production of the handbook. The handbook provides guidance on the core elements considered essential for coordination purposes and should be fully adopted by all INSARAG classified teams. This work will help improve the coordination of major international disasters involving Urban Search and Rescue. / Recommendations: / UKISAR personnel are contributing to the development of INSARAG, including the development of the handbook, and urban search and rescue generally. This engagement needs to continue at current levels with other INSARAG members stepping forward to participate more broadly in working groups and to undertake work on behalf of INSARAG. There are no specific recommendations. / Impact Weighting (%):14 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: All UK ISAR personnel and canines on request are fully prepared to deploy overseas and operate in austere environments for up to 14 days.
Output 4 score and performance description: A
Progress against expected results: / Number of canines available for immediate response (Year 1 target – 12 dogs available). / Over the course of the last year UK ISAR management has taken the decision to reduce the operational canines available for international response from 14 to 12, in order to reduce costs, reduce the impact on UK national resilience and align to the 3:1 ratio principles. Due to staff retirements and reduction in numbers there is currently one vacancy within the rota groups. / Number of personnel who are fully vaccinated and prepared for immediate response – (Year 1 Target 240 personnel): / UK ISAR currently has an overall team strength of 266 personnel that are fully vaccinated. Each Fire and Rescue Service takes responsibility for ensuring that vaccinations are kept up to date through their respective Occupational Health Departments. The medical team and structural engineer take responsibility for their own upkeep and receipts are passed through the UK ISAR business centre and refunded from DFID budget. Each Service receives an identical contribution from the DFID budget. / Recommendations: / Logframe target for available dogs needs to be reduced from 14 to 12. / Impact Weighting (%):14 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 5: UK ISAR have effective management, and administration functions in place to support the operational elements of the team.
Output 5 score and performance description: A
Progress against expected results: / Management, administration and reporting functions are effectively undertaken in the appropriate timeframe – (Year 1 target – all financial and reporting data submitted as per timeframes in the operational guidelines): / Since the transition of UK ISAR into Chief Fire Officers Association (CFOA) National Resilience (NR) Limited (April 13) the team have been able to operate in a more structured and professional manner. The team currently has a full time coordinator (funded by CFOA NR and DFID) and access to a range of support functions (finance, procurement, documentation support, legal advice, centralised training, IT, transport). These arrangements have improved the support given to the operational teams. / Recommendations: / From DFID’s perspective, it appears that management and administrative functions have been improved since the CFOA National Resilience arrangements were put in place. Financial and narrative reporting has been provided to DFID as required. No recommendations. / Impact Weighting (%):9 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 6: Fire AID better able to track availability of UK equipment for donation and match to applications for assistance from target countries
Output 6 score and performance description: A
Progress against expected results: / This output was only agreed recently (June 2013) and reporting on results is not due until the end of March 2014. Initial activities are underway, and Fire Aid are conducting a procurement exercise to appoint a website developer to upgrade their current site. / Recommendations: / None / Impact Weighting (%):5 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: A / 1.3 Direct feedback from beneficiaries / DFID has not deployed UKISAR teams in any disaster during the past year. Therefore feedback from beneficiaries is not available.
1.4 Summary of overall progress / The UKISAR programme ensures rapid deployment readiness is in place and maintained. Large numbers of personnel have received specialist and other training and participated in training exercises. Equipment and logistical requirements have been met and refreshed where necessary. UKISAR has continued to engage with INSARAG, and has supported development of a new INSARAG handbook. Up to 240 personnel (plus canines) prepared for immediate response. The new management and administrative arrangements with CFOA National Resilience appear to be working well.
1.5 Key challenges / The programme benefits from the UK fire service commitment of staff time and other in-kind resources provided by the 15 fire and rescue services (FRS) and DCLG/CFOA arrangements. It is important that this support is maintained. The current restraints on expenditure in the public sector, has meant that most FRS’s are reducing staffing levels, and looking to instigate savings across all elements of service delivery. This could affect future staff attendance at training and development events. / The project also benefits from the use of FRS logistical support equipment. This equipment is owned by individual FRS, with storage provided by West Sussex FRS. There is a risk that access to these resources could be withdrawn or assets are no longer refreshed or maintained.
1.6 Annual Outcome Assessment / Project has met all required targets and is on track. This should enable UKISAR to remain fully prepared to provide a rapid, assessed and coordinated response, saving as many lives as possible within the limited timeframes available.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / The main costs associated with this project relate to the maintenance of equipment and training levels. The equipment required for training and for maintaining effective readiness and 24/7 deployable capacity has to be stored, maintained and replaced (if necessary). These activities were all costed in the project budget and expenditure has been in line with these estimates. / Cost drivers not included in the project budget are the salary and related costs of UK Fires and Rescue Service personnel, which are met by individual services. Also not included in the budget are the costs of equipment required for training and deployment. These costs are significant and would need to be met by DFID if the UK FRS was no longer able to fund these services. If this were to happen, DFID would have to reconsider the cost benefit of the provision of such a service. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There were no significant changes to the evidence base for this project. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation is currently planned.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The risks of this tested arrangement not being able maintain equipment, training and readiness to deploy a specialist team are currently low. This facility and capacity have been managed for more than ten years, and management and administration of this project have been strengthened by the new management and oversight provided by CFOA National Resilience. This arrangement is working well so far. / However, it is possible risks may increase. The effects of the current Comprehensive Spending Review has meant most UK Fire and Rescue Services are reducing staffing levels, and instigating savings across all levels of service delivery. This may prevent staff attendance at training and development events, and logistical and maintenance support might be reduced. To mitigate risks, budget lines where FRSs contributions may no longer be available, such as vaccinations, are fully costed in the project budget and will be met by DFID (if required). In view of these funding pressures, risks will monitored on a regular basis throughout the project, and if necessary reassessed. We recommend adding this as a low risk in the Business Case risk matrix. / The Fire AID component is also seen as low risk – the database and website development proposed should be within their capabilities.
Risk of funds not being used as intended / The risks of funds not being used as intended is very low. The project is subject to double controls, by both DFID and the UK Fire and Rescue Service through CFOA, and fully accountable under UK Government guidelines, procedures and legislation. / Within DFID, the CHASE Humanitarian Response Group will manage expenditure. Audit, accounting and reporting / monitoring arrangements have been clearly specified in the MOU with CFOA and the Accountable Grant arrangement with Fire Aid. Final reports are requested within three months of the project completion. DFID requires partners to provide a copy of their certified Annual Audited Accounts (AAA) and that they clearly show DFID funding as a distinct line of income. / 4.4 Climate and Environment Risk / The climate and environment risks and opportunities remain low. As described in the Business Case, the climate and environmental risks remain negligible, mainly related to transport arrangements, where possible single flights for the entire deployment and local transport resources will be used.

5. Value for Money
5.1 Performance on VfM measures / VFM Performance measures remain as specified in the business case. UK ISAR can be assessed in terms of DFID’s three components of humanitarian value for money; cost, quality and speed. / The speed at which UK ISAR teams deploy from Britain to the disaster zone and become fully operational in the affected area. / The 24/7 availability of an optimum number of trained and experienced search and rescue experts to comprise ideally sized functional UK ISAR teams of 60-70 persons. / The quality of UK ISAR liaison and coordination with INSARAG, other search and rescue teams, state and UN coordination mechanisms / The quality of procedures undertaken in the transfer of survivors rescued by UK ISAR for follow up medical care. / The quality of internal UK ISAR coordination and command and control in training and deployments, and in functional operational relationships with DFID CHASE. / The cost of search and rescue preparedness set against the above benefits. / As there were no deployments of the UKISAR teams during the year it is not possible to assess operational performance. In terms of preparedness staff training has been in line with agreed levels, equipment has been maintained at a constant state of readiness in line with INSARAG guidelines, and personnel are fully prepared to deploy rapidly. / 5.2 Commercial Improvement and Value for Money / The added value of this project lies in providing an additional layer of international capacity to an existing UK service and as needs demand, rapidly deploying a high quality search and rescue team into a disaster zone to support and supplement a rapid local and international response. / The UK Fire and Rescue Service applies its standard procedures in procurement and international technical expertise in ensuring the most appropriate specialist equipment and best value for money. The interoperability of the 15 services, overseen by the CFOA, ensures that a minimum of duplication of equipment is achieved, and that there is no redundancy in any potential team composition-equipment combination which might be required for a particular event. / Equipment costs charged to DFID are minimised by utilising existing fire and rescue service equipment wherever possible. DFID contributes to the maintenance and replacement of this equipment, as well as meeting some standing charges. For equipment used on deployment, DFID and UKISAR have agreed criteria for when equipment replacement costs will be reimbursed or not. / 5.3 Role of project partners / Search and rescue deployments promote good inter-departmental relations and co-operation between DFID, the FCO, the Department for Communities and Local Government (DCLG) and the Cabinet Office, all of which are involved in the UK’s search and rescue deployments. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
Project has met all required targets and is on track. This should enable UKISAR to remain fully prepared to provide a rapid, assessed and coordinated response, saving as many lives as possible within the limited timeframes available. / The following issues will be followed-up with UKISAR: / DFID should review indicators (particularly 1.1 and 1.2) and milestone targets with UKISAR to find a better measure to show how many UKISAR personnel have benefited from DFID funded training. / UKISAR personnel are contributing to the development of INSARAG activities, including the development of the handbook, this engagement needs to continue but not increased. / Logframe target for available canines needs to be reduced from 14 to 12. / We recommend that UKISAR should provide a comprehensive list of equipment for deployment at least once a year for audit purposes, even if there have been no deployments. / Given the increasing financial pressures on UK fire service budgets, we will include this as a low risk in the Business Case risk matrix.

8. Review Process
DFID desk review based on output reporting provided by the CFOA National Resilience.