Type of Review: Annual Review

Project Title: PATH Meningitis Vaccine Project 2010-15

Date started:	2010
Date review undertaken: November 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is supporting a product development partnership, the Meningitis Vaccine Project (MVP) to develop a polyvalent Meningitis vaccine for Sub-Saharan Africa that will control the remaining 15% to 20% of meningococcal infections not covered by existing vaccines. MVP engages private-sector collaborators to apply their development, manufacturing, and distribution strengths to innovative technologies that would not be a private-sector priority, and therefore achieve maximum sustainable benefit for public health in developing countries. DFID will provide £3,619,788 over 5 financial years (2010-2015) to this project.

What are the expected results?
The Meningitis Vaccine Project (MVP), based at PATH, is aiming to contribute to the elimination of meningitis as a public health problem in Sub-Saharan Africa. / The intended outcomes of the research are: / Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature, and that meets a target price of between £0.82 and £1.65 per dose. / Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrate the vaccine’s safety and immunogenicity in partnership with Serum Institute of India Ltd.

What is the context in which UK support is provided?
There are research gaps into essential technologies such as vaccines and medicines to treat neglected diseases that affect the world’s poorest populations where there are no current products or where those that exist are either too expensive, difficult to access, no longer produced, highly-toxic or ineffective. / Meningitis is a deadly and debilitating disease that causes an estimated 70,000 cases alone in an area of sub-Saharan Africa known as the African meningitis belt, which stretches from Senegal to Ethiopia and has the largest burden of meningitis in the world. Meningitis kills one in ten people who are infected and leaving one-quarter of survivors severely debilitated. The number of cases of meningitis has dramatically reduced since the introduction of the Meningitis A vaccine in 2010, but this vaccine does not target all the disease-causing serotypes. New vaccines are required to prevent meningitis infections by these other serotypes.

## Section A: Detailed Output Scoring

Output 1: Development of an affordable, thermostable, polyvalent conjugate meningococcal vaccine that has a four-year shelf life at room temperature, and that meets a target price of between £0.82 and £1.65 per dose.
Output 1 score and performance description: A - Outputs met expectation / Progress against expected results: / MVP has met the milestones in the performance framework, held technical review meetings and successfully developed material for a phase one clinical trial. Unavoidable setbacks meant timings were slightly delayed, although achieved within the current reporting period. / More than 50 developmental vaccine formulations containing Groups A, C, Y, W, and X conjugates were prepared at laboratory scale using various conjugation chemistries and evaluated in comparative mouse and rabbit immunogenicity studies to support the selection of the final vaccine. / Evaluations of activity show that the final vaccine candidate is performing strongly when compared to other available licensed quadrivalent vaccines / Multiple freeze-dried and spray-dried vaccine formulations were prepared and characterised for stability to support the selection of the final vaccine formulation. / A bead-based, multiplex immunoassay was developed to handle a large number of / samples from animal immunogenicity studies. / The patent families of interest were followed in the patent courts and an external law firm conducted a second intellectual property analysis which provided important guidance to the vaccine development strategy. / Of particular note is that the SIIL team confirmed that the heat stabilisation method for the vaccine will be freeze drying (lyophilisation) over spray drying.
A number of issues and blockages around Intellectual Property (IP) delayed some parts of the work, e.g. on conjugation chemistry. The work is now proceeding, but the impact has been a slight delay in production of the vaccine, by around 4 months. The high risk nature of product development research means that delays of this nature are ‘expected’ and the programme has managed its work to minimise any impact on final delivery. / Clinical trials are now expected to begin in April 2015. There are, currently, some regulatory issues with clinical trials approvals in India. To overcome these barriers the programme is considering moving the clinical trials to African regions. The location of the clinical trials is under discussion and once locations are agreed the programme will provide detailed planning and budgeting for carrying out these clinical trials in Africa. / Recommendations: / MVP to keep DFID informed about the impact of delays to the vaccine production in the coming year. / MVP should report on the costs and logistical implications associated with carrying out vaccine safety and clinical trials in Africa in the next reporting period. / MVP to keep DFID informed of the regulatory changes in India and what impact this will have on the clinical programme. / Impact Weighting (%): 75% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 2: Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrates vaccine safety and immunogenicity, at Serum Institute of India Ltd
Output 2 score and performance description: A - Outputs met expectation / Progress against expected results: / Work with the Serum Institute of India Ltd (SIIL), to produce the polyvalent conjugate vaccine, has progressed according to milestones within the performance framework. / SIIL characterized, optimized, and confirmed laboratory scale production of a Meningitis X / Polysaccharide and has identified a Good Manufacturing Practices (GMP) suite to prepare the vaccine for clinical evaluation. / Pre-clinical results from both mouse and rabbit studies allowed MVP and SIIL teams to select a lead vaccine formulation for final development.
Due to the technical hurdles in developing Men X polysaccharide at pilot and GMP scale and challenges in selecting an efficient conjugation option, PATH have incurred delays in several downstream objectives, including: / Validation of the critical analytical methods for production of Phase 1 clinical trial / material / Production of Phase 1 clinical trial material. / Initiation of toxicological studies with Phase 1 clinical trial material (now planned for June 2014). / The overall delays against expected results are around 4 months. As for output 1 the programme has a risk mitigation strategy to ensure that (inevitable) technical delays are accommodated within the work programme to minimise any impact on final delivery. / Recommendations: / MVP to keep DFID informed of the progress with the production of Phase 1 clinical material. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A – Output met expectation / 1.3 Direct feedback from beneficiaries / Partners in both Burkina Faso and Chad have welcomed the development of a polyvalent conjugate vaccine for multiple strains of meningitis. The success of MenAfriVac in protecting populations against meningitis A has demonstrated the potential to almost eliminate meningitis related deaths during the epidemic seasons across the meningitis belt of Africa.
1.4 Summary of overall progress / MVP is developing a polyvalent conjugate vaccine for meningitis ACWXY using conventional product development techniques. The IP patent issues have been largely resolved, which means that MVP has progressed well during the year and made up some lost time. The regulatory environment in India is posing some challenges and alternative options for the clinical development programme are being investigated.
1.5 Key challenges / PATH expects technical challenges during the polysaccharide fermentation process in the scale-up of laboratory scale conjugates from 2L to 20L, necessary for vaccine production and safety trials. / There are a number of issues in India around the approval of clinical trials. PATH has the correct permissions, but is considering moving toxicological and clinical trials out of India. This will require more planning and costing for successful vaccine safety trials to take place in a new setting.
1.6 Annual Outcome Assessment A – Outcome met expectation / MVP continues to make good progress against the outcome. There is growing interest in the work by the countries impacted by Meningitis and from other funders.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / The programme will underspend in the current financial period, due to delays in some areas of the technical work. Product development research is high risk and it is not unusual that changes to the spending plans are required during the early stages of research. Spending plans have been revised and will be closely monitored over the lifetime of the programme. / 2.2 Key cost drivers / Salaries and staff related costs, laboratory equipment and consumables are the key cost drivers. MVP is managing costs appropriately whilst they explore funding options for clinical testing to be carried out in Africa. / Vaccine development is a costly process, especially in the latter stages of development. MVP has a partnership arrangement with SIIL, who provide cost effective approaches to development of new vaccines. / Technically there is a focus on costs to ensure the production and scale-up of the vaccine conjugates. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / As in previous years the impressive success following the introduction of the Meningitis A conjugate vaccine continues. Wherever the vaccine has been introduced at scale (Burkina Faso, Mali, Niger, northern Cameroon, western Chad, and northern Nigeria) the results have been the same—a rapid disappearance of Group A meningococci as a cause of meningitis. In Burkina Faso where there was a large outbreak of Meningitis X a few years ago there is recognition of the need for the new polyvalent vaccine. / Surveillance data are showing the continued absence of Group A disease. / 3.2 Where an evaluation is planned what progress has been made? / Not applicable

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Product development is high risk and potential vaccine candidates can fail at any stage in the development process. PATH hosts a number of different vaccine development programmes, including MVP. The staff at PATH has experience of applying lessons learned across programmes and has also developed experience at managing these risks. They have taken approaches to ensure the successful development and licensure of the vaccines. / There is an established programme to roll out the MenAfriVac vaccine, so that once developed the new vaccine developed by MVP will have a clear implementation pathway.
Risk of funds not being used as intended / This is low risk. PATH has well established internal and external audit procedures. An external independent Financial Audit is performed annually to certify the availability of funds and assess adequacy of funds. Copies of the unqualified Audited Financial Statements for 2012 have been examined by DFID. In addition PATH has extremely detailed policies covering Ethics; Financial Stewardship; Conflict of Interest; Fraud and Corruption and Whistleblowing, which meet DFID’s assurance expectations. / PATH has a strong a governance structure and robust practices. There were no recommendations associated with financial management in an external review commissioned by the Bill & Melinda Gates Foundation in 2010. / PATH has the right to review SIIL’s project-related data, records, etc. (including detail of all financial transactions). They have no concerns with SIIL’s financial management or performance on the project. SIIL provides semi-annual technical and financial reports to PATH. / 4.4 Climate and Environment Risk / There are no significant environmental impacts of the vaccine development work at the current time. MVP works with regulators to ensure that environmental issues (associated, for example, with used product and packaging disposal) are appropriately addressed and/or studied as part of the development process, prior to the adoption of new vaccines. The WHO prequalification process for any new diagnostic involves an assessment of potential climate and environment risks. / The principal environmental impact of mass vaccination campaigns is that of waste disposal (needles, syringes, and vials). MVP funded an environmental assessment in Burkina Faso prior to introduction of the Men A conjugate vaccine, in part to develop a countrywide plan for waste disposal. The work, led by WHO has served as a model for waste management in other countries and for other products. / In the longer term the environmental impacts of a polyvalent meningitis vaccine should be positive with reduced inappropriate treatments of disease in poor populations contributing to more effective and efficient utilisation of drugs and associated health services.

5. Value for Money
5.1 Performance on VfM measures / Funding vaccine development through a product development partnership (PDP) such as the MVP provides value for money through: / the use of a portfolio approach which allows funding to be redistributed if individual projects are stopped if they do not meet their milestones; / the leveraging of contributions (resources, expertise, funding, access to drugs and other in-kind resources) from the private sector (in low, middle and high income countries); / support for the continued development of the most promising candidates; facilitating opportunities to explore innovative partnerships with private and public sector organisations (in many different countries including low and middle income countries) to reduce costs. / MVP further enhances its value for money through strong partnership working with other PDPs hosted in PATH and its partners as well as global partnerships (such as GAVI), policy-makers, influencers, operational researchers and programme staff on the ground – which can significantly increases the likelihood of vaccine uptake in endemic countries. / The staff at MVP is constantly looking for better technical solutions to develop vaccines and are able to share knowledge and expertise with other vaccine development colleagues. For example PATH colleagues are able to identify new solutions as existing commercial patents end and techniques become available. / 5.2 Commercial Improvement and Value for Money / Through its internal processes, with a focus on the development of new vaccines from existing technology platforms, the programme is able to provide a competitive environment for innovation and improved value for money. In addition the organisation works with a range of different industrial partners, which improves value for money, by leveraging in resources, staff time and expertise from other organisations / 5.3 Role of project partners / DFID is one of MVP’s donors who are involved through regular discussions with the programme directly and through various international and WHO based fora. All donors are aware of the financial constraints and the need to identify ways to increase value for money. / Ensuring value for money in developing products for use in low income countries, where there is no viable commercial market, is central to the way PDPs work with their partners from a range of different backgrounds, including pharmaceutical companies, other private sector organisations, academic researchers, advocacy organisations and local community groups. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Overall MVP has made good progress during the 2012/13 period. The IP issues have been largely resolved and conjugate development process has proceeded well. The regulatory environment in India is posing some challenges and alternative options for the clinical development programme are being investigated. / Recommendations: / MVP to keep DFID informed about the impact of delays to the vaccine production in the coming year. / MVP should report on the costs and logistical implications associated with carrying out vaccine safety and clinical trials in Africa in the next reporting period. / MVP to keep DFID informed of the regulatory changes in India and what impact this will have on the clinical programme. / MVP to keep DFID informed of the progress with the production of Phase 1 clinical material.

8. Review Process
The review was carried out by members of the human development research team in DFID, following review meetings and discussions with the programme and other staff at PATH, independent scientific experts and other funders.