Type of Review: Annual Review

Project Title: Support to the Public Procurement System in Mozambique

Date started:	26/11/2012	Date review undertaken: 26/11/2013
## Introduction and Context
What support is the UK providing?
£3.9m over the period 2013-16 for strengthening public procurement operations and oversight in Mozambique. Of this amount, £2.6m is financial aid to the GoM and £1.6m is Technical Assistance managed directly by DFID. / Mozambique approved its first regulatory framework on public procurement in 2005. This support programme will focus on consolidating and strengthening the procurement reform process that has followed. Significant improvements to the procurement system can be achieved by addressing the numerous human and institutional capacity constraints that exist. This includes strengthening the supervision function of the procurement oversight agency (UFSA) and improving the actual procurement operations in the procurement units (UGEAs) themselves – particularly at provincial level. Investment in information and management systems will help to get a comprehensive overview on the actual public procurement practices in Mozambique and consequently to better orient UFSA’s oversight function. As the technical expertise is considered particularly low at decentralized levels, the project will specifically concentrate on provincial institutions. The general system strengthening approach will be complemented by a pilot in the education sector, with focus on contract implementation and supply chain management issues. Continuous interactions between UFSA and the pilot sector will help generate lessons that can influence other sectors and/ or future projects in this area.

What are the expected results?
The proposed impact of this programme is: “The public procurement system in Mozambique ensures more efficient Government spending”. The envisaged outcome is “Public institutions at the central and provincial levels run transparent and open procurement competitions”.

What is the context in which UK support is provided?
Despite some noticeable improvements since the establishment of a modern legal framework in 2005, which was replaced in 2010 by the Decree 15/2010, the public procurement system in Mozambique still faces considerable challenges and risks. Various structural deficits – such as insufficient transparency and information on public procurement, weak internal control and audit mechanisms, or the lack of an effective capacity building system translate into a broad range of operational procurement issues, such as: / Insufficient documentation of procurement process including filing and archiving / Bad planning and timeliness of procurement processes / Non-compliance with procurement regulations on construction contracts for public works / Weak execution, supervision and quality control of public works, goods and services / One important contributing factor to the low performance of the public procurement system is the weak institutional capacity of both the UGEAs and the oversight body UFSA. With most of the UGEAs, responsible for the actual procurement operations, having been put in place only after 2007, the public procurement system in Mozambique is still very young, and consequently inexperienced. Particularly at decentralized levels, the basic structures are not yet fully operational and have only limited technical expertise. / Whilst school construction and textbook purchase are considered two major issues in the national education system, it is recognised that procurement of goods and services in general is a concern in the sector. Procurement issues range from inappropriate and insufficient definition of standards, non-compliance with global building standards and specifications, lack of transparency in the award of contracts, lack of supervision and quality assurance in the contract management, and authorisation of payments without proper evidence of delivery.

## Section A: Detailed Output Scoring
Output 1: A reliable information management system for public procurement is established in e-SISTAFE
Although approved in November 2012, there have been significant overall delays in beginning implementation of this programme. Regarding the financial aid component (direct support to UFSA) the programme only started in July 2013. UFSA has not had prior experience of this type of financial support, which led to delays in concluding the DFID Memorandum of Understanding between DFID, UFSA and the Ministry of Foreign Affairs (March 2013) and then in setting up the necessary financial arrangements for the programme to facilitate the transfer of resources from the Ministry of Finance to UFSA, and for UFSA to provide authorisation that funds can be drawn down by MINED (for the focus sector work). DFID made the first disbursement in late June which meant that programme implementation could begin in July. The milestones on which this review is based were set assuming a full year of project implementation, given that the implementation period has in fact been only 5 months, a number of these milestones have not yet been met. That said, it is also the case that there has been a slow start to project implementation, with mixed engagement of government counterparts during the period, in part due to changes in the composition of top-management at the National Directorate of Assets (of which UFSA is part) following the death of the National Director. / Recommendation: Working arrangements with UFSA, and MINED, will be clarified following this review. / Recommendation: The logical framework for this programme will need to be reviewed following this Annual Review to review the timeframes attached to a number of milestones, across all outputs. / Similarly, there have been delays in getting the Technical Assistance component of the programme up and running. There were constraints on the availability of Procurement Group to support the procurement process and delays in getting feedback from MINED on proposals for the resident coordinator to be assigned to MINED’s financial administration department which delayed final agreement and award of the contract. The contract has now been signed, approved by the PUSS, and the TA should be in place mid-January. This support will also help boost the overall pace of execution, clarification on ways of working, and revision of the logical framework. / These delays have affected progress against the milestones for all outputs of this project and should be considered in reading the rest of this section of the Annual Review – for outputs 1-6. / Output 1 score and performance description: B - Outputs moderately did not meet expectation / One milestone was met, and delays in the other are explained by overall project implementation delays. / Progress against expected results: / Progress was measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / 1: No. and value of (i) total of all forms of tenders; (ii) public biddings (iii) limited biddings; (iv) biddings in 2 phases (v) bidding with pre-qualification; (vi) biddings of small dimensions (vii) direct contracting published quarterly on UFSA’s Portal a) In general b) Per sector c) Per province The system is developed Met / System Developed and Rolled out to GoM institutions from July of this year. / 2: % of procurement processes supervised and monitored by UFSA and by the DPPFs that are correctly reflected in the information management system No milestone for this reporting period n/a / 3: No. of feedback messages provided from UFSA to the UGEAs each year regarding inconsistencies of information introduced in e-SISTAFE 2000 Activity delayed. / Commentary and analysis:
An application within Mozambique’s IFMIS (Integrated Financial Management and Information System) e-SISTAFE to capture procurement information has been developed by UFSA in partnership with the GoM’s institution responsible for managing e-SISTAFE (CEDSIF - Centro de Desenvolvimento de Sistemas de Informação de Finanças) and rolled-out to government institutions from July of this year. At present, it is too early to assess to what extent the information produced by the functionality is credible and the tool has been designed in a way that captures less information than initially envisaged. However, by year-end, data on a representative sample of public expenditure executed for contracts awarded under each procurement modality in 2013 should be available to enable the establishment of a meaningful baseline for these indicators. / Recommendations: / Monitor the quality of the reports extracted from e-SISTAFE and based on the available sample define a baseline for output 1 indicators (by March 2014). / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: The distribution of roles and responsibilities between UFSA and DPPFs in the public Procurement system is better defined
Output 2 score and performance description: B - Outputs moderately did not meet expectation / Progress against all milestones is behind schedule, in part to the delayed start date but also due to unforeseen, but positive, activities by GoM that will contribute to this output and will need to be considered in terms of their implications for the activities and milestones envisaged. / Progress against expected results: / Progress was measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / 1: % of UGEAs (i) per province and (ii) at central level with information updated annually by UFSA and the DPPFs in the database Mapping exercise concluded and information integrated into a consolidated database in UFSA Delayed / 2: Dissemination of a “Diploma Ministerial” (DM) about the roles and responsibilities of the DPPFs MD disseminated Specific milestone delayed but GoM is undergoing a review of organisational charters for NDA and DPPF that will inform this. / 3: The mid-term strategic plan for the public procurement reform is guiding UFSA’s annual work-plans Plan approved Delayed / 4: Organogram and job descriptions for UFSA and focal points in DPPFs existent - Organogram published on UFSA’s portal, job descriptions approved and people nominated Delayed
Commentary and analysis: / In addition to the overall delays reported above, activities under this output have been delayed due to a parallel on-going process of revising organisational charters for both the National Directorate of Assets (of which UFSA is part) and Provincial Planning and Finance Directorates statute (DPPF – Direcção Provincial de Plano e Finanças). This will ultimately be beneficial to the project and it would not have made sense to move ahead with these activities before this revision is completed. The TA will look at the implications of this for activities planned under output 2. / Additionally, as a further sign of GoM’s commitment to improving procurement systems and ensuring that the appropriate agencies are staffed to fulfil their functions, UFSA has also significantly increased its number of staff from 26 to 47. / Recommendations: / Use TA to appraise the extent to which the changes to the statutes of UFSA and DPPFs mitigate some of the institutional issues in the way procurement oversight is enacted, and assess the implications for the activities and milestones envisaged under this output. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: The UGEAs at central and provincial level master public procurement regulations
Output 3 score and performance description: C - Outputs substantially did not meet expectation / Progress against expected results: / Progress was measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / 1: No. of guidelines in different areas of public Procurement published on UFSA’s Portal in support of the UGEA’s work 3 Delayed / 2: No. UGEA members at (i) central, (ii) provincial and (iii) district levels who have obtained the certificate in a) “basic” procurement training b) “advanced” procurement training c) “specialized” procurement training in the education sector Design of a Training strategy finalized, and manuals for new training programmes developed: Basic Training, Advanced Training, Specific Trainings for Education, Control Bodies, DAF Directors and the Private Sector Delayed / 3: Average no. of questions from UGEAs answered daily through UFSA’s Portal (within 1 day) No milestone for this reporting period n/a / 4: % of supervised and monitored Procurement processes at (i) central and (ii) provincial levels with documentation in line with UFSA’s standard formats( nine in total) a) In general b) In the education sector Define baseline and milestone for this indicator for subsequent years Delayed / Commentary and analysis:
The activities under this output have been delayed as they constitute a core work-stream for both the resident TA and the specialised short-term TA available on a short-term basis. The DFID delays in operationalizing the TA component for the project have meant that the training activities have been postponed. However UFSA has been undertaking routine trainings and supervisions of UGEAs as part of its normal annual plan. / Recommendations: / Prioritise these activities as part of the TA work-plan in order to catch-up progress on this output area. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: UFSA’s supervision activities are based on a comprehensive monitoring system of UGEAs
Output 4 score and performance description: B - Outputs moderately did not meet expectation / Progress against expected results: / Progress was measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / 1: The annual supervision/monitoring plans correspond to the monitoring criteria defined in the supervision strategy Supervision / monitoring strategy and mechanisms developed Delayed / 2: No. of reports (a) of supervision, (b) monitoring and (c) joint audits with IGF at (i) central, and (ii) provincial level consolidated by UFSA and/or the DPPFs into the monitoring database Monitoring database for UGEAs, systems of monitoring and monitoring visits designed based on mapping exercise of UGEAs; Monitoring guidelines updated and guidelines for monitoring visits designed Specific milestone delayed but increase in supervision activity and improved coordination / 3: No. of graduates of (i) IGF, (ii) TA, (iii) senior officials of the sectors (DAF, Permanent Secretaries, Provincial Directors) at (a) central and (b) provincial/regional trained on Public Procurement matters Supporting guidelines for TA, IGF, DAF Directors in view of supporting the analysis of procurement documents available Delayed / Commentary and analysis:
The DFID delays in operationalizing the TA component for the project have meant that the all activities related to this output have been postponed programme (this output constitutes a core work-stream for both the resident TA and the specialised short-term TA available on a short-term basis). However monitoring and supervision visits have been taking place (including joint audits with the General Inspectorate of Finance) and there are signs of better coordination and information sharing with internal and external controls institutions (this is also monitored as part of the GBS PAF). / Recommendations: / Prioritise these activities as part of the TA work-plan. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 5: UFSA ensures improved private sector access to critical procurement information and bidding opportunities
Output 5 score and performance description: B - Outputs moderately did not meet expectation / Progress against expected results: / Progress was measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / 1: No. of suppliers registered within the e-SISTAFE Supplier’s Database in line with official procurement rules Concept note about the management procedures about the Supplier’s Database available in coordination with Ministry of Commerce On track / A concept note is developed and available for an updated suppliers’ database / 2: UFSA’s Internet Portal respects the OECD minimum criteria No milestone for this reporting period n/a / 3: No. de private sector companies that participate in a combined training & discussion event about public Procurement at (i) central and (ii) provincial levels Concept of interaction with the private sector developed; and guidelines for the private sector about procedures for participating in public tender processes published on UFSA’s Porta Delayed / Commentary and analysis:
As part of the SISTAFE ICT modernisation projects, progress has been registered in terms of conceiving an integrated IT application for procurement, contract and asset management [however, developing e-procurement, which involves both computerising manual procedures and a degree of process reengineering, is beyond the scope of this programme]. UFSA and CEDSIF have developed business models for the project’s core modules linked to e-SISTAFE i.e. the consolidated single suppliers’ register (Cadastro Único de Empreiteiros de Obras Públicas, Fornecedores de Bens e Prestadores de Serviços ao Estado) and the standard catalogue of goods and services (this is linked to another on-going activity on surveying and determining reference prices). The registry will be available online, and linked to the Single Taxpayers’ Identification Number (NUIT – Número Único de Identificação Tributária) registry at the Tax Authority. The revised Cadastro will ensure enhanced reliability in terms of the legitimacy of firms that are allowed to bit for public contracts. UFSA’s website is also showing signs of gradual improvement. The activities under this output would also greatly benefit from specialised technical input that will be mobilised under the TA package made available by the programme. / Recommendations: / Explore synergies in the planned programme of support to CEDSIF to facilitate and accelerate the implementation of activities focussed on procurement-related information systems and private sector communications and interactions. Engage within projects in the PSD portfolio to explore options to reinforce engagement with the private sector. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 6: MINED has the systems in place for more efficient and organized public procurement at central and provincial levels
Output 4 score and performance description: C - Outputs substantially did not meet expectation / Progress against expected results: / Progress was measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / 1: The automation of monthly procurement reporting in MINED at the national level is based on an integrated database linking provincial and national level. Design of an integrated database finalized Delayed / 2: No. of integrated system monitoring reports referring to central and provincial levels that are produced in MINED at central level. A comprehensive monitoring strategy of the national and provincial levels is available Delayed / 3: No. and % of procurement plans prepared by the UGEAs at (i) provincial and (ii) central level in the education sector submitted to (a) MINED and (b) UFSA in line with the standard formats Two (2) central and one (1) provincial procurement plan prepared and two (2) reports submitted to UFSA Delayed / 4: - No. of a) lessons learnt and b) working standards developed in the educaion sector regarding public procurement, implemented together with other Ministries (indicator on which UFSA will need to report) No milestone for this reporting period n/a / Commentary and analysis:
The activities under this output have all been delayed. Education was selected as a focus sector for this programme towards the end of the design phase; the idea being that for PFM reform to be effective, "downstream" sector agencies need to work in tandem with, and provide regular "end-user" feedback to core "upstream" central agencies such as UFSA. direct engagement with MINED through the project is aimed at building ownership of reforms across agencies and facilitating effective lesson-learning and feedback on where/when/why/how systems and processes work (or not) to then be incorporated in the reform process. / However, to date MINED engagement has been weak, with apparently limited buy-in from their side. The fact that MINED were brought on board late in the design process is one of the factors contributing to this. The overall coordination and communication role sits with UFSA and as yet they have not worked out effective ways of working with MINED, nor actively put in place the administrative steps needed to make resources available to MINED. This means that this component is further behind schedule than others (with very little being achieved even in the initial 5 months following the delayed programme start). It is also true that the MINED focal point (Finance Director) has not accorded priority to this programme within competing demands on her time (in an already donor-crowded sector). DFID delays in putting the Technical Assistance component in place – including the education sector adviser – have also contributed. In the past 2 months, MINED have been involved in finalising the selection of the TA and it is expected that the arrival of the TA in mid-January will help get activities on this programme underway in a meaningful way. / Recommendations: / Prioritise these activities as part of the TA work-plan. Use the TA to facilitate dialogue between UFSA and Mined and generate more traction with respect to the programme. / Continue working with education sector colleagues in Human Development Team to facilitate engagement with MINED and other education sector donors, and to input to TA work plan for education sector. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.
1. Progress and results
1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: B - Outputs moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / As implementation is still in its early stages, no direct feedback has been sought from beneficiaries.
1.4 Summary of overall progress / As explained above, the programme suffered long delays in becoming effective which means it has only been operational (UFSA component) for 5 months. The TA programme has not yet gotten underway – with additional implications for the pace of programme in the component delivered directly by UFSA. As a result there has been very little progress across all outputs by end November 2013; / the BC was approved in December 2012; / the DFID Memorandum of Understanding (Exchange of Notes) was signed in March 2013; / the first disbursement of £400,000 made in July 2013 (of which about 60% is expected to be executed by end December 2013); / Bids for the TA package were received and evaluated in July 2013, and following submission and approval by PUSS, the contract with the selected service-provider for the TA (Crown Agents) was signed in November 2013. / The TA team is expected to be operative by mid-January 2014.
1.5 Key challenges / The main challenges to this programme are related to weak strategic, technical and managerial capacity and poor dialogue and coordination between UFSA and MINED. There also appears to be inconsistent ownership by UFSA, which partly also derives from UFSA’s limited capability to engage productively in the design process. This has in-turn generated some mismatch as to the expectations and approach of the programme (e.g. with regards to the TA component of the programme). / Another operational challenge are the complex implementing arrangements (from financial, governance and management standpoints), the implications of which were probably insufficiently appreciated during design (especially MINEDs involvement as focus sector). / More generally, political economy dynamics are also a likely contributory factor to the perceived lack of enthusiasm towards interventions that “go against the grain” such as this one. In practice, transparent and efficient procurement not a government priority and this is reflected in the fact that UFSA is a weak agency, subordinated to MF and with relatively limited independence and mandate. However, we continue to view procurements reform as too important to ignore, and are of the view that some reform is possible. This is important to our financial aid and economic development work in general.
1.6 Annual Outcome Assessment / Given that most activities underpinning the programmes’ outputs have been postponed, progress against indicators measuring the outcome (“Public institutions at the national and provincial levels run transparent and open procurement competitions”) has also been slow. / Progress against expected results: / Progress is measured against the following milestones for the specific output indicators: / Indicator Milestone by November 2013 Progress Achieved by November 2013 / No. of tender processes (i) sent to the Administrative Court (total) (ii) approved(iii) returned (iv) rejected No milestone for this reporting period n/a / 2: % of supervised tender processes at (I) central, (ii) provincial and (iii) district level with complete documentation (a) General (b) In the Education Sector Define baseline and milestones at (i) central, (ii) provincial and (iii) district level Delayed / 3: No. of follow-up actions agreed between UFSA and Sector Ministries at central and provincial level based on the results from the information management system and the supervision visits No milestone for this reporting period n/a / 4: No. of (a) tenders (b) and contract awards at (i) central, (ii) provincial and (iii) district levels published on UFSA’s Portal in line with the standardized formats set by UFSA Define baseline and milestones at (i) central, (ii) provincial and (iii) district level Published tenders: Central level Provincial level Contract awards: Central level Provincial level Delayed

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / First disbursement of £400,000 was made in June 2013. / 2.2 Key cost drivers / The first financial report for the programme will be produced by end February. This will provide the first opportunity to look at cost drivers. / 2.3 Is the project on-track against original timescale: No / Given that the programme only got underway 6 months after it was approved, there has been only limited progress towards the milestones set for end November 2013. The logical framework will be reviewed to reflect revised timeframes for key activities and milestones.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence have been registered. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation is envisaged but it is too early to be planned. The scoping for this will be reported on in the Inception Report to be produced by the TA.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level – High / Still rated as high overall (as per original assessment during design). Below is an update on key risks identified: / Risk Description Impact Probability Update / 1. Insufficient political leadership at Senior level for implementing the procurement reform effectively across all Sectors, and in particular within the Education Sector as pilot, and enforcing the actual application of procurement rules (political) H M At least formally, high level commitment appears to be there. However the programme appears to be largely supply driven. / 2. Insufficient technical human resources, particularly at provincial level, hinder UFSA and DPPFs to fulfil their (additional) responsibilities that are supported by the project and might hamper actual delivery and/or quality of services (institutional) H H Weak capacity (often coupled by weak commitment) is evident. / 3. The insufficient number of qualified staff in the UGEAs, particularly at decentralized levels, combined with high staff rotation undermines effective capacity building of the procurement function with negative impacts on the compliance and performance of the procurement processes (institutional) H M Plans for a separate procurement officer career, that would have professionalised this function in the Mozambican Civil Service, have been shelved for the moment in favour of preliminary steps towards a more comprehensive revision of career streams within the broader PFM cadre. / 4. Given that UFSA’s representation at provincial level in the DPPFs is not formalized, centralised decision making and the lack of clear hierarchical structures between UFSA and DPPFs will undermine system strengthening. (institutional) M H Not clear to what extent this is an issue. Will use TA to propose options for reform in the institutional set-up that are potentially better suited in terms of UFSA exercising its mandate. / 5. Insufficient coordination and collaboration between UFSA and MINED hampers aligned approaches in project implementation between the two Ministries and effective transfer of lessons learnt. (institutional) H M Coordination with, and buy-in from, education sector is weak. Will use TA to facilitate better inter-institutional dialogue and communication. / 6. The weak institutional set-up within the State Asset Directorate of the Ministry of Finance and lack of institutional autonomy hinders UFSA’s function as independent oversight body (institutional) L H The extent to which this risk materialises is difficult to gauge but will continue to monitor. / 7. Trainings of UGEAs with little impact on the actual day-to-day operations in procurement undermine increased compliance of procurement processes (institutional) M M To be monitored once the training programme gets underway. / 8. Interest of the political elite and blurring boundaries with the private sector distort effective programme implementation, e.g. UGEAs are not effectively empowered within Line Ministries in order to ensure compliance with procurement rules (Political economy) M M To be monitored as part of monitoring of the wider governance environment. / 9. Lack of synergy between DFID’s procurement project and procurement programmes of other donors (PFM programme of the WB, procurement interventions in the education sector of KfW and Candada) leads to duplications and inconsistencies M M The WB currently has no plans to directly engage in procurement reform. Regular communications with the HDT and other donors are taking place. / 10. Weak complaint mechanism undermines the enforcement of the procurement legislation (institutional) L M UFSA to scope options for reform with support from programme-funded TA
Risk of funds not being used as intended / Fiduciary and corruption risks are assessed as substantial (as per original assessment). / 4.4 Climate and Environment Risk / N/A

5. Value for Money
5.1 Performance on VfM measures / The first financial report will be submitted by end February 2014; this will provide an opportunity to undertake the first review of the agreed VfM indicators and make adjustments to them as appropriate. / 5.2 Commercial Improvement and Value for Money / The service provider for the TA component of the programme was selected through a PRG-managed mini-competition in the context of DFID’s Governance and Security framework agreement with pre-selected qualified firms. / This has generated efficiency savings for DFID (in terms of transaction costs and quality of the bidders), as opposed to running a full open competition. / Post-tender negotiations with the supplier resulted in a revised commercial proposal that achieved a total reduction of £320,800 or 21% of the contract value. / 5.3 Role of project partners / The TA team from Crown Agents will be operational by mid-January. The flexible, short-term expertise will also be mobilised early on to maximise the impact of the TA component, deliver quick wins and help accelerate progress against activities currently far behind schedule. / 5.4 Does the project still represent Value for Money: Too early to tell. / It is too early to tell but it is expected that once the TA team is in place, and coordination issues are resolved, there will be more traction and accelerated delivery of outputs, which will drive VfM for DFID’s relatively small investment in an important, but underfunded, area of PFM reform. As verified by the difficulties experienced to date in getting the programme up-and-running, this is a high risk intervention but the potential benefits (and so VfM) are also large given that improved procurement systems and processes should lead to more economical and efficient use of public resources in general. / 5.5 If not, what action will you take? / The general recommendations outlined in this review will be critical to ensuring VfM; at this stage no specific VfM actions are recommended.

6. Conditionality
6.1 Update on specific conditions / The SoS signed off an overall Partnership Principles Assessment in June in the context of the general budget support programme. This was updated in September. Beyond the overall assessment there are no concerns specific to this programme relating to DFID’s partnership principles.

7. Conclusions and actions
The programme is significantly behind schedule given delays in beginning the UFSA executed component, a generally slow level of activity as the programme has started, and the fact that the TA component is not yet in place to provide the implementation support needed. The TA component has been procured and will be in place in January. We expect a step change in the pace of delivery once the TA is in place, and we will be closely monitoring programme delivery over the first 4 months of 2014. / Although issues are gradually being resolved, weak technical and managerial capacity and poor dialogue and coordination between UFSA and MINED, constitute significant risks to the attainment of successful outcomes. It is expected that when up-and-running, the resident Technical Assistants assigned to UFSA and to MINED will play a positive role in linking the institutions and ensuring regular and productive technical dialogue. Coupled with an effective use of the additional funding made available through the programme, this should help pick up the pace of implementation and improve progress towards milestones. / The Technical Assistance will be in place by mid-January. DFID will hold early kick off meetings with the TA to clarify our expectations with them particularly regarding DFID views on immediate priorities for their initial work plan. A short period of technical work between the TA, UFSA, MINED and DFID will follow, during this work plan will be produced. This would then prove an opportune moment for a high level meeting between DFID and the Vice Minister of Finance (with oversight of UFSA) to communicate any key issues and concerns we have and confirm both DFID and GoM commitment to successful delivery of this programme. / An inception report will be due from the TA by end-June. This will provide lessons and feedback on the current approach (including on whether the assumptions underpinning the programme need to be reconsidered) and identify any potential remedial measures that could be implemented to ensure success. Any changes will need to be reflected in the logframe at this stage as well. / It is recommended that the programme be recalibrated to align with government reporting cycles with the annual milestones set for end December each year. Full year performance and financial reports would then be submitted to DFID by end February of the following year, and the annual review completed in consultation with UFSA and the TA by end May. These changes will need to be captured in the internal DFID systems. / However, given our concerns regarding the overall slow start on this programme we are not recommending that the next AR is postponed until May 2015. Rather we would suggest completing an interim Annual Review in August 2014, to review progress over the second 6 months of implementation and provide an opportunity to review the TA inception report and record any key findings from that. / To facilitate this, a light touch review of the logical framework (to reset timeframes for key milestones and identify some realistic interim milestones for end June 2014) will be completed by end Feb 2014. / Given the important but risky nature of this programme, we will also seek to bring in independent support to conduct a more fundamental mid-term review at an appropriate point. The exact timing will be confirmed following the August 2014 Annual Review (considering any recommendations that may emerge from that – including through the TA inception report – which may affect programme duration, implementation arrangements and the logical framework). / Summary of Recommendations: / Recommendation: Who By When? / Clarify working arrangements with UFSA, and MINED and the TA support including DFID engagement Lead Adviser End March 2014 / Initial review of logical framework to revisit the timeframes for milestones, across all outputs and identify interim milestones with realistic deliverables for end June 2014 – to be assessed in August 2013 Review Lead Adviser with inputs from TA End February 2014 / Monitor the quality of the reports extracted from e-SISTAFE and based on the available sample define a baseline for indicator 1 (Output 1) Lead Adviser End March 2014 / Use TA to appraise the extent to which the changes to the statutes of UFSA and DPPFs mitigate some of the institutional issues in the way procurement oversight is enacted, and the implications for the activities and milestones envisaged under output 2 Lead Adviser with inputs from TA End February 2014 / Hold an early kick-off meeting with the TA when in country in order to agree priorities for their initial work plan including a plan to catch up on delayed output areas (particularly 3, 4 and 6) Lead Adviser Mid Jan 2014 / Once TA work plan agreed at technical level with TA and UFSA, organise high level meeting (Head of Office and Vice Minister) Lead Adviser End March 2014 latest / Explore synergies in the planned programme of support to CEDSIF to facilitate and accelerate the implementation of activities focussed on procurement-related information systems and private sector communications and interactions Lead Advisers for both programmes July 2014 / Use the TA to facilitate dialogue between UFSA and MINED and generate more traction for this programme within the sector. Lead Adviser with inputs from TA January 2014 / Undertake an additional Annual Review in August 2014 to check progress over second 6 months of implementation and review TA inception report. The outcome of this inception period and the Annual Review process would be expected to influence programme work planning, working arrangements and the logframe for subsequent years. Lead Adviser and Programme Officer End August 2014 / Agree on a revised reporting calendar for the programme which aligns with Government financial and performance reporting timeframes whilst also meeting DFID requirements and make changes in DFID internal systems Lead Adviser and Programme Officer January 2014 / Continue working with education sector colleagues in Human Development Team to facilitate engagement with MINED and other education sector donors, and to input to TA work plan for education sector. Lead Adviser and Education Adviser On-going / Conduct an Independent Fundamental Review of the programme at an appropriate mid-term point in programme implementation Lead Adviser and Programme Officer To be determined, probably mid 2015 as input to Annual Review

8. Review Process
This review was carried out by the Lead Adviser for the programme and has been Quality Assured by the GET Team Economic Adviser. / Documents consulted – UFSA/CEDSIF internal documents; General Budget Support Performance Assessment Framework Indicator Technical Notes; GBS Annual Review (PFM pillar report).