Business Case
Ghana Oil and Gas for inclusive growth

October 2013

Table of Contents

Intervention Summary
What support will the UK provide?
The proposed intervention on Oil and Gas for inclusive growth in Ghana will support the development and implementation of the legal framework and key state institutions involved in the management of the sector to ensure they carry out their functions effectively. Concurrently it will promote accountability by building the capacity of civil society and Parliament to monitor and challenge state performance.

The intervention helps delivering the G8-Ghana partnership on Extractives launched by President Mahama and the Prime Minister in June 2013.

The intervention is based on the Natural Resource Charter. Three key outputs, pivotal for maximising benefits of oil and gas for Ghana, form the basis for the design:

- Strengthening oversight and enhancing regulation of the sector. Clear policy, robust legislation and an effective and accountable regulatory body are necessary prerequisites to regulate private sector operations, and ensure the best possible development progress is achieved from the use of natural resources.
- Improving revenue capture is critical to maximising the direct benefits from the oil and gas sector. The Government’s ability to do so will depend on the clarity of the fiscal regime and the technical capacity of authorities to collect royalty payments and tax revenues.
- Improving revenue management is important to ensure transparency and avoid adverse macroeconomic consequences associated with natural resources windfall gains, such as drawing too heavily on revenues in times of high oil prices to meet budget deficits, and the so-called Dutch Disease (large inflows of revenue associated with the resources extraction leads to an appreciation of the real exchange).

How will UK funds be used?
DFID will commit £17.25 million for 5 years between 2014 and 2018. The intervention is structured around three outputs and a management budget:

1. Output 1: £ 7,70 million. Strengthening oversight and enhancing regulation.
2. Output 2: £ 4.00 million. Improving revenue capture.
3. Output 3: £ 4.05 million. Improving revenue management.

In addition, £1.5 million has been set aside for supervision, reviews, monitoring and audit.
Why is UK support required?
Oil was found in commercial quantities off the coast of Ghana’s Western Region in 2007. Extraction started in 2011. Production, presently just over 100.000 barrels per day, is expected to increase significantly in the coming years.

Oil production adds roughly 4% to GDP. If well-regulated and managed, oil and gas can provide a major boost to Ghana’s development. Once gas starts flowing (scheduled for 2014) it has the potential to support Ghana’s transformation agenda as well as plans to transition from development aid. While potentially good for the Ghanaian economy, there are also serious risks. Regional examples of the “resource-curse” are plenty. Ghana has moved from identification of oil to production in a very short span of time and the institutional framework is therefore still under development. Access to “easy” oil money reduces a government’s incentives to strengthen and collect direct taxes, which in turn may undermine the citizens’ ability to hold government to account.

The UK is well-placed to provide support in the sector for a range of reasons, including technical expertise, the UK being home to a number of large oil companies, including the major oil company in Ghana – Tullow, longstanding and good relationships with Ghana’s Government, civil society and Parliament. The UK planned intervention complements existing technical interventions led by the World Bank and Norway’s Oil for Development programme, which seem to focus strongly on the Executive branch of government whereas the UK intervention also empowers citizens and Parliament.

At the international level, the programme coincides with UK leadership in the G8 for an improved focus on tax avoidance and evasion – including extractive sectors. In Ghana there is parallel increased attention to taxation led by the Minister of Finance. The UK-led G8 partnership with Ghana forms a strategic dialogue mechanism for the intervention.
What are the expected results?
The headline outcomes are increased revenue and improved regulatory quality in the oil and gas sector. In turn, this will increase growth and stability and reduce poverty.

By the end of the programme, the intervention is expected to add 5% annually to revenues from the oil and gas sector – conservatively estimated at £30 million per year. Ghana’s composite score on RevenueWatch’s Resource Governance index – an indicator of regulatory quality - will have also improved by 5%.

Output level results include:
- The Petroleum Commission will be a well-established and efficient regulator (leading on contracts, licensing, permits; hosting the data repository centre) – and the oil industry is seeing a faster more consistent contracting and operating framework.
- An improved Oil and Gas Sector Policy
- Clearer links between the national budget strategy and the Oil and Gas sector
- Ministry of Finance will be able and experienced in analysis and fiscal modelling – and therefore mitigating risks of Dutch Disease
- Civil society and Parliament will be more effective in playing their oversight role
- Taxation is more transparent, and
- The Heritage Fund is well-managed

The programme is medium risk, with the main risks around political and institutional incentives for reform. The programme management is designed to understand and actively mitigate these risks. At DFID level, programme team oversight will work closely other parts of the UK mission in Ghana and the UK (e.g. on transfer pricing and taxation).

Fiduciary risks are low/medium. Around 50% of the budget will be channelled as financial aid to key government partners (non-budget support financial aid) and civil society organisations (accountable grants). The remaining budget is directly within DFID-control through a project advisory unit, which will work with partners and manage a Strategic and Technical support facility.

Business Case
Strategic Case
Context and need for DFID intervention
A.1 Rationale
After more than 20 years of exploration activity, commercial quantities of oil and gas were discovered off the coast of Ghana in 2007. Production from the Jubilee oil fields began four years later at the end of 2011 at a level of 70,000 barrels per day (bpd) and presently stands at 130,000 bpd. Proven oil reserves stand at 0.7 billion barrels[1], with associated natural gas which is due to begin production in 2014, and more oil and gas in prospect.
[1] Source: US Energy Information Agency

The Ghana Government has made it clear that it wants to maximise the opportunity for growth and national development while minimising the chances of Ghana falling prey to the ‘resource curse’.[2] In light of a rapid move from discovery of commercial reserves to production the government had limited time to prepare and establish the legislative and institutional framework necessary to regulate the industry or to minimise the risk of environmental and social damage.
[2] The term ‘resource curse’ was first used by Auty (1994), who discussed the economic, institutional and political economy conditions that cause resource abundance to lead to stagnation, waste, and conflict.

At the highest level, President Mahama has reaffirmed Ghana’s existing commitment to international standards such as the Extractive Industries Transparency Initiative (EITI). In June 2013 Ghana entered a partnership based on the Natural Resource Charter[3] on extractives with the G8 during the London summit. The Government has demonstrated intent through the introduction of legislation such as the Petroleum Revenue Management Act and Petroleum Commission Act, drafting of the Exploration and Production Bill and Local Content Legislative Instrument, and establishment of an Independent Regulator to provide oversight and manage the sector well.
[3] See http://naturalresourcecharter.org/ for further information on the Charter.

However, the speed of reform has left some institutional weaknesses unaddressed. An assessment of Ghana’s legislative and institutional framework shows that, despite initial reform efforts, weaknesses persist. Constraints include the need for clear strategic leadership from the Ministry of Energy, overlapping responsibilities between the Ghana National Oil Company (GNPC) and the sector regulator, the Petroleum Commission, a general lack of coordination and sector expertise across the state entities involved in the management of the resources.

Furthermore, there is a risk that without effective and accountable institutions, additional resources from oil and gas could fuel a culture of short-term political decision-making that could hinder, rather than enhance, the opportunities for long-term growth and benefits for the people of Ghana. Bi-partisan politics and election campaigns based on ambitious spending plans have in the past left little room for long-term national plans and investments that lead to sustainable and equitable growth[4].
[4] The Government is unlikely to meet IMF targets to reduce the fiscal deficit in 2013 given the post-election decision to raise the public sector wage bill in this year’s budget and no long term national development plan exists.

Civil society – supported by donors - has been active in demanding accountability through the setting up of an oil and gas platform as well as the Public Interest and Accountability Committee (PIAC).

However, increased oil and gas knowledge as well as funding and coordination are required to strengthen and target their demands and provide an essential complement to strengthen government institutions.

Analysis related to preparation of this business case suggests there is an urgent need to ensure revenue flows from the sector are captured and utilised by the state, while minimising the risk of economic mismanagement and negative social or environmental impacts.

The proposed intervention will support the development of the legal framework and key state institutions involved in the management of the sector to ensure they carry out their functions effectively. It will also promote accountability by building the capacity to monitor and challenge state performance by civil society and Parliament as a corollary for capacity building. The private sector will benefit; industry consultations consistently point out the importance of a stable, fair and predictable operating environment. Companies are less worried about taxation levels than rapid changes to the regulatory framework and overlapping mandates of oversight bodies. Three key areas, pivotal for maximising the benefits of oil and gas for Ghana, form the basis for the proposed project design:

- Strengthening oversight and enhancing regulation of the sector. Clear policy, robust legislation and an effective and accountable regulatory body are necessary prerequisites to regulate private sector operations, and ensure the best possible outcome is achieved from the use of natural resources.
- Ensuring revenue capture is critical to maximising the direct benefits from the oil and gas sector. The Government’s ability to do so will depend on the clarity of the fiscal regime and the technical capacity of authorities to collect royalty payments and tax revenues.
- Improving revenue management is important to ensure transparency and avoid adverse macroeconomic consequences associated with natural resources windfall gains, such as drawing too heavily on revenues in times of high oil prices to meet budget deficits, and the so-called Dutch Disease[5].
  [5] Dutch Disease is the term used to describe a situation whereby large inflows of revenue associated with the resources extraction leads to an appreciation of the real exchange, making imports cheaper (see Cordon and Neary, 1982).

Addressing the areas of high risk for Ghana’s successful management of natural resources
Key challenges for ensuring effective management of the oil and gas sector
Weaknesses exist along the entire extractives decision chain, but can be centred on six of the precepts of the Natural Resource Charter (see Annex III). These span from the initial decision to develop fields, to negotiating and monitoring contracts through to collecting revenues and managing these resources.

There is a need to strengthen the legislative framework, as well as the means of the implementation through new regulations and capacity building. In addition, there is a critical role for accountability actors to complement capacity-building. The key challenges in strengthening the institutions and management of the sector can be summarised as follows:

Industry regulation
- The vision for regulation of upstream activities has not been fully realised. The Petroleum Commission was established as the main regulator for upstream activities. However, its ability to regulate the industry effectively has been hindered by lack of funding from central government, weak processes and organisational development, and limited leadership from the Ministry of Energy.
- Poor oversight and accountability. The Ministry of Energy lacks the technical capacity and leadership to provide strong oversight over the industry; it continues to depend on the GNPC for informed decision making. In parallel, civil society has insufficient access to information to establish stronger public accountability, and also lacks the technical understanding to effectively monitor the sector.
- Weakness in negotiation of contracts. An inter-ministerial negotiation team led by the GNPC manages petroleum agreements. The team is made up of representatives of the Ministry of Energy, Ministry of Finance, Ghana Revenue Authority and the Petroleum Commission. However, the GNPC is the only organisation with the technical skills to negotiate terms effectively. A greater challenge function is required from the other agencies to ensure contracts deliver the best possible outcome in line with national priorities.
- Inadequate environmental oversight. The Environmental Protection Agency, along with the Petroleum Commission, is responsible for evaluating the environmental impact assessments included in development plans, and monitoring the environmental management of operations. Neither have sufficient institutional capacity to carry out this mandate, nor are there robust disaster mitigation plans in place.
- Implementation of Local Content Act. The Petroleum Commission will need to develop the capacity to implement and monitor local content policy. A technical appreciation of the procurement procedures of the oil companies and their major suppliers is required, as well as an understanding of the scale and pace of the industry’s development and linkages to other sectors of the economy. Currently, the Petroleum Commission does not fully have the necessary industry knowledge to ensure that the application of the Local Content legislation brings the intended benefit.

Revenue capture
- Leakage in collection of oil revenues. There are concerns around revenue collection arising from the lack of technical knowledge in the GRA. The issues of concern include under-reporting of export volumes, admissible deductions and allowances, transfer pricing and treatment of local and foreign tax credits and debits.
- Limited oversight of fiscal terms in contracts. The flexibility to negotiate tax obligations through petroleum agreements has in some cases resulted in a lack of clarity regarding tax liabilities. There is a need for the MOFEP and GRA to play a greater role in negotiating contracts and ensure that national tax laws are not undermined.
- Lack of capacity in revenue administration. The GRA has limited technical knowledge of the oil and gas business, in particular with regard to industry cost structures and accounting for spending that is ‘cost-recoverable’, as well as to commercialisation and marketing of petroleum-related activities. Experience to date suggests that the fiscal arrangements and legislation are not sufficiently clear to ensure full compliance.
- Parliament and civil society organisations (CSOs) have few financial and analytical resources to scrutinise contracts. Petroleum agreements are taken to Parliament for final approval, and these are rarely subject to informed challenge.

Revenue management
- Macroeconomic risks. If public expenditure is not aligned to the domestic absorptive capacity of the economy, then the impact of an appreciation of the real effective exchange rate (‘Dutch’ disease) is a major macroeconomic risk to Ghana.
- Inaccurate revenue forecasts. Coordination is required between the MOFEP and GRA (and BOG) to forecast accurately the revenues that can be expected to accrue from the oil and gas fields. Weak coordination and lack of shared revenue models and technical knowledge have led to an over-estimation of the benchmark revenue used to determine the allocation of oil resources to the annual budget funding amount.
- The benchmarking process has not been effectively implemented, which has led to a misallocation of revenue flows between treasury accounts and between petroleum funds.
- There is no investment policy for Ghana Petroleum Funds, without which the BOG is restricted in its possibilities for managing the Heritage and Stabilisation funds.
- PIAC needs strengthening and the funding to help civil society better hold Government to account. PIAC was decreed under the PRMA but the Government funding has been limited and it has taken financial and technical support from civil society and international NGOs to make it a reality and sustain it.

A.2 Rationale for DFID intervention
The aim of the project is to ensure the effective management of oil and gas resources in a way that maximises benefits for the people of Ghana. To achieve this goal a combination of capacity building for the relevant institutions and strengthening citizens’ ability to constructively engage (incl. Parliamentarians, civil society and the Public Interest and Accountability Committee) as demonstrated in figure 1 below.

DFID can play a particular role in the oil and gas sector in Ghana. The World Bank and Norway already have sound technical interventions in place. However, lessons from these two interventions correspond with emerging international lessons in oil and gas that technical support alone is not as effective as a more holistic approach. The World Bank and Norwegian interventions work primarily with the executive and primarily although not exclusively with the Ministry of Energy. Our intervention proposes to work with a range of partners which complements and strengthens the existing interventions and builds on DFID’s experience in supporting institutional reform in an appropriate way.

By supporting three complementary areas of industry regulation, revenue capture and revenue management through a mix of working with both government and non-government actors, the management of oil and gas resources will be strengthened and secured in a way that maximises the benefits for the people of Ghana.

Figure 1: Intervention logic to strengthen industry regulation, revenue collection and revenue management

B. Impact and outcome

What will the Impact be?
The expected impact is to contribute to inclusive economic growth and poverty reduction (through a well-managed Oil & Gas Sector).

What Outcome is planned to achieve this impact?
The headline outcomes are increased revenue and improved regulatory quality in the oil and gas sector. By the end of the programme, the intervention is expected to add 5% annual to revenues from the oil and gas sector – conservatively estimated at £30 million per year. Ghana’s composite score on RevenueWatch’s Resource Governance index – an indicator of regulatory quality - will have also improved by 5 percentage points.

Three outputs shape the core of the theory of change, i.e. improving regulation, revenue collection and revenue management. The outputs are based on the Natural Resource Charter’s 12 precepts, and cover the 6 precepts which are found to be the weakest links. Key assumptions underpinning this logic are around political incentives for reform, institutional incentives for reform and adequate budget allocations (and releases) to the supported agencies.

Appraisal Case
This section provides options for a DFID project with the aim of improving the management of oil and gas resources to maximise the development benefits for the people of Ghana.
A. What are the feasible options that address the need set out in the Strategic case?

This section proposes three options for the delivery of the proposed programme: all three contain both an effort to strengthen public sector institutions in the oil and gas sector and support to build voice and public accountability through CSOs and oversight bodies. However, the approach, and proposed use of aid, differs markedly in each case:

Option 1, Government focus: An institutional development approach focusing on Ministry of Energy, Finance and Ghana Revenue Authority and the Petroleum Commission with limited support to Parliament and media. Key assumption: Government is firmly committed and able to drive governance and regulatory reform and that the leadership of the main sector organisations know what they need to do.
Option 2, demand-side focus: The majority of support is provided outside government to a few strong and strategic civil society organisations, complemented by support packages for small innovative ideas, e.g. on use of technology to drive accountability. Key assumption an institutional approach is not appropriate because powerful vested interests will hinder change, leaving few openings and little hope for governance reform.
Option 3, a comprehensive approach: Support will be provided to reformers in state institutions while building constructive external pressure on those in the state resisting reforms. Working ‘with the grain’ in both government and civil society, support will be provided in a way that is demand driven and flexible enough to respond to opportunities as they arise. Key assumption: government commitment for seeing through the reforms and our programme able to address critical areas and vested interests.
Option 4 is the counter-factual “do nothing” option.

Option 1: Supply-side focus – developing institutions: This approach would focus aid on the key public institutions in the sector. It would assist the Government in systematically assessing organisational needs and then deliver capacity-building support.

Leadership would be provided by the Ministry of Energy supported by the Office of the President. The aim would be to enable senior management teams to implement a fully functioning new regulatory body (i.e. the Petroleum Commission) and to reform the existing institutions (i.e. the Ministry of Energy, MOFEP and the GRA) so they can carry out a range of essential revenue-related functions efficiently and effectively.

The programme would cover all or some of the following tailored to the needs of the specific organisation in question:
- Further legislative changes and introduction of regulations;
- Development and implementation of a corporate plan;
- Redefining organisational and departmental roles and responsibilities;
- Organisational structures and design;
- Systems, procedures and operational guidelines;
- Senior management development through advice and mentoring; and
- Human resource development and training.

This approach requires a substantial investment in capacity building. It also needs to be integrated with an effort to meet any investment funding gaps, for example for equipment or for acquisition of new information systems.

Under this option we would only provide minimal critical support to civil society and only in areas directly related to the institutional support such as the PIAC. The option assumes sufficient funding is already available for oil-related civil society, e.g. through STAR-Ghana.

Such a sector development approach is common amongst donors working in Sub-Saharan Africa at the start of a reform exercise. International and Ghanaian experience tells us that sector institutional development has been more successful where there is strong political support for undertaking such a major reform initiative and where senior management in the organisations are able to make good use of technical assistance and training.

In Ghana, examples of such an approach include the World Bank, which here focused its Oil and Gas programme around the Ministry of Energy, Petroleum Commission and MOFEP. However, it faced initial implementation challenges and capacity building has concentrated on training and equipment provision. Operational costs for the Petroleum Commission office and staff have also been funded. Partners have been relatively slow to respond with specific proposals for institutional development and these have been narrowly focused on training.

DFID has relevant experience with the establishment of autonomous public bodies, albeit in different sectors. This has generally been successful and partner governments have welcomed substantial long-term technical assistance support, including experts in senior line and advisory positions.

Option 2: Demand-side focus – Voice, public accountability and oversight: In this option, the emphasis of the project would be placed on creating pressure on ministries and statutory authorities to deliver improvements in revenue management, collection and utilisation. An important facet of the approach would be to encourage public scrutiny. This would involve supporting advocacy, lobbying and forums for more informed public debate in order to highlight obstacles and increase the pace of institutional reform.

The approach would involve:
- A vigorous effort to actively engage in the issues and steer around obstacles to reform, using whatever means appropriate such as assessing and investigating cases of mismanagement and corruption; including strong efforts to promote CSO advocacy to seek Government action to implement current legislation.
- Enhancing the capacity of civil society to monitor performance, highlighting shortfalls and using public opinion to ensure transparency on the part of the public bodies and private companies engaged in the sector.
- Promoting the role and enhancing capacity of public oversight and accountability bodies to scrutinise and sanction poor performance and delivery in the oil and gas sector.

Option 2 assumes there are fewer opportunities for reform in state institutions because political leaders and stakeholders are content with the status quo and that whatever technical gaps exist can be overcome with support from the WB and Norwegian interventions.

The aim would be to work with and nurture the incentives for Government to improve the effectiveness of the public institutions managing, regulating and developing oil and gas revenues. By encouraging public accountability politicians can be held responsible for any failures to mobilise oil revenues for development. Periodic elections and public pressure may help build pressure for MDAs to take steps to improve their effectiveness.

Option 2 therefore involves UK aid being provided to expand and finance:
- Work undertaken by NGOs and the media to monitor and report on Government performance in relation to licensing, capture of tax revenue and management of the heritage and stabilisation funds;
- Applied policy analysis and research on relevant topics such as macroeconomic management and forecasting of oil revenues and the investment of oil revenues; and
- Capacity building and funding of parliamentary sub-committees, PIAC and the Auditor General’s office to develop the range and quality of their investigation and reporting in relation to oil and gas revenues.
Delivery would require adopting elements of the experience from the Facility for Oil Sector Transparency (FOSTER) and Infrastructure Advisory Facility programmes in Nigeria.

This option requires a proactive approach by programme managers to identify issues and to work on them with CSOs and oversight bodies to ensure advocacy and oversight is based on high quality, evidence-based analysis and well-targeted.

In Ghana there is evidence that oil and gas-related CSOs have been somewhat influential. Public interest and demand from civil society arguably led the Government to decide to consult more widely on the development of the legal and institutional framework for managing and regulating oil and gas revenues. This seems to have been a major factor in ensuring that the legislation passed so far is in line with international norms and good practice.

Another example is the first PIAC report, which highlighted a possible overestimation of corporate tax payments by oil companies and the consequent impact on the stabilisation fund. The concerns identified have led the Government to adopt more realistic forecasts and to take steps to rectify capacity constraints in MOFEP.

There is also academic literature and evaluations of NGO campaigns in many sectors that show how demand-side pressure can alter public policy, laws and the approach of public organisations. There is, however, less evidence in the oil and gas sector, although the DFID-funded FOSTER project in Nigeria has early evidence that if well managed, progress can be made in promoting change in challenging environments.

Option 3: Strategic institutional development and public accountability: Option 3 combines strategic interventions in building supply-side public institutions, with a more responsive and opportunistic element that supports demand-side accountability and empowerment actors. These components will be complemented by a “Strategic and technical support facility” which will seek to identify further opportunities for supporting reform efforts in public sector institutions and beneficiaries outside Government.

The strategic and technical support facility would develop and refine ideas and approaches for working with oversight bodies including PIAC, the Audit Office and Parliament. There would also be a specific effort to extend the work of CSOs, think tanks, and other accountability actors and interest organisations (chamber of mines, chamber of commerce etc) so that they can engage more substantively with public sector institutions. The aim would be to promote constructive dialogue and to develop new instruments of public accountability and information provision. It would build the interface between accountability actors and Government.

Where the institutional capacity-building interventions come up against barriers to reform, demand-side initiatives in complementary areas and in creative ways could be supported. For example, efforts to improve the regulation of licensing agreements or revenue collection performance could be linked with support to civil society and the media to track and monitor Government efforts in these areas.

There is some experience with this type of approach in oil and more extensively in other governance reform areas. The State Partnership for Accountability, Responsiveness and Capability (SPARC) programme in Nigeria and Financial Management Programme (FINMAP) in Uganda have elements of such a programme as it aims to work simultaneously with public entities, civil society and the media in a flexible way to address serious constraints and obstacles affecting the governance, management and utilisation of resources.

This option recognises that the conditions for the development of a fully worked through institutional development strategy in the key state institutions (the Ministry of Energy, the Petroleum Commission, MOFEP and the GRA) may not yet be fully met. However, there are parts of these organisations where there are strategic entry points around already well-defined needs and potential projects. It is therefore possible under this option to develop a more selective and focused approach to institutional development and building infrastructure and further reform.

The approach also recognises the value of maintaining flexibility, so that support can be adjusted as the political environment dictates and the programme progresses. It would be grounded in strategic partnerships with the key Government institutions that have already requested support, but also leave room for new opportunities where entry points present themselves.

Examples of projects with public institutions are shown in Annex VI based on preliminary discussions with stakeholders. This approach would depend on the ability of government to generate and sustain political support for addressing internal coordination challenges as different parts government give up certain functions (some commanding considerable power and influence).

Option 3 is based on the technical, legal, institutional and political discussions with partners during the design phase. The options works to reinforce the policy environment and at the same time mitigate risks and negative drivers. There would be a substantial programme of support to the key public institutions in the sector where the needs are already defined (MOFEP, the GRA and the BOG). Support would also be extended to the Ministry of Energy and the Petroleum Commission to help define their needs in more detail and over time to adopt a phased build-up of institutional support.

Institutional support would include capacity-building technical assistance (long-term advisory and short-term expertise) plus training support and could cover some of the areas identified in Option 1. Such support could be started immediately as part of the first phase of the proposed programme.

Choosing between the options
We have selected four key criteria against which these options can be assessed. We have summarised these in the box below:

Table 1: Evaluation of options against criteria
Criteria	Government ownership	Degree of policy influence	Sustainability	Economic benefit
Option 1	Medium	Medium	Medium	Medium
Option 2	Low	Medium	Medium	Medium
Option 3	Medium	High	High	High
Option 4	N/A	Low	Low	0

Section 5 considers the economic benefits in more detail but this chart suggests that Option 3 should be preferred from the range of possible interventions. This is because it offers the Government flexibility and ownership and a high level of influence over the development of sector policy and institutions while also achieving the highest economic return to the proposed investment. It also recognises government’s intentions on transparency – e.g. through EITI. Social impact is also likely to be higher under this option because engagement with civil society will help support reformers in government to ensure employment benefits from the industry and to ensure the effective use of oil revenues for poverty reduction.

Option 1 offers a good level of government ownership but is expected to generate lower overall economic benefits because it places less emphasis on accountability and deploys a delivery model for technical assistance that, in practice, has only occasional successes. Social impact will likely be lower for the same reason. Option 2 has the big disadvantage of low ownership by the government, longer time frames and lower economic benefits than Option 3.

B. Assessing the strength of the evidence base for each feasible option

While there are no technical fixes that guarantee improved outcomes in a complex high-profile sector like oil and gas the evidence suggests that a holistic, strategic and flexible approach is most effective and efficient.

Table 2 below the quality of evidence for each option is rated as either Very Strong, Strong, Medium, Limited (or No Evidence)

Table 2, Summary strengths of Evidence Base for Options 1-3
Option	Evidence rating	What the evidence says
1	Medium	Technical support focused on the executive works when political support is strong and clear (and vice-versa)
2	Medium	Few examples of large programmes focusing entirely on demand side interventions in countries where government is approachable. / Limited evidence on the extent to which civil society will be able to engage constructively and effectively influence government. / Evidence of risk of undermining government legitimacy and creating tension between government and civil society/Parliament.
3	Medium	Increasingly strong evidence that working strategically and opportunistically on all core elements of state capability, accountability and responsiveness is the most effective in places like Ghana. / Evidence from similar interventions that strategic support facilities can play crucial catalytic role (strong examples from similar DFID projects – but narrow evidence-base).

Option 1: Government focus: Evidence of Impact?
Medium: There are clear and well-documented technical gaps within the executive in Ghana on oil and gas management. The design work largely reconfirmed these findings. In turn, this is the reason why the existing WB and Norwegian interventions focus on the executive. However, the evidence is equally clear that except in situations where government leadership (political and operationally) and management capacity is very strong, technical stand-alone interventions tend to “punch below their weight”.

Initial experiences from existing interventions in Ghana support this evidence, i.e. while there have been improvements in terms of capacity, the overall capability remains low and the overall regulatory framework remains weak.
Option 2: Demand-side focus: Evidence of Impact?
Medium: Demand side interventions can be effective in a number of ways. However, in a situation where government capability is limited and yet open to engagement civil society interventions tend to try to fill the gap and start providing capacity support to the executive. While well-intended, there is limited evidence that it actually leads to systemic and sustainable improvements in capability and responsiveness.
Option 3: Coordinated strategic support to both government and demand-side: Evidence of Impact?
Medium: Increasingly strong evidence of successful experiences, e.g. in the FOSTER programme in Nigeria as well as within a number of non-extractives interventions. In addition, the design mission identified the following strengths:
- There are present gaps in donor support, with a substantial focus on technical support to the executive.
- It could improve allocative efficiency, and allow proactive management.
- External intervention may be able to “join the dots” and facilitate and encourage partners who may otherwise not meet and collaborate to do do.
The Counterfactual
Key features of the option of not intervening include higher risks of resource curse, weakening of the citizen-tax link, waste and increased corruption.

C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner?

The implicit objective of the intervention is to improve overall capability and responsiveness of Ghana’s government to regulate, collect and manage oil and gas resources.

All options therefore aim to build local capacity. Options one attempts to do so directly within the executive. Option 2 focuses on strengthening the demand-side, with an assumption that demand-side push will lead to an executive response. Option 3 concurrently supports direct local capacity building of government, Parliament, the PIAC, media and the wider demand-side.

D. What is the likely impact (positive and negative) on climate change and environment for each feasible option?

There are no significant experiences from similar interventions in Ghana, but there are lessons from other work on natural resources and environmental governance in Ghana, particularly from the mining sector, mining revenue audits and projections and experience of Strategic Environmental Assessment and environmental regulation.

In line with the DFID Future Fit agenda, positive recognition of opportunities is suggested as part of dialogue. The programme is able to pro-actively encourage and support robust environment policies and regulation to ensure risks are addressed and that implications for revenues and for institutional mandates, responsibilities and capacities in this Business Case are taken into account. At a minimum, the programme should ensure a do-no-harm approach, including ensuring attention to health and safety and financial dimensions of environmental liabilities, and helping to compile an overview of environmental procedures, standards and contact points. This will help to deliver a clear institutional and regulatory set-up with designated mandates, tasks and resourcing that has been important to the development of oil and gas and geothermal energy[6] in other countries.
[6] Sander, M (2012) Lessons learnt from geothermal-friendly regulatory frameworks in Iceland, Kenya, New Zealand, Philippines and the United States of America. Geothermal Resources Council Transactions at https://pangea.stanford.edu/ERE/db/IGAstandard/record_detail.php?id=14115

1. By clarifying responsibilities, procedures and potential liabilities, it will reduce investor and operator risk and promote implementation of a stable and predictable regulatory framework. This will also assist in terms of civil society and Parliamentary oversight and accountability.
2. The likely climate change and environmental risks and opportunities of the different options all depend on the extent to which environmental capacities and measures are further addressed through other programmes, beyond DFID alone. The risks to the preferred option on institutional accountability and public accountability are categorised as C (low potential impact), the potential opportunities are classified as B. This relies on effective integration of the environmental regulation, procedures, capacities and liabilities with the areas under focus through this programme.

The option of supply-side institutional development is graded as medium risk (in the absence of relevant on-going inputs) and medium opportunity. Option 2 on demand-side accountability is partly addressed through a complementary DFID programme, the Western Region Coastal Foundation.

Table 3, Climate Change risks and opportunities
Option	Climate change and environment risks	Climate change and environment opportunities
1. Supply-side institutional development	B – manageable potential risk	B – medium opportunity
2. Demand-side accountability	B – manageable potential risk	B – medium opportunity
3. Institutional accountability and public accountability	C – low potential risk	B – medium opportunity

See Climate Assurance note (quest number 4214432) and annex VIII for further detail.

E. If any, what are the likely major impacts on social development?
The direct impact of the programme on social development is limited. However the indirect impact is very significant.

Oil and gas resources have the potential to have major social impacts in Ghana. Oil provides revenue needed to move Ghana firmly up the Middle Income Country ranks. In this scenario, government services would improve and over time, quality of education, health and other services would improve. Infrastructure would improve leading to faster growth and more jobs. Gas can be used to increase power generation and thereby further accelerate growth and competitiveness.

On the other hand, if the oil and gas resources are not well managed, the impact on social development could at best be limited and at worst very negative (Angola, DRC, Nigeria, Equatorial Guinea).

Other DFID interventions are supporting equity, gender and social development issues.

F. Economic Appraisal; Costs and benefits of the intervention

Cost
Option 3 involves significant costs associated with working both with government and with civil society. The combined costs are estimated at US$17.25 million. Table 4 below provide a breakdown for each year of implementation. Annex IX contains a breakdown by institution with a brief description of activities.

Table 4: Costs of Option 3 per year
	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Output 1, Strengthening oversight and enhancing regulation						£7,700,000
Petroleum Commission	£900,000	£900,000	£900,000	£500,000	£500,000	£3,700,000
Ministry of Energy	£350,000	£350,000	£100,000	£100,000	£100,000	£1,000,000
Strategic and Technical support, social media and civil society	£900,000	£900,000	£500,000	£350,000	£350,000	£3,000,000
Output 2, Improving revenue collection						£4,000,000
GRA	£700,000	£400,000	£200,000	100,000	100,000	£1,500,000
Strategic and Technical support, social media and civil society	£600,000	£600,000	£500,000	£400,000	£400,000	£2,500,000
Output 3, Improving revenue management						£4,050,000
Ministry of Finance & Economic Planning	£350,000	£350,000	£350,000	£350,000	£350,000	£1,750,000
Bank of Ghana	£250,000	£200,000	£100,000	0	0	£550,000
Strategic and Technical support, social media and civil society	£590,000	£540,000	£240,000	£190,000	£190,000	1,750,000
Monitoring, audit	£500,000	£350,000	£250,000	£200,000	£200,000	£1,500,000
Total	£5,140,000	£4,590,000	£3,140,000	£2,190,000	£2,190,000	£17,250,000

Costs of sub-optimal options
The main differences in costs of Option 1 against Option 3 are:
- The costs to government agencies, which are estimated to be increased by 50% specifically for capital expenditure as equipment and material would be supplied;
- The costs of supporting Parliament, PIAC and CSOs, which are estimated to less than half of those of Option 3, with support to only the key needs in the PIAC and Parliament.
- The costs of ‘Programme advisory and influencing facility’ would be reduced to £0 as the approach would be conventional and state focused; and
- Audit, monitoring and review are relatively high, due to the need absence of a strategic influencing unit; reviews will likely take longer and audits will have to be more extensive.

The main differences in costs of Option 2 against Option 3 are:
- The costs of supporting government institutions (not envisaged in option 2)
- The costs of supporting Parliament, PIAC and CSOs, are reflecting outputs on capacity building, analysis/building evidence and effective media and engagement strategies.
- The support Social Media and Broadcast outputs, which are also larger as significant additional pressure will be needed to affect change; and

Table 5: Costs of Option 1 and Option 2 versus Option 3
	Option 3	Option 1	Option 2
GRA	£1,500,000	£2,250,000	£0
Petroleum Commission	£3,700,000	£5,550,000	£0
MOFEP	£1,750,000	£2,625,000	£0
Ministry of Energy	£1,000,000	£1,500,000	£0
BOG	£550,000	£825,000	£0
Parliament, PIAC, CSOs,	£750,000	£300,000	£2,000,000
Social Media, Broadcast	£500,000	£250,000	£1,666,667
Strategic and Technical support facility	£6,000.000	£0	£1,166,667
Monitoring, audit	£1,500,000	£1,175,000	£1,000,000
Total	£17,250,000	£14,475,000	£5,833,333

BENEFITS
This section seeks to assess the benefits of the intervention against its costs. Many of the benefits from the intervention are hard to quantify, and therefore any quantification of the benefits is likely to significantly underestimate the potential overall benefits from each option.

Quantified benefits
Effective management of the sector (quality regulations with clarity of roles, relationships and consistency of procedures) improves regulator efficiency, transparency and accountability. It also reduces ad hoc behaviour, potential for delays, business loss, and corruption, and allows for better monitoring and accountability. This can translate into significant benefits in monetary terms for a country, for instance by avoiding delays due to mismanagement and reducing leakages, illicit flows and loopholes.

Avoided losses
1. It is estimated that poor management of the oil and gas sector in Nigeria costs between 1% and 10% of total revenues to government. At the higher end, this costs Nigeria around US$6 billion a year from a government take of US$60billion (Nigeria EITI reports and Petroleum Revenue Special Task Force reports).
2. Further evidence suggests that an improved governance environment (civil society, industry and public sector) can yield significant benefits by avoiding illicit financial flows. For example, according to Global Financial Integrity, ‘illicit financial flows from Africa totalled at least $854 billion, and could reach as high as $1.8 trillion when taking into account missing data from certain countries and other conduits of illicit flows not captured in the study’. Resource-rich economies are likely to suffer more from illicit flows. On average, ‘countries that export oil lost capital at nearly $10 billion per year, far outstripping the $2.5 billion per year lost by the group of countries exporting non-fuel primary commodities.’[7] [8]
  [7] ‘Plugging Africa’s Leak’, Foreign Policy in Focus: http://www.fpif.org/articles/plugging_africas_leak
  [8] The absence of a collaborative framework between different government agencies can translate into significant financial losses. (Paul, T., May 2012, ‘Fiscal fallings, fallacies and fixes’).

In addition, effective oversight can reduce exemptions and loopholes in the application of the regulation. For example, assessing cost structures and auditing have led to the ‘disallowing’ of capital allowances. In Ghana, a recent audit report by the GRA reduced the total cost on which capital allowances would have been granted in an oil field by $529 million. At a tax rate of 35% that is effectively future tax liability of $185 million. In Nigeria, coordinated efforts between the Ministry of Finance, the Federal Inland Revenue Service and the Nigeria EITI to follow up on findings from the NEITI Auditors Reports captured an additional US$ 440 million for the government.[9]
[9] Together they captured an additional: ‘$80,740, 000 from the 1999-2004 audits, for 2005 audit the sum of $90,907,000 was recovered and from 2006-2008 audits the sum of $270,984,622 have so far been recovered based on the findings of our audits respectively’.

Applying the Nigeria figure of 10% oil revenue losses to Ghana would suggest possible loss of around £50 million in 2014[10]. A more conservative figure of 5% losses in Ghana is assumed here, combined with a success rate – incorporating an element of implementation risk along with acknowledgement that these losses cannot realistically be removed entirely – of 15% for Options 1 and 2 and 30% for Option 3. The higher rate for Option 3 reflects the fact that it simultaneously tackles government capability and civil society ability to scrutinise and publicise issues. This combines relatively high government ownership with synergies between interventions, which is more costly, but increases the chance of success. The impact on the analysis of applying these different success rates, along with other key variables, is explored in the sensitivity analysis outlined below.
[10] Using oil revenue estimates from IMF Article IV report for Ghana, June 2013, p.28.

Oil revenues are projected by the IMF to increase from 1.1 billion cedis (£330 mill) in 2013 to 2.9 billion cedis (£900 million) in 2017. It is assumed that it will take 2 years after initial implementation for the benefits of reduced losses to be realised, which are calculated as 5% of revenue multiplied by the success rate for each option. The benefits are assumed to continue for 4 years after the end of project implementation, but with a ‘decay rate’ of 50% (i.e. halving) each year. This results in benefits that peak at £11.0 million by the 5th and final year of the project for Options 1 and 2, and £21.9 million for Option 3. All of the costs and benefits are discounted to present values at a central rate of 10%, as described below. Applying a 2-year delay before any reduction in losses is achieved, leads to a conservative estimate since discounting ensures that later benefits are accorded a lower value.

Delays avoided
The new Tweneboa, Enyera and Ntomme (TEN) oilfield, with estimated recoverable reserves of 245 million barrels of oil (and 365 billion cubic feet of gas), is planned to come on stream in 2016, reaching peak production of 100,000 barrels per day (bpd) by 2018. Without support to government institutions to facilitate the process, it is assumed here that the development is likely to incur a delay of 1 year. This is considered a conservative assessment; as is a slow initial increase in production of 20,000 bpd each year over 4 years. If this 1-year delay can be avoided through the institutional strengthening provided by this project, this will bring oil revenues on stream a year earlier[11]. Revenue earned on each barrel of oil is estimated from total government revenues from oil in 2012 divided by the volume of oil ‘lifted’. Using this figure assumes a constant future price of oil, and assumes that revenues accrue only from royalties and carried- and participating-interest. Approximately the same amount again was budgeted by the government for 2012 for corporate income tax derived from the oil industry; this was not realised due to companies off –setting costs of investment against tax. Zero corporation tax is also assumed here for the initial years of the TEN oilfield as well.
[11] Bringing production forward by one year will also lead to the production ending a year earlier, which is taken to be in 25 years’ time. This future reduction in revenues is incorporated into the calculations, although the application of discounting significantly reduces the value of these future negative benefits.

A one-year delay would therefore lead to 20,000 bpd revenue forgone for each year from 2016 to 2019, which is valued at £47 million per year. A success rate of 30% is applied in avoiding this delay, for Options 1 and 3. It is expected that Option 2, which does not directly improve government capacity, will not derive this benefit. This therefore estimates benefits for increased government revenue for Options 1 and 3 of £13.5 million[12] for each of 4 years, starting from year-3 of the project.
[12] The annual revenue loss avoided in Option 3 is actually marginally higher, at £13.6 million, since this incorporates slightly lower expected ‘losses’ (as explained in the first quantified benefit) of a fraction of this revenue.

A third quantified benefit derives from avoided delay in the foreign direct investment (FDI) that accompanies oil and gas development, and the subsequent impact that this investment can have on economic output. This is estimated as a delay in 10% of FDI growth, which is converted into value-added (GDP) using an Incremental Capital-Output Ratio (ICOR) of 1-to-5.[13] This results in an estimated benefit for Options 1 and 3 of between zero and £3 million per annum, starting in year 2 of the project.
[13] Projected FDI is taken from IMF (2013), which demonstrates growth of around $350 million each year. 10% of this is around $35 million each year, which translates to around $7 million of output each following year (assuming investment impacts output a year later). This is using an ICOR of 5.0. USAID, 2009, "Ghana: Economic Performance Assessment", suggests an ICOR of 5.0 for 2003-2007; while ACET, 2012, "Ghana Economic Transformation Case Study - DRAFT", suggests an improved ICOR more recently of 2.9, which would increase the estimated size of this benefit. The benefit is the difference between projected growth with and without the delayed FDI, each year, which is estimated as between zero and $3 million each year.

Unquantified benefits:
Effective management and scrutiny of the oil and gas sector will have a wide range of benefits beyond those that are easily quantifiable or directly attributable to this intervention. Some of these are presented below, but are not included in the cost-benefit analysis.

- Reduced costs of doing business in Ghana, leading to more profitable firms who then pay more taxes. For example the Petroleum Commission is now charging US$150,000 for licensing, which used to be just US$2,000 when it was conducted by GNPC. Similarly, local firms have to register with the Petroleum Commission at a cost of US$5,000 before they can supply an international oil company. This shows how weak or inefficient regulation is already pushing up the costs of doing business in Ghana and creating obstacles that can impede the development of supply chains.
- Infrastructure created that can be used for other sectors. For instance, port facilities built or improved for the oil and gas sector can be used for other industries. As an example, the natural gas industry in Trinidad and Tobago required a new port to be built to import raw materials for manufacturing that used gas as an input, and for export of products. That port (Point Lisas) is now the biggest container port in the country, supporting a range of other businesses.
- Clearer fiscal terms should result from more effective government engagement in the oil and gas sector, saving time and money for government and for industry.
- Contribution to GDP and jobs. Value added is generated directly by the sector, including through wages and salaries for employment created.
- Wider impacts of improved transparency. Improved transparency of production, pricing, costs and tax payments allows parties external to the Government (such as academics and researchers) to analyse and compare different operators and countries, which can lead to the detection and deterrence of tax evasion and transfer pricing, among other benefits.
- Indirect and induced job creation. Every job created in the extractives sector can lead to an additional 1 or 2 jobs created in other sectors.[14] This could include off-site contractor employees working for the operation (i.e. those staff on the contractors’ payrolls who are employed to fulfil contracts at the operation); employees working at the operation’s suppliers and at contractors’ suppliers or subcontractors whose employment is attributable to business generated by the operation; and employment generated in the region by (community) social investment activities, including local business development.
  [14] The Mining Partnerships for Development handbook estimated this multiplier. The first study estimated that, for every job created in a mine, a further 1.65 to 2.5 jobs are created elsewhere – based on the World Bank study Large Mines and the Community. The second study estimated that, for every job created in a mine, a further 1.25 to 2.37 jobs are created elsewhere, the higher figure relating to ‘world-class mines’. This was from Schodde and Hronsky, ‘The Role of World-Class Mines in Wealth Creation, Society of Economic Geologists’, Special Publication 12, 2006, pp. 71–90. 1:2.5 jobs is closer to OPM’s experience of undertaking socioeconomic impact assessments using input–output (Guinea) and CGE models (Romania).
- The skills developed in the jobs created by the industry can provide economic benefits in other sectors of the economy. For example, in Trinidad and Tobago, the oil and gas sector employs 4% of the workforce, yet over 25% of the workforce has technical and vocational skills that are applied in a range of industries. Some of the schools that deliver much of this training were initially built specifically to meet the oil, gas and power industry needs and have been able to extend their offering to help the development of other sectors (construction, manufacturing, food processing, etc.).
- Improved safety regulation and culture in other sectors. For example, construction companies who work in the oil and gas sector also work for other clients. They may take the high-level safety culture out of the sector into their other projects.

Balance of costs and benefits
The costs incurred during the 5 years of project implementation are compared with the quantified benefits derived from year 2 to year 6 for increased FDI and subsequent GDP, from year 3 to year 9 for losses avoided, and from year 3 to year 31 for avoided delay in revenue from the new TEN oilfield (the longer time period is to allow for negative benefits in the outer years). All of the costs and benefits are discounted at a rate of 10%, to derive Net Present Values, to reflect the higher value to society of resources now than future resources.

All three options result in high benefit-to-cost ratios (BCR). This stems from the potentially large impacts that can be achieved from making improvements to the management of very substantial oil revenue streams. The highest BCR (of 5.5) is achieved by Option 3: it is the most costly of the options, but by combining substantial support to both government and to civil society, it is estimated to achieve considerably higher benefits. The next highest is Option 1, with its focus on improving government capability (BCR 4.9), although Option 2, which is considerably less costly to implement, still achieves a BCR of 4.5, with its support exclusively to civil society.

Table 6: Balance of costs and benefits
(in £ million, present values at 10% discount rate)	Option 1	Option 2	Option 3
Costs	£12.6	£5.1	£15.0
Benefits	£61.3	£22.9	£82.7
NPV, net benefits	£48.7	£17.8	£67.7
Benefit-Cost Ratio (BCR)	4.9	4.5	5.5
Internal Rate of Return (IRR)	110%	88%	120%

Sensitivity Analysis
It is important to stress test the key assumptions underpinning this analysis, particularly to compare across options that are all estimated to have strong benefit-to-cost ratios. By assessing the impact of altering variables within the analysis, it was found that there was little if any impact on the comparative BCRs of altering: the rate of discount, the exchange rates employed, the ‘decay function’ for benefits achieved beyond the project period, or the benefit derived from increased FDI and subsequent GDP.

If success for Option 3 in avoiding delay falls to 18% (from 30%) then Option 2’s net benefit exceeds Option 3 (and is well above Option 1, which falls below Option 2 as soon as success in avoiding delays falls from 30% to 26%). If success for Option 3 in avoiding revenue losses falls to 24% (from 30%) then Option 1’s net benefit exceeds Option 3. The results are therefore sensitive to assumed success rates, but reducing rates for the preferred option could point towards either of the other two options. Similarly, if revenues from the TEN oilfield are more than double what is assumed (220%), then Option 1 is preferred, while if these future revenues are half of what is assumed (55%), then Option 2 is preferred. While such variation is possible, particularly given the volatile nature of oil prices, there is no reason to suppose that either of these is extremes is more likely than the central estimate.

Another key assumption is that losses that might be avoided represent 5% of government revenues from oil. If this rises closer to 9% (closer to the level that Nigeria might be experiencing) then Option 2 becomes preferable. However, it is unlikely that Ghana suffers the same degree of loss as Nigeria, and this would imply an unrealistically high impact from such a relatively small project.

Finally, for the preferred option, Option 3, to become non-worthwhile (with a BCR below 1) would require a substantial reduction in estimate benefits. Option 3 retains a BCR of 2.5 if benefits from avoid revenue losses are reduced to zero, and a BCR of 3.1 if benefits of avoided delays are reduced to zero. Only when these benefits are simultaneously reduced by around 85% does the BCR for Option 3 fall below 1.
G. Theory of Change for the preferred option
The theory of change follows the intervention logic and is based on the 6 Natural Resource Charter precepts which the programme attempts to address. The Precepts come together in the 3 outputs.

The theory of change was prepared based on the findings of the design mission and prior and subsequent discussions and interactions with partner organisation, other donors, the EITI and the Presidency. This confirmed the impact, outcome and output levels and identified detailed processes and inputs required for the change to materialise. Finally, it helped identify the assumptions between each level.

Theory of Change for effective use of Oil and Gas

Additional revenue captured

Inputs
Resources & modes of engagement
Process
Programmes/policy interventions
Outputs
Access to & control of economic resources & opportunities
Outcome
 Effective management of oil & gas resources
Impact
Improved inclusive growth rates and less poverty
Technical input and training on legislation, regulation and oversight
Systems and tools (equipment) support provided.
International engagement complements technical in-country support.
Civil society, PIAC and media trained (technical and strategic) on analysis and effective engagement.
Government able to collect resources and transform them into sustainable growth and poverty-reduction interventions
Support to Government capability: Bilateral support to Petroleum Commission, GRA, MOF, BoG, Support to MoE through the WB
Improved management, accountability and transparency in the oil and gas sector
Improved regulation
Improved revenue management
Improved revenue collection

Support to empowerment and accountability, through ACEP, PIAC

Technical and strategic support through the advisory facility

International engagement through the G8 partnership

Assumptions:
Input -> process	Process->output	Output->outcome	Outcome->impact
Support facility in place	Implement. Capacity	Political leadership	Improved regulation
Credibility established	Risk appetite	Ability to enforce	Increased revenue
Management capacity	Stakeholder commitment

The assumptions up to output level are largely within the control of the project. The output->outcome assumptions are not directly within the project’s control. An important part of the design analysis and consultations has been to better understand the nature of the assumptions, the underlying risks, drivers and challenges as well as what the programme and wider UK efforts can do to make sure the assumptions hold. The comprehensive approach backed up by technical support from an advisory facility and political support through the G8 – Ghana partnership and wider political dialogue all focus on strengthening leadership, enforcement and commitment. See the detailed Theory of Change in Annex V.

H. What measures can be used to monitor Value for Money for the intervention?

Within the overall scope of the logframe as the main management tool three levels of VFM indicators could usefully be monitored. The inception phase will help refine or add to these indicators:

Effectiveness (“What”; outcomes, behavioural change): Headline indicator on oil and gas tax collection. Indicators on improved enforcement, better scrutiny of contracts, clearer institutional framework (e.g. the de facto role of the Petroleum Commission corresponds with the Act) better management of the heritage fund and improved capacity and engagement of civil society, the PIAC and Parliament.

Efficiency (“How”; outputs, improved systems and capacity): Indicators on individual institutional improvements as well as indicators on improved collaboration and coordination between relevant partners.

Economy (“At what cost”; inputs and activities): Benchmarking costs and management contract compared to similar interventions. The benchmarks are key, but given the complexity of the sector and degree of specialism required, benchmarks should be used in a way that still allows contracting the right people, who are essential to the credibility and success of the programme.

I. Summary Value for Money Statement for the preferred option
There are substantial benefits to be derived from the interventions considered in this programme. A number of potential benefits have not been quantified, but even with only three possible benefits quantified, estimated benefits substantially outweigh the costs. This stems partly from the fact that large impacts that can be achieved from making improvements to the management of very substantial oil revenue streams. However, largely negative experience elsewhere in Africa of oil revenues damaging governance suggests that the kind of impacts that this programme aims to achieve are not straightforward. So, while the preferred option (Option 3) has an estimated return of £5.5 for every £1 invested, there are significant risks around programme implementation and failure to achieve outcomes. These are mitigated to some extent in the preferred option, which combines direct support to government institutions along with support to civil society to hold those institutions to account. Ensuring value for money will also require regular review and scrutiny of progress.

Commercial Case
Direct procurement will be for one service provider for the duration of the programme.

A. Clearly state the procurement/commercial requirements for intervention

The commercial requirement in this case is to obtain highly specialised technical services and programme management at the least possible cost. Given the specialised knowledge required and the multiple interventions expected, a Service Provider will be sourced. We will tender through the Wealth Creation PEAKS.

During the duration of the project we will also engage directly experts and audit firms to help DFID carry out effective monitoring, independent reviews; annual reviews, audits and project completion reviews.
B. How do we expect the market place will respond to this opportunity?

We expect the market to respond positively. The scope of the programme includes technical aspects of oil and gas sector work, such as exploration, regulation, revenue management and taxation. Against this background, we expect some or most bids to come from consortia. In recent months, 5 companies have proactively visited DFID Ghana to promote and highlight their expertise within the extractives sector, and a recent similar tender run in another country four high quality bids were received. International service providers will be encouraged to partner with Ghanaian organisations in consortia, in order to maximise local content and knowledge transfer.

C. How does the intervention design use competition to drive commercial advantage for DFID?

DFID will conduct a mini-competition within the Wealth Creation PEAKS to select the service provider. Suppliers have already demonstrated appropriate expertise at competitive costs sourced through the PEAKS. The PEAKS process will enhance competition and encourage bidders to look for effective ways to deliver the outputs .The terms of reference will be structured to encourage flexibility and innovative thinking in how the programme is delivered, in order to achieve maximum results.

Criteria to be used for assessment will concentrate on experience and success in implementing programmes of this nature in a political and high-profile sector; experience of working in regulatory and revenue management in the extractives sector with particular emphasis on Oil and Gas; an understanding of and appropriate proposed response to the context of Ghana; and the ability to deploy rapidly and to maintain a high quality team over the course of the programme to deliver results. These will be considered alongside financial and organisational criteria, including demonstrably robust financial management; and a credible value-for-money proposal. It is envisaged that fulfilling these criteria is best fulfilled through a mix of Ghanaian and international expertise and partners.

A review point with a break clause in the contract will be included at the end of one year which will allow DFID to scrutinise the initial assumptions about cost drivers, and to renegotiate elements of the contract if required. This is a new area for DFID in Ghana. The intervention design enables us to benefit from competition in three ways:

- Expertise: It incentivises bidders to bring in expertise across a range of technical areas, which a programme implemented directly by DFID would not be able to deliver.
- Strategy: We get the best value for money in terms of implementation strategy – a programme with substantial flexibility on how to achieve outputs and work towards outcome targets.
- Results/costs: Payment will be on the basis of achieved outputs. Bidders will be incentivised to focus on results and thereby to efficiently and economically target activities and inputs

D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?

The major cost drivers are:
- Consultancy fee rates for technical experts (a mix of Ghanaian and international consultants)
- Direct expenses relating to the provision of consultants (e.g. travel, accommodation, visas, etc.)
- Indirect overhead costs of administering the project through a management team. These will include amounts within each fee to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, Ghanaian office, etc. We aim to negotiate a contract with management fees <10% and with transparency of overheads.

The experience and quality of consultants and programme management team are critical factors in securing value in this programme. Experts must be able to influence high-profile and important government policies and spending decisions in a country that is increasingly less aid-dependent, and in a sector with substantial vested interests.

E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention?

1. The contract for the service provider will be managed by the DFID-Ghana Governance Team with support from DFID Procurement Group., Selection of the provider will be carried out by a panel including DFID-Ghana and Government of Ghana Representative. Any conflict of interest will have to be declared and appropriate action taken. Scoring of bids will be based on the ability to deliver the services specified in the terms of reference and based on pre-defined criteria.
2. The detailed evaluation criteria and weights will be developed in consultation with PRG, the senior commercial adviser and the DFID Ghana Governance Team. They will reflect the focus on strategic influencing, systemic change and capacity building, the mix of expertise required and experience with DFID output based payments.

The contract will be structured as a six-month inception phase and a four and a half year implementation phase making a total duration of five years. There will be an option to terminate the contract after inception or throughout the project for failure to deliver. Competition will be based on the principle of maximum results for the stated budget, rather than on lowest budget for expected results. Bidders will need to show credible plans to achieve targets and results. In order to attract high-quality bids, there will be a pre-bid meeting with interested bidders.

The management contract and supplier performance will be closely managed throughout the life of the programme. The contract with the service provider will be designed to include payments authorised against satisfactory delivery of outputs, specific objectives and indicators/milestones. Alongside this, a range of performance-based KPIs will be developed and revisited at set intervals currently envisaged to be; i) the review at the end of the inception phase; ii) mid-term review; iii) end of project review).

Measurement of progress against these, linked to measurement of performance against the logframe, will take place during Annual Reviews. Quarterly financial and narrative progress reports will be also be monitored against work plans and financial forecasts.

Delivery through a third party entity (multilateral organisation; civil society organisation or support to government)

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner?

There will be two areas of indirect procurement where DFID will deliver the programme through civil society organisations and the World Bank.

Based on a proposal submitted to DFID by the African Centre for Energy Policy (ACEP), an accountable grant arrangement will be agreed between the parties to support the implementation of the demand side accountability of oil revenue management and regulations. ACEP is the main, specialised think tank on extractives in Ghana.

The Public Interest Accountability Committee (PIAC) will also be supported to strengthen their capacity to effectively carry out their mandate as a watch dog on government in managing the oil revenue. This will help build up their public accountability and reporting arrangements which will further embed voice and accountability structures in the oil and gas sector. This support will be provided through an Accountable Grant to Revenue Watch Institute (RWI) who is currently hosting the secretariat of PIAC.

PIAC was decreed under the Petroleum Revenue Management Act. It has taken financial and technical support from civil society and international NGOs to make it a reality and sustain it. As a result PIAC is not yet fully established with systems to effectively manage donor funds. So far all financial and technical support is channelled through RWI systems which are robust to ensure proper accounting for these funds. The support through RWI will not only ensure the effective management of the funds but also ensure VFM as the existing structures and systems of RWI will be used.

The Ministry of Energy will be supported through an arrangement with the World Bank to fund a number of outputs under the World Bank’s Oil and Gas Capacity Building Project. The Instrument to be used to provide funding to the World Bank will be an Externally Funded Output (EFO)agreement signed by DFID and the World Bank. The EFO is a standard World Bank instrument, which DFID has extensive experience with.

B. What assurance has been obtained on capability and capacity to deliver?

ACEP is an energy and petroleum non-profit think tank in Ghana. Their mission is to work to ensure prudent extraction of natural resources in Africa and the translation of resource revenues into real development outcomes. Since 2010, they have engaged with Government and other Civil Society organizations to ensure the passage of the Revenue Management law. They have also made a lot of policy inputs into the Petroleum Exploration and Production bill which is currently with Parliament. This funding mechanism is being used because it harnesses the expertise of ACEP and delivers value-for-money though capitalizing on the existing assets that ACEP brings into the Programme which includes; technical expertise in the petroleum and energy sector, effective advocacy and lobbying skills, strong organizational management and established network with other CSOs, parliament and government at all levels.

Other potential proposals were explored. However, none were as specialised as ACEP’s and generally these proposals fit better under the DFID-funded Strengthening Transparency, Accountability and Responsibility in Ghana programme.

The Revenue Watch Institute (RWI) was established in 2006 as an independent non-profit policy institute and grant making organization that promotes the effective, transparent and accountable management of oil, gas and mineral resources for the public good. Through capacity building, technical assistance, research, funding and advocacy, they help countries realize the development benefits of their natural resource wealth. RWI works in more than 30 countries including Ghana. RWI is a respected Policy NGO in the Oil, gas and mineral resource sector. RWI provides technical training and networking support to more than 50 partner organizations on every aspect of oil, gas and mining to build technical capacity and develop their monitoring, research and advocacy.

This project is looking to leverage this expertise because it capitalizes on the expertise and networking capacity of RWI to strengthen PIAC to deliver their mandate. In Ghana RWI has received funding from other development partners such as GIZ, the Open Society Foundations, the William and Flora Hewlett Foundation and the Norwegian Oil for Development Fund over several years and is known for their strong organizational and financial management systems to effectively manage the funds.

A due diligence assessment conducted by DFID MENAD scored RWI globally as medium risk. It stated that RWI has a robust management system in place to ensure that staff members have the appropriate capabilities and experience to carry out the required duties of their positions. RWI has sufficient professional experience, staff processes, systems, financial capability and assets to ensure delivery of project[15].. Prior to the signing of the AG letter, a due diligence will be conducted on the Ghana Office of RWI to provide further assurance of their capacity and capability.
[15] Due Diligence Assessment on Revenue Watch Institute, May 2013

C. Is there an opportunity to negotiate on anticipated costs?

DFID has had preliminary discussions on various cost elements of the programme such as office expenses, staff cost, equipment and audit fees especially on the proposal from ACEP and RWI. Subject to programme approval, is anticipated that further savings could be made during negotiations and implementation.

Financial Case
A. Who are the recipients of all proposed payments?

The main recipient of payments will be the service provider who implements the Technical Assistance and Management component of the programme on behalf of DFID. Through this facility, they will support government ministries and agencies to improve accountability and transparency in the oil and gas sector.

The Government of Ghana (Ministry of Finance, Ghana Revenue Authority, Bank of Ghana and the Petroleum Commission) is the recipient of Non-Budget Support Financial Aid.

ACEP and RWI through accountable grants to implement the demand side accountability of the programme and to strengthen PIAC.

The Ministry of Energy through an Externally Funded Output agreement signed by DFID and the World Bank. This may potentially also cover outputs related to the Petroleum Commission.

Other recipients of payments would be independent consultants reviewing the project to ascertain progress made against the logical framework and financial Auditors conducting audit to provide assurances that the organisations’ accounting systems are robust.

B. What are the costs to be incurred directly by DFID?

Costs incurred directly by DFID will be:

- Management and Technical Assistance to the Government of Ghana through a service provider will be £6,000,000
- Non-Budget Financial aid to four Government institutions and ministries will be £7,500,000
- Accountable Grants to ACEP and Revenue Watch will be £1,250,000
- Support to the ministry of Energy through an Externally Funded Output with the World Bank will be £1,000,000
- Cost of annual reviews, Audit, Monitoring etc will be £1,500,000

C. What are the costs to be incurred by third party organisations?

The main costs incurred by ACEP and RWI relate to analysis, consultation and dissemination of information as well as training, media coverage or media production.

D. Does the project involve financial aid to governments? If so, please define the arrangements in detail.

DFID support to the Government of Ghana will be under a non-budget financial aid mechanism. The UK Partnership Principles will apply to this programme. This grant will be governed by provisions within a bilateral MoU with each of the four ministries and agencies which will be signed between the Government of Ghana and the UK Government. Funds will be disbursed based on a “request for funds” letter received from the Ministry of Finance and payment will be made into designated accounts held by the Central Bank, the Bank of Ghana.

E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin?

The Programme will be funded through our current resource allocation under programme budgets.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting?

The expected cost of the programme is £17,250,000 over a five (5) year period. Table 7 below gives the approximate breakdown of these costs by year.

Table 7: Profile of Estimated Costs per year
	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Output 1, Strengthening oversight and enhancing regulation						£7,700,000
Petroleum Commission	£900,000	£900,000	£900,000	£500,000	£500,000	£3,700,000
Ministry of Energy	£350,000	£350,000	£100,000	£100,000	£100,000	£1,000,000
Strategic and Technical support, social media and civil society	£900,000	£900,000	£500,000	£350,000	£350,000	£3,000,000
Output 2, Improving revenue collection						£4,000,000
GRA	£700,000	£400,000	£200,000	100,000	100,000	£1,500,000
Strategic and Technical support, social media and civil society	£600,000	£600,000	£500,000	£400,000	£400,000	£2,500,000
Output 3, Improving revenue management						£1,750,000
Ministry of Finance & Economic Planning	£350,000	£350,000	£350,000	£350,000	£350,000	£1,750,000
Bank of Ghana	£250,000	£200,000	£100,000	0	0	£550,000
Strategic and Technical support, social media and civil society	£590,000	£540,000	£240,000	£190,000	£190,000	1,750,000
Monitoring, audit	£500,000	£350,000	£250,000	£200,000	£200,000	£1,500,000
Total	£5,140,000	£4,590,000	£3,140,000	£2,190,000	£2,190,000	£17,250,000

The projections are indicative within the overall budget framework and actual allocations and spend between the budget lines will be adjusted based on partner performance and the need to keep the programme as effective as possible to respond to changing political situations in the oil and gas sector and the wider political context. Annual project reviews will recommend appropriate adjustments to allocations. As part of the tendering process for the Technical Assistance management component, the Service provider will be expected to provide credible estimates on the cost, which will be judged against similar DFID Programmes.

Non- Budget Support Financial Aid, Accountable grants and fees to service provider will be profiled on an annual basis and updated based on narrative and financial reports on a quarterly basis. DFID will keep a tight control over disbursement and forecasted spend. Forecasting will be updated by DFID on a monthly basis.

G. What is the assessment of financial risk and fraud?

The potential for financial risk and fraud is low for DFID funds.

Funds for this intervention will be spent through government systems using Ghana’s procurement, accounting, reporting and audit systems. Ghana’s public financial management are adequate to provide assurances on appropriate use of these funds. The design phase spent significant time on assessing financial management capacity in the 4 government agencies where support is planned and agree any additional safeguards needed ahead of fund disbursement.

The most recent DFID Fiduciary Risk Assessment (FRA) for Ghana completed in 2011, rated the overall fiduciary risk as ‘substantial’ (down from ‘high’ in 2005 and likely to improve further), An Annual Statement of Progress was undertaken in September 2013 to confirm that Government systems are still robust. A new FRA is due in January 2014. To provide more assurance for the efficient and effective management of the project, DFID will conduct a due diligence assessment of the capability of key staff on the project in the individual agencies and ministries.

DFID will mitigate the risk of financial impropriety and fraud firstly through requiring bidders to demonstrate robust financial and procurement systems and processes as one of the criteria for the competitive bidding process. The service provider’s financial management capability, including appropriate accounting and identifying potential fraud, will be part of the assessment of tenders.

As outlined in section D above, government partners receive money against approved work plans. The most recent DFID Fiduciary Risk Assessment(FRA) for Ghana completed in 2011, rated the overall fiduciary risk as ‘substantial’ (down from ‘high’ in 2005), while the corruption risk was considered ‘moderate’ (also down from ‘high’ in 2005). It identified progress in procurement oversight and audit, but pointed to possible areas of financial risk arising from:

•	weak planning and budgeting systems leading to poor allocation of resources;
•	weak commitment controls leading to unplanned fiscal deficits; inefficiencies.

An Annual Statement of Progress was undertaken in September 2013 to confirm that Government systems are still robust. A new FRA is due in January 2014.

Appropriate due diligence assessment of the Petroleum Commission and GRA will be undertaken to provide more assurance on their capacity to manage the funds. Some of the proposed partners (such as Ministry of Finance) are very familiar with DFID requirements. In addition to the normal dialogue and supervision undertaken by the DFID lead adviser and project officer, the service provider will also engage with the partners on a regular basis and thereby be in a strong position to sense or detect corruption and fraud signs.

ACEP has received funding from the DFID-led civil society pooled fund’ STAR-Ghana and is recognized as being a strong effective partner. To reassure ourselves, we will conduct a due diligence on ACEP prior to the signing of AG letter. Break points will also be introduced during the implementation period to ensure that service provided are appropriate and of high quality.

DFID programme staff will carry out spot-checks of the Programme Implementer’s systems and scrutiny of their financial statements, completion of asset registers and other evidence as appropriate. We will work with partner organisations to strengthen financial oversight. Continued disbursement of funds will be contingent upon adequate financial oversight mechanisms. We will work with partners to ensure that the agreed results are being delivered and funds are directed as appropriate.

The programme will also be subjected to periodic independent financial audit through the life of the programme to ensure that funds approved are used for the purposed intended.

H. How will expenditure be monitored, reported and accounted for?

Project progress will be monitored according to standard DFID internal procedures, involving Annual Progress Reports and a final Project Completion Report. These will be based on progress against the logframe which may be amended during the course of the project.

Expenditure incurred by the service provider will be invoiced to DFID monthly in arrears, covering approved activities implemented during the month. Such invoices will be scrutinised for accuracy by a DFID programme officer and quality assured by the deputy programme manager; any inconsistency would be resolved prior to the invoice being paid by DFID Accounts Department. The service provider will be expected to continuously monitor the progress of intervention and submit quarterly, six monthly and Annual progress reports to DFID.

The Accountable Grant project with ACEP and RWI will have separate logframes which will feed into the overall project logframe. Quarterly updates on expenditure and progress, and how they impact on the project logical framework will be required and assessed prior to making subsequent disbursements. DFID will have the right to access relevant records of these Partners for the purpose of expenditure verification.

Any capital assets procured under this programme will be treated in accordance with DFID procedures and declared to the DFID programme manager. DFID will determine how to dispose of remaining assets at the end of the programme.

The project will undergo periodic financial and value for money audits of its operations and recommendations from these audits will be taken forward with the programme. These audits will be carried out by independent audit firms who will assess the project against Effectiveness, Efficiency and Economy of its approach of implementation.

I. Are there any accounting considerations arising from the project?

No.

Management Case
A. What are the Management Arrangements for implementing the intervention?

The programme has four main components: non-budget support financial aid to four government ministries and agencies; technical assistance and project management by a contracted service provider who will establish an advisory unit; Accountable Grant agreements with the African Centre for Energy Policy (ACEP) and Revenue Watch Institute (RWI) and support to the ministry of Energy through an Externally Funded Output with the World Bank. Non-Budget Support Financial Aid – An MoU will be signed with the Government of Ghana to provide non-budgetary financial aid for funding specific activities of four agencies(Ministry of Finance, Bank of Ghana, Ghana Revenue Authority and the Petroleum Commission).

Technical coordination and direction of programme will be provided by the DFID Senior Governance Adviser with support from the Service provider. Project management support will be provided by a programme officer within the Good Governance Team in DFID.

Strategic and technical support and management: The project will be based around a small advisory facility where demand-driven technical and strategic support is made available to a) Government where reformers exist; and, b) Accountability actors, including the PIAC, civil society organisations and media.

Accountable Grant - Support to both the ACEP and RWI, will be given as an Accountable Grant and managed by the DFID Ghana programme team in line with DFID procedures, including, for example, annual and quarterly workplans and the quarterly reporting of results and finances.

EFO with the World Bank: The World Bank will manage the outputs of this arrangement on behalf of DFID. DFID will be supporting Component A.1(a) – Resource Management MOE (£1.5 million). This component supports MoE as it builds capacity to provide sector policy direction and supervise the regulatory agencies and state-owned companies that report to the Minister.

The advisory unit
The advisory unit, staffed and managed by the service provider will provide advice on interventions under the strategic and technical support facility as well as having management oversight of implementation. It will also provide support to all partners on design and implementation of their workplans. The design phase identified this setup as the recommended approach for political environments such as the oil and gas sector, where potentially powerful vested interests exist. The existing World Bank project expressed interest in collaborating with the unit. This approach recognizes that the success of reforms depends in large part on the political will and commitment of leadership and institutions. Where that exists, the project will nurture and support government institutions.

An advisory facility approach implemented by a service provider is deemed to be the best option. The facility would be managed at arms-length and be demand-driven, overseeing a pool of funds with the aim of:

- Delivering a range of demand-driven interventions and support as requested by government and non-government beneficiaries. This includes those interlocutors that sit between supply- and demand-side accountability actors;
- Proactively engaging and influencing indirectly the pace and direction of reform by supporting applied policy research by think tanks, professional bodies and other non-traditional organisations. Supporting greater use of social media and other public accountability forums will aim to reinforce governance and accountability in the oil and gas sector; and Reporting to DFID on the management and administration of the entire suite of projects funded under the programme.
- The advisory facility will engage with other donor support at the technical level – primarily the WB and Norway. The DFID lead adviser will lead donor engagement at other levels, such as the Energy Sector Working Group.
- There will be regular interaction between the advisory facility and the DFID lead adviser and the DFID project officer. On top of this, the DFID lead adviser will have regular meetings with both government and non-government partners as required on policy, implementation issues and financial management.

Once appointed the service provider will be expected to:

- Propose a budget and activities for the inception phase;
- Undertake an inception phase that includes a detailed sector political economy analysis and report on the plans, procedures and processes for implementing the programme;
- Define and cost the implementation phase of programming in more detail; and
- Agree detailed reporting arrangements and a system for monitoring programme impact, incl. key performance indicators.

In parallel as a first phase, the following actions will be undertaken:

- The Petroleum Commission, with a short initial diagnostic consultancy be undertaken to define the requirements and produce a project concept note;
- The Ministry of Energy, with the engagement of a strategy adviser;
- MOFEP, with the engagement of a strategy adviser;
- The GRA, with support on oil and gas tax administration; and,
- The BOG, mainly on capacity building for petroleum fund management.

In these cases there are already detailed proposals and these are summarised in the project concept notes and ToRs for advisors in Annex VI and VII. We will explore ways to identify and recruit short-term advisers and consultants to meet the needs of these beneficiaries so that inputs can be provided as rapidly as possible. Once the service provider is selected, they will engage with the implementing partners and advisers to determine how best to coordinate the input with other inception phase activities.

B. What are the risks and how will they be managed?
178. There are a number of potential risks which can undermine the achievement of improved governance, transparency and accountability in the sector. The main risks are in two clusters; political support and institutional incentives. Fiduciary and management risks are low.

Where possible, the main risks are internalised into the programme strategy (as opposed to maintaining assumptions about them). Even if political support and leadership is a constant risk, the programme can mitigate them in a range of ways. The G8 partnership provides an avenue for dialogue and commitment at the highest level. Support through Parliament, ACEP, PIAC and social media increases the demand for accountability. And the technical support and dialogue helps government partners to respond.

Table 8, threats, risks and response in the oil and gas sector
Threat or risk Likelihood Likely impact Response / Capture of state regulatory bodies by corrupt interests Low Medium Manage and encourage CSOs to remain vigilant. Support international accountability / Insuffcient commitment by Office of President Medium Medium Develop high-level engagement strategy. Use direct, G8, media and CSO avenues. / Manipulation of licenses and agreements Low Medium Improved systems in MoE and PC. Support CSO analysis and media. / Political interference in management or operations of Petroleum Commission Medium Medium Encourage heightened influencing and monitoring by CSOs / Ministry of Energy and GNPC resist transfer of responsibilities to Petroleum Commission Medium High Technical support to MoE and PC. Key focus area of advisory unit and CSOs. / Funding of Petroleum Commission operations not sufficient Medium Medium Technical support to PC (budget preparation), CSO and media engagement. Budget support and G8 engagement. / Weak leadership and capacity in Petroleum Commission Medium Medium Key project focus area. / Political manipulation of trust fund formula, e.g. misuse of benchmark for use of oil revenues in budget Low High Focus area of PIAC, media and civil society project support.. / MOFEP budget management insufficient and reduces effective utilisation of oil revenues Medium Medium Public financial management support through other programmes (budget support) / Poor fund management by MOFEP and BOG Low Medium Technical support to BoG. Manage and encourage CSOs to remain vigilant. / GRA unable to ensure compliance with tax regime or control avoidance and diversion Medium Medium Key focus areas of technical support to GRA. / Capture of civil society by corrupt interests Low Low No action / Absorptive capacity of CSOs, Parliament and other bodies limited Medium Low Project support needs to be tailored to take into account / Adverse environmental and social impact Low Low No action / Public backlash about lack of employment and business opportunities from oil and gas Medium Medium Media support should encourage evidence-based reporting and coverage to undermine ‘urban myths’

179.	The period of the run-up to elections as well as after elections in 2016 pose potentially high institutional and political risks, which the Governance Team and the advisory unit will monitor.

The advisory facility will play a key role in risk management – see section A above and in identifying new risks and strategies for existing risks.

Should the operational, fiduciary or political environment change dramatically, with the advice of the service provider, the DFID lead adviser and project officer will explore possible options. To the extent possible, implementing partners will be consulted. Depending on the nature of changes, options for continuation will be the primary focus, but if no value-for-money options can be found, options may include project termination.

C. What conditions apply (for financial aid only)?
A portion of this programme will be given as non-budget Financial aid to four ministries and institutions. Ahead of disbursements, we assess commitment to the UK’s Partnership Principles. These are as set out in HMG’s Conditionality Policy and Guidance and to be agreed in our bilateral MoU between HMG and the Government of Ghana on this programme: DFID’s four partnership principles apply and have been assessed in December 2012 as Ghana being compliant:

- Commitment to poverty reduction and the MDGs – Ghana has made huge progress in poverty reduction with a strong poverty focus in the national budget maintained. Significant progress has been made on several of the MDGs although several others are unlikely to be fully met. More needs to be done on growing inequities.
- Commitment to human rights and other international obligations – Ghana is among Africa’s best human rights performers and ranked third in all of Africa for its record on rights in the 2012 Ibrahim governance index. Progress on non-discrimination (including gender equality and other appropriate forms of non-discrimination such as disability, age and lesbian, gay, bisexual and transgender [LGBT] rights) has been slow: Ghana is ranked 122 out of 140 countries on the gender inequality index and domestic violence is a big challenge.
- Commitment to strengthening financial management – Although the Government ran up a worrying fiscal deficit (12%) in 2012 ahead of the elections, the new Minister of Finance has been transparent about the need to address this, and early measures already taken include reducing fuel subsidies, moving public servant salaries on to the new biometric system and proposing concrete measures to increase domestic resource mobilisation. A range of public financial management reforms are on-going although they have shown mixed results. Ghana tends to fare better than its peers in corruption rankings although there is concern over an increase in petty corruption.
- Commitment to strengthening domestic accountability – Ghana had a sixth consecutive, peaceful and well-managed election in 2012. It has a vibrant press and civil society, is a founding signatory of the Open Government partnership, and has recently made progress in improving domestic accountability.

The UK government in Ghana is promoting social, economic, civil and political rights through our development programmes and diplomatic efforts. DFID has programmes supporting all of these principles including leading a multi-donor civil society programme to promote transparency and accountability. DFID Ghana will perform a detailed assessment of performance against these partnership principles on an annual basis. In addition, a light touch assessment will be done as part of the annual review process.
D. How will progress and results be monitored, measured and evaluated?
Programme progress will be monitored using DFID’s standard performance management. An annual review will be performed of progress against logframe indicators. Because of the multiple components of the programme, which may not all be reflected in a logframe, a broader monitoring and evaluation framework will be developed and monitored by DFID. The annual review will also re-examine the assumptions in the theory of change. The service provider will help prepare annual reviews and support partners in their preparations.

Ministries and Agencies will develop annual work plans for the specific areas that DFID will support, with a results framework. Funds will be disbursed to them on a quarterly basis, and disbursement will be dependent on the submission of narrative and financial reports with progress against agreed quarterly targets. This will be managed and monitored by the DFID Programme Officer.

ACEP and RWI will develop annual work plans for the specific areas that DFID will support, with a results framework. Funds will be disbursed to them on a quarterly basis, dependent on narrative and financial reports with progress against agreed quarterly targets
World Bank: The World Bank will send us six-monthly reports on progress based on the duration of our support to the Government through them. In addition, DFID will participate in the regular supervision missions led by the WB task team leader.

Logframe: Quest No of logframe for this intervention: 4269501
ANNEXES

Annex I Institutions and capacity gap analysis
There are several state institutions that have an active role in managing the oil and gas wealth. The table below provides an overview of the main functions of the each entity.
Institutions and their mandates across the NRC decision chain

This annex presents an assessment of each institution involved in the management of oil and gas. The summary covers the following institutions:
- Ministry of Energy;
- Petroleum Commission;
- GNPC;
- MOFEP;
- GRA; and
- BOG.
The summary covers the mandate and accountability mechanisms of each institution, the institutional situation and skills set, and plans and priorities for assistance.

Ministry of Energy
Mandate and accountability
The Ministry of Energy acts in support of the Minister of Energy who represents the Government in the negotiation of all petroleum agreements and is responsible for their approval in consultation with the Petroleum Commission. The Minister is also a member of the Energy Sub-Committee in Cabinet.
The core functions of the Ministry are to ensure oversight of the sector and the corporate bodies involved (Petroleum Commission, Energy Commission, National Petroleum Agency, GNPC and GNGC). The Ministry of Energy is responsible for policy, planning and monitoring of upstream and downstream development.
Institutional situation and skills set
The Ministry has the capacity to carry out core functions but has been reliant on contract staff (some on secondment) to fill key posts in the Petroleum Directorate. There is an active training programme supported by the World Bank and Norway. Steps were taken in 2012 to assess requirements for additional posts and approval is awaited. A functional review is planned under the World Bank project.
The continued expansion of the oil and gas sector requires increased capacity to develop the policy and strategic framework for the future development of the sector. A priority for the Ministry of Energy is to develop a three-year rolling strategic plan incorporating any planned changes or refinements to work plans, structures and staffing. The Chief Director needs to build up a strong and experienced management team but it has been difficult to achieve this in practice. Currently, there are vacancies in senior posts including the Director of Petroleum and the Head of Upstream Development.
Plans and priorities for assistance
The World Bank is providing support for equipment and training which appears to be going well after some delays in specifying needs. According to the World Bank Project Adviser, there is a need for an oil and gas policy expert to provide strategic advice to the Minister and the Chief Director. Once the functional review is completed there may also be a need to help refine organisational structures and staff development plans. There are gaps in funding for training and it was suggested that attachments to the oil industry could be useful for some Ministry of Energy staff.
Conclusion
The Ministry of Energy is pivotal to the development of the sector. DFID should consider offering training and advisory support if the specific requirements can be clarified and cannot be met by the World Bank. Any training support should be linked to a needs assessment and involve on-the-job and informal job-related training in Ghana.

Petroleum Commission
Mandate and accountability
The Petroleum Commission was established under the Petroleum Commission Act of 2011, for the regulation and management of utilisation of petroleum resources and for the coordination of the policies in relation to them. This is in accordance with Article 269 (1) of the Constitution.
The core functions of the Commission are to promote efficient petroleum activities to achieve optimal levels of resource exploitation, recommend policies to the Minister and to monitor and ensure compliance with national policies, laws, regulations, agreements and standards among all participants in the sector.
The Commission is also responsible for monitoring, inspecting and auditing all petroleum activities, promoting local content and participation, managing a national data repository, granting permits, advising the Minister on development and decommissioning plans for petroleum fields and infrastructure, preparing annual public reports on petroleum resources and activities and analysing petroleum economic activity and submitting economic forecasts on petroleum to the Minister.
Prior to the launch of the Petroleum Commission, most of the regulatory functions were performed by GNPC and the Ministry of Energy retained an important role, for example in the approval and signing of licenses and agreements with the industry.
The Minister and Ministry of Energy provide the policy framework for the oil and gas sector as a whole and for the Petroleum Commission. As an autonomous body, the Petroleum Commission should have a high degree of independence. In practice it is accountable to the Ministry of Energy and the President for the effective and efficient conduct of the regulatory function consistent with Government policy.
Until such time as the Petroleum Commission is fully functional, the regulatory functions remain shared between the Petroleum Commission, GNPC and the Ministry of Energy. It is undesirable for the transition to the new institutional arrangement to be drawn out or to be allowed to persist. This situation would result in undermining the new legislation, a conflict of interest between GNPC’s commercial and regulatory functions, overlap of responsibilities and institutional confusion and uncertainty in the industry.
Institutional situation
The Commission is governed by a Board of seven persons appointed by the President, including its Chairperson, CEO and one representative of the Institute of Geoscientists, who is nominated by the Institute. Other than the CEO, no member of the Board may be appointed for more than two terms, each of which is for three years.
At present the Petroleum Commission is still in a start-up phase. Around 50 staff are in post in temporary offices pending their transfer to a new headquarters. The World Bank think the staffing level is high in relation to the size of the Ghanaian oil sector but despite these staffing levels there are important gaps in the technical and operational areas.[16]
[16] Interview with the World Bank.
The Petroleum Commission is funded by Government through the normal budgetary process. Despite ostensibly having a high level of autonomy, the Petroleum Commission is constrained to set its wage bill and salary structure in line with public service norms. Funding is provided for salaries but at levels which make it difficult to compete in the labour market for scarce technical skills.
According to the new senior management team, the Government has not allocated sufficient resources to meet the total start-up and anticipated costs required for the Petroleum Commission’s operational costs, new buildings, equipment, vehicles, etc. World Bank funding is, however, available under the Oil and Gas Capacity-Building Project. At present the Petroleum Commission is paying substantial recurrent charges for the rental of temporary accommodation.
The post of CEO is vacant and the new senior management team has only just been recruited. The organisational structure is based on earlier work carried out by consultants which allows for four directorates (Finance/Administration, Operations, Resource Management and Special Services). The Commission’s inability to recruit sufficient technical staff has led the Acting CEO to combine the Resource Management and Operations Director roles for the time being.
Funding is available to meet expertise and staffing gaps under the World Bank project but the Petroleum Commission has been slow to follow up and identify specific requirements. The World Bank has itself identified some high priority areas for capacity development including: (1) processing applications for field development plans and exploration licenses; (2) managing local content issues; (3) monitoring compliance with petroleum agreements; and (4) preparing to assume custody of the national data repository. Terms of reference for senior staff and advisers in these areas are seen as a high priority by the Bank.
Constraints on effectiveness
The Petroleum Commission requires stronger leadership and urgent action to fill the vacant CEO post. The President should either confirm the existing Acting CEO in post or make a new appointment. Once a new CEO is in place it will be easier to build a senior management team and to develop a strategic vision and forward operational programme.
The Commission is in the process of preparing a corporate plan and as a matter of priority this process needs to be used to develop a three-year rolling plan for the full transfer of all regulatory responsibilities and for the establishment of the structures, staffing, regulations, procedures and systems needed to carry out all the core functions of the Petroleum Commission.
Once the Petroleum Commission has clearly defined strategic objectives, operational plans and a capacity-building programme, it can develop an associated investment and recurrent budget. Until such a plan and forward budget are prepared it is not possible to accurately assess the funding gap. However, the resourcing of such a programme will be critical to the successful establishment and operation of the Petroleum Commission. It would also provide a financial framework within which donor funding from the World Bank, Norway and DFID could be incorporated.
The Petroleum Commission does not have a sustainable financial position at present. Funding options need to be considered and a policy framework developed, including funding its operations from the industry. This is possible within the existing legal framework. In addition to funds provided via the national budget voted for by Parliament and approved by the Minister of Finance, the Commission may raise funds in the performance of its functions and from donations and grants.
The Petroleum Commission’s organisational structure is being re-examined, in light of an on-going strategic planning exercise. The Petroleum Commission has been constrained in its ability to attract suitable personnel, given the general shortage of Ghanaians with requisite industry experience and the salary levels on offer. As with the Ministry of Energy, recent graduates are being hired, with several being trained to postgraduate level. At the executive level, recently retired GNPC personnel are currently filling some of the management gaps in technical areas. Administrative and non-technical positions are being filled through open recruitment but several petroleum-specific technical roles requiring experienced personnel remain unfilled. Some personnel have been seconded from the Ministry of Energy.
The Petroleum Commission needs to focus on delivering the range of regulatory services that it must provide urgently to the industry in order to establish credibility and to ensure that the required oversight of new developments is provided while also encouraging exploration and development. In order to achieve this, the senior management team will need to develop some clear objectives and performance targets to deliver in high priority areas over the coming 12 months.
A new CEO should also prioritise an institutional development programme to ensure that the new organisation can actually deliver these objectives. This kind of approach has been adopted by other agencies[17] and it would focus on:
[17] Interview with the CEO of the National Petroleum Authority.
- Clarifying and restating the role, responsibilities and duties of the Petroleum Commission;
- Updating or reviewing of organisation structures and job descriptions to ensure the Petroleum Commission is ‘fit for purpose’ and can deliver core functions;
- Development of operating instructions and procedures for Petroleum Commission staff;
- Achieving the full staff complement and prioritising acquisition of technical skills (which can be aid funded if necessary);
- Introducing IT systems that provide an interface with other stakeholders (GNPC, Operators, and Contractors) for managing the bidding and contract award processes as well as monitoring oil and gas operations in real time. IT for national data archive and for all business processes is also necessary;
- Human resource development strategy, including recruitment, retention, induction, promotion, etc.;
- Supporting implementation of the local content policy; and
- Mentoring and training staff in specific areas.
The shortage of skilled personnel and funding is compounded by the lack of regulations and operating procedures. These need to be prepared for all staff so that personnel know what is expected of them and how to carry out their jobs. Job descriptions need to be prepared to reflect the procedures.
The new management team suggests there is a shortage of experienced personnel and an urgent need for an effective on-the-job training programme, so as to increase the competence of the existing technical staff. This will require mentoring by aid-funded advisers, senior Petroleum Commission staff and cross-postings in other organisations in the sector.
The Petroleum Commission has considerable obstacles to overcome before it can be fully effective. The constraints outlined above need to be addressed if the Commission is to become able to interact with the sector investors and operators and to regulate them effectively.
Plans and priorities for assistance
Discussions with the Petroleum Commission senior management team identified that a critical area of concern for the Petroleum Commission was the high rental costs on their temporary accommodation and the lack of Government resources for capital spending on equipment and for non-salary recurrent costs.
It is possible that these areas could be considered as part of a broader programme with well-defined results and an outcome that could justify the package of inputs required. However, in our view the broader problem of funding is fundamental and should be tackled in the context of a clear three to five year planning and financing framework linked to specific outputs.
GNPC
Mandate and accountability
The GNPC was established under the Ghana National Petroleum Corporation Law, 1983 (P.N.D.C.L. 64) to undertake the exploration, development, production and disposal of petroleum. The Act empowered GNPC to, among other things, engage in petroleum operations and enter into petroleum exploration and production (E&P) agreements and other petroleum contracts, while conducting its affairs on sound commercial lines. The GNPC reports directly to the Minister of Finance.
The GNPC is liable to pay tax under the Companies Code, 1963 (Act 179). Any surplus remaining after taxes and retained earnings under a reserve fund to provide for expenditures for carrying out GNPC long-term plan and the annual work programme must be transferred to the Consolidated Fund. Furthermore, the books and accounts of the Corporation are to be audited annually by the Auditor General.
Institutional situation
The GNPC was set up as a national oil and gas company in 1983, training many technical and commercial personnel and participating in exploration and marketing activities. During that time, several international oil companies active in exploration activities partnered with the GNPC, providing opportunities for GNPC personnel to gain access to international know-how. By 2000, the GNPC had a staff of over 1,500, including several very experienced technical staff. In 2001, a change in policy saw the GNPC move from being directly involved in E&P to becoming a facilitator of investments in the upstream sector. This change resulted in a large number of the technical professionals being made redundant and migrating.
By the time of the Jubilee discovery in 2007, the GNPC was reduced to a very small number of almost entirely senior technical staff. The discovery also highlighted the potential conflict of interest of the GNPC in acting as a regulator, on behalf of the Minister, as provided for under P.N.D.C.L. 64, and as a party to operations. The GNPC is a joint venture partner in all production sharing agreements, usually carried through from the exploration phase. This prompted the Minister of Energy to make the policy decision to move the regulatory role back to the Ministry and develop the requisite capacity internally.
In 2010, a draft E&P Bill, to address the new realities of the sector, was presented to Parliament, when it was realised that the Constitution required the formation of a Commission to oversee the management of petroleum. The draft E&P Bill was withdrawn and the bill to establish the Petroleum Commission was then introduced. The Petroleum Commission Act of 2011 set up the Petroleum Commission as the regulator. The Petroleum Commission has since recruited personnel from the GNPC and some senior technical staff who have recently retired are currently leading the Petroleum Commission, including the Acting CEO.
After the start-up of GNGC in 2011, to operate and manage activities related to natural gas development the GNPC transferred the ongoing project to monetise gas produced from the Jubilee field, inclusive of the engineering and project management personnel. As a consequence, the GNPC’s entire engineering department has almost disappeared, leaving them short of required capacity to conduct their oil-related activities.
Constraints on effectiveness
The shortage of skilled personnel at the Ministry and lack of funding at the Petroleum Commission has meant that the GNPC continues to be responsible for some regulatory support functions, such as the appraisal of Plans for Development, on behalf of the Minister. As there is no clear path to transferring administrative control and capability between the three agencies, the GNPC is obliged to continue this role, for the safe and efficient management of the industry.
As a consequence of this shortage, many tasks in the state sector are being conducted by a handful of experienced people, almost all of whom have come from the GNPC, spread across four separate agencies. Compounding the situation, the high level of activity means that there is little time for senior staff to get involved in the administrative processes required to design operational systems and procedures for the new GNPC or to mentor and coach new hires.
The GNPC is also faced with financing challenges resulting from the more than a dozen oil and gas discoveries that will each require major capital injection for the GNPC to provide its share of equity capital.
Plans and priorities for assistance
The programme – using the advisers to the Minister and Petroleum Commission and targeted organisational development opportunities – will support the administrative transfer or regulatory functions from the GNPC and support the design and operation of a collaboration system to share the experience and knowledge of the limited number of Ghanaian personnel spread across multiple agencies in the state sector, inclusive of the Ministries of Energy and Finance, the various regulators and the GNGC.

MOFEP
Mandate and accountability
MOFEP has the mandate to ensure macroeconomic stability for the promotion of sustainable economic growth and the development of Ghana. The Ministry has responsibility over the budget planning and execution, debt management and macroeconomic forecasting. Fiscal spending has proved challenging to control, rising from 26% of GDP in 2006 to 43% in 2011. The Ministry has been unable to control a rising wage bill and increased public spending commitments following an election year in 2012.
Institutional situation and skills set
The Ministry is considered to be politically weak, and with insufficient power to curb spending. This partly reflects the volatile political environment that leads to frequent changes in Government as power changes between the two ruling parties. It also reflects the relative weakness of the Executive and the need for institutional strengthening of the Ministry. The current Deputy Minister is regarded as a reformer with the technical knowledge to spearhead a reform programme, but he lacks the political support from his party to make headway.
The Ministry is made up of 11 divisions that seem to work in isolation of each other with no clear distinction in roles. For example, both the Economic Research and Forecasting Division and the Real Sector Division provide forecasts that feed into the budget. Similarly, the Budget Office rarely uses information provided by the other division, such as the Public Investment Division of Debt Management. There is limited coordination across the Ministry, which again reflects the need for institution development.
Plans and priorities for assistance
The World Bank is leading a large public financial management reform programme through the implementation of an Information System. The project has not been very successful, and after six years less than half of the budget is executed through the system. GIZ has provided support to the Tax Policy Unit to strengthen their analytical capabilities and contribute to developing the national tax policy. This support has resulted in the approval of various bills that have widened the tax base.
The Real Sector Division has requested support to increase their understanding of the oil and gas sector and develop a fiscal model to improve forecasting.
GRA
Mandate and accountability
The GRA is responsible for collection and assessment of tax revenues from petroleum-related activities. This includes corporate income tax, capital gains tax and withholding tax on subcontractors as provided in the PITL 1987, and other tax liabilities covered in the Inland Revenue Act 2000 including VAT for subcontractors, unless otherwise specified in the petroleum agreements between the Government and contractors.
The core function of the GRA with respect to the oil and gas sector is to ensure full compliance with tax laws covering petroleum-related activities.

Institutional situation and skills set
The GRA is an independent authority established in 2010 reporting directly to the Ministry of Finance. The GRA resulted from a successful merging of previously separate institutions to encompass Customs, Small Taxpayers and Large Taxpayers Units. Over recent years the GRA has been carrying out an ambitious reform plan which has included re-structuring of the organisation, skills investment and a modern tax administration system. There are, however, still many areas that require further strengthening, for example integration of a tax administration system, as well as process and organisational development.
At a policy level, the GRA is not sufficiently influential to sway policy discussions. Concerns regarding the revenue implications of sector strategies are often disregarded and advice regarding revenue forecasts not used. Increased coordination with other ministries would facilitate the GRA’s institutional effectiveness, as would a revenue forecasting model developed in conjunction with counterparts in MOFEP.
The Petroleum Unit has been set up within the Large Taxpayers Unit with the mandate to collect from and ensure the compliance of taxpayers involved in petroleum-related activities. As a relatively new unit and a highly technical industry there is a need for skills upgrading in particular knowledge relating to upstream petroleum operations, industry cost structures and accounting, and commercialisation and marketing of petroleum-related activities. The Customs Unit is responsible for monitoring production levels of oil at each lifting to ensure the correct amount of royalty payments are received. This is an area that Customs staff are unfamiliar with and ill-equipped to sufficiently scrutinise.
Plans and priorities for assistance
Other donors have been active in providing support to the GRA. GIZ has provided support for the modernisation programme through human resources development, advisory services to guide a training strategy and office furniture. The World Bank has funded the implementation of a modern tax administration system, which is still in the very early days of roll-out, having only just completed the first module of registration.
The priority for DFID’s assistance would be to provide technical training to the Petroleum Unit on upstream petroleum operations, including cost structures accounting, and marketing for petroleum products to improve understanding of the industry. Training on audit tools for the oil and gas sector would also benefit the team to improve the quality of audit activity and improve tax compliance. Another area that concerns the GRA is validation of oil lifting off the Floating Production Storage and Offloading unit. Support here could involve assistance to establish an independent metering system or training in calibration techniques.
Conclusion
The GRA is an important institution for the collection of oil and gas revenues and limiting of revenue leakages. As a relatively young institution new to the oil and gas sector, support could yield positive results very quickly. Both the Commissioner and the department members expressed a desire to receive support as soon as possible.

BOG
Mandate and accountability
The BOG has the mandate to support macroeconomic stability through maintaining price stability and creating an enabling environment for sustainable economic growth. It pursues this objective through sound monetary and financial policies.
In relation to the oil and gas sector, the Petroleum Revenue Management Act decrees that the BOG has responsibility for the day-to-day operational management of the Petroleum Holding Fund within the framework provided by the Minister of Finance.
The Petroleum Unit is also a stakeholder engaged in the committee responsible for executing the benchmarking formula as prescribed in the PRMA.
Institutional situation and skills set
The BOG is an established institution independent from the Government and with the ability to attract a skilled workforce.
For the purposes of the day-to-day management of the Petroleum Holding Fund, a new team – the Petroleum Unit – has been set up in the Treasury department. The team is currently staffed with three people.
The Petroleum Unit has expressed concerns over the lack of clarity regarding the framework for the investment of the Petroleum Holding Fund. As the level of funds increases, this will be more important in order to maximise the return on investments.
Plans and priorities for assistance
The Petroleum Unit has received assistance from the Norwegians in the form of training, but additional support could be provided to improve the trading systems in use, knowledge of investment mechanisms, and forecasting.
The BOG could act as an agent of restraint on excessive public spending, consistent with its mandate to maintain macroeconomic stability. It should also be part of the development of a revenue forecasting model together with MOFEP and GRA.

Annex II Legislative framework
The legislative framework governing upstream oil and gas activities has had to adapt quickly to accompany the rapid developments in the sector. Up until the discovery of commercial quantities of off-shore oil and gas reserves in 2007, the legislative framework consisted solely of the establishment of the Ghana National Oil Company through the GNPC Law, and the Exploration and Production Bill of 1984 supplemented by the Petroleum Income Tax Law (PITL) of 1987. The nature of the legislation reflected the industry’s focus on exploration activities rather than development and production.
As the industry has grown, the legislative framework governing the sector has made progress. In 2011 the Petroleum Commission Act was approved which establishes a new legal institution under the Ministry of Energy to regulate and manage upstream oil and gas activities, replacing the GNPC as the regulator for upstream activities. Also in 2011 the Revenue Management Act was approved to provide a framework for the collection, allocation and management of petroleum revenue, including monitoring mechanisms. Still in discussion and awaiting approval is the Petroleum Exploration and Production Bill to repeal the previous legislation from 1986, as well as the Local Content Bill to supplement the Petroleum Commission Act.
The scope and content of the legal framework is comprehensive, covering all aspects of the NRC value chain.
Scope of legislative framework

Upstream operations
The draft Exploration and Production Bill 2013, which is expected to repeal the previous PEP Bill[18], uses international best practice and is comprehensive in its approach to upstream petroleum activities including all obligations and rights referring to licensing, exploration, development, production and abandonment.
[18] The Petroleum Exploration and Production Law of 1984 currently in place is considered inadequate, old and not reflective of modern day best practice. Certain requirements like the need for environmental and health and safety assessments are not included and nor are the terms of the fiscal model clearly specified.
The industry has highlighted concerns over increased power on the part of the state in areas such as ownership of natural gas, the ability to undermine the stability of petroleum agreements, arbitration provisions, and data use. Rather than intrinsic weaknesses in the law, these concerns reflect an attempt from industry to maximise its benefits. The Bill is currently being debated and will go Parliament to be approved.
What is not clear in the PEP Bill are the mechanisms for implementing the legislation. As soon as the Bill is approved provisions for implementation will require clarification through regulations and guidelines. Areas that require clarification vary from the regulation of operations to the negotiation of petroleum agreements.
Regulator
There are three regulators covering upstream, midstream and downstream operations. All three are established through law by the National Petroleum Authority Act 2005 for the downstream regulator, the Energy Commission Act 1997 (Act 541), and the Petroleum Commission for upstream operations. The legislation is adequate in providing the mandate for the regulators and broadly defines their functions.
In all three pieces of legislation there are provisions for regulations to define the mechanisms through which the institutions can deliver their mandate. In the case of the downstream regulator the National Petroleum Authority and the midstream regulator the Energy Commission, both have existed for longer periods of time and have clear regulations that govern their procedures.
A gap in the legislation exists regarding assigned responsibility for regulating midstream and downstream natural gas operations, such as petrochemical plants and distribution of natural gas by-products. This will become more relevant as Ghana commences natural gas production, with plans underway to commercialise stocks for the domestic market.
In the case of the Petroleum Commission, the Petroleum Commission Act is adequate in so much as the mandate is aligned with policy. However, the accompanying regulations that will empower the Petroleum Commission to carry out its functions are yet to be developed. The Local Content Legislative Instrument has been prepared and is being debated before approval, but there is a need to cover other areas such as the establishment of fees, for granting permits and licenses, penalties to impose when standards are violated and the mechanisms for negotiating petroleum agreements. The institution is very new and the rules that will allow the Petroleum Commission to deliver its mandate have yet to be written and approved.
With respect to the Local Content Legislative Instrument there is a welcome provision to establish a Local Content Committee, which allows for non-government members to be brought on to the Board. Currently there are two independent members out of seven, which should be beneficial in getting an industry perspective at a decision-making level.
Fiscal model
Ghana has opted for a hybrid system of production sharing and concessionary regime to govern contractual arrangements in the upstream petroleum industry. Non-tax revenues are covered in the PEP Bill, unless otherwise stated in the petroleum agreements and tax payments detailed in the PITL 1987 supplemented by the Inland Revenue Act 2000.
The PEP Law of 1984 includes loose provisions for the payments of rental payments, royalties, tax payments and state interest. In the absence of clear guidelines, the GNPC and the Minister of Energy negotiated many of the current terms in the petroleum agreements.
The proposed PEP Bill is more explicit in its treatment of fiscal provisions and additional payments have been added such as a bonus payments, additional oil entitlements and capital gains tax, yet the rate at which these must be levied is not stated and the opportunity to over-rule in petroleum agreements still open.
Petroleum revenues

Non-tax revenues:
- State Initial or Carried Interest, the State receives a 10% interest in each contract area
- State Additional Interest, following the discovery of commercial quantities the State is entitled to buy additional interest
- Royalty on Gross Production of Crude Oil, established in the PEP 84 Law, the rate is not fixed in law, rather agreed in petroleum agreements (varying from 5 to 12.5%)
- Additional Oil Entitlement, established in the PEP84 Law, requires additional payments to be made to the Government as the post-tax rate of return exceeds a certain level. The level if not fixed in the law but rather agreed in the petroleum agreements.
- Bonus, established in Draft PEP Bill
- Surface Rental, provided in the PEP 84 Law, specific rates are negotiated in petroleum agreements.

Tax revenues:
- Corporate Income Tax, 50% in PITL, 35% in model petroleum agreements
- Capital Gains Tax, included in IRA 2000 and draft PEP Bill
- Withholding Tax, IR Act 2000
- VAT, IR Act 2000, exemptions included in petroleum agreements
The PITL 1987 has provisions for corporate income tax and withholding tax on services delivered by subcontractors unless otherwise stated in the petroleum agreements. Tax liabilities for subcontractors are included in the Inland Revenue Act 2000, covering income tax, withholding tax and VAT. The prescriptions in the IR Act are very clear. In practice the rates levied have been lower than those originally stated in the law and in some cases exemptions have been permitted (VAT).
There are several weaknesses with the PITL that should be considered for repeal. These include an unlimited period for cost recovery against income tax payments, but more serious is the provision to waive withholding tax payments when the subcontractor is an affiliate. Failure to capture withholding tax on payments between affiliates facilitates the transfer of income from one sister company to another, encouraging tax evasion.
There are also weaknesses with the implementation of the fiscal model. There are no regulations guiding the negotiation of petroleum agreements and no formal mechanism to ensure fiscal priorities are conveyed. There are similarly no regulations to guide the treatment of tax laws (for example, cost recovery or transfer pricing). Similarly, there are no clear regulations to inform the tax authorities on penalties and procedures for tax evasion.
Revenue management
The Revenue Management Act 815 of 2011 provides a framework for the collection, allocation and management of petroleum revenue, including monitoring mechanisms. The Act is comprehensive in that it covers the allocations and disbursements of revenue between the petroleum funds. The Act provides for the establishment of an Investment Advisory Committee to manage the investment of heritage funds, as well as the Public Investment and Accountability Committee as an independent body to ensure accountability.
The weakness of the legislation lies in its implementation, as while provisions are made the exact nature of these are not detailed and discretion is left to the Minister. Financing for both the Investment Advisory Committee and Public Investment and Accountability Committee is not explicitly detailed. The Law articulates the need to invest petroleum funds in a Long-Term National Plan; however, in the absence of a plan the Minister has discretion to choose where to place funds. There is a need to clarify the implementation of the Act through regulations and institutional arrangements.

Annex III The Natural Resource Charter: an assessment of challenges facing Ghana
The Natural Resource Charter is a set of 12 principles, or ‘precepts’, intended to guide the exploitation of natural resources so that the economic opportunity offered by resource wealth leads to maximum and sustained benefits for citizens.
The precepts flagged here as presenting high governance risks in Ghana are:
- Precept 3: Fiscal policies and contractual terms;
- Precept 4: Award of contracts;
- Precept 5: Managing local impacts;
- Precept 6: National resource companies;
- Precept 8: Stabilising expenditure; and
- Precept 9: Efficiency and equity of public spending.
These six precepts are of central relevance to this study and can be thought of as the ‘weakest links’ in the value chain.
Precept 3: Fiscal policies and contractual terms
Fiscal policies and contractual terms should ensure that the country gets full benefit from the resource, subject to attracting the investment necessary to realise that benefit. The long-term nature of resource extraction requires policies and contracts that are robust to changing and uncertain circumstances.
Typically the main governance risk around fiscal and contractual terms is that exercised by individual (ministerial) discretion. Both of the relevant pieces of legislation – the Petroleum Exploration and Production Law 1986 (PEP 1986) and the proposed PEP Bill 2013 – are clear in the fiscal tools that are available to the Government to collect revenue from oil and gas-related activities. However, neither are explicit in the mechanisms for negotiating contractual terms. Both pieces of legislation leave a certain amount of freedom to the Minister of Energy through the regulatory body (previously the Ghana National Petroleum Corporation (GNPC) and now the Petroleum Commission) to negotiate specific terms in the petroleum agreements with contractors.
There are three obvious risks worth highlighting. The first is that ministerial discretion in approving the size of the state’s (carried) interest in a field and fiscal conditions (royalties, acreage fees, tax liabilities, etc.) requires a high degree of transparency to minimise the risk of corruption. The second is the capacity of state institutions to negotiate contractual terms with well-resourced and very experienced private sector counterparts. The third relates to the petroleum agreements currently in place and under negotiation that are being dealt with by GNPC, which faces a clear conflict of interest over representing the state’s interest and its own commercial gain as a partner in the joint venture.
Institutional strengthening for the Petroleum Commission as well as tighter guidelines through developing the regulatory framework could minimise these risks. The Government of Ghana does follow international best practice in that there is an established inter-agency negotiating committee that comprises the Ministry of Finance and Economic Planning (MOFEP), the Ghana Revenue Authority (GRA) and the Minister of Energy. However, the technical understanding of the oil and gas industry of these entities is limited and their influence weak.
Once licenses are issued, there are then concerns around revenue collection arising from the lack of technical knowledge on the part of the GRA, which is responsible for collection of revenues. The issues of concern include under-reporting of export volumes, admissible deductions and allowances, transfer pricing and treatment of local and foreign tax credits and debits.
Precept 4: Award of contracts
Competition in the award of contracts and development rights can be an effective mechanism to secure value and integrity.
Successful tenders for oil prospecting and mining licenses depend on the breadth, quality and access to geological information. Currently this information is housed with the GNPC with an expectation of a new national data repository being set up within the emerging Petroleum Commission. The challenges for a new institution will be to collect, manage and package this information so that it attracts investors, ensuring a thorough tender process and clear specification of the mutual rights and obligations of the Government.
There is an urgent need to provide additional support to build the technical expertise of the Petroleum Commission in preparation for the transfer of responsibility for negotiating contracts from the GNPC. The Petroleum Commission is a young institution, and has yet to develop its operating procedures and the technical expertise of existing staff, as well as fill many posts that remain vacant.
Once licenses and contracts are issued, inspecting performance and following up on compliance by operators with work programmes and expenditure commitments seems to be another potentially serious risk. If the regulator is not able to enforce relinquishment clauses, through following up implementation of the terms of the contracts without ‘fear or favour’, then there is a high risk of speculators coming in and ‘flipping’ contracts. This would deprive the Government of the true value of the field and thus tax revenues, as well as relinquish control to the license holder over oil field development.
In addition there are gaps in the regulatory landscape concerning midstream activities such as petrochemical plants using natural gas as feedstock or fuel. The Energy Commission is charged with regulating natural gas pipelines, associated with power generation, and the National Petroleum Authority is charged with mid- and downstream crude oil and oil products, but not natural gas and products. This will present challenges when production of natural gas commences in 2014.

Precept 5: Managing local impacts
Resource projects can have significant positive or negative local economic, environmental and social effects which should be identified, explored, accounted for, mitigated or compensated for at all stages of the project cycle. The decision to extract should be considered carefully.
The major and immediate governance risk associated with off-shore production of oil and gas is around environmental oversight. The disaster-preparedness of the Government is currently very low; it has limited experience in execution and supervision on the ground, poor work flow planning, and logistical constraints that are further complicated by overlapping jurisdictions of Government agencies, most notably the Environmental Protection Agency and Petroleum Commission.
Local communities are raising concerns that increased petroleum activities are having detrimental impacts on living standards by raising the cost of living but not delivering benefits through increased numbers of jobs or levels of public expenditure. There is evidence of pressure for the Government to consider options for allocating sub-national shares of the oil revenues.[19]
[19] During public consultations on the Revenue Management Act, chiefs of the Western Region made demands for the Government to allocate a percentage of the oil revenue to the area. The request was blocked by the NDC party currently in power.
Local content is an essential element of national policy to ensure additional jobs are created and spill-over effects are transmitted from the oil and gas sector to the rest of economy. Policy and Legislation must be designed with a clear understanding of the sector’s demand, existing national capacity, and requirements to develop indigenous capacity to meet the needs of industry. In the absence of appropriate legislation and the capacity to implement it, there is a risk that high expectations for job creation will not be met.
A Local Content Bill has been drafted however there are concerns that the Bill prescribes over-ambitious local content targets[20] for Industry without providing the necessary support to develop the skills and capacity to meet Industry needs. Beyond the Legislative framework, the Petroleum Commission will need to develop the capacity to implement and monitor local content policy. This requires the collaboration of many stakeholders, e.g., oil and gas companies, international service companies, SMEs, educational institutions, a technical appreciation of the procurement procedures of the oil companies and their major suppliers, and an understanding of the scale and pace of the industry’s development and linkages to other sectors of the economy. Currently the Petroleum Commission does not have this capacity.
[20] According to the Local Content Bill, companies will be required to source up to 90% of all staffing, goods and services nationally, within ten years of start-up.
Precept 6: National Resource Companies
Nationally owned resource companies should operate transparently with the objective of being commercially viable in a competitive environment.
The GNPC is the dominant public sector agency in the sector. It has the strongest capability, experience and resources. Even after the recent reform it continues to perform many of the key roles traditionally carried out by regulator. One vision for the sector includes a purely commercial function for the GNPC, setting it free from government interference, and subjecting it to commercial disciplines. Until this happens the potential for political meddling is high given their large budget and their interest in the petroleum agreements they are currently negotiating on behalf of the Government.
In the absence of a clear regulatory framework for the mid- and downstream natural gas segment of the sector, the Ghana National Gas Company (GNGC) has been leading the development of the natural gas sub-sector, much as GNPC did in the early days of oil production. The GNGC is thus acting as both an investor and a quasi-regulator in the mid- and downstream natural gas sector, by negotiating and contracting with investors.
Precept 8: Stabilising expenditure
Effective utilisation of resource revenues requires that domestic expenditure and investment be built up gradually and be smoothed to take account of revenue volatility.
Oil revenues for government can be volatile because of changes in price and production, this can present challenges to the management of a country’s budget. As a result, the government has set up a Stabilisation Fund to reduce the volatility of public expenditure and a Heritage Fund to increase savings from windfall gains through temporary high oil prices.
The Petroleum Revenue and Management Act (PRMA) provides a framework to determine the allocation of petroleum revenues between the annual budget and Stabilisation and Heritage Funds. However in practice these rules are easily flouted. This is either done directly by setting too high benchmark revenue estimates or indirectly by borrowing internationally against future revenue streams. This poses a major macroeconomic risk to the country that would seriously undermine any other efforts to reduce poverty through use of revenues.
The need for civil society to ensure accountability from the government is also recognised by the PRMA, which establishes the creation of the PIAC. Nevertheless, government commitment to this important accountability initiative is questionable, as it takes support from civil society and international NGOs to make it a reality and sustain it.
The Bank of Ghana (BOG) is responsible for managing the investments of the Heritage Fund. As the fund increases, clearer guidelines defining how funds can be invested will be required. The PRMA established an Investment Advisory Committee to provide oversight over Petroleum Fund Investment Policy; however, at present guidelines have been drafted but not yet approved.
If expenditure is not controlled and aligned to the domestic absorptive capacity of the economy then this is a major macroeconomic risk to Ghana. An appreciating real exchange rate that drives down the competitiveness of other sectors of the economy could be a very regressive factor for poverty reduction. Those most affected would be cash-crop farmers of cocoa, timber and possibly even the mining sector. Improved macroeconomic planning and reporting is necessary to control and mitigate these risks, as is increased policy dialogue between the relevant institutions (MOFEP and the BOG).
Precept 9: Efficiency and equity of public spending
Government should use resource wealth as an opportunity to increase the efficiency and equity of public spending and enable the private sector to respond to structural changes in the economy.
The quality of public spending in Ghana is very low. Because of high and inflexible recurrent expenditure commitments on salaries and wages there is very little room for capital expenditure to respond to structural changes in the economy. Often the budget is not implemented as intended, evidenced by the low execution rate of capital expenditure. As a result, budget execution fails on all three measures of sound public financial management: (1) low levels of fiscal discipline; (2) priority spending is not influenced by long-term development plans; and (3) weak operational effectiveness.

Annex IV Theory of Change
The proposed project assumes there is scope for governance, institutions and accountability in the sector to be further enhanced. Ghana has started to lay the foundations with sound energy sector policy and legislation but they need to be refined and implemented. Progress has stalled as a result of wavering political support, lack of focus, and reluctance on the part of the Ministry of Energy and GNPC to release control or to resource the newly established regulator (i.e. the Petroleum Commission). The strengthening of civil society, PIAC in particular, is an essential complement to such legislative and institutional strengthening.
Industry needs predictable and stable rules and regulations to ensure the viability of their current and future investments. Contrary to some popular myths, oil companies have an interest in promoting transparency and accountability in the regulation of the sector. A growing industry, acting as an investment jump-off point for West Africa, complements the public and local community desire to see more employment opportunities. The industry has untapped potential to exert pressure through establishing a Chamber of Commerce and using professional bodies to maintain momentum for seeing through the reforms.
Civil society from the beginning has had an active role and is directly influencing governance and public institutions by monitoring developments and lobbying for changes in the law. Equally, DFID will need to play a role in this push, exerting influence at a Presidential level to encourage the appointment of an experienced high calibre CEO at the Petroleum Commission and to hold the organisation and the Ministry of Energy accountable for the future development of the sector.
Strengthening oversight and enhancing regulation of the sector
The proposed project will aim to influence Government to promote a policy vision of better governance, institutions and accountability in the sector. It assumes that political interests will promote development objectives and that there is only a limited risk of overt rentier state political interference in the allocation of licenses or diversion of revenues.
The Ministry of Energy is critical to the change process but has allowed the reforms to stall. Bureaucratic vested interests in the status quo, a lack of leadership from the Minister, the limited capacity of the Petroleum Commission, and continued availability of GNPC advice are all factors that have led to the inertia in the reform programme. The Minister needs to separate fully the policy, regulatory and commercial functions currently shared by the Ministry of Energy, the Petroleum Commission and the GNPC. Equally, the Ministry of Energy has to provide strong leadership and a clear policy direction to steer all the Government stakeholders in the sector.
In principle, it should be in the interest of all stakeholders to clarify overlapping roles and strengthen institutional capacity. However, the Minister continues to rely heavily on GNPC advice as they have the most experience and knowledge of the sector and because the Petroleum Commission is not yet fully capable. The GNPC is undergoing its own reform agenda to try to develop into a commercial firm and achieve its goal of becoming a lead operator in the oil and gas sector. The GNPC should also desire a competent regulator. In addition, the GNGC has been recently set up to lead on the developments of a commercial gas market. They too require steering from the Minister and a clear policy direction.
The project assumes that the resistance to change in the Ministry of Energy can be overcome. There are three basic ways in which change can be brought about. The first is by building the technical capability of Petroleum Commission so that it becomes credible to the industry and GNPC, the second is increased demand for accountability from the President, and the third is through supporting civil accountability actors and monitoring bodies to sustain their demands on the Ministry of Energy for full implementation of the legislation.
Because of the highly political nature of the oil and gas sector, the institutional changes envisaged under the proposed project will need to be complemented by support to CSOs to help ensure they are better informed and sufficiently capable to be more proactive in lobbying for change, giving analysis and support to parliamentary committees and the media, and crucially by building the capacity of key public sector organisations.
Technical assistance to the public sector under the project will improve policy advice and help to resolve any ambiguities in the roles and responsibilities of the various organisations involved in the sector. Strategic advisers will be provided to the Minister of Energy and to MOFEP. A key part of the change process will be the removal of technical and operational barriers to improved performance in the Petroleum Commission. Arrangements for sustainable funding arrangements and staffing will be developed and implemented. There will also be a focus on improving technical operational aspects, helping secure a reliable funding source, providing training and professionalisation, as lobbied for by the industry.
Oversight and regulation also requires refinement to the existing laws to resolve any areas of ambiguity about the responsibilities and funding of the Petroleum Commission. There is also a need to introduce a series of regulations to allow new procedures to be implemented.
The project will actively build capacity for Parliament, civil society and the media to scrutinise the role and function of all public bodies involved in the sector, so as to further enhance accountability. It will also work with civil society and the industry to promote their engagement and advocacy in areas of public interest such as the development of local industry and employment.
Ensuring revenue capture
The optimisation of the fiscal regime and the collection of tax revenues in the sector depend on the collective effort of all the public sector bodies involved. These interests are not always aligned and collaboration is weak.
MOFEP has a clear interest in ensuring the fiscal policy framework is consistently applied in oil contracts and that the tax policy implications are fully understood. The GRA wants to accurately anticipate tax revenues and royalty payments and enhance the capacity to collect revenue.
However, internal government systems for sharing information are weak, while structures are run in parallel and do not promote collective action. The GRA does not have the capacity to assess and collect tax revenue effectively from the sector. The capacity to consider tax policy options (rates and coverage) also needs to be increased in MOFEP and the GRA. MOFEP and the GRA are represented in the negotiation of future petroleum agreements however they lack sufficient knowledge of the sector to help ensure the best deal for Ghana.
The project will focus on the entry points where there is government support for change. Both MOFEP and the GRA are change champions. Support will be provided to the GRA to build the revenue administration capacity of the Petroleum Unit in order to accurately assess and collect oil sector revenues. Advisory support to MOFEP will aim to influence MOFEP and GRA strategy and encourage more attention to tax policy issues so that this aspect can be addressed as well.
The transparency of the tax system and the integrity of revenue collection is a key concern for civil society. PIAC monitors the situation and the level of scrutiny will be maintained by capacity building and financial support under the project. It will encourage a more proactive engagement to follow up and address any specific weaknesses identified in the revenue capture arrangements.
Improving revenue management
Inevitably there is strong political pressure in election years and more generally with the perceived new oil wealth to finance politically important projects or to placate interest groups. The project assumes these interests can be kept in check. It is not inevitable that vested interests will override Government commitments to maintaining macroeconomic stability and the need for managing oil revenues sustainably, including with well-run Stabilisation and Heritage Funds (for future generations).
The project will enhance the technical capacity of MOFEP and the BOG to ensure that the institutional requirements, systems and procedures for sound revenue management are in place.
By building up this capacity the project will help to enhance the credibility of the small but growing technocratic group of competent officials in both organisations and encourage cooperation. The availability of accurate revenue information will also promote accountability within and outside the public sector.
As oil revenues increase there is a need for careful management of the macroeconomic consequences. These include the potential Dutch Disease effects on the economy and the risks of drawing too heavily on revenues in times of high oil prices to meet budget deficits that become ever unsustainable.
MOFEP has a strong interest in ensuring revenue forecasts are accurate and are effectively used by decision makers in the overall economic policy framework and annual budgeting process. The project will enhance MOFEP’s role and influence by providing a refined forecasting model, as well as expertise to advise on the macroeconomic aspects and to train technical staff. The project will also provide strategic advice and training to MOFEP to help ensure credible forecasts are incorporated effectively into the national budget. It will ensure senior officials and the Minister of Finance are properly briefed and aware of policy options so that national oil resources are more likely to generate development-related spending. The process of developing this capability will be joint with the GRA and BOG to ensure that all three institutions share the same analytical foundations for revenue forecasting as a necessary condition for improved institutional coordination.
The BOG has responsibility for managing both the oil trust funds and for general Treasury management. MOFEP and the BOG’s main interest is to ensure the effective management of the trust funds in line with legal requirements governing their use. The project will provide software, equipment and training to the BOG in order to enhance its oversight of oil revenue flows and the control of the oil trust funds.
Fortunately, public interest in the management of oil revenues is high, even if not always fully informed; in principle, this places the Government under pressure to explain and justify their allocations of oil revenues to current spending and any withdrawal from the trust funds. The project will support, enhance and sustain public pressure through sector-specific targeted analysis and research, ensuring that accountability actors have the information and capabilities to maintain scrutiny and that, at the same time, Government performance is explained and justified to the public. In addition, the project will build research capability in the Secretariat of the Public Accounts Committee and sponsor specific targeted analysis by PIAC and think tanks.

Annex V Project descriptions by Institution
Project name: / Institutional and human resource development of the Petroleum Commission
Project leader: Petroleum Commission
Project summary: / The project is designed to support the Petroleum Commission develop the capacity to undertake all the functions envisaged by the Minister of Energy as set out in the Petroleum Commission Act. / Strategic planning, delivering results and funding options / A short- or long-term adviser could be provided to advise the CEO and the senior management team in these and other areas related to the implementation of the Petroleum Commission Corporate Plan and the delivery of core regulatory and industry monitoring functions. / In addition, a fund for flexible short-term consultancies related to specific issues could also be considered, for example to support senior management work in key areas. / Examples of areas of support could include: / Introduction of management by objectives with defined performance targets for the Petroleum Commission as a whole and for each division; / Production of a business plan and performance management system that would deliver the corporate objectives of the Petroleum Commission; / Preparation of a Petroleum Commission financial forecasting and budgeting system incorporating all the requirements of the business plan and showing any funding gaps that could be met by aid; and / Development and implementation of a policy to ensure financial stability, including arrangements for charging and funding from the industry. / Human resource development, organisational development and training / The review team proposes that DFID finances short- and longer-term practical training and that a plan for this be developed in conjunction with the Petroleum Commission senior management team. / Also, that a flexible fund be provided to meet the short-term expertise requirements for special human resource studies and possibly also to meet the costs of an adviser to the Director of HR & Training / The Director of Finance and the Training Officer identified this area as the priority for DFID support. Training was requested to develop staff capability to undertake key functions, including regulation of the industry, revenue management and policy coordination. The priority is practical training as most staff are well qualified academically (i.e. to postgraduate level). / Human resource development is crucial for the Petroleum Commission and it is noted that the World Bank and Norway are also assisting with training. Training should be undertaken on the basis of a systematic training needs analysis reflecting the requirements in each division. This should involve on-the-job and informal mentoring as well as formal courses and attachments. / The review team propose that DFID assists the Petroleum Commission in undertaking a training needs analysis and then links this to a training programme to ensure that a pool of staff can be developed with the required technical and managerial skills. / A human resource development strategy is also needed to develop recruitment and promotion procedures and policy that reflects the labour market situation. Comparator pay surveys could be useful, as would work on pay and grading. / The review team further proposes that DFID offer assistance to support: / Finalisation of the functions, organisation structures and job descriptions for all key posts; / Prepare induction and guidance manuals for staff; and / Special studies, e.g. to identify skills shortages in the industry and strategies to retain staff. / Technical and operational areas / The review team proposes that DFID provides long-term and short-term technical experts either as advisers to existing senior Petroleum Commission staff already in post or to fill vacant line positions until a qualified Ghanaian national is available. / There are considerable gaps in technical expertise within the Petroleum Commission and some further diagnostic work is required to specify the needs more precisely and to prepare job descriptions and terms of reference. A short consultancy should be undertaken urgently so that the Petroleum Commission can agree with DFID a list of technical and operational expertise required to cover the gaps that have been identified. / Upon the agreement of specific areas and terms of reference, DFID could then provide a flexible fund to facilitate recruitment of the required experts for the period of time required. / Based on discussions with the senior management team and GNPC, the following should be considered: / Expert adviser to work with the Directors of Resource Management, Operations and Special Services; / Support to prepare regulations, operating procedures and to provide hands-on mentoring and training in their use for Petroleum Commission staff; / Specialist expertise in some or all of the following areas: / Development and production stage of oil and gas operations / Reservoir engineering skills and modelling / Pre-production costing / FPSO costing / Skills and expertise linked to the Local Content Policy in: / Procurement and tender processing / Logistics management / Tender evaluation / Software to manage the bidding process. / Systems support / The PC has expressed a desire to introduce and IT system to manage bidding and contract award processes. The system would have an interface with the GNPC, Operators and Contractors, and would automate certain processes reducing opportunities for interaction with PC staff and as such misconduct. / There are also discussions of introducing an IT system to facilitate monitoring of oil and gas operations in real time. The PC has indicated the Brazilian National Petroleum Regulator has expressed and willingness to develop capacity and provide software on a commercial basis. / A third requirement is support to manage the data repository which is currently being managed by the GNPC.

Project name: / Oil and gas policy
Project leader: Ministry of Energy
Project summary: / The Ministry of Energy is responsible for policy and overall oversight of energy and petroleum policy in Ghana. The recent discovery of oil and gas presents immense opportunities, which if managed well will provide an important contribution to the state’s annual budget, and economic growth by catalysing the nation’s industrial potential. / DFID proposes to fund an experienced oil and gas and petroleum policy adviser to the Ministry with a view to provide policy and operations advice in the following areas: / Clarify policy and strengthen management of the oil and gas sector / The rapid development of the oil and gas sector from exploration to production has required the establishment of the Petroleum Commission as the regulator for upstream petroleum activities. The legislative framework is currently being reviewed to account for developments in the sector with the draft E&P Bill 2013, and Local Content Legislative Instrument awaiting approval in Parliament. There are, however, many challenges with the implementation of the law, which include: / Fostering the development of a strong Petroleum Commission; / Enabling a transfer of power from the GNPC to the Petroleum Commission; / Clarifying the roles of and coordinating all state actors involved in the sector; / Developing subsidiary regulations/legislative instruments for the E&P and Local Content legislation; and / Identifying and filling gaps in existing and proposed legislation, such as may affect the development and management of the natural gas sector. / Lead commercialisation of gas sector / The Jubilee field is currently producing natural gas, which will soon be commercialised, the field operated by ENI is awaiting approval, and other fields will soon join that queue. GNGC has been set up as the national gas company in charge of commercialisation of gas in the national and international market. Plans are currently underway to complete a pipeline from the Jubilee field, and building of an LPG plant to process the natural gas. The Ministry needs to provide strong policy oversight and in particular: / Lead policy on factors affecting the development of natural gas, such as gas pricing, infrastructure development and management, reserves to production levels and natural gas usage with GNGC and other actors; / Clarify regulatory roles in relation to gas of the Energy Commission, the National Petroleum Agency and the Petroleum Commission; / Clarify operational roles and collaboration approach in relation to GNGC, GNPC, and other state companies; and / Lead decisions regarding investment in processing plants and by-products. / Provide technical support to the Ministry for its day-to-day activities / With the shortage of experienced technical and commercial capability in the Ministry of Energy, the Minister faces significant challenges in conducting his role in areas such as: / Approving licenses, plans of development and other permits, as required for petroleum operations; / Developing the capabilities of the Ministry for efficient operations and reporting; and / Training, developing, mentoring and retaining new staff at all levels. / To cover these issues, DFID proposes to fund a specialised Petroleum Adviser to the Minister of Energy, who can inform decision making, capacity development and support coordination of the interests and performance of the various state institutions in the sector.

Project name: / Institutional strengthening of petroleum tax policy and administration
Project leader: / MOFEP – Real Sector Division
Project summary: / The management and collection of upstream petroleum revenues and their volatility present major challenges to the MOFEP, as do other oil sector management issues such as determination and financing of the Government’s equity oil and gas through the GNPC. / These terms of reference provide for technical support to MOFEP to strengthen directly the Oil and Gas Unit of the Real Sector Division (of MOFEP). As a corollary, the macroeconomic management function of the Budget Division of MOFEP and the tax administration and collection functions of the GRA will also be strengthened. / The goal of the Oil and Gas Unit will be to ensure that MOFEP receives timely technical and operational advice to improve management of the sector and enable more revenues to be captured by the Government. Technical support will focus on building capabilities in the following areas: / Upstream forecasting model – to forecast short-, medium- and long-term oil revenues on the basis of the current fiscal and regulatory regime, based on adaptation of the current model and real-time access to financial and operational data on a producing-field-based approach; to be developed jointly between MOFEP, GRA and BOG. / Supporting the tax administration and audit function of the GRA – to contribute to fiscal policy design, support the GRA’s audit functions, and help minimise tax leakage; and / Special projects. Capacity to respond quickly to a wide range of unexpected sector issues, such as public investments in the sector, in collaboration with other public agencies involved in sector fiscal and financial matters. For example, this might include reviewing the pricing formula to interrogate and contribute to discussions on the methodology and calculation of the official selling price. Includes a communication role to ensure support for macroeconomic stability.

Project name: / Strengthen oil and gas revenue collection
Project leader: / GRA
Project summary: / The GRA is responsible for the collection and assessment of tax revenues from petroleum-related activities. This includes corporate income tax, capital gains tax and withholding tax on subcontractors as provided in the PITL 1987, as well as other tax liabilities covered in the Inland Revenue Act 2000 including VAT for subcontractors, unless otherwise specified in the petroleum agreements between the Government and contractors. / In practice, the flexibility to negotiate tax obligations through petroleum agreements has in some cases led to confusion regarding tax liabilities. In addition, a lack of technical knowledge of the oil and gas business on the part of GRA staff suggests the GRA may not be achieving full compliance from the relevant taxpayers. / The aim of this programme is to equip the GRA and other relevant ministries (i.e. MOFEP and the Ministry of Energy) with the technical expertise to develop a clear and predictable fiscal regime for future contracts, provide accurate forecasts of tax revenue and ensure full compliance from tax payers with their tax obligations. / Development of a model for Ghana’s fiscal regime for the upstream petroleum sector (review of legislative framework). Identify areas of potential dispute between legislation (namely PITL 1987, Inland Revenue Act 2000 and discretion exercised in petroleum agreements (e.g. corporate income tax rates for contractors, provisions for capital gains tax, withholding tax for subcontractors, and VAT exemptions)); and provide clarification through practice notes or private rulings issued by the Commissioner or regulations issued by the Minister of Finance. / Upstream forecasting model – to forecast short-, medium- and long-term oil revenues on the basis of the current fiscal and regulatory regime, based on adaptation of the current model and real-time access to financial and operational data on a producing-field-based approach – developed jointly with MOFEP and BOG; / Capacity building for staff / Introduction to upstream petroleum operations – covering the technical characteristics of E&P activities, industry cost structures and accounting, and commercialisation and marketing of petroleum-related activities. / Fiscal metering, for Customs in collaboration with the Petroleum Commission. / Audit techniques and audit plans and manuals, developing in-house skills to identify areas for audit and establishing procedures for outsourcing audit activity if necessary.

Project name: / Capacity building for Petroleum Fund Management
Project leader: / BOG – Petroleum Unit in coordination with MOFEP and Investment Advisory Committee
Project summary: / The BOG is responsible for the management of Ghana’s petroleum funds. The petroleum funds consists of two funds: the Stabilisation Fund intended for smooth public expenditure in periods of revenue shortfall; and the Heritage Fund for investment in fixed securities to generate income for future generations. / The Revenue Management Act 2011 details precisely how petroleum revenue is defined and allocated between the various funds. However, in practice challenges involved in implementation of the Act have led to misallocation of funds and lower levels of funding for petroleum funds. In addition, a lack of clear guidelines and skills capacity for investment of the Heritage Fund will lead to risk of lower-than-expected returns on investments as the size of the fund increases. / The aim of the project will be to ensure that the BOG’s Petroleum Unit have the necessary skills to influence the allocation of petroleum revenue between funds, and maximise returns on investments made in the Heritage Fund for future generations. Technical support will focus on developing the following areas: / Capacity building for Petroleum Unit Secretariat / Investment guidelines from Investment Advisory Commission; / Manual and training on cross-currency trading; and / Training to oversee outsourcing of investment funds. / Systems support / Needs assessment for additional terminals/new system. The Petroleum Unit currently uses Bloomberg, but as the level of funds increases a larger system may be required; / Needs assessment for Portfolio Management System that provides market information; and / Automated trading. / Upstream forecasting model – to forecast short-, medium- and long-term oil revenues on the basis of the current fiscal and regulatory regime, based on adaptation of the current model and real-time access to financial and operational data on a producing-field-based approach – to be developed jointly with MOFEP and GRA; / Special projects. Capacity to respond quickly to a wide range of unexpected sector issues, such as scrutiny of MOFEP’s fiscal discipline, exchange rate trends, etc.

Annex VI Terms of Reference for ‘First movers’
The following TORs were discussed with senior staff at the Ministry of Energy.
Terms of Reference – Special Petroleum Adviser to the Minister of Energy
Background
The Ministry of Energy is responsible for policy and oversight of energy and petroleum and Ghana. The recent discovery of oil and gas presents immense opportunities, which if managed well will provide an important contribution to the State’s annual budget, poverty reduction, economic growth and industrialisation.
Prior to these discoveries, the Ministry’s role of upstream regulator was delegated to the GNPC. This role is in the process of being transferred to the newly formed Petroleum Commission. The Minister of Energy will still be responsible for very important technical decisions in the upstream (such as licensing and approval of plans for development) and mid- and downstream.
Because of the need for collaboration across agencies, an understanding of the technical factors in upstream, midstream and downstream, an understanding of the policy, commercial and technical relationships between the linked activities and actors and the power structure and relationships in Ghana, the Ministry is best placed to provide leadership of the sector. According to the CEO of the successful downstream regulator, the National Petroleum Authority (NPA) the Ministry needs very strong technical expertise to interact with, support and manage the regulators.
The Ministry will be the agency coordinating:
- The petroleum regulators - Petroleum Commission (upstream), Energy Commission (midstream and natural gas) and NPA (downstream and marketing) by aligning their strategies and coordinating their work in areas, such as mid and downstream natural gas processing and manufacturing, where there is lack of clarity as to the roles of the regulators and potential for overlap;
- GNPC and the PC in transferring capacity and responsibilities in regulating the upstream;
- The State companies, GNPC and GNGC in managing the overlap and potential "turf wars" that might evolve;
- The government’s limited human capacity that is spread thin across the upstream sector, some within each of the MoEn, GNPC, GNGC and PC;
- The linkages and value trade-offs that will be required between the up-, mid- and downstream segments; and
- The information flow and linkages to other parts of government and the economy.
Objectives
As the Ministry seeks to develop the requisite capacity, the industry is rapidly growing and evolving. In the interim, Ghana’s regulators and policy makers must continue to make decisions and act in ways that will allow the industry to operate efficiently, while securing Ghana’s short, medium and long term benefits.
To fill the short-term gap, an adviser to the Minister will provide immediate support for the policy making, technical know-how and organisational development that are currently needed.
Duties and Responsibilities
The tasks and activities that the adviser will be expected to conduct include:
- Providing guidance and support in clarifying policy and strengthening management of Ghana’s oil and gas sector;
- Providing support to those framing the evolving legislative framework, such as the draft E&P Bill 2013 and subsequent Regulations (L.I.s) and Regulations pursuant to the Petroleum Commission Act 2011, such as the Local Content L.I. 2013;
- Helping to identify gaps in existing and proposed policy and legislation, such as may affect the development and management of the natural gas sector;
- Supporting the transfer of responsibilities from GNPC to Petroleum Commission;
- Providing guidance in clarifying the roles of and coordinating all State actors involved in sector;
Providing support to the commercialisation of natural gas, by helping the Ministry to:
- Provide strong policy oversight of natural gas;
- clarify regulatory roles in relation to gas of EC, NPA, and PC;
- clarify operational roles and collaboration between GNGC, GNPC, VRA and other State companies; and
- lead decisions regarding investment in processing plants and by products.
Providing technical support to the Ministry for its day to day activities, in areas such as:
- approving Licenses, Plans of Development and other permits, as required for petroleum operations;
- developing the operational procedures of the Ministry for efficient operations and reporting;
- training, developing, mentoring and retaining staff at all levels;
- local content and participation policy implementation across the sector; and
- coordinating limited human resources and information use and collaboration, so that Ghana can get the most out of its limited capacity.
Knowledge, Skills and Competencies
The adviser to the Minister should be able to bring a breadth and depth of experience in policy, strategy, regulatory, leadership, operational (oil and natural gas: upstream (exploration, development and production), midstream and downstream), commercial (tax, financial, negotiating, business analysis), organisational development, coaching, mentoring and advocacy.
While it may not be likely to attract an individual with specialty in all these facets of the sector, an suitable adviser will be very experienced in several of these, particularly policy and strategy in a regulatory setting, underpinned by a strong technical base and with a working knowledge of the other areas.
Qualifications and Industry Experience
A combination of training and experience, as follows:
- Qualifications – Degree in an oil and gas technical or commercial discipline (Finance, Law, Engineering, geology/geophysics), preferably at a Masters level;
- At least 10 years experience working as a regulator in a developing country’s petroleum sector;
- At least 5 years of significant high level executive or leadership roles in the petroleum sector, in a regulatory or operational entity;
- Experience in various parts of the petroleum value chain (exploration, development, production, oil, natural gas);
- Experience in crafting and implementing policy;
- Experience in strategy development and implementation.
- Understanding and experience in petroleum law and contracts;
- Understanding and experience in negotiations;
- Experience in Organisational Development, coaching and mentoring; and
- Experience in local content and supplier capacity development.
Outputs
- Legislation and requisite regulations identified for upstream
- Policy, legislative and regulatory gaps and/or overlaps and actions to remove them identified
- Clear policies and roles of regulators and State companies across the value chain
- Ministry of Energy ‘s Organisational Development Framework developed and implementation started
- Ministry’s operational and reporting procedure framework developed and implementation started
- Administrative transfer of regulatory control from GNPC to Petroleum Commission
- Clear natural gas development policies and strategies
- Consistent and transparent procedures for field development approvals
- Transparent licensing procedures
- Clear collaboration and information sharing protocols across the sector agency and other governmental and civil society actors
- Local content and participation policy being implemented.
Timeline
Duration - 2 years
Start date – As soon as possible
Reporting
Reports to Chief Director but works directly to the Minister as required.
Annex VII Stakeholders interests and incentives in supporting a reform programme in the oil and gas sector
Responsible Institutions/Stakeholders	Interests	Incentives	Traffic light (Red for a ‘spoiler’, Amber for ambivalent, and Green for a supporter of reform)
Presidency	Leave a legacy; control competing forces within party and government; shepherd Ghana onto the ‘oil and gas’ world stage; show that it is not inevitable that Ghana will go the way of other resource-curse afflicted countries;	Positive incentives: Win the next election by showing can drive reform; control patronage and largesse; / Negative incentives: Consolidation of political support is the priority and challenging established or vested interests may alienate supporters.
Ministry of Finance and Economic Planning (MOFEP)	More influence over fiscal terms within Petroleum Agreements; increase revenues to government; ensure greater macroeconomic stability; reduce off-budget expenditure; increase trust in government;	Positive Incentives: Increase position of MOFEP vis-à-vis other agencies; capture more revenues for government;
Ghana Revenue Authority	Increase revenue capture;	Positive incentives: Able to retain 3% of all revenues to cover operational costs; maintain independence from politics;
Bank of Ghana	Oversight of Heritage Fund and Stabilisation Fund.	Positive incentives: Maintain independence from politics and technical status; demonstrate technical capability and join club of wealthy countries with successful sovereign wealth funds;
Ministry of Energy	Increase internal knowledge of sector so as to become oil and gas sector policy making body of government; professionalise new service; see through separation of policy, regulatory and commercial functions;	Positive incentives: Easier to manage competing parts of sector if more clearly devolved roles and responsibilities’; / Negative incentives: Minister may prefer to maintain the status quo and reinforce MOE authority and control rather than relinquishing to the PC. Taking on interests and promoting change may also be politically risky.
Ghana National Petroleum Company (GNPC)	Develop into an international successful Oil and Gas company with ambitions to explore and operate own fields. Requires a strong regulator in Ghana to protect its interests as a equity shareholder.	Positive incentives: Some commercial interests or GNPC managers may resist full transfer of responsibilities to PC and prefer to retain regulatory control.
GNGC	Manage development of master Gas Plan including new infrastructure and pipelines. / Tighten control of gas market; get the best price for gas;	Become a credible private enterprise in gas market
Petroleum Commission	Wrestle regulatory control from GNPC – most notably over negotiating Petroleum Agreements; secure budget for operations; gain office space; recruit professional staff on competitive wages; seek transfer of best staff that had regulatory role under Ministry of Energy and GNPC;	Become a professional regulatory agency independent from government interference; show leadership in the local content debate;
National Petroleum Authority (downstream sector regulator)	Continue to manage downstream operations in an effective manner. Continue to report to Ministry of Energy but with autonomy in part achieved through self-financing	Continue to carry out function and stay away from stepping on others ‘turf’
Energy Commission	Continue to manage midstream operations in an effective manner. Continue to report to Ministry of Energy but with autonomy in part achieved through self-financing	Continue to carry out function and stay away from stepping on others ‘turf’ Expand control of midstream gas subsector
Environmental Protection Authority	Assess and manage environmental impact assessments, and monitor operations to ensure environmental impacts are avoided.	To raise influence over sector decisions and raise funds from issue of permits
Parliamentary Petroleum Committee	Increase influence over Petroleum Agreements.
Parliamentary Accounts Committee	Increase oversight and control of spending agencies (GNPC);
Investors & Contractors	Greater clarity of roles and responsibilities within government agencies; certainty over contracts; minimal interference; recognition for important and positive contribution industry makes to revenues; increase exploration and production in Ghana	Massive financial and reputational risks to manage and mitigate;
PIAC, Civil Society, Media	Greater transparency in the sector; recognition that accountability actors have an important ‘voice’;	Reassure constituencies that they are relevant and making a difference to their cause or interests; Sustained funding through National Budget for PIAC
Donors and diplomatic community	Leave a legacy as donors financial role in direct budget support decrease; represent strategic and commercial interests of country; reduce potential for violent conflict; retain relevance to government of Ghana in time of falling aid budgets and increasing internally generated revenues within Ghana;	See their influence maintained despite Ghana graduating to a middle-income country;
International community (INGOs; Media)	Transferring ‘lessons learnt’ from other countries;

Annex XIII CLIMATE AND ENVIRONMENT ASSESSMENT

Ghana’s growth has historically been driven by natural resources and fluctuating commodity prices. The economy is at a transition, particularly with the stimulus of the oil and gas find in the Western Region. This is reflected in the emphasis on extractive industries, infrastructure, transport, and agricultural modernisation in the Ghana Shared Growth and Development Agenda. The incoming NDC Government Manifesto in 2012 has a further focus on economic diversification, private sector, enterprise and jobs, manufacturing and exploitation of district resource endowments.
Ghana now has unprecedented economic opportunities. However, patterns of high economic growth have contributed to unplanned urbanisation, ad hoc land use[21], and heavy natural resource and environmental degradation (rural and urban). This occurs in a context of stretched management and governance systems, and weak planning and regulatory compliance. Hence, Ghana now faces new challenges in driving growth whilst reducing resource pressures and managing the emergent risks of climate variability and change as the country becomes a net greenhouse gas emitter[22]. Ghana has comprehensive legislation and regulations on environmental protection and supporting institutional frameworks focused on the mining industry. Despite this, acute and chronic mining-related pollution has occurred in both aquatic and terrestrial ecosystems[23] and the goods and bads of investments and impacts have not been equitably allocated.
[21] In the Western Region, onshore development has serious implications for, e.g. implications for Cape Three Points, a globally significant biodiversity area and the last fragment of coastal forest in Ghana (indeed among last for West Africa); Ankasa, one of few remaining Pleistocene refuges around Gulf of Guinea, ranking alongside patches in Cote d’Ivoire and Mount Cameroon in terms of global biodiversity significance and “genetic heat index”; and Important Bird Areas (hotspots identified by BirdLife International and Ghana Wildlife Society) along coast and in adjacent forest patches or wetlands (Amansuri further along coast) are also at additional risk due to these pressures
[22] EPA (2011) National Greenhouse Gas Inventory Report for 1990-2006. Vol 1. Synthesis report. unfccc.int/resource/docs/natc/nir_1990-2006.pdf‎
[23] See, e.g., the documentation of reduced agricultural productivity by some 40% due to the expansion of mining production, with evidence of greater air pollution and increased rural poverty near mining areas in Aragon, FM & Rud, JP (2013) Modern industries, pollution and agricultural productivity: Evidence from Ghana. Working Paper. International Growth Centre
Government of Ghana, with its partners is now responsible for overseeing an industry with potentially significant impacts on workers, the environment, and large areas of ocean and shore. In this context, even small probability adverse events can have significant and far-reaching effects, including major financial liabilities[24]. These can extend beyond national boundaries, with multinational operations in one country being jeopardised by its liabilities in another country’s fields. Recent US experience points to regulatory inability to complete necessary reviews, including environmental and oil and gas production verification inspections, with an ill-defined process for defining a significant environmental impact.[25] This resonates with Ghana, where a relatively minor spill resulted in a punitive - and contested - penalty being imposed on Kosmos Energy, in the absence of a supporting legal framework.
[24] US General Accountability Office (2007) MARINE TRANSPORTATION: Major Oil Spills Occur Infrequently, but Risks to the federal Oil Spill Fund Remain. GAO-07-1085
[25] US Government Accountability Office (2010) OIL AND GAS MANAGEMENT: Key Elements to Consider for Providing Assurance of Effective Independent Oversight. GAO-10-852T
Institutional responsibilities, structures, procedures and provisions on oil and gas are still emerging in Ghana, with a lack of clarity on oversight.  Unless further highlighted, current procedures present a risk that little follow-on action is taken on securing and acting on environmental management and regulation in a coherent practice.  Given the overlaps and similarities with, and the experience of, development of oil and gas resources elsewhere in Africa, fragmented support can pay inadequate attention to environmental and social measures and resourcing.[26]   This presents further risks for potential investors.
[26] See, e.g., COWI/Uganda NEMA (2012) A capacity needs assessment for the environmental pillar institutions in Uganda. Final Report and NORAD (2013) Facing the Resource Curse: Norway’s Oil for Development Program. Final Report.
A complex legal framework is required to be in place for oil spill liability and response funding and to determine who is responsible and will ultimately pay the costs associated with any spill. Ghana has made good advances with many elements such as its oil spill contingency planning, sector environmental guidelines, elements of Strategic Environmental Assessment and its AKOBEN industry performance rating system. However, there are still likely to be unforeseen loopholes, drawing on areas in which Ghana has had little experience or capacity to date[27],[28].
[27] See, e.g. Achaw, O-W & Boateng, ED (2012) Safety practices in the oil and gas industries in Ghana. International Journal of Development and Sustainability 1(2): 456-465. Sakyi, PA et al. (2012) Ghana’s Quest for Oil and Gas: Ecological Risks and Management Frameworks.
[28] In Uganda, local hazardous waste management has been criticised, where companies stockpiled waste in the absence of any longer-term arrangements. That in turn was deducted as costs of oil production, reducing the taxable income streams and revenue base. GoU has made “significant efforts to put in place fairly elaborate policy, legal and institutional mechanisms to address the environment[al] challenges of the gas and oil sector, the lack of capacity to implement these policies and enforce the corresponding laws has grossly undermined their effectiveness.” NORAD (2013) Facing the Resource Curse: Norway’s Oil for Development Program. Final Report.
The following were identified as key to ensuring adequate and independent regulation in the US oil and gas fields:
- Technical expertise: The organisation should have sufficient staff with the expertise to perform sound assessments.
- Ability to perform reviews and require that findings be addressed: The organisation should have the working knowledge necessary to review compliance with requirements, developed through periodic reviews, and should also have sufficient authority to require compliance with its findings and recommendations.
- Enforcement authority: The organisation should have sufficient authority to achieve compliance with requirements.
- Public access: The organisation should provide public access to its reports so that those most affected by operations can get information.
- Independence: The organisation conducting oversight should be structurally distinct and separate from the entities it oversees.
Ghana has experience on mining industry bonds and remediation. However, the nature and extent of the oil and gas finds present may constitute additional financial and fiscal liabilities. As an example, the USA’s 1990 Oil Pollution Act, enacted after the 1989 Exxon Valdez spill, authorized an Oil Spill Liability Trust Fund using the polluter pays principle. This was intended to pay for certain oil spill clean-up costs and damages using a light tax on oil and gas revenue production and imports for immediate response costs and when the responsible parties cannot be identified or do not cover clean-up costs. Federal government may also seek reimbursement for these costs from the responsible parties[29].
[29] US General Accountability Office (2010) DEEPWATER HORIZON OIL SPILL: Actions Needed to Reduce Evolving but Uncertain Federal Financial Risks. GAO-12-86
However, the experience of the Deepwater Horizon spill in 2010 has necessitated a major review of these arrangements[30]. This has required exploration of the drivers behind oil spill costs (such as toxicity and persistence of the type of oil, time of year relative to fishing or tourism seasons, location and accessibility of the spill, proximity to and disruption of economic centres, and effectiveness of the spill response. Institutional lapses meant that the revenues to form the Spill Liability Fund were not collected adequately. Overall, revenue management and capture has been classed as weak[31], with confusion in oversight over infrastructure and metering, high turnover of regulatory and monitoring staff (often into the industry), and instances of inappropriate contact between industry and regulatory staff[32]. Periodic dating is needed in penalty, insurance and remedial bond schedules, to allow for inflation, market factors, and changing technology and load factors. Damages from the Deepwater Horizon spill to date have been far in excess of the cap set on individual spills under the Liability Fund, and have overwhelmed the additional dedicated Trust Fund established by BP, requiring a further, ongoing, judicial review in September 2013.
[30] US General Accountability Office (2010) OIL SPILLS. Cost of Major Spills May Impact Liability of Oil Spill Liability Trust Fund. GAO-10-795T
[31] US General Accountability Office (2013) OIL AND GAS MANAGEMENT. Continued Attention to Interior’s Revenue Collection and Human Capital Challenges is Needed. GAO-13-647T
[32] US General Accountability Office (2008) OIL AND GAS ROYALTIES: The Federal System for Collecting Oil and Gas Revenues Needs Comprehensive Reassessment. GAO-08-691
A degree of flexibility is required for climate and environmental inputs in this support programme. This can draw on existing lessons and outputs on natural resources and environmental governance (NREG) in Ghana, particularly from the mining sector, mining revenue audits and projections, and experience of Strategic Environmental Assessment and environmental regulation. In line with the DFID Future Fit agenda, positive recognition of opportunities is suggested as part of dialogue. It is recommended that the programme pro-actively encourages and supports robust environment policies and regulation to ensure risks are addressed (beyond this support and DFID alone) and that implications for revenues and for institutional mandates, responsibilities and capacities in this Business Case are taken into account. At a minimum, the programme should ensure a do-no-harm approach, including ensuring attention to health and safety and financial dimensions of environmental liabilities, and helping to compile an overview of environmental procedures, standards and contact points. This will help to deliver a clear institutional and regulatory set-up with designated mandates, tasks and resourcing that has been important to the development of oil and gas and geothermal energy[33] in other countries. By clarifying responsibilities, procedures and potential liabilities, it will reduce investor and operator risk and promote implementation of a stable and predictable regulatory framework. This will also assist in terms of civil society and Parliamentary oversight and accountability.
[33] Sander, M (2012) Lessons learnt from geothermal-friendly regulatory frameworks in Iceland, Kenya, New Zealand, Philippines and the United States of America. Geothermal Resources Council Transactions at https://pangea.stanford.edu/ERE/db/IGAstandard/record_detail.php?id=14115
In line with the outputs, the following measures are recommended:
Output 1 Sector oversight enhanced and effective regulation.
- Fully independent and resourced Petroleum Commission effectively carrying out statutory duties. (Clarify responsibilities/duties on environment or implications, especially with Environment Protection Agency, Ministry of Environment, Science and Technology, Ghana Maritime Authority, Energy Commission, Petroleum Commission and GNPC)
- Sector policy and strategy for development of sector with stronger leadership, inclusive processes and implementation plan (clarify responsibilities/duties on environment or implications; measures to review and strengthen consideration of relevant environmental provisions and capacities and their practical application in Ghana, e.g. include reviews and compilations of resource material for developers, Parliament and civil society on national – and international, where relevant - institutions, capacities, policies, procedures and standards)
- Strengthened capacity of Parliament, CSOs, media, so they can monitor developments, ensure public accountability and increase exposure of mismanagement or corruption. (i.e. an informed accountability group on the relevance of environment to sectoral regulation, oversight and liabilities)

Output 2 Ensuring revenue capture
- Greater tax compliance (number of audits resulting in additional revenue collected) (lessons and practice from gold audits; relevance of environmental charges to declared oil costs and tax liabilities; lessons of US experience of Deepwater Horizon spill and environmental liability trust fund)
- Ghana Revenue Authority Petroleum Unit more effectively engaging with industry (synthesis of lessons from UK North Sea regulation and industry liaison approaches could be fed in by BERR and others, including info flow on these environmental and liabilities/implications for revenues and costs for Ghana – noting that this will be a small percentage of any information flow; clarify any gaps in individual Petroleum Agreements; check for any contradictions in production sharing agreements with environmental requirements; link to previous revenue projection work from mining and forestry; potential impact on revenue streams by environmental remedial bonds, insurance cover and inflated operator costs if environmental provisions are not in place; adequacy of capacity and processes by Petroleum Unit in Large Taxpayers Unit to ensure correct royalties for each uplifting, including provision for any gas venting or flaring)

Output 3 Improving Revenue Management
- Greater fiscal oversight of oil and gas sector by MoFEP (building on NREG lessons with MoFEP, i.e that sectoral engagement and understanding improved the basis for sectoral budgeting and understanding of revenue base; include environmental links from outputs 1&2 into any annual report on industry)
- Revenue modelling capacity of Real Sector Division of MOFEP enhanced (again, build on NREG experience with the mining and forestry sectors)
- Commission short brief to synthesise lessons and experiences relevant to Bank of Ghana that could feature lightly in its annual reports on the industry.

The likely climate change and environmental risks and opportunities of the different options all depend on the extent to which environmental capacities and measures are further addressed through other programmes, beyond DFID alone. The risks to the preferred option on institutional accountability and public accountability are categorised as C (low potential impact), the potential opportunities are classified as B. This relies on effective integration of the environmental regulation, procedures, capacities and liabilities with the areas under focus through this programme. The option of supply-side institutional development is graded as medium risk (in the absence of relevant ongoing inputs) and medium opportunity. Option 2 on demand-side accountability is partly addressed through a complementary DFID programme, the Western Region Coastal Foundation.

Option	Climate change and environment risks	Climate change and environment opportunities
1. Supply-side institutional development	B – manageable potential risk	B – medium opportunity
2. Demand-side accountability	B – manageable potential risk	B – medium opportunity
3. Institutional accountability and public accountability	C – low potential risk	B – medium opportunity

Annex IX: Description of costs of Option 3 by Institution
	Total	Description of costs
Ministry of Energy	£1.000,000	Long-term advisers in the Ministry of Energy supported by a short-term petroleum specialist advising directly the Minister of Energy for two years.
Petroleum Commission	£3,700,000	Institutional and human resource development. Fill staff gaps (three to five people a year for three years), training courses and equipment. One of the advisers would be a petroleum specialist (£300,000-£400,000); and one would be an organisational development specialist (£150,000–£200,000 a year).
GRA	£1,500,000	To develop a clear and predictable fiscal regime for future contracts; provide accurate forecasts of tax revenue; and ensure full compliance from taxpayers with their tax obligations. This includes one full-time petroleum tax specialist in years 1 and 2 (£200,000), as well as continuous short-term support in audits and cost structure assessments.
MOFEP	£1,750,000	Estimate of £1 million over three years. 1. Senior Technical and Policy Adviser to Director and policy analysts; 2. Institutional strengthening Adviser; 3. Short- and longer-term on-the-job training; 4. Communication and outreach programme.
BOG	£550,000	The aim of the project will be to ensure that the BOG’s Petroleum Unit have the necessary skills to influence the allocation of petroleum revenue between funds, and maximise returns on investments made in the Heritage Fund for future generations. This will be delivered through capacity-building activities as well as short-term technical inputs for particular tasks.
Citizen engagement and empowerment	£750,000	Training and technical assistance to analyse petroleum legislation; provide scrutiny of petroleum agreements and key sector bodies such as GNPC. Field visits could be organised to assess the direct and indirect impacts of extracting oil on local communities. This programme would be tied up with another one for members of civil society and the media in order to promote press coverage and wider dissemination of information.
Social media, Broadcast	£500,000	Using the media to increase public awareness of the risks within the oil sector will strengthen accountability and could help to sustain the Government’s reform effort. This can be achieved through increasing access to information, improving advocacy practises and encouraging investigative and evidence-based advocacy. The project could also ‘buy’ a slot on primetime TV or radio programmes.
Strategic and technical support Facility	£6,000.000	Based on the three objectives of improved oversight and regulation, better revenue collection and better revenue management, this facility provides TA and links the initiatives, taking advantage of opportunities and synergies.
Monitoring, audit	£1,500,000	10% additional for DFID's annual reviews, M&E and audit.
Total	£17,250.000