Type of Review: Annual Review

Project Title: South African Partnership for Effective Development Cooperation

Date started:	11/2012	Date review undertaken: 01/10/13

 Introduction and Context

What support is the UK providing?
The UK is providing £5,000,000 over the period from August 2012 to March 2015.

What are the expected results?
This programme will increase the transformational impact of South African development cooperation on poverty, under-development and marginalisation in Africa. We will contribute to this change by working with South African partners to put in place the institutions, skills and knowledge needed to implement successful development programmes and policies. / An indirect, but significant result of the intervention will be to strengthen the working partnership between the UK and South Africa on international development issues. We expect this to increase the results we can achieve together through collaborative work on policies and programmes in future. / The programme will lead to four outputs: / i. The new South African Development Partnerships Agency is able to draw on international best practice / ii. South Africa has the skills needed to manage development policy and programmes professionally / iii. Programme design and resource allocation are based on sound evidence and policy knowledge / iv. South African engagement on global development policy issues is informed by high-quality independent analysis

What is the context in which UK support is provided?
South Africa has the potential to play a transformative role in reducing poverty on the African continent. As part of this role, the Government of South Africa (GoSA) has long engaged in some form of international development cooperation beyond its borders. Though precise figures are elusive, one 2006 estimate of total development assistance was between $363m and $475m. But the potential importance of South Africa as a development partner goes beyond its financial contribution. As an African country, South Africa can bring regional expertise and influence to development partnerships which OECD donors cannot. Its recent history lends it unique legitimacy in working on issues of conflict mediation and transitional justice. Its experience of HIV/AIDS and tuberculosis epidemics has left an unparalleled depth of knowledge on aspects of clinical research. / South African development cooperation is at a moment of transition. The priority given to a strengthened contribution to African development is set out in a range of policy statements and actions. At a continental level, a new South African Development Partnership Agency is being established. At a global level, South Africa is deepening cooperation with other “southern” powers – primarily Brazil, India, China and Russia, through the IBSA group and increasingly through BRICS. Although in many ways South Africa is still finding its feet as a fully engaged member of the international community, its position as sub-Saharan Africa’s leading economy and as an emerging development actor gives it an increasing voice in global development policy discussions. / However, there remain constraints on the effectiveness of these new development partnerships. The lack of an overarching development agency has limited South Africa’s ability to coordinate assistance strategically, to ensure that resources are allocated where the need is greatest, or to judge whether specific investments represent the best way to achieve results. South Africa lacks dedicated professional expertise in development management. And there is very little independent analysis or public discussion of South Africa’s regional development policy, including the channels through which it can achieve the greatest results or the specific roles its institutions and policies can best play within the range of existing actors. / Changes in context since programme approval / This review considered the current context for this programme. It judged that: / The institutional context for South Africa’s development cooperation to other countries remains complex. A number of departments and agencies (including DIRCO, the National Treasury, the DTI and the Presidency, as well as line ministries such as the SA Revenue Service and the Department of Defence) remain engaged in the provision and management of development cooperation. There is limited coordination but also limited settled agreement on how future arrangements should be structured and managed. This is a challenging context for DFID to work in. / The political context appears slightly more favourable than at the time of approval. There is growing independent analysis and public discussion of South Africa’s regional development policy, including the channels through which it can achieve the greatest results or the specific roles its institutions and policies can best play within the range of existing actors. Though evidence is limited, public opinion appears to remain broadly in favour of South Africa’s development role on the continent (63% in favour according to a recent poll). As witnessed in recent South African contributions at the 2013 UN General Assembly, South Africa is playing an increasing role in the post-2015 development debate. The 2013 UK – South Africa Bilateral Forum communique demonstrates a clear willingness and agreement for the UK and South Africa to work together regionally and globally for effective development results.

## Section A: Detailed Output Scoring

Output 1: The new South African Development Partnerships Agency is able to draw on international best practice in establishing management structures
Output 1 score and performance description: B – moderately did not meet expectation.
Progress against expected results: / Output Indicator 1.1 Baseline Aug 2012 Milestone Sep 2013 / Existence of institutional and legal structures for South African Development Partnerships Agency Planned Agency business plan presented to Cabinet. Legislation in process. Plan and legislation approved. Agency established and financially operational. / Achieved Presidential minute signed in May 2013. Agency established and in new offices in DIRCO. Legislation to create Partnership Fund for Development still pending. / Source / Parliamentary reports, DIRCO annual reports, DIRCO interviews / Output Indicator 1.2 Baseline Aug 2012 Milestone Sep 2013 / Establishment of effective systems for oversight and accountability of development assistance drawing on international expertise Planned No systems in place for new agency Parliament and DIRCO audit teams familiar with international models of development oversight / Achieved Policy frameworks developed to support Presidential minute creating SADPA. Draws on visit to UK in 2012 to understand oversight systems. / Source / DIRCO annual reports and interviews / Output Indicator 1.3 Baseline Aug 2012 Milestone Sep 2013 / Progress of workforce planning for new agency drawing on relevant international models of organisational development Planned No workforce plan in place Workforce plan developed, reflecting international best practice. Staff recruited to 30% of posts. / Achieved SADPA organogram and job descriptions in place for around 40-50 staff, drawing on advice from DFID HR. Recruitment underway for 5 initial posts in September 2013. / Source / DIRCO annual reports and interviews / Overall this output is making progress, though behind the timescale envisaged in this logframe. The new agency was formally established in May 2013 through a Presidential minute and gazetted in Parliament. It is not yet financially operational, nor has recruitment into posts yet been substantially undertaken (though this began in September 2013, with 5 senior level posts advertised in the press on 29th September, and with appointments expected by November). A Bill to create a new “Partnership Fund for Development”, replacing the current African Renaissance Fund, has been prepared by DIRCO and is ready to be passed, though this may happen only after elections in 2014. In the meantime SADPA will assume responsibility for the African Renaissance Fund (ARF), providing enhanced oversight and accounting capacity to the management of this fund (which has been subject to accusations of poor control in recent months). / Progress on other issues has met expectations, and is now accelerating. DIRCO (with the assistance of the Technical Assistance Unit, TAU, within the National Treasury) has moved forward with the technical work, and has drafted a 3 year human resource plan and competency framework, medium term budget programming portfolios, strategic framework, operational systems, policy guidelines, legal procedures, tools and instruments for project design, monitoring and evaluation and financial accountability. / DFID’s support in this area has been significant both through responsive, ad hoc sharing of expertise (on financial oversight, HR, IT systems, and programme management), through more structured financial support (an agreement with TAU which is currently only in the early stages), and through highlighting the importance of this element of the broader bilateral relationship (including at the UK-SA Bilateral Forum in September 2013). / Recommendations: / To ensure progress against this output remains on track requires action to be taken to address the institutional and political hurdles which risk delaying the ability of the new agency to begin operations. Much of this is outwith DFID’s control, and any efforts to support the process will need to be done sensitively and carefully to avoid accusations of undue interference. / Suggestions include: / DFID to continue support to current efforts by DIRCO to be inclusive towards various stakeholders in the establishment of SADPA. DFID should continue to support the voices from across government and civil society who argue that South Africa needs an agency to act as a nodal point for its external development cooperation, and to coordinate the efforts of various players and properly track and account for all of South Africa’s development assistance. It is important that this fundamental rationale is reinforced. / With the recent agreement of DFID funding for the SADPA project management office through the National Treasury, a set of jointly agreed targets and milestones have been put in place for this component. These should form the basis for monitoring this output under a revised logframe. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: South Africa has the skills needed to manage development policy and programmes professionally
Output 2 score and performance description: C – substantially did not meet expectation
Progress against expected results: / Output Indicator 2.1 Baseline Aug 2012 Milestone Sep 2013 / Number of SADPA staff and other GoSA officials familiarised with international models of programme management cycle systems and procedures Planned 0 10 / Achieved 8 / Source / DFID quarterly programme monitoring; DIRCO interviews / Output Indicator 2.2 Baseline Aug 2012 Milestone Sep 2013 / Number of SADPA staff and other GoSA officials familiarised with international models of development communications skills and strategies Planned 0 5 / Achieved 0 / Source / DFID quarterly programme monitoring; DIRCO interviews / Output Indicator 2.3 Baseline Aug 2012 Milestone Sep 2013 / Establishment of effective systems and skills for results-based management and evaluation of development interventions Planned No systems in place for new agency Basic programme monitoring systems agreed reflecting international best practice / Achieved No specific discussions held on programme monitoring and evaluation processes. / Source / DFID quarterly programme monitoring; DIRCO interviews / The ability to achieve milestones under this output has been substantially limited by slower than expected progress in staffing SADPA. In addition the decision to respond to DIRCO requests in a very demand-driven way, while successful in building a relationship of trust and establishing a reputation for being a helpful, responsive partner, has meant that efforts have not been focused in the areas foreseen in the logframe, including around communication skills and monitoring/evaluation processes. / On the other hand, DFID has supported a range of ad hoc interventions to improve the skills needed to manage development policy and programmes professionally. For example: / Identification of ICT systems for development cooperation, with a small team of DIRCO and National Treasury officials (June 2013) / Role profiles and organisational development strategies, with the SADPA Director (November 2012) / Programme management cycle introduction, with a team of 8 officials from DIRCO and the National Treasury (May 2012 – relevant to this output and not captured elsewhere in DFID results reporting, though before the financial start of the programme) / Visit to London to explore issues of development cooperation oversight and accountability, with senior DIRCO officials including the Director General and a Member of Parliament (March 2012 – relevant to this output as above) / Furthermore, and as a complement to the above, DFID has supported National Treasury’s Technical Assistance Unit (TAU) for the establishment of the SADPA Project Office, thereby helping to ensure that issues and lessons identified through this assistance can be embedded in new policy and processes. / Recommendations: / Working through TAU is a tactically very sensible approach, which should ensure that technical assistance provided is more effective, efficient and sustainable. This is because the outputs and approach of this proposal have been developed by DIRCO, ensuring full ownership of the process by the Government of South Africa. By ensuring the involvement of the National Treasury in the establishment of SADPA, it enhances inter-departmental coordination in future development cooperation strategy. / DFID should continue and seek opportunities to expand the technical assistance provided by TAU to ensure a greater number of GoSA officials & SADPA staff have the skills to manage development policy and programmes effectively. Though continuing to respond to demand from DIRCO is a sensible strategy, DFID should proactively consider priority areas such as monitoring and evaluation where UK expertise could be particularly fruitful. / As for output 1, targets and milestones should be made consistent with SADPA’s own planning process as set out in the project documents for the support to TAU. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Programme design and resource allocation are based on sound evidence and policy knowledge
Output 3 score and performance description: A – met expectations
Progress against expected results: / Output Indicator 3.1 Baseline Aug 2012 Milestone Sep 2013 / Number of substantive formal discussions facilitated by UK between South Africa and other development actors on interventions in fragile states, peacebuilding and stabilisation Planned 0 2 / Achieved 3 (through ISS programme on post-conflict development, with case studies and events held on SA interventions in DRC and Burundi and South Sudan) / Source / DFID programme quarterly monitoring / Output Indicator 3.2 Baseline Aug 2012 Milestone Sep 2013 / Number of substantive formal discussions facilitated by UK between South Africa and other development actors on the role of the private sector in development interventions Planned 0 2 / Achieved 2 (interpreted as including wider growth issues including customs system reform, which contribute to private sector growth across Africa) / Source / DFID programme quarterly monitoring / Output Indicator 3.3 Baseline Aug 2012 Milestone Sep 2013 / Number of South African development interventions in focus areas incorporating UK-commissioned expertise or evidence in design Planned 0 0 / Achieved 0 / Source / DIRCO annual reports, DIRCO interviews / This output aims to capture UK work with South African institutions providing development cooperation in specific sectors, where UK and international expertise can help make that cooperation more effective and help reflect international experience in its implementation. / Progress has been made through DFID support to three organisations: the Institute for Security Studies (ISS), on South Africa’s post-conflict development policy; the World Customs Organisation, working with the SA Revenue Service (SARS) on how South Africa can engage with third countries on customs reform; and UNFPA, working with the SA National Department of Health to increase South Africa’s leadership of a regional agenda on maternal health (including through a high-level African Union meeting in July 2013). / This is partially reflected in two of the logframe indicators, though in this review we have interpreted “the role of the private sector in development interventions” broadly as including wider work on constraints to private sector growth through customs systems. As expected, there have been no formal discussions with SADPA yet about new South African interventions through this agency which explicitly incorporate UK expertise in their design – the agency is at too early a stage. / Support to ISS has resulted in a number of formal discussions on interventions in fragile states, peace building and stabilisation. The products of the support to ISS has been 2 country case studies, 2 country feedback sessions, 2 policy briefs and 1 advisory panel meeting, focusing on South Africa’s conflict and peace building work in Burundi, DRC and South Sudan. To produce these outputs, ISS held a number of formal discussions with a range of development actors on interventions in fragile states. This helped to strengthen relationships with project stakeholders, especially DIRCO, through continued sharing of information that will contribute to future policy and programmatic development for South Africa’s post conflict development and peace building agenda. Stakeholder meetings provided a platform for South African institutions to hear what other stakeholders were engaged in and get feedback about both their strengths and weaknesses in DRC, Burundi and South Sudan. / Participation in the ISS project from government (DIRCO policy and regional desks, DTI, DBSA and others) has been strong, and initial feedback from government stakeholders has indicated that the research has been of value. An envisaged “task team” on post-conflict development policy, convened by SADPA but not yet operational, would provide a clear future opportunity to link research findings to policy formulation and will be important in the next phase of this work. / The support to SARS and WCO has contributed to South African development interventions incorporating UK commissioned expertise or evidence in design, given the close links between International Relations Team at HM Revenue & Customs with both WCO and SARS, in 6 African countries (selected through a combination of country requests to the WCO and SARS, and WCO diagnostic analysis of country needs). Specifically it has resulted in: / Customs reform and modernisation, including through better risk management, and new capabilities such as post-clearance audit controls that alleviate congestion at borders in Kenya and South Sudan; / Classification: implementing an internationally-applied standard to identify goods as they move across borders. Classification infrastructure support missions were carried out to Angola and Seychelles; / Compliance: introducing strategies to improve the ability of customs systems to secure compliance with national laws. Advisory support was provided to Lesotho on Customs Enforcement Strategies and Cross Border protection; to Kenya Revenue Authority on Canine Enforcement and a regional workshop hosted on mutual administrative assistance and compliance management. / Integrity: preparing action plans and tools to tackle corruption in customs systems, through support to the development of an integrity pilot project in Malawi. / UK support to UNFPA enabled the National Department of Health to co-host a major AU conference on Maternal, Neonatal and Child Health (MNCH) in Johannesburg in July 2013. This contributed to South Africa’s increasing role on agreeing regional health standards, and created an opportunity for professional technical discussions and exchange on effectiveness of health interventions to address countries in the region most affected by HIV/AIDS and determinants of maternal mortality. South Africa’s role was pivotal in sharing best practice and in reinforcing technical and professional networks to help accelerate MDG completion and discussions on future cooperation in health development. DFIDSA are now in further discussions with UNFPA on how most effectively to build on this event, and this relationship, to enable South African institutions to help others implement these standards through new forms of south-south cooperation. / Recommendations: / It has become clear over the course of the first year of this programme that significant opportunities exist for the UK to work with a wide range of South African partners to support and facilitate successful south-south cooperation initiatives. SARS, ISS and (though at an earlier stage) UNFPA appear credible organisations who have delivered important work in the first year towards achieving this output. This provides an important opportunity to explore how such partnerships can best operate in practice (an important issue for DFIDSA’s future transition plans), as well as deliver tangible results which could not otherwise be achieved. Doing so through this programme in a coherent way which matches DFIDSA’s future priorities should be framed and measured more clearly than as currently under this output. / Given South Africa’s rich history of public-private partnerships and corporate social responsibility within and to an extent outside its borders, DFID should look for ways to engage better with the private sector (as well as government institutions, academia and civil society) to explore their role in contributing to international development priorities. Working closely with the CSR arms of South African companies that operate on the continent could be a good start. DFID SA should also explore facilitating discussions between South Africa and DFID policy teams, and current relationships between DFID and the private sector in the UK, for example the ‘Practitioner Hub for Inclusive Business’, and Trade in Global Value Chains Initiative. DFIDSA’s work with the University of the Witwatersrand over recent months has yielded extremely valuable planning and networking on public private partnership discussions in the energy sector, which may also be a good basis for further thinking. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: South African engagement on global development policy issues is informed by high-quality independent analysis
Output 4 score and performance description: A+ – moderately exceeded expectations
Progress against expected results: / Output Indicator 4.1 Baseline Aug 2012 Milestone Sep 2013 / Number of UK-funded research papers or events on role and effectiveness of South African bilateral aid and trilateral partnerships Planned 0 3 / Achieved 5 civil society briefing events with Parliament or DIRCO on SA's development diplomacy (IGD). / Source / DFID quarterly programme monitoring; implementing partner quarterly and annual reports / Output Indicator 4.2 Baseline Aug 2012 Milestone Sep 2013 / Number of UK-funded research papers or events on South African role in multilateral development institutions and processes Planned 0 3 / Achieved 3: event on SA and BRICS; published report on SA and multilateral development diplomacy; event on SA and post-2015 agenda (all IGD) / Source / DFID quarterly programme monitoring; implementing partner quarterly and annual reports / Output Indicator 4.3 Baseline Aug 2012 Milestone Sep 2013 / South African participation in post-2015 Millennium Development Goal process Planned Little evidence of internal discussions or coordination SA Government and civil society engaged in discussion around High Level Panel conclusions / Achieved SA civil society leading youth consultations in 10 African countries and feeding into range of policy opportunities at national, AU and UN levels (African Monitor). IGD/Oxfam event on SA and post-2015 in Sep 2013. SA Government vocal on post-2015 at UNGA. / Source / DIRCO interviews; UN reporting / Good progress has been made against all indicators, with 4.1 and 4.3 notably exceeding expectations. / Support to the Institute for Global Dialogue (IGD) has resulted in research and analysis as well as engagement with key stakeholders in government, academia and civil society to build an understanding of the political drivers that shape development policy. IGD has convened dialogue and triggered debate on these issues. This has resulted in some civil society organisations starting to discuss these broader development issues. IGD is also producing a number of reports on bi-lateral aid, multilateral development and trilateral partnerships, including Multilateral Development Cooperation: What does this mean for South Africa’s Foreign Policy; and BRICS Summit: Partnership for Development and Integration. / There is some evidence that DIRCO have been reaching out increasingly to a few think tanks (including African Monitor) to request analytic input into their thinking on development policy: the Africa Monitor director addressed DIRCO heads of mission and has produced a series of internal briefing papers on these issues. African Monitor have also been instrumental in revising the chapter of the National Development Plan which deals with foreign policy issues, ensuring the inclusion of international and regional development issues. / DFID’s support to African Monitor has resulted in a substantially greater ability of South African civil society to develop a clear evidence base around the views of African youth on the post-2015 development agenda, based on innovative mobile phone-based consultation. African Monitor have overall shown a good ability to translate this into advocacy opportunities within and well beyond the High Level Panel process, including through leading the African civil society group supporting President Ellen Johnson Sirleaf, and through input to the African Common Position on post-2015 being formulated by the African Union. DFID’s funding to the IGD/Oxfam-led post-2015 event in September 2013 represented the first notable opportunity for civil society to engage in detail on this agenda with government, at a timely moment following UNGA, and is likely to create more opportunities to build on this in future. / There is good evidence to suggest that the South African government is increasingly active on development policy issues and is taking a keen interest in post 2015 MDG process and very much engaged in debates around this. For example President Zuma’s speech at UNGA 68 had a very strong focus on the MDGs and the post 2015 agenda. South Africa co-facilitated the UNGA Special Event on the MDGs; they are one of two southern African representatives in the steering group for an African Common Position on post-2015; and (beyond government) Graca Machel played a central role in the development of the UN High Level Panel Report. This is despite relatively little coherent civil society engagement to date on the post-2015 MDG process in South Africa. / Anecdotal reporting from DIRCO indicates that the ability of a few trusted civil society organisations (including IGD) to convene and analyse debate on development policy issues has been valuable. Though it is difficult to quantify and evidence to this point is limited, this provides some initial support for the assumption around this output that “better analysis and understanding of global development issues contributes to greater policy engagement and better decision-making”. / Recommendations: / It is unlikely that relying solely on IGD and African Monitor will result in next year’s milestones being reached. At the same time it probably makes sense to complement this work by supporting a more diverse range of actors within South Africa to engage in the growing discourse on the role and effectiveness of South African bilateral aid and trilateral partnerships and on South Africa’s role in multilateral development institutions and processes. / DFID should explore opportunities to build civil society engagement in the post 2015 MDG debates by creating a mechanism, or else fund an existing one, which could enable civil society to do more work in this area. Probably the most efficient and effective way to do this from a strategic and from a programme management perspective is to explore possibilities of supporting civil society platforms, which can engage networks of civil society organisations working on particular themes (e.g. gender) and have the institutional links to global civil society and south-south networks. This will contribute to greater independent analysis and public discussion of South Africa’s development policy, including the channels through which it can achieve the greatest results or the specific roles its institutions and policies can best play within the range of existing actors. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A – outputs met expectations / 1.3 Direct feedback from beneficiaries / Identification of beneficiaries under this programme is challenging, since the delivery chain between policy activity and results for the poor is long and complex. / There have been detailed discussions with a number of direct beneficiaries of this programme (civil society, think tanks, GoSA officials, other bi-lateral donors) and the annual review reflects feedback and perspectives provided by these beneficiaries. / It should be possible in future reviews to consider more indirect beneficiaries, mainly through the south-south cooperation elements in output 3. These could include for example those benefiting from improved customs systems, or those in the health sector elsewhere in Africa benefiting from South African expertise.
1.4 Summary of overall progress / The agreed outcome of this programme is that “South African regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice”. / Due to the delays in the establishment of SADPA the outputs have so far contributed little to the “proportion of South African bilateral development programmes disbursed or coordinated through SADPA” (outcome indicator 2). However with DFID funding a plan is now in place for SADPA to commission a baseline study which will make this data available in future. / On the other hand work delivered under output 4 (South African engagement on global development policy issues is informed by high-quality independent analysis) through UK funded research, papers and events, has contributed to considerable progress towards the level of South African participation in multilateral development policy processes (outcome indicator 1). / It is too early to judge or indeed measure any progress towards impact indicators, and there remains a question as to whether those impact indicators are too ambitious. / Outcome Indicator 1 Baseline Aug 2012 Milestone Sep 2013 / Level of South African participation in multilateral development policy processes Planned SA signed up to Busan principles, including Global Partnership on Development Effectiveness SA is a routine participant in GPDE process as a provider of development assistance / Achieved SA attended GPEDC steering committee in Addis Ababa as one of a small number of "emerging provider" representatives. SA considering its role and reporting for the 2014 GPEDC ministerial. More active on south-south cooperation standards through other fora outside GPEDC, including BRICS and IBSA. SADPA increasingly vocal in these global debates, and seen as an institutional leader for global south-south cooperation discussions. / Source / GPEDC progress reporting / Outcome Indicator 2 Baseline Aug 2012 Milestone Sep 2013 / Proportion of South African bilateral development programmes disbursed or coordinated through SADPA Planned TBC: estimated under 4% through ARF Reliable figures exist. At least 10% through SADPA / Achieved No reliable figures yet exist, though with DFID funding a baseline survey is now planned by SADPA which will generate this data and significantly contribute to the transparency of SA development cooperation. / Source / DIRCO and National Treasury annual reports and interviews; independent analysis of SA aid flows funded by this programme
1.5 Key challenges / Delays to the establishment of SADPA, which are related to complexities around the institutional arrangements required for the management of the new agency, risk hindering progress towards the programme’s outcome as currently framed. / At the institutional level it remains to be seen to what extent the many public bodies currently involved in providing some form of development cooperation outside South Africa are willing to have their work better coordinated by a nodal agency like SADPA. Arguably the complexities around the institutional arrangements required for the management of the new agency and fund are one of the main reasons for the long delay in the formalisation of this new agency. Currently four government departments play a significant role in international development cooperation, and each could make a case to lead, have oversight and provide direction to South Africa’s development cooperation and provide institutional support to SADPA. The National Treasury already manages incoming development cooperation to South Africa and has been engaged with OECD-DAC in the aid effectiveness discourse. It leads South Africa’s engagement in global development fora, such as the World Bank, AfDB, G20 and OECD. As the financial guardian of South Africa’s public finance it is concerned with financial accountability. / Ultimately the politics is critical. Some commentators have suggested South Africa’s own socioeconomic realities may constrain the extent to which this administration, 12 months away from an election, is keen to move ahead in establishing its own development cooperation agency as taxpayers at home could be sensitive to financing development projects in Africa, while poverty in South Africa is widespread and public services are not delivering as they should. On the other hand public support for the establishment of a development agency is strong (a recent survey by the Universities of Stellenbosch and Cape Town found that 63% of respondents agreed that South Africa should provide aid to others on the continent), which suggests that plans to establish a new agency could have the support of the majority of South African citizens. / Another challenge is how to manage offers of matched project funding for the new agency from “traditional” donors (an issue raised in principle by GIZ and USAID). This risks distorting South Africa’s development cooperation policy, and putting it under pressure to promote others’ development agendas rather than its own. Due to its historical legacy of providing development assistance and its perceived legitimacy in the eyes of continental partners, offers of foreign funding are high and SADPA may have to manage more money from foreign donors than from its own national resources. / To avoid the distorting effects of foreign donor funding, whilst making use of it to increase the poverty impact of South Africa’s development policy and programmes, SADPA has recognised the need to establish clear priorities and policy frameworks through an internal process, and then approach donors to work in partnership on specific programmes.
1.6 Annual Outcome Assessment / At this early stage, the programme is broadly on track and has achieved some encouraging results despite challenges around delays to the establishment of SADPA.. However the first year has been very process-focused and evidence around the contribution to outcomes for South Africa, for partners, and for development cooperation remains weak overall. / The available evidence from the programme at this stage suggests in particular that: / This programme has helped create opportunities for the UK and South Africa to work closely together on the establishment of SA’s new development agency, and to help ensure structures and procedures are managed professionally and in line with best practice through adequate internal support; / The programme has facilitated a range of discussions around DFID’s role in facilitating south-south cooperation, which will make an important contribution to thinking about a future UK-SA development relationship which increasingly looks beyond South Africa’s borders; / That cooperation itself has begun to achieve measurable results (though these require improved quantification by partners in the next year), including improvements to customs systems in a range of other African countries; / The programme has enabled South African civil society to engage in development policy issues, particularly around the post-2015 debate, in a way which is both useful for government and which has begun to increase the level of public scrutiny and accountability around these issues. / While we have decided not to evaluate the programme, there is a case for a stronger, more analytical, impact focussed review to be commissioned alongside the annual review next year, in addition to the VFM analysis recommended below.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / The total budget for this programme is £5,000,000 from November 2012 – March 2015. A total of £866,270 has been spent against the total programme budget during the period under review November 2012 to October 2013. This equates to 17% of the budget. Spend has been initially slow with only the grants with African Monitor, the Institute for Global Dialogue and the MOU with the World Customs Organisation/SARS spending in 2012/13. Spend in 2013/14 has picked up, with the Institute for Security Studies grant as well as the support provided to UNFPA for the International Conference on Maternal, Newborn and Child Mortality. The programme is currently 58% spent against the 2013/14 forecast. / Although spend has accelerated, this still represents a low level of spend compared to the projections in the business case. There are a number of reasons for this: it is worth noting that it is not due to any individual partner underspending against budget or underperforming. Rather, it is mainly a consequence of limits of the number of interventions which can be reasonably managed by limited capacity in DFIDSA, and the relatively small size of individual interventions in this policy area. The time taken in agreeing and authorising interventions with a range of new partners has been a secondary factor, despite the relative speed and flexibility offered by this programme. / Year 0 Year 1 Year 2 Total / 2012/13 2013/14 2014/15 2012-15 / Forecast in BC Actual Forecast Actual Spend Forecast in BC Actual Forecast Actual Spend Forecast in BC Actual Forecast Forecast in BC Actual Forecast Actual Spend to date / Institutional support to SADPA / 100,000 0 0 200,000 200,000 0 200,000 300,000 500,000 500,000 0 / Facilitating policy dialogue / 250,000 50,000 50,000 500,000 676,871 460,029 1,750,000 1,800,000 2,500,000 2,526,871 510,029 / Building evidence on SA dev coop / 150,000 186,253 186,253 350,000 200,000 169,988 1,500,000 1,586,876 2,000,000 1,973,129 356,241 / Total 500,000 236,253 236,253 1,050,000 1,076,871 630,017 3,450,000 3,686,876 5,000,000 5,000,000 866,270 / Meeting future spend targets is feasible though will be challenging. A total of £2,006,000 from the programme’s £5,000,000 budget is currently committed under grants and memoranda of understanding with partners. This leaves £2,994,000 available for commitment to new opportunities between now and March 2015. Some of these opportunities have been provisionally identified (e.g. support to University of Cape Town, increased and more coherent work with civil society as recommended in this review). As the programme’s steering committee has identified, a degree of continued flexibility is helpful given the nature of the programme’s objectives. However there is an increasing risk of being unable to commit and spend the total allocation within the current spending period: this is considered further under the risk section below. / 2.2 Key cost drivers / The main cost drivers across this programme and its various components are primarily expert technical advice and research, travel, accommodation and meeting facilities costs. These represent roughly 51.8% of budgets for components approved to date. Though this is high compared to most DFID programmes, it reflects the nature of this policy-oriented programme and is in line with expectations in the business case. / 2.3 Is the project on-track against original timescale: No / The programme is slightly behind its original timeframe. The setting up of the SADPA component has been slow. SADPA has not yet been formally established. There have been a number of institutional and political hurdles to overcome, but which have been necessary to establish a good working relationship with DIRCO. / The WCO/SARS component has had some setbacks and delay in the synchronisation of mission dates between various stakeholders. But the project still remains viable and is demonstrating progress. The delays in carrying out certain activities in the project and the challenges of a regional project that involves a host of parties/countries can be overcome with time and continued effort.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Evidence of need / There has been some further analysis from academic and civil society sources of South Africa’s development policy and institutions over this period. In particular, the SA Institute for International Affairs published a research report in August 2013 on “South African Development Partnership Agency: Strategic Aid or Development Packages for Africa?”. The Institute for Global Dialogue, through funding received under this programme, have published a report on “Multilateral Development Cooperation: What does it mean for South Africa’s foreign policy?”. An article by Brendan Vickers, “Towards a New Aid Approach: South Africa as African Development Partner”, was published in January 2013 in the Cambridge Review of International Affairs. / This work has in general reinforced the evidence around SADPA as a significant policy response to improving the coordination and effectiveness of South Africa’s development cooperation. It has further articulated the potential contribution this cooperation could make to development in the region and across the continent should its effectiveness be enhanced (i.e. in line with the outcome of this programme). And it has emphasised the strong links between the creation of a new development institution and South Africa’s increasing voice on the global development policy agenda. All these issues reinforce the theory of change set out for this programme. / Evidence on approaches / There has been much less new external evidence around the approaches proposed under this programme to link outputs to outcomes. This falls into three areas: / On support to SADPA, evidence has relied mainly on sharing experience with other donors in South Africa and with comparable DFID experience in other countries (including Brazil, India and China) where the UK is working with “new” development agencies. The responsive, demand-led approach under this programme, targeted at meeting short-term needs to build helpful relationships, is in line with emerging best practice from those sources. / Evidence on how traditional donors can best support and learn from south-south cooperation remains extremely thin. Again this programme is informed principally by emerging experience from other DFID offices including Brazil and China. In South Africa, GIZ and USAID have made available evidence from their own review of trilateral cooperation approaches, though this is too recent (Sep 2013) to have yet been integrated into planning for this programme. Broader work has been carried out recently by the OECD and UNDP on south-south and trilateral cooperation, which again could be compared to approaches in this programme. / Evidence on working with civil society to strengthen policy approaches to development cooperation in an “emerging power” is almost entirely lacking, and this programme’s approach is necessarily based mainly on internal learning rather than external evidence. / 3.2 Where an evaluation is planned what progress has been made? / The business case for this programme judged that “given the moderate overall financial value of this programme, and the challenges of assessing the impact of UK-funded activities on broader South African policy issues, we do not judge that an external evaluation of this programme would be appropriate”. This remains an appropriate judgement. / However there remains a need to ensure that emerging evidence from this programme is properly captured and can fully inform both DFIDSA transition planning and wider DFID work with emerging powers. This is particularly relevant in two areas: working with a wide range of institutions to understand what kind of partnership can best facilitate effective south-south cooperation (and what the benefits can be for all sides of such a partnership); and working with civil society in an emerging power as part of a development relationship which looks outwards to regional and global results. / DFIDSA should therefore work further with Global Partnerships Department and other “emerging power” offices including Brazil, India and China, to consider how best to strengthen the theory of change (demonstrating clearly the links between activities, outcomes and impact), and to improve monitoring of outcomes accordingly during the remainder of the programme. This should draw on comparable processes conducted for similar programmes in other offices, and DFID’s central efforts to measure the outcomes of work with emerging powers. It should be designed in such a way that it contributes effectively to future thinking around monitoring policy work and global partnership programmes.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The risks identified in the business case remain relevant but to this point have not significantly affected the programme outcome. / The establishment of SADPA, though delayed, remains a clear priority for the Government of South Africa and has featured highly in GoSA statements (e.g. the 2013 Foreign Policy Budget Vote Speech). / South Africa’s willingness to work with the UK on this agenda remains relatively strong, despite broader challenges in 2013 around the UK-SA development relationships and bilateral discussions with the UK (e.g. SADPA and regional cooperation featured strongly in the 2013 Bilateral Forum communique). / Local capacity to implement activites has been variable, resulting in delays in progress (e.g. in establishing operational programmes with SARS and IGD). However activities underway are now starting to demonstrate results. / The most significant risk is around the commitment and accurate forecasting of funds, given the range of activities funded through this programme and the need to retain flexibility. As set out in section 2 above, some 58% of funds remain unallocated to activities at this one-year point. / This is a risk which can be managed by DFID, but which will require an urgent decision on handling by the DFIDSA programme team if it is not to become an issue later in the programme cycle. Options include: / Agreeing that the level of funds currently unallocated to activities remains appropriate to ensure flexibility, despite the risk of underspend. This would require a high risk appetite around future forecasts; / Considering the benefits of extending the programme by one year to March 2016. This would also ensure that activities linked to the post-2015 debate in the UN can continue up to and beyond the 2015 UNGA session at which these negotiations will conclude. / Reducing the overall programme budget, recognising that the limits on the number of activities which can be managed, and the small average size of individual activities under this programme, were not fully taken into account in the business case. / Agree an option to programme all available funds (or a higher proportion) in a manner which does not significantly increase the management burden on DFIDSA, including by scaling up existing interventions where they are achieving success, and taking a platform approach with NGOs in order to increase management efficiency.
Risk of funds not being used as intended / This risk is judged to be low, given the assurance measures set out in the business case and reviewed under section 5 below. All funds are disbursed only on examination of full financial reporting under DFID accountable grant or MoU guidance. / The programme team in DFIDSA should consider using spot checks of implementing partners as an additional measure in the coming year. / 4.4 Climate and Environment Risk / Potential negative climate and environment impacts of this programme were judged in the business case to be “negligible”. DIRCO have not to this point requested any support from the UK on sharing best practice on climate and development through this programme, which was identified as the major potential benefit – and our current demand-driven approach to assisting SADPA limits our ability at the moment to be more proactive in raising this.

5. Value for Money
5.1 Performance on VfM measures / No formal VfM assessment was carried out with this review, due to the early stage of most spending activities. This annual review considers whether systems currently in place are adequate to ensure VfM. It may be appropriate as part of the next annual review to include more detailed scrutiny of project partner performance once more data is available. / At the level of individual programme components, a range of measures are applied to ensure DFID funds are spent in a cost effective manner. This includes a rigorous review of quarterly financial reports from all project implementers; and full scrutiny of budgets when new proposals are considered for funding. This has in several cases resulted in negotiated savings from scrutiny of input costs: for example a saving of 36% was made when negotiating the support DFID provided to the UNFPA International Conference on Maternal, Newborn and Child Mortality. / The effectiveness of interventions has been assessed through embedded results frameworks for all interventions over £250,000 (and for some interventions under this value). These are used as the basis for progress monitoring with project implementers on a quarterly basis, and are clearly linked to the programme’s logframe. It will be essential that future commitments are subject to the same process. / 5.2 Commercial Improvement and Value for Money / All spend so far through this programme has been indirect: no direct spend has been incurred through DFID’s commercial processes. / Before agreements have been put in place, implementing partners have been subject to proportionate due diligence processes (including assurance of procurement processes) in line with normal accountable grant and MoU compliance tasks. Budgets have been negotiated as described above. / 5.3 Role of project partners / This annual review has not included an in-depth assessment of the performance of implementing partners, focusing instead on the delivery of outputs and coherence of activities in relation to intended outcomes. / Such an exercise may be appropriate at the next review, given both the better availability of data at that point and the need for evidence on individual partner organisations to support future programming decisions. / 5.4 Does the project still represent Value for Money : Yes / There is strong value for money justification for the programme overall. In particular, and in line with the VfM statement set out in the business case, the non-quantifiable benefits of the programme are significant in providing value to DFID’s investment in this programme. These include the already strong relationships being established between DFID and the implementing partners such as DIRCO and SARS. These relationships are significant in continuing closer cooperation between the UK and SA on global development policy. / 5.5 If not, what action will you take? / No action necessary, though a more detailed VfM assessment should be considered as part of the 2014 annual review of this programme.

6. Conditionality
6.1 Update on specific conditions / Not applicable: in this period no DFID funds were disbursed directly to the Government of South Africa as financial aid under this programme. The agreement with TAU to support the SADPA project office will be a form of non-budget support financial aid, and should be reviewed as such in future annual reviews.

7. Conclusions and actions
Relevance and need / This is an important and innovative programme which is working with South African partners to put in place the institutions, skills and knowledge needed to implement successful development programmes and policies. It has relevance to DFID’s emerging powers work in other countries; it fits squarely under the first objective of DFID’s overall emerging powers strategy agreed by Ministers in 2012, “to improve the effectiveness and efficiency of development assistance”, and is one of the core programmes currently in operation to achieve results under this objective. / Ultimately the programme should contribute to increasing the impact of South African development cooperation on poverty in Africa. The programme is also strengthening the working partnership between the UK and South Africa on international development issues, for example on health and tax reform. It thereby creates a strong basis for collaborative work on policies and programmes in future. / The programme can be seen as an end in itself in ensuring South Africa’s development assistance in the continent is more impactful. It can also be seen as a means to an end, and it is clear that the programme can also be an important way of trialling different approaches and relationships for south-south and triangular cooperation – and possible partners in this. This is already happening, for example through work with the National Department of Health and SARS, and further opportunities should be explored to build on these novel approaches. / Coherence and ability to deliver outcome / This is a complex programme with many disparate components. At this point it remains adequately aligned to the agreed outcomes, with all components contributing to a reasonably clear theory of change. This will need to be continuously reviewed to ensure it is maintained. The recommendations below on revising the logframe will help to address this. / Also relevant to maintaining coherence is the extent to which the programmes needs to balance an opportunistic, demand-driven approach with a clear and focused set of priorities. To date the steering committee has accepted the need for opportunism to build relationships and explore work with a wide range of partners. This has delivered benefits. However, with a range of activities now up and running, and with some clear wider priorities for the UK-SA partnership now agreed through the Bilateral Forum in September 2013, this calculation is now shifting. DFIDSA can now consider being more strategic about selecting these opportunities based on UK and South African priorities, existing DFIDSA programmes, good value for money and the ability to deliver clear development results in the region. / Support to the training of GoSA and SADPA officials to manage development programmes and policy effectively has been perceived as beneficial and is proving useful in terms of cementing and buliding bilateral relationships. Working with TAU has been an efficient and effective use of resources and should ensure greater ownership by GoSA and a more sustainable transfer of skills. In view of this, DFID should continue to seek opportunities to ensure a greater number of GoSA officials & SADPA staff have the skills to manage development policy and programmes effectively. This can be through TAU or through ad hoc opportunities with DFID. / DFID should explore opportunities to get more civil society engagement in the post 2015 MDG debates by creating a mechanism, or else fund an existing one, which could enable civil society to do more work in this area. One way would be to support civil society platforms, which can engage networks of civil society organisations working on particular themes and have institutional links to global civil society and south-south networks. This will contribute to greater independent analysis and public discussion of South Africa’s development policy, including the channels through which it can achieve the greatest results or the specific roles its institutions and policies can best play within the range of existing actors. / Value for Money / The assumptions in the business case about value for money still hold. VfM is ensured and monitored at the intervention level through scrutiny of budgets, procurement systems, and financial statements, and through clearly agreed results frameworks with each implementing partner linked to the programme’s overall logframe. Overall VfM remains sound, particularly given the (difficult-to-quantify) impact of the programme on broader relationships. / This review has not included a full assessment of implementing partner performance, which should be considered as part of the 2014 annual review. / Management and monitoring systems / Management of the programme through a combination of a quarterly steering committee, lead advisory capacity from the DFIDSA Head of Global Development Partnerships, and programme management capacity from the DFIDSA Head of Cabinet, has so far worked adequately in ensuring compliance tasks are fulfilled. However this is a time-intensive programme which places significant demands on those involved. Moving lead responsibility for individual elements to DFIDSA programme teams, as is increasingly the case (e.g. for the work with UNFPA) will help resolve this; but will require strong central oversight to ensure coherence is maintained and lessons shared across the programme. / Currently the log frame does not capture the important aspects of the programme around innovative and exploratory approaches to working with new partners on south-south and trilateral cooperation, but it needs to. Being explicit about the opportunities this programme provides for helping DFID SA to transition out of bilateral development assistance and explore newer approaches and relationships for development cooperation may provide a stronger rationale for engaging in a range of opportunistic – though less clearly results orientated – partnerships in priority areas. / At the moment the logframe of the programme is too focused towards the establishment of SADPA, and captures less what the programme is doing to explore and support new approaches towards south-south cooperation, such as the work of SARS and Dept of Health. If the objective is to improve South Africa’s development to effectiveness, the LF needs to capture the results of working through new relationships, for example with individual Ministries and agencies. These new relationships will be critical in opening doors and new pathways for the period after the end of bi-lateral development cooperation. / Recommendations / Based on the above, this review concludes that DFIDSA should consider: / Restructuring the logframe into three clear outputs. These could focus on (i) support to SADPA; (ii) facilitating (and learning from) effective south-south cooperation with a range of governmental and non-governmental partners; and (iii) enabling civil society in South Africa and the region to engage in the development discourse at national and global levels. This would increase the coherence around the programme and create a better balance in the results framework between focusing on SADPA as an institution and understanding the broader picture of South Africa’s development activity in Africa. Logframe indicators should be revised to be consistent with sub-components, including the targets for the SADPA project office. / Agreeing a clear approach to managing spend over the remainder of the programme. This should represent one of the options set out in the risk section above, and may include a series of measures to allocate funding to activities without significantly increasing the management burden on DFIDSA; it should also include considering the benefits of a no-cost extension of the programme if this will enable results to be achieved more effectively. / Maintaining an opportunistic and demand-led approach to supporting south-south cooperation initiatives, but being more proactive about priority areas in line with DFIDSA’s future transition plans. This focus should be based on DFID’s wider analysis of future UK priorities, South African added value in the region, and the efforts of other bilateral and multilateral development partners, and might draw on the shared objectives agreed by the UK and South Africa at the 2013 Bilateral Forum. / Ensuring greater civil society engagement in South Africa’s development policy and the post 2015 development agenda. Probably the most efficient and effective way to do this from a strategic and from a programme management perspective is to explore possibilities of supporting civil society platforms rather than individual organisations. / Ensuring lessons from monitoring and evaluation of the programme can be clearly embedded in DFID’s wider emerging powers work and DFIDSA’s transition planning. This includes improving project-level monitoring, where possible, through identifying indirect beneficiaries (e.g. those in third countries benefiting from South Africa expertise) and including this constituency in monitoring plans. It should also include considering improved outcome-level monitoring and evaluation, drawing on lessons from other DFID offices and central thinking in Global Partnerships Department. Such a process might cover structured reviews of lessons from this programme around UK support to south-south partnerships, and around how best to work with civil society as part of a new kind of development relationship which looks to results in the region rather than in South Africa.

8. Review Process
This review was conducted over the period from 23 September 2013 to 18 October 2013. / Indranil Chakrabarti, Head of DFID team in Brazil, led the annual review process. Will Hines (Head of Global Partnerships, DFIDSA) and Karen Terblanche (Head of Cabinet, DFIDSA) provided inputs to a number of sections. / Indranil Chakrabati and Sandy Baldwin (Deputy Head, DFIDSA) have provided a quality assurance function to the final report. / Project reports, discussions with DFID staff and other bilateral donors and interviews with local stakeholders from GoSA, academia and civil society all helped inform the review.