Annual Review – Report Summary Sheet

Title: Somali Health and Nutrition Programme (SHINE)
Programme Value £ (full life): 89 million		Review Date: November 2018
Programme Code: 204903	Start Date: November 2015	End Date: / March 2021

Summary of Programme Performance
Year	2016	2017	2018
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204903/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204903/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

This is the 3rd Annual Review of the Somali Health and Nutrition Programme (SHINE), an £89m five-year (2016-21) programme tackling the high levels of preventable maternal and child deaths among Somali women and children. A fluctuating humanitarian situation persists in Somalia with conflict, instability and periodic drought and flooding. The country has some of the world’s highest child and maternal mortality rates; less than 10% of women give birth in a health facility; female genital mutilation affects almost all women causing increased obstetric complications; and preventable childhood diseases such as pneumonia and diarrhoea remain major killers with low routine immunisation rates.[1] Total spending on health remains considerably below the 60USD per capita recommended by WHO for essential health service delivery in low income countries, . SHINE seeks to improve both supply and demand for health and nutrition services by:
[1] UNICEF State of the World’s Children. 2017.

- Focusing on delivery of the essential package of health services (EPHS) and aligning to the Somalia National Health Sector Strategic Plans (HSSP).
- Empowering vulnerable populations, especially women and children, to overcome barriers to accessing services and make healthy choices.
- Strengthening the Somalia Health Authorities (SHAs) leadership and oversight of service provision to promote local accountability and ownership and enable them to increasingly respond to the needs of their populations.

The programme demonstrates DFID’s continued commitment to improving the health status of Somalis while also contributing to wider objectives of poverty reduction and state and institutional strengthening. As the largest health development donor by some margin, DFID provides over 50% of long-term support to the health sector. SHINE uses a mixed delivery approach, and after a slow and staggered start considerable progress has taken place in the last year to structure the components and ensure a coherent approach and clear linkages between them. The status of each component is outlined in brief below. To date £26.9m of the £89m has been disbursed:

- The Community Health and Nutrition through Governance and Empowerment (Change) programme provides essential health service delivery and regional and district system strengthening through a consortium of international NGOs: Save the Children (Karkaar, Puntland), Trocaire (Gedo, Jubbaland) and Health Poverty Action (Sahil, Somaliland), led by Population Services International (PSI). Service delivery has continued uninterrupted and in early 2018 the consortium prioritised quality of care and use of data as the focus of their ongoing system strengthening work.
- The Sahan (Somali Advocates for Health and Nutrition) demand creation and behaviour change programme managed by PSI works to design, test and pilot new and revised approaches to behaviour change and build evidence for what works. A substantial pipeline of interventions exists. Progress in working with SHINE service delivery partners to pilot them in the field has been slow but is now beginning.
- The SHINE Supply programme will provide essential health service delivery in 16 districts in Banadir, Galgaduud, Awdal and Toghdeer starting in January 2019, and national system strengthening support. The contract was awarded to Mott Macdonald (MM) in July 2018, a request for proposals to determine service delivery partners, and a rapid review to prioritise health systems work, are ongoing.
- The Commodity Security programme will involve UNICEF procuring and distributing supplies to SHINE Supply supported locations. Planning has taken place to ensure supplies are available for service delivery starting in January 2019. Ongoing supply chain strengthening support through UNICEF and UNFPA is building on work started in the inception phase, including improving forecasting and quantification of supply needs.
- UNICEF EPHS bridge support has continued services in eight regions previously covered by the DFID supported Joint Health and Nutrition Programme (Banadir, Lower Juba, Galgaduud, Mudug, Bari, Awdal, Togdheer and Sanaag) during delays in contracting of MM. This provided a reduced package of services until September 2018 (some further support has been provided through humanitarian funding until March 2019). From January 2019 services in 16 of these previously UNICEF supported districts will be managed through MM and further support to UNICEF will continue services in a number of the remaining districts and expand support to the full EPHS package.

A very lengthy procurement of SHINE Supply meant adaptation of the original design to enable the programme to deliver. The UNICEF bridge funding put in place to continue services and cover the delays in 2017-18 will be transitioned in 2019-20 to the now contracted SHINE Supply programme, and a more comprehensive service delivery programme with UNICEF. The diagram below summarises the structure going forward:

SHINE (2016-2021) £89m

        Service delivery and health system strengthening
Sahan: Design of demand creation and behaviour change interventions and piloting with service delivery partners across locations.
SHINE SUPPLY
EPHS Service Delivery and district/regional health systems strengthening

Locations: Awdal &Toghdeer, Somaliland; Galgaduud, Galmadug and Banadir

Additional system strengthening work at the national level and in Federal Member States.
UNICEF Commodity Supply

Locations: SHINE Supply Sites

UNICEF and UNFPA supply chain strengthening support.

CHANGE
EPHS Service Delivery and district/regional health systems strengthening

Locations: Sahil, Somaliland
Karkaar, Puntland
Gedo, Jubaland

UNICEF
EPHS Service
Delivery and district/regional health systems strengthening

Locations: TBC

Summary supporting narrative for the overall score in this review (1/2 page)

Despite procurement delays meaning changes to the implementing arrangements SHINE partners have provided essential health services to an estimated 1 million women and children between 1st October 2017 and 31st September 2018 demonstrating positive progress and exceeding key service delivery targets. As well as vital routine service delivery this coverage reflects an important contribution to the drought response. In 2017 the persistent lack of rain caused a significant increase in food insecurity and malnutrition, large scale displacement and a high risk of famine. This also led to high demand for health and nutrition services. SHINE partners helped meet these increased needs, particularly in parts of Karkar, Gedo and Sahil under the Change programme which received an influx of people many of whom have remained.

Overall the Change programme continues to perform strongly providing over 500,000 out-patient consultations to address common child and maternal health issues and making good progress on integrating nutrition and family planning services in the last year.

The route to market for the SHINE Supply programme was determined in 2016 after approval of the overall Business Case. A protracted 20-month process to contract Mott Macdonald to deliver the programme means they have only been in place since July 2018 and are working to support the start of service delivery in January 2019. In the interim UNICEF has played a critical role enabling continuity of service provision through the bridge funding provided under SHINE. They have achieved impressive coverage of the limited number of services supported with over 90,000 women delivering in institutions due to an increase in 24-hour operations, and over 160,000 children immunised with the pentavalent vaccine. However, weaknesses of this focus on a narrow number of services only at higher level facilities will see a revised partnership with UNICEF until the end of SHINE deliver the more comprehensive EPHS package provided by other SHINE service delivery partners.

The Change programme continues to lead the way in developing systems at the district and regional level and lessons from this have been shared with the SHINE Supply and UNICEF teams. Lessons include building of local government ownership leading to mobilisation of resources from the community to support renovations and training on accurate forecasting of supply needs reducing wastage. The next phase under Change will see partners work closely with the Somali Health Authorities on tools to improve supervision of staff and use of routinely collected health information data to inform decision making and improve quality of care. The Sahan health behaviour change programme managed by PSI has made progress in agreeing and getting buy in for its approach. This brings new human centred design and behavioural science thinking to the Somali health sector to help improve behaviour, in particular uptake of services. While a pipeline of interventions exists, progress in testing and piloting these with partners in the field and generating an evidence-base for their impact has been disappointing. PSI has limited geographic coverage themselves and has been slow to engage others. Getting these partnerships in place is now the focus.

In the next year SHINE will focus on achieving a coherent approach across Change, Shine Supply and UNICEF supported service delivery locations: delivering services, building capacity and systems, testing new demand creation approaches and measuring value for money and impact of the different modalities.

Recommendations for the year ahead (1/2 page)
DFID will support partners in:
1. CHANGE programme: Testing, adjusting and measuring the impact of the proposed tools to improve quality of care and use of data in Change regions with a view to rolling them out across other SHINE areas from July 2019.
2. SHINE Supply: Supporting the contracting of service delivery partners to promote timely and efficient delivery of services; and agreement of priorities for health system strengthening support and initiating work by (January 2019).
3. Commodity Security Programme: Ensuring the timely and effective quantification, procurement and delivery of health and nutrition supplies for Shine Supply supported districts (from January 2019); and ensuring a good working relationship between UNICEF and Mott Macdonald.
4. UNICEF service delivery: Finalising and implementing the service delivery support package ensuring coherent linkages in geography and approach with other SHINE partners (by Dec 2018).
5. SAHAN testing and piloting: Ensuring partnerships with SHINE service delivery partners are in place by January 2019 to test and pilot interventions in targeted locations across Somalia.
6. Linkages between SHINE components: Explicitly strengthening linkages between the multiple SHINE components across 3 main areas: service delivery approach, health systems support, and integration of demand creation activities. Facilitated by quarterly SHINE partner meetings sharing of lessons, coordination of support and working in partnership will improve collective impact.
7. Monitoring & Evaluation (M&E): Finalising the harmonized SHINE logical framework now that all partners are in place – without radically changing outcomes (by January 2019). Ensuring M&E includes a coherent approach to value for money and enables comparison of different approaches to inform future health programming.
8. Linkages with the humanitarian programme: Continue regular close coordination and collaboration between SHINE and the Building Resilience in Communities in Somalia (BRCiS II) programme, and other parts of the humanitarian portfolio looking for efficiencies and joint working opportunities.
9. Financial management: Improving the accuracy of the financial forecasting of partners, with particular focus on PSI (by March 2019).

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Improve the standardisation, coverage and quality of Essential Package of Health Services (EPHS)
Output number per LF		1	Output Score	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)		Milestone 3 (Annual Review 3 2018)			Score
		CHANGE	UNICEF EPHS Bridging[2]	Total
1.1a) % of EPHS facilities offering integrated modern birth spacing	Expected	75% (Health Centre (HC), Referral Health Centre (RHC), and Hospital -higher level facilities)	N/A
	Achieved	74% (Services in 20 out of 27 facilities).			A
1.1b) % of EPHS facilities offering nutrition specific intervention package	Expected	90% (RHC, HC, Hospital)	N/A
	Achieved	100% Nutrition screening and referral in 27 facilities			A
1.2) Number of women delivering with help of a skilled birth attendant	Expected	15,206	48,626	63,832
	Achieved	16,054 (6 % above milestone)	95,304 (95% above milestone)	111,358	A++
1.3) Number of U1 children vaccinated with pentavalent 3 doses	Expected	27,916	132,516 (UNICEF under 5)	160,432
	Achieved	33,303 (19% above milestone)	162,132 (22% above milestone)	195,435	A+
1.4a) Number of U5 children (CU5) and Number of pregnant and lactating women (PLW) receiving a package of nutrition specific interventions.	Expected	Number of U5 children: 260,000 / Number of PLW: 58,500	UNICEF no target set	318,500 (Change)
	Achieved	CU5: 281,472 (8% above milestone) / PLW: 65,610 (12% above milestone)	CU5: Not included / PLW: 466,515	347,082 / (Change)	A
1.4b) Number severe acute malnutrition (SAM) treatment	Expected	3,697 (Change)	N/A	3,967 / (Change)
	Achieved	7,703 (108% above milestone)		7,703 / (Change)	A++
1.5) Number of women attending 3+ ante-natal visits	Expected	18,634 (Change)	Target set for ANC 4 (not 3+)	18,634 / (Change)
	Achieved	25,547 (37% above milestone)	8,9763	25,547 / (Change)	A++
1.7) Total Number of outpatient visits	Expected	496,742 (Change)	N/A	496,742 / (Change)	A+
	Achieved	551,518 (10% above milestone)		551,518 / (Change)
[2] Progress under UNICEF relates to service data for Oct-Dec 2017 from the £5m 2017 bridge funding and Jan-Aug 2018 data from the £3m extension provided for Jan-Sep 2018.

Note.
Due to margin of error in setting service delivery targets (A= up to 10% above, A+=11-30%, A++=31%+)
Inception milestones for SHINE Supply and Commodity security outlined in the narrative below.
A more detailed table including milestones for earlier Annual Reviews is included as Annex 1.

Provide supporting narrative for the score

The A+ score reflects strong performance against Output 1 indicators on delivery of the essential package of health services (EPHS); and positive progress on integrating nutrition and family planning.

The CHANGE programme supports service delivery in a total 90 health facilities and reached over half a million people in Sahil, Somaliland (HPA); Karkaar, Puntland (Save the Children) and Gedo, Jubbaland (Trocaire) between October 2017 and September 2018 (£4.8m disbursed). Strong delivery through CHANGE has continued uninterrupted since the start of SHINE. In the last year they have consistently exceeded targets. The bridge funding to UNICEF has maintained support to much needed services across former JHNP regions. While there have been some issues with the ambition and process to set milestones with UNICEF their reach, across the limited services supported, has been very positive.

Both programmes have seen a high influx of internally displaced people into service delivery areas due to the drought which began in 2016. Partners have managed to effectively work to meet this increased demand. In recognition of this trend DFID agreed additional humanitarian Internal Risk Facility (IRF) funding to Change partners for July 2018-March 2019 to help address this increased demand and expand to one additional district in Gedo. Health support was also included in IRF funding to UNICEF over the same period. This support is captured under the Somalia Humanitarian and Resilience Programme (SHARP).

The next year will see transition to delivery through the SHINE Supply programme managed by Mott Macdonald and a new phase of support to UNICEF. Good progress has been made by both to initiate service delivery in January 2019 with leadership from the Somali Health Authorities on choice of locations and approach. DFID will work to ensure a coherent approach across all service delivery components for the final two years of SHINE.

Trends across programmes

Integration of nutrition and family planning services (Output 1.1a and b)

Under CHANGE progress on family planning has improved with full integration of services into health centres, referral health centres and hospitals in Sahil and Karkaar. Delivery in Gedo is lagging but discussions are ongoing with the Jubbaland Ministry of Health on a phased roll out. The planned partnership with Sahan represents a good opportunity to accelerate uptake. The EPHS UNICEF bridging did not include support to these services but the next phase of UNICEF service delivery, and the SHINE Supply programme both will from January 2019.

Skilled birth attendance (Output 1.2)

CHANGE and UNICEF both exceeded their targets for skilled birth attendance. UNICEF achieved almost double the original target. This reflects a substantial push on institutional delivery driven by the extension of operating hours to provide 24-hour care in many key facilities. This change in approach needs to be reflected in future milestones.

Pentavalent vaccination (Output 1.3)

CHANGE and UNICEF substantially exceeded their milestones. Supplies are supported by GAVI and delivery has been supported by cold chain improvements and uninterrupted supply. CHANGE have also leveraged USAID funding for immunisation and nutrition (see below) outreach services.

Nutrition (Output 1.4)
The greater disaggregation of nutrition information (Outputs 1.1b, 1.4a/b) – a recommendation from the 2017 AR – has helped track progress. CHANGE has exceeded their targets for 1.4a on provision of a basic package of nutrition interventions to pregnant women and under-fives (vitamin A, micronutrients etc). For treatment (1.4b) the milestone was also substantially exceeded, and will need greater ambition next year. Partners were cautious because DFID only covers operational costs but not nutrition treatment supplies under Change but partners have been successful in securing other funding from IrishAid in Gedo and UNICEF in Sahil leading to good results. There have been some challenges in Karkaar but Save the Children has leveraged funding from the drought response. DFID IRF funding has also been used for nutrition (see later). UNICEF bridge funding only included micro-nutrients to pregnant and lactating women. A target was not set due to UNICEF not knowing whether they would secure additional funding to supplement the DFID bridge funding.

Antenatal care (Output 1.5) and Outpatient consultations (Output 1.6)
CHANGE exceeded their milestone for 3 antenatal visits and for outpatient consultations. UNICEF are on track against their milestone for 4 antenatal visits (they did not set a target for 3 visits but demonstrated good progress). The target will be harmonised across service delivery partners in the future.

CHANGE programme
Progress since the last review is closely aligned to the 2017 Annual Review recommendations. These focused on stepping up work on improving quality of care (see output 2), continuing efforts to integrate family planning, recognising the need to respond to spikes in need due to drought and other events, and progressing work with the private sector.

Private sector engagement
After a mapping of private facilities during the Change inception phase a pilot model for implementation in a selected sample of facilities in Sahil and Maroody-Jexx regions of Somaliland was agreed in August 2018. This will see an innovative social franchise deliver the standardised EPHS package with the aim of providing affordable, accessible services through the private sector, under Ministry of Health policy and guidance. The intervention will be carefully monitored to measure the objectives of:
- Increasing overall utilization of health services, contributing to Somaliland Ministry of Health’s Health Sector Strategic Plan
- Contributing to an increase in the overall quality for health services;
- Reducing the burden on the public sector for those with a willingness and ability to pay;
- Providing a platform for cross-referral between the private and public sector; and
- Providing access to private sector health utilization data through the national DHIS2.

This approach draws from PSI’s global experience and also lessons from a pilot in Maroody-Jeex region funded through USAID. It has generated interest from GAVI and PSI, Ministry of Health and UNICEF have agreed to include immunization services in the pilot to provide leanings on the potential of the private sector to expand immunization coverage[3].
[3] PSI presented learnings from the USAID pilot at the GAVI meeting in August 2018. The pilot includes a community demand creation component that is tracking uptake of services by client in public sector health facilities. This model has generated interest by Global Fund and has also led to an agreement with MOHD and UNICEF (GAVI) to include immunization services in the private sector pilot.

#### On the Somaliland Ministry of Health’s request the pilot will also produce case studies addressing the objectives in detail and feed into development of the national public private partnership framework.
UNICEF Bridge funding
The funding to UNICEF was only planned as a temporary measure for 12 months (£5m for 2017) to bridge the contracting and transition to a private management agent for the SHINE Supply component. Further delays meant an extension until September 2018 (additional £3m). In July 2018 a contract was signed with Mott Macdonald, but given the need to first determine locations and then contract service delivery partners a final bridge funding was provided via the humanitarian programme (IRF) to cover July to December 2018.

In 2016 the reduced ‘bridge’ package of services (excluding primary health units, family planning and nutrition treatment services) was agreed to enable coverage across a wide geographic area, formerly covered by the JHNP and not taken up by other donor programmes. This decision was meant to be short-term but its extension has exposed issues with the approach. Where possible UNICEF has used other, primarily humanitarian funds, to supplement DFID bridge funding and provide the full EPHS package but in some places only skeleton provision has been possible. UNICEF has performed well against the narrow services supported (primarily skilled birth attendance, some antenatal care and immunisation) with particularly impressive progress in institutional delivery due largely to an increase in facilities offering 24-hour care. However, the limited ability to have impact with the reduced service package is recognised by both UNICEF and DFID.

New service delivery with UNICEF: Delays in the contracting of Mott Macdonald and reduction of the Sahan budget made additional resources available for the final 2 years of SHINE. Given that the transition of some districts to service delivery support though Mott SHINE Supply leaves some previously supported districts un-covered; and UNICEF’s reach and performance to date and partnership through the commodity security programme, a decision was made in August 2018 to continue supporting UNICEF service delivery. This will take a revised approach learning from the bridge funding and will be fully aligned and coherent with support through the rest of SHINE. This will include:
- A return to delivery of the full EPHS package including family planning, nutrition and primary health units.
- Maximising geographic synergies with other support through SHINE to enable building of health system structures at the regional level.
- Exploring a partnership with the Sahan behaviour change programme.

SHINE Supply (Mott Macdonald)
Finalising the SHINE Supply contract was top priority after the 2017 Annual Review. Despite a 20-month procurement Mott Macdonald began work in July 2018. In future SHINE Annual Reviews SHINE Supply service delivery partners will contribute to results under Output 1. For this review however the following inception milestones were set:
- Agreement on the geographic locations for service delivery support and related resource package;
- Launch of Request for Proposals;
- Agreement of SHINE Supply governance structure;
- Development of value for money and monitoring, evaluation and learning strategies;
- Preparation of draft logframe;
- Agreement on Key Performance Indicators;

Mott Macdonald has made good progress on all of these with the most significant early achievements being the agreement of service delivery locations and associated resource allocations with the Somaliland, Federal Government and Federal Member State Ministries of Health. This was based on agreement of clear needs based criteria, careful analysis and consultation leading to prioritisation of 4 regions and 16 districts correlating with the approximate 2 million target population.[4] The Request for Proposals was launched as planned on 24th September with a schedule to assess bids and agree contracts to start January 2019.
[4] A separate document outlines this process and agreement in more detail. The regions are Awdal (two districts), Togdheer (two districts) in Somaliland; Galgaduud region (two districts); and Banadir Region (ten districts), all within those previously supported by UNICEF/JHNP.

Commodity Security Programme (UNICEF/UNFPA)
The joint UNICEF/UNFPA Commodity Security Programme inception phase (£3m) ran from September 2017 to August 2018. Delays in Mott contracting meant the procurement of supplies to support service delivery through SHINE Supply was not possible, although pre-positioning and planning took place. The inception phase also saw the initiation of supply chain strengthening work captured under output 2.

A review of the inception phase to inform the implementation phase (£12m) saw the following decisions made. These will be reflected in the programme document currently being finalised.
- Procurement and distribution: Recognition that UNFPA does not have a comparative advantage in procurement or distribution of supplies (i.e. UNICEF supply division has long term agreements with all the same suppliers; and UNFPA’s approach to distribution relying on Ministry of Health storage and distribution capacity carries significant risks) led to a decision to have UNICEF implement this element of the programme alone. This will itself contribute to simplifying the supply chain.
- Supply chain system strengthening: This element of the programme will remain joint and the programme document will outline the exact roles based on clear comparative advantage. UNFPA’s role will likely focus on continuing their pre-existing work on the logistic management information system and working to ensure health worker capacity exists to utilise family planning commodities distributed.

Work is also going on to estimate the nutrition and health supplies needed for SHINE Supply supported facilities, and ensure that supplies are ready for service delivery partners in January, while also recognising the need to involve these partners in more accurate forecasting as soon as they are contracted.

Lessons identified this year, and recommendations for the year ahead linked to this output

Change programme
- Outreach services are essential to promoting uptake of key service delivery interventions amongst hard to reach populations with little access to static health facilities. Work to ensure continuation of these after USAID funding stops (February 2019).
- Involvement of the Government is critical to ensuring uptake and sustainability of family planning. This needs to be pursued in Jubbaland to roll out the agreed integrated model.
- A partnership with Sahan will help address barriers to seeking care, including for family planning.
Interest in engaging with the private sector by the Somali Health Authorities is substantial and it is recognised as a critical element of achieving universal health care. Experience from the Somaliland pilot needs to be shared across other Change regions and the country as a whole.
- Review and adjust output indicators for nutrition given their substantial overachievement, and finalise an attribution factor for 1.5b given multiple donor support to treatment.
- Given the challenges in realising long-term nutrition funding for Karkaar, DFID will support the exploring of options after the IRF.

UNICEF Bridge funding and service delivery
As outlined above lessons regarding the limitations of the ‘bridge’ funding package approach will be used to inform a more comprehensive approach, coherent with that through the rest of SHINE, for the next phase of UNICEF service delivery support.

SHINE Supply
- Careful and meaningful engagement of Government has built ownership and support for the programme which needs to be sustained.
- The programme has made fast progress but remains at an early stage. Close management will be required to ensure a smooth move into service delivery implementation as planned in January 2019.

Commodity Security Programme (CSP)
- As outlined above lessons from the inception phase have already been used to re-structure the UNICEF/UNFPA partnership for the implementation phase.
- The last 3 months (July-Sep) have also exposed some tensions between Mott Macdonald and the CSP partners and where lines of responsibility lie between the two. A clear modality for how these two components will work together is being agreed.

Cross-cutting
- Identifying a consistent and reliable denominator population figure to measure utilisation remains a challenge. Population under-estimation leads to over-estimation of coverage figures. This issue along with agreeing shared indicator definitions and methodologies for generating milestones will be looked at by the SHINE M&E Group – see later.
- To counter the risk of fragmentation due to the different service delivery modalities under SHINE DFID Health Advisers will invest heavily in both SHINE and sector governance and coordination mechanisms, and ensuring a shared approach to service delivery between partners.

Output Title	Strengthen government oversight of service provision (monitoring and data use; supply chain systems; health information systems; human resources for health)
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress	Score
Change programme: Monitoring, supervision & data use / 2.1a) % of regions/districts conducting 4 quarterly “integrated” supportive supervision visits.	a) 100% of regions/districts carrying out quarterly Integrated Supportive Supervision	100% (all 3 CHANGE regions conducted joint quarterly ISS with the MoH and implementing partner (IP) in each region.	A
2.1b) % of follow up recommendations from integrated supportive supervision visits actioned.	b) Develop an improved tracking tool for ISS recommendations	Agreed with MoHs pilot of HNQIS tool in Change regions to replace paper tracker currently in use.	A
2.1c) Number of tangible examples of data and evidence being used for decision making and service improvement (milestones will show progression).	c) 3 tangible examples of evidence being used (e.g. for routine planning and budgeting)	Annual planning and review meetings led by the MoH conducted in all 3 CHANGE regions to review EPHS service delivery.	B

Note. Inception milestones for SHINE Supply and Commodity security outlined in the narrative below

Briefly describe the output and provide supporting narrative for the score
Reporting under Output 2 in the 2016 and 2017 Annual Reviews focused on set up activities: provision of UNICEF EPHS bridging support during contracting of the SHINE Supply component, initiation of the inception phase of the commodity security programme and analysis of the status of the health system and EPHS management functions in Change regions. As outlined below work has progressed considerably in recommended areas including in the focusing of the Change HSS work and initiation of supply chain strengthening activities under the commodities programme giving an overall score of A.

The Change programme
Change is most advanced in its specific health systems work contributing to Output 2. Based on a review of gaps and consultation with Somali Health Authorities, partners decided in May 2018 to focus on quality improvement and use of data for decision making and the indicators above were agreed.

Quality improvement: Partners have been conducting integrated supportive supervision activities in all three Change regions (100% achievement of output 2.1). However, a need for an improved system led by district and regional health offices to drive quality improvement was recognised.
- The Health Network Quality Improvement System (HNQIS) – is a digital tablet based tool which enables assessment of health worker and health facility performance. The tool can be aligned to national standards and includes a scoring system, a clear method for recording recommendations and their uptake and a coaching/training function. Data can be printed, shared by email and uploaded to the Somalia Digital Health Information System (DHIS II).
- The system will initially be rolled out in Change regions with the longer term aim of wider national uptake and the harmonization and improvement in the impact of supervision.

Data 2 Action (D2A): The CHANGE programme also recognised that the DHIS II is not being taken advantage of, data is entered but not analysed or used for decision making. Partners are working with the Somali Health Authorities in Change regions to support and build their capacity to use a data-to-action (D2A) approach to review regional level performance. The approach focuses on improving functionality and use of the existing DHIS II platform. It relies on regular review of monitoring data for performance management and promotes data driven, evidence-based discussions and decision making to improve service delivery outcomes. Milestone 2.1 c) was ambitious for this year and better examples of evidence being used for decision making (output 2c) remain limited, and the milestone was ambitious given the use of evidence will be supported by work on D2A and should increase in the coming year with its roll out.

Inter-regional cooperation and learning takes place successfully through CHANGE, although a trip by the Jubbaland Ministry of Health Director General to Somaliland proved very politically sensitive, and engagement is easier in neutral locations.

SHINE Supply
The Output 2 milestone for this Annual Review was the initiation of a rapid Health System Strengthening (HSS) review to inform allocation of the SHINE Supply £2m HSS budget. The review is looking across key health system building blocks including governance and leadership, human resources, information systems, quality improvement, financing and supply chain management. It involves collating existing work and consulting with partners and Somali Health Authorities on their priorities. This process is due for completion by early November. It will recommend investments based on a set of criteria including: need, ability to have impact in the 2 years of implementation remaining and coordination and coherence with other HSS investments through SHINE and other actors. There is the option of providing additional investment to regions receiving service delivery support, and/or working at the State or National level. The review will itself be shared and provide a resource to the sector to help coordinate and inform use of future resources. Priorities will be agreed and reflected in the updated SHINE log frame by December 2018.

Commodity Security Programme
The commodity supply programme inception phase (August 2017-18) initiated work on the supply chain strengthening element of the programme and planned for the implementation phase. This included meeting the following inception milestones:
- Development of the Health and Nutrition Supply Chain Sector Strategy that the commodity security programme will contribute to.
- Setting up Supply Chain Technical Working Groups (FGS, Somaliland and Puntland) to guide implementation of the Strategy.
- Regional level training of trainers on the Logistics Management Information System (LMIS) to support further cascading of the system, and distribution of LMIS tools.
- Capacity development and mentoring of Ministry of Health leadership and supply management staff.
- Targeted warehouse improvements.
- Development of standard operating procedures (SOPs): medical and nutrition supplies management guide, distribution and logistic management tools (e.g. way bills).
- Institutionalisation of supply chain management through discussions to integrate it into pre-service curricula for doctors and nurses.
- Development of draft indicators for inclusion under Output 2 for the implementation phase which will be finalised and included in the updated SHINE log frame by December 2018.
- Reducing lead times (time from order to delivery)
- Improving forecasting and quantification of supplies
- Improving efficiency and government ownership of the supply chain.

Lessons identified this year, and recommendations for the year ahead linked to this output
Change programme
- Change partners experience has revealed the need to support quality of care through improvements to supportive supervision and use of data. Roll out of both the HNQIS and DHIS II D2A tools needs to be accompanied by capacity building, mentoring and support of MoH staff and monitoring of impact. This will provide important evidence for their value and inform longer term institutionalisation.
- DFID has and will continue to encourage partners across all the SHINE components to incorporate the HNQIS and D2A approach within programming to promote linkages and coherence.

Cross-cutting
- Indicator 2.1 needs revising as 100% has been achieved. This should now focus on roll out of the HNQIS tool. Updated indicators and milestones will be agreed as part of the revision of the SHINE logframe by January 2019.
- Output 2 will also be updated to include indicators to track work under SHINE Supply and the Commodity Security Programme.
- Given the multiple health system strengthening investments across SHINE DFID will work on a cross-component health system strengthening plan to coordinate and synergise efforts.

Output Title	Develop and support scale up of proven behaviour change interventions (healthy behaviours include health service utilisation)
Output number per LF		3	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress	Score
3.1 (Extended) Inception phase completion	-Validation workshop and other deliverables in 3-month action plan. / -Programme approach and theory of change developed and agreed upon	Achieved	A
3.2 Number of interventions designed, tested, and piloted/evaluated (ready for scale up)	20 prototypes designed	Achieved	A
	At least 3 partnerships with implementing partners in place for testing and piloting (each having tested at least 2 interventions by the end of September 2018)	Not achieved. Starting October 2018 PSI will partner with at least 2 implementing partner to pilot and test designed prototypes.	C
3.3 Number of evidence generation and synthesis products and processes used in prototype development (to improve focus on prototypes that work)	A minimum of 12 evidence generation or synthesis products (i.e. Number of documented insight generation processes, Prototype testing processes, Innovation Labs reports, Discovery days) used in prototype development.	9 (validation workshop report, prototype journey, prototype tracker, innovation lab reports birth spacing, nutrition, antenatal care, first prototype implementation manual, little book of learnings, behavioural insights slide deck)	B

Provide supporting narrative for the score
Managed by PSI, Sahan is an adaptive programme aimed at designing, testing, piloting and gathering evidence for new approaches to increase access to and utilisation of reproductive, maternal and child health and nutrition services and promote healthy behaviour. It uses a human centred design approach, applying behavioural science to understand people’s behaviour through observation and immersive research; combining this with expert knowledge, and working closely with users themselves to design interventions or ‘prototypes’ and test and iterate them before piloting at greater scale to measure impact. PSI is working with the organisation ThinkPlace to help do this.

After a slow start focusing on formative assessments (including social network analysis, ethnographic research, information ecosystem analysis and landscape evidence review) a 3 month action plan (Sep-Nov 2017) was agreed to get endorsement for the findings of the studies, the proposed human centred design approach and approach for contracting sub-implementing partners. This was completed with a validation workshop in November 2017 and a programme approach and theory of change agreed in January 2018.

Designing of interventions continued with field research and a series of successful consultation and design workshops generating ideas. These were subsequently turned into prototypes and captured on a tracker representing a pipeline of early stage interventions. However, progression to testing and piloting these interventions with implementing partners stalled. Early market engagement exercises were not followed through to partnerships due to capacity issues, and reticence to sub-grant the funds. A decision in February to approach key actors in the sector (e.g. Save the Children, UNICEF) to work together on addressing their specific issues and needs on demand creation both through new interventions or the tweaking and improving of existing ones, did not get traction either.

After repeated encouragement and support from DFID to progress to field testing but little movement and recurrent under-spend, the weakness of PSI in both its geographic (largely Somaliland) and service delivery (only small scale direct work with private sector) footprints became increasingly apparent. In August 2018 a decision was made to reduce the budget and ensure PSI partners with SHINE service delivery partners (through Change, SHINE Supply and UNICEF) to enable field testing and piloting.

The last quarter (July-September 2018) saw the first intervention developed and packaged for pilot. The mother to mother (M2M) prototype represents the tweaking of a traditional community education intervention to focus on 1:1 sessions at home, using mothers to reach other mothers, and focusing specifically on non-users of health services. After testing by PSI a pilot will begin on 1st October 2018 with HPA to look at impact of the approach on service utilisation.

It is primarily the failure to move more interventions from the design stage to field testing and piloting and therefore generation of evidence that has determined the score of B.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Weaknesses in PSI’s ability to deliver the field elements of the programme alone and associated delays in moving to testing and piloting interventions led to a decision to enforce partnerships with SHINE service delivery partners. Progress in these partnerships, and others e.g. for media work, is critical to programme success and will require close DFID monitoring.
- DFID has worked with PSI on a costed work plan for the remainder of SHINE, including the grants to partners to help avoid further delays. This still allows flexibility in the exact prototypes to be piloted but provides the structure necessary to enable delivery of the field testing element of the programme and for DFID to hold PSI to account.
- Recognising the importance of the monitoring and evaluation of piloted interventions, the specific expertise required to effectively do this for behavioural interventions and learning from past issues with PSI capacity DFID will explore a partnership with the Busara Centre for Behavioural Science and contracting this support through DFID’s Monitoring and Evaluation of the Somalia Humanitarian portfolio (MESH II) programme.
- Turnover in senior Ministries of Health staff has made orientating and building ownership by staff time consuming and challenging. However, enthusiasm and interest in the programme is high and to mitigate turnover understanding and ownership will be spread more widely.
- Initial milestones for testing and piloting proposed by PSI for future years were very low, a greater focusing of the reduced budget has resulted in revisions to increase ambition in this area. As with the other SHINE components the log frame indicators will be reviewed and finalised by January 2019. As well as successful progress from designing, testing to piloting it will be important to capture those that fail and the reasons for this and to publish findings that add to the evidence base on demand creation. Output 3.3. also needs to focus on quality as well as quantity of products.

Output Title	Promotion of a learning culture in SHINE to inform the wider health sector
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress	Score
Practical examples of SHINE partners sharing knowledge and best practices leading to a new activity/initiative by another stakeholder (may include health sector tools, guidelines, case studies, webinars, event reports, best practice guides and other outputs).	At least 5 examples where SHINE partners/others shared knowledge/best practices in ways that led to a new activity/initiative) / a) Change=2; b) Sahan=2; c) CSP =1; d) SHINE Supply =0	a) Change: 5 practical examples shared / b) Sahan: 1 Presentation of approach at Social Behaviour Change Conference (April 2018) / c) CSP: 1 Standard Operating Procedures developed / d) SHINE Supply: 0	A

Briefly describe the output and provide supporting narrative for the score

Reporting for the 2016 and 2017 Annual Reviews under Output 4 focused on setting up the modality for monitoring, evaluation and learning with agreement to incorporate it into the wider Monitoring and Evaluation of the Somalia Humanitarian (MESH) programme and some engagement with partners in place on their log frames, theories of change and learning agendas. As recommended SHINE has worked more closely with MESH in the last year, and partners have begun to focus their learning agendas, but due to the staggered start some are more advanced than others. Very strong progress under Change is instrumental to the A score.

Change programme
Change has provided 5 examples of lessons from the programme concretely influencing others:

- During the DFID visit to Berbera in May 2018 the Somaliland Ministry of Health recognised the flexibility and innovation of the Change programme in Sahil, the strength of government collaboration, the regional approach and effective nutrition integration (with UNICEF) citing it as a model of best practice. The approach is included as a strategic priority in the HSSP (2017-2021).
- In Puntland the Change delivery model in Karkaar has informed the roll-out of a standardized EPHS model across the other regions of Puntland and elsewhere. This includes the Community Health and Accountability Programme (CHASP) supported by Sweden and Switzerland and implemented by Save the Children. A team visited Change supported facilities and held meetings with the district and regional health offices in Karkaar to inform the programme.
- The Change team led by PSI has had several meetings with Mott MacDonald to share lessons learnt on implementing services and strengthening systems in Change supported regions/districts. These experiences have directly influenced the approach outlined in the request for proposals launched under the SHINE Supply programme.
- The private sector model, initially piloted by PSI with USAID funding in Maroody-Jeex and now being supported in Sahil through Change generated interest from GAVI. The Somaliland Ministry of Health and UNICEF have now agreed to include immunisation services in the package to provide learnings on the potential of the private sector to expand immunisation coverage.
- The Somali Standard Treatment Guidelines were developed in English for all 4 levels of the health system. In Gedo Trocaire recgonised the need for a Somali version, particularly at the primary health unit level manned by Community Health Workers. They made a translation and have submitted it to the Federal and Jubbaland Ministries of Health for endorsement. Once agreed it will be made available more widely filling an important gap.

Sahan programme
The Sahan programme has defined a clear learning agenda and there is a lot of anecdotal evidence of its human centred design approach generating enthusiasm and influencing others in the Somali health sector and more broadly. To date the acceptance of two abstracts for presentation at the Bali International Conference on Social Behaviour Change (April 2018) and considerable feedback and discussions stemming from these represents the most concrete example of sharing learning. The next year should see many more examples of this, including sharing findings not just on the approach, but evidence of impact in the field.

SHINE Supply Programme
No milestone has been included due to the early stage of the programme but there is some very early indication of increased government ownership and progression in thinking on allocation of resources due to their involvement in determining the geographic locations for service delivery. Evidence of this includes Ministries of Health defending the choice of locations at the RFP launch and the FGS calling a meeting with key partners to iron out issues with coordination.

Commodity Security Programme
The inception phase saw development of Standard Operating Procedures for supplies management that have been taken up by other sector stakeholders.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The importance of early and genuine government consultation to build joint ownership has been demonstrated by the SHINE Supply programme. DFID will ensure this approach is maintained and shared by other components and will finalise SHINE Supply governance structure and modality for ensuring government involvement across all SHINE components (by December 2018).
- Joint SHINE partner meetings to ensure linkages, coordination and sharing of lessons between the components have proven critical particularly due to the complex programme design and these will be continued on a regular basis and linked to wider governance structures.
- SHINE will take full advantage of MESH II to support an integrated approach to monitoring, evaluation and learning across the components.
- Challenges in coordination of SHINE partners are a microcosm of the wider health sector. As the largest health donor DFID will step up to co-chairing the Pillar Working Group on Social Development and participate fully in the health, nutrition and WASH sub-working group.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The programme’s theory of change in the business case rested on 4 basic assumptions:

1. Investment through a mix of interventions and mechanisms allows for increased geographical reach, empowerment of both government and communities, combined with spreading of risks. A mixed delivery will enable organisations to focus on their areas of comparative advantage and encourage competition on efficiency and effectiveness. A single oversight body will then promote coherence and complementarity between components.

Assumption 1 has proved more difficult in practice than in theory. While different organisations do have comparative advantages to a degree it is not clear:

1. That those chosen to deliver a given component were always the best placed to do so (e.g. there have been substantial issues with PSI’s capacity to deliver the Sahan programme); and:
2. That the supposed focus on comparative advantage of each agency justifies the resulting highly complex set of partners and coordination issues. For example the business case:
- Looked separately at how a private agent would best deliver contracting of services and UN agencies procurement of supplies but gave no consideration to how the two would work together, despite this being fundamental to success.
- Included two different approaches to service delivery (Change an NGO consortia and SHINE Supply a private management) with a desire to keep Change as a separate structure to test new approaches. Arguably this was retrospectively justified by the delays in Mott’s contracting but does not promote coherence long term.

The staggered start of the different SHINE components and in particular the delayed contracting of SHINE Supply has exacerbated issues. For example:
- The idea of an oversight body for coherence has only become a possibility in year 3 now that all partners are finally on board.
- Delays in contracting Mott Macdonald led to temporary bridge funding to UNICEF which is now being overhauled and extended to the end of SHINE given under-spend elsewhere due to delays. This means 3 service delivery modalities are now being used but it will enable comparison to inform the best and simplified modality for future support.

2: Improved quality and standardization of EPHS increases access to services. A focus on breadth (including nutrition and family planning) and quality could be first trialled through ‘an embedded EPHS’ model in the Change programme.

Evidence through the Change programme supports this assumption. Lessons to date from this approach are being used to inform SHINE Supply and UNICEF service delivery, and work is going on to further improve quality in Change regions. Lessons from which will also be shared.

3: Tackling key barriers to access will increase demand for health services. A greater focus on demand side barriers and wider social determinants will both prevent ill health and increase use of services when needed. Piloting and building evidence for new approaches, with a focus on the community level will improve the cost-effectiveness of demand side interventions.

Delays in the Sahan programme moving to piloting new interventions and measuring their impact means there is to date limited specific evidence from SHINE to back up the assumption. However, global evidence remains strong as does the intention to test this assumption.

4: Improved supply and demand of proven health interventions will increase utilization of quality care and reduce morbidity, disability and mortality.

This assumption remains valid and is backed up by substantial global evidence and experience from Change to date. The piloting of demand creation interventions in SHINE service delivery locations over the next two years will provide substantial further evidence on a comprehensive demand and supply approach.

In February 2018 a MESH supported M&E workshop with SHINE partners led to an updated theory of change, focusing on assumptions 2-4. The report[5] also discusses the relative emphasis needed on demand and supply to gain maximum impact and questions whether sufficient focus is being placed on the former. This will be further reviewed and updated by the M&E working group now that all partners are on board.
[5] DFID Somalia SHINE Draft M&E Framework MESH. March 2018.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

As outlined in the theory of change SHINE works on the premise that:
- Provision of quality services (Change, UNICEF, and as of January 2019 SHINE Supply);
- Accompanied by demand creation and behaviour change interventions (ongoing activities by Change and UNICEF partners, and partnerships with Sahan to trial new approaches); and
- Additional systems investments:

Will increase utilisation of quality health services and other healthy behaviour (at the outcome level) and ultimately improve health status (at the impact level).

Service utilisation is at the heart of the outcome level indicators in the SHINE log frame. In the next two years of SHINE this indicator will be accompanied by measures of quality, government ownership and changes in other health related behaviours, which will lead to improvements in health status at the impact level. These are being finalised by the M&E Working Group.

The Change programme has had a demonstrable impact on utilisation and is moving on to improving and measuring quality.

Outcome	2018 milestone
CHANGE	Expected	Achieved
Supply: Health Facility Utilisation Rates Numerator -Total health facility visits in a year; Denominator - Total catchment population	0.6 outpatient visits per year per person	0.91 outpatient visits per year per person

The temporary and reduced breadth of the UNICEF bridging support to service delivery has limited performance at the outcome level but support for 2019 and 2020 will see a renewed focus on quality and comprehensive service delivery, taking lessons from Change. The move to ensure formal partnerships between Sahan and SHINE service delivery partners will also enable measurement of the uptake of services and healthy behaviours at the impact level due to specific demand creation interventions.

Despite the complexity of the programme design the interventions are aligned to the theory of change and contributing to the expected outcomes and impact. In the final two years with all components delivering, a focus will be placed on linkages and coherence of approach to maximise impact of the interventions through different components across SHINE.

Given past experience work is already beginning to think about how to reflect lessons from SHINE’s design, procurement and implementation in development of its successor.

Explain major changes to the logframe in the past year (1/2 page)

The logframe required considerable updating (completed in May 2018) during the review period to ensure it captured developments in the work under each component. With the all partners only recently on board, final revisions will be made by January 2019.

Annex 2 is a table highlighting the key changes that the logframe underwent during the review period:

Describe any planned changes to the logframe as a result of this review (1/2 page)

A SHINE partner meeting on 2nd October agreed that given that from January 2019 multiple partners will contribute to the same indicators (e.g. service delivery), and some elements are still being finalised (e.g. SHINE supply health system work) an M&E group with a representative from each component will work between October and December/January 2019 on a harmonised SHINE logframe, shared indicator definition sheet, approach to defining milestones, clear log frame to theory of change narrative, and plan for moving reporting online via MESH. It will also ensure DFID can monitor the comparable value for money of different partners supporting similar interventions, particularly unit costs for delivery of services. The Group will be chaired by DFID and supported by MESH.

More specifically the M&E group will also consider:
- Inclusion of contraceptive prevalence rate (CPR) at impact level (although data constraints exist)
- Best impact measure of collective system strengthening efforts.
- Measurement of population for denominator to measure service coverage (look at using new UNFPA figures).
- Measurement of additional family planning users under output 1.2 (to align with central reporting)
- Including measurement of default and death rates for SAM treatment under 1.4b (align with central reporting guidance).
- Under output 3.1 include capturing prototypes that fail and do not progress, differentiate by track 1 or 2, and inclusion in a prototype system
- Under output 3.2 clearly define how this differs from 4.1 on learning.
- How to improve gender and disability disaggregation
- How to improve monitoring and use of value for money (see below).

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The SHINE VfM approach set out in the Business Case focused on increasing service delivery efficiencies by continuing to shift away from simple input and economy measures to focus more explicitly on the cost drivers and also track data on unit costs of EPHS delivery.

An analysis conducted by DFID with the Health Consortium for the Somali People (HCS) – now the Change Programme - in 2014 showed the costs of EPHS delivery in Somalia to be USD 5.88 per capita which is comparable to similar fragile countries of Afghanistan (USD 5.50), DRC, South Sudan, and even Ethiopia, Kenya, and Rwanda (which range between USD 5-12).

Since this analysis Change partners have worked out their budget by output which has enabled better tracking of spend to results and monitoring of variable costs. Staff and supplies are key cost drivers. While the former has been difficult to reduce given resistance from government on increasing their contribution, harmonisation with government pay scales has helped. Progress has been made on more efficiently competitively procuring supplies. This work and trends in increased service utilisation have brought down the unit costs of service delivery under Change. A Change budget realignment is taking place so that savings are converted to greater service delivery.

Reduction of the Sahan budget and reallocation to service delivery through UNICEF will contribute to an increase in overall results for the same total budget. Removal of UNFPA from procurement under the Commodity Security Programme and upfront bulk procurement by UNICEF has also improved value for money of this component.

In early 2018 a value for money framework across SHINE components was agreed which includes service delivery unit costs, amongst other measures of economy, efficiency, effectiveness and equity. Change have begun to report against this template but as other partners come on board quantitative comparative reporting will be strengthened.

4 Es	Key indicators	Monitoring
Economy / (Lowest price for Inputs of required quality)	- Consultant rates / - Per Diem rates / - Cost of key commodities	Quarterly budget reporting / Quarterly budget reporting / Reported annually (at Annual Review)
Efficiency / (Inputs produce Outputs of required quality for lowest cost)	- Unit cost for EPHS (breakdown by service) / - Ratio admin costs/total other costs and/or total budget to number reached. / - Lead time for commodities (planning to arrival in country) / - Unit cost per prototype	Report bi-annually (end Sep, end March) / Quarterly reporting / Quarterly reporting (log frame indicator) / Quarterly prototype tracker review
Effectiveness / (Outputs achieve Outcomes)	- Stock outs (monthly at facility level -focusing on key tracer drugs) / - Government leadership and ownership / - Unit cost per DALY averted / - Health service utilisation rates	Quarterly reporting (log frame indicator) / Quarterly reporting (log frame indicator) / Report bi-annually (end Sep, end March - CHANGE) / Quarterly reporting (log frame indicator)
Equity (fair distribution of benefits)	- Disaggregated service use data / - Choice of implementing areas / - Prototype behaviour change power	Quarterly reporting (log frame indicator) / TBD during SHINE Supply inception phase. / Quarterly prototype tracker

Mott Macdonald has presented their budget and monthly expenditure reports according to their outputs, which will help track spend, and the commodity security programme will also adopt this approach. This will enable shared indicators and allow tracking and comparison of performance across the components. A comparison of key service delivery unit costs across the different programme modalities (Change- NGO consortium; SHINE Supply – Private management; and UNICEF – UN delivery) will be top priority to inform future support.

The SHINE M&E Group will review the value for money framework as part of their objective to harmonise monitoring across components and look at how best update the earlier analysis on service delivery unit costs.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

All costs and outputs remain in line with the assumptions and estimates in the SHINE Business Case. Analysis and experience to date shows that the Somali EPHS is an effective approach for delivery, with positive service delivery results[6]. This is supported by wider evidence that using an ‘Essential Package’ approach to health service delivery, with a strong focus on reproductive, maternal and child health interventions, is effective in tackling the major health challenges[7].
[6] The SHINE BC includes detailed analysis on the efficiency and effectiveness of EPHS delivery in Somalia and overview of the different programmes that have supported EPHS roll out in Somalia. The two main mechanisms have been JHNP and HCS, both DFID funded.
[7] It is important to acknowledge that Somalia is still in the early stages of roll out of the EPHS, following over 20 years of humanitarian provision and unsystematic short term support to health.

Given the slow start it is only now that all components are entering implementation and it is appropriate for an increased focus to be placed on VfM with final agreement of shared indicators and close monitoring planned as outlined above.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
Overall risk rating: Moderate

Overview of programme risk

The overall residual risk rating for the programme remains moderate and all specific risks are being closely monitored and mitigation actions have been taken appropriately. All five components of SHINE are now operational with the following partners on board: (PSI-CHANGE, PSI-Sahan, Commodity Security- UNICEF/UNFPA, UNICEF Bridge/Service delivery and SHINE Supply –Mott Macdonald). Each partner maintains their own component specific Risk Register to ensure that the risks are regularly monitored and risks reported quarterly so as to feed into the overall SHINE Risk Matrix.

A slow inception phase of the Sahan programme and delayed procurement of Mott Macdonald presented significant risks to programme set up and delivery which required specific mitigation through the UNICEF bridging support.

Operational and Context (including conflict): Overall this category of risk has been flagged as moderate. Volatility in the security situation especially in Southern Somalia means it remains a high risk environment. While recognising the widespread fragility and high needs SHINE does not focus on the most unstable regions of Somalia and works through a variety of delivery channels, with organisations experienced in humanitarian delivery. With these mitigation measures in place the risk of deterioration in security and access creating an unacceptable safety risk for implementing partners is possible but we are in a strong position to maintain continuation of service delivery under all but the most serious deterioration of circumstances.

Experience shows the highest risk lies around the management of valuable medical supplies. There have been examples of theft during transit by road, and in some circumstances air lifting is used to mitigate this. Al Shabab have also occasionally looted health facilities for supplies but SHINE partners.

In 2017/18 the drought posed a high risk of malnutrition among women and children and DFID responded quickly to provide humanitarian funding to our health and humanitarian partners to avert possible effects of the drought. DFID and partners will continue to monitor the situation in 2018/19 when flooding is predicted and for any other adverse environmental effects so as to be able to respond effectively to meet emerging needs.

A delay by several months to the OJEU process for the procurement of a Management Agent to manage the Supply component posed a major risk for the programme being able to deliver health services in the regions earlier anticipated. However, bridging support to UNICEF was provided in 2017 to minimise the impact of the delays. An extension of this was provided from Jan-to Sept 2018, and humanitarian IRF funding leveraged to continue services until December 2018 and provide additional emergency health support. The Mott Macdonald SHINE Supply contract started in July 2018 and will only begin EPHS service delivery in January 2019.

The iterative and adaptive nature of the Sahan demand creation programme has required close support and there is need for constant review and management of risks to ensure delivery in the coming year. The slow uptake of funds has been managed by reducing the overall budget which will be used to continue wider support to health services through UNICEF to the end of SHINE.

The politics remains complex. While the FGS has committed to strengthening governance structures to incentivise peace and stability, relations with the FMS remain turbulent. The inclusion of Somaliland adds a further complicating factor in managing government involvement in the governance of SHINE. Work is going on to work out the best governance structure for the remainder of SHINE now that there are multiple components working across the country. DFID continues to work closely with Somaliland, FGS and FMS to ensure their leadership of the programme.

Fiduciary/Financial Risks: Overall this category of risk has been flagged as possible and its impact major, however adequate mitigation measures have been put in place, reducing the residual risk to moderate. This risk if not properly mitigated could severely affect the achievement of the programme’s objectives or its efficiency if funds were not utilised for purposes intended.

Our funding to the UN (UNICEF, UNFPA) for the Commodities programme and bridging has been through separate MoUs after due diligence assessments to both. An updated UNFPA DD is being worked on jointly with the governance team.
UNICEF also has fiduciary safeguards in place as per their rules and procedures to enable the thorough management of downstream partners. They have had a few fiduciary incidences involving loss of supplies and the programme team has worked with UNICEF in addressing these and instituting measures to minimise any repeat. UNFPA will no longer procure supplies due to their supply chain management and reliance on the Ministry of Health being deemed too high risk.
The UN’s stringent expenditure reporting processes have provided information of funds utilised and any balances held so far. Audit statements received from UNICEF give no indication that funds have been spent inappropriately. We expect an audit statement from UNFPA by Dec 2018.
In the CHANGE and Sahan programmes, both managed by PSI, fraud and corruption are mitigated through financial, accounting and auditing procedures and any issues raised with down-stream partners at quarterly meetings. A due diligence was conducted on PSI and a number of partners in April 2016 to check financial management, expenditure control systems and strengthen the internal audit capacity of implementers. PSI was rated as having strong governance systems in place both at headquarters and at the Somalia country level, though was requested to broaden the scope of the corporate risk matrix beyond security risk. PSI was also rated as having good internal control and financial systems in place with sound policies in place; past audit reports were unqualified and revealed a healthy and smooth cash flow.
Despite this a vehicle and some medical supplies allocated to a downstream partner were reported as missing. The team has put in place more robust mitigating measures with PSI, the concerned partner and the wider consortium members in order to stem avenues where fiduciary related incidences may occur; and the DFID team continues to closely monitor the situation – including regularly encouraging partners to report on fraud.
The SHINE programme is subject to Third Party Monitoring through the verification of a number of activities in Somalia. Third party monitoring of Change has been taken forward initially through Learning and Monitoring Programme for Somalia (LAMPs) but a plan is being made to transition to the Monitoring and Evaluation for the Somalia Humanitarian Programme (MESH) to join the other components that are just beginning. Third party monitoring has proved very useful especially in the hard to reach areas where project monitoring may be limited. For Change the findings have been useful in identifying requirements for rehabilitation related to infrastructure (WASH, electricity installation, gender disaggregated toilets, repair of roofs/walls of facilities following the Cyclone in May, etc.) the findings have been discussed with partners to help define a rehabilitation plan to improve infrastructure in line with improved access to health service delivery. The plan has informed the rehabilitation work funded under the IRF as well.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery against planned timeframe

There has been varied performance in delivering against planned timeframes across SHINE.

1. The CHANGE programme is now into the third year of implementation after completing a 9 month inception phase (April-December 2016); and its delivery partners have successfully maintained service delivery. While there were challenges in mapping out how best to support government oversight, a clear implementation plan is now in place.
2. The Sahan programme had an extended inception period, and has subsequently been slow to move into partnerships to test interventions in the field. This has affected its ability to utilise the full budget leading to a decision to reduce this to £8m.
3. The Supply Component was delayed, with a contract between DFID and Mott Macdonald signed in July 2018.
  1. The mixed delivery approach was approved end September 2016 after a longer than expected early market engagement process and extra time to ensure government support of the approach.
  2. The OJEU process for the Fund Manager initiated in October 2016 was expected to take 12 months but took longer with the contract approved by the Minister and Cabinet Office in June 2018. To ensure service delivery continued, the SHINE UNICEF bridging support was extended until Sept 2018 and further support provided to UNICEF from humanitarian funding until December 2018 to avoid service interruption.
  3. The Commodities Security component call for proposals took place in November 2016. The process was delayed (UNICEF initially refused to participate as a backlash from closure of the JHNP and lacked a Chief of Health until June 2017); MoUs were signed with UNICEF and UNFPA in August 2017 who have just completed a year of inception and are due to submit a programme document in October to cover the rest of SHINE.
  4. Delays in the Supply component and reduction of the Sahan budget have enabled a partnership with UNICEF on service delivery to be extended until the end of SHINE. This will move away from bridging and provide a comprehensive approach aligned with the other service delivery components.
4. Initial plans to use the Global Evaluation Framework Agreement (GEFA) for Monitoring and Learning (M&L) were put on hold while it was re-tendered. In the meantime, a decision was made in 2017 to integrate SHINE into the humanitarian programme’s monitoring through MESH. Initial work to update the SHINE programme log-frame and M&L approach is provided under the MESH I programme that (ended in Sept 2018). Going forward SHINE M&L will be fully integrated and implemented through the MESH II programme that is expected to start in December 2018.

Performance of partnership (s)

The SHINE programme took on key lessons from DFID’s previous health programmes: Health Consortium for the Somali People and JHNP[8] and opted for a mixed delivery mechanism aiming to benefit from the comparative advantage of NGOs, UN and a Private Management Agent and the flexibility this range of partners brings.
[8] Refer to HCS PCR completed in September 2016 and JHNP PCR completed in December 2017.

SHINE partners include a consortium of NGOs led by PSI for the Change programme; PSI also implements Sahan; a Management Agent (Mott Macdonald) to manage the implementation of the SHINE Supply component; UNICEF/ UNFPA implementing the Commodity Security Component and UNICEF providing additional service delivery. The M&E component is being taken forward through the privately contracted MESH consortium.

SHINE aims to leverage the specific expertise of different agencies (e.g. UNICEF procurement and logistic capacity, Mott Macdonald contract management, and NGOs flexibility and adaptiveness). The overall approach has led to a complex set of partnerships although efforts are being made to simplify and streamline management of these (e.g. reduction in UNFPA’s role, work on overall SHINE governance structure). DFID has a good relationship with all partners, and given the fractured relationship with UNICEF at the end of the JHNP this reflects significant progress. There are however teething issues with the relationship between partners, in particular working out a modality for Mott Macdonald and UNICEF to work together; and the best way for all SHINE components to engage with the Somali Health Authorities. Under the new service delivery money a particular effort is being made to address issues the Somali Health Authorities have with the way UNICEF operated under the JHNP. The bigger politics also complicates things with Somaliland pushing for a separate governance mechanism, and the FGS wanting to oversee all FMS, but Puntland not accepting being treated on par with the others. Work is taking place to find the best solution.

There have also been issues with PSI’s capacity. The Inception phase for Sahan and Change revealed the need for PSI to strengthen their human resources to deliver both programmes. Despite progress PSI has still carried gaps for extended periods of time hampering delivery and response time. The Deputy-Country Representative is currently doing a good job of driving the programme while a new lead is recruited. DFID has insisted on a workplan and budget that can be monitored for the length of the programme and is carefully scrutinising progress. SHINE Supply will be the first time that private management agent is being used to manage a health programme in Somalia. Value for money and performance will be carefully managed to inform future programmes.

Asset monitoring and control

The partners each manage a DFID specific asset register for all equipment procured for use within the health facilities, the SHA offices and for programme operations. All projects are expected to update DFID on the asset registers during their quarterly reporting.

Quality of financial management

DFID is the sole donor to all five on-going components (CHANGE, Sahan, SHINE Supply, Commodity Security, and UNICEF Bridge/service delivery) of the SHINE programme. CHANGE and Sahan are Accountable Grant Arrangements, while the EPHS Bridging Support and Commodity Security Programmes are MoUs to the UN and the SHINE Supply component a contract with Mott Macdonald.

PSI has requested for advance payments for CHANGE and Demand, highlighting their inability to pre-finance the programmes. PSI struggled with accurate forecasting during the inception phase of Sahan but constant monitoring by DFID has enabled management of any drops in forecasts. The slow inception phase of Sahan meant PSI was not able to present accurate forecasts in the FY 2016/17 and 2017/18, dropping approx. £2.8m from this year’s forecast and a total of £6m since the programme start date. This delayed implementation prompted the team to review the funding to this component and explore reallocation to UNICEF. DFID has disbursed £26.9m at the end of September 2018 and is due to disburse a further £13m before the end of December.

Total Budget: SHINE Main Component Breakdown

SHINE	Programme Name	Budget end Sep 2017 £m	Budget end Sep 2018 £m	Total spend up to end Sep 2018
1. Supply
	UNICEF EPHS Bridge (end September 2018)	8	8	£8m (all disbursed)
	SHINE Supply (Mott Macdonald)	20	20	£414,555 disbursed
	Commodity Security Programme (UNICEF/UNFPA)	15	15	£3m disbursed (£8m forecast for November)
	CHANGE[9] (PSI managed)	27	27	£13,681,692m disbursed
	UNICEF service delivery	N/A	11	£5m forecast for Dec
2. Demand	Sahan demand creation (PSI managed)	16	8	£1,802,204m disbursed
Un-allocated (taken off Mott contract)		3	N/A	N/A
TOTAL		£89	£89	£26.9
[9] Community Health and Nutrition through Local Governance and Empowerment (CHANGE)

Date of last narrative financial report(s)	PSI (SAHAN and CHANGE)15th Nov; Mott Macdonald 1st Nov; UNICEF bridge report 9th Oct; UNICEF/ UNFPA commodities Oct 18.
Date of last audited annual statement (s)	PSI Sept 18; UNICEF August 17 (available on UNICEF website); Mott N/A as component has just started.

MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

This Annual review has drawn on partner data from the quarterly reports from both the CHANGE and Sahan programmes, six monthly UNICEF EPHS bridging reports, monthly SHINE Supply reports (since July) and the inception report of the Commodity Supply Programme.

During the review period, DFID has conducted regular consultations and feedback sessions with the Somali Health Authorities and Somali health sector donors in Nairobi, Mogadishu and Hargeisa. These consultations have been key to ensure that the views of government and key stakeholders are fed into the implementation of SHINE.

Across Change supported sites the LAMPS programme has undertaken third party monitoring, talking to beneficiaries, health staff and reviewing facilities. This feedback has been communicated to partners and enabled improvements in delivery. Additionally, a field visit to Berbera in the Sahil region of Somaliland enabled the DFID team to see the work of Change first hand and better understand the approach and progress.

MESH provided support to update the logframe and theory of change during early 2018 and under MESH II will provide a wider range of support to SHINE, including finalising the log frame, providing third party monitoring of all components and providing rapid evaluation support to the piloting of interventions through Sahan.

There will be continual documentation of key lessons as the SHINE programme progresses.

Evidence (1/2 page)

As reflected in the theory of change strong evidence underpins the design of SHINE and its focus on delivery of services, building systems and government oversight and generating demand for services. In turn through the indicators in the log frame SHINE is contributing to the evidence base for investments in each of these key areas and ongoing learning is fed back into programme implementation and shared with other stakeholders. The SHINE M&E Group, supported by MESH will ensure opportunities for using and generating evidence across the components. The Somalia Health and Demographic Survey (due in late 2019) will provide a wealth of data to help with monitoring the programme.

Learning (1/2 page)

Output 4 in the logframe focuses on learning. DFID will continue to support partners to learn from each other during the implementation of each SHINE component. Lessons are being documented and will inform the design of the next Business Case.

Progress on recommendations from previous reviews (1/2 page)

Significant progress has been achieved against the 2017 recommendations. Most of this is captured under individual outputs but in summary this includes:
- Initiation of the SHINE Supply component and transition to service delivery through this contract with Mott Macdonald and supplies through the UNICEF commodities programme (output 1).
- Further definition and implementation of health system strengthening and government oversight support through the Change programme (output 2)
- Close management of the Sahan programme. Due to slow progression to testing of interventions in the field this has involved a reduction in budget and decision to enforce partnerships with SHINE service delivery partners (output 3).
- Work in close partnership with MESH. This has begun but will be expanded through MESH II (output 4).

Annex 1: More detailed Table of results for Output 1 (including milestones from earlier Annual Reviews)

Indicator(s)		Milestone 1 / (Annual Review 1 2016)	Milestone 2[10] / (Annual Review 2 2017)	Milestone 3 (Annual Review 3 2018)		Score
				CHANGE	UNICEF EPHS Bridging[11]
1.1a) % of EPHS facilities offering integrated modern birth spacing	Expected		New indicator added to measure integration	75% (HC, RHC, and Hospital -higher level facilities)	N/A
	Achieved			74% (Services in 20 out of 27 facilities).		A
1.1b) % of EPHS facilities offering nutrition specific intervention package	Expected		New indicator added to measure integration	90% (RHC, HC, Hospital)	N/A
	Achieved			100% Nutrition screening and referral in 27 facilities		A
1.3) Number of women delivering with help of a skilled birth attendant	Expected	7,887	59,730 (CHANGE: 12,664; UNICEF: 47,066)	15,206	48,626
	Achieved	7,669 / (CHANGE: 6,463 JHNP: 1,206)	63,148 / (CHANGE: 14,497; UNICEF: 48,651)	16,054 (6 % above milestone)	95,304 (200% above milestone)	A++
1.4) Number of U1 children vaccinated with pentavalent 3 doses	Expected	14,338	130,206 (CHANGE: 21,873;UNICEF:108,333)	27,916	132,516 (UNICEF under 5)
	Achieved	13,346 / (CHANGE: 10,805 JHNP: 2,541)	122,428 / (CHANGE: 27,370; UNICEF: 95,058)	33,303 (19% above milestone)	162,132 (76% above milestone)	A++
1.5a) Number of U5 children (CU5) and Number of pregnant and lactating women (PLW) receiving a package of nutrition specific interventions.	Expected	114,515	312,533 (CHANGE: 221,000; UNICEF: 91,533)	Number of U5 children: 260,000 / Number of PLW: 58,500	UNICEF no target set
	Achieved	126,434 / (CHANGE:120,293 JHNP: 6,141)	442,434 / CHANGE: 361,117 (CU5=264,974 PLW=96,143) / UNICEF: 81,317	CU5: 281,472 (8% above milestone) / PLW: 65,610 (12% above milestone)	CU5: Not included / PLW: 433,357	A
1.5b) Number severe acute malnutrition (SAM) treatment	Expected		Not separated out previously	3,697 (Change)	N/A
	Achieved			7,703 (108% above milestone)		A++
1.6) Number of women attending 3+ ante-natal visits	Expected	24,647	19,801	18,634 (Change)	UNICEF no target set
	Achieved	26,178 / (CHANGE: 16,810 JHNP: 9,368)	35,930 / CHANGE: (ANC2=18,585 & ANC3+=17,345)	25,547 (37% above milestone)	8,9763	A+
1.7) Total Number of outpatient visits	Expected		Not included previously	496,742 (Change)	N/A	A
	Achieved			551,518 (10% above milestone)
[10] Milestones and progress under CHANGE relate to October 2016 – September 2017. For UNICEF bridging funding they relate to January-September 2017 as the funding is for the calendar year 2017. Milestones have been given pro-rata for up until end September.
[11] Progress under UNICEF relates to Jan-Aug 2018 data, and extrapolated Sep data from the £3m extension provided from Jan-Sep 2018. . Service data for Oct-Dec 2017 is not included because of poor quality of UNICEF reporting giving insufficient disaggregation.

Annex 2. Changes in SHINE logical Framework:

Impact/ Outcome/ Output level	Change Status	2017 Logframe	2018 Logframe (updated)
Outcome statement	Updated to reflect focus on quality.	Improved access to essential health services	Increased utilisation of quality essential health services
Outcome indicator	Removed because not measurable	% of Somalis surveyed with increased access to the 4 core elements of the EPHS	Not included
Outcome indicators	Removed because it is impact level indicator.	Contraceptive Prevalence Rate (CPR)	Not included (no new data). Will be considered by M&E group for inclusion in final revision but note issues with currently modelled data.
Outcome 1	Added as critical indicator of quality/access to services.	N/A	Supply: Stock-outs - % of supported EPHS facilities without stock outs of essential medicines in one month period
Outcome 2	Added due to increasing focus on quality of care.	N/A	Supply: Quality of care - 2a) % of supported EPHS facilities meeting the minimum quality standard, focusing on key EPHS services under Output 1; / 2b) % of mystery patients having positive user experiences (mystery patients are ‘pretend’ patients sent to check services)
Outcome indicator 3 b) (demand)	Added to capture work of Sahan on increasing utilisation.	Only 3a) included which measured utilisation of services provided through the Change programme focusing on supply side interventions.	Demand: Health Facility Utilisation Rates: Numerator – total health facility visits amongst those receiving intervention; Denominator – total number receiving a given behaviour change intervention during pilot period
Outcome indicator 4	Added to capture work of Sahan on increasing healthy behaviour.	N/A	Demand: Health Behaviour Uptake Rates. Numerator - Number exhibiting a given healthy behaviour amongst those receiving intervention; Denominator - Total number receiving given behaviour change intervention during pilot period
Outcome indicator 5	Added in 2018 to capture increasing focus on system strengthening and Ministry of Health’s role.	N/A	Government Leadership: Number of tangible examples of concrete Government leadership (e.g., transparency of financial contribution, increased proportion of staff paid by government – even if funding comes from partner), convening and leading of meetings, etc.
Output 1.1	Added in 2018 to better capture integration progress.	N/A	1.1a: % of EPHS facilities offering integrated modern birth spacing. 1.1b: % of EPHS facilities offering nutrition-specific intervention package
Output 1.3	Changed to reflect correct immunisation schedule for age.	# of U5 vaccinated with pentavalent 3 doses	# of U1 children vaccinated with pentavalent 3 doses
Output 1.4 a) and b)	Refined in 2018 to separate figures for U5 and pregnant women and nutrition treatment.	# of U5 children and # of pregnant women receiving nutrition specific interventions	1.4 a # of U5 children and # of pregnant women receiving nutrition specific interventions (figures reported separately). / 1.5 b # of children receiving treatment for severe acute malnutrition
Output 1.6	Included in 2018 as only gender disaggregated data available from HMIS	N/A	1.6 # of outpatient consultations (disaggregted by sex)
Output 2.1	Revised in 2018 to reflect focus of Change programme’s work on embedded EPHS	Embedded EPHS support in place through the Change programme (more a milestone than indicator)	Monitoring, supervision & data use 2.1a) % of regions/districts conducting 4 quarterly “integrated” supportive supervision visits. 2.1b) % of follow up recommendations from integrated supportive supervision visits actioned. 2.1c) Number of tangible examples of data and evidence being used for decision making and service improvement (milestones will show progression).
Output 2.2	In the process of being revised as SHINE supply and the commodity programme finalise plans.	Supply component designed to support a strong reform agenda on EPHS management & HSS	Not included in 2018 Annual Review, will be updated by January 2019.
Output 3.1	Revised in 2018 to reflect evolution of the Sahan programme.	Demand creation support designed to address barriers to access and health promotion	Number of interventions designed, tested and piloted/evaluated (ready for scale up)
Output indicator 3.2	Created in 2018 to reflect evolution of the Sahan programme.	N/A	Number of evidence generation and synthesis products and processes used in prototype development (to improve focus on prototypes that work)
Output 4.1	Created in 2018 to reflect programme progressing in implementation and focus on learning creating change.	Monitoring and Learning Framework established to track performance and document lessons (more a milestone than indicator)	Practical examples of SHINE partners sharing knowledge and best practices leading to a new activity/initiative by another stakeholder (may include health sector tools, guidelines, case studies, webinars, event reports, best practice guides and other outputs)

ANNEX OF ACRONYMS

Community Health and Nutrition through Local Government Empowerment	CHANGE

Essential Package of Health Services	EPHS

Federal Government of Somalia	FGS

Federal Member States	FMS

Global Alliance for Vaccines and Immunisations	GAVI

Global Evaluation Framework Agreement	GEFA

Global Fund to Fight AIDS, TB & Malaria	Global Fund

Human-centred Design	HCD

Health Consortium for the Somali People	HCS

Health Monitoring Information System	HMIS

Health System Strengthening	HSS

Internally Displaced People	IDPs

Integrated Supportive Supervision visits	ISS

Joint Health and Nutrition Programme	JHNP

Learning and Monitoring Programme Somalia	LAMPS

Management Agent	MA

Memorandum of Understanding	MoU

Ministry of Health	MoH

Monitoring and Evaluation of the Somali Humanitarian Programme	MESH

Monitoring and Learning	M&L

Mott Macdonald	MM

Non-Governmental Organisation	NGO

Official Journal of the European Union	OJEU

Population Services International	PSI

Procurement and Commercial Department	PCD

Severe Acute Malnutrition	SAM

Somali Health Authorities	SHAs

Somalia Humanitarian and Resilience Programme	SHARP

Somali Health and Nutrition Programme	SHINE

Somalia Humanitarian, Health and Resilience Team	SHHARE

Terms of Reference	ToR

Tropical Health Education Trust	THET

United Nations	UN

United Nations Fund for Children	UNICEF

Value for Money	VfM