UK Department for International Development

Extension of the Education Sector
Support Programme in Nigeria
(ESSPIN)

August 2014 – January 2017

Children from St James’ School, Sabo Oke, Ilorin, Kwara State playing the ‘snake game’ using low cost materials to create chains of numbers with arithmetical rules. Photo by Oluseye ‘Tunde’ Ibiwoye

Business Case

October 2013
Contents
	Pages

Intervention Summary	1 - 4

1. Strategic Case
Why is DFID’s intervention needed?	5 - 9
Impact and Outcome we expect to achieve	9 - 11

2. Appraisal Case
What are the feasible options that address the need set out in the Strategic Case?	11 - 13
Description of preferred option	13 - 15
Theory of change and evidence base	15 - 20
Assessing the need for Capacity Development	21
Climate change and environment category	21
Social Impact Appraisal	22 - 25
Fragile and conflict-affected countries	25 - 26
What are the costs and benefits of each feasible option?	26
Cost benefit framework for the appraisal	26 - 33
Balance of costs and benefits	33
Risk and sensitivity analysis	34 - 35
Climate and Environment Assurance Note	35
What measures can be used to assess Value for Money for the intervention?	35 - 38
Summary Value for Money Statement for the preferred option	38

3. Commercial Case
Clearly state the procurement/commercial requirements for intervention	38
How do we expect the market place will respond to this opportunity?	38
How does the intervention design use competition to drive commercial advantage for DFID?	39
What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?	39 - 40
How will the contract be structured and how will contract and supplier performance be managed through the life of the intervention?	40

4. Financial Case
Overview of costs	40
Delegated authority	41
Cost profiling and forecasting	41
Financial and fraud risk assessment	41 - 42
Monitoring, reporting and accounting for funds	42
Financial accounting considerations	42 - 43

5. Management Case
What are the management arrangements for implementing the intervention?	43 - 44
What are the risks and how these will be managed?	44 - 47
How will progress and results be monitored, measured and evaluated?	47 - 53

Annexes in separate document

Glossary
CGP	Civil Society-Government Partnership
CIFF	Children’s Intervention Fund Foundation
CS	Composite Survey
CSOs	Civil Society Organisations
DFID	Department for International Development
EDOREN	Education Data, Operational Research and Evaluation in Nigeria
EMIS	Education Management Information System
ESSPIN	Education Sector Support Programme in Nigeria
FME	Federal Ministry of Education
GEP3	Girls Education Programme
GON	Government of Nigeria
GPE	Global Partnership for Education
HMG	Her Majesty’s Government
ICAI	Independent Commission for Aid Impact
IDB	Islamic Development Bank
IDP	International Development Partner
IMEP	Independent Monitoring and Evaluation Programme
IQTE	Islamiyya Qur’anic and Tsangaya Education
JSS	Junior Secondary School
LGEA	Local Government Education Authority
MIS	Management Information System
MLA	Monitoring Learning Achievement
MTSS	Medium Term Sector Strategy
PATHS2	Partnership for Transforming Health Systems
PMC	Programme Management Committee (DFID)
SBMC	School Based Management Committee
SC	Steering Committee
SHOA	State House of Assembly
SLPs	State Level Programmes
SMoE	State Ministry of Education
SMT	Senior Management Team (ESSPIN)
SPARC	State Partnership for Accountability, Responsiveness and Capability
SSIT	State School Improvement Team
SSO	School Support Officers
SUBEB	State Universal Basic Education Board
TDP	Teacher Development Programme
TPD	Teachers’ Professional Development
UBE IF	Universal Basic Education Intervention Fund
UBEC	Universal Basic Education Commission

Intervention Summary

Title: Extension of the Education Sector Support Programme in Nigeria

What support will the UK provide?

This extension to the Education Sector Support Programme in Nigeria (ESSPIN) is estimated to cost £35 million for continued work with the State Governments of Enugu, Jigawa, Kaduna Kano, Kwara and Lagos. An unallocated balance of £6.3 million from the current approved funding for ESSPIN will be utilized for this extension. The UK will therefore need to provide an additional £28.7 million to cover the full cost of the extension.

Through this extension, the total funding provided to ESSPIN since July 2008 will increase to £134.6 million. ESSPIN was originally approved by Ministers in 2007 as a £105.9 million programme. £99.6 million has been spent on the current phase which will come to an end in July 2014. The extension will commence in August 2014 and continue for 2.5 years, finishing in January 2017. ESSPIN is delivered through an existing consortium, headed by Cambridge Education, contracted by DFID. External evaluation and audit will be contracted separately by DFID.

Why is UK support required?

Learning outcomes in Nigeria are very low and access to basic education is limited:
- 10.5 million children are out of a school in Nigeria – the highest number of any country in the world. Most of these children are in Northern Nigeria and the majority are girls.
- 23.1 million children are in school but learning little. Pupils lack the foundation skills they require by the end of Grade 2 and so cannot cope with Years 3-4 curricula. Pupils reaching the required standard in Grade 2 English ranged from only 38% in Lagos to just 8% in Kano.
- Teaching standards are extremely low. Out of 20,000 teachers in Kwara State, only 75 teachers had sufficient working knowledge to enable them to teach the Grade 4-6 curriculum for 9-11 year olds. Only 17 teachers in Lagos were capable and there were no teachers at all in Jigawa and Kano States.
The extension of ESSPIN will allow DFID Nigeria to deliver commitments in its Operational Plan (2010-15). In the first year of the extension (2014-5), an additional 300,000 children will have benefitted from ESSPIN support, contributing to the achievement of the UK target that an additional 800,000 Nigerian children will be supported to enrol in school from 2010 to 2015.[1]
[1] ESSPIN is contributing to the delivery of DFID Operational Plan results alongside the Girls’ Education Programme (GEP3) implemented by UNICEF.

What are the objectives of the extension?

The expected impact is ‘better learning outcomes for children of basic education school age in six states’. The intended outcome is ‘quality of, and access to, basic education improved equitably and sustainably’. There are four Outputs which continue from the current phase, namely:

- Strengthened Federal Government systems supporting states' implementation of school improvement
- Increased capability of State and Local Governments for governance and management of basic education at State and LGEA levels
- Strengthened capability of primary schools to provide improved learning outcomes
- Improved inclusion policies and practices in basic education.

To achieve objectives, ESSPIN will continue to support the implementation and ‘roll out’ of an integrated ‘school improvement programme’ (SIP) that has proved to be highly successful, and has gained the widespread support of the 6 State Governments. The proposed scope of the extension is to:
- Deepen support to the existing 10,117 schools participating in ESSPIN in six states, extend support to a further 1,191 schools, reaching 11,308 schools in total by 2016.
- Deepen support to the existing 32,000 students in non-formal (Islamic and Nomadic) education centres, and to extend support to a further 23,000 students.

What are the expected results?

The overall number of Primary 2 and Primary 4 students with improved learning outcomes will increase from 1.49m in 2014 to 1.83 million by 2016.[2]
[2] Impact indicator 1b in the ESSPIN logframe

3.3 million Students[3] will benefit from ESSPIN supported school improvement, with more girls than boys enrolled and benefitting in the 3 Northern States.
[3] Impact indicator 2a in the ESSPIN logframe

An additional 134,000 disadvantaged and vulnerable children in Northern Nigeria will benefit from attending improved primary schools by 2016.[4]
[4] Impact indicator 4b in the ESSPIN logframe

More schools will meet ‘school quality benchmarks’, specifically:[5]
[5] Outcome indicator 1 in the ESSPIN logframe
- 6,300 schools will meet the quality standard benchmark, representing 37% of all public primary and junior secondary schools in the six states
- 700 schools will meet a new advanced quality standard benchmark

How will impact be sustained?

The prospect for sustainability is high, with success contingent on the Government of Nigeria investing in interventions developed through ESSPIN. ESSPIN is owned and led by the State Commissioners for Education in each of the 6 States. The principle implementing agency is the ‘State Universal Basic Education Board’, under the overall direction of the Chairpersons and Executive Secretaries.

ESSPIN’s rate of leverage has so far been impressive, with all State Governments now contributing to the direct costs of school improvement. During the extension, ESSPIN will continue to work closely with State governments to ensure that they take on an increasing proportion of costs. Overall, it is proposed that government funding would reach 70% of direct costs for school improvement, and 45% of the total DFID investment will be funded by Government by the end of the programme.

What is the value for money assessment of the project?

The economic appraisal has demonstrated the programme should be very good value for money with a net present value (NPV attributable) to DFID of £87 million and an internal rate of return (IRR) of 27% on this additional investment of £35 million. This case is further strengthened by the existence of benefits that cannot be quantified.
1.	Strategic Case

Why is DFID’s intervention needed?

Context for DFID’s intervention
Nigeria is a long way from meeting the Education Millennium Development Goals (MDGs):
- 10.5 million children are out of a school in Nigeria – the highest number of any country in the world. Most ‘out of school’ children are in Northern Nigeria and the majority are girls,[6]
  [6] UNESCO (2012) Global Monitoring Report, Factsheet Education in Nigeria
- 23.1 million Nigerian children are in school but learning little (UNESCO Global Monitoring Report 2012). Pupils lack the foundation skills they require by the end of Grade 2 and so cannot cope with Years 3-4 curricula. Pupils reaching the required standard in Grade 2 English ranged from only 38% in Lagos to just 8% in Kano,
- Teaching standards are extremely low. Out of 20,000 teachers in Kwara State only 75 teachers had sufficient working knowledge to enable them to teach the Grade 4-6 curriculum for 9-11 year olds, only 17 teachers in Lagos were capable and there were no teachers at all in Jigawa and Kano States.[7]
  [7] ESSPIN (2010) Baseline surveys on Teacher development needs, and Monitoring of Learning Achievement
Key factors leading to Nigeria’s extremely poor education outcomes include; high levels of household poverty particularly in the North, socio-cultural biases particularly for girls, poor school infrastructure and instructional materials, a lack of qualified teachers, as well as weak governance and low levels of accountability. Complex institutional arrangements in the education sector are major challenges for the achievement of universal basic education.[8] Roles and responsibilities between the three tiers of Government, and between Government and parastatals are poorly defined, resulting in limited accountability for education outcomes.[9] The ‘Universal Basic Education Commission’ (UBEC) was set up in 2004 but funding flows to States are unpredictable and there is a lack of federal engagement with implementation at state and local levels.
[8] World Bank (2008) Nigeria: A review of the costs and financing of public education. Volum II: Main Report. Report 42418-NG.AFTH3. Human Development Unit, Africa Region, World Bank.
[9] Centre for Universal Education, Brookings Institute (April 2013) Accelerating Progress to 2015: Nigeria. Published by UN Global Education First Initiative.

DFID’s current investments in the sector

DFID is providing support to help address needs and overcome constraints but existing interventions are insufficient to meet the challenges of the Nigerian education system. DFID is currently contributing in the following ways:

1. Education Sector Support Programme in Nigeria (ESSPIN) improving children’s learning outcomes in six states (Enugu, Jigawa, Kaduna, Kano, Kwara, Lagos) £105.9 million, 2008 -2014.
2. Girls’ Education Programme (GEP3) aiming to get a million more girls into better schools and learning in five states (Bauchi, Katsina, Niger, Sokoto, Zamfara) £103 million, 2011-2019.
3. Teacher Development Programme (TDP) will train 66,000 primary teachers in Mathematics, Science and Technology and English using innovative technologies to scale up teacher training in DFID focal states. £37.2 million, 2013-2019.
4. Developing Effective Private Education in Nigeria (DEEPEN) will improve quality in low fee private schools in Lagos State. £18 million, 2013-2018.
5. Education Data, Research and Evaluation in Nigeria’ (EDOREN) is a new initiative to generate evidence of what works to support education outcomes in Nigeria. £6 million, 2013-2017.
Nigeria is also in the process of applying to the Global Partnership for Education (GPE) for five northern states (Jigawa, Kano, Kaduna, Katsina and Sokoto) for $100 million for the period 2014-2016. USAID is preparing a new intervention which is likely to focus on their strategic education priorities of improving basic education access, youth and early grade reading in Northern Nigeria. It is widely acknowledged however that even with the addition of these new interventions, the major challenges facing Nigeria’s education system will not be quickly addressed. A large part of the solution is getting the Government to improve basic education service delivery, and to strategically influence the scope and scale of public investment in education.

How is ESSPIN addressing the challenges?

ESSPIN has been working successfully with the federal government and six state governments (Enugu, Jigawa, Kaduna Kano, Kwara and Lagos) to improve the basic education system. A major focus of the programme is an integrated approach to ‘school improvement’, whilst building capacity at state, local government and school level. Following the Mid Term Review, (July 2011) DFID asked ESSPIN to substantially scale up its work on ‘school improvement’ from 1,000 schools (Phase 1 schools) to a target of 10,000 schools (Phase 2 and 3 schools) by July 2014. This ‘scale up’ once achieved, will represent 52% of all public primary schools in the six states, but only one third of the 52% will have reached the benchmark for a ‘quality school’ by July 2014.

An ‘Independent Commission on Aid Impact’ (ICAI) review of Education in Nigeria[10] in 2012 gave ESSPIN an amber / green rating but challenged DFID to do more on learning outcomes. This recommendation was recently endorsed by the findings of the first ESSPIN ‘Composite Survey’[11] (June 2012). This Survey looked at the impact of the ESSPIN programme on teaching and learning in the 6 States. Results showed measurable improvement in teaching, but suggested it will take longer to have a significant impact on children’s learning (see Figure 1.1 and Figure 1.2 below). The Composite Survey assessed schools based on defined standards of quality. A higher proportion of ESSPIN intervention schools (Phase 1 and Phase 2 in Figure 1.1 below) were found to meet the quality standard compared with those schools in the control group.
[10] Independent Commission for Aid Impact (November 2012) “DFID’s Education programmes in Nigeria” Report 16
[11] ESSPIN Composite Survey Full Technical Report http://www.esspin.org/index.php/resources/abs/programme/349/ESSPIN-060-ESSPIN-Composite-Survey-Technical-Report.

Figure 1.1: Proportion of schools which met ‘quality standard’ by phase, ESSPIN Composite Survey June 2012
Schools that meet quality standard
The Composite Survey provided evidence that children in ESSPIN intervention schools received a higher proportion of well-delivered lessons compared with children in ‘control group’ schools and that teaching is improving over time (2010-2012). The graph below (Figure 1.2) illustrates the case with Primary 2 numeracy.

Figure 1.2: Proportion of Primary 2 pupils who met numeracy criteria, ESSPIN Composite Survey June 2012

(The difference between 2010 and 2012 is statistically significant in ESSPIN Phase 1 schools at the 95% confidence level, but is not statistically significant in control schools in 3 states with comparable data combined: Lagos, Jigawa, Kaduna).

Why extend ESSPIN?

A recent external annual review (October 2012) scored ESSPIN A+ but the review team questioned whether the work on improving learning would have reached a level of ‘sufficient and irreversible impact’ by the end of the programme (July 2014). The review noted that whilst ESSPIN is delivering results for students and teachers, it would benefit from more time to ensure sustainable impact on schools. The proposed extension provides the opportunity to increase results and deepen ESSPIN’s ‘school improvement programme’. It will ensure a more sustainable impact on State education systems, giving more time to build critical capacity to sustain the emergent teaching and learning improvements. The bulk of the funding required to secure additional results in learning achievement will come from the six Nigerian State governments participating in ESSPIN.

Extending ESSPIN’s work in Nigeria will allow DFID to make a significant contribution to global education targets in Nigeria, to contribute to DFID’s broader Business Plan, Results Framework, and DFID Nigeria’s Operational Plan (2010-15). An extension of ESSPIN will also allow DFID to respond not only to ICAI’s recommendations but also to the concerns of the UK National Audit Office (NAO) and the UK ‘Public Accounts Committee’ on the need for better monitoring and reporting on learning outcomes. The proposed extension of ESSPIN is also strongly in line with DFID’s recent position paper on education: to improve learning, reach more children and keep girls in school.[12]
[12] see DFID (July 2013) “Education position paper, Improving learning, expanding opportunities”

By July 2014, ESSPIN will have started to introduce the school improvement model into approximately 10,000 schools. However, because schools have been drawn into the project incrementally, they will all be at different stages of development. Only 3,500 will have attained the benchmark of a ‘good quality school’. The underlying assumption is that only ‘good quality schools’ will consistently produce improved learning outcomes for its students. The extension will enable Phase 1 schools to experience a full six year cycle of support which, in education terms, is a reasonable timeframe to test the ‘school improvement model’.

If ESSPIN’s approach continues to prove sufficiently effective, it could be scaled up further as part of a future DFID programme, or provide lessons for how Government and development partners should operate differently in the future. Trend data through repetition of ESSPIN surveys and further qualitative research will enable DFID to explain what works well and why within the ESSPIN approach. It is proposed that DFID would fund 2 additional ESSPIN Composite surveys[13] in June 2014 and then again in June 2016.
[13] ESSPIN Composite Survey Full Technical Report http://www.esspin.org/index.php/resources/abs/programme/349/ESSPIN-060-ESSPIN-Composite-Survey-Technical-Report.

Nigerian elections are planned for early 2015. Extending ESSPIN will help to ensure DFID Nigeria had an established education programme in place that could adapt and respond to the pre and post-election “churning” in Nigeria. A new programme is more likely to struggle to get going and adapt to election uncertainties, putting results delivery at risk. If there is no extension, and ESSPIN ends in July 2014 as currently planned, there is a risk that ESSPIN schools will become ‘isolated centres of excellence’ and some schools could also ‘slip back’. There is also a risk that there will be insufficient State level support to sustain longer term investments in basic education. This is essential if poor education standards are to be raised in Nigeria.

Requirement for additional funding beyond July 2014
ESSPIN’s current financial allocation is £105.9 million, as detailed below.

Table 1.1: Summary of ESSPIN’s finances
Current financial allocation for ESSPIN to July 2014		£105.9m
Of which allocated to:
Cambridge Education (implementation partner)	£93.4m
External monitoring and audit	£6.2m
Total allocation		£99.6m
Unallocated financial allocation at July 2014		£6.3m

A total budget of £35 million will be needed to fund the extension. DFID Nigeria proposes to draw down unallocated resources (£6.3 million) from the 2007 financial decision for ESSPIN, and request an additional allocation of £28.7 million to fund the extension.

Impact and outcomes that ESSPIN Extension will achieve

For the extension, ESSPIN’s impact statement has been revised to more accurately reflect the overarching objective of improving learning outcomes. It is now framed in the following terms: ‘Better learning outcomes for children of basic education school age in the programme’s six states.’ The Outcome has also been elaborated to incorporate a stronger focus on sustainability: ‘Quality of, and access to, basic education improved equitably and sustainably.’

To achieve objectives, ESSPIN will continue to support the implementation and ‘roll out’ of its’ integrated ‘school improvement’ programme that has proved to be highly successful, and has gained the widespread support of the 6 State Governments.

The proposed scope of the extension is to:
- Deepen support to the existing 10,117 schools participating in ESSPIN in six states, extend support to a further 1,191 schools, reaching in total 11,308 schools by 2016.[14]
  [14] Includes all public schools in 5 States, and mission schools in Enugu
- Deepen support to the existing 32,000 students in non-formal (Islamic and Nomadic) education centres, and to extend support to a further 23,000 students.

The expected headline results are:

The overall number of Primary 2 and Primary 4 students with ‘improved learning outcomes’ will increase from 1.49m in 2014 to 1.83 million by 2016.[15]
[15] Impact indicator 1b ESSPIN Extension Logframe

3.3 million Students[16] will benefit from ESSPIN supported school improvement, with more girls than boys enrolled and benefitting in the 3 Northern States.
[16] Based on average public school size of 290

An additional 134,000 disadvantaged and vulnerable children in Northern Nigeria will benefit from attending improved primary schools by 2016.[17]
[17] Impact indicator 4b in the ESSPIN logframe

More schools will meet ‘school quality benchmarks’, specifically:
- 6,300 schools will meet the quality standard benchmark, representing 37% of all public primary and junior secondary schools in the six states
- 700 schools will meet a new advanced quality standard benchmark

To achieve these results, the extension will deliver the following outputs:

- Increase the number of effective Head Teachers from 5,646 to 6,960. Of which 5,125 will meet a higher advanced effectiveness benchmark, compared to 1,620 in 2014.
- Increase the number of competent Teachers from 20,000 to 29,800. Of which 24,300 will meet a higher advanced competency benchmark, compared to 6,500 in 2014.
- Increase the number of functioning SBMCs from 3,590 to 4,482. Of which 3,553 will reach a higher advanced effectiveness level, compared to 806 in 2014.
- Increase the number of schools with inclusive practices from 5,167 to 6,960. Of which 5,125 will have an advanced level of inclusivity, compared to 1,620 in 2014.
- Increase the number of schools using School Development Plans from 3,730 to 4,563. Of which 4,185 will achieve an advanced level of implementation compared to 1,620 in 2014.

During the extension, ESSPIN will continue to support DFID Nigeria’s anti-corruption action plan and explore new opportunities to promote adaptation to climate change and environment protection through its existing school networks, particularly in the ‘dry land’ Northern States. Opportunities could include scaling up initiatives on the ‘greening’ of schools, and integrating information on climate change and adaptation into SBMC training, head-teacher and teacher training, classroom instructional materials and lesson plans. To ensure the sustainability of initiatives, piloted activities will be planned and implemented with the State Government agencies responsible for Education, Environment and Climate Change.

2.	Appraisal Case

What are the feasible options that address the needs set out in the Strategic Case?

There are several possible options to achieve the intended outcome and impact defined in the Strategic Case:

- Option 1: end ESSPIN in July 2014, as originally planned, and design a new programme with a new service provider
- Option 2: extend and deepen ESSPIN for an additional 30 months from July 2014 to January 2017 with the current service provider.
- Option 3: end ESSPIN in July 2014 and do nothing further (the counterfactual).

A recommendation to merge ESSPIN and GEP3 was made by ICAI following its review of DFID Nigeria’s education programme in 2012[18]. This proposal was rejected in DFID’s management response to ICAI on the basis that having two projects in a diverse and complex country like Nigeria helps spread risk and that GEP3 had only just started and merited more time to prove itself.
[18] Independent Commission for Aid Impact (November 2012) “DFID’s Education programmes in Nigeria” Report 16

Assessing feasibility of potential options

In assessing which of the above options are feasible, the following evaluation criteria have been applied to each option: track record and visible momentum for change, sufficiency of scope and coverage, capability and capacity of the technical assistance, timing and continuity, increased value for money through minimising transaction, set up and engagement costs and limiting risk.

Option 1: End ESSPIN in July 2014, as originally planned, and design a new programme with a new service provider

This option would require DFID to initiate a new design process, consult widely within Nigeria, approve a new Business Case and embark on a competitive bidding process. If the new programme is to start in July 2014, then the design would need to start now to provide sufficient time for consultation, approvals and contracting.

Merits: It would enable DFID to take a longer term view of the investment required over a period of up to 5 years. In designing the new programme, it would be possible to explore the potential synergies with GEP3 and TDP and build in explicit linkages based on the implementation experience gained in these two complementary programmes.

Demerits: Starting something new would not align well with the 2015 Nigerian political cycle (Presidential elections April 2015).This new programme would be mobilised in the period leading up to the national elections. A new service provider, without the track record and established political and working relationships, would find it difficult to gain traction when the political attention is focused on the elections. Continuity could be lost through the service provider adopting alternative approaches or ‘style’ of implementation. There is a risk of a vacuum occurring, with a loss of momentum, should the contracting process prove not to be seamless with a gap before the new technical assistance team is mobilised. Even if there is no delay in mobilising, there would still be a significant learning period for the new team to become fully effective in delivering this large and complex programme. Value for money would suffer both through the transactional costs to DFID of adopting a new contracting process, as well as the less than productive effort incurred by the new team to become fully operational.

Option 2: Extend and deepen ESSPIN for an additional 30 months from July 2014 to January 2017 with the current service provider

Merits: Visible progress is being made across all components of the programme and there are early, but persuasive, signs that this programme is having a significant impact on school performance. Continuity is essential to maintain the momentum for change especially when faced with the likely reduced appetite for reform during the period leading up to the national elections in 2015. The opportunity to build on the learning, relationships and influencing of ESSPIN would be lost. Also managing a path through a period of uncertain state budget allocations to school improvement programmes (SIPs) during 2015 and 2016 will require a high degree of flexibility, informed by robust and reliable information systems and sources. Prospects for value for money are greater since there is no additional mobilisation and set up costs; the operational teams and the delivery infrastructure are already in place.

Demerits: The lack of competition in negotiating the contract extension may not drive down costs to the extent that full market testing might.

Option 3: End ESSPIN in July 2014 and do nothing further

All of the 6 states have rolled out elements of the SIP with varying levels of budget commitment; management systems have been strengthened with more capable staff working at the state and local government level. Community based organisations have been strengthened to increase citizen’s voice and a start has been made to demand increased accountability from the state for education service delivery. Capacities at the federal level have increased with reforms starting to take place in the national systems for the management and oversight of the basic education sector. There are foundations in place which government could build on without further DFID support through ESSPIN.

Merits: No further investment and supervision required by DFID; able to focus its attention on supporting the implementation of GEP3 and TDP. Avoids the potential risks associated with the national elections in 2015 and possible disruptions to implementation.

Demerits: There is insufficient time for the various state funded initiatives, many only starting in 2013, to take hold and demonstrate success. Technical capability requires further strengthening both in the schools and more broadly across management within the sector. There are risks that the early gains are not embedded within Government systems; continued funding by states during the upcoming election period may not materialise and thereby undermine the early successes of the approach.

These three options were assessed according to the following criteria (1 – low score, 5 – high score)

Table 2.1: Assessment of preferred option
Criteria	Option 1 / New programme	Option 2 / Extend current programme	Option 3 / Do nothing
Track record and visible momentum for change	3	5	1
Sufficiency of scope and coverage	5	5	2
Capability and capacity of the technical assistance	3	5	0
Timing and continuity	3	5	0
Increased VfM through minimising transactions, setup and engagement costs	2	4	0
Limiting risk	2	4	1
Total score	18	28	4

Taking all of these factors into account, option 2 to extend is preferred. The recently completed 2013 Annual Review[19] concurs with the case for an extension to ESSPIN:
[19] The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP), (June 2013) “Annual Review of the Education Sector Support Programme in Nigeria (ESSPIN)”

“The performance of ESSPIN in early 2013 demonstrates that there is a strong case for the project to be extended. If the widening of coverage of school improvement across ESSPIN supported States is to take place, and the deepening of good school improvement practice is to take root, technical and advisory support, political engagement and high quality monitoring and evaluation is required for at least a further two years”.

Description of the preferred option

ESSPIN will continue to work in its six states (Enugu, Jigawa, Kaduna Kano, Kwara and Lagos). Depending on the evolving security situation in the North, emphasis and spending may be adjusted. Greatest effort and resources will be focused on delivering the ‘school improvement programme’ (Outcome 3), a major programme priority since the midterm review of ESSPIN (2011). Progress is being made in all States and recent annual reviews have recommended a ‘deepening’ and ‘consolidation’ of ESSPIN’s approach based on a valid theory of change. Greater effort in the extension will be placed on ‘embedding’ and ‘sustaining’ new ways of working, such that they become part and parcel of the routine management of basic education. A flexible responsive approach, underpinned by regular political economy analysis, will enable ESSPIN to address emerging priorities and provide differentiated technical support to education leaders and decision makers in States.

The extension will continue with the current four Outputs with the following balance of effort (weighted in line with the proposed budget allocations) as Table 2.2 below illustrates:

Table 2.2: Profile of weighting by Output
Outputs	Weighting %

Strengthened Federal Government systems supporting State implementation of school improvement	11
Increased capability of governance and management of basic education at State and Local Government levels	15
Strengthened capability of primary schools to provide improved learning outcomes	54
Improved inclusion policies and practices in basic education	20
Total	100

As noted above, Output 3 remains a major priority for the extension. It will focus on creating better learning opportunities for all children by improving the quality of schools. The current levels of learning achieved by the majority of children in Nigeria’s public primary schools are unacceptably low, and are particularly severe in the North.[20] This has been confirmed in ESSPIN’s Composite Survey (2012). Although some improvements from an earlier learning assessment (2010) were identified for ESSPIN supported (Phase 1) schools, very low proportions of children are achieving grade appropriate levels of English literacy and maths. Most children struggle with even the most basic elements of the Primary 1 and 2 curricula by the time they reach the fourth grade of primary school.
[20] ESSPIN (2010) MLA Baseline reports for Kano, Kaduna, Jigawa, ESSPIN (2012) Composite Survey, USAID (2012) Early Grade Reading Assessments in Sokoto and Bauchi States

Table 2.3. Number and proportion of children able to demonstrate defined levels of literacy and numeracy
Test	Composite Survey 2012
	Male	Female	Total
P2 Literacy	9,168 (4.8%)	6,114 (3.2%)	15,285 (8%)
P2 Numeracy	10,595 (5.4%)	7,063 (3.6%)	17,658 (9%)
P4 Literacy	2,855 (1.2%)	1,903 (0.8%)	4,758 (2%)
P4 Numeracy	8,761 (4.2%)	5,841 (2.8%)	14,602 (7%)

Children’s acquisition of the ‘building blocks of learning’ – such as the skills for ‘early reading’ and ‘number concepts’, are not translating readily into ‘applications of that learning’ – such as ‘reading with comprehension’ or ‘solving maths problems’. As demonstrated in the Composite Survey (2012) poor learning outcomes for students can be traced back to teachers’ own low levels of literacy and numeracy, their limited understanding of the primary curriculum, as well as their limited skills in scaffolding children to better access the curriculum.

Outcome 3 will deliver an integrated approach to improving school quality by supporting head teachers to be more effective, supporting teachers to be more competent, supporting school based management committees (SMBCs) to become functional, promoting the use of school development plans, and embedding inclusive practices in all school activities. To reflect a higher level of ambition for those schools already benefitting from ESSPIN support, a new measure of an ‘advanced quality school’ will be introduced. There will two strands to the ‘school improvement programme’:
- To bring more schools up to the quality standard by extending ESSPIN’s reach into new schools and providing further support to schools already supported but not yet meeting the standard
- To consolidate support to those schools already at the standard, ensure that none slip back below the standard, while others improve to a new ‘advanced quality standard’ level.
This dual approach will also be applied to all sub-components of the school improvement model, with the introduction of an ‘advanced effectiveness’ standard for teachers, head-teachers and school based management committees.

Specific interventions to ‘strengthen teachers’ will be supported, in close coordination with and complementing the new DFID funded ‘Teacher Development Programme’ (TDP). Teachers will be supported to be able to better respond to the needs of vulnerable children, and those children being left behind. Teachers will be supported to monitor children’s ‘progression’ through different levels of knowledge and skills, and to develop new skills as part of their own classroom practice. Renewed emphasis will be put on improving the use of lesson plans, learning outcome benchmarks, and formative classroom assessment. A new ‘challenge fund’ is proposed with two objectives: 1) to support low cost, locally developed, innovative ways of putting reading or story material into classrooms, and 2) community and school managed initiatives to ensure pupils in primary grades 1 – 3 have something to write on and with.

Output 4 retains its importance for improving access and equity, and includes new targeted interventions to extend the reach of ESSPIN to a greater number of marginalised students. Building on the findings of recent Annual reviews and the 2012 composite survey, ESSPIN has revitalised its strategy with State Governments to deliver ‘inclusive education for all children’.[21] During the extension, ESSPIN will provide reinforced support to Northern State Governments’ for interventions which target girls’ education, for community led schooling in nomadic communities and for integrated Islamic Qu’ranic and Tsangaya Education (IQTE).
[21] www.esspin.org/resources/abs/programme/352/Inclusive-Education-Approach-Paper

ESSPIN will continue to work with Mallams to introduce secular subjects (Maths, English, Hausa, Science and Social Science) into Islamic (Tsangaya) schools. The model includes training for community based teachers (secondary school graduates) and a condensed version of the primary school curriculum (from 6 to 4 years). Almajarai students that complete the course are supported to take an exam allowing them to transition to the formal system. It is estimated that by the end of the extension, 75% of the direct costs of supporting integrated IQTE will be met by State Government budgets. The targets for ‘non-formal education’ are outlined below. Further details are provided in the social impact appraisal.

Table 2.3.1: Targeted support for non-formal education centres (IQTE and Nomadic Education)
	2014		2016
IQTE	Number of Centres	Number of Students	Number of Centres	Number of Students
Tsangaya	380	17,480	621	28,576
Islamiyya	149	5,520	244	9,024
IQTE sub-total	529	23,000	865	37,600
Nomadic	60	9,285	100	15,485
Total	589	32,285	965	53,085

Efforts under Output 1 will continue to focus on working with UBEC and helping to facilitate the timely release of UBEC-IF funding. The work on strengthening national systems, in order to support SIPs in the States, will concentrate on three strands: monitoring learning achievement, quality assurance, and the implementation of SBMCs. The emphasis in Output 2 will shift more towards building management systems and staffing capabilities at the LGEA level whilst retaining some continuing support to the key education agencies in State Governments. During 2012-2013, there has been an increase in ‘inter-state’ learning and peer support to quality assure the work of other State teams. This will be continued during the extension as part of a two way professional development process.

Continued support to all six states is both pragmatic and offers the best prospects for sustainability. During the current phase of ESSPIN, all State governments have been persuaded to utilise their own resources in direct support of school improvement. Evidence of progress provided through the Composite Survey (2012) made this leverage possible and each State is now pursuing an incremental ‘scale up’ that will take another two to three years to complete. ‘Roll out targets’ are based on ESSPIN’s current political economy analysis of existing commitments and predicted trends over the next two years. These are set out in the Table 2.3.2 below. ESSPIN’s ‘roll out’ plan includes reaching 100% of public primary schools in 3 States (Lagos, Kwara, Kano) and at least 80% of schools in Jigawa. There is room for further expansion in Kaduna, and Enugu’s current rollout plan (an additional 25 schools per local government area) would in principle take the number of SIP supported schools to 43% of all schools in the State.

Table 2.3.2. ‘SIP roll out targets’ for each State
State	No. of Phase 1 schools	2014 estimated target	2016 estimated target	2016 target as % of all schools
Lagos	100	1003	1003	100%
Kwara	1440	1440	1440	100%
Kano	312	5330	5330	100%
Jigawa	198	1002	1503	80%
Kaduna	165	1070	1760	41%
Enugu (public)	91	91	91	8%
Enugu (mission)	30	181	181
Total	2336	10117	11308

Continuing in all six states, and ‘ramping up’ school performance through State funding through to January 2017, provides an opportunity to demonstrate greater impact from DFID’s investment and increase Value for Money. As more schools reach an advanced quality standard and States spend their own funds on incremental rollout of the school improvement programme, DFID will help ensure that improvements in learning outcomes are sustained. ESSPIN will repeat the Composite Survey in 2014 and 2016 and conduct further qualitative and longitudinal research to fully understand the outcomes of the School Improvement programme. This will provide, for the first time in Nigeria, comprehensive trend data on learning outcome change and improved school quality. This evidence base will be invaluable to Nigerian policy makers and resource planners engaged in the sector.

This extension will strongly complement the investments being planned in the sector, such as the new USAID reading programme ($60 million) and the Global Partnership for Education ($100 million). If Nigeria’s application to the Global Partnership for Education (GPE) is successful, new funding for schools and local governments (grants) will support the ‘roll out’ of school improvement in the three Northern States (Kano, Kaduna, Jigawa) from March 2014 to 2016. During the extension, DFID and ESSPIN will need to facilitate synergy and alignment between ESSPIN’s activities on school improvement and the incoming GPE resources. Whereas ESSPIN is a largely technical assistance programme, the GPE has been designed to provide additional financing to mobilise SBMCs, to provide school improvement grants, girls’ scholarships and female teacher scholarships. The success of the proposed GPE investments in Kano, Kaduna and Jigawa will to some extent also depend on DFID’s decision to continue its investment in education in those States up to the end of 2016.

Theory of change and assessing the evidence base

The problem that ESSPIN is helping to address is the very low level of learning outcomes in Nigeria’s basic education system. This is caused by the poor quality of teaching, compounded by the constraints on access to basic education especially for the poor, for girls and for other disadvantaged groups. ESSPIN’s approach to addressing these challenges is to work strategically with all three levels of Government (Federal, State and Local) to adopt an integrated, multifaceted reform programme with improving school performance as the central focus. ESSPIN’s School Improvement Programme (SIP) includes the following five pillars, with four cross cutting areas for capacity development:

SCHOOL IMPROVEMENT PROGRAMME
Greater head teacher effectiveness
Introduction of school development plans
Increased teacher competence
Data on school quality used to inform education planning
Effective planning and budgeting to support school improvement
Institutional capacity in States to deliver and sustain school improvement
Civil Society and government partnerships to strengthen voice and accountability
Adoption of inclusive practices to meet the needs of all pupils
Establishment of functional school based management

The main assumption underpinning this integrated approach is that ESSPIN, by piloting an effective school improvement model with demonstrable results, will secure state government buy-in and convince States to utilise their own considerable resources to expand the positive impact of the model to all children.

Although implementation of the SIP is necessary and essential, on its own it is not sufficient to bring about the intended Outcome, namely “the quality of, and access to, basic education improved equitably and sustainably.” Complementary and parallel improvements are needed in the management, oversight and service delivery systems and processes which are being used by the three levels of Government. Given the particular issues around access and equity, ESSPIN helps to tackle these barriers through targeted capacity development interventions alongside its work in schools and across Governments. The strengthening of citizens’ ‘voice’ in basic education forms part of the process to improve access and to increase accountability. Figure 2.1 on the following page sets out the ‘results chain’ illustrating the linkages from Outputs to Outcome and through to Impact. The key assumptions and the evidence to support this theory of change are discussed further below.

Assumption – Improving school performance results in better learning outcomes

There is an emerging body of evidence to indicate that the implementation of the school improvement programme (SIP) is starting to make a difference. The conclusion of the recent ESSPIN Composite Survey[22] concludes the following: ‘In schools supported by ESSPIN, levels of teacher competence, school development planning, governance and (to a lesser extent) inclusiveness and leadership are higher than in control schools[23] and are associated with higher learning outcomes by pupils on several measures...’ Further, it concluded that ‘the first round of the Composite Survey provides plausible evidence that the ESSPIN intervention logic is valid....’ The most recent Annual Review of ESSPIN[24] confirmed that “the theory of change has validity”. The strength of this evidence is medium.
[22] Ibid
[23] Control schools are those schools not included in and supported by the ESSPIN programme
[24] The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP), (June 2013) “Annual Review of the Education Sector Support Programme in Nigeria (ESSPIN)”

The Composite survey results, summarised in Table 2.4 below confirm that ESSPIN is starting to achieve positive results with respect to improving school quality and learning outcomes.

Table 2.4: Composite survey results for school quality and learning outcomes
Indicator	Phase 1 / schools	Phase 2 / schools	Control schools	All schools
School quality	15%*	7%*	0%	2%
% Primary 2 pupils with skills for reading comprehension	8%	9%	5%	9%
% Primary 4 pupils with skills for reading comprehension	8%*	9%	2%	4%
% Primary 2 pupils able to perform / Primary 2 arithmetic	19%*	16%	10%	12%
% Primary 4 pupils able to perform / Primary 4 arithmetic	8%	7%	8%	7%

Estimates marked * are significantly different between Phase 1 (or 2) and Control Schools at the 0.05 level, i.e. there is a high degree of certainty that ESSPIN intervention schools are significantly different from non-intervention schools.

Evidence from the Composite Survey indicates that ESSPIN Phase 1 students outperform their counterparts in control schools in numeracy and literacy at both Primary 2 and Primary 4 levels.[25] A more powerful picture of performance emerges when the distribution of learning outcomes is further analysed by State, and across ‘learning domains’ and ‘performance quartiles’. For example in Jigawa State:
[25] ESSPIN Composite Survey Full Technical Report http://www.esspin.org/index.php/resources/abs/programme/349/ESSPIN-060-ESSPIN-Composite-Survey-Technical-Report.
- 13% of ESSPIN supported pupils in Year 2 of primary school are in the top quartile score (75%-100%) for literacy, compared with 2% for pupils in control schools
- In year 4 of primary, ESSPIN supported students score 22% in literacy tests, compared with 1.8% in control schools
- On numeracy tests, Primary Year 2 pupils scored 27% compared to 10% in control schools
- Primary 4 pupils, scored 3.9% in numeracy tests compared to 0% in control schools.

Figure 2:1 ESSPIN Results Chain

Impact	Better learning outcomes for children of basic education school age in the programme’s six states
Outcome	Quality of, and access to, basic education improved equitably and sustainably
Outputs	Improved inclusion policies and practices in basic education / Strengthened capability of primary schools to provide improved learning outcomes / Increased capability of State and Local Governments for governance and management of basic education at State and LGEA levels / Strengthened Federal Government systems supporting states' implementation of school improvement
Inputs	Facilitating increased disbursement rate of UBE Intervention Funds	Improving LGEA management systems	Improving head teacher effectiveness	Improving standard of inclusive policies and practices at State level
	Establishing quality national system for / monitoring learning achievement	Improving LGEA service delivery systems and processes	Increasing teacher competence	Increasing number of inclusive schools
	Establishing quality national system for / quality assurance	Improving LGEA school support and quality assurance services	Adopting inclusive practices	Increasing number of IQTE pupils included
	Establishing quality national system for / SBMC implementation	Improving level and quality of State/LGEA engagement with local communities	Introducing school development plans
			Establishing functional school based management committees (SBMCs)

Assumption – Better performing schools lead to increased enrolments

In relation to enrolment, ESSPIN is achieving positive results. Between 2009 and 2012, ESSPIN focus schools in Jigawa, Kaduna, Kano and Enugu enrolled primary age children (6-11 year-olds) at a higher rate than the state average (this distinction does not apply in Lagos and Kwara where ESSPIN works in all LGEAs). Increases in primary net enrolments in ESSPIN focus LGEAs compared with state total increases were as follows:

Table 2.5: Primary net enrolment increases in ESSPIN focus LGEAs compared to state-wide totals
States	Focus LGEAs	State wide
Jigawa	26%	14%
Kano	26%	11%
Kaduna	5%	3%
Enugu	45%	33%

 Source: ESSPIN derived from Annual School Census

In northern states, where girls’ access to education is a particular challenge, there is clear trend of more girls’ enrolling in primary schools than boys over the last 3 years. Overall, girls accounted for 54% of all additional children in primary education (gross enrolment) in these States.

Assumption - Successful pilots will leverage additional Government funding for ‘scaling up’

There is strong evidence to confirm that ESSPIN has been successful in leveraging additional Government funding for SIP roll out. Table 2.6 below summarises the funding leveraged for the SIP to date. State government funding is currently leveraged through 1) support to SUBEBs to access UBE-Intervention Fund, and implementing departmental work plans targeting school improvement, and 2) support to Ministries of Education to access funds from annual State budgets based on inclusion of school improvement programmes in the MTSS. Both leverage routes have required concerted political engagement by ESSPIN, working with DFID State Representatives and education team. Strategic engagement of DFID Nigeria management team with State Governors and Commissioners has also helped ensure financial commitments from States are realised. A key strategy has also been building alliances with key civil servants and engaging with a range of stakeholders on school improvement planning. Progress with leverage has not been uniform and has been evolving over time, as a result of changes in the political and education leadership in each State.

During the extension, leverage rates will be affected by political uncertainty building up to and subsequent to the 2015 Nigerian elections. This period of ‘churning’ could have an impact (potentially both positively and negatively) on federal and state budget releases. Changes in the management of ‘Universal Basic Education’ fund could also have an impact; emerging plans to include a new budget line on ‘school improvement’ in the UBE Act would be very positive for ESSPIN States. Other opportunities to leverage new funds are emerging and ESSPIN is actively positioning partner States to benefit from these resources. These include federal funds from the MDG Office and the former ‘Education Trust Fund’, private sector partnerships and international donor initiatives such as the ‘Global Partnership on Education’.

Table 2.6: Financial resources leveraged for school improvement between July 2012 – March 2013
STATE	July-December 2012 (£)	January - March 2013 (£)	Total leveraged July 2012-Mar 2013 (£)
Enugu	0	260,000	260,000
Jigawa	728,000	221,200	949,200
Kaduna	732,000	568,000	1,300,000
Kano[26]	112,000	664,000	776,000
Kwara	153,600	142,800	296,400
Lagos	516,000	984,000	1,500,000
Federal	932,000	0	932,000
Total	3,173,600	2,840,000	6,013,600
[26] A further £837,500 has been approved by the Kano State Government in 2013 for SIP rollout to all 5,300 primary schools in the state

Source: ESSPIN Quarterly Reports

ESSPIN’s overall success to date is evidenced by the fact all State governments are now funding aspects of the school improvement programme from their annual education budgets. For example, (a) all States fund their State School Improvement Teams, (b) Lagos State government is providing school grants to all primary schools, and (c) the Annual School Census is routinely funded by States. In addition, Kano State government is funding IQTE expansion and has started to expand the teacher training component of the school improvement programme to all primary schools.

At the Federal level, ESSPIN has supported States to secure their UBEC ‘intervention funds’ which need to be ‘matched’ 50:50 with State funds and are largely used to construct and renovate school classrooms. Between 2010 and 2012, UBEC funding has helped construct 2000 classrooms and renovate 2,700 classrooms across the six states. ESSPIN has also worked with UBEC to ensure more flexible conditions for disbursing ‘unmatched grants’ within the UBE-Intervention Fund. As a result, States have access to a predictable source of funding (£560,000 annually) for school improvement.

Overall strength of evidence

Overall, the strength of the evidence for ESSPIN’s theory of change is medium, with the potential to become stronger with the findings of the Composite Surveys in 2014 and 2016.

Assessing the need for Capacity Development

ESSPIN is part of DFID’s portfolio of ‘state level programmes’ (SLPs) which have a strong emphasis on capacity development; this focus will be carried forward into the extension of ESSPIN. In terms of improved governance and strengthened management systems and processes, ESSPIN is working closely with ‘State Partnership for Accountability, Responsiveness and Capability’ (SPARC) programme. The ‘Medium Term Sector Strategy’ (MTSS) approach to State education planning and budgeting was developed in conjunction with SPARC. ESSPIN’s success in deploying the MTSS within education led to rollout of the framework in other line ministries, namely health, water resources, agriculture, environment and transport, with support from SPARC. ESSPIN and SPARC have also collaborated in shifting the format of annual State budgets from basic economic classifications (recurrent, capital, overheads) to Activity Based Budgeting (ABB) which allows easier tracking of expenditure for specific projects.

ESSPIN has further addressed the challenge of better managing State education expenditures through:

1. Strengthening annual planning cycles through the use of ‘Departmental Work Plans’ (DWPs) to link activities to approved budgets, and as the basis for requesting budget release.
2. Commissioning ‘public expenditure reviews’ (PER) to unpack State annual expenditures on education and establish patterns of spend, particularly related to school improvement lines. Final reports are available for Kano, Kaduna and Jigawa and will inform further PFM analysis and capacity building for Ministries of Education.
3. Quarterly Monitoring Reports (QMR) on budget performance, presented at quarterly meetings of Education Commissioners and SUBEB Chairs. Reports enable discussions on budget performance and bottlenecks to ensure more effective budget utilisation.
Continuing the work to monitor and track public expenditure will strengthen the links between the education plans, budgets and allocations. Further improvement and embedding of the ‘Education Management Information Systems’ at State level will strengthen the evidence base for monitoring improvements in schools. ESSPIN is also working closely with the ‘State Accountability and Voice Initiative’ (SAVI) to identify relevant CSOs; building their capacity to scrutinise the State education budget and undertake issue based advocacy on behalf of local communities.

Climate change and environment category
Table 2.7
Option	Climate change and environment risks and impacts	Climate change and environment opportunities
1	C	B
2	C	B
3	C	C

Social Impact Appraisal

Context[27]
[27] The statistics presented below are extracted from World Bank, AFTED, Africa Region (June 2013) “Nigeria Education and Skills Policy Notes Policy Note 1: Education Access, Equity and Quality in Nigeria” Report # 77597_NG

Children from the poorest (lowest wealth quintile) households, and those with mothers having less than primary education, are largely excluded from school. Both boys and girls from such backgrounds are much less likely to be in school at all ages. Those children with this socio economic background that do start school, will normally start late at the age of 10-11. The high cost of schooling is a major factor limiting attendance. For an average child from the poorest quintile, the total cost (including tuition, uniforms, textbooks, transportation and all other related costs) is one fifth of household income.

Girls from the North, rural areas and poorest families have very low educational attainment. They are least likely to attend school. The percentage of ‘out of school’ children is highest in the north of the country, ranging from 43 % of boys, to 53 - 54 % of girls. In the North West region, where ESSPIN operates, a smaller percentage of girls (47%) than boys (57%) attend formal, or integrated religious schools. Girls are less likely to be in the formal secular education system, and more likely to be in non-integrated religious schools, which do not teach at least one of the following subjects: English, Mathematics, Social Studies or Science.

A further factor limiting girls’ attendance is that schools are not seen by parents as a safe and secure environment for their female children. There are concerns over the lack of separate and sufficient toilet facilities for girls. The predominance of male teachers and their behaviour is perceived by some parents as a threat to their girl child. There is anecdotal evidence of school-based violence and sexual harassment of girls and female teachers. To secure girls from sexual harassment and exploitation, parents have prevented their daughters from completing school and husbands have prohibited wives from teaching.[28]
[28] Evidence from USAID COMPASS Nigeria (2004-2008) confirmed that teachers’ attitudes towards female pupils influenced parents’ decisions about their daughters’ attendance

Women’s overall role in education is limited by the prevailing traditional, socio-cultural structures and practices within an inherently patriarchal society. Women’s role in community life focuses mainly on child bearing, child rearing and taking care of the home. The introduction of school based management committees (SBMCs) provides a potential forum where women can participate in the decisions around their children’s education.

ESSPIN’s approach to inclusive education[29]
[29] www.esspin.org/resources/abs/programme/352/Inclusive-Education-Approach-Paper

The overarching objective of ESSPIN’s approach is ‘more children, especially girls, in school, learning more’[30]. This encapsulates ESSPIN’s broader objectives on access (more children in school), equity (especially girls) and quality (learning more). Good schooling will increase the educational space in which children feel welcome, attend school regularly, and learn while they are there. ESSPIN’s ‘school improvement’ approach aims to reduce the number of ‘out of school’ children through better performing schools, and complements ESSPIN’s more specific interventions to support girls' education, education for children affected by disability, and nomadic children.
[30] Ibid

ESSPIN’s Access and Equity framework[31] envisages inclusive policies and practices at state, school and community level; with schools having functioning ‘School Based Management Committees’ (SBMCs) reflecting women and children’s concerns and support inclusive education, where civil society advocacy and community mobilisation bring about school improvement, benefiting all groups including marginalised children. ESSPIN’s ‘school improvement programme’ provides the platform for promoting inclusive practices at school level through systematic head teacher and teacher support programmes, and specific infrastructure targeting the needs of girls.
[31] Ibid

ESSPIN’s institutional development work addresses access and equity, embedding gender within Medium Term Sector Strategies (MTSS) and associated annual budgets and incorporating sex disaggregated data in school census and annual education performance reports. At federal level, efforts are ongoing into improve stakeholder engagement, influence policy and planning, and leverage resources for access, equity, inclusion and gender.

What progress has been made so far?
The 2013 Annual Review[32] concluded that ‘progress is being made both in terms of specific inclusion strategies for marginalised groups and through gender mainstreaming’.
[32] The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP), (June 2013) “Annual Review of the Education Sector Support Programme in Nigeria (ESSPIN)”

ESSPIN has promoted innovative strategies for inclusion through its deployment of ‘Challenge Funds’ (CF) in States. The CF has established a significant intervention in Jigawa State where community owned schools in nomadic settlements are supported to bring more children, especially girls, into school and to improve the overall quality of teaching and learning. In Kwara, the CF is supporting a rural housing scheme for teachers (in association with the Local Government) as a strategy for improving retention of rural children, especially girls, in school. Kwara has also piloted a Community-EMIS initiative which aims to equip local communities with information on schools to improve the quality of decision making and school support at local levels.

Another important dimension of ESSPIN’s work to extend basic education to Almajirai (street children) through ‘Tsangaya’ Qu’ranic schools. The vulnerability of this group has been exacerbated by the worsening economic situation, and by conflict and insecurity in northern Nigeria. In addition to offering these children an alternative route to Junior Secondary School, ESSPIN’s intervention keeps them off the streets where they are vulnerable and subject to abuse.

The success of ESSPIN’s efforts to date for girls is evidenced by the following results. Girls’ enrolment in school, both in absolute and percentage terms, has increased at a faster rate than boys over the last three years, as Table 2.8 below illustrates.

Table 2.8: Increase in enrolment for boys and girls by State between 2009-12
State	Cumulative Change 2009-12			Cumulative Change 2009-12
	Male	Female	Total	Male	Female	Total
Jigawa (N)	25,175	37,297	62,472	9%	18%	12%
Kano (N)	142,873	159,476	302,349	13%	17%	15%
Kaduna (N)	68,434	77,360	145,794	12%	16%	14%
Kwara (W)	16,907	18,425	35,332	15%	18%	16%
Lagos (SW)	10,457	3,720	14,177	5%	2%	3%
Enugu (SE)	6,468	4,766	11,234	4%	3%	4%
Total	270,314	301,044	571,358	11%	14%	13%

 Source: ESSPIN derived from Annual School Census
Over 570,000 additional children (53% girls) enrolled in primary schools in the six States supported by ESSPIN between 2009 and 2012. Thirty four percent of this total enrolled in ESSPIN focus Local Government Areas (LGEAs). In Northern Nigeria, where girls’ education represents a particular challenge, girls accounted for 54% of all additional children in primary education (gross enrolment). The increase was higher for girls than for boys in each of the three Northern states.
In terms of learning outcomes,[33] girls are performing, on average, 7 to 8 percentage points better than boys on measures of Primary 2 literacy and Primary 4 numeracy. Female teachers perform significantly better than male teachers in inclusive classroom practices.[34]
[33] ESSPIN Composite Survey Full Technical Report http://www.esspin.org/index.php/resources/abs/programme/349/ESSPIN-060-ESSPIN-Composite-Survey-Technical-Report.
[34] Ibid

Five states now have Inclusive Education Policies (IEPs) with Kaduna already implementing its policy. 39% of Phase 1 schools meet the SBMCs women’s inclusiveness standard[35] compared with only 7% in control schools. The increase in numbers of SBMCs reflecting the concerns of women indicates a proportionate increase from 62% in 2012 to 79% in 2013In terms of children’s participation the Composite Survey reports that 23% of Phase 1 schools met the standard for inclusiveness compared with 4% of the control schools.
[35] Standard comprises criteria for attendance, leadership, raising issues and issues leading to action

Recent research findings[36] show that SBMC Women’s Committee members are now engaged in a range of school related activities in their communities, including conducting educational awareness campaigns, fund raising, house-to-house visits, school visits, and ensuring that teachers are in class teaching children. In all six states, members have started to address the issue of out of school children and those who are missing classes or struggling to learn. One approach is to visit the markets and see whether children are present; parents of these children are counselled to send their children to school.
[36] Women’s Participation in School Based management and Communities within the complex socio-cultural context of Nigeria, Report~ ESSPIN 425, Abuja, October 2012

ESSPIN’s inclusive education activities during the extension

ESSPIN will continue its work to increase girls’ access through a range of interventions including: capacity support to women leaders and gender champions to mobilise for girls’ education; influencing work with community gatekeepers, including local leaders and support to government-run ‘Second Chance’ schools for girl dropouts coming back into basic education. In relation to community schools for nomadic communities, ESSPIN will help to provide infrastructure (water and sanitation facilities, classroom upgrades, e.g. from thatch walls to concrete), school materials such as school uniforms and school bags, training of volunteer teachers, support to Community-EMIS to enable participatory monitoring of school attendance by local communities and more effective safe spaces for women and girls through School Support Committees. Support to IQTE will include: training of volunteer teachers, provision of teaching and learning materials, practical and vocational skills acquisition training (especially for girls in Islamiyya), and the expansion of ‘Tsangaya’ integrated Qu’ranic schools for additional cohorts of Almajirai street children and other vulnerable boys.

Working in fragile and conflict-affected situations

ESSPIN is working in two Northern states, Kano and Kaduna, which over the last two years have been subject to civil disturbances arising from the operations of Boko Haram[37] and the Government’s response. More recently, targeted attacks by Boko Haram on boarding schools and tertiary education institutions, resulting in multiple student deaths, indicate a growing level of threat to education in some Northern States. Education is recognised as an area where policy choices can have immediate consequences in locations where armed conflict is prevalent; ‘what is taught in school, how it is taught, and how education is financed and delivered are all policy areas in which government decisions have both an early and lasting impact, for better or for worse’[38]. There are three ways in which education can exacerbate conflict: (a) the provision of too little education, especially for the poor, (b) unequal access to education resulting in a sense of injustice, and (c) the wrong type of education where the needs and concerns of minorities and disadvantaged groups are either not addressed or are ignored and thereby excluded[39].
[37] Congregation and People of Tradition for Proselytism and Jihad is better known by the Hausa name ‘Boko Haram’ meaning “Western education is sinful". It is a jihadist militant organisation based in the north east of Nigeria, north Cameroon and Niger, strongly opposed to man-made laws and westernisation. Source: Wikipedia
[38] UNESCO EFA Global Monitoring Report (2011) “ The hidden crisis: Armed conflict and education”
[39] Ibid

ESSPIN’s emphasis on greater access, equity and quality, combined with the involvement of communities through the SBMCs, is an approach which has the potential to do the maximum good and pose the least risk of inadvertently doing harm in the conflict affected states. Although not directly attributable to the ESSPIN approach, the impact of conflict on education has not become evident so far. Typically, these negative consequences are seen first in the decrease in enrolment and attendance rates. There are no signs of this occurring. A second consequence is a diversion of funding away from education to meet the costs of conflict. Again, this is not evident; indeed the opposite is true with increasing funding from the states.

ESSPIN’s positive promotion of inclusion should go some way in minimising the risks of marginalisation. For example, through the ‘Tsangaya’ strand of their work with Islamic Education, ESSPIN is bringing in Almajirai boys voluntarily (who, at the right age, are sometimes conscripted to perpetrate violence in the North) and providing them with some basic literacy. Through this initiative also, ESSPIN has formed positive relationships with Malams[40] who are influential in conflict affected areas. Also, SBMCs are taking positive action to mobilise their local communities and engage meaningfully with government providers, thus minimising the risk of unresolved grievances which might stimulate civil unrest.
[40] Mallams are religious instructors who also are preachers

The 2013 Annual Review[41] highlighted the need for ESSPIN to gain a better understanding through research how conflict in the North is affecting education and whether the lack of educational opportunity is fuelling conflict. Alongside this proposed research, the longer term implications for the work of State teams in difficult and pressured circumstances should be examined.
[41] The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP), (June 2013) Annual Review of the Education Sector Support Programme in Nigeria (ESSPIN)

What are the costs and benefits of each feasible option?

This appraisal considers two options: (i) the existing programme, ESSPIN, is extended from July 2014 to January 2017, (ii) the programme finishes with no extension in July 2014. For the following cost-benefit analysis, the latter option is treated as the counterfactual – what would happen in the absence of the intervention. All costs and benefits are calculated relative to this counterfactual.

Cost benefit framework for the appraisal

Expected resource costs of the intervention

Extending ESSPIN will incur the following economic costs:

Project investment by DFID – £35 million over 2.5 years. The full outline and time profile of these costs is set out in the financial case. Of the £26.4m spent directly on the four project outputs, more than half (£14.1m) is for Output 3, delivering the school improvement programme. Spending on Outputs 1 and 2 (£2.9m and £4m respectively) largely backs up investments in Output 3 by ensuring appropriate management systems and processes to support school improvement are in place at federal, state and local levels. The £5.4m investment in Output 4 ensures that gains made through the School Improvement Programme are achieved in an inclusive manner with additional support to more marginalised groups. Given the extent to which the project targets buy-in and leverage from the Nigerian Government, it necessarily has a strong technical assistance focus.

Leveraged investment by State Governments – The success of ESSPIN is contingent on the Government of Nigeria investing in ESSPIN approaches. In key areas of investment, the current rate of leverage is high. For the direct costs of the ‘school improvement programme’, an ambitious target for state governments has been set, to take on 70% of total costs. Overall government funded leverage is expected to be 45% of total project investment.

Direct costs for providing children’s education – ESSPIN is expected to improve both enrolment and retention of students in schools. This will incur a cost on Government which has to pay the direct cost for providing education to more children for longer. This analysis will use £125 per year for every primary student. This was calculated as the unit cost required in Nigeria to meet EFA-FTI Guidelines (i.e. particular teacher-pupil ratios, capital investment to support enrolment increases etc.).[42] This is likely a high-end cost estimate, ambitious in terms of resources needed to be spent by Government for a quality provision of education.[43]
[42] Chang, G-C. et al. (2009), “Estimating the costs of education development – case study for DRC, Nigeria and Sudan for EFA GMR 2010”, Background paper prepared for Education for All Global Monitoring Report 2010
[43] World Bank benchmark is £50 for primary education (DFID 2009 Education Portfolio Review) – but only considers recurrent costs, not the capital costs required when enrolment is expanding.

Direct private costs for children going to school – Additional children going to or staying in school longer as a result of the project, incur a direct private cost for each year they spend in school. The World Bank’s 2008 review of public education in Nigeria calculated average per pupil private costs at primary schools as £4.85 per year.

Indirect opportunity costs for children going to school – Children going to or staying in school longer because of ESSPIN may also incur an opportunity cost (for themselves or for their family) from not being able to work. This is set as 40% of an uneducated adult’s assumed salary, implying an opportunity cost per student per year of £123.[44]
[44] GDP per capita GBP 1,026 (World Bank 2012). Average salary for uneducated adult assumed as 30% of GDP per capita (GBP 308).

Table 2.9: Summary of Economic Costs for Extension
(£ millions)	2014/15	2015/16	2016/17	2017/18	2018/19	Total
Output 1 (DFID)	1.2	1.2	0.5	0	0	2.9
Output 2 (DFID)	2.0	1.5	0.5	0	0	4.0
Output 3 (DFID)	6.5	6.8	0.8	0	0	14.1
Output 4 (DFID)	2.3	2.3	0.8	0	0	5.4
Indirect project costs (DFID)	3.0	3.5	2.1	0	0	8.6
GoN leveraged costs	6.8	6.9	2.2	0	0	15.9
GoN direct costs of education provision for additional children	2.1	3.9	4.1	4.3	4.3	18.6
Additional children in school’s direct costs	0.1	0.2	0.2	0.2	0.2	0.8
Additional children in school’s indirect (opportunity) costs	2.1	3.8	4.0	4.2	4.2	18.3
Total Economic Costs	26.1	30.1	15.2	8.7	8.7	88.6

Note: Numbers may not add up due to rounding

Expected benefits of the intervention

The economic benefits from ESSPIN predominantly arise from two key sources (both resulting from improving the quality of schools):

1. Quality premium - Students who would have gone to school anyway learn more
2. Enrolment and retention premium - Students who would otherwise have dropped out or who would not have gone to school in first place are more likely to enroll and stay in school.

Rate of return to education

Calculating these benefits requires an understanding of the rate of return to education. This is the marginal benefit from a student spending one more year at school. It should capture benefits that are both private to the student and their family and those that accrue to society as a whole.

Direct private benefits of education: the most direct and easily calculated private benefit is the increased wage individuals can earn after leaving school. Globally an additional year of primary education increases an individual’s salary by on average 10%.[45] The evidence also suggests that the returns in sub-Saharan Africa are higher than global averages.
[45] Colclough et al. (2010: 739), “The changing pattern of wage returns to education and its implications”, Development Policy Review, 2010, 28 (6)

Indirect private benefits of education: benefits which raise the welfare of students beyond income include: enjoyment of education in itself, greater productivity in activities beyond formal employment, improved health through greater understanding of health issues, better use of financial assets (saving and consuming more efficiently); increased agency; job satisfaction beyond salary; and many other examples. Monetising these returns is difficult. McMahon (2004) estimates them to be 80% of the direct market returns to education.[46]
[46] McMahon, W. (2004) “The social and external benefits of education”, Ch.6 in ‘International Handbook on the Economics of Education’

Social benefits of education: benefits that accrue to society more broadly include improved public health, fiscal returns to government from higher tax revenues, political and institutional benefits (e.g. stronger respect for human rights)[47], reduced risks of conflict[48], environmental benefits and both improved climate change mitigation[49] and adaptation[50]. There is good reason to believe these benefits are particularly strong in Nigeria, most notably in ESSPIN’s three Northern States where health outcomes are extremely poor and issues of conflict are increasing. Monetising these social benefits is extremely difficult. Nevertheless, excluding them would mean neglecting possibly the most important benefits of education in Nigeria. McMahon (2004) calculates that the overall social returns to education in Africa more than double the private wage returns.[51]
[47] Appiah, E. & McMahon, W. (2002), “The social outcomes of education and feedbacks on growth in Africa”, Journal of Development Studies, 38 (4), 27-68). For a more recent review of the evidence see Kremer et al. 2011 draft paper, “Education as Liberation?”
[48] See Global Monitoring Report 2011
[49] Wheeler, D. and Hammer, D. (2010) “The Economics of Population Policy for Carbon Emissions Reduction in Developing Countries”, Working Paper 229 Center for Global Development, November 2010
[50] Blankespoor, B., Dasgupta, S., Laplante, B and Wheeler, D. (2010) “Adaptation to Climate Extremes in Developing Countries: the Role of Education”, World Bank Policy Research Working Paper 5342
[51] McMahon, W. (2004) “The social and external benefits of education”, Ch.6 in ‘International Handbook on the Economics of Education’

Quality premium - International rate of return calculations for education are estimated relative to the quantity of education received. Implicitly the rate of return is calculated for the average level of quality across the system. Nevertheless, the evidence is extremely clear that it is the quality of education actually received rather than simply its quantity which ultimately determines the returns from schooling.[52] Students getting a better quality of education should get a higher rate of return.
[52] Hanushek & Woessmann (2008), “The role of cognitive skills in economic development”, Journal of Economic Literature, 46:3

Measuring the quality premium for ESSPIN

ESSPIN targets improving quality on a whole-school basis. Students at better quality schools should in turn get improved learning outcomes. To date ESSPIN has developed a measure determining whether a school is of ‘quality standard’. To be assessed as good quality, a school has to meet at least three of five Output standards relating to teacher competence, head-teacher effectiveness, school development planning effectiveness, SBMC functionality and school inclusiveness.[53]
[53] 23 criteria underpin these standards. To meet the school quality outcome standard, teacher competence has to be one of the three output standards reached.

By July 2014 (the start of ESSPIN’s extension) 3,500 schools will be meeting the quality standard (of around 10,000 supported in total). The 2012 Composite Survey found that not a single non-ESSPIN control school met the same quality standard.

In terms of school quality, ESSPIN’s support in the extension will have two broad objectives:

1. Bring more schools up to the quality standard by extending ESSPIN’s reach into new schools (up to 11,308 public and mission schools) and providing further support to schools already supported but not yet meeting the standard
2. Consolidating support to those schools already at the standard, such that none slip back below the standard, while some improve to a new ‘advanced quality standard’ level.[54]
  [54] To be defined as meeting four of the five output standards, with more than half the school’s teachers meeting advanced effectiveness benchmark
Targets for the extension (compared to the counterfactual of no extension) are as follows:

Table 2.10: Schools meeting quality standards
	Baseline (2013-14)	Yr 1 Extension (2014-15)	Yr 2 Extension (2015-16)	Yr 3 Extension (2016-17)	2017-18	2018-19
Schools supported[55]	10,117	11,308	11,308	0	0	0
QS schools	3,500	4,800	6,300	6,300	6,300	6,000
(of which) AQS schools	0	500	700	700	700	700
Counterfactual QS schools	3,500	3,000	2,750	2,500	2,250	2,000
Counterfactual (of which) AQS schools	0	0	0	0	0	0
[55] Including only Public Schools (and Mission Schools in Enugu). Not including any IQTE centres or nomadic schools.

Notes: QS = Quality Standard. AQS = Advanced quality standard.

In the counterfactual, it is assumed that there will be significant ‘slipping back’ of schools already at the quality standard. This is because many would only have had two years of initial support through ESSPIN, and this may prove insufficient to ensure the sustainability of improvements.

Working with and securing significant leverage from Government of Nigeria should achieve significant sustainability of ESSPIN’s impact. To capture this, the analysis considers how many schools remain at Quality and Advanced Quality standards for the two years immediately following the intervention. However, estimating the additional rate of return for students going to better quality schools is not straightforward. The following direct private wage returns will be assumed:

Students at non-quality standard (non-QS) schools	9.1%
Students at quality standard (QS) schools	9.5%
Students at advanced quality standard (AQS) schools	10.0%

Although sub-Saharan Africa countries usually achieve higher than average returns from primary education, the assumptions here are deliberately conservative given uncertainty over the level of the quality premium. The rate of return for QS schools is 5% higher than that for non-QS schools, while the rate of return for AQS schools is 10% higher. In ESSPIN’s 2012 composite survey, it was found that students in ESSPIN supported schools were twice as likely to achieve the appropriate Primary 2 numeracy standard and four times more likely to achieve the appropriate Primary 4 reading comprehension standard. This suggests that the quality premium may be very significant indeed. In any case, the sensitivity analysis will test altering the quality premium and consider what minimum level would be needed to justify the intervention.

The indirect private and social returns to education will be estimated as doubling the private wage returns. This is cautiously in line with McMahon (2004), who calculates that the overall social returns to education in Africa more than double the private wage returns. As already argued there is good reason to believe that the social benefits in Nigeria will be particularly strong.

Non-quantified benefits from the quality premium

To keep the analysis conservative and straightforward the following benefits will not be quantified:

- There should be some quality improvement in all schools that ESSPIN supports, even if they don’t improve enough to reach the Quality Standard threshold. In Kano, ESSPIN operates a slightly modified ‘School Improvement Programme’ that focuses only on teacher and head teacher effectiveness. These schools will struggle to reach the ‘Quality Standard’ despite having significantly improved teaching and school management. Nevertheless, students in these schools will also get improved returns to their education.
- ESSPIN will support 55,000 students in non-formal (Nomadic and IQTE) education centres. These students will also get higher rates of return from better quality education.
- ESSPIN’s inclusive education strategy is particularly focused on girls. As such girls should particularly benefit from improvements in school quality.
- The majority of ESSPIN’s schools will be in its three focus states in Northern Nigeria (8,593 out of 11,308). As already argued, given the greater incidence of poverty, conflict and health problems, social rates of return may well be higher for students supported in Northern Nigeria.

Measuring the enrolment and retention premium for ESSPIN

Better quality schools attract more students to enrol and should also mean less students drop-out. Over the course of 2009-2012, an additional 570,000 students enrolled in primary schools across ESSPIN’s 6 states. Girls accounted for 54% of this increase. The proportional increases in ESSPIN supported local government areas were on average 10% higher than those for non-ESSPIN supported local government areas in the same states (25% increase vs. 15% increase). Nevertheless, the exact attribution to ESSPIN is not certain and will be the subject of more focussed monitoring and evaluation in the extension.

For the present analysis, it will be assumed that ‘Quality Standard’ schools attract and retain additional 2.5% students, while Advanced Quality Standard schools get additional 5% students. The average non-quality standard school is assumed to have 290 students, based on data from 2009/10 in ESSPIN’s logframe handbook when all schools were effectively non-quality standard schools. As such, QS schools will be assumed to enrol 297 students, while AQS schools will enrol 305.

ESSPIN has a particular focus on social inclusion. Inclusivity cuts across all the output criteria required for achieving the Quality and Advanced Quality standards. There is in addition a standalone output criteria focussing only on whether schools have inclusive practices. As a result of this focus, which will be even stronger in the extension, ESSPIN’s existing phase has seen more girls than boys being additionally enrolled in school. As such it will be assumed that a higher proportion of the additional students attracted to and retained in schools will be girls.

The social benefits of girls going to school are generally believed to be higher than for boys.[56] In Nigeria and particularly in ESSPIN’s three Northern states the social benefits are likely to be high given the prevalence of early marriage and high infant and maternal mortality rates. For example, girls under 15 are five times more likely to die during pregnancy and child birth.[57] To simplify the analysis the additional benefits from girls rather than boys going to school will not be quantified, but considered a further non-monetised benefit of the extension.
[56] Schultz, P. (2002) “Why Governments Should Invest More to Educate Girls,” World Development, 30: 207-225
[57] UNFPA (2005) “State of World Population 2004. The Cairo Consensus at Ten: Population, Reproductive Health and the Global Effort to End Poverty”

Summary of benefits table

Table 2.11: Summary of quantified benefits
Who Benefits / An additional 0.4m (2014/15), 0.8m (2015-17), 0.9m (2017/18) & 1.0m (2018/19) students get a better quality of education at Quality Standard schools and consequently get higher wages and other indirect private benefits. / An additional 0.2m (from 2014/15 to 2018/19) students get a better quality of education at Advanced Quality Standard schools and consequently get higher wages and other indirect private benefits.	Quantification / Students at QS schools get additional 0.4% wage return for each year of higher quality education / (For this and below, all returns are calculated relative to a weighted average salary base for a primary student) / Students at AQS schools get additional 0.9% return for each year of higher quality education	Monetary Benefits / £3 per student from four years after the education for 18 years / £5 per student from four years after the education for 18 years
Wider society benefits from better educated students’ better health, reduced crime, more consideration for environment	Students at QS/AQS schools get additional 0.4%/0.9% social return for each year of higher quality education.	£3/£5 per student from one year after the education for 22 years
An additional 7 & 15 students (4 & 9 female) are enrolled at each school becoming QS & AQS respectively and consequently get higher wages and other indirect benefits from each additional year of education	Each additional student at QS / AQS schools gets 9.5% / 10% wage return for each year of education	£40 / £42 per student from four years after the education for 18 years
Wider society benefits from more students with more education having better health, reduced crime, more consideration for environment	Each additional student at QS / AQS schools gets 9.5% / 10% social return for each year of education	£40 / £42 per student from one year after the education for 22 years

Balance of costs and benefits

Table 2.12: Overall summary of costs and benefits (£ million)
(£ millions – Present Values)	ESSPIN Extension
Project investment costs	35
Directly leveraged GoN costs	15
Marginal costs to GoN (more children in school)	15
Marginal direct costs to students	1
Marginal indirect costs to students	15
Private returns to students	94
Indirect private and social returns	147
Total Net Present Value	164
Benefit-Cost Ratio	3.65
Internal Rate of Return	26.6%

Notes: All figures are discounted with a rate of 10%, as used across DFID Nigeria programmes. All costs and benefits are calculated relative to the counterfactual. NGN-GBP exchange rate of 250, USD-GBP exchange rate of 0.66.

The cost-benefit analysis finds a high net present value of £164m, a Benefit-Cost ratio of 3.65 and an internal rate of return of 27%. This represents a considerably higher return than the opportunity cost of capital often considered for developing countries of 10-12%. This suggests the investment represents very good value for money for DFID. When considering the previously outlined non-monetised benefits in addition to the programme’s calculated benefits, the economic case for the programme is even stronger.

The attribution of programme benefits to DFID is assumed to be 52%. This is the pro rata share of total inputs which are funded by DFID. The other 48% is for the Government of Nigeria accounting for leveraged funding supporting ESSPIN investments (24%) and additional costs from supporting more students staying in school longer (24%).

When considering only DFID’s input costs and the percentage of benefits attributed to DFID, the NPV becomes £87m and the internal rate of return remains at 27%.[58]
[58] The DFID specific NPV is lower because by only considering DFID’s attribution, both overall costs and benefits are lower – smaller projects with equivalent positive returns always have lower NPVs.

Risk and sensitivity analysis

Table 2.13: Sensitivity analyses
What if:	BCR	IRR %
QS Quality premium @ 4%	3.2	24%
QS Quality premium @ 2%	2.1	18%
No additional enrolment/retention	3.7	28%
Number of schools at quality standard @ 80%	2.7	22%
Number of schools at quality standard @ 60%	1.5	14%
GDP per capita @ 75%	2.7	22%
GDP per capita @ 50%	1.8	16%

Reduced quality premium – If the additional rate of return for Quality Standard schools falls to 2% (and the corresponding premium for Advanced Quality Standard schools falls to 4%) then the IRR falls to just below 20%. To find the break-even point for the project, the quality premium would have to fall to just 1%, combined with no enrolment gains.

This break-even point would imply students at QS and AQS schools would need a rate of return just 0.1% and 0.2% higher respectively than non-QS schools (9.9% & 10% vs. 9.8%), to justify the intervention. Given the proportion of students in ESSPIN schools already showing significant improvements in learning outcomes, going beyond this small increase seems highly likely. The large benefits from even a small quality premium emphasise the deep gains that can be made from supporting and leveraging resources for whole state education sectors. Both students and government pay large costs for primary school with or without ESSPIN’s support. Improving its quality, while leaving many of these costs unchanged has a very high return.

Reduced number of schools reaching quality standards – If the project fails to hit its targets for the number of schools reaching both QS and AQS, then benefits fall significantly. However, the project would have to achieve below 52% of its targets before project benefits fall negative.

No additional enrolment/retention – If better quality schools had no impact on increasing enrolment project benefits would not be greatly affected.[59] This emphasises that most of ESSPIN’s benefits come from improving quality of schooling, rather than attracting more children to school. However, both the additional value from marginalised students more likely to go to school and access to education being a human right are significant unquantified benefits that strongly justify the project’s goal of increasing enrolment.
[59] In fact, while the NPV decreases, the IRR and BCR actually increase. This is because returns from the quality premium are at a higher rate than from the enrolment/retention premium. Decreasing enrolment gains decreases overall returns to the intervention, but while decreasing costs to government it increases the average rate of return on a given pound of their investment. (The rate of return on leveraged funds spent on school improvement is higher than the rate of return on additional costs from more children being enrolled in school. Both rates of return are, however, positive).

GDP per capita – If average incomes in Nigeria were lower, this decreases the benefits by decreasing the overall returns from education. However, GDP per capita would have to fall massively (and unrealistically) low to make project benefits negative. Nevertheless, this emphasises the complementarity between supporting the education sector and DFID’s other investments supporting Nigeria’s private sector and overall economic development.
Climate and Environment Assurance Note

See Annex 2

Measures to assess Value for Money

ESSPIN has performed impressively on VfM to date with unit costs for achieving key results measured and reported consistently over the last two programme years. A clear strategy has been adopted to drive unit costs down without compromising on impact. For example, the proportion of international to national TA has reduced from 71% at the start of the project (2008) to 38% this year (2013), achieved through a careful strategy of gradually building up the capacity of national consultants. ESSPIN’s monitoring of unit costs quarterly also shows falling unit costs for key indicators during the 5th year of the programme.

Table 2.14: Quarterly monitoring of key VFM indicators
Indicator	Jan-Mar 2013	Apr-Jun 2013	Trend
Schools trained to use a School Development Plan	£734	£600	Down £134 (18%)
Head teachers trained to operate effectively	£1,163	£758	Down £405 (35%)
Teachers trained to deliver competent lessons	£338	£282	Down £56 (17%)
Community members trained to set up SBMCs	£112	£71	Down £41 (37%)

Source: ESSPIN Quarterly reports

Unit costs for delivering training to SBMCs and teachers compare favourably to other major education programmes. In 2012, it was estimated that it cost £183 for ESSPIN to train one teacher for 6 days, with 10 days’ follow-up support in the classroom.[60] Whereas UNICEF’s unit cost for training one teacher at a workshop for 5 days was £341. The cost to ESSPIN for a public teacher who can deliver competent lessons in numeracy and literacy was £140. Assuming the teacher supports 50 students per year and continues teaching for 20 years, this would represent a cost per student who benefits from improved teaching of just 1.5 pence.
[60] Incorporating an estimate of the salary cost for the State School Improvement Team, who are paid for by the Government, not ESSPIN.

The recent annual review (2013) made some useful recommendations to improve ESSPIN’s approach to VFM, the response to which is set out below. It also confirmed that ESSPIN continues to represent good value for money for DFID. ESSPIN has been effective at generating leverage from Government of Nigeria. In Year 4 of the project alone (2011-12), nearly £21 million of investment was leveraged for school improvement, in addition to other funding for State education sector plans (MTSS). Targets for the extension are ambitious and contingent on 70% of direct ‘school improvement plan’ costs being leveraged from Government.

ESSPIN’s approach on VFM during the extension

Since 2011, ESSPIN has been putting in place good quality management and monitoring systems to be able to report on the indicators of economy, efficiency and effectiveness. The extension of ESSPIN will build on this strong foundation and respond to the recommendations of recent Annual reviews. Annex 3 sets out a comprehensive range of indicators for monitoring ESSPIN’s VfM covering economy, efficiency, effectiveness, cost-effectiveness and equity.
VFM will be further strengthened by ensuring that all indicators are captured systematically both in terms of ‘what it costs to pay for an input’ (e.g. training a teacher) and ‘what it costs to achieve the corresponding output’ (e.g. an effective teacher). This will enable better understanding of whether output costs are driven by input costs, or by poor rates of converting inputs into outputs. A further area to be built on is reporting every VFM indicator by State. ESSPIN operates in six widely contrasting states across Nigeria with project implementation differing in each one. This offers a rich data-set to further interrogate value for money. Where output costs are low in one particular state, it will be possible to analyse how this can be carried across to other states. In the extension there will also be a greater focus on using VfM data for regular management decision-making, beyond simply reporting on VfM data.

In terms of the overall economic costs, it is not just financial costs to DFID which matter. In the extension, ESSPIN will report on the cost burden imposed on others. This is being done to some extent for costs imposed on Government for the SIPM[61]. During the extension it will be systematically considered for the implementation of certain inputs. For example, training teachers could take them away from teaching and away from school; or attending SBMC meetings may incur travel costs for the participants. ESSPIN’s VfM should be strong in this area, particularly as it adopts a ‘school-based’ training approach, which avoids taking teachers out of the classroom for lengthy workshops.
[61] A full picture would have to consider how many additional children enrol and stay in school as a result of ESSPIN and so incur additional costs on Government for providing their education.

ESSPIN’s effectiveness indicators are modified from the existing phase of the programme. This is because the existing indicators cannot reasonably have costs comprehensively attributed to them. The new indicators will not be in terms of cost, since the measures are instead capturing how well ESSPIN’s outputs will be converted to impact. More children in Quality and Advanced Quality Standard schools will mean more children having the chance to improve learning outcomes. More children going to school overall is an impact in itself and will also increase the number of students benefitting from outputs and thus in turn increasing the number of students achieving learning gains. More resources invested by both Government and school communities in basic education will both help achieve outputs in the first place, as well as improving the conversion of these outputs into better student learning. It should also improve the sustainability of the ESSPIN’s gains, a vital aspect of the economic benefits.

The extension will monitor two headline cost-effectiveness indicators:
- Cost per additional student reaching proficiency in numeracy and literacy at P2 and P4
- Cost per additional student achieving improved learning outcomes.

These two indicators will be measured relative to total programme cost, since all inputs contribute to this impact of student learning. The second indicator is broader than the first. Only considering students that reach a particular literacy and numeracy competency standard at P2 and P4 will significantly understate project cost-effectiveness. The most recent Annual Review has highlighted that the Composite Survey should allow for measures of learning gains beyond this.

Measures of equity should always complement a VfM framework. This is because while supporting more marginalised students is often more expensive, this does not mean it should be neglected in a pursuit of driving down unit costs. The economic benefits from improving outcomes for the most marginalised in society are higher than those for achieving the same outcomes from more fortunate individuals, so ESSPIN’s performance with regard to equity will be a key element of reporting on Value for Money.

Other requirements for a full VfM assessment

To relate benefits to the economic analysis requires an assessment of the extent to which being in a Quality or Advanced Quality Standard school leads to improved learning outcomes and improved retention/enrolment. This is also important to test the ESSPIN ‘theory of change’ that a holistic approach to school improvement is required to achieve learning gains. Given that many schools will achieve different standards for each component of the School Improvement Programme this could help inform what the optimal balance of scarce resources should be across the SIP sub-components (teacher effectiveness, Head Teacher effectiveness, school development planning, functional SBMCs).

When would the programme no longer represent Value for Money?

As seen in the economic appraisal, the economic return from this project is almost wholly from improved school quality and learning outcomes, with only marginal gains from increased student enrolment. As such the Value for Money of ESSPIN becomes questionable to the extent that there are minimal improvements in school quality or learning gains. Since learning gains often do not immediately manifest themselves, requiring students to be in an improved learning environment for a sustained period, they will not be fully captured by assessments before project end. Similarly, learning assessments will only look at two grade levels – P2 and P4. Nevertheless, if there are no statistically significant learning gains, then conclusively the project will not represent value for money.

More immediately measurable will be judging how many schools reach Quality Standard and Advanced Quality Standard. Following the project’s Theory of Change, if a school meets the Quality Standard criteria then students should enjoy improved learning. This has been shown to be the case in the 2012 Composite Survey. As seen in the economic appraisal, if less than 3,300 schools are at the Quality Standard then ESSPIN would no longer be value for money. This 3,300 figure would mean achieving only 52% of the actual ESSPIN target.

Value for Money Statement for the preferred option

The economic appraisal has demonstrated the programme should be very good value for money with a NPV attributable to DFID of £87m and an IRR of 27%. This case is further strengthened by the existence of benefits that cannot be quantified. Nevertheless, the Value for Money framework is vital to ensure that this value for money is maximised during programme implementation.

3.	Commercial Case

Direct procurement through a contracted supplier

Clearly state the procurement/commercial requirements for intervention

The commercial requirement in this case is to obtain technical services and programme management to the highest possible standard at the least possible cost. Three possible routes to obtaining the additional services required were considered: (1) to negotiate a cost extension with the existing consortium of service providers, (2) to obtain additional services through a separate open tender, or (3) to invite UNICEF to manage the extension alongside its management of GEP3. Option 3 was dismissed following an early decision that UNICEF needs to focus on implementing their existing DFID portfolio.

DFID Nigeria has secured agreement from the Procurement Group to proceed with single source procurement. The reasons for favouring a single tender extension in preference to fresh competition are set out in the next section. Procurement activities for this extension phase are set out below:

- DFID will contract Cambridge Education to provide technical assistance for implementation through a consultancy contract
- Disbursement of grants to schools in communities will be managed by Cambridge Education through a ‘Managed Fund’ to be approved as part of the consultancy contract
- Contracting for works and services will be done by Cambridge Education from the ‘Managed Fund’.
- Procurement of vehicles and equipment will be through ‘Crown Agents Nigeria’ under a core country agreement with DFID Nigeria
- External evaluation, annual reviews and audit services will be managed separately by DFID through existing service providers (e.g. IMEP/ECORYS, EDOREN/Oxford Policy Management) under commercial contracts already issued by DFID Nigeria.

How do we expect the market place will respond to this opportunity?

ESSPIN is a large contract and strategically important for the consortium leader (Cambridge Education). It is also an important source of business for key consortia members (British Council, Social Development Direct, and Save the Children) and their involvement builds their credibility to undertake future work for DFID and other development partners elsewhere. There are reputational benefits to be derived from a continued association with this successful programme.

It is considered highly likely that serious competitors will be deterred from investing in bids. Bidding for such a large and complex programme will be costly. The risk of not winning is significant when faced with the reality of the current situation. The present consortium is in a strong position for the following reasons: the management and delivery infrastructure is in place in Abuja and across six states, the implementation teams are fully resourced with capable staff (with a significant proportion of the expertise provided by Nigerians) and most importantly, the programme is delivering with visible signs of success at a time when security issues add to the complexity of operating effectively.

The risk to prospective bidders will be exacerbated by the fact that a very extensive pool of experts with Nigerian experience is committed to the existing provider. Putting together a similar pool would be very challenging, and luring existing ESSPIN consultants away would be difficult if the existing consortium was seen as being likely to win in a competitive bidding scenario.

Taking all of these factors into account and faced with the evident success of the present consortium, prospective bidders are unlikely either to bid at all or be able to submit credible, competitive bids in terms of lower costs and/or higher quality.

However, in principle, a market exists. An ‘ESSPIN extension’ could be tendered to the 16 companies pre-qualified under the education sub-sector of the Fragile and Conflict-Affected States framework. However, the ‘Teacher Development Programme’ recently tendered through this framework, attracted only two responses. This limited response occurred despite the absence of an existing service provider on the ground. An extension of an existing programme, with a long-established incumbent with a successful track record, will not be more attractive to the market.

Finally, it is unlikely that going out to a new competitive bidding process will result in value for money. In addition to the bidders’ costs, there will be significant transactional costs to DFID in issuing bidding documents, evaluating bids, short listing potential service providers and selecting the preferred bidder. These costs are only justified where there is reasonable expectation that DFID will be able to select a more cost effective bid than it will be able to negotiate through a single source contract. The evidence presented above suggests that a competitive bid, incorporating substantial cost reduction and quality improvement benefits, is highly unlikely to materialise.

How does the intervention design use competition to drive commercial advantage for DFID?

The threat to revert to an open competition will be implicit in telling the incumbent that DFID will require further savings to be surrendered if we are to proceed with a single-sourced, cost extension. However, the consortium may well perceive the likelihood of our not proceeding, if savings cannot be secured, as being low. The desire to strengthen their relationship with DFID, to maintain a significant presence in the Nigeria market through continuing a positive relationship with ESSPIN, may be stronger drivers of a willingness to reduce costs further. Working with DFID Procurement Group, we will ensure a detailed negotiation with the service provider, to ensure that inputs and costs are realistic, and that the proposal meets in full our interests related to quality, timeliness, cost, and overall value for money.

What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?

Major cost elements include fee rates for technical experts, accommodation costs and per diems, security costs, and the cost of administering the programme. There are a number of elements that affect the price. These are management costs spread between salaries, direct overhead costs relating to the provision of staff and brought-in consultancy (e.g. medical insurance, visas), indirect overhead costs to contribute to the costs of being in business, such as corporate operations, managed funds for programme support activities, recruitment, back office administration, headquarters cost. The quality of consultants is critical to adding value in a programme seeking to influence major government policies and spending decisions in a country that is not aid dependent. With a difficult security situation, it is a challenge to find highly capable consultants for key long-term roles that arise, to attract people willing to work in the North, and to keep costs down. Due to the conflict and insecurity, consultants cost more, and the cost of keeping them safe also increases.

How will the contract be structured, and how will contract and supplier performance be managed through the life of the intervention?

Additional resources would be added to the Cambridge Education contract, in the form of a contract amendment for a cost extension for a maximum sum of £33 million over 30 months. We would aim to sign for less, through a model that incentivises payment by delivery, or at least a higher percentage of the contracted fees payable on delivery of tangible outputs. During the negotiation of the contract extension, the option for introducing an element of ‘payment by results’ will be discussed and agreed. The remaining funds (£2m) will be managed separately by DFID for External Evaluation, Reviews and Audit. These services will be provided by existing service providers (ECORYS, OPM) already commercially contracted by DFID Nigeria to provide these services for other DFID programmes.

4.	Financial Case

Overview of costs

The expected cost of the extension is £35 million over 2.5 years. Table 4.1 gives the approximate breakdown of these costs by programme year.

Table 4.1: Approximate breakdown of extension costs by programme year
2014/15	2015/16	2016/17	Total
£15.0m	£15.2m	£4.8m	£35m

Table 4.2 gives the cost breakdown by programme component.

Table 4.2: Approximate breakdown of extension costs by programme component
Component	Amount (£ million)	% of total
Output 1	2.9	8
Output 2	4.0	11
Output 3	14.1	40
Output 4	5.4	15
Internal monitoring & research	2.9	8
Project Management	3.2	9
Crown Agents	0.5	1
External evaluation and audit	2.0	6
TOTAL	35	100

Cost profiling and forecasting

The expected monthly costs for the first year of the extension and quarterly costs for the following year and a half are as follows:

Table 4.3: Approximate breakdown of extension costs by month for July 2014 to June 2015 (£m)
Jul	Aug	Sep	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun
1.4	1.2	1.2	1.5	1.2	1.2	1.3	1.2	1.2	1.2	1.2	1.2

Table 4.4: Approximate breakdown of extension costs by quarter for July 2015 to December 2016 (£m)
Jul-Sep 15	Oct-Dec 15	Jan-Mar 16	Apr-Jun 16	Jul-Sep 16	Oct-Dec 16
3.7	3.8	3.8	3.9	3.4	1.4

Financial and Fraud risk Assessment

There are four key financial and fraud risks:
1. Risk of funds being misappropriated
2. Risk of funds not being used as intended
3. Risk that expenditure does not represent value for money for DFID.
4. Risk of loss due to reduced financial management and oversight in conflict affected locations.
The risk of financial loss is low. The rationale for this assessment is presented in Figure 4.1 below

Figure 4.1: Financial and fraud risk assessment
Risk	Probability	Basis for assessment	Mitigation
Risk of funds being misappropriated	Low	No significant losses identified related to fraud since the start of ESSPIN. Internal financial controls adopted are effective. All expenditures incurred only following properly authorised requisition and payment procedures in line with the delegated authorities specified in the programme’s Finance Manual. This Manual mirrors the parent company’s authorisation protocols which sets fixed limits for authorisation of payments for different categories of expenditure or commitments. Similarly there is a Procurement Manual; procurement of large items will be undertaken by DFID’s procurement agent In Nigeria, compliance with these financial procedures and practices are subject to checks by the service provider’s UK based internal audit as well as the annual audit of the parent company. State teams are audited regularly by staff visiting from Abuja. Furthermore there is an ethical code of behaviour for all staff to follow; non-compliance results in disciplinary proceedings. All ESSPIN staff have completed a mandatory training course on business ethics, and signed a declaration ‘Business Ethics: Getting It Right - Policy Compliance’. The parent company became the first company of its kind to be independent externally accredited for its anti-bribery practices, conforming to BS10500[62].	The effective controls adopted in the programme will continue into the extension: / All DFID funds will be managed by the lead service provider / DFID will continue to commission annual independent audits / Service provider’s HQ will continue to check on compliance with corporate standards and guidelines
Risk of funds not being used as intended	Low	ESSPIN, through its detailed work planning process and progress reporting, is able to demonstrate that programme funds are used for the purposes intended as agreed with DFID. Quarterly spending versus budget reports are produced by ESSPIN at a summary level by Output and these are reviewed jointly with DFID at the quarterly meeting of the Programme Management Team chaired by DFID.	Existing programme monitoring and reporting arrangements will continue for the extension. Annual independent reviews will verify the results reported by the programme. Composite Surveys in 2014 and 2016 will highlight effectiveness of programme spend.
Risk that expenditure does not represent value for money for DFID.	Low	2013 Annual review confirmed ESSPIN’s delivery of VfM. Procurement of goods is carried by DFID’s contracted procurement agent – Crown Agents. Any school infrastructure works procurement is done through an open and transparent process. Independent engineering consulting firms are hired to monitor and report on quality of work done.	DFID will continue to scrutinise value for money assessments reported through Annual Reviews. Programme Management Team will review routinely the programme’s compliance with the VfM framework.
Risk of loss due to reduced financial management and oversight in conflict areas	Medium	ESSPIN has had to limit travel to some locations, particularly for international staff. If security conditions worsen, there is a risk it could become more difficult to exercise sufficient oversight over operations. However, programme management is led by Nigerian and located in Abuja where the majority of management and financial systems coordination takes place.	DFID will continue to ensure, as much as possible, that independent review and audit teams visit all programme locations including those in conflict affected areas.
[62] BS 10500:2011 - Specification for an anti-bribery management system (ABMS)

ESSPIN is supporting DFID Nigeria with the implementation of its Anti-Corruption Action Plan 2012-15, particularly through support to better public sector management in education. Efforts will continue through the programme’s assistance of Medium Term Sector Strategies (MTSS) and annual budgeting and planning, strengthening procurement procedures, education public expenditure reviews and tracking, and on accountability - building the capacity civil society organisations and school based management committees to scrutinise education budgets and the results of education services for their children.

Monitoring, reporting and accounting for funds

Monitoring and accounting of expenditure will take place using the ARIES system and standard DFID Nigeria procedures for inspecting invoices to ensure Value for Money and compliance with agreed fees and reimbursable costs. ESSPIN will provide DFID with monthly statements of costs for invoicing and reimbursement purposes. The format will be in line with that specified in the contract. In addition, ESSPIN will submit quarterly financial statement to DFID summarising, by Output, the actual spend against the agreed budget both for the current quarter and for the ESSPIN financial year[63] to date. Any significant differences between spend and budget will be explained. Also, there will be a facility to analyse spending data in more detail using the programme’s Excel based accounting system and its Chart of Accounts. Annual financial statements will be prepared by ESSPIN and these will be subject to a DFID commissioned independent Audit.
[63] ESSPIN’s financial year is July to June; Government’s financial year is January to December; DFID’s financial year is April to March

On a periodic basis, the Service Provider will be required to provide all financial information for the Value for Money framework outlined in the Appraisal Case. Agreed unit costs will be monitored as follows: (a) economy unit costs estimating value of inputs will be reported quarterly in Quarterly reports, (b) efficiency unit costs estimating cost of annual results achieved will be reported annually in Annual Reports and (c) effectiveness unit costs estimating programme cost of impact will be reported every two years to coincide with the Composite Survey.

Financial accounting considerations

There are no financial accounting considerations. At the end of the programme in January 2017, Cambridge Education will submit to DFID for approval a ‘disposal plan’ for the assets purchased with the programme’s funds in line with DFID’s assets management guidance note.

5.	Management Case

What are the Management Arrangements for implementing the intervention?

DFID management

DFID Nigeria will oversee implementation of the programme through the ‘Programme Management Committee’ (PMC). Membership comprises (a) DFID Programme Officer, Education Adviser and other cross cutting advisers where relevant, and (b) ESSPIN’s Senior Management Team (SMT). In addition to the PMC, DFID’s State Representatives will have routine contact with ESSPIN’s state teams. These representatives will attend the state level steering committees when convened.

The PMC will meet quarterly to review technical and financial progress reports, and agree forward work plans and budgets prepared by ESSPIN. The risk assessment and mitigation strategy and value for money framework will be reviewed every six months. The results of annual reviews in 2014, 2015 and 2016, and the analysis and findings provided in the July 2014 and July 2016 Composite Surveys will be scrutinised by the PMC. Contract administration will be led by DFID UK, in liaison with DFID Nigeria.

Service provider

ESSPIN’s National Programme Manager will report to the DFID Programme Officer. At the national level, ESSPIN’s SMT will be responsible for the overall management of the programme and the routine supervision of the six state teams. Each State will have a fully resourced ESSPIN Team headed by a State Team Leader reporting directly to the Deputy Programme Manager in Abuja. Reporting by each state team will consist of the following: a weekly security bulletin; monthly financial returns and summaries, three month rolling work plans (including cash forecast and leveraging estimates), and quality assurance details; a quarterly narrative report providing updates on security and travel, political economy, leverage and political engagement and risk management plus a key results table (for past quarter and year to date). In addition, there will be regular Technical Team meetings where the national and state teams come together to discuss progress, share experiences, raise any issues of concern, and explore the need for any refocusing of the programme’s activities.

Role of State Governments

The routine oversight of the programme in each state will be led by the respective Education Commissioners who are members of the State Executive Council, chaired by the Governor of the State. The Permanent Secretaries in the State Ministries of Education are the key administration contact points for the ESSPIN State Team leaders. The Chairpersons and Executive Secretaries of the SUBEBs, together with the Education Secretaries of the participating LGEAs, represent the main contacts for routine operational matters. The Education Commissioner will chair the ESSPIN Steering Committee with its membership drawn from the key stakeholders in the education sector. The main role of the Steering Committee will be to provide political and technical oversight of ESSPIN’s work in the state. It will receive the work plans and progress reports prepared by the ESSPIN state team leader. In addition to the ESSPIN Steering Committee, there is an overarching committee, chaired by the Secretary to the State Government, to oversee the three state level programmes (SLPs) funded by DFID.

In addition to the state specific structures, ESSPIN will continue to facilitate regular quarterly meetings of the Education Commissioners’ Forum. This Forum provides the mechanism to share lessons learned, to discuss any issues of common concern relating to ESSPIN implementation, to seek solutions to shared problems and to enable ESSPIN to keep current on issues relating to the political economy of education service delivery both nationally and within the partner states. Management arrangements are depicted in Figure 5.1 on the following page.

What are the risks and how these will be managed?

The programme is assessed as medium risk. Two of the three major potential threats relate to the programme’s success in leveraging Government funding for the roll out of the SIP and the forthcoming national elections in 2015. These two risks are interlinked, in the sense that the availability of current levels of funding, and potential additional commitments, may be affected by the shifting spending priorities in the period running up to the election and also in the year following the election. The expectation is that the 2015 and 2016 budget releases will be unpredictable.

The programme will respond to this uncertainty through maintaining close links with its partners in the state as well as tapping into the information and influence of DFID’s other state level programmes operating in the ESSPIN states. Through this network, early signs of funding going ‘off track’ should be identified. In addition, the programme will retain flexibility in its ability to refocus efforts to areas where progress continues to be made with the scope for reallocating its own resources away from non-productive, and towards productive, areas.

The third major risk relates to security. Continuing violence in the North, although focused currently in Yobe and Borno states, will have a ‘spill over’ effect on the ESSPIN states such as Kano and Kaduna. Any barriers to ESSPIN working unhindered in its states may slow down implementation, possibly dilute the quality of its engagement with its partner states and definitely will result in increased costs. The programme will respond to these potential security risks through maintaining its close and well informed security risk monitoring system which has been in operation, successfully, for the last two years.

Figure 5.1: ESSPIN Management Structure

State programme x 6
National programme

DFID
State
Reps
Steering Committee
DFID State Level Programmes

Legend:
Formal reporting and accountability
Flow of information/communication
Contract management

ESSPIN State Team Leader

SBMCs at
 LGEA level
State Ministry of Education
Steering Committee SLPs
ESSPIN State Team
ESSPIN States
Education Commissioners’ Forum
State Executive Council
Federal Ministry of Education
National Planning Commission
DFID Abuja, ESSPIN Programme Management Committee
Service provider
UK
DFID
UK
ESSPIN National Team
ESSPIN Senior Management Team
Steering Committee ESSPIN
The full risk analysis, together with the proposed mitigation measures, is presented in Table 5.1 below.

Table 5.1: Risk analysis and mitigation
#	Risk	Mitigation	Residual risk rating L/M/H
			Prob’ty	Impact	Overall
Political risks
1	Changes at any time in the leadership group, within the education organisations at federal and state levels, result in less support to the ESSPIN programme.	Engage with second tier leaders, technical and admin cadres to maximise likelihood of continued support despite change at the top. / Disseminate compelling evidence of impact to persuade new incumbents to sustain support to ESSPIN.	M	H	M
2	The post 2015 election changes bring in a new administration which is not supportive of the previous Government’s agenda for education.	Engage with opposition representatives and particularly with state transition committees in partnership with DFID and SLPs.	M	H	M
3	ESSPIN implementation will slow. Pre and post-election hiatus will disrupt and delay decision making as the attention of key personnel in Government is diverted to elections issues	Judicious use of ESSPIN contingency funding to maintain momentum.	M	M	M
4	Post UK national elections in 2015, DFID’s education programme in Nigeria is scaled back resulting in reduced ESSPIN funding.	Effective communication of ESSPIN evidence of impact to bolster support for Nigeria education investment and ESSPIN specifically.	L	M	L
Funding risks
5	Existing state funding commitments to SIP rollout do not continue due to the pressure of other spending priorities in the 2015 and 2016 state budget allocations and releases. Similarly, new commitments do not emerge for the same reason	Build commitments from alternative funding sources (GPE, CIFF, BMGF, IDB) which do not depend on the Nigerian political cycle.	M	H	M
6	ESSPIN implementation targets are not met due to insufficient Government funding. States fail to deliver the scale of the additional funding needed for ESSPIN to reach its targets in full.	Be flexible and responsive in reprioritising ESSPIN spending between states. Political engagement at highest levels of DFID/HMG with GON and states.	M	M	M
7	Flexibility in the UBEC IF for Teacher Professional Development is removed which reduces the funding available to states for SIP (and to a lesser extent SBMC) roll out	Active engagement already underway with UBEC and SUBEBs to prevent restrictive alteration of UBEC TPD Guidelines.	M	H	M
Safety and security risks
8	Conflict in the North prevents ESSPIN staff visiting with the resulting slowdown in implementation.	Capacity development of in-state teams and national team members. Increased reliance on SSIT/CGP for cross-state support. Adaptive security stance by ESSPIN.	M	H	M
9	ESSPIN-supported schools are targeted by insurgents thereby severely disrupting the schools’ ability to operate normally with the full pupil and teaching complement.	ESSPIN support mainstreamed through state and local authorities, without branding, particularly under roll-out.	L	H	M
10	ESSPIN engagement with the IQTE schools is prevented thereby limiting the programme’s approach with developing integrated education.	Careful groundwork with malams and community before engaging in any IQTE expansion. Demand-driven participation only.	L	L	L
Implementation risks
11	Performance of ESSPIN schools falls back due to reduced state funding during 2015 and 2016	Continued professional development of SSIT and SSOs to bolster their performance and support function.	M	M	M
12	Lack of budget discipline and ineffective utilisation of budget allocations by education MDAs.	Quarterly monitoring reports and political engagement with sector leaders making MTSS process and budget discipline increasingly meaningful and relevant.	M	M	M
13	Resistance to inclusive education approach leads to continued marginalisation of disadvantaged children.	ESSPIN inclusive education approach mainstreamed in education sector systems, planning and continuous professional development, as well as in training.	L	L	L
14	Failure to implement an SBMC IF equivalent to TPD IF restricts progress on school governance.	Intensive lobbying of drivers of change in UBEC and SUBEBs, plus FME, SHOA and IDPs.	M	M	M
Value for money risks
15	Increased costs arising from worsened security in the North squeezes out funding for programme delivery	Deepen efforts to collaborate with peer programmes on security risk mitigation measures.	M	L	M
16	Targets are not met with the available funding	Iterative budget adjustments as better data on costs and leverage flow through.	L	M	L
Climate and Environment Risks
17	Poor disposal of materials used for learning products could impact local environment. School borehole projects could impact local environment.	Align environmental safeguards of Service provider with those endorsed by DFID to encourage best practice for more sustainable resource use.	L	L	L
18	Natural resource scarcities influence changes to coping strategies, declining pasture, inadequate to water and health could affect attendance and learning.	Explore opportunities to raise awareness and knowledge base on the linkages between climate change and education. Nominate a DFID Climate and Environment Adviser to oversee the ESSPIN.	L	L	L

The relative significance of each of these risks is mapped in Figure 5.2 below as an impact-probability matrix.

Figure 5.2: Impact-probability matrix

Impact	High	9	1, 2, 5, 7, 8
	Medium	4, 16	3, 6, 11, 12, 14
	Low	10, 13	15
		Low	Medium	High
Probability

These risks, plus any emerging threats to the likely success of the programme, will be monitored quarterly as part of the review and reporting process.

Responding to climate change and protecting the environment

During the extension, ESSPIN will explore opportunities to do more to promote adaptation to climate change, and environment protection through its existing school networks established in 6 States. Opportunities could include:
- Working with local leaders to ‘scale up’ initiatives on ‘greening’ of schools,
- Integrating information on climate change and adaptation into SBMC training, head-teacher and teacher training curriculum, classrooms instructional materials and lesson plans,
- Partnering with local CSOs to deliver workshops and debates regarding the environment and climate change in schools, particularly around adaptive livelihoods.
- Working with SMBCs to pilot environmental activities such as water harvesting, recycling of materials, and school gardens.
To ensure the sustainability of initiatives, pilot activities will be planned and implemented with the State Government agencies responsible for Education, Environment and Climate Change.

How will progress and results be monitored, measured and evaluated?

Monitoring Plan

ESSPIN has in place an extensive monitoring system which enables it to review progress from increasingly diverse complementary perspectives[64]. The system comprises two elements: ‘input and output monitoring’, which will assesses whether work plans are being realised, and ‘output to purpose monitoring’ and ‘impact monitoring’, which assess whether results are being achieved. The results of this monitoring ensures that reliable and timely information is used to (a) enable the State MoE and SUBEB in each focus State to take informed policy decisions, (b) provide information that will inform FME policy and strategy decisions and (c) enable ESSPIN management and DFID to review performance against clear measures based on sound evidence and take action as required to ensure key targets are met. There are three types of indicators used in the monitoring system:
[64] ESSPIN (2012) “Monitoring and Evaluation Framework”
1. Logical framework (logframe) indicators
2. Work plan indicators
3. School resource indicators

The logical framework and its indicators are detailed in Annex 1. Work plan indicators feed into the Results Monitoring Table which is reviewed quarterly by DFID[65]. School resource indicators are used by the education authorities in each state to inform their own planning processes. Wherever possible, ESSPIN’s monitoring system is integrated with, and intentionally intends to strengthen, the states’ own approach to accessing data to inform decision making.
[65] Copy of the Results Monitoring Table is available in all ESSPIN quarterly reports.

ESSPIN’s reporting feeds into DFID’s Operational Plan headline results as well as central education indicators on the number of additional children supported in schools. A new dimension is that the lograme now includes indicators to capture progress on learning outcomes at impact level. This responds to a broader shift in DFID to develop learning indicators for all its education programmes. ESSPIN has made good progress in developing an approach to quantify these results, initially through the ‘Monitoring Learning Achievement’ assessments (2010) and more recently through the Composite Survey (2012). Both survey instruments tested pupils’ literacy and numeracy abilities after two years and four years of schooling. Learning outcomes will continue to be assessed through the Composite Surveys scheduled for 2014 and 2016. Further work to align with emerging global learning metrics, and to explore alternative measurement approaches will be supported by DFID in Nigeria and London.

ESSPIN uses a wide range of mechanisms for data collection and analysis, and these include administrative and regular monitoring data sources[66] supplemented by surveys and studies[67]. It is a continual challenge to ensure that data collected through administrative systems is accurate and complete. In addition to quantitative data analysis, ESSPIN uses a qualitative ‘self-assessment’ methodology to assess progress and results especially in those areas relating to capacity and organisational development[68].
[66] These include: Annual School Census, School Support Officer Reports (SUBEB – School Services Department), Civil Society-Government Partnership Reports (SUBEB – Social Mobilisation Departments), SUBEB records (Works and PRS Departments), UBEC disbursement records and Annual FME Report on Four-Year Strategy
[67] These include: Household Surveys (including NEDS), State Annual Self-assessment Exercises, Public Expenditure Studies on School Improvement , Composite Survey (incorporating elements of Monitoring of Learning Achievement, Classroom Observation Survey, Teacher Development Needs Assessment, Head Teacher Survey and Community Survey), EMIS Verification Survey
[68] Self-assessment is used to measure improvements in: national systems at the federal level; quality of education management systems at state and LGEA levels; quality of civil service advocacy at community level; and extent of inclusive education policies at state level

Annual Reviews and Audits will be carried out in 2014, 2015 and 2016, and will be contracted independently by DFID to assess progress of the programme. The Annual Review in 2013 recommended the need for continued data quality assurance of EMIS. Two validation exercises have been conducted to date using a contracted independent company. In discussion with DFID, it has been agreed that the EDOREN Initiative will be responsible for subsequent data quality assessment and EMIS validation during the extension.

The Value for money framework is included in Annex 3.The proposed indicators for the VfM monitoring are fully detailed in the VfM framework as earlier set out in the Appraisal Case. During the extension, the VfM framework will be adopted to help inform regular management decision making processes which will be achieved via a joint ESSPIN/DFID dialogue.

Presently the programme is assessed as medium risk. The national elections in 2015 may have negative consequences on ESSPIN’s ability to leverage Government funding; shortfalls in funding will affect the programme’s ability to meet its targets. In terms of monitoring the security situation, ESSPIN has developed an effective approach with a tightly knit network of State offices providing routine feedback. This close and well informed monitoring will also continue.

Evaluation and Research Plan

A central element of the evaluation plan during the extension is repeating the ‘Composite Survey’ (CS) to assess the effectiveness of head teachers, teaching-learning practices, the functioning of SBMCs, together with an assessment of student learning achievement. The first Composite Survey, relating to ESSPIN performance to July 2012, was published in March 2013 and provided strong evidence of the success of the programme. The Composite Survey will be repeated mid-2014 and mid-2016 with sufficient time for the analysis to be completed and results disseminated before the end of ESSPIN in January 2017. Surveys will provide trend data and help inform State level decision making and will be supplemented by qualitative research to build understanding about why teaching and learning outcomes are changing.

The recent 2013 Annual Review[69] strongly recommended to supplement the Composite Survey with additional qualitative research to fully understand ‘how particular components of the integrated school improvement programme are making a difference and why… to be able to demonstrate and explain the value added of particular interventions in some detail and in a way that can be tracked over time’. Research was particularly recommended to better understand the impact of 1) institutional changes at the national and state level, and 2) functional school based management on changes in student learning outcomes. It was also suggested that ESSPIN should investigate the impact of conflict on education in Northern States. Following further discussion and agreement with DFID, a ‘deepening’ of the evidence base for ESSPIN will be commissioned, in part through the existing ‘Education Data, Research and Evaluation in Nigeria’ (EDOREN) Initiative, contracted to OPM, with additional funding of up to £1 million.
[69] IMEP Annual Review of ESSPIN, June 2013

DFID Nigeria is intending to evaluate the suite of 5 State Level Programmes (SLP), of which ESSPIN is a part. The SLPs have been chosen as candidate for evaluation, using the key criteria in the DFID Nigeria evaluation strategy, due to the size and the significance of these programmes. The principle rationale for the evaluation is to provide accountability, both to the UK taxpayer and the Government of Nigeria, for the £400 million that has been allocated for these 5 State level programmes. It will also identify key lessons learnt to inform future programme development in Nigeria. The SLP evaluation will be implemented for DFID Nigeria by the ‘Independent Monitoring and Evaluation Project’ (IMEP) contracted to ECORYS. The evaluation was originally planned for 2015 but dates will be revisited once the extension plans for the SLPs are concluded, and to consider best timing for influencing future decision making. Summary evaluation questions include:
- Is there evidence that the suite of SLPs has had its anticipated impact?
- Do any changes appear to be sustainable?
- In the light of these two findings, does expenditure on the suite represent reasonable value for money?
- What are the key lessons to be identified from the implementation of the SLP suite?

Different options were considered to answer the evaluation questions, considering the complex multi-stranded nature of the SLP suite and data collection realities. The final decision on data sources is:
- IMEP final reviews of each SLP, drawing on SLP’s own internal reporting and evaluations
- A critical review and compilation of the SLP suite framework indicators and their trends in States
- A comparison of summary data for selected States
- A structured qualitative field study based around health facilities and schools
Evaluation questions, theory of change, and methodology are detailed in the design and approach paper, which has been quality assured by DFID with recommendation to accept with modest changes.[70]
[70] Evaluation Quest number 3809 220

The extent to which ‘ESSPIN specific’ questions can be addressed will be considered in the final scoping of the SLP evaluation:
- To what extent has ESSPIN had a measurable impact on access to education?
- To what extent has ESSPIN had a measurable impact on equity in education?
- To what extent has ESSPIN had a measurable impact on learning outcomes?
- To what extent is there evidence that Nigerian resources are better used to improve education access, equity and learning as a result of ESSPIN’s intervention?
- To what extent has ESSPIN demonstrated that it represents good value for money in comparison to other projects/programmes?

It may not be possible to cover any or all of these questions in the broader evaluation of the SLPs. DFID Nigeria is therefore proposing to address the more specific ESSPIN evaluation questions in partnership with the recently established ‘Education Data, Research and Evaluation in Nigeria (EDOREN) initiative, which is managed by Oxford Policy Management..