Type of Review: Annual Review

Project Title: EDUCATION SECTOR SUPPORT PROGRAMME IN NIGERIA (ESSPIN)

Date started:	JULY 2008

Date review undertaken: 20-27 MAY 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
ESSPIN is a six year, £83.5m education programme, which is due to close in mid-2014. It provides technical assistance and direct project support in six Nigerian States (Enugu, Jigawa, Kaduna, Kano, Kwara and Lagos), in order to enable significantly more Nigerian children to complete a full cycle of basic education of acceptable quality, leading to meaningful learning outcomes. / This investment will demonstrate the educational benefits that result from an integrated approach to school improvement; encompassing multiple interventions at the school level. It is designed to strengthen the capacities of State governments and local communities to actively support sustainable school improvement and to assist the six States to utilise their own resources more effectively. In turn, this will help to scale up the impact of DFID’s investment.

What are the expected results?
By mid- 2014, an estimated four million Nigerian children (at least 47% of them girls) will be receiving a better quality of basic education, in a minimum of 10,500 schools (public and non-state), across the six programme States; improving their basic literacy and numeracy skills. Targets have been set for improvements in reading with comprehension, an understanding of number, and the ability to do basic calculations – all starting from a very low base. / The six States will be using their own financial resources more efficiently and effectively, to provide good quality education for all children, regardless of circumstance and background. This will be reflected in results that show timely budget releases and high utilisation rates for basic education. / The capability of primary and junior secondary schools (JSS) to improve basic learning outcomes will have been strengthened. Schools will be characterised by the implementation of school development plans, effective head teachers, competent teachers delivering well planned lessons, School Based Management Committees (SBMCs) mobilising community support, good practice on inclusiveness, and improved school environments.

What is the context in which UK support is provided?
Challenges / Two thirds of Nigerians live in poverty. Over 40% of children are severely food deprived and lack easy access to water and to good shelter. An estimated 10.5 million children are out of school (42% of primary aged children). Approximately 90% have never attended school; 55% of whom are girls (although an unknown number have Islamic instruction). The percentage of children out of school in the Northern States far exceeds that in the South (30 times greater in the NE than the South E) / Learning outcomes are deeply unsatisfactory. Two thirds of children who have completed Grade 6 in Northern States are unable to read. A significant number of students take 10 years to master basic reading, writing and competency skills. Generally, public service schools are of poor quality. Some parents have lost faith in their ability to teach their children; some transferring to private schools. Learning is constrained by teachers who lack pedagogical skills and are often poorly motivated. Communities are fragmented and lack the voice to call education service providers to account. School infrastructure is inadequate, decaying or both. The flow of direct funds to schools is limited and uneven. The monitoring of, and support for schools is weak. Government planning systems are limited, unable to draw on relevant evidence. The priority accorded to education by the political establishment, notably State Governors is unpredictable. Consequently, levels of financing and attention to systemic reform vary by State and over time. / These challenges are compounded in some Northern States, including Kano and Kaduna, by increasing levels of insecurity. This is requiring measures to ensure the safety of ESSPIN programme staff and define ways of working that can sustain programme delivery. State governments are under pressure to divert resources from social sectors, including education, to security.

## Section A: Detailed Output Scoring

Output 1: Federal government systems that support states' implementation of school improvement strengthened and functioning
Output 1 score and performance description: / A / Performance against Output 1 has been solid. Support and assistance at both Federal and State levels to ensure better disbursement of available funds to basic education has been sustained. ESSPIN supported States benefit from higher disbursements rates than non-ESSPIN States. / The ability of ESSPIN to support the design and the implementation of Federal institutional reforms in six areas remains uneven, although notable progress has been made on the roll out of a well-sequenced and thought through approach to creating functional SBMCs across Nigeria. / Progress against expected results: / Indicator 1.1: Disbursement rate of UBE Intervention Funds (Matching Grants) for basic education (3-year rolling) / Overall, ESSPIN’s 6 States accessed a total of N10bn out of N14bn released by Universal Basic Education Commission (UBEC) over the period 2010-2012, compared with N37bn out of N73bn accessed by the remaining 31 States. This represents a much higher disbursement rate for ESSPIN States (70%) over non-ESSPIN States (51%). / Milestones / 2009-11 Actual 2010-12 Actual / Enugu 89% 54% / Jigawa 78% 73% / Kaduna 78% 64% / Kano 100% 100% / Kwara 100% 64% / Lagos 84% 64% / ESSPIN States 88% 70% / Non-ESSPIN States 66% 51% / Source: UBEC publication of IF disbursements from 2005-2012 (ubeconline.com, 4 Feb 2013) / The UBEC Intervention Fund is an extremely important source of funding for infrastructure, teacher training and learning materials for basic education in Nigeria. A total of N31 bn. (equivalent to £129m.) was made available in 2011, allocated equally across all States. Access to these funds requires matching funds from the States. The disbursement rates in the table (above) measure the capacity of States to access the Fund over three year periods, 2009-2011 and 2010-2012. For the former period, ESSPIN states accessed 88% of their entitlement compared to 66% in the non-ESSPIN States. / The lower disbursement rate for the 2010-2012 period for both non-ESSPIN and ESSPIN States (with the exception of Kano) is due to low rates of disbursements in the 2012 fiscal year. This is due largely to the inability of States to provide their counterpart funds in a timely manner, which in turn, is due to delays in passing State budgets. / As of 4 February 2013, 17 out of 37 States had not fully accessed their full 2011 allocations (Enugu the only ESSPIN state; and seven States had not fully accessed their 2010 allocations (no ESSPIN States). The dissolution of the State SUBEB in Enugu appears to be an influential factor in this regard. / 2013 annual State budgets in ESSPIN States include the requisite counterpart funds to free up the 2012 UBEC-IF allocation. However, the late appropriation of 2013 budgets and the perennial challenge of low budget releases mean disbursement rates are unlikely to improve until the second half of 2013.
Indicator 1.2: National systems established for a) Monitoring Learning Achievement (MLA) b) Assessment of Teacher Competence c) Annual School Census d) Quality Assurance e) Accreditation of Teacher Education Colleges and f) SBMC implementation / Based only on ESSPIN facilitated self-assessment by Federal institutions in April 2013, progress in the first quarter of 2012 is most evident in the work on the rolling out nationally of SBMCs and on Quality Assurance. ESSPIN’s investment of £30,000 for TA freed up just under £1m of UBEC resources for the roll out of SBMCs. / a) Learning Assessment (Federal Ministry of Education/Policy Planning Management &Research (FME/PPRM); UBEC): The MLA Ministerial Committee has clarified roles and responsibilities and identified sources of funding for a national MLA system. Work on the development of appropriate MLA instruments and a capacity building plan has not yet been initiated. / b) Teacher Assessment (National Teachers Institute; UBEB; Teachers Registration Council of Nigeria (TRCN); National Commission for Colleges of Education (NCCE): Initial thinking by the Ministerial Committee has to be followed by the allocation of funding at Federal and State levels and a major advocacy exercise with teacher unions to make clear that the assessment is not a performance management tool. / c) Annual School Census (FME PFM&R: UBEC): There is no improvement in the institutional management of the Annual School Census and National Education Management Information System (NEMIS). The IDPs are coming together behind USAID as lead agency working with NEMIS. World Bank funds are being made available. ESSPIN has played a light touch role. / d) Quality Assurance (FME Federal Inspection Service: UBEC): ESSPIN has facilitated a QA Ministerial Committee. This has brought UBEC and the FIS together. UBEC resources and FIS expertise could together lead to a better coordinated national QA support system. / e) College of Education (CoE) Accreditation (NCCE): ESSPIN has completed its work with NCCE, developing an accreditation toolkit for use in Colleges of Education. It is now expected that the new Teacher Development Programme will pick up this strand of work. / f) School Based Management Committees (FME PPM&R, FME Basic &Secondary Education; UBEC) The nationwide replication of ESSPIN’s SBMC model is underway funded by UBEC. / The logframe rubric is that by June 2014, ESSPIN should help Federal institutions to reach self-assessment grades of at least B (against agreed criteria) in five systemic areas. There should be improvement in four areas from 2012 to 2013, with the status quo in one, and a proposed transfer of responsibility of College of Education Accreditation to DFID’s new Teacher Development Programme. / On first quarter 2013 evidence, B grade self-assessment has already been attained on SBMCs and Quality Assurance but work on Learning Assessment appears to have fallen back. / Milestones / June 2012 Actual March 2013 Actual June 2013 Target June 2014 Target / Learning Assessment D D C B / Teacher Assessment D C C B / Annual School Census C D B B / Quality Assurance C B B B / CoE Accreditation B / SBMCs C B C B / Source: Federal Self-Assessment Report, April 2013 / Recommendations: / Work on 1.1 should be sustained, based on a clear analysis of the strategies that have proved most effective. Learning at both Federal and State levels, on what types of ESSPIN engagement and intervention is proving most effective should be recorded and analysed. / Under 1.2, ESSPIN should continue to identify and work in support of those systemic Federal reforms where there is a clear commitment to effecting change, currently on SBMCs and Quality Assurance (QA). / Impact Weighting (10%): / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

Output 2: Capability of State and Local Governments for governance and management of basic education at State and LGEA levels strengthened
Output 2 score and performance description: / A+ / Steady and significant progress is being made by ESSPIN with an increasingly sophisticated and responsive mix of political engagement and capacity building; a view confirmed by State Commissioners in ESSPIN States. / Progress towards 2013 targets against 2012 performance on all four sub-outputs is positive in nine cases, where 2013 first quarter self-assessment indicators exceed end of reporting year targets. Lagos is ahead of its 2013 targets for all four indicators. In 10 instances, March 2013 grades match June 2013 targets. In the remaining five cases, 2013 performance is below the 2013 target; Enugu in three instances.
Progress against expected results: / Indicator 2.1: Quality of strategic and operational planning and budgeting, budget execution, performance monitoring and reporting at State and LGEA level / From a relatively weak base in 2012, Enugu and particularly Kaduna are judged (by criterion based self-assessment) to have improved while Kano remains at the same level. Kwara and Lagos have both improved from a B rating to A, while the performance in Jigawa is judged to have remained stable. / Other forms of qualitative reporting broadly support the self-assessments but given the very broad compass of this output, unsurprisingly, there are variations across its individual components. / Milestones / 2012 June Actual 2013 March Actual 2013 June Target June 2014 Target / Enugu C B B A / Jigawa B B B A / Kaduna C A B A / Kano C C B B / Kwara B A C B / Lagos B A B A / Source: State Self-Assessment Reports, April 2013 / Indicator 2.2: Quality of service delivery systems and processes at State and LGEA level / By June 2014, it is planned that ESSPIN should help the six State governments to reach an A grade self-assessment in Enugu, Jigawa, Kaduna and Lagos and B grade in Kano and Kwara. First quarter 2013 self-assessments indicate that Lagos and Kwara have progressed while Enugu may fall short of its June 2013 target. / The self -assessment reports for each State give a more nuanced indication of progress against individual criteria. / Milestones / June 2012 Actual March 2013 Actual June 2013 Target June 2014 Target / Enugu D C B A / Jigawa C B B A / Kaduna C B B A / Kano B B B B / Kwara C B C B / Lagos B A B A / Source: State Self-Assessment Reports, April 2013 / Indicator 2.3: Quality of school support and quality assurance services at State and LGEA level / By June 2014, it is planned that ESSPIN should help the six State governments to reach self-assessment grades of A in Enugu, Kaduna, Kwara and Lagos and B in Jigawa and Kano in this central component of ESSPIN’s intervention model. The grades in March 2013 point to progress so far this year in Kaduna and Lagos (A grades) but lack of progress in Enugu. The evidence of progress in this area is now better informed by the detailed findings of the Composite Survey (see below). / Milestones / June 2012 Actual March 2013 Actual June 2013 Target June 2014 Target / Enugu C C B A / Jigawa C B B B / Kaduna C A B A / Kano C B B B / Kwara B B B A / Lagos C A B A / Source: State Self-Assessment Reports, April 2013 / Indicator 2.4: Level and quality of State/LGEA engagement with local communities on school improvement / The June 2014 target is that ESSPIN should help State governments and their LGEAS to reach self-assessment grades of A in Enugu, Kaduna, and Lagos and B in Jigawa, Kano and Kwara. Initial grades for 2013, point to a diverse performance pattern across the States, with Kwara and Lagos being most confident about their work in this area. / Milestones / June 2012 Actual March 2013 Actual June 2103 Target June 2014 Target / Enugu D C B A / Jigawa C B B B / Kaduna C B B A / Kano C C B B / Kwara C A C B / Lagos B A B A / Source: State Self-Assessment Reports, April 2013 / At a State level Lagos records A grades across the self-assessment board. This tends to confirm other evidence of progress being made by the Lagos SUBEB and MoE in supporting school improvement, and the receptivity of State leadership to institute reform. In Kaduna, school improvement is being driven by the leadership of the Commissioner and the SUBEB Chair - often in difficult political circumstances. Jigawa has made significant progress but has not yet achieved A grades. There is slow but steady institutional change. There is no shortage of commitment but a dearth of technical capacity. / Kano maintained 2012 levels of institutional capacity with regards to all but one indicator against a backdrop of insecurity, affecting adversely the planning and monitoring of projects. However, the government remains committed to reform, evidenced by the imminent expansion of ESSPIN’s literacy and numeracy programme to all primary schools (5000+). And despite fiscal instability, UBEC TPD funds are being ring-fenced for school improvement work. / Enugu self-assessment scores are lower than for other States. Some progress has been made over the past year even in the absence of a SUBEB Board following its dissolution last year. It is hoped a new Board will be constituted with the Governor back on seat after a long absence. Kwara has made substantial progress on planning, budgeting, quality assurance, service delivery systems and community involvement since self-assessment in 2012. Attention is required in particular to the very low level of budget release (less than 20% for the Ministry). / Recommendations: / The 2014 self-assessment targets should not be written in stone. They should be re-assessed regularly to reflect the diverse and often difficult circumstances in which individual States operate but without prejudice to aiming high. / Aggregate lessons should be learned and disseminated systematically with regard to why specific advances in 2.1-2.4 have been made possible and then made to work. This evidence is important as school improvement good practice spreads and deepens. Self-assessment is important and case studies useful but a more research based approach is needed as the Programme moves to a more advanced phase. In this regard the Composite Survey data should be utilised to maximum advantage (see Section 3). / Impact Weighting (16%): / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

Output 3: Capability of primary schools to provide improved learning outcomes strengthened
Output 3 score and performance description: / A+
The four indicators under Output 3 represent critical components of the integrated school improvement approach. On all four sub-outputs, the annual review team (May-June) found a steady upward trajectory. ESSPIN’s 2013 Annual Report (published later in October 2013) has provided the complete picture of achievement during the year, and has been used to complete the final scoring of Output 3. Importantly, ESSPIN 2013 Annual Report has ensured a more complete picture of what results were achieved through ESSPIN and State government funding for indicator 3.4. It is important to note here that Output 3 annual milestones are assessed on the basis of ‘conversion rates’ rather than the number of additional schools that joined the SIP. As such, significant increases in results are expected in the 2013/14 school year, when many of the Phase 2 schools that joined the SIP this year, will start to become effective. / Background: / June 2013 logframe milestones were estimated based on projections of the roll out of Phase 2 schools; roll out that is dependent on State funding and sustained political backing. This being so targets are difficult to predict. At present, the effectiveness of school improvement outputs (indicators 3.1-3.3) can be assessed most accurately in the schools in which ESSPIN has intervened directly. / Indicators 3.1-3.3 (key elements of school improvement) are based on the achievement of targets against specified criteria that reflect a complete cycle of training followed by on-going school-based support. A complete cycle typically takes one school year. Accordingly, not all Phase 2 schools could be assessed for this review, as most joined the programme late last year or subsequently. / Indicator 3.1: Number and proportion of public primary schools using a school development plan [SDP] / Results are restricted to public primary schools. / Milestones / June 2012 Actual June 2013 Target June 2013 Actual 2013 SIP schools All State Primary Schools 2012/13 / Enugu 111 188 121 130 1,221 / Jigawa 168 307 398 501 1,920 / Kaduna 136 328 355 682 4,380 / Kano 166 616 - - 5,251 / Kwara 501 449 908 1,465 1,466 / Lagos 577 408 491 1,001 1,001 / Programme 1,659 2,296 2,273 3,779 15,239 / Source: State School Support Officer (SMO) Reports, April 2013 and ESSPIN Annual report October 2013 / The use of SDPs in primary schools receiving ESSPIN school improvement interventions has grown from 11% in the six States (June 2012) to 15% at the end of the year (June 2013). Sixty percent of all primary schools in receipt of school improvement interventions are using school development plans as of March 2013. / After substantial engagement from ESSPIN and DFID, Kano State has decided to place priority on teacher and head teacher training activities over the SBMC component of the SIP, therefore no data on this indicator can be reported for Kano. The monitoring and reporting system for Kano is now being adjusted to make it ‘fit for purpose’ for the newly launched ‘Teaching skills Programmes’ (TSP) which is a flagship initiative of the State focused on improving teacher’s literacy and numeracy skills. All 5,300 public primary schools in the State have been brought into the programme and the TSP will be largely funded by the Government. / Indicator 3.2: Number and proportion of head teachers in public primary schools operating effectively / Milestones / June 2012 Actual June 2013 Target June 2013 Actual 2013 SIP schools All State Primary Schools 2012/3 / Enugu - 188 103 130 1,221 / Jigawa - 307 342 501 1,920 / Kaduna 150 328 511 682 4,380 / Kano - 616 - - 5,251 / Kwara 1,041 1,231 1,114 1,465 1,466 / Lagos 521 408 826 1,001 1,001 / Programme 1,712 3,078 2,896 3,779 15,239 / Source: State School Support Officer (SMO) Reports, April 2013 & ESSPIN Annual report October 2013 / Overall, there is an increase in the number and proportion of head teachers judged to be effective from 11% (data available for three States – Kaduna, Kwara and Lagos) in June 2012 to 18% (for five States) in June 2013. Sixty eight percent of all head teachers in schools benefitting from ESSPIN interventions have been assessed effective. This proportion is expected to increase in the 2013/2014 school year when more head teachers will have completed the full training/support cycle. Again, no data was collected for Kano (see 3.1 above). Kwara is slightly behind in this component of the SIP because the State had initially prioritised literacy and numeracy teaching and the development of lesson plans over school leadership. However, although short of the June 2013 target, Kwara’s proportion of effective head teachers at 86% represents the highest conversion rate of all States. / Indicator 3.3: Number and proportion of teachers in public primary schools who can deliver competent lessons in literacy and numeracy / Milestones / June 2012 Actual June 2013 Target June 2013 Actual 2013 SIP schools (teachers) All State Primary School (teachers) 2012/13 / Enugu 406 1,417 1,214 1,400 12,167 / Jigawa 601 1,076 2,748 5,127 13,142 / Kaduna 721 1,567 2,690 8,184 46,648 / Kano 340 3,234 - - 44,352 / Kwara 3,227 7,038 7,982 13,931 13,931 / Lagos 2,582 2,142 7,109 11,141 13,238 / Programme 7,877 16,474 21,743 39,783 143,478 / Source: State School Support Officer (SMO) Reports, April 2013 & ESSPIN Annual Report October 2013 / ESSPIN has achieved its June 2013 target. In June 2012, 6% of primary teachers in the six States were assessed competent, rising to 15% (for five States) in June 2013. In relation to all of the teachers who have benefited from the ESSPIN teacher support programme, 55% of participating teachers were assessed as competent (June 2013). / No data was collected for Kano in 2013 for the reasons given above. / Indicator 3.4: Number of learners, especially girls, benefitting from better infrastructure: a) toilets b) clean water c) new or renovated classrooms / June 2013 targets were set in 2011, based on projections from the MTSS of the number of water, toilet and classroom facilities planned for by each State. Attribution of facilities directly funded by State governments is therefore critical to the achievement of the 2013 targets. / ESSPIN’s approach has been to provide a limited number of clean water points, gender segregated toilets and classroom facilities with the expectation that the demonstration of good practice and further technical advice and support will influence the States’ own supply of comparable school infrastructure. The actuals reported below are based on facilities directly provided by ESSPIN and State Governments. / The review team judged the basis for attributing State funded facilities as sufficiently strong. As an example, ESSPIN is currently supporting Lagos SUBEB through its technical consultant to manage construction workflows – quality control, acceleration of contract payments, and reduction of project completion time from 24 months to 18 months. This provides a strong basis for attribution and allows ESSPIN to include in its results for Lagos an additional 34,000 children benefitting from classroom improvements and 14,400 children from improved water and sanitation facilities. A total of £1.36m of State resources was leveraged. / Of the 3 infrastructure outputs (toilets, water and classrooms), 2 sub outputs were achieved (toilets, classrooms) and 1 was not completely achieved (water). Water results were not met due to lack of government investment in two States, Enugu and Jigawa. In Enugu, the absence of Governor resulted in major delays to public sector delivery across the State. In Jigawa, whilst there is strong commitment to school improvement overall, there is an administrative anomaly in the State which has hampered delivery of the water targets. The responsibility for construction of water facilities, including to schools, lies with the Ministries of Water Resources and Works, not with SUBEB. It is not clear whether this will be resolved; and the situation is outside of ESSPIN immediate control. / It should also be noted that whilst the numerical targets for the number of children benefitting from water interventions was slightly missed this year, the sub-target for overall no. of girls benefitting from water provision was achieved. This is a strong endorsement of ESSPIN’s focus on equity and inclusion. Overall, the targets for ‘girls benefitting’ (figures in brackets below) were exceeded for each of the 3 infrastructure outputs. / In terms of value for money, ESSPIN’s recent annual report estimates that ‘clean water and sanitation has been constructed by ESSPIN at a cost of 2 pounds per child per year, delivering an estimated 4.6 million pupil-years of hygienic school environments’. This VFM metric estimates a larger benefit to more children from the longer life span (estimated at 15-20 years) of the constructed facilities that are of good quality. The results reported below which are based only on ‘children enrolled in schools’ if calculated on this basis would be significantly higher. / Infrastructure results depend on the leverage of State funding and therefore require attribution. ESSPIN has attributed ‘State results’ for the first time this year using State infrastructure data for the reporting year (2012/13) only. ESSPIN’s infrastructure programme has been running for 3 years, so theoretically it should be possible for further attribution of State results to be claimed from previous years. The feasibility of this should be considered with DFID for future ESSPIN reporting. / Number of girls in brackets. / Toilets Clean water Classrooms / June 2013 Target June 2013 Actual June 2013 Target March 2013 Actual June 2013 Target March 2013 Actual / Enugu 10,560 3,376 7,000 3,376 1,200 17,024 / (5,280) (1,628) (3,500) (1,628) (600) (8,001) / Jigawa 48,000 48,747 77,000 40,811 9,720 12,704 / (19,200) (22,911) (30,800) (19,181) (3,888) (5,971) / Kaduna 27,809 69,772 31,617 49,924 1,680 16,800 / (12,973) (32,793) (14,775) (21,114) (773) (7,896) / Kano 60,630 95,024 86,644 81,968 25,280 26,432 / (29,318) (44,661) (39,872) (38,525) (11,620) (12,423) / Kwara 14,214 19,093 14,214 23,653 8,464 6,272 / (6,681) (8,974) (6,681) (11,117) (3,978) (2,948) / Lagos 53,409 23,338 26,309 24,810 51,409 22,776 / (26,705) (10,969) (13,155) (11,661) (27,705) (13,055) / Total 214,622 259,350 242,784 219,810 97,753 107,008 / (100,157) (121,895) (95,628) (103,310 (20,859) (50,294) / Source: SUBEB School Infrastructure Records, March 2013, ESSPIN Annual report October 2013 / 2012 results are not included as they were calculated on a different basis. 2013 actuals use standard utilisation rates of 350 children per water point, 40 children per toilet cubicle, and 40 children per classroom; proxy measures for numbers of learners benefitting. Learner numbers are calculated from Annual Census enrolment data for schools receiving infrastructural facilities. / Recommendations: / A decision needs to be taken about whether reporting against junior secondary schools and non-State schools should be included in the 2013/14 Annual Report, or a clear case be made as to why ESSPIN cannot report at this level. If this level of reporting cannot be done, a full evaluation of the project against its stated targets cannot be made. It should be recognised that while SMO and SSO reports provide valuable monitoring information – including through their contribution to capacity building – the Composite Survey should be recognised as the key source of evaluative evidence for the SIP. / Impact Weighting (42%): / Revised since last Annual Review? Y/N / Risk: Medium / Revised since last Annual Review? Y/N

Output 4: Capability of communities and civil society to support learner participation and articulate demand for inclusive, quality basic education services strengthened

Output 4 score and performance description: / B / The evidence that communities and CSOs are playing an important role in supporting learner participation and articulating demand for quality basic education is fairly strong when triangulated across data sources. However, this is challenging work which for the objective of inclusion to be realised requires fundamental change in attitudes and behaviours. Progress across the 6 States is general positive but is currently not meeting the numerical annual targets on SBMC functionality and reflecting the voices of women and children. / Activity on this output is still impressive and the number of schools reached with SBMC support and training exceeds the annual target for 2013. Examples of impact so far are captured in a qualitative study report and a series of case studies. It would be reasonable to expect that within a short period of time, many of these SBMCs will meet their effectiveness criteria. The ESSPIN team remains confident that final targets will be met by July 2014; this will probably demand a fast tracking of training and monitoring support to States over the coming months. / Considering that 90% of SBMCs supported and assessed were found to be fully functional, the shortfall against numerical targets is not a failing of the support model but, like the rest of the SIP, a function of ESSPIN’s success with securing the release of State government funding. ESSPIN is actively managing this risk through political engagement and, as a result, Lagos, Kaduna, Jigawa (and Enugu from October 2013) are all rolling out the full SIP package, including SBMCs, in every focus school. The quality of support through ESSPIN and the adoption of ‘Inclusive Education Policies’ by the 6 States, gives good confidence that progress will be maintained. Greater depth and a longer time frame will be needed for results to be sustainable. / Progress against expected results: / Indicator 4.1a: Number of public primary schools with functioning SBMCs / June 2012 Actual June 2013 Actual June 2013 Target No. established SBMC June2013 No. SBMC focus schools assessed June 2014 Target / Enugu 98 118 270 272 121 / Jigawa 178 186 344 501 198 / Kaduna 135 112 328 645 165 / Kano 256 312 616 576 312 / Kwara 209 239 449 645 255 / Lagos 86 - 408 1004 100 / Programme 962 1,047 2,910 3643 1,151 4,591 / Source: State Social Mobilisation Officer (SMO) Reports, April 2013, ESSPIN Annual review October 2013 / 1,019 schools have functioning SBMCs (March 2013); an increase of 57 since June 2012. The target for June 2013 is 2,910. / Assessed in terms of quality, 90% of SBMCs that have completed the training and mentoring cycle are functional, up from 84% in 2012. Variation by State ranges from 99% in Kano to 68% in Kaduna. These can be explained by a variety of factors such as the scale and commencement of rollout as well as the priorities of the State in a context where the capacity to rollout all aspects of school improvement at the same time does not exist. Kaduna and Jigawa have rolled out fully in all Phase 2 schools, Kwara and Kano are in process, and Lagos and Enugu are still in the planning phase. Cross state comparisons have limited meaning as each context is unique. Lagos, for example, has complicated issues to resolve as it moves from a cluster-based SBMC to the individual school-based model. This has made it impossible to assess any SBMCs for effectiveness during this period which affects the achievement of the overall result although the State has full funded the establishment of SBMCs in all primary school and the training and mentoring scheme has commenced. / In addition to self-assessment, the Composite Survey provides useful evidence. It shows that 47% of Phase 1 schools have a functioning SBMC compared with 19% of control schools. To meet this standard SBMCs need to meet at least six of ten criteria covering aspects of membership, organisation, awareness raising activities, inclusion, interaction with government, women’s and childrens’ committees, school visits, and the contribution of resources. Kaduna (55%) and Jigawa (53%) did particularly well. This is noteworthy and encouraging, because the initial SBMC baseline research in 2009 indicated very weak links between communities and schools and between communities and local government. More specifically, for example, it shows that Kaduna control schools are mobilising resources at a similar level to ESSPIN schools. Assessed alongside monitoring reports observing that nearby schools have asked ESSPIN supported schools for help, there is evidence that interest in the model is spreading. / As a third source of evidence, these findings were triangulated by the AR review team during observation of a daylong meeting of Education Commissioners and SUBEB chairs. Jigawa and Kaduna stood out in terms of enthusiasm and grasp of performance across the indicators and across the LGEAs. Kaduna talked convincingly about how strongly they believed in school improvement, the importance they attach to concepts of learning outcomes and value for money which are new for them, and how the Composite Survey results had proved to them that improvements were possible. / A fourth source of evidence is the qualitative research paper entitled Impact of Support to SBMCs (April 2012).This provides useful baseline evidence on factors contributing to success. More than 75% of respondents reported that SBMCs were mobilising community resources, increasing enrolment, solving problems of attendance and inclusion, and responding to requests from LGEAs. Some of the examples provided in this study and in monitoring reports indicate substantive interventions by SBMCs who held teachers and head teachers to account. At the same time, a majority of research respondents reported that community resources were not enough to meet need and that the LGEA was not always responsive. / Indicator 4.1b: Number of communities where SBMCs reflect concerns of women and children / June 2012 Actual June 2013 Actual June 2013 Target No. of SBMCs est.June 2013 No. SBMC focus schools assessed / Enugu 14 110 220 272 121 / Jigawa 142 171 277 501 198 / Kaduna 77 95 266 645 165 / Kano 253 290 501 576 312 / Kwara 151 216 365 645 255 / Lagos 79 - 33 1004 100 / Programme 716 882 1,662 1662 1,151 / Source: State Social Mobilisation Officer (SMO) Reports, April 2013, ESSPIN Annual Report October 2013 / The increase in numbers of SBMCs reflecting the concerns of women indicates a proportionate increase from 62% in 2012 to 79% in 2013. The apparent drop in Lagos is explained by a policy change which breaks SBMCs from clusters into individual school units. / Quantitative analysis tells us little about the quality of participation. The SMO monitoring reports provide many examples of the kinds of issues women raise and indicate that this sometimes results in action being taken. In some cases, the issues are different from those raised by men, but in others the concerns of women are not different from those of the overall SBMC. In relation to girls’ education, for example, there are some notable examples of where initiatives for girls stem from the actions of men, such as in Kano where an influential Chief Imam has taken the model to Islamiyya schools where girl learners are in the majority. / The Composite Survey provides additional evidence on women’s participation. Across ESSPIN States, 10% of all public primary schools meet the SBMC women’s inclusiveness standard against criteria of attendance, leadership, raising issues, and issues leading to action. Of these, 39% of Phase 1 schools meet the standard compared with 7% in control schools. Enugu (57%) and Jigawa (46%) achieved well above the mean. In Enugu, women members were already quite active before ESSPIN interventions so the leadership support provided by ESSPIN was able to build on an existing foundation of women’s voice. In Jigawa, where men and women do not traditionally sit together to discuss issues and make decisions, the challenge is greater. / Neither of these evidence sources provide information about the frequency or regularity of women’s attendance or of how inclusive the committees are towards women. The qualitative study demonstrated that, although participation in the women’s committees is growing, there is a gap between women raising issues and actions being taken by the SBMCs on those particular issues. Certainly women are under-represented on the overall SBMC where decisions are made, but this is a complicated issue that reflects more than simply the voice of women. Factors such as whether the issues are actionable and whether there are funds available may be equally or more important than gender considerations. / In terms of children’s participation, the Composite Survey indicates that 23% of phase 1 schools met the standard for inclusiveness compared with 4% of the control. Jigawa (41%) and Enugu (32%) scored well above the mean. In Jigawa, as with women’s participation, social values have not generally been supportive of children’s participation, so the findings are encouraging, especially as all criteria show a significant difference between Phase 1 and control schools. An indication of increased acceptance and demand is that children in Phase 2 schools were already attending SBMC meetings and raising issues even though there was no children’s SBMC Committee in place. No such effect was found in Enugu. Again, the qualitative research cautions against unrealistic expectations, finding that some child participants in SBMCs were reluctant to talk in front of adults, especially their views about the SBMC itself which may imply negativity or about issues they feared would not receive support, such as beatings. These are early days to expect significant change. / Indicator 4.2: Quality of civil society advocacy and mobilisation for school improvement and marginalised groups at community and LGA level / June 2012 Actual June 2013 Actual June 2102 Target June 2014 Target / Enugu D B B B / Jigawa B B B A / Kaduna C A B A / Kano C B B B / Kwara B A B B / Lagos B A B A / Source: State Self-Assessment Reports, April 2013 / The 2013 State Self-Assessment exercise shows that by June 2013, three States had met their June 2013 performance target and three had exceeded it. Five out of six had improved on their 2012 rating. For Jigawa, which has highly motivated leadership, continuing self-assessment at B is probably a reflection of the major capacity challenges of the State in the face of ambition rather than a plateauing of progress. / CSOs have two major roles: one building the capacity of SBMCs and women’s and children’s committees; the other advocating with local and state government. On the former, the effectiveness of the CSOs is encapsulated in output 4.1a (effective SBMCs) as they provide general management and leadership training, as well as specific modules on inclusion, gender, child protection, networking and advocacy. / In Kaduna and Jigawa, positive relationships have developed between CSOs and government that have enabled the direct contracting of CSOs, using SUBEB funds, to directly contract CSOs to support SBMCs in their Phase 2 rollout. Kwara has engaged some CSOs in this work but there is not yet a clear commitment or strategy to complete the training and ensure the critical mentoring support necessary to make SBMCs fully functional. Enugu has developed its own state specific SBMC policy, which it is implementing with ESSPIN support but has not yet committed to rollout using its own resources. In Lagos, the Director of Social Mobilisation is fully committed to partnering more formally with CSOs to roll out SBMCs to all 1,001 schools in the State once the huge task of restructuring cluster-based SBMCs has been completed. / Qualitative research indicates that SBMCs are clearly building their confidence in holding duty bearers to account and that LGEAs are responding to some of the concerns. The capacity building efforts of the CSOs and the development of CSO Government Partnerships (CGPs) can claim some credit for this because the process of developing a functional relationship with a partly dysfunctional bureaucracy is complex. It is particularly challenging because of fundamental mistrust between government and CSOs. The development of positive relationships seems to have started with the SMOs who are well connected to schools and communities and these relationships have grown as results have been observable. / Indicator 4.3: Inclusive education policies and practices / 4.3a: Inclusive education policies at State level / Five states now have Inclusive Education Policies (IEPs) with Kaduna already implementing their policy / Milestones / Jun 2012 Actual June 2013 Actual June 2013 Target June 2014 Target / Enugu D D C B / Jigawa C B C B / Kaduna B A B A / Kano D C B B / Kwara C B C B / Lagos C B B A / Source: State Self-assessment Reports, April 2013 / Five states improved their self- assessment rating by June 2013, although Kano did not reach their aspirational target. Kaduna received an A rating for its outstanding work, including being the first State to successfully access UBEC’s Special Education fund to support its inclusive education programme. Only Enugu maintained its D rating from 2012. Collection of planning data on out of school children is at different stages: in Kaduna a state-wide survey has been undertaken; in Lagos initial focus is on the remote Makoko fishing community; Kwara has used the C-EMIS; and Enugu and Jigawa are in planning mode. / To support implementation of the IEPs, the states also have Inclusive Education Committees that are responsible for coordinating the range of activities overall, as well as advocating for and monitoring expenditure on inclusion through the MTSS. / 4.3b: Number of inclusive schools / June 2012 Actual June 2013 Target June 2013 Actual 2012/2013 SIP schools June 2014 Target / Enugu - 188 185 130 / Jigawa - 307 386 501 / Kaduna - 188 356 682 / Kano - 616 - - / Kwara - 1,231 927 1,465 / Lagos - 408 776 1,001 / Programme - 2,938 2,630 3,779 5,194 / Source: State School Support Officer (SMO) Reports, April 2013, ESSPIN Annual Report October 2013 / Monitoring reports indicate significant progress in making schools more inclusive. However, no trend can be determined yet because monitoring criteria for inclusiveness were only introduced into the SSO monitoring system over the last year. / At school level, 51% of schools met the criteria overall. Kano experienced slow budget release which delayed SIP activities and meant that schools could not be assessed in this period. If Kano was excluded, the overall figure for other States would be higher. / Balancing perceptions of good performance, findings from the Composite Survey indicate that there is no statistically significant difference in meeting the school inclusiveness standard between all schools (17%), ESSPIN Phase 1 (18%), Phase 2 (16%) and control (19%). This is probably an indication of the depth of the challenge in achieving outcomes related to inclusion, compared with the essential preparatory work of outputs. / Outside of the main model of school improvement, Challenge Funds have been used by some states to improve inclusiveness by incentives for rural teachers in remote or isolated schools and communities, out of school data collection, material incentives to encourage attendance by particular groups and construction of additional classrooms to meet excess demand. / In Jigawa, ESSPIN has supported the Girls Education Initiative (GEI) for 3,500 girls in 3 LGEAs. An internal midterm assessment in March 2013, claims that retention in basic education and transition to JSS is better in ESSPIN supported schools compared with state supported schools. The small size of the sample and the generally weak quality of demographic data in Nigeria mean that this may not be reliable, especially as some differences are small. The State government is now planning to roll out GEI further using its own funds and is in a stronger position to provide monitoring and mentoring following restructuring of the SUBEB and LGEA Social Mobilization departments and units. There is a strong focus on inclusion of girls. / 4.3c: Number of communities supporting inclusive education / June 2012 Actual June 2013 Actual June 2013 Target SBMC focus schools No. SBMCs est.June 2013 / Enugu 71 93 188 121 272 / Jigawa 167 179 341 198 501 / Kaduna 139 102 328 165 645 / Kano 225 312 616 312 576 / Kwara 227 246 449 255 645 / Lagos 62 - 408 100 1,004 / Programme 891 932 2,330 1,151 3,643 / Source: State Social Mobilisation Officer (SMO) Reports, April 2013, ESSPIN Annual Report October 2013 / SMO reports indicate that 80% of SBMCs in focal schools that have been trained to support inclusive practices within communities and schools were found to be effective in Juneh 2013, compared with 77% in June 2012. These figures are not directly comparable because the 2013 assessment was more rigorous. / Qualitative research shows that, although SBMC efforts are strongly linked with increased enrolment and attendance, and taking account of some notable exceptions, most have not yet developed the deeper understanding of, or concern for, diversity that would promote inclusion of the most marginalised groups. These are new concepts and there are many challenges. For example, there are several examples of where disabled children have been provided with the mobility to attend school but fewer examples of how schools are routinely seeking to improve learning for all disabled children. Therefore, although the first steps are promising, results at scale on inclusiveness will take a lot longer and require deeper engagement. / Recommendations: / The reasons behind the under achievement of targets in this output needs to be reviewed and next steps agreed with DFID. Improving the evaluability of qualitative data and increasing the mix of evaluation methods is important. Self-assessment is an important method because it is institutionalised in the state system, develops capacity for both monitoring and mentoring, and is increasing in rigour. But it uses ‘case studies’ which in focusing on successes may paint an overly positive picture. The Composite Survey provides a more objective and balanced analysis but the focus on inclusivity is limited. / The 2012 qualitative study of SBMCs was useful in providing evidence that balanced positive achievements with the realism of slow progress in attitude and behaviour change. What is now needed is qualitative evidence that can be tracked and compared over time, with more attention paid to refining indicators for the many domains that are currently described in self-assessments and qualitative studies simply as ‘improving’. / Consideration should also be given as to whether inclusiveness should be measured at outcome level. Currently, measurement of the various categories of inclusion, other than gender, stops at output level, and is impossible to track the additional numbers of disabled, linguistic, nomadic and other marginalised children have also increased absolutely and relatively. The quality of schools outcome indicator similarly captures inclusion only at the general level. / Impact Weighting (32%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: / The overall output score is A / 1.3 Direct feedback from beneficiaries / Given the Abuja-based nature of the review mission, the only beneficiaries with whom the annual review team interacted, at a meeting specially convened by ESSPIN, were State Education Commissioner’s (except for Lagos), SUBEB Chairs and other officials. / At this gathering, the impression gained was that there was almost universal support (even acclaim) for the work of ESSPIN: we could not have got where we are now without ESSPIN interventions. The power of the integrated school improvement model was identified, as was ESSPIN ability to tailor its work to the diverse political, financial and educational circumstances of individual States. The flexibility and responsiveness of ESSPIN was noted while staying true to its theory of change. The recent publication of the Composite Survey was seen as the first evidence of what works. At the same time it pointed to the importance of having a much stronger research capacity within States.
1.4 Summary of overall progress / Against very considerable odds (weak capacity, weak data and evidence, insecurity, political uncertainty, slow budget release and disbursement, diversity across States), ESSPIN is making good progress across all four outputs, performance is uneven for some of the different sub-outputs in Output 3 and 4 and across the different States. After criticism in both the MTR and the 2012 Annual review – work on Output 4 is now conceptually stronger, meaning that issues of inclusion are being dealt with increasingly across the programme and in an integrated way within the school improvement model. Achievement of the Output 4 targets for SBMCs will require a scaling up of current training and mentoring support over the coming months to ensure that July 2014 targets are met. / The ICAI Report on DFID’s Education Programmes in Nigeria rated ESSPIN green/amber (the programme performs relatively well overall against ICAI’s criteria for effectiveness and value for money. Improvements should be made) against delivery, impact and learning and amber/red for objectives. Overall ESSPIN was rated green/amber. The ESSPIN ‘Composite Survey’ published in March 2013 provides good evidence to enable DFID to respond to ICAI’s concerns about measuring programme impact and monitoring learning outcome changes for students in ESSPIN supported schools.
1.5 Key challenges / Forward Planning. Defining challenges going forward is complicated by uncertainty as to how long ESSPIN has to run. The programme is scheduled to close at the end of June 2014. Permission has been given to develop and to submit a business case for the extension of ESSPIN to the end of 2016. Should there be only one year left, the challenge is to deepen and roll out school improvement to the extent possible in all six States, guided primarily by the need to leave policies, plans, capacities and systems in place with the chance to sustain school improvement in the coming years. The Composite Survey would have to be conducted again early in 2014 and a set of other evaluative studies launched. The uncertainty that exists among Nigerian ESSPIN staff will need to managed. / If extended, a three and a half year time frame (from mid-2013) would provide the opportunity for ESSPIN to widen coverage and deepen good practice in line with its increasingly responsive and flexible model. / Insecurity. In both scenarios the insecurity of the Northern States will need to be addressed. First in terms of its implications for the future of schooling; second – as it is now – in terms of programme management and staff safety.
1.6 Annual Outcome Assessment / Programme Outcome: Improvements in basic education services in terms of access, equity and quality / Quality indicator: Number of public primary schools in focus states that meet the benchmarks for a good quality school (%) / No actuals were recorded for this indicator in June 2012 as evidence from the Composite Survey was not available until 2013. Evidence that the SIP contributes to overall school quality is, therefore, based on a comparison of Phase 1 focus schools (with ESSPIN intervention) and Control schools (with no ESSPIN intervention). / Logframe milestones for this indicator are based on a percentage of SIP focus schools, estimating the probability of the different elements of the SIP package co-occurring. This approach is now superseded by the empirical findings of the Composite Survey. / Number of good quality schools July 2012 / ESSPIN Control / Enugu 40 / Jigawa 67 / Kaduna 52 / Kano 23 / Kwara 258 / Lagos 73 / Programme 513 3 / Source: ESSPIN M&E Composite Survey, March 2013 / To be assessed as being of good quality, a school has to meet at least three out of four Output standards relating to head teacher leadership, teacher competence, school development planning, and functional SBMCs. According to these rigorous criteria, only 513 schools (3% of all schools in the six States) are of good quality. In the absence of ESSPIN, only 3 schools in the Control group approach the standard. / At a programme level, this means 14% of the 3,779 SIP focus schools had achieved the quality standard by June 2012. Given that this estimate is based on data collected almost twelve months ago, it is expected by ESSPIN that this proportion of schools will have increased considerably by the time of the next Composite Survey in 2014. / Access indicator (proxy for Logframe Outcome Indicator 2): Number of additional children in primary schools in focus states from 2009-2012 and proportion that are girls / Additional children enrolled / Cumulative Additional Enrolment 2009-12 Percentage Change 2009-12 / Male Female Total Male Female Total / Jigawa 25,175 37,297 62,472 9% 18% 12% / Kano 142,873 159,476 302,349 13% 17% 15% / Kaduna 68,434 77,360 145,794 12% 16% 14% / Kwara 16,907 18,425 35,332 15% 18% 16% / Lagos 10,457 3,720 14,177 5% 2% 3% / Enugu 6,468 4,766 11,234 4% 3% 4% / Programme 270,314 301,044 571,358 11% 14% 13% / Source: Annual School Census Reports, 2010-2012 / Over 570,000 additional children (53% girls) enrolled in primary schools in the six States supported by ESSPIN between 2009 and 2012. Thirty four percent of this total enrolled in ESSPIN focus LGEAs. In the Northern states of Nigeria, where girls’ education represents a special challenge receiving significant DFID and State government investment, girls accounted for 54% of all additional children in primary education (gross enrolment). The increase was higher for girls than for boys in each of the three Northern states. / Further analysis shows that between 2009 and 2012, ESSPIN focus schools in Jigawa, Kaduna, Kano and Enugu enrolled primary age children (6-11 year-olds) at a higher rate than the State average (this distinction does not apply in Lagos and Kwara where ESSPIN works in all LGEAs). Changes in primary net enrolments between 2009 and 2012 in Jigawa, Kaduna, Kano and Enugu were 26%, 5%, 26% and 45% in ESSPIN LGEAs, compared with the State averages of 14%, 3%, 11% and 33% respectively. / There is insufficient monitoring and evaluative evidence to determine whether individual schools that have improved across a range of school improvement criteria has resulted directly or indirectly in significant increases in enrolment in Phase 1 schools. In addition, explanations are needed for enrolment gains in non-ESSPIN schools. / IMPACT Assessment / Nigeria’s own resources are efficiently and effectively used to achieve the MDGs for universal education and gender equity / Impact Indicator 1: Proportion of Primary 2 and Primary 4 pupils in public primary schools in focus states with ability to read with comprehension and do basic arithmetic calculations / Logframe estimates for this indicator for October 2012 were: / Grade Learning domain ALL Male Female / Grade 2 English literacy 12% 12% 12% / Grade 4 English literacy 20% 17% 23% / Grade 2 Numeracy 33% 33% 33% / Grade 4 Numeracy 21% 20% 20% / The targets above were set following the ‘Monitoring of Learning Achievement’ (MLA) baseline assessments conducted by ESSPIN in Phase 1 schools in 2010. Conducting the baseline MLA resulted in major steps forwards over which assessment items to use, how to construct appropriate tests for the pupils, administering those face-to-face, marking schemes and setting standards. This learning informed the second round of pupil assessments, conducted in June and July 2012 as part of the ‘Composite Survey’ of school leadership, governance, inclusiveness, teaching and learning. The 2012 exercise allowed for fine-grained analysis by state, grade, subject, learning domain and gender for each category of intervention at school level, thereby setting up mid- and end-point evaluations of impact. / Major aspects of ESSPIN had not taken shape in 2009 when the baseline was designed, including the existence of ‘Phase 2’ schools, therefore control and intervention groups were not distinguished at that time. It was possible to retain enough equivalent items to compare results between 2010 and 2012 in the case of Primary 4 numeracy, but not in the other tests. Following the mid-term review (Nov 2011) and agreement to ‘scale up’ school improvement activities in ‘Phase 2’ schools with Government funding, new targets were agreed with DFID to map onto the measurement of learning indicators, for which the first set of results are shown in the table below. / Final technical and State reports published in March 2013 have allowed ESSPIN for the first time to be able to demonstrate that there are significant improvements in specific learning outcomes as a result of ESSPIN interventions in Phase 1 schools. The Survey is of exceptional quality in the context of education in Nigeria. Sampling was undertaken with care, the data were cleaned extensively and the statistical analyses were rigorous. The Survey’s findings can be read with a good measure of assurance. No previous surveys in the education sector have come close to the quality of the Composite Survey. / Programme (estimates for 4 states) Indicator Phase 1 schools Phase 2 schools Control Schools All schools / % P2 pupils with skills for reading comprehension 8% 9% 5% 9% / % P4 pupils with skills for reading comprehension 8%* 9% 2% 4% / % P2 pupils able to perform P2 arithmetic 19%* 16% 10% 12% / % P4 pupils able to perform P4 arithmetic 8% 7% 8% 7% / Source: ESSPIN M&E Composite Survey, March 2013 / The asterisk in the table (above) indicates areas of statistically significant difference. / Impact Indicator 2a: Public primary and JSS net enrolment rate (Net Enrolment Rate) in focus states / The NER targets in the logframe are as follows: / School type Baseline (2009) Milestone (June 2012) Milestone (June 2013) / Primary 84% 87% 89% / Junior Secondary Schools 54% 56% 58% / Net enrolment data has to be treated with extreme caution, particularly given the weakness of the underlying population data when calculating net enrolment data. However, as result of ESSPIN support annual education census data have improved. / Primary NER data for Kano is deeply problematic. In 2011 it was discovered that the population data on 6-11 year-olds in Kaduna and Kano (from the 2006 National Population Census) was flawed. It reported fewer children in the primary school age population than there were in school. Until the next National Census scheduled for 2016, NER calculations for the two States will remain in the region of 100%. This means that overall programme milestone data are largely meaningless. Currently the log frame has no targets. / Accepting that it is not easy or even feasible to interpret this data without many caveats, a few broad observations can be made using School census data. Kwara is some way away in 2012 of reaching its 2013 target, Lagos appears to have met its NER objectives, while meeting the target seems attainable in both Enugu and Jigawa in both primary JSS. / Net enrolment into JSS remains critically low in the Northern States, particularly Jigawa. The State Government recognises the problem and a girls’ education initiative is being piloted by ESSPIN in three LGAs. This is being reviewed for its effectiveness with a view to scaling up the initiative through SUBEB. / Milestones / June 2012 Actual June 2013 Target / Enugu Pry 66% JSS 54% Pry 54% JSS 49% / Jigawa Pry 58% JSS 26% Pry 56% JSS 32% / Kaduna Pry 100% JSS 59% Pry 100% JSS 65% / Kano Pry 100% JSS 32% Pry 100% JSS 47% / Kwara Pry 63% JSS 52% Pry 82% JSS 60% / Lagos Pry 82% JSS 85% Pry 82% JSS 84% / Programme Pry 90% JSS 51% Pry 89% JSS 58% / Source: Annual School Census Reports, 2010-2012 / Further analysis shows that between 2009 and 2012, ESSPIN focus schools in Jigawa, Kaduna, Kano and Enugu enrolled primary age children (6-11 year-olds) at a higher rate than the State average (this distinction does not apply in Lagos and Kwara where ESSPIN works in all LGEAs). Changes in primary net enrolments between 2009 and 2012 in Jigawa, Kaduna, Kano and Enugu were 26%, 5%, 26% and 45% in ESSPIN LGEAs, compared with the State averages of 14%, 3%, 11% and 33% respectively. / Impact Indicator 2b: Number of children supported by DFID per annum in primary and lower secondary education in focus States / This indicator estimates the number of learners in the six States benefiting from ESSPIN. This is interpreted as the number of learners benefiting from the school improvement programme initiated in focus states with DFID resources but rolled out state wide with government resources. Milestone values are calculated by multiplying an average number of children per school by the number of focus primary and junior secondary schools where ESSPIN is having an influence. / Based on logframe milestone data for June 2012, it is reported that nearly 720,000 children in primary and Junior Secondary schools were being supported to varying degrees by the ESSPIN programme in that year. In the March 2013 quarterly review, is recorded that just under 780,000 learners (363,000 girls) are benefitting from the programme in public schools and 32,000 (13,900 girls) in non-State schools, against June 2013 targets of 1.58 million (747,000 girls) and 24,600 (12,300 girls) respectively. / Accepting that the benefits to these children are not uniform in their coverage, together with the figure of an additional 570,000 children (Outcome Access data above) the “DFID support” data nevertheless represent a not insignificant step towards the headline objective in the DFID operational plan (2011-2015) of the number of additional children receiving education in Nigeria: 800,000 by 2015 (75% girls). It is, however, some way off its headline milestone for June 2013 of 1.58 million. / Impact Indicator 3a: Public primary education completion rate in focus states / ESSPIN calculates completion as the percentage of children completing the last year of public primary school – the total number of students in the last year less the number of repeaters in that grade, divided by the total number children of official graduation. This indicator is extremely difficult to calculate given the available data and earlier comments on the deep flaws in net enrolment data. Consequently, data provided by ESSPIN has therefore to be treated with great caution. / In addition, judging whether ESSPIN has enabled the achievement of higher completion rates cannot be judged quickly but requires accurate time series data, which is not yet available. Currently the figure of a completion rate of 58% in the school year 2011/12 (see below) does not measure ESSPIN’s contribution; neither do the targets for June 2013 carry conviction. / Primary Completion Rates / Milestones / June 2012 Actual June 2013 Target / Enugu 63% 47% / Jigawa 41% 48% / Kaduna 65% 68% / Kano 70% 82% / Kwara 50% 53% / Lagos 52% 88% / Programme 58% 53% / Source: Annual School Census Reports, 2010-2012 / Impact Indicator 3b: Number of children supported by DFID per annum completing primary education rate in focus states / This indicator takes the numerator value used to calculate completion rates in focus states, i.e. the total number of pupils in Primary 6 less the number of repeaters. This is a more plausible indicator than trying to measure percentage completion rates. It relates to all schools in which ESSPIN interventions have taken place, directly or through State roll out. No figure was readily available to measure this indicator other than milestone data in the logframe. / Impact Indicator 4: Gender parity index (gross enrolment) in public primary schools in focus states / While these figures appear to be relatively plausible, the problems associated with data in the Northern States referred to in Output indicators suggest that limited reliance should be placed on the accuracy of the table below provided by ESSPIN / Milestones / June 2012 Actual June 2013 Target Target June 2014 / Enugu 0.92 0.99 / Jigawa 0.71 0.74 / Kaduna 0.84 0.87 / Kano 0.86 0.93 / Kwara 0.90 0.94 / Lagos 1.04 1.02 / Programme 0.86 0.92 0.93 / Source: Annual School Census Reports, 2010-2012

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / The total approved DFID budget for ESSPIN (2008-2014) is £83.5 million, of which £71.9 million (86%) had been spent by end March 2013. Year 5 (ending June 2013) expenditures are on track to meet the budgeted total. A contract amendment has been proposed, which will increase the total budget by £8.7 million (plus another £0.5 million through the Crown Agents) to a total of £92.2. The additional funds are to cover increases arising from security concerns, and to continue the programme at current levels until July 2014, in anticipation of a project extension (below). / 2.2 Key cost drivers / The key cost drivers for ESSPIN over the whole project have been operational technical assistance (28.6%), divided equally between short and long term, support for capacity development (13.0%) and support to schools (19.6%) – a combined total of 61.2%. For the first nine months of year 5 these expenditures were 66.7% of the total. / During the first two years of the project, international TA costs were 75% of the overall TA cost. The share fell to 60% over the following two years and is anticipated to fall further to 45% in year 5. By way of partial comparison, the share of Overheads in Year 3 of the SAVI project was 58%.Overall, operational expenditures have been 79.4% of total expenditures and are 82.1% so far in year 5. The respective figure for SAVI in Year 3 was 74% / Trends in the major categories of expenditure appear to be moving in the appropriate directions. / 2.3 Is the project on-track against original timescale: N/A / See 2.1 above regarding the planned contract amendment for year 5/6 of the current project. In addition to the contract amendment, DFID Nigeria is preparing a business case to propose a further cost extension to January 2017 of up to £33 million to consolidate further the existing activities. The extension will provide additional support to State governments which are planning significant expansion of basic education and school improvement in line with the ESSPIN approach.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The publication of the Composite Survey early in 2013 marks a major shift in the ability of the ESSPIN programme to demonstrate the impact of its work against the five output pillars in the integrated school improvement model and in reporting on indicators of progress towards better learning outcomes at P2 and P4 grades in literacy and numeracy. / Analytical products to date based on the Composite Survey, include a technical report with overview findings, six State reports and a gender analysis. Further and more detailed analysis is planned. The data should be mined to extract maximum analytical value. / While the Composite Survey overall reinforces the worth of the integrated school improvement approach, by highlighting different levels of performance across ESSPIN interventions, there is scope now to examine more fully what explains these variations (e.g. between head teacher effectiveness and teacher competency) and to adjust programme investments for deepening the programme accordingly. / The 2012 Survey also provides an important baseline against which performance can be tracked again in 2014 and desirably – if ESSPIN is extended - in 2016. / The survey will be of interest beyond Nigeria both for its methodology and its initial findings on what works in difficult and sometimes dysfunctional systems. / 3.2 Where an evaluation is planned what progress has been made? / The review of the process by which the 2012 Composite Survey was designed, managed and produced is underway between OPM and ESSPIN. Its lessons need to be learned quickly so planning for 2014 Composite Survey commences without delay – particularly so if the project closes in mid-2014 which would require survey work early in 2014. / The Monitoring and Evaluation Strategy (2011) will need to be revisited and specific evaluative studies developed to look more deeply at the impact of specific components of the programme. ESSPIN has good monitoring systems in place and good illustrative case studies. But it lacks evaluative work that aggregates lessons learned, for example, in how and why school development planning is making a difference in school performance.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / 4.2 Assessment of the risk level / ESSPIN reports on risk to programme implementation at the State level in each quarterly report set against an all country risk assessment that is reviewed and signed off on a regular basis. Its forward planning activities include risk mitigation strategies. / There are a range of risks to maximising the benefits which lie outside of ESSPIN’s control and influence. The most significant of these risks may well prove to be the spread of insecurity and conflict and the effect that this may have on schooling in Northern Nigeria. The evidence base for analysing this effect is weak. Conversely there is no known research on the impact of the lack of educational opportunities on disaffection among young people. / ESSPIN’s response to the situation in the North is to run a well-regarded security management information and planning system which DFID regards as calm, systematic and balanced. There would appear to be potential for ESSPIN to work with DFID Conflict and State level advisers to further assess the risk of the spread of insurgency and its relationship to and impact on education. / ESSPIN has learned that political uncertainty is part of the educational landscape, especially as this relates to changes in leadership, policy direction and the financing of education at both Federal and State levels. A particular concern has been lack of transparency in UBEC funding regulations although ESSPIN has been instrumental in helping to develop The Review of Federal Government Approved Guidelines for Accessing, Disbursing and Utilizing the FGN-UBE Intervention Fund. During the review, however, State Commissioners expressed some concern that the Teacher Professional Development fund might be drawn back from States to be re-allocated centrally, at Federal level. / At State level the political risk lies with a lack of commitment to education and school improvement at the level of the Governor and the State Commissioner for Education. Currently, in five out of the six States ESSPIN has secured a high degree of buy in to ways of enabling more children to attend better schools. Enugu is the exception partly due to a set of circumstances that has left the State without strategic leadership. / In addition, there is the risk that ESSPIN will be unable to leave a sufficient legacy; structures and capacities that can endure in the face of political uncertainty. ESSPIN has gone some considerable way to achieve reforms which have a chance of being sustained. At the same its demonstration effect, evidenced in the Composite Survey is expected to lead to replication of its model. / Given the above, an assessment of risk might best be described as medium to high. That it has been categorised as medium reflects the progress that has been made ESSPIN in embedding its work in State systems in relation to Outputs 2-4.
Risk of funds not being used as intended / There is no evidence to suggest that ESSPIN funds are being used inappropriately. A high proportion of the budget is being used for technical assistance. Funds that are used for direct project support are limited and carefully managed. / 4.4 Climate and Environment Risk / There are no climatic and environmental risks. The infrastructure component of ESSPIN is alive to these risks

5. Value for Money
5.1 Performance on VFM measures / Economy and Efficiency. / ESSPIN has made significant progress in responding to DFID’s requirement to give focused attention to its Value for Money (VFM) strategy since early 2011. Until then, ESSPIN had been required only to produce monthly statements, invoicing by major items such as fees, reimbursables and programme support activities. It had done little additional analysis of its expenditures, let alone linking these with results. / In preparation for the 2011 MTR, the project submitted a VFM Strategy. This included five indicators of specific item costs (e.g. average cost per workshop participant) and began the complicated process of allocating expenditures across sub-outputs and then relating these to 33 ‘results’ (e.g. person days of teacher training). / In the 2011-12 Annual Report, and in preparation for the 2012 Annual Review, ESSPIN again presented its five ‘key indicators of economy’ and, under the Efficiency section, presented Year 4 actual expenditures and total programme projected expenditures against the delivery of 23 sub outputs that were taken directly from the Logframe in an effort to provide estimates of unit costs. Unfortunately, Year 4 expenditures were related to levels of delivery in Years 1-4, thereby undermining the calculations. / Since the 2012 Annual Review, ESSPIN has worked in three areas. First, it has re-allocated aggregate expenditures for Years 1-5 across sub-outputs. Second, it has switched attention from measuring the cost of delivery to also measuring the cost of effective delivery. For instance, in addition to answering the question how much does it cost to train a teacher to improve her teaching in literacy and numeracy, the effort has shifted to estimating how much it costs to train an effective teacher in these areas. Similarly, in addition to estimating the cost of establishing a School Based Management Committee (SBMC), the attempt has been made to assess how much it costs to establish a functioning SBMC. A full set of these unit costs reflecting the effectiveness of the project inputs has now been prepared. / The key source of information for assessing effectiveness in the schools has been the monitoring system put in place across the States utilising state government staff trained by ESSPIN. / The third area of work has been to widen the calculation of the economy and efficiency indicators at an aggregate level to, where appropriate, the six individual project States. The laborious work of allocating expenditures by sub-output across each of the project States has been completed and the unit costs of delivery to date are being calculated. Work is also now proceeding to combine measures of delivery with measures of effectiveness, preparing the way for presenting the unit costs for sub outputs across each of the project States. / ESSPIN’s reporting to DFID includes Quarterly Reports and an Annual Report. The current intention is to report information in the Quarterly Reports on the unit costs for a core set of eight sub outputs using the most recent cost information and, again, to relate these to another set of sub-outputs which will reflect the unit costs associated with total life-time project expenditures and levels of delivery. For the Annual Report, the project will also present the set of unit costs to date which reflect the effectiveness of the project’s delivery. Examples of the type of information being generated are shown below (in £). / SBMC Head Teacher Teacher / Current Unit Cost of Training to date 743 1163 338 / Projected Unit Cost of Training by Project End 415 718 181 / Current Unit Cost of Effective Training to date 1358 2284 387 / Projected Unit Cost of Effective Training to date 761 711 140 / At present, unit costs (reflecting total costs and total results to March 2013) are significantly higher than those projected over the lifetime of the project. Given the high level of fixed costs in establishing the programme, the expansion of additional activities are likely to be at a lower unit cost bringing the overall unit cost down somewhat. It is also possible, that as the SBMCs become better established, and as the reinforcement activities to improve teacher and head teacher performance prove effective, the unit costs of effective interventions programmes in these areas will decrease. / ESSPIN has worked hard since 2011 to respond to DFID’s emerging VFM agenda, however, this has also been challenging, particularly on measures of Efficiency. It is obvious that a great deal of laborious work has been undertaken; a) on the disaggregation of total expenditures across total sub outputs, and more recently on sub outputs by State; and b) on results, and effective results, in order to provide evidence in a systematic way to the on-going monitoring of ESSPIN through its Logframe. The framework for reporting to DFID on Economy and Efficiency through the Quarterly Reviews and Annual Reports is in place. / It is now important that the existing data, and the additional data planned to be generated, are used as part of management decision making processes around the allocation of resources and to increase VFM during the remaining period of project implementation. There are at least three areas in which both ESSPIN and DFID should be interested. / In addition to the regular monitoring of cost indicators (under Economy), systematic attention could be given to the often wide differences between the unit costs to date of delivering an activity and the projected unit cost across the lifetime of the project. The reasons for the differences need to be sought, an argument made as to why the marginal unit cost may fall in the future, and consideration given as to how that fall might be accelerated such that the differences between the actual and projected unit costs are minimized by the end of the project. Similarly, the addition of unit cost data to the discussion of the actual effectiveness of the sub outputs currently based on the regular monitoring exercises would add to the quality of that discussion. It may be, for instance, that more resources are needed to improve the quality of head teacher training, increase its effectiveness and lower the unit cost of effective training. Overall, the systematic use of cost data in management discussions of the delivery and effectiveness of activities should be encouraged. / Another area in which the unit cost data will be useful for management is inter-state comparisons. Why does it cost more per teacher to deliver a teacher training course in State A than in State B? Why does it cost more to establish a SBMC in State B than in State A? Further, while differences in the effectiveness of activities across states can be gleaned from the routine monitoring activities, again, the addition of unit costs will sharpen the discussion. Even if there are legitimate reasons for differences in unit costs between the States, just raising the issue and forcing explanations can be effective. / Thirdly, the disaggregated cost data, in particular, will be useful in discussions with State governments regarding the cost of rolling out aspects of the School Improvement Programme. The extent to which these rollouts occur is central to the overall impact and sustainability of the project. State governments have limited uncommitted funds. Trade-offs will need to be made even within the basic education sub-sector. Data on both costs and the effectiveness of individual activities increase the possibility of better quality decision-making. / Overall, the movements of the ‘five key indicators of economy’ and of the ‘key cost drivers’ described in 2.2 suggest that ESSPIN has been successful in efforts to improve the Economy aspects of VfM. However, the data on unit costs of delivering discrete activities show that these costs have so far been higher than were initially anticipated. At first sight, this would suggest that at least some of the Efficiency objectives of VfM have not, as yet, been met. The reasons need to be explored by ESSPIN and DFID. / Effectiveness / ESSPIN’s approach to Effectiveness in the VFM framework is to assess the cost of achieving a set of indicators which are reported in the Annual Report. These indicators are not the same of those in the Logframe which emphasise learning achievement, net enrolment rates, primary completion rates and the gender parity index. As discussed in the Outcomes section of this report, there are significant problems in measuring the last three of these indicators in Nigeria, mainly resulting from inaccurate population data. / The effectiveness indicators, with results taken from the 2012 Annual Report, are : / Cost of children benefitting from school improvement £23 per child per year / Additional children in focus primary schools £86 per child per year / Number of schools improved £1,300 per school / State resources leveraged for basic education £28 per DFID £1 / As presently estimated, the costs need more attention. For example, the basis for estimating the cost per child of benefitting from school improvement activities is taken from a single year and covers the whole set of expenditures associated with Outputs 3 and 4 (School Improvement and Community Support - £16.5 million in Year 4), while the basis for estimating the cost per additional child in focus primary schools is said to include head teacher support, teacher training, SBMCs and inclusive education measures – just £1.6 million in Year 4. Further, the resource leverage indicator assumes that all of UBECs three main grants to project states have resulted from ESSPIN’s attempts to improve UBEC’s institutional capacity. The ESSPIN team will consider the measurement of these indicators further and report on them in the 2013 Annual Report. / Until recently, it has not been possible to report progress on the Logframe impact indicator for learning achievement. With the results from the Composite Survey, the ESSPIN team aims to add to the indicators and, through their more detailed expenditure estimates, to respond further to the VFM agenda on effectiveness. The latter may not be easy, since the headline learning achievement indicators (to be used to measure impact in the Logframe) simply present the differences in the proportion of children who are assessed as performing at their grade level in project and control schools rather than providing a numerical estimate of increased achievement across all children in the project schools. / However, it may be possible to use the actual test scores on the wider set of questions which children were asked. Some of this has already been done through the work which ESSPIN is undertaking to understand to what extent children in P4 in project schools have mastered the curriculum of P1-3 compared to children in the control schools. Limiting the analysis of effectiveness to the headline learning achievement figures will drastically underestimate the total learning gains, and the cost per gain. / Prior to this ambitious piece of work being undertaken, it is still possible to provide some judgements regarding Effectiveness within the VfM agenda. In DFID’s paper, Approach to Value for Money, 2011, the core question in relation to Effectiveness is ‘how well are the outputs achieving the desired outcomes in poverty reduction’ and the paper’s first example relates to primary education – are DFID’s education investments delivering educational outcomes of value? / In this context, ESSPIN is demonstrating its effectiveness in two significant ways – by increasing the number of children in schools and, most important, by increasing the quality of schooling and levels of learning in project schools and then across the six States. So far, the project has demonstrated important achievements in both areas. / Schools benefitting from the project. Following the requirement of DFID and the recommendations of the MTR in 2011, ESSPIN’s focus and targets changed towards a faster and expanded pace of the service delivery aspects of the project which then led to a greater emphasis on persuading state governments to increase the number of schools receiving/implementing the core elements of ESSPIN’s School Improvement Programme. / In 2011, the ESSPIN programme was being implemented in 2310 public primary schools (14% of the six State total). The revised ESSPIN Strategy Paper (2011) set a target for 2014 of 9248 public schools – a very substantial increase given that much of the required funding and effort, would be from State governments and their staff. The most recent Quarterly Report shows that almost 4,000 schools are now in the ‘programme’ and, based on on-going discussions with the state governments, the target is for 8797 schools by June 2014 (54% of all public schools in the six states). / Since attainment of the targets depends largely on actions taken by State governments, they are necessarily imprecise and uncertain. For example, there has been no increase in schools added to the programme in Enugu over the past year, but with Kano planning to implement a State wide programme, the overall result would be that 64% of all schools in the Six states will be covered by June 2014. While still uncertain, it is very likely that the number of schools being improved through ESSPIN will be well above that initially anticipated. / Learning achievement. The Composite Survey (2012) demonstrates that in most of the areas measured, those behaviours/activities in the project schools which are expected to lead to improved learning achievements are superior to those in non-project schools (in 85% of cases the differences are positive and in half they are positive and statistically significant). If the ESSPIN theory of change is correct, this will lead through to the higher learning achievement of students. And there is well-founded evidence that this is happening. / To re-cap on the learning achievement results described in Impact Indicator 1, in three of the four measures, students in the ESSPIN project schools are performing at a much higher level than those in the control schools. In two cases, the differences are large and are statistically significant – while just 2% of children in P4 in control schools had the full set of skills for reading comprehension, the figure was 8% in the project schools; and while 10% of children in P2 in control schools were able to perform appropriate arithmetic skills the figure was 19% in project schools. It is still early days in terms of project outcomes leading to increases in pupils’ learning achievement but these initial results, obtained so soon after implementation of ESSPIN interventions, are an indication that the benefits from the project are likely to be higher than could have been anticipated at the start of the project. / While it cannot be definitively demonstrated in the fifth year of ESSPIN’s life that the overall measurable benefits of the project are, or are likely to be, greater than the costs, it can safely be argued that the project is online to achieve the requirements of Effectiveness within DFID’s VfM framework. / 5.2 Commercial Improvement and Value for Money / Procurement of items above £5000 managed by the Crown Agents. Infrastructure items are procured according to an agreed design and price by local firms identified by SUBEBs and the Rural Water and Sanitation Agency, monitored by two local consultants with final oversight by an international consultant (four visits in Year 4, reflecting the period of major construction). / 5.3 Role of Project Partners / The six State governments are the main partners in the ESSPIN project. In terms of expenditures, they pay the salaries of the teachers being trained and of cadres of ministry personnel receiving professional development and support. In the ‘roll out’ part of the project, during which the ESSPIN approach is expanded to many more schools than have been involved in the first phase of the programme, all of the State governments are using their financial entitlements for training schemes for basic education which are funnelled through the Universal Basic Education Commission. / The project also has relatively small programmes with agencies of the Federal Ministry of Education and with the Independent Universal Basic Education Commission. / 5.4 Does the project still represent Value for Money : Y/N / ESSPIN was planned, appraised and initiated before the explicit, post 2010 VfM agenda was rolled out by DFID. However, in line with all proposed projects at the time, an economic and financial annex to the ESSPIN appraisal document was prepared. / This argued that while the economic benefits resulting directly from an expanded and improved education system in the focus States could be anticipated to be large, they could not be measured beforehand. Instead, the focus was placed on possible efficiency savings in three areas in which the project would engage with governments – procurement, payrolls and UBEC’s large allocations of grants to states for primary education. Using a variety of (unverified) assumptions it was anticipated that the benefits in these areas might exceed the total costs of the project by £52 million (with a 6% discount rate). The veracity of these estimates could not be checked during this ‘light touch’ annual evaluation. However, as discussed in 5.1 it is now possible to go beyond the work of the appraisal report and consider some of the direct educational benefits from the project which have accrued and can be measured, and which will have positive economic returns. In particular, evidence of an improvement in learning achievement now provides a stronger case than that originally made for anticipating that at the conclusion of ESSPIN, the project will have provided Value for Money. / As at the end March 2013, ESSPIN’s overall expenditure totalled £72m over five programme years, of which 79% has been for operational expenditure. This sum of money, relative to the scale of the basic education challenge in six States (estimated total population of over 40 million), requires that ESSPIN be highly strategic in its interventions if it is to contribute to sustainable improvements in basic education in often dysfunctional systems. The evidence of this report is that ESSPIN’s strategic interventions are making both an educational and a political difference, drawing on a sound and still evolving theory of change. The levels of disbursement of UBE intervention funds in ESSPIN States, the adoption of school improvement strategies owned increasingly by individual States, the roll out of contextually appropriate school based management arrangements, and the early evidence of improved learning outcomes in better schools, indicate that ESSPIN is a productive investment. / Five years is a very short period in the lifetime of education reform in any country, let alone one where the politics of education are both paramount and uncertain. It is difficult to place a value on political influence but ESSPIN has achieved a level of political traction –albeit still fragile – which is both impressive and important in Nigeria. As earlier sections have made clear there is room for improvement in reducing unit costs to enhance efficiency and effectiveness – not least in demonstrating affordable good practice by State governments – but overall, and certainly relative to original project projections ESSPIN still represents value for money. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / There are no specific conditions associated with ESSPIN programme investments

7. Conclusions and Actions
Set against the backdrop of the findings of the MTR 2011 and the considerable uncertainty within DFIDN about the future of ESSPIN at that time, the programme has responded well and its current level of performance is to be commended. It cannot be said too often that ESSPIN is complex and ambitious within the Nigerian context. That it now has evidence that points to an upward trajectory at the outcome and impact levels is very positive. / Not surprisingly there are many ways in which the project can improve – a fact that is recognised within the ESSPIN teams. The recommendations in this section are limited to five strategic considerations. / Extension / The performance of ESSPIN in early 2013 demonstrates that there is a strong case for the project to be extended. If the widening of coverage of school improvement across ESSPIN supported States is to take place, and the deepening of good school improvement practice is to take root, technical and advisory support, political engagement and high quality monitoring and evaluation is required for at least a further two years. / Composite Survey / The review of the process by which the 2012 Composite Survey was developed – technical and managerial - should be completed quickly, so that planning for the proposed mid-2014 Survey should be initiated without delay. The Survey is central to evaluating the impact of ESSPIN. / Further Evaluation / While the Composite Survey is the essential quantitative evaluative tool, ESSPIN should commission topic specific qualitative evaluation studies which look in the aggregate, at how particular components of integrated school improvement are making a difference and why (e.g. school development planning). A project of ESSPIN’s complexity and ambition needs to have a research capacity be able to demonstrate and explain the value added of particular interventions in some detail and in a way that can be tracked over time. / Indicators / The ability of ESSPIN to demonstrate progress and VFM at the outcome and impact levels is constrained by the poor quality of data, albeit that the annual census process and product in the ESSPIN States has improved considerably. A quality assurance review should be conducted to assess whether net enrolment, completion rates and gender parity is sufficiently rigorous for decision making, and, if not, what alternative sources can be used? / VFM / Over the past six months, ESSPIN has advanced considerably to respond to DFID's VFM requirements. Now it is necessary to move beyond reporting procedures to using VFM related data for regular management decision making processes. Experience over the last two years suggests this would be done most effectively via a joint ESSPIN/DFID dialogue. / Conflict, Security, and Programme Management / Day to day security management is well handled. What is needed now is some research and scenario mapping as to a) the implications of increased conflict on education in Northern States and b) whether the lack of educational opportunity is fuelling conflict. This should be a DFID wide exercise and not limited to ESSPIN. In terms of ESSPIN programme delivery, the longer term implications for the work of State teams in difficult and pressured circumstances should be reviewed.

8. Review Process
Following the 2012 Annual Review (September 2012) and the publication of the ICAI report in DFID Nigeria Education Programmes (November 2012), the 2013 review was conceived as a “light touch” review. The review was managed by the DFID senior education adviser through the Independent Monitoring and Evaluation Programme (IMEP) ECORYS. / Consistent with the Terms of Reference (16 April 2013), an Approach Paper was developed (subsequently endorsed by DFID). The Approach Paper set out ways of working that would concentrate on the preparation of the final review report, with a short narrative report focusing on a set of questions defined by documentation review prior to the mission. For meetings in Abuja, priority was given to the ESSPIN Abuja team, the ESSPIN State team leaders and State Commissioners and SUBEB Chairs. An in-country mission took place from 20-27 May in Abuja. The three person review team comprised an educationalist, an education economist and a social development specialist. Following the in-country visit, it was acknowledged that due to the early date of the annual review, monitoring data for 2 output areas was not yet available to enable final scoring. ESSPIN’s Annual Report 2012-13 completed received in October 2013 has been used to update and complete the project scoring.