Type of Review: Annual Review

Project Title: Lablite: Moving DART (Developing Anti-Retroviral Treatment) implementation forwards into policy and practice in Africa.

Date started:	January 2011.	Date review undertaken: 30th October 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Lablite is an implementation research project, designed to demonstrate that the delivery of antiretroviral therapy using clinical monitoring, as developed in Developing Antiretroviral Therapy in Africa (DART), can be safely, equitably and cost-effectively decentralised in Africa and effectively rolled out. DFID will provide £1.98 million over five financial years 2010/11 – 2014/15 to fund the project.

What are the expected results?
The goal of the project is to improve the impact and efficiency of HIV programmes in Africa, thus enabling more people to be on effective treatment from available resources, and for treatment to be provided more equitably, particularly in remote rural areas. Its purpose is to accelerate the use of cost-effective, evidence-based approaches to monitor Antiretroviral Therapy (ART)/HIV treatment programmes in Africa. / Ultimately, a successful Lablite project will support health systems strengthening by providing decentralised Lablite ART delivery. / The outputs attributable to DFID’s support are: / a) The clinical outcomes of a decentralised Antiretroviral Therapy Lablite monitoring package used in representative health centres and their referral hubs by trained and supervised staff in Malawi, Uganda and Zimbabwe. / b) Costs, coverage and equity implications established for the decentralised Lablite patient monitoring strategy and compared to standard approaches recommended in National ART Guidelines in Malawi, Uganda and Zimbabwe. / c) Stronger capacity of African networks and key opinion makers to better engage in the process of getting research into policy and practice; and communicate new knowledge and data to relevant stakeholders and planners and policy makers.

What is the context in which UK support is provided?
One barrier to Anti-Retroviral Therapy (ART) roll-out in Africa is the perception that all patients on treatment need regular laboratory tests - to maximise the effectiveness of ART and minimise the potential for side effects. This is a major obstacle, particularly in rural areas, because these laboratory tests need substantial infrastructure (e.g. machines, electricity, reagents, supply chain), and trained personnel, which are costly to set up and then maintain. It also hugely constrains decentralised long-term care provision, which is vital also for patients who currently have to walk many miles to access treatment. The results of the Developing Antiretroviral Therapy(DART) trial showed conclusively that it is safe to deliver ART with clinical monitoring, but without the need for a large number of routine toxicity tests to be carried out / The objectives of the project are to demonstrate how a decentralised Lablite monitoring package would work in lower level health centres, providing safe and effective care; and to assess the costs, coverage, and equity implications of decentralised Lablite patient monitoring for scale up of service delivery in Africa.

## Section A: Detailed Output Scoring

Output 1: The clinical outcomes of a decentralised Anti-Retroviral Treatment “Lablite” monitoring package used in representative health centres and their referral hubs by trained and supervised staff in Malawi, Uganda and Zimbabwe.
Output 1 score and performance description: A+ Output moderately exceeded expectation
Progress against expected results: / The team have made significant steps towards disseminating the results of the baseline survey to relevant stakeholders both in-country and internationally. A paper comparing results across Malawi, Uganda and Zimbabwe has been submitted to an international journal and individual country situational analysis reports are being produced. These reports will be used to further communicate results across Ministries of Health (MOH) and other implementers, as well as informing the international and multilateral organisations involved in HIV and AIDS. In addition a number of policy briefs, aimed at national and international policymakers, will address specific issues including access to viral load monitoring, prioritisation of resources in the light of 2013 WHO guideline recommendations, access to paediatric ART and strengthening supply chain management to minimise drug shortages. / The baseline survey will be repeated at the end of the project in an extension of the original proposal. / The demonstration project aspect of Lablite is now well underway, with facilities in all three countries either initiating and following-up patients on ART or poised to do so. In Uganda two rural health centres in each of the southern and northern demonstration project districts (Kalungu and Agago) are now delivering full HIV services in static clinics. In Malawi four facilities in Phalombe are initiating ART. In Zimbabwe one rural facility in Zvimba district is now accredited to initiate treatment for HIV, while accreditation for another two is imminent. / Preparation for decentralisation from ‘hub to spoke’ has been a lengthy process in all three countries. A number of processes were necessary to assess and ensure fitness of facilities to deliver ART (the accreditation process); and facilitating accreditation with a specifically ‘Lablite’ approach to ART delivery brought some additional issues which needed discussion and agreement. / Working closely with the relevant departments in MOH, the country teams have carried out Training Needs and Pharmacy Assessments; developed training materials which either supplement or stand-alone from existing national training curricula; implemented training on a ‘train the trainer’ mentoring model - whereby ‘hub’ staff become trainers and mentors to staff at the spoke facilities - and have actively mentored on site; developed, designed, piloted and evaluated checklist job-aide algorithm tools to facilitate clinical monitoring of patients at spoke facilities, including identifying referral triggers where laboratory diagnostics are warranted. Following these activities, facilities underwent the formal MOH accreditation process before becoming part of the national drug distribution systems. / Training materials developed include a suite of video case studies for use in both initial and refresher trainings, and mentoring. These have been filmed in Malawi and Uganda and are partially supported by the Doris Duke Charitable Foundation in a parallel project to Lablite which is focussing on building capacity for communication of health messages in sub-Saharan Africa. Local clinicians, people living with HIV and AIDS and others have been trained in filming and editing in Uganda, Malawi and Kenya, with further training to take place in Zimbabwe. The video case studies are accompanied by a case book manual, and are being piloted prior to MOH approval in Malawi and Uganda. They will be made available for use nationally once approval is given. The checklist job-aide developed in Uganda will also be rolled out nationally. / In Zimbabwe, the team has made a significant contribution to the development of a new, integrated, national training curriculum in which elements of the Lablite approach are incorporated. / Project staff in the UK have developed data collection tools for the demonstration project which enable the capture of clinical outcomes from existing facility and patient level records. This has been an iterative process, requiring bespoke tools for each country reflecting the different registers in use. The team are working closely with district health staff familiar with local context in data collection. The work is ongoing as the team considers how to overcome the difficulty of ascertaining individual patient outcomes in a setting where many patients are lost to follow-up and little formal process is in place. The first data collected from Malawi is currently under analysis. / Two further elements have been added to the project since the last project review: a population-based household-level survey carried out in a sub-county of Agago district, Northern Uganda; and a study examining more closely the qualitative aspects of decentralising access to ART from the perspective of both healthcare workers and patients. Phase one of the population surveys – data collection from over 1400 households – has been completed and is being written up for publication. An abstract on the initial data has been accepted for oral presentation at the ICASA 2013 conference. The survey will be repeated a year after decentralised ART is introduced to the area. / Data collection for the qualitative study is now complete and analysis underway. The study is continuing to build capacity for social science in the project centres which was started in ARROW Young Lives. / Recommendations: / It is important that the team continue to document each step of the way so that others can implement this model of ART provision in the future. / The team should prepare a report at the end of the programme highlighting the lessons learned throughout the process and providing a helpful manual for others who wish to roll out the implementation in other countries. / Impact Weighting (%): 70% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 2: Costs, coverage and equity implications established for the decentralised “Lablite” patient monitoring strategy and compared to standard approaches recommended in National Anti-Retroviral Treatment guidelines in Malawi, Uganda and Zimbabwe.
Output 2 score and performance description: A+ Output moderately exceeded expectation
Progress against expected results: / The approach to Health Economics in Lablite has evolved substantially since the original proposal, and is now much more ambitious. The work is largely driven by infectious disease modelling, within which the costing implications of Lablite and other ART delivery alternatives are being assessed. This approach has been made possible by establishing a close collaboration between infectious disease modellers at University College London (UCL) and health economists at the University of York, leading to a larger role for MRC CTU. / The focus of the economics work was broadened following review of the cost-effectiveness literature on HIV treatment in Africa. Cost-effectiveness analyses (CEA) have tended to be “piecemeal”, investigating particular aspects of HIV treatment alone, rather than evaluating the whole range of options facing decision-makers. Most cost-effectiveness modelling has not incorporated the effects of treatment on transmission although recent trial evidence has indicated this may be one of the major benefits of treatment. It has tended to simply assess the mean costs and benefits of alternatives without adequately considering the scale of implementation and constraints in delivery that typify health systems in Africa. The failure to adequately consider competing calls on the resources required to fund particular interventions is a major limitation. / The economics and modelling work in Lablite has been designed to overcome some of these limitations. It is innovative and adapts cutting-edge methods until now only applied in developed countries for application within developing country contexts. For example, value of implementation and value of information analyses inform implementation and research decisions. This is a model for appropriate and comprehensive application of CEA in resource limited settings as a means to generate greater health gains for populations in need of healthcare. The Lablite health economics team have started to publish some work critiquing this approach; and have also been invited to take the central role in advising which methods are adopted for a ‘reference case’ in economic evaluation guidelines being developed by the Gates Foundation. Lablite has provided the major opportunity for the development of these approaches relating to appropriate methodologies. / Lablite also incorporates some aspects of health policy and systems research relating to the effects of HIV treatment delivery alternatives on human resources for health, laboratory infrastructures, and non-health consequences for patients. This is an area in which African health economists have made good progress, working closely with colleagues in the UK. A paper authored by the health economist in Zimbabwe, on Paediatric Quality of Life estimation methodologies in the African context, was recently published in the Value of Health journal. An abstract of work led by the health economist in Malawi on Informal Care and Productivity estimation methodologies has been accepted by the ICASA 2013 conference. / Members of the team were invited to contribute to CEA/modelling to inform the WHO Consolidated Treatment Guidelines (in which they are credited), under the umbrella of the HIV Modelling Consortium. This led to a report with the consensus conclusions that ART can be delivered with clinical monitoring alone, and that regular viral load monitoring is the most expensive strategy and should only be recommended where ART coverage targets have already been met. A subsequent paper reinforcing the consensus modelling evidence is in press at Lancet Global Health with an editorial commentary from the Lablite Principal Investigator. / The economics research taking place alongside the Lablite demonstration project is on-going. Data collection tools for all elements of the socio-economic analyses (on informal care/productivity, quality of life, and equity) are now complete, ethically approved and piloted. Data collection is currently being undertaken to inform equity analyses. Therefore all modelling and economics data needs are either complete, or have clear plans for completion. / The economic issues examined in Lablite are vital for the funding agencies that support the roll out of ART, notably PEPFAR, GFATM and (increasingly) the budgets of national governments. Although considerable progress has been made in ART roll out the gap between those on treatment and those becoming infected is still large and increasing. This is a key issue for UNAIDS and other multilateral and international organisations involved in the fight against HIV/AIDS. If the research programme is successful in identifying more cost effective ways of providing ART, the evidence produced has the potential to be very influential. / Recommendations: / The programme needs to strengthen the existing linkages with the Bill and Melinda Gates Foundation, the Global Fund (GFATM), MSF, PEPFAR, UNAIDS, WHO and any other relevant organisations, to ensure that the approach and results are taken account of by these agencies as they develop policy. / The health economics aspects of Lablite are innovative and wide-reaching. The team must ensure that the methods developed are made accessible for others to be able to use in the future. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Stronger capacity of African networks and key opinion makers to better engage in the process of getting research into policy and practice; and communicate new knowledge and data to relevant stakeholders and planners and policy makers.
Output 3 score and performance description: A – Output met expectation
Progress against expected results: / The team have to manage the study in the face of the resource constraints of working in Sub Saharan Africa. There is an active element of building up the capacity of local researchers within the programme, who are actively managing the processes under difficult circumstances. / The programme has been designed to include all stakeholders throughout. At the bi-annual Investigators committee and planning meetings all stakeholders, including community representatives, are invited and encouraged to participate. In particular, colleagues from MOH are encouraged (and indeed have made the effort) to join the working meetings. The project team are clear that Lablite needs to be sensitive to the needs of the participating countries, addressing issues that are of importance to them. As such, MOH are considered project partners. These close in-country collaborations have allowed relationships between researchers, implementers and policymakers to develop in a way that will support the uptake of research findings to policy and practice. / Lablite strives to increase capacity for research in Africa across a range of disciplines. Project Coordinators, Health Economists and Social Scientists have benefitted from attending short courses at the Centre for Health Economics, York University and London School of Hygiene and Tropical Medicine, as well as spending periods of time working directly with trial statisticians and epidemiologists at the MRC CTU offices in London. / The efforts, described against outputs 1 and 2 above, to engage with the Bill and Melinda Gates Foundation, GFATM, MSF, PEPFAR, UNAIDS, WHO and any other relevant organisations, that are a corollary to the academic side of Lablite, but are an aspect which is becoming increasingly central as the project progresses. Members of the team have, over the past year, given invited seminars at GFATM and Gates, sat on WHO guidelines committees and contributed editorial comment to international academic journals on the issues that Lablite is addressing. / Recommendations: / The programme should provide information about the number of women and men working on the team and the gender breakdown for capacity building activities. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A+ Outputs moderately exceeded expectation / 1.3 Direct feedback from beneficiaries / The programme is working closely with the Ministry of Health in each of the three countries at national and local level. There have been complex negotiations to fit the Lablite protocol with National and local plans for delivery of ART which are largely funded by International Programmes. Ministries of Health demonstrate a genuine enthusiasm for the project and for engaging with further activities, such as a potential project using the Lablite set-up to investigate options for prevention of mother to child transmission.
1.4 Summary of overall progress / Progress has accelerated in the last year and the programme continues to show strong support from local stakeholders, particularly the MOH in the three countries. Overall the programme appears fully on track to achieve its objectives. / Interaction with organisations such as the Bill and Melinda Gates Foundation, GFATM, MSF, PEPFAR, UNAIDS, WHO and any other relevant organisations will continue as Lablite progresses. There is recognition outside the project that Lablite is well-placed to produce evidence which will be particularly relevant to the current HIV treatment guidelines debate / .
1.5 Key challenges / A key challenge for Lablite is the wide-ranging scope of the project, both geographically and in terms of its cross-disciplinary nature. The project is being coordinated by the UK team who maintain a close watch over all aspects, and are centrally collating all documentation. In the early stages of the project building the relationships with key stakeholders, especially MOH was considered a significant challenge. As the project progresses, however, it is clear that those stakeholders are comfortable with the premise and activities of Lablite and are fully engaged. / The MRC Clinical Trials Unit (CTU) has recently moved to become a unit at University College London (UCL). AS a result of the move the Lablite project has to be transferred from a Memorandum of Understanding to an Accountable Grant. This transfer is ongoing and will be complete by the end of 2013. The change has not impacted on the progress of the programme.
1.6 Annual Outcome Assessment A+ Outcome moderately exceeded expectation / Lablite is designed to provide evidence to convince global programmes that ART roll out can be done without expensive laboratory monitoring. Progress during the year gives confidence that it will be possible to achieve the outcomes of this very complex research programme within the timescale allocated.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / The key cost drivers are staff and staff-related costs, transportation (oil and fuel costs are rising due to the Global Financial situation). Other cost drivers are incidental costs for surveys, data collection, monitoring and training costs. / Earlier concerns about foreign exchange losses in Zimbabwe have now reduced as the currency is more stable since the decision of the government to use the US Dollar. Exchange rate losses remain a risk in the context of the global economic downturn. / 2.3 Is the project on-track against original timescale: No / A costed extension was requested to enable follow-up of demonstration sites for at least a year; and repetition of the baseline and population-based surveys.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The results of the ARROW trial (a trial like DART in children) bear out the principles being demonstrated in Lablite and concerns regarding their negative impact on Lablite can be dismissed. The results do, however, give confidence that Lablite should be incorporating more paediatric aspects into the project, in order that an integrated family-centric model of decentralised care can be demonstrated. This ultimately remains a priority for the project, if it is to offer a practicable alternative to existing practices. / 3.2 Where an evaluation is planned what progress has been made? / Not applicable

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / The programme remains at high risk. The political situation in Zimbabwe has stabilised following the general elections this year. The Government of Zimbabwe has adopted the use of the US Dollar, so the extreme exchange fluctuations have now stabilised, therefore this risk has reduced. The continuing Global financial crisis has had a knock on effect of the budgets of Governments and some funding agencies. There is a demonstrable risk of interruption to ART supplies. This risk is relevant, not just to the research, but to ART provision for many countries in Sub Saharan African.
Risk of funds not being used as intended / This is low risk. The funds are administered by the MRC Clinical Trials Unit (CTU) which has recently transferred to become an MRC unit at UCL, which has a reputation as a world class research institute with robust accounting processes in place. / The in-country systems have been developed and refined over many years for implementation of clinical trials and the same mechanisms are now being used for Lablite including internal audit functions and annual audits. No funds are being channelled through Government structures in any of the three countries. / 4.4 Climate and Environment Risk / The major risks are related to travel and meetings. If the results are favourable the impact will be positive with reduced travel for individuals who are infected with HIV, as services are provided closer to where they live. There is potential to use the existing distribution chains for getting ART to community level, rather than having separate vertical arrangements. / There are appropriate procedures in place for the disposal of waste, including clinical waste, and these are built into the research protocol.

5. Value for Money
5.1 Performance on VfM measures / The study is designed to improve value for money for the delivery of ART, increasing the number of patients treated for the same finite amount of money. The results of DART suggest up to 33% more people can be treated safely and effectively using the same funding envelope, if expensive and potentially unnecessary laboratory costs are removed. / 5.2 Commercial Improvement and Value for Money / The internal structure of the programme, including drawing on the expertise of the MRC CTU, and the technical and managerial capacity of MRC and UCL ensures the most robust approaches are taken to improve value for money. / 5.3 Role of project partners / The organising arrangements, careful budgeting and annual meetings, which are designed to include all partners, identify any improvements that can be made in value for money. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? / Not applicable

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
The programme is on track and as last year, continues to build on the complex negotiations, both within the programme and with key external stakeholders. The research programme has made significant progress and senior managers continue to keep a strong focus on achieving the outputs. / Interaction with organisations such as the Bill and Melinda Gates Foundation, GFATM, MSF, PEPFAR, UNAIDS, WHO and any other relevant organisations, will continue as Lablite progresses. There is recognition outside the project that Lablite is well-placed to produce evidence which will be particularly relevant to the current guidelines debate. / Recommendations: / The team to continue to document each step of the way so that others can implement this model of ART provision in the future. / The team prepare a report at the end of the programme highlighting the lessons learned throughout the process and providing a helpful manual for others who wish to roll out the implementation in other countries. / The programme needs to strengthen the existing linkages with UNAIDS, PEPFAR and GFATM, to ensure that the approach and results are taken account of by these agencies as they develop policy. / The health economics aspects of Lablite are innovative and wide-reaching. The team to ensure that the methods developed are made accessible for others to be able to use in the future. / The programme should provide information about the number of women and men working on the team and the gender breakdown for capacity building activities.

8. Review Process
The review was undertaken by members of the Human Development team of DFID’s Research and Evidence Division together with independent member of the steering committee. DFID staff have had a number of meetings and discussions with members of the Lablite team throughout the year, including the health economics team.