Type of Review: Annual Review

Project Title: DFID Uganda HIV Prevention Programme

Date started:	18.11.2013	Date review undertaken: 18-21.11.2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £16.3m over four years (2011/12-2014/15) through a variety of channels to improve the effectiveness of Uganda’s HIV/AIDS prevention response. Initial components of the programme comprised: 1) Support to the Government of Uganda for the revision, operational plan and monitoring of the National HIV Prevention Strategy (NSP), implemented by the Uganda AIDS Commission (UAC), the Ministry of Health (MoH) and The World Bank; 2) Support for Combination Prevention Implementation to 6 pilot districts through various UN agencies (JUPSA) and an impact evaluation of HIV combination prevention as delivered by this component implemented by the World Bank; 3) Support of a Civil Society Fund (CSF) including its interim financial management costs from July 2011 to date, during the search for a new management agent; 4) Development and support of a Knowledge Management Communication Centre (KMCC), implemented by Delta Partnership. / After a critical Annual Review in October 2012 (B), support through the UN and the Civil Society Fund was terminated, but support to the World Bank for the operational manuals for the NSP, and support to the KMCC, remained. In addition, residual funds were allocated for the procurement of HIV test kits as well as for further technical support to the Ministry of Health and its decentralised (district) structures. The Civil Society Fund was allowed to retain £1.1m that was already paid into the fund in order to allow for a seamless transition into support by other development partners for the grantees. KMCC was requested to change from a “centre” to an “initiative”, to demonstrate an integrated structure that supports UAC, instead of being a stand-alone, parallel entity.

What are the expected results?
The expected impact and outcomes did not change with the re-structuring, but some changes to output indicators were decided: / The expected impact of the programme is: a reduction in the number of new HIV infections occurring annually in Uganda from 120,000 in 2009 to 72,000 by 2014. / The planned outcome of the programme is: improved effectiveness of the prevention response. / DFID attributable outputs and their respective indicators in the revised logframe are: / Completion, implementation and monitoring of a national HIV prevention strategy and action plan. / Development / update of the National HIV Prevention Strategy & Action Plan addressing socio-cultural and structural drivers of the epidemic. / Identification of effective intervention packages through the NPS. / Improved capacity of MoH and UAC to coordinate the implementation of the National HIV prevention strategy. / Improved HIV strategic planning at district level. / Improved capacity of The National Aids Documentation & Information Centre (NADIC) to synthesise, store and disseminate HIV information. / Improved policy and practice through effective dissemination and uptake of HIV-related research, evidence and lessons learned from experience. / Production of well-targeted HIV/AIDS knowledge and evidence and communication to a wide range of stakeholders. / Usage of HIV/AIDS thematic knowledge to inform emerging policies and practices. / Improved knowledge management and communications capacity of national stakeholders. / During the course of the current annual review, the need for 2 further outputs were discussed, as these are part of the restructured programme: / More effective prevention response through community mobilisation and engagement in addressing structural drivers of the epidemic (through Civil Society Fund). / 950,000 people reached through new social change communications programmes focusing on HIV prevention. / It is worth noting that although a decision was made to close this component after the 2012 annual review, DFID still had a substantial amount of the money already in the basket fund, and therefore it was important to track the results of these funds. / Increased access to HIV testing and counselling / Reduction of the national gap on HIV test kits.

What is the context in which UK support is provided?
The current state of the HIV epidemic in Uganda is largely unknown at the moment, owing to lack of data, most notably on incidence but also on prevalence since the last AIDS Indicator Survey (2011). All programming therefore relies on 2011 Aids Indicator Survey estimates and antenatal sentinel site data. / Uganda’s 2011 AIDS Indicator Survey showed a rising HIV prevalence to 7.3% (up from 6.4% in 2004), but without strongly reliable incidence data, it is unclear whether the rising prevalence is caused by an increased number of new cases or more HIV+ survivors due to scale up of anti-retroviral therapy (ART). The 2011 AIDS Indicator Survey (a reliable source) showed that the incidence of new cases was 145,000. UNAIDS modelled estimates show slightly declining incidence of new cases. More research is needed to understand whether the number of new cases is going up, or not. / There has been substantial critique of Uganda in recent years for not sufficiently addressing the epidemic after it allegedly set the best worldwide example on how to reduce HIV in the late 1990s. Uganda President Museveni’s leadership in acknowledging HIV and its drivers and giving clear messages to the people was instrumental for bringing AIDS prevalence down from 18% in 1990/91 to 6.3% by 2006 (where it stabilised for several years). In recent years, however, political messaging does not seem to have had the same impetus and universality so that the public received mixed messages from the health service and NGOs. For instance, the strong and unified messages for prevention and in favour of condom use by government and other stakeholders, were not as unified in recent years, when quality of condoms was questioned repeatedly and prevention messages were diluted by a relative focus on abstinence and be-faithful. Arguably this has led to a slower uptake of AIDS prevention services such as safe male circumcision and condom use. Recently, this may again see a reversal, as the President took an HIV test in public, promoting awareness and prevention. / A large number of stakeholders is active in the context of HIV – and this appears in some respects to have weakened the overall response to the epidemic in light of large coordination challenges. The mandate of the Uganda AIDS Commission (UAC) is to coordinate a multisectoral AIDS response across ministries including the Ministry of Health, the Ministry of Finance, Planning and Economic Development, and the Ministry of Local Government among others. The Ministry of Health (MOH) is responsible for the biomedical response to the AIDS epidemic, playing a large role in coordinating the majority of resources for the AIDS response. The United Nations has at least nine organisations working on the AIDS response, increasing the overall coordination challenge. Three US Government agencies also play a significant role. The civil society response to the HIV/AIDS epidemic has been strong in delivering a community response to behavioural and structural drivers of the epidemic. / Despite considerable development partner support (included with DFID are DANIDA, Irish Aid, SIDA, and the US Government), there has been relative under-resourcing to prevention interventions, with a heavy concentration on treatment and care. According to some sources, this includes biomedical prevention mechanisms which haven’t been provided to a sufficient threshold to allow for a full impact evaluation of combination prevention.

## Section A: Detailed Output Scoring
Output 1: Completion, implementation and monitoring of a national HIV prevention strategy and action plan
Output 1 score and performance description: / A / Overall, outputs met expectation, with 2 indicators of 4 showing a satisfactory performance (A) and 2 indicators not meeting expectations (B) but expected to be achieved within the coming year.
Progress against expected results: / Indicator 2013 milestones 2013 status (Oct) / Indicator 1 / National HIV Prevention Strategy & Action Plan addressing socio-cultural and structural drivers of the epidemic NPS Action Plan updated for the period 2013 – 2015 (To be done by MoH) This is planned to be achieved with the additional £800k support to MoH through CDC. The funding arrangements are still being set up with CDC Foundation. B / Indicator 2 a, b, c / Effective intervention packages identified through the NPS NPS M&E guidelines developed (To be done by World Bank) Routine Monitoring Systems improvement Framework (data collection, management and use Systems) and Capacity Building Plan was delivered; / Source: WB EFO 421 progress note A / NPS implementation manual developed / (To be done by World Bank) Operational Manual to guide implementation of the NPS 2011-2015 has been developed. / A report on the Costing of the NPS 2011-2015 including the Costing tool for HIV planning has been developed / Source: WB EFO 421 progress A / Impact evaluation of combination prevention in Rakai district carried out and lessons replicated (To be done by World Bank) The impact evaluation in Rakai is on-going and due to be completed by 2014. / The baseline report for Combination Prevention Impact Evaluation (CPIE) on the estimation of HIV Prevalence and Risk Behaviours in Most at Risk Key Populations in Rakai district, Uganda has been completed and delivered by June 30,2013 / Source: WB EFO 421 progress note B / The restructuring of the programme was finally agreed in July 2013, therefore the current progress does not reflect a full calendar year, but more realistically 4 months, especially where activities or funding arrangements had to be newly set up, such as with CDC Foundation to provide technical assistance to the MoH and district structures. Against this background, the progress of this output is satisfactory and likely to meet the end-target at the end of next year. Agreements with CDC Foundation and MoH appear near finalisation and the WB has finalised the study protocols and guidance documents for the Impact Evaluation. The Impact Evaluation could not realistically be completed within 2013. / Recommendations: / Given the short duration of the restructured programme, no further adaptation appears justified now and progress appears as satisfactory as possible in the given timeframe. / The agreement with the CDC Foundation should be put in place as soon as possible and close monitoring by the DFID team should continue to ensure that this output remains on an upward trajectory, subject to ongoing coordination work amongst the different US Government agencies. / Particular monitoring by the DFID U team should also be given to the World Bank executed Impact Evaluation in Rakai District. While WB documents and staff highlight that this Impact Evaluation will document the overall effectiveness of this particular package of combination prevention, the relative contributions of various behavioural and biomedical prevention tools to improve HIV prevention will not be rigorously evaluated in this evaluation. The latter, albeit challenging and perhaps impossible with current resource envelopes, would be needed in order to plan an effective and efficient HIV prevention combination in various contexts, by providing more information about which components of the combination are successful and which are not. Therefore the messaging following the Impact Evaluation must be carefully planned. In addition, it is unclear at present how the Impact Evaluation will avoid selection bias by evaluating a district that has received significant HIV prevention attention over many years. / Impact Weighting (%): 15 / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? Y / In light of the previous annual review the risk was moved from medium to high. This review does not see a reason to change this at this time, although the output is more on track than in the previous annual review.

Output 2: Improved capacity of MoH and UAC to coordinate the implementation of the National HIV Prevention strategy
Output 2 score and performance description: / A / Of two indicators, one was scored at satisfactory performance level (A) and one did not meet expectations (B) but is expected to be achieved within the coming year.
Progress against expected results: / Indicator 2013 milestones 2013 status (Oct) / Indicator 1 / Improved HIV strategic planning at district level District HIV planning guidelines developed and utilised to develop district HIV strategic plans (to be implemented by MoH) Guidelines are in place but yet to be used to support district strategic plans. The latter is pending finalisation of funding arrangements to the Ministry through CDC / Source: MoH interview B / Indicator 2 / The National Aids Documentation & Information Centre able to synthesise, store and disseminate HIV information A functional e-mapping system established at UAC (to be implemented by World Bank) A web-based database for mapping of service organizations working in HIV sector at district level, what services they are providing and where they are providing these services was established including development of an Operations manual for the electronic data base; / Source: WB EFO 421 progress note A / Indicator 1 solely depends on the funding arrangement through the CDC Foundation (see also above). The mapping of service organisations appears to be complete. No verification could be done during this review. The WB and MoH provided assurance that dedicated staff is in place to oversee this process in the future, and that districts will benefit from this exercise in identifying gaps and better streamlining (external) resources. The rationale and benefit for this is clear, but whether districts perceive this as beneficial and will contribute to this exercise remains to be shown in future. / Recommendations: / It would be beneficial for the DFID team to verify the extent to which districts will adopt this tool, their perceived benefit and how this will be fed by district teams in future. At the minimum this should be made part of the PCR exercise (e.g. including a fieldtrip to 1-2 sample districts). / Impact Weighting (%): 15 / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N

Output 3: More effective prevention response through community mobilisation and engagement in addressing structural drivers of the epidemic
Output 3 score and performance description: / (B) / Only one indicator remains of a list of indicators that were previously monitored for this output. This indicator can only be monitored for the first quarter of the Uganda FY (from July 2013-October 2013) or for the FY 2012/13 (July 2012-June 2013). For this annual review, the former is taken as an indication of current progress, also following the restructuring of the programme. This indicator was re-inserted into the logframe during the current annual review as some remaining funds with the CSF will be spent only during the current review year.
Progress against expected results: / Indicator 2013 milestones 2013 status (Oct) / Indicator 1 / No. of people reached through new social change communications programmes focusing on HIV prevention 950,000 in FY 2013/14 (as taken from the CSF annual and quarterly report target) Of the target of 500,000 for the previous FY 2012/13, 962,889 were reached (a significant over-achievement). / However, so far this FY 2013/14, of a target of 950,000, only 186,768 people have been reached in the first quarter (until end Sept. 2013); i.e. 19.7% of the CSF Tracker target after 25% of the time period and therefore off track. B / During the restructuring, it was decided not to allocate further funding to the CSF. This decision followed substantial delays in the approval and allocation of funds to the CSF. All of this resulted in delays in the actual work of the CSF which made the achievement of the envisaged targets for this financial year highly unlikely. In addition, management was kept on on an interim basis without a competitive procurement process. DFID has agreed to fund the financial manager (Deloitte) until Jan 2014, until a more permanent management is in place following a normal tender process. However, a final management arrangement had not been put in place by December 2013 and although plans are firmed up for the financial manager to include technical management (through subcontracting), a long-term plan is still awaited. / This decision notwithstanding, already allocated and spent funds by DFID that are with the CSF but not yet spent onward to the executing CSOs were allowed to remain in the CSF (£1.1m). This means that the CSF is still accountable for its results to DFID, which is why the above indicator is part of the revised logframe and reviewed here, even if no new funding is allocated to this component.Of all previous indicators, only one is presently measured on an annual basis. Whether or not the other indicators will be reported upon, depends on the future technical management. / Recommendations: / Given the above mentioned decisions of terminating this activity, future monitoring of this output by DFID should be performed in a proportional manner. / Impact Weighting (%): 15 / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? Y / No risk was specified previously and this indicator was re-introduced into the logframe, given the ongoing activities of the CSF with DFID funding.

Output 4: Increased access to HIV testing and counselling
Output 4 score and performance description: / A / Satisfactory performance on the first indicator (A) and expectations not yet met on the second indicator (B) but likely to be achieved by end of March 2014.
Progress against expected results: / Indicator 2013 milestones 2013 status (Oct) / Indicator 1 / National gap on HIV test kits reduced Mechanism for procurement of test kits set up IPA has been contracted, has started procurement of HIV test kits due to be delivered to NMS by end of December 2013 / Source: IPA progress mails + MoH interview A / Test kits delivered to NMS and ready for distribution IPA have provided updated delivery schedules indicating that the first consignments will arrive in December and all deliveries will have been received by end of March 2014. / Source: IPA updated delivery status report B / This component (procurement and delivery of test kits) was introduced to the programme as part of the restructuring of the programme and upon the request of the MoH. This commodity supply is an important element for HIV Prevention in Uganda and therefore complements the other elements of the DFID funded HIV Prevention programme. / The test kits have been procured in a short time frame by IPA and are expected to arrive in country in December and the rest by March 2014. / Recommendations: / In the weeks leading up to this annual review, information was received by DFID U that in a previous delivery of test kits, empty boxes had arrived at facilities. The incident was discussed with the HIV coordinating team at the MoH, who identified this as a singular incident, which did not show any systemic pattern. That notwithstanding, DFID U will need to consider how the successful and complete delivery of test kits that are about to arrive in country (funded by DFID) can be assured; and/or whether a separate delivery channel is warranted. DFID U should also consider broadening the indicators which at the moment, do not reflect performance on the milestone and only indicate arrival of test kits at National Medical Stores. / Impact Weighting (%): 30 / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? Y

Output 5: Improved policy and practice through effective dissemination and uptake of HIV-related research, evidence and lessons learned from experience
Output 5 score and performance description: / A / Of 3 indicators, one exceeded expectations, one met expectations and one indicator did not meet expectations.
Progress against expected results: / Indicator 2013 milestones 2013 status (Oct) / Indicator 1 / Well-targeted HIV/AIDS knowledge produced and communicated effectively to a wide range of stakeholders Thematic knowledge presented to at least 2 major national events in 2013 EMTCT Synthesis findings presented at not only 2, but 3 major national events (MoH national stakeholder conference, 2012, Uganda Society for Health Scientists (USHS) 14th Annual Scientific Conference May 2013 (along with a BCC knowledge synthesis poster presentation), and the Research, Academia and Science (RAS) Annual Experts’ Meeting in October 2013, (Approximately 300+ stakeholders combined) / Source: KMCC revised Log-frame Progress 2013 A+ A+ / At least 5 major multimedia presentations by end 2013 - Minibuzz eMTCT shows (e.g. interactive TV shows, public screening and similar activities) Interactive TV show – Minibuzz – proved particularly popular and as such KMCC has exceeded its target of 5 multi-media presentations by 2, broadcasting 7 Minibuzz shows (5x EMTCT + 2 fisher-folk focused) so far. / Source: KMCC revised Log-frame Progress 2013 A+ / Indicator 2 / HIV/AIDS thematic knowledge used to inform emerging policies and practices Print materials designed, printed and distributed (1 knowledge sharing event information pack for BCC knowledge sharing event and 2 communiques produced by end 2013 8 communiques/products produced for print (excluding two working papers on EMTCT and BCC): EMTCT Policy Brief, BCC abridged report, BCC knowledge sharing event information pack, EMTCT National Campaign folder insert; EMTCT Campaign Bandanas, Minibuzz DVD EMTCT highlights from 4 shows; Ntungamo/Lira Minibuzz Show DVDs; Tororo/Moroto Minibuzz DVDs. / Source: KMCC revised Log-frame Progress 2013 B B / At least 1 major activity to target influencing groups in 2013 Attempted to engage with Parliamentarians during ongoing events and activities. Awaiting formal approval of revised log-frame, work plan and budget before committing time and resources to longer-term relationships and specific focused activities. / Source: KMCC revised Log-frame Progress 2013 B / Indicator 3 / Knowledge management and communications capacity of national stakeholders improved Documented and verified capacity building support for NADIC in at least 2 major areas (including a user needs assessment and knowledge synthesis) in 2013 Two significant mentoring sessions held with UAC (mentoring programme as part of UNA activities – first draft report produced). / Source: KMCC revised Log-frame Progress 2013 A / This component of knowledge dissemination and uptake was arguably the most successful element of the programme and was retained during the restructuring. The number of presentations and activities provide an indication of the success of this component. / Whereas in previous years (according to reports and information by DFID U staff), the service provider and its services were not adequately recognised by its counterparts in the Ugandan government, notably the Uganda AIDS Commission, this perception has changed to a more successful partnership. This also follows the change of approach by KMCC from a “centre” to an “initiative” within the Ugandan structures (e.g. UAC). The service provider is now not only providing knowledge generation and dissemination but also puts high attention on capacity building for NADIC and the UAC more broadly. / It is not entirely clear why indicator 2 could not be met to full expectations. Excuses of waiting for approval should not halt or delay programme progress and this may need to be communicated more clearly to the service provider. In particular, attention by the service provider should be put on influencing. But overall progress is sufficient and meets expectations or has exceeded expectations. / Recommendations: / While the output has progressed and, overall, met expectations, the service provider still works mostly parallel to the UAC and NADIC rather than inside these organisations. NADIC faces human resource capacity constraints and although additional staff are being recruited, this is unlikely to bring NADIC to its full potential. In addition the current setup of a parallel structure will not be sustainable in the long term. Consideration should therefore be given to how KMCC could be further integrated with NADIC/UAC. This would not only facilitate/enhance the capacity building element, but would actually strengthen UAC “from within” and would have the potential to lead to a more sustainable outcome. There would also be more potential for influencing UAC and NADIC in their operations. There may be merit in hiring / contracting (by KMCC) an expert with change management experience on a short term basis. / When this point was raised both with MoH and UAC staff, all sides agreed that a more integrated approach by KMCC (e.g. of working with one-two staff inside UAC buildings) would be beneficial and very welcome. However, a risk inherent in this integration of KMCC would be that operational (day-to-day) decisions of KMCC could be delayed by administrative structures and procedures. Therefore this move could be planned gradually. E.g. one staff member of KMCC could physically move to UAC, for whom space would be available as was assured by UAC during this review. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / The logframe has been updated on account of the restructuring following last year’s critical annual review. / 1.2 Overall Output Score and Description: / A. The overall output score is satisfactory, especially in light of the short timeframe since restructuring of the programme. This is a very good result following last year’s critical annual review. / 1.3 Direct feedback from beneficiaries / The ultimate beneficiaries as in the recipient population of HIV Prevention in Uganda were not part of this light-touch annual review. But the remaining intermediate beneficiaries and clients of this programme, in terms of UAC, MoH, CSF, WB and other stakeholders (Irish Aid as lead agency of the AIDS Donor Partners) were all interviewed. Although some regrets were voiced over DFID leaving the CSF, overall there was broad agreement, or, at least, understanding for the DFID’s move to restructure the programme throughout the last year, including at the financial manager of the CSF. / Government (both in UAC and MoH) were highly appreciative of DFID’s continued engagement in terms of TA to the MoH (and Districts via CDC Foundation, forthcoming), to UAC through KMCC and the delivery of commodities (HIV Test kits), all regarded as needed and complementing and supporting Ugandan national HIV prevention activities. / DFID is also still regarded as an important and influential voice on HIV prevention in Uganda. All parties expressed the wish for DFID to remain a donor among the AIDS Donor Partners. DFID was in particular seen as an important partner in terms of monitoring other multilateral assistance (especially GFATM). The recent restructuring appears to be perceived as a strength of DFID, showing decisive action rather than accepting non-performance and delays.
1.4 Summary of overall progress / Since the last annual review in October 2012, the project has gained more momentum and traction in terms of achieving results. Outputs, which were considered not achievable in the lifetime of the programme, were replaced by procuring badly needed HIV Test kits. This may be complemented by funding from another DFID programme. The procurement is well under way, although caution must be exercised over the distribution in-country. The termination of the support to CSF at a time when funds had just been disbursed to the selected CSF organisations was regarded as premature by some stakeholders and hopes were issued that DFID would extend funding. However, in light of the programme duration, it would have been unlikely that all originally planned milestones and outputs would have been achieved. / The World Bank led outputs are showing good results, such as the completed electronic mapping of service providers as well as the planning and guidance of the Impact Evaluation in Rakai District. The evaluation itself is not yet complete, and, the 2013 milestone is considered by this annual review as too ambitious and not achievable in the current year. / The DFID support to knowledge generation and dissemination via the KMCC is showing good results, but could be more integrated into the Ugandan government to achieve better acceptance, sustainability and influence on the Ugandan structures.
1.5 Key challenges / The main challenge for the programme to achieve its overall target is now time, and everything should now be done to speed up the agreement with CDC Foundation for technical support to districts, but also for KMCC to look into ways of supporting UAC “from within” and support NADIC as an integral part rather than a parallel structure. / A second challenge inherent in the original programme design is the lack of one overall entity that would keep the programme aligned and focussed on outputs and targets. Most outputs although coherent in technical terms, are delivered by different partners (WB, MoH, UAC, KMCC). One lead partner (either contracted or an international reputable NGO) could have avoided this scattered approach. However, it is not recommended to create this single oversight structure now due to the limited time left to the end of the programme. / A number of further challenges are apparent in the wider Ugandan HIV prevention context. This includes first and foremost the lack of robust data (especially on incidence but also robust prevalence estimates, including among key risk population groups) on which to base further planning. At the moment it appears that no other donor is taking this forward. / A second major challenge is the number of stakeholders involved and its divergence of views and priorities. Although this situation appears to have improved somewhat during the last year, this will remain a stumbling block until a clear leadership is established within the Ugandan government and among stakeholders. At present, and from the interviews undertaken, it appears that the Ugandan MoH will have the biggest capacity to lead this dialogue. Certainly, the influence of the Presidential family cannot be neglected and, where possible, every effort should be made to ensure the President’s continued support for the entirety of HIV Prevention.
1.6 Annual Outcome Assessment / An outcome milestone has not been identified for 2013 in the original or revised programme logframe. In light of the critical annual review last year and the current Performance Improvement Plan, this should be corrected as soon as possible, even if now retrospectively for 2013 to demonstrate what progress was expected and its achievements again this plan. In the revised logframe there is also a new indicator on the percentage of people ever having taken an HIV test and received their result. This indicator is very valid in light of the new programme component, but a target for end-of-programme has not been set either. / The first indicator “NPS operational guidelines developed and utilised at District levels to implement combination HIV Prevention (CHP)” with its end-target of “Districts effectively implementing CHP” may still be achievable in the programme duration. It is not entirely clear, however, how the implementation of CHP will be measured. It is also not clear how this will be achieved by the programme as the programme now operates more at national level except for the impact evaluation in one district (Rakai), but has abandoned its other interventions at district level, with the exception of the electronic mapping of services at district level (as implemented by the WB). It would therefore be recommendable to revise the end target to add wording that is more attributable to current programme interventions. E.g. “completion of NPS and operational guidelines” for 2013 and “integration of NPS and operational guidelines in district planning” or similar. / The third indicator on reduction of test kit gaps is likely to be met with the procurement of test kits through DFID U. It is more questionable what will happen beyond this procurement and how the availability of test kits will be sustained in the longer term. / The above comments notwithstanding, the overall purpose (outcome) statement of “improved effectiveness of the prevention response” is likely to be achieved and contributed to by this programme in multiple ways: the NPS and operational guidelines have been revised already; there is more monitoring of HIV prevention services available through the e-mapping tool; activities by KMCC have substantially contributed to improving knowledge and disseminated the evidence base on which to base future interventions; and the delivery of HIV test kits will go a far way to improving the HIV Prevention response in the country. However, large impediments to HIV Prevention still prevail in Uganda at current times, which are largely beyond the scope of the current programme: the number of stakeholders active in HIV prevention and treatment without clear leadership (both at government level, but also among multilateral agencies and Civil Society) and the dearth of epidemiological data (even on a cohort or sentinel surveillance basis) are the most prominent obstacles to successful HIV Prevention. Coordination is modestly but constantly improving, with support also from highest level in the Ugandan government. There is scope that a more effective and unified HIV response may be (re-)established in Uganda. There may be a role for DFID to play in future to help this process further.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / With the HIV test kits being procured, and all other areas of the programme spending mostly according to plan, the project appears to be on track. The programme has spent a total of £11,609,341 to-date out of the £16.3m programme budget. As a result of restructuring, £4m was re-allocated to the HIV test kits procurement (to be spent by end of fiscal year) and £800k to CDC/ MOH district led programming. The HIV test kits procurement which presents a large portion of the re-allocated budget will be fully delivered by end of March 2014 as indicated in the delivery schedules from IPA. The remaining balance of programme funds is committed in on-going arrangements to end of project in December 2014. / 2.2 Key cost drivers / HIV test kits are by far the main cost driver of the programme since its restructuring. Other cost drivers are expected to be mainly on Personnel at various agencies, including WB, KMCC, Civil Society management. / 2.3 Is the project on-track against original timescale: / Yes, following the restructuring, it appears likely that the programme will meet its specified output targets by the anticipated end-date or shortly thereafter.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is evidence now that, in comparison to the previous annual review, divisions between entities in the Ugandan government are improving. There is also evidence that the World Bank has moved with its outputs forward and various tasks are now completed. There is further evidence that the Civil Society Fund is operational in funding 23 civil society organisations throughout the country, despite previous delays. / The above suggests that the programme targets at output and outcome level (especially following the restructuring) are achievable to a large extent. / 3.2 Where an evaluation is planned what progress has been made? / An overall programme evaluation is not planned. However, the impact evaluation of combination HIV prevention in Rakai is on-going.

4. Risk
4.1 Output Risk Rating: Medium / Project Memorandum Risks Probability Impact What happened / The UAC fails to achieve consensus and stakeholder buy-in or fails to win political support for the NPS Low High The NPS generally had stakeholder buy-in; in 2013, with the restructuring of the programme, there is greater harmony in coordinating the implementation of the NPS. / GOU will fail to deliver responsive prevention services leaving communities frustrated and disempowered Medium High The MoH made a request to DFID to strengthen district-led programming, and this is likely to trickle down and improve community empowerment. / AIDS DPs fail to maintain current CSF management arrangements Medium High The ADPs have not yet been able to establish a sustainable CSF management structure / HIV test kits get pilfered in the supply chain Medium High Supplies are expected to be delivered at NMS at the end of December 2013, and this risk has not yet happened. Measures need to be put in place to mitigate the risk / Contextual changes such as increased mobility due to regional economic integration or to instability in neighbouring countries may facilitate the spread of HIV, working against achievement of programme interventions Low Medium No major contextual changes occurred. / 4.2 Assessment of the risk level / As outlined above, the restructuring of the programme and the performance improvement plan have all contributed to making this programme more achievable and contributed to mitigating the risk of non-achievement. Some parts of the programme may therefore now be classified low risk, e.g. the procurement of test kits. / In light of the history of the programme and the overall national HIV prevention response in Uganda, a “medium” risk rating appears appropriate.
Risk of funds not being used as intended / Normal DFID fiduciary oversight arrangements are in place, with partners with a good track record of implementation. This review sees no evidence and has no reason to assume that funds are not being used as intended, although a more detailed review of civil society activities was not within the scope of this review, but the reporting as well as the financial data appear sound. / There is a risk that small quantities of HIV test kits may be pilfered in transit to district facilities(as has occurred reportedly in the recent past). Consideration should therefore be given to how this risk can be mitigated; but there may not be an easy solution to this, as tight monitoring and/or direct delivery may not be possible and would disenfranchise the Ugandan public sector delivery system. DFID may need to rely on complementary interventions providing support to National Medical Stores. / 4.4 Climate and Environment Risk / No considerable risks in terms of climate effects are foreseen as a result of this programme, nor have there been any such observations. / In terms of environmental risks, there is a risk that medical waste arising from HIV testing (and associated procedures, such as later treatment of patients) would not be appropriately and safely disposed of. Not safely disposed sharp objects may be a source of infection. Appropriate disposal and medical waste management should therefore be assured (and/or monitored) when HIV test kits are distributed. This would include the presence of an adequate such policy at national level, and possibly random interviews at district/facility level of how waste disposal is carried out. Should this finding be inadequate, additional training may be considered to improve on the safety of such waste management.

5. Value for Money
5.1 Performance on VfM measures / As stated in the previous annual review, a business case format had not been adopted before this programme was conceived. The Project Memorandum did not specify in detail any VfM considerations or measures. / The observations of the previous annual review do appear to remain valid for the outputs that were retained in the current revised programme. As for the new output on procurement of HIV test kits, these have been procured by a procurement agent (IPA) according to international (and DFID applicable) procurement rules and IPA will supply a narrative explaining how they have achieved an estimated US$400,000 of cost savings (around 10% against budget) through contract negotiations. / Overall the restructuring and performance improvement plan of the programme in and of itself is a measure to improve on value for money in terminating inefficient and ineffective programme outputs, and introducing a new output that is requested for by the Ugandan government and that is an essential part of effective HIV Prevention (the test kits). / 5.2 Commercial Improvement and Value for Money / The knowledge generation and dissemination has been contracted by a competitive tendering process to Delta Partnership consultants. / Similarly, the procurement for HIV test kits has been performed according to international tender procedures by IPA. IPA carried out a costing exercise prior to contracting the different GoU pre-qualified suppliers, against the GoU rates versus other market estimates and was able to realise savings of $400k over the entire procurement budget. / The technical assistance to the Ministry of Health and districts will be channelled through CDC Foundation, which will undergo a due diligence process before an accountable grant can be finalised. A route of direct funding of the MoH was not considered feasible in light of restrictions on channelling money to the Government of Uganda. / 5.3 Role of project partners / The observations of the previous annual review are still valid. No additional observations. / 5.4 Does the project still represent Value for Money : Yes / With the restructuring of the programme and the Performance Improvement Plan, the programme has improved on VfM to the extent possible. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / No conditions were set for the current programme. The programme is not set for Budget or Sector Budget support.

7. Conclusions and actions
Following a critical annual review in 2012, DFID U had considered an early termination of the HIV Prevention Programme. Following a process of internal consultation, it was decided to continue the programme but close 2 interventions: the support to districts via the UN system (JUPSA) and the support to the Civil Society Fund (although money already disbursed was not requested back). Instead and upon the request of MoH, HIV test kits are being procured for the remaining funds in the programme and technical assistance to the MoH (for the support to districts is being secured via CDC Foundation). Other outputs are being retained. / The restructuring and Performance Improvement Plan has put the programme in a position to still achieve (part of) its original aim and outputs. Non-effective parts of the programme are closed. / There has been a general understanding amongst partners that for DFID U to terminate non-performing parts of the programme was a good step. It appears that DFID is still considered an important partner in the AIDS Donor group and as an important monitor of the HIV response in Uganda. / The remaining programme outputs are performing to expectations. In terms of knowledge generation and dissemination by KMCC (under delta Partnership), there may be value in considering further integration with UAC and NADIC not only for better and ongoing capacity building at NADIC and UAC, but also to increase the initial capacity of NADIC to perform its duties and for KMCC to play a larger role in influencing and changing NADIC into a recognised and effective element of UAC. It is clear that the latter objectives would go beyond the current programme scope, but any such influence and support to UAC “from within” would be helpful to sustain the efforts of KMCC. / The World Bank has shown progress to the extent expected within its mandate of this programme. Naturally, it could not perform an impact evaluation of Combination HIV Prevention in districts where the relevant Combination Prevention is not yet in place. However, the rationale for the Impact Evaluation in one district and its stated objectives would benefit from more intensive monitoring by DFID U, if staff time allows. The recommendation of the previous annual review still stands and is considered very important: i.e. to employ an Impact Evaluation specialist to assess and review the planned Impact Evaluation in Rakai. This review would suggest that this should be a seasoned epidemiologist with experience in evaluation as well as in HIV prevention including incidence and prevalence measurement. / This review also aimed to assess broadly the need and comparative advantage for DFID U to consider a future investment in HIV prevention. This question was therefore an integral part of all interviews. All partners without exception suggested DFID to retain funding to HIV Prevention in Uganda. Despite and perhaps even because of DFID’s decisive move to restructure and terminate non-performing programme interventions, DFID is seen as an important partner with substantial influence and leverage. DFID’s role was considered particularly important in terms of monitoring the multilateral response (such as through the GFATM) , but also in terms of knowledge generation and research. This review certainly identified the lack of research and data upon which to build national and donor planning a major constraint to any future planning of HIV prevention response. DFID was also seen as an important contributor to Technical Assistance (such as in MoH), which was considered a comparative advantage of other donors’ support. / This review certainly sees value in DFID considering a future funding phase for HIV Prevention in Uganda. However, for any future engagement in HIV Prevention, DFID should consider the following: / A detailed political economy analysis should be undertaken to better the various influences and positions in HIV prevention in Uganda by the Ugandan Government, CS, multilateral and bilateral partners. / Secondly, a future programme should consider employing one contractor (or possibly a major international NGO under an accountable grant) that will coordinate a DFID programme without the need for DFID U itself to coordinate various stakeholders and actors. / Thirdly, the future programme should consider how and where best DFID could influence HIV prevention at the highest level. Possibly, influence should be sought at highest political level.

8. Review Process
Following an extensive annual review in the previous year followed by a restructuring and Performance Improvement Plan (decided up on in July 2013 and implemented thereafter), this review was performed as a light-touch exercise. The review was carried out by the DFID Southern Africa Regional Health Adviser jointly with the DFID U team between 18-22 November. / The following partners were visited and interviewed as part of the review: / Irish Aid (as current chair of the AIDS Donor Group) / World Bank (with teleconference of additional WB staff members) / Ministry of Health (Aids Control Programme team) / UAC and NADIC / KMCC (delta Partnership) / Deloitte (financial manager of the CSF) / Chemonics (technical manager of the CSF) / For the review, the original Project Memorandum and logframe, revised logframe versions, the Annual Review of 2012 (narrative and DFID formatted versions), the submissions and correspondence concerning the PIP, the KMCC quarterly and annual reports, the CSF annual report, the Project Concept outline of CDC Foundation, the revised NSP (in part), the guideline and planning documents (such as the Study Protocol) of the Impact Evaluation (Rakai District) (in part) were all consulted alongside other documents.