ADDENDUM TO BUSINESS CASE - Humanitarian Assistance and Resilience Building in South Sudan

SUMMARY INFORMATION
Project Name	Humanitarian Assistance and Resilience Building in South Sudan (HARISS)
Country or region targeted	South Sudan
Type of cost extension (if applicable)	No-cost extension
Original project budget	£443,000,000 / Cost-extension approved by Ministers on 02 May 2018. Budget increased to up to £565,000,000.
Original project start and end dates	1st April 2015 – 31st March 2020
Cost extension value (if applicable)	Not applicable
New project end date (if applicable)	31st May 2020
Business Case Quest/Vault Document No.	Original business case (Vault 5217450) / 1st Business case Addendum and Approval (Vault 3100911)

INFORMATION
What is the project’s purpose?
HARISS is a 5-year programme designed to save lives, avert suffering, maintain human dignity and reinforce the coping capacities of people affected by conflict and shocks in South Sudan. / The programme marked significant shift in how the UK supports the delivery of humanitarian aid in South Sudan, from short-term assistance which meets only immediate needs to a more flexible, multi-year approach which (where feasible) seeks to increase the resilience of affected populations. This shift is a core plank of the UK’s humanitarian reform agenda, and South Sudan was one of the first countries to pilot it. / Up to £443 million was approved by UK Ministers in the original HARISS business case, which was estimated to reach 3 million people between 2015 and 2020. The programme is centred around four main components: / Life-saving humanitarian assistance to reach the most immediate needs of vulnerable people through: i) the provision of food, water, sanitation, and hygiene, health, nutrition, shelter and emergency non-food items; ii) strengthened humanitarian coordination systems which support the whole humanitarian response to be more effective and accountable. / Resilience-building to help vulnerable people prepare for, cope better with, and recover from conflict and natural hazards (including climate-induced) that cause humanitarian disasters and stresses. Through supporting people’s coping capacity, the programme seeks to reduce the need for more expensive emergency assistance. This resilience approach has focused on three areas: / Food security and livelihoods. Supporting livelihood opportunities as alternatives to food aid such as diversified food production systems, stimulating market recovery through cash interventions, supporting traders to source supplies, and enabling vulnerable people to access markets. Also working with households and communities through cash for work schemes to strengthen infrastructure that supports livelihoods and climate change adaptation. / Protection activities helping vulnerable populations better cope with and reduce their exposure to abuses, particularly in relation to Gender Based Violence (GBV). Support for protection has included community-based protection mechanisms, GBV risk reduction and preventions, and increased access to response and treatment services. / Emergency preparedness and response, supporting early planning, warning and action ahead of and in response to disease outbreaks and population displacements. This includes a rapid response capability to deploy within 72 hours. / Monitoring, evaluation, accountability and learning (MEAL) to ensure that the programme learns and adapts, and remains value for money. Third-party monitoring and evaluations assess progress again humanitarian standards and contractual targets and measure performance in terms of: i) conflict-sensitivity; ii) accountability to affected populations; and iii) value for money. / An Internal Risk Facility (IRF) of £6 million per annum to provide the programme with flexibility to respond rapidly to shocks and unforeseen needs across the country. / The programme is delivered through a range of different partners including the UN (FAO, UNICEF, WFP, IOM and the South Sudan Humanitarian Fund), INGOs (Oxfam, IMC, MedAir, HI, Goal and REACH), International Committee of the Red Cross and a private sector consortium (led by IMC Worldwide). It has been running for over three years, and overall performing well given the complex context (i.e. Annual Review scores: 2015 exceeded expectations (A+), 2016 met expectations (A), and 2017 met expectations (A)).
What is the objective of the cost extension or other changes?
The objective of the no-cost extension is to extend the HARISS programme by two months, from an end date of the 31st March 2020 to 31st May 2020. / This two month extension is to enable the HARISS MEAL component contract (Evidence and Learning Facility in South Sudan – ELFSS) which is management by IMC Worldwide to continue for two months after the main delivery partners (e.g. UN, INGOs, Red Cross) have concluded their projects. / This will allow ELFSS which is leading on Third Party Monitoring (TPM) across the portfolio time to synthesis learning and TPM reporting by 31 May 2020. This would contribute to a Project Completion Report of HARISS, subsequently due 31 August 2020. / We are not proposing the extension of any other Accountable Grants, Memorandums of Understanding or contracts which relate to the core delivery of the HARISS programme. We are planning for a successor humanitarian programme to start substantively 1st April 2020.
What is the additional and total support the UK will provide?
The total UK support available up to £565,000,000 as per the original business case and cost-extension approved by Ministers on 02 May 2018. / No additional support will be provided as only the delivery timeframe has been changed.
What are the expected results?
The expected results have not changed from the original business case and cost-extension addendum. This no-cost extension only increases the duration of the programme by two months to enable learning from the MEAL supplier to contribute to the wider programme closure.
What is the approach to implementation?
The implementation approach has not changed from that proposed in the business case. Implementation will be through a range of partners including INGOs, UN agencies, Red Cross and private sector. / The original business case and first business case addendum gives regard to the Gender Equality Act. This still holds, with this addendum making no substantives changes in this regard.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
There are no key changes to the original business case or first business case addendum. / The theory of change remains broadly unchanged, and there is no new evidence from ongoing monitoring, evaluation or learning work.