Annual Review

Project Title:	Increasing Access to Reproductive Health commodities in Ethiopia

Date started: November 2011	Date review undertaken: August 26- September, 25 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Introduction and Context
What support is the UK providing?
DFID is providing £18m from November 2011 - March 2015 to DKT to increase access to Reproductive Health (RH) commodities as part of the UK’s efforts to accelerate progress towards the health MDGs in Ethiopia. The programme is supporting the private sector, through social marketing, to increase the sustainable demand for and supply of RH commodities for family planning and HIV prevention. This is deemed the most cost effective way of reducing maternal mortality and HIV infection and compliments DFID’s scaled up support to Ethiopia’s health sector. / Our support is assisting DKT to socially market a full range of RH commodities including male and female condoms, oral contraceptive pills, injectable and implant hormonal contraceptives, medical abortion drugs, misoprostol for post-partum haemorrhage and Manual Vacuum Aspiration (MVA) kits. DKT are also exploring the social marketing of other important commodities such as clean birth kits and oral rehydration salts for the treatment of diarrhoea. DKT is a valued partner of the Federal Ministry of Health (FMOH) and supplies commodities to government health facilities when public supplies run out. DKT is also the main importers of RH commodities for organizations such as Marie Stopes International and IPAS who run RH clinics and programmes in the country. / In addition to supplying commodities, DKT implements a wide range of awareness building and targeted behaviour-change communication activities to enable rural and urban women / couples make informed Sexual and Reproductive Health (SRH) decisions. DKT works with pharmacies and drug vendors to ensure correct RH advice is provided with its commodities as well as through the Wise Up campaign that targets commercial sex workers and their clients. Whilst promotion and awareness activities continue nationwide DKT is increasingly focusing efforts on high risk or vulnerable populations such as university students and women in remote underserved regions such as Afar and Somali. These efforts will further assist Ethiopia reach its contraceptive prevalence target of 66% by 2015 and reduce the growing inequities between urban and rural populations.

What are the expected results?
The impact of the programme is to accelerate progress towards Ethiopia’s health MDGs, in particular a reduction of maternal mortality from 676 deaths per 100,000 live births to 262 by 2015; reduce the total fertility rate from 4.8 children per women to 4 by 2015; and decrease HIV adult prevalence from 1.5% (2011 Ethiopia Demographic Health Survey). / The programme’s outcome is to increase the use of contraceptives among Ethiopian women and the use of condoms for protection from HIV by the most at risk men and women. / The programme’s outputs are : / Increased supply of RH commodities / Increased demand for RH commodities; and / National RH supplies system strengthened. / The business case predicted that over four years the programme will distribute: / 295 million male and 136,000 female condoms; / 12 million cycles of oral contraceptives; / 5.6 million injectable contraceptives; / 2.2 million emergency contraceptives; and / 1.2 million misoprostol tablets to prevent post-partum haemorrhage / And that these commodities would help avert: / 2.5 million unintended pregnancies; / More than 8,000 maternal deaths; / More than 240,000 abortions; and / Between 35,000 and 100,000 HIV transmissions. / Based on demand and updated sales targets the number of commodities planned to be distributed over the programme’s lifespan is greater than the numbers provided above. These results therefore should be seen as a minimum and are expected to be exceeded.

What is the context in which UK support is provided?
DFID has been supporting social marketing of Sexual and Reproductive Health (SRH) commodities through DKT Ethiopia since 2005. Support has been managed on our behalf by the Embassy of the Netherlands through a Joint Grant Agreement together with Irish Aid. / Whilst the new £18m Increasing Access to RH Commodities in Ethiopia programme was being designed DFID was also developing its RH Framework Agreement. To achieve optimal value for money all suppliers of new RH programmes are to be identified through a procurement process – either using the restrictive tender under the framework agreement or through an open competitive bidding process. To allow continuity of commodity supply it was agreed that the first year of this new programme (£6.5m 2011/12) would be implemented by DKT, whilst the RH Framework Agreement was being finalized. This support continued to be managed by the Embassy of the Netherlands under the Joint Grant Arrangement. / In May 2012 a procurement process under the RH Framework Agreement was conducted and identified DKT as the supplier for the remaining period of the programme. Whilst the overall impact and outcome of the programme has not changed we requested bidders to focus programme activities to reach the most vulnerable and underserved populations (See Quest 3709816). This is in response to the 2011 Ethiopian Demographic Health Survey (EDHS) results that showed growing disparities in RH indicators among Ethiopia’s urban/rural populations and in the Developing Regional States (DRS). / A new milestone contract was signed with DKT in October 2012 and is used for managing our support going forward. This new support continued to be part of the Joint Granting Arrangement with the Embassy of the Netherlands. Funding from Irish Aid has discontinued after December 2012 due to domestic financial constraints. . As we are now requesting DKT to focus on the more remote and underserved populations, cost per benefit achieved will be higher. However it is believed that working in the most difficult areas, where fertility and maternal morbidity is considerably higher than elsewhere, will ultimately have a greater impact on Ethiopia’s maternal mortality and fertility rates. / This review covers the period of October 2012 to September 2013.

Section A: Detailed Output Scoring
Output 1: Increased supply of RH commodities
Output 1 score and performance description: Six indicators out of which 4 have been scored: two A++ two A+, one A and one not scored. Overall score for Output 1: A++ moderately exceeded expectation. / Summary: / Output 1 is a major deliverable result under the program, improving SRH products supplies is a critical component of DFID’s Reproductive Health Framework for results. DKT has been delivering 20 to 30% of the total Couple Year Protections (CYPs) achieved in Ethiopia. It has continued to be the major reproductive health products supplier to the private sector and NGOs, in the review period. There are considerable achievements in expanding access to SRH products by the general population and particularly this year by the previously underserved rural and pastoralist populations. The results of this review have demonstrated a sign of shift in demand from short to long-term contraceptives; the country level demand for the later has improved. Moreover, the demand for DKT condoms have continued to be relatively reduced GoE has continued improving its own procurement capacity. The importation and less targeted distribution of free condoms by USG partners have significantly reduced the demand for DKT condoms by NGOs and their clients. / Except for female condoms and lubricants, all products distributed during the review period have either met or exceeded targets. Delayed registration of female condoms, due to multiple unprecedented and changing requirement of GoE has affected female condoms distribution. A restrictive product promotion environment and a slowly growing demand for the produce are among the major factors for the underperformance in lubricants. / Progress against expected results: / Indicator 1.1: Couple Years Protection provided by reproductive health products sold by DKT / During the review period, contraceptives that DKT distributed had generated a total of / 3,683,922contraceptive years of protection. This achievement is 191% of the target. Score: A++ Substantially exceeded expectation / Baseline Milestone 1 (2012/13) / Couple Years Protection provided by reproductive health products sold by DKT Planned 1,924,247 / Achieved 3,683,922[1] / Narrative: / This is a new indicator introduced in the log frame during the last annual review; it monitors the cumulative effect of the distribution of individual commodities to provide a higher level result measurement. Tracking this indicator encouraged the project to adopt the change in preference to different types of contraceptives by the nation. The high achievement under this indicator is primarily associated with a planning challenge in forecasting the shift in annual demand towards long term contraceptives (an IDU gives a CYP value of 576 condoms) and an upsurge of promotion to meet the DKT Ethiopia 1 billionth condom distributed campaign targets. / The four major contributors to the CYP generated during the review period are Intra Uterine Devices (42.6%), injectable (18%) male condoms (16.7%) and Implants (13%). This marks the beginning of change in major sources of CYPs attribution by type of contraceptives, long term contraceptives exceeding injectable, oral contraceptive and condoms. It is to be noted that the increase in the use of modern contraceptives in Ethiopia has been associated with the sharp increase in the use of injectable from 3% in 2000 to 21% in 2011. / GoE has been able to procure its own supply of contraceptives this year, a small growing demand from the private sector is observed. PSI through its USAID funded program procured and distributed free condoms estimated amount of 30-40 million in over 100 towns through its sub-grantees and other programs. See Annex 1 for list of all SRH commodities distributed in the review period, all exceeded targets except female condoms, and water based lubricants. Registration of Female condoms registration process by GoE delayed distribution to end users, while the restricted promotion of lubricants that can be used by men who have sex with men has limited performance. This challenge will continue over to the next years. / Indicator 1.2: % of pharmaceutical outlets in market towns stocking at least three DKT RH product categories: DKT’s market penetration survey in 2013 (MAP 2013) that covered 164 urban kebeles and 219 market towns with 1,395 randomly selected pharmaceutical outlets had confirmed that 88% of the outlets in market towns stock at least 3 products which is above the 80% target for each type of outlets. Score: A met expectation / Baseline Milestone (2012/13) / % of pharmaceutical outlets in market towns stocking at least three DKT RH product categories Planned 59% (2012) 80% / Achieved 88% / Indicator 1.3: % of market town service providers (clinical outlets) stock at least three DKT product categories: The MAP 2013 confirmed 93% of clinical outlets in market towns stock at least three of DKT’s products. During visits to randomly selected market town clinics, the review team observed that the providers are predominantly equipped with short acting contraceptives. All interviewed were not providing long term contraceptive services primarily due to lack of skill and training. Despite the presence of other DFID and Embassy of the Kingdom of Netherlands (EKN) funded projects in the market towns (such as Marie Stops and Family Guidance clinical projects), there is a limited collaboration and effective referral linkage between DKT’s Rural Market town initiative and these programs. Score: A++ substantially exceeded expectation / Baseline Milestone (2012/13) / % of market town service providers (clinical outlets) stock at least three DKT product categories Planned 44% (2012) 56% / Achieved 93% / Indicator 1.4: % of urban (excluding market towns) pharmaceutical outlets stocking at least five DKT product categories: MAP 2013 survey reported 71.5% of pharmaceutical outlets in big town provide five or more DKT product categories. This coverage varies among regions, the lowest in Somali (45%) and Benishangul-Gumz (56%) regions, while Afar and SNNP are among the low penetration range of 62%. Score: A+ moderately exceeded expectations / Baseline Milestone (2012/13) / % of urban (excluding market towns) pharmaceutical outlets stocking at least five DKT product categories Planned 44% (2012) 50% / Achieved 71.5% / Indicator 1.5: 50% of non-pharmaceutical outlets in urban areas stocking condoms: The DKT Market Penetration survey done in 292 urban kebeles, concluded the weighted coverage of condoms availability was 47%. Score: A+ / Baseline Milestone (2012/13) / % of non-pharmaceutical outlets in urban areas stocking condoms Planned NA 32% / Achieved 47% / Indicator 1.6: Rural kebeles (villages) meet the minimum standard of coverage (with at least one private outlet stocking at least one brand of condom): This is only measured every two years and is not available for 2012. Score: NA / Recommendations: / Although most of the factors that attributed for the overachievement were linked to seasonal fluctuation and DKT’s own intensified campaign of reaching a billion condoms distributed, DKT has agreed to review some of its target and improve the quality of demand creation and distribution of the commodities for 2013/14. The joint donors will follow the status through quarterly reports. There is a need for a rigorous review of progress on this indicator in the next annual review, by when seasonality and predictability of demand factors will be better understood to make a stronger recommendation, if the contract targets shall be amended. / According to a mapping survey by DKT in 2013, 23% of rural market town sites don’t have access to long-term contraceptive service providers and outlets. DKT has gather GPS data on the distribution of outlets at rural market towns but have not completed creating a network of public, NGO and private service providers for each market town; where by referrals after counselling of rural mothers will be completed by service provision. In 2013/14 DKT shall establish model referral clinical networks working with NGOs like MSI, FGAE and private clinics. This will be further supported by a new model evaluation funding from Gate’s Foundation. The success of this approach should be reviewed in the next Annual Review. / The demand for commodities and therefore the number of commodities distributed is unpredictable and influenced by a multitude of factors including demand, presence of commodities from other suppliers and restrictions. DFID has initiated negotiation and rounds of discussion with USG, UNFPA and EKN to identify major challenges and collaboration points; it has also taken an active part in the development of condom strategy. DKT should actively and consistently be involved in national level universal demand forecasting and the gauging process to find the right balance between free and socially marketed condoms, based on evidence it may revise down the male condom forecasts. / Impact Weighting: 60% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N/A
[1] All data under this indicator covers October 2012 to September 2013 distribution

Output 2: Increased demand for RH commodities
Output 2 score and performance description: All indicators scoring A. Overall score for: A met expectation.
Progress against expected results: / Narratives: / The new log frame proposed in 2011/12 tracks demand for family planning among high risk/vulnerable groups: female sex workers; rural women and high education students. It employs a standard behaviour survey that measure change based on a ‘Likert’ scale for motivational, ability and opportunity factors affecting behaviours of contraception use. In this review period DKT conducted the first Behavioural Change Impact Survey (BICS12). All of the output indicators under the new log frame will serve as a baseline status and some shall be tracked through Output tracking surveys every year. / DKT uses a peer education techniques and counselling to make change among the BICS indicators track. A high coverage (more than 80%) with education and counselling will improve the status of behaviours that are selected for the log frame. / There were no milestone figures for 6 out of 9 all of the indicators during the review period. However for scoring purpose, the reviewers propose to analyse the number of targeted population reached through DKT’s peer education and counselling on HIV, family planning, Sexually Transmitted Infections (STI) and negotiation skills. DKT has reached 174,822 higher educational institute students and 8,146 female sex workers and their clients with reproductive health education and messages, all exceeding targets. This is a reliable proxy indicator that suggests positive change might have happened on the status of 2.1-2.3 and 2.7-2.8. / Moreover, DKT had reached 680 market towns and more than one outlet in each of these towns, through communication campaigns that served more than 220,000 rural women and men and 6,663 with a small group based counselling and referral services. Up to 14% (385,000 doses) of all injectable sales happened in the market towns that DKT moved in this year. This shows the impact on 2.1 and 2.2 has been high enough to stimulate women procuring and using the contraceptives. / Indicator 2.1 Baseline Milestone (2012/13) / Social Norm score increases from 3.12 to 4.0 among FSW in DKT Wise up areas Planned 3.12 3.5 / Achieved Survey data not available / Indicator 2.2 Baseline Milestone (2012/13) / Self-efficacy score increases from 4.63 to 4.80 among FSW in DKT wise-up areas Planned 4.63 4.7 / Achieved Survey data not available / Indicator 2.3 Baseline Milestone (2012/13) / Attitude score increase from 4.16 to 4.5 among FSW in DKT wise-up areas Planned 4.16 4.3 / Achieved Survey data not available / Indicator 2.4 Baseline Milestone (2012/13) / Perceived availability score by rural women of reproductive health age (RWRHA)increases from 3.6 to 4.0 Planned 3.6 / Achieved 3.6 / Indicator 2.5 Baseline Milestone (2012/13) / Support score among RWRHA increase from 3.6 to 4.0 Planned 2.6 / Achieved 2.6 / Indicator 2.6 Baseline Milestone (2012/13) / Attitude score among RWRHA increases from 2.6 to 3.3 Planned 3.10 / Achieved 3.10 / Indicator 2.7 Baseline Milestone (2012/13) / Social support among higher education institution (HEI) students increases from 3.1 to 3.6 Planned 3.10 / Achieved 3.10 / Indicator 2.8 Baseline Milestone 1 (2012/13) / Belief score for HEI students increases form 3.1to 4.0 Planned 3.7 / Achieved 3.7 / Recommendations: / Whilst, the rapid scale-up in reaching over 600 rural market towns through communication campaigns has been promising, the review has identified a limited reach to youth and inability to provide range of contraceptives on site as emerging challenges. The review team recommends for a continues analysis of effectiveness of the approach at different market towns, a profiling of market towns based on performance and further decision on how to continue programming at different levels of success rate shall be conducted by DKT. DKT should be able to determine the best locally tailored method of availing contraceptives for the newly created demand at market towns to increase cost effectiveness. / The rural market town activities could be slightly modified to address young yet-to-be or newly married couples during wedding sessions in large numbers in different parts of the country. These sessions in addition to informing couples about contraceptive methods, could be used to empower newlyweds to plan their family sizes, safe conception and other maternal and reproductive health message. / Demand creation in developing regional states (DRS), particularly pastoralist regions of Afar and Somali continued to prove challenging due to cultural, social factors and high turnover of staffs. Depending on how successful the new demand side program in these locations; DKT may start primarily focus on supply and logistic component for providing contraceptives and other SRH products. / Only 23% of these sites have access to outlets with full contraceptive options; the referral linkage between those counselled by this approach and clinical service providers is at early stage, probably leading to a high cost per successful provision contraceptives for each demand created. No private or public provider that the review team visited in the two towns reported any referrals from the MTAs. This review recommends for a mapping of clinical services around the MTA and establishment of effective referral linkage and collaboration with other programs to increase efficiency. / DKT implemented the newly proposed logframe during the annual review in 2012; indicators under this output have required 3 surveys of extensive data collection and analysis. This review proposes not to conduct follow-up surveys for consecutive years under indicators of sex workers and university students, rather to have an end-term final evaluation that will be compared with what has been recorded this year. This recommendation will be reflected in the attached proposed slight modification of the current logframe. DKT will continue to do annual tracking surveys for behaviours on family planning by rural women, as this is a new initiative that requires a strong evidence base decision making. / Impact Weighting: 30% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N/A

Output 3:National Reproductive Health supplies system strengthening
Output 3 score and performance description: Two indicators scoring A Overall scoring for Output 3: A met expectations. / Progress against expected results: / Indicator 3.1: Increased number of outlets reporting positive experience of DKT Training / Baseline Milestone 1 (2012/13) / Increased number of outlets reporting positive experience of DKT Training Planned 50% 60% / Achieved data wasn’t collected and not available / DFID has discussed the reasons for the absence of data on this indicator; DKT didn’t collect quality and complete data after and during the provision of the trainings. DKT is establishing a new functional system that feeds credible data to monitor this indicator in the future. / Indicator 3.2: Improved polices supporting private sector distribution of RH products / Score: A meets expectation / During the reporting period, the Ethiopian government adopted its first National Condom Strategy that outlines principles of maintaining the distribution of condoms through private sector. This is a major positive policy move that will allow us to know the universal needs and recommended means of distribution of condoms in Ethiopia. This policy has initated discussions around the sustainability of condoms supply in Ethiopia and finding the right balance of social marketing versus free condoms in view of sustainability. DKT sits in the national technical working group that drafted the strategy document. The government registered or re-registered 8 new product for private sector distribution; Sensation Heat (with a warming agent in the lubricant), Trust Implants, Miso-Fem misoprostol tablets, Elelta Clean Birth Kits (with and without misoprostol), and Smooth Move personal lubricant, Second Generation Female Condom(‘FC2’), iPlan oral contraceptives, and MVA Plus. This is an improvement particularly for FC2 and lubricants registration, which had some policy and operation challenges of registration. / Indicator 3.3: Research methodology and results shared with RH community : Score A meets expectation / DKT/E collected data for the three (3) BCISs covering rural women and men, higher education / students, and female sex workers in 2012 and finalized the reports during the current reporting period. DKT/E disseminated findings in May 2013 along with MSI/E at a workshop attended by partners and donors. Score: A / Recommendations: / The outcome of the policy change was not sufficient enough to coordinate different players distribution free and socially marketed condoms, which further requires an active involvement of DKT in quantifying the universal demand for condoms, proposing the right balance and monitoring mechanism of the distribution of free and paid condoms. This may require jointly commissioning some studies that can inform such decisions and flagging the need to have a clear guidance by the national government at higher level of donors-GoE forums. / DKT in the next years of implementation shall be able to identify and intervene on what favourable policy changes and respective activities are required. / Impact Weighting: 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N/A

Section B: Results and Value for Money
1. Progress and results

1.1 Has the logframe been updated since last review? Yes, the logframe that was provided in the Business Case was updated in Jan 2013 to reflect baseline values under Output 2 but the indicators were not changed. A proposed change on frequency of data collection under output 2 for the remaining period is attached with this review report. / 1.2 Overall Output Score and Description: / A+ outputs moderately exceeded expectations. / 1.3 Direct feedback from beneficiaries / Yes, rural women and men, university students, sex workers in the wise up programme and some of the DKT young marketers were interviewed by the review team. Members of the rural community interviewed expressed positive feeling on the quality of MTA campaigns and growing replication effect messages transmitted during such events. The sex workers reported that drop-in centres and income generation schemes along with condoms have empowered them towards healthy practice. They have reported DKT’s programme increased the acceptability of condom use with paying partners and that the availability of affordable and attractive condoms enabled them to protect themselves from HIV infection and unwanted pregnancy. The young marketers were very positive about the income they receive from condom sales even though sales have recently decreased due to the flooding of the market with free condoms. This feedback is similar to last year’s observation.
1.4 Summary of overall progress / The Increasing Access to RH Commodities in Ethiopia programme has progressed well and continued to achieve high output level results as it progress in to the second year of implementation. It has exceeded expectations in areas such as commodity distribution, and training of sex workers and university students. DKT has been able to conduct, use and disseminated 3 major surveys that measured the current status of behaviours among the major target groups of the program. / DKT has succeeded in the large scale roll out of social marketing in to rural communities; it has managed to get 10 field teams up and running covering hundreds of centres of market towns that pull men and women from more than 10-30 kebeles, each. The uptake of commodities is improving among the low Contraceptive Prevalence Rate DRS. / The challenge of getting sex works to use condoms event with their regular clients have continued. Report from a survey to estimate the size of female sex workers population in seventeen towns indicates that 57.4% and 64.3% of the study participants reported that they have heard about Wise Up and its services [2].This is a high level of coverage and progress. / DKT has continued to involve young people in the program, during the review period, the Young Markets (YM) initiative sold nearly 26 million pieces of condoms and earned income amounting to US$113,000.The initiative has also become an source of ‘sales talent’ for DKT’s mainstream sales activities. DKT had hired a number of the best performing YM salespeople and will continue to do so going forward. / A potential duplication with USAID’s MULU prevention program for sex workers is happening in over 20 towns, DKT’s sub-grantee TLH has reported some of its peer educators and targeted beneficiaries have started receiving similar services and additional incentives that is affecting the local level acceptance of the project. DKT’s donors have started mapping the level of the duplication and solutions. MULU prevention program provides clinical services including HIV testing and treatment for STIs, DKT can collaborate with the program by referring sex workers to these clinics. / The theory of change is still seen relevant to the programme and does not need adjusting. The higher than expected sales figures demonstrate that our assumptions on effective marketing, reliable distribution systems, people using distribution outlets and commodity affordability/accessibility are holding true. People know about the products, are accessing them and buying them at higher levels than expected. However we will only know whether the outputs translate into outcomes and impact (i.e clients are using them consistently and correctly) when we measure the outcome and impact indicators: % students having unprotected sex (BICS), reduced HIV prevalence (the next EDHS) and reduced fertility in the Mini- EDHS.
1.5 Key challenges / The main challenge identified were the difficulty to estimate the annual demand of free and paid condoms, limited predictably of long term contraceptives demand, socio-cultural barriers and a potential duplication of effort with USG new HIV prevention program. The increased capacity of the public sector to procure and supply RH commodities (especially condoms) in Ethiopia has continued to reduce DKT’s role as a backup supplier. / This year a technical group that outlines the global need of condoms and detailed strategy of forecast, procurement, registration and distribution has been working to resolve the some of the challenges mentioned above. DKT has taken part in the technical working group, DKT and its donors have been engaged in multiple meeting with USG and the implementing partner, but not much has been improved in coordinating efforts to reduce the impact of free condoms on socially marketed ones. DKT and its donor partners along with UNFPA and GoE need to continue to coordinate with USAID more closely on condoms and other suppliers. / The effort to create demand among sparsely populated mobile communities in fragile environments has been challenged by the limited presence of clinical and non-clinical outlets, high staff turnover, socio-cultural barriers and the technical difficult of designing the appropriate messages and selection of the socially appropriate communication channel. The demand on short term contraceptives at Afar has not been changed. There are also substantial cultural and religious barriers to women in these areas to utilising family planning, DKT may need to highly collaborate with DFID’s new demand side program for pastoralist areas to better understand the determinants of behaviour and choice of media at these locations.
1.6 Annual Outcome Assessment / The programme has made a good progress to achieving the programme’s outcomes and goals. The refocusing of the programme toward reaching less served populations will help ensure that the programme continues to meet the SRH needs of Ethiopia’s population and together with our investments in the health sector, bring about a reduction in maternal mortality and HIV infection.
[2] Report on Sex Workers Population Size Estimation in Seventeen Towns of Ethiopia. Momentum Consultancy PLC, August 1, 2012

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / Yes, the program has met all of its contractual milestones to date & the full forecast for the review period has been spent. This review has observed the contractor is delivering faster than planned; it uses two sources of money. The management at DKT has flagged with this pace they may run out of funds and may require an early call down of funding that the originally agreed schedule of payment. DFID will monitor the progress in financial and physical terms to make informed decisions on this regard. / 2.2 Key cost drivers / The key cost drivers identified in the business case are (i) unit costs of commodities; (ii) mix of commodities procured; (iii) distribution costs, and (iv) freight and handling fees. / This year 45% of the cost was attributed to procurement ($ 6.97 million) and transportation ($0.37 million) of commodities, followed by 30% expenditure in promotion and communication costs that partly attributes to the scale up of capital cost intensive rural and DRS based social marketing. We continue to monitor these costs and have not seen any major increase from the original budget. DFID and DKT will continue working to identify the best cost–effective combination of contraceptives as the pattern of demand and supply is now shifting more to long-term contraceptives, at national level. DFID’s contract with DKT for the remaining period of support has negotiated costs down from the original commercial proposal and will monitor cost drivers throughout its life span. DKT are still managing to cover all staff salary costs from the sales of its commodities. / 2.3 Is the project on-track against original timescale: / Yes, exceeded CYP targets, which are major indicators of progress

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no change in evidence base that has implications on the project, DKT’s own large scale behavioural surveys were the major source of new evidence, findings highlighted the new focus on rural men, women, non-paying partners of sex workers and higher education institute students should continue. The evidence from EDHS 2011 has helped refocus programme activities on reaching the most vulnerable and underserved populations. Whilst this new evidence does not change the overall theory of change or purpose of the project it has changed the focus of activities and the indicators by which programme success will be judged. These changes can be seen in the new programme design and logframe on Quest: 3709820 and 3709816. / 3.2 Where an evaluation is planned what progress has been made? / An independent evaluation of the programme will be conducted in March 2015 together with the other developing partners. Behaviour Change Impact Survey, Market Town mapping Survey, Urban Coverage Assessment Surveys have been conducted to populate baseline value for the new logframe.

4. Risk
4.1 Output Risk Rating: / Low / 4.2 Assessment of the risk level / The original risk assessment for the programme is still relevant. A risk assessment was submitted by DKT as part of their proposal for the new period of support and risk overall to be low (See Quest: 3709890). The Office of Auditors General (OFAG) findings of poor financial management in universities presents a new risk, mitigation strategies are been put in place by DKT (see below).
Risk of funds not being used as intended / DKT has submitted the annual audit and expenditure reports as required by DFID. These have been examined, commented on and discussed with DKT and the other Joint Grant Arrangement partners. There is no evidence to suggest that UK’s funds have been used for areas outside of the programme agreement (e.g. staff salary or taxes) or lost to fraud or corruption (See Quest: 4079448). Following the 2012 OFAG report by GoE, which reported a considerable amount violation of regulation by some universities, the reviewer team did an in-depth review of the £150,000 grant transferred to universities through the Higher Education Initiative (HEI) under this program. In all universities, DKT will implement a mix of safeguard mechanisms including: multiple tranches of advance after reviewing reports shift the support to universities in to more of in-kinds than cash and conduct systematic spot checks. The progress on this shall be reported by the next semi-annual report in January 2014. / 4.4 Climate and Environment Risk / There has been no major change in the climatic or environmental risk factors that were stated in the business case. / The business case identified that the most significant negative impact of this programme on the environment could be the unsafe and inappropriate disposal of health care waste. The FMOH is including the construction of incinerators for health care waste disposal in the construction of its new facilities. Sharps boxes for needles and the disposal of contaminated waste are available in health centres and governed by clinical waste disposal guidelines. However the standard of safe health care waste disposal in private clinics or in pharmacies is not known. We will advise DKT to include advice and information on safe clinical waste disposal in their interactions with private providers who sell their products. / The programme is also having a positive environmental effect by reducing unwanted pregnancies and potentially slowing population growth. Rapid population growth is likely to pressure environmental resources-water and land availability and food security and access to services. It is associated with rising greenhouse-gas emissions. Family planning can improve the health and well-being of women and families, increasing resilience in the face of climate change and slow population growth. Climate change experts have identified family planning as the best single buy to reduce carbon emissions[3] .Population increase leads to migration and movement into areas of greater environmental hazard. Migration is rising in Ethiopia with environmental and climate pressures being the key drivers.[4]
[3] See Wheler D and Hammer D The Economics of Population Policy for Carbon Emissions Reduction in Developing eCountries. Centre for Global Development Working Paper 22. 9 November 2010
[4] Foresight Report on Migration and Global Environmental Change (2011) – see www.bis.gov.uk/foresight/migration for the full report and background papers; and accompanying Nature article, Climate change: Migration as adaptation. www.nature.com/nature/journal/v478/n7370/full/478477a.html.

5. Value for Money
5.1 Performance on VfM measures / The business case outlined the following indicators to monitor value for money during the programme period. The measurement for 2012/13are provided below: / Comparison within and beyond Ethiopia of unit costs of commodities procured / DKT has managed to continue procuring SRH products cheaper than the other main suppliers in the country (USAID and UNFPA).This has been true although the commodities are packed and branded for individual level sale, unlike the others which import bulk products to be distributed free at public facilities and NGOs. The following table summarizes cost comparison by major products, for full details see Quest 3980898. / Product Unit cost DKT Unit Cost USAID Unit Cost UNFPA / Combined Oral Contraceptive [5] $0.18 $0.28 $0.24 / Male condoms[6] $0.031-$0.041 $0.031-$0.033 $0.027-$0.037 / Injectable (bulk)[7] $0.54 $0.86 $1.05 / Implant $8.04 $19.62 $8.925 / IUD[8] $0.37 $0.30 $0.39 / Misopristol $0.14 NA $0.51 / Number of and cost per Couple Year of Protection (CYP) provided / The cost per CYP was calculated by dividing the total grant money utilised over the review period[9] by the number of CYPs generated by DKT during the same period. For 2012/13 this is US$ 6.2 /CYP , higher than last year’s 5.73/CYP. The increase in unit cost is primarily associated with the high capital and community mobilization cost associated with new initiatives reaching rural (MTA) and pastoralist communities. This is highly cost effective when compared to the global estimate of US$8 per year per women using contraception This value can also get compared with DKT’s own performance in 2012 in India (1.34USD), Turkey (10.79), and Mozambique (13.65)USD. [10] / As noted in the 2012 review, that the US$ 6.2 is slightly an overestimate of the actual cost as it includes costs of distributed commodities that do not yield CYPs (medical abortion drug, MVA kits, oral rehydration salts and lubricants). / Number of and cost per unintended pregnancy prevented / A total of 703,098 unintended pregnancies were averted during 2012/13 at a cost of US$ 11.5[11] per unintended pregnancy averted. This rate is lower than $ 21.1 of last year and below the global average of US$28 to avert an unintended pregnancy as estimated by the Guttmacher Institute and used as the bench mark in the Business Case. / Using an impact calculator (MSI International Impact Tool) estimate the number and cost of maternal deaths and DALYS saved – this year’s review is based on MSI Impact calculator 2, which has a slightly different assumptions. We used MSI Impact calculator 2.1 for last year. The new model attributes the impacts of contraceptives more for improving DALY than maternal mortality. Hence, the modelled cost effectiveness of contraceptives is now high for DLAY in relative to mortality prevented gains. / A total of 1,333 maternal deaths were averted during 2012/13 at a cost of US$ 6,608 per maternal death. This is more expensive than the global average of US$ 3,050 as estimated by the Guttmacher Institute and quoted as a benchmark in the Business Case. It has also gone higher from $ 5,496.26 last year; this is primarily attributed to the change in assumption of MSI impact tool 2, which has revised its assumption for the impact from FP commodities on maternal death. The reviewed program is not a typical safe motherhood program, it doesn’t provide delivery, blood, surgery and antibiotics services to be fully compared and efficient as set by the Guttmacher Institute. However, the program still represents good VFM, when this is broken in to DALY’s saved. / A total of 1,649,509 DALYs were averted at a cost of US$ 4.90 per DALY averted. This is lower than the global average of US$ 62 as estimated by Guttmacher Institute and quoted in the Business Case. In general, the Guttmacher milestones are not the best indicators to monitor this program, which in not a typical safe motherhood program. / The higher than average cost per maternal death averted may be explained by this calculation only including the impact of contraceptives and not including the impact of misoprostol and MVA kits. If these were included the number of maternal deaths averted would be higher and the cost per death averted would be reduced. / Number and costs of HIV infection averted. / With 1.5% HIV prevalence in Ethiopia (EDHS 2011), 150 transmissions can be averted per 1,000,000 condoms used. In 2012/13 DKT distributed 71,141,088 male condoms in Ethiopia. This could prevent 10,671 HIV transmissions. The cost of the condoms including shipping and branding costs was US$ 3,059,066. This results in the cost per HIV transmission averted at US$287.This is a crude estimate that assumes all condoms distributed are used correctly and effectively. More in depth research would be required to ascertain the exact number and costs of HIV averted by this programme. Whilst there is no benchmark for the cost of HIV transmission averted provided in the business case, the cost reported is highly cost effective. / 6. The improvement in efficiency has been gained through DKT assisted capacity building of FMOH and private sector in doing forecast, promotion and distribution of SRH commodities, it has trained and capacitated over 40 higher education institution to plan and execute reproductive health and HIV programs for youth. / 5.2 Commercial Improvement and Value for Money / The new initiatives that are pushing DKT’s resources to hard-to-reach locations and communities are incurring more cost. The year 2012/13 have laid the foundation for creating more demand in previously unreached areas. The cost incurred includes procurement of capital items that will be used in the remaining period of implementation. The demand being created can result in an increased sale of commodities in 2013/14 and beyond, leading to an improved level of cost effectiveness. If DKT succeeds in creating demand in previously underserved areas, even marginally, this will have a high impact in saving lives and initiates social norm change, that can’t be simply captured through MSI Impact Calculator. The value for money for these program in-terms of maternal death is also much higher than what is calculated through MSI impact calculator this year, as the medical abortion drugs impact is not captured. Unsafe abortion is top 4th cause of death in Ethiopia, the impact from drugs and kits distributed (178,000 and 6,400 respectively) couldn’t be estimated, as it requires the actual number of medical abortion conducted, which we don’t have. / DKT is providing social marketing services across the country and covering all of their staff costs with the revenue raised from the sale of their products. They are also promoting commodities aimed at different segments of the market so that the more expensive products can subsides the cheaper commodities aimed at those less able to pay. / DFID’s new RH commodity quality policy requires DKT will be required to only procure commodities that have been qualified under it. This will reduce the number of products and manufacturers that DKT can buy commodities from and may require a lengthy process of registering new products in Ethiopia, thus potentially reducing the competitiveness of DKT. The other major condom provider, USG, also procures items that meet Stringent Regulations, but they distribute them for free, less targeted and in large volume. Consequently the unit costs of commodities are likely to increase, in the future. Currently DKT has not been reported it as a challenge. This will have to be monitored closely throughout the programme lifespan. / 5.3 Role of project partners / The Embassy of the Netherlands has been leading the oversight of DKT as the lead donor under the Joint Grant Agreement. This has been at zero cost to DFID. We have continued to be satisfied with the Netherlands leadership and oversight of our support to DKT. All financial and programmatic reports and audits have been received on time and to a satisfactory standard. Audit issues have been followed up and resolved within the expected timeframe. We will continue to work with the Netherlands under a similar arrangement going forward, they provided technical assistance to improve cost effectiveness by improving mix of contraceptives DKT supplied. / 5.4 Does the project still represent Value for Money / Yes. The assessment of the value for money indicators above shows that this programme still represents good value for money. DKT’s well established brands, logistic systems and over 4700 pharmaceutical, 5800 clinics, and 20,000 non-pharmaceutical outlets have made it to continue being a high VFM partner for SRH commodity distribution in Ethiopia. / 5.5 If not, what action will you take? / Not relevant.
[5] DKT prices include branded packaging (3 pack box and dispenser box)
[6] DKT and USAID prices include foil printing. UNFPA prices do not include foil printing. Packaging, artwork and shipping not included.
[7] DKT price includes syringe and needle. USAID and UNFPA products do not include syringe or needle. DKT's packaged product (Confidence) includes one each vial, syringe and needle, instructions and reminder card in sealed blister pack. 20 blister packs / branded dispenser box.
[9] The review period for all cost effectiveness covers July 2012- June 2013
[10] DKT INTERNATIONAL COST AND RESULTS – 2012. Accessed at http://www.dktinternational.org/wp-content/uploads/2013/06/2012-COSTRESULT-Expanded-2.pdf
[11] Note, all impact calculations were made using MSI Impact 2 , the result reported are not life span effect, but of 2012 and 2013

6. Conditionality
6.1 Update on specific conditions / Not relevant.

7. Conclusions and actions
DFID Ethiopia’s Increasing Access to RH commodities in Ethiopia programme has performed well in the review period. It has exceeded all indicators that could be measured , reached its 1billion condos target, made progress in finalization of female condoms and lubricants. The program has succeeded, while operating under major challenges of difficulty in forecasting the national level demands and potential duplication. Value for money of the programme has continued to be good. Awarding the contract for the remaining programme period through a competitive procurement process has driven our commercial advantage and should ensure continued value for money going forward. / The progress in scaling up MTA to rural sites has been promising but requires a close follow-up and collaboration with clinical service providers and outlets to reduce the missed opportunity of losing mothers reached by the MTA campaigns that are interested to use contraceptives. If DFID’s new demand side program succeeds in improving demand better in 2013/14, DKT’s scope can be reduced to commodity logistics and outlets management in pastoralist areas. This will be determined during the annual review for 2013/14. / The level and depth of duplication with the USAID sex workers program needs to be determined, DKT can refer sex workers for clinical services to the program, while the other can reduce the distribution of free condoms among its targets. / In conclusion DFID’s support is making a major contribution to the supply of sexual and reproductive health commodities in Ethiopia. DKT continues to be a strategic partner in achieving our goals. It is the number one supplier of SRH commodities for the private sector and NGOs in Ethiopia and still remains an important back stopper for the public sector DKT’s transparency, commitment, and alignment with the government’s priority SRH goals is evidence of its success.

8. Review Process
The Annual Review was informed by independent reviewers (Dr Mengistu HaileMariam, Dr. Takele Geresu and Astede Beyene) from August 26 to Sept 25,2013th. The review team used a mix of methods and triangulation of in-depth interviews, observed site level implementations and reviewed key program documents and relevant literature. / In-depth interviews were conducted with the donors, NGOs working on SRH (FGAE, Youth Associations) relevant Federal and Regional government representatives of FMOH and Federal HIV & AIDS Prevention & Control Office, DKT central and regional staffs at levels. / Progress review in implementation of the project during the year was informed by examination of relevant documents including the proposal submitted, two semi-annual reports (covering June/12- July/13), the project log frame and FY2012 Annual review report. Quest # 3909879 and 4202372 / Site visits were conducted to two project sites in East Shoa Oromia, North Shoa Amhara and Addis Ababa. The field observation included a visit to market town community mobilization activities, sex workers, youth centres and University programs.

Annex: 1 Detailed SRH commodities distribution data and CYP

ITEMS		Oct12-Sep13 Sales	Sales - CYP	Sales v Target
Male Condoms	Pieces	71,141,088	592,842	136%
Female Condoms	Pieces	5,494	46	11%
Oral Contraceptives	Cycles	3,787,629	252,509	112%
Injectable Contraceptives	Vials	2,758,358	689,590	161%
IUDs	Devices	326,964	1,569,427	337%
Implant Contraceptives	Packs	151,804	485,773	158%
Emergency Contraceptives	Packs	1,874,711	93,736	162%
Misoprostol	Tablets	498,336	NA	114%
Medical Abortion Drugs	Packs	193,860	NA	159%
MVA Kits	Kits	7,919	NA	208%
Cannulae for MVA Kits	Pieces	16,609	NA	126%
Lubricant	Sachets	69,690	NA	66%
ORS	Sachets	3,172,456	NA	162%
Totals			3,683,922	191%