## Sheet1
SARPAM | Southern African Regional Programme on Access to Medicines & Diagnostics
IMPACT | Impact Indicator 1 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014) | Assumptions
Increased access to high-quality affordable essential medicines in Southern Africa (Links to MDG Goal 8, Target E8) | Reduction in average days out of stock of 10 essential medicines in central medical stores (CMS) in Member States of the Southern African Development Community (SADC). (List of Selected Medicines based on SADC priorities: TB, Malaria, HIV, diabetes, Women and Child Health: Amoxycillin 500mg; artemeter & lumefantrine: 20+120mg; ceftriaxone 250mg pwd for injection; glibenclamide 5mg tablet; medroxyprogesterone acetate 150mg/ml; .oxcytocin 10IU/ml injection; paracetamol 120mg/5ml; susp; rifampicin/isoniazid: 150 + 75mg table; zidovudine/ 300mgl/amuvudine: 150mg tablet; zinc 20mg dtablet) | Planned | 59 days, on average, per 12 month period out of stock in CMSs across 6 Member States | 40 days per 12 month period out of stock in 6 SADC Member States CMSs | 30 days per 12 month period out of stock in 8 Member States CMSs | 20 days per 12 month period out of stock in 9 - 12 Member States CMSs. | Adequate resources at CMS to monitor out of stock situations; Member States are purchasing their own medicines, not donor funded. Member States have adopted the policy for prevention of malaria in pregnancy.
Achieved
Source
InfoHub - through Member States (MSs) reports; SADC Information sharing platform.
| Impact Indicator 2 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| Average availablity of intermittent presumptive treatment, Sulphurdoxine/pyrimethamine (SP), for malaria during pregnancy in Eliminate Malaria (E8) countries. (Countries are: Angola, Botswana, Mozambique, Namibia, South Africa, Swaziland, Zambia and Zimbabwe. | Planned | No baseline | 4 E8 SADC Member States reporting on 100% availability of SP in CMS | 6 E8 SADC Member States reporting on 100% availability of SP in CMS | All E8 Countries have SP available in CMS.
Achieved
Source
E8 country reports in collaboration with SADC Malaria Programme and the Southern African Malaria Network (SARN)
OUTCOME | Outcome Indicator 1 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014) | Assumptions
Improved efficiency and competitive market for essential medicines in the SADC region to meet the health needs of poor people | Ratio of CMS prices (public sector) of selected essential medicines for maternal and reproductive health in SADC Countries against international standards (Measured as the ratio of the local (CMS) price of each medicine against the MSH Global Pricing Index reference price. Medicines include: oxytocin 10IU/ml injection; Ferrous sulfate/folic acid 200 - 0.4mg tablet; magnesium sulphate 500mg/ml injection; medroxyprogesteron acetate 150mg/ml injection; levonorgestrel 0.75 mg tablet) | Planned | Median public sector procurement prices as a ratio of median supplier prices of 2.3 for the lowest-price generic medicines for maternal and reproductive health. | Median public sector procurement prices as a ratio of median supplier prices lower than 2.2 for the lowest-price generic medicines for maternal and reproductive health. | Median public sector procurement prices as a ratio of median supplier prices lower than 1.5 for the lowest-price generic medicines for maternal and reproductive health. | Median public sector procurement prices as a ratio of median supplier prices lower than 1 for the lowest-price generic medicines for maternal and reproductive health. | Other donors/ICPs deliver development assistance (funding and TA) as committed, in a timely fashion, to support areas of the business plan not supported by DFID. Other areas of ICP programming complement this. Civil Society has the resources and opportunities to engage with the SADC Pharma programme and to support implementation of the business plan. Member States continue to support objectives of SADC business plan and operational plan. Broader SADC Regional Development and Integration strategies and plans are effectively implemented, with Pharmaceuticals considered a priority programme area. Human Resources and capacity within the SADC Sec and Member States are developed and available to implement the Pharmaceutical Business Plan (PBP).
Achieved
Source
Baseline from 2010 SADC Pharmaceutical Market Analysis Study; SADC MS Reports; InfoHub
| Outcome Indicator 2 |  | Baseline (2010/11) | Milestone 1 (Nov 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| Level of transparency in procurement processes by publishing awarded tenders | Planned | N/A | Baseline = 1) Establishing public dissemination of most recently awarded tenders. | 4 - 6 SADC countries publish tenders awarded | 8 and more SADC countries publish tenders awarded
Achieved
Source
SADC Member States Reports; InfoHub (medicines.sadc,int)
INPUTS (£) | DFID (£) |  | COST SHARE (£) | LEVERAGE (£) | Total (£) | DFID SHARE (%)
| £10.4 million (Excludes Inception Phase investment) |  | Private Investors (though Impact Fund) £3.2m SADC Secretariat: Staff time; Office facilities (£50,000) ADB Infectious Diseases Project: Est. £2m AMRHI - World Bank Trust Fund £5m | UNIDO Technical Support for Local Manufacturing. (Staff placement); UNDP technical support to trade/TRIPS components of BP (TA and £TBA); WHO support through routine assessments and technical assistance (Geneva and AFRO); Global Access to Medicines Research Network research grants (£TBC) | DFID: £ 10.5 m Cost-Share: £10.25 m = £20.75 m (ESTIMATED) | ~ 50%
INPUTS (HR) | DFID (FTEs) |  | Note: Leverage contributes towards the overall aim of the programme objectives but not directly to SARPAM
5% Governance Adviser; 25% Health Adviser; 20% Programme Manager; Some limited engagement by country office staff in SADC MS
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014) | Assumption
Regional cooperation for medicines regulation and procurement | Number of SADC Member States participating with the pooled procurement information-sharing on prices, availability and suppliers of selected medicines | Planned | No Member States sharing information on the prices, availability and suppliers of seelcted medicines (mechanism not yet established). | 3 Member States informally sharing information on prices, availability and suppliers of selected medicines in preparartion for implementation of the pooled procurement mechanism (information sharing methodology being pilotted). | 6 Member States formally sharing information on prices, availability and suppliers of selected medicines as part of the pooled procurement mechanism. | 10 or more Member States formally sharing information on prices, availability and suppliers of selected medicines as part of the pooled procurement mechanism. | Adequate funding available to implement the plan; Member States commitment to share information. Staffing remains stable & available at the SADC Secretariat. Political support and legislation conducive
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
10% |  |  | Reports of the Pooled Procurement Agency to be established; InfoHub: medicines.sadc.int, Monitoring Reports submitted by SADC Member States |  |  |  | MEDIUM, Member States are willing to share lessons learnt.
| Output Indicator 1.2 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| Number and types of case studies documenting lessons learnt from information exchange and work sharing as part of the SADC Pharmaceutical Programme |  | no case studies exist | one case study (Botswana) demonstrating savings at CMS from informal sharing of information on prices of selected medicines. | 3 success stories of expertise exchanged amongts MSs. | 9 success stories of expertise exchanged amongst Member states.
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
5% | [6 empty] | MEDIUM, Member States are willing to share lessons learnt.
| Output Indicator 1.3 |  | Baseline (2010/11) | Milestone 1 (Nov 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| Common Technical Document (CTD) format for submission of applications for registration of medicinesfor use by SADC Regulators adopted | Planned | N/A | desk review of CTDs completed and commented on by all SADC Regulators | Draft CTD format reviewed and commented on by all SADC Regulators | Agreed CTD format adopted for use by all SADC Regulators.
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
10% |  |  | Regulatory forum meeting records; SADC Health Ministers Records |  |  |  | MEDIUM, Political commitment to use a common technical dossiers format for the registration of medicines, nationally.
| Output Indicator 1.4 |  | Baseline (2010/11) | Milestone 1 (Sep 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| SADC member states have incorporated maximum public health flexibilities in their national IP and patent legislation | Planned | 2007 status report of SADC MSs legislation | Updated status report of use of TRIPs flexibilities in national legislation | 3 SADC Countries reviewed and submitted recommendations for revision of national legislation to relevant national committees | 6 member states have started the process of revising their national IP/patent legislation, and 2 member states have sent an amendment bill to Parliament
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
5% |  |  | InfoHub; Monitoring Reports submitted by SADC Member States, National Portfolio Committee Minutes |  |  |  | HIGH, National will and technical capacity to under the legislative review processes
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014) | Assumptions
Institutional architecture and partnerships to improve access to medicines in the SADC region strengthened and functional | Level of performance of the SADC Secretariat to deliver the Pharmaceutical Programme | Planned | Member States and Civil Society have endorsed the SADC Pharmaceutical Business Plan (PBP) implementation and M&E plans. A multi-stakeholder programme governance mechanism has been approved by SADC Ministers of Health to oversee its execution. | Approved results based monitoring system established by the SADC Secretariat. (2012 -2013) | SADC Sec updates and revises implementation plan for the SADC Pharmaceutical Programme, including end of SADC PBP review | Updated SADC Strategy or business plan approved by SADC member states. | SADC Sec playing a co-ordinating role. Stable staffing & political support for the programme within the SADC Secretariat. Stakeholder/Partner capacity & funding available for their engagement. Member State governments show interest, have capacity & resources to contribute towards implementing the PBP. UN Agencies formally participate in new partnership activities. Good accountability amongst partners to deliver on their commitments. Sustained role or mandate of the SADC Secretariat in health (resulting from a review of the current RISDP). Member State governments or the SADC Secretariat support involvement of Civil Society in SADC structures and programmes. Funding available to support and sustain the work of Civil Society Organisations (CSOs) and Faith Based Organisations (FBOs). Formal CS representation possible through CS capacity, availability & agreement on who should represent.
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
20% |  |  | SADC Secretariat progress reports; MS reports / expressed views; Record of Pharmaceutical Advisory Committee Meetings; DFID Annual Programme Reviews; SADC PBP Mid-term Evaluation; Stakeholder Opinion Surveys; Records of SADC Health Ministers meetings. |  |  |  | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014) | Assumptions
Reliable evidence and transparent pharmaceutical market intelligence informing policies and decisions on access to medicines identified and available | Southern African Access to Medicines InfoHub Services Usage Statistics (Based on logged usage of: Registered Users Database; InfoHub Helpdesk, recorded in an Issue Management System; Data submissions by users into InfoHub Mobile Medicines Database Applications; InfoHub Website Statistics) | Planned | Very limited usage and not logged - mostly internal to the programme | Statistics on logged usage of InfoHub Services collected and reported as a Baseline. | At least 100% growth in logged usage of the InfoHub Services from the Baseline | At least 500% growth in logged usage of the InfoHub Services from the Baseline | Multi-stakeholder support for transparency and willingness of information providers to share information. Improved quality of pharmaceutical information collected through country systems. Skills for collecting and using information & improving ICT infrastructure in SADC Member States. Increasing uptake & willingness to use of information to inform decisions. Economies of scale in acquiring information. Research capacity in a number of SADC Member States & research funding opportunities. Timeframe is adequate for influencing policy through research. Capacity and membership of Civil Society networks to implement new interventions in some SADC countries
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
5% |  |  | InfoHub logged usage dashboard reports derived from application monitoring (independently verified by external reviewers); SADC regional conference presentations; Online / Mobile opinion polls of InfoHub Service users; DFID Annual Reviews |  |  |  | LOW
| Output Indicator 3.2 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| Southern African Access to Medicines InfoHub Services Usage Statistics (Based on logged usage of: Registered Users Database; InfoHub Helpdesk, recorded in an Issue Management System; Data submissions by users into InfoHub Mobile Medicines Database Applications; InfoHub Website Statistics) | Planned | Very limited usage and not logged - mostly internal to the programme | Fully functioning InfoHub services in place, with open access databases, links to global datasets, access to information services and a mobile interface | At least 10 SADC Member States, with logged use of InfoHub information services and mobile data submission at least once per quarter | All 14 Member States, with logged use of InfoHub information services and mobile data submission at least once per quarter
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
5% |  |  | InfoHub Database Reports; Civil Society Grant Recipient Monitoring Reports; DFID Annual Programme Reviews; Regional Conference Presentations and Poster Reports |  |  |  | LOW
| Output Indicator 3.3 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014)
| Evidence that Civil Society is influencing pharmaceutical policies and decisions relating to access to medicines in SADC countries documented and shared (Case Study: an annual summary report of campaign, advocacy and lobbying based interventions that clearly shows documented evidence that civil society is influencing pharmaceutical policies and decisions relating to access to medicines in SADC countries) | Planned | No formal documentation of CS influence in SADC Countries (Although CS has collected Pharmaceutical Market information through formal surveys and innovative campaigns. However, this includes few SADC countries & the information is not being used systematically) | At least one documented case study of how CS has influenced policies and decisions within SADC countries | At least three documented case studies of influenced policies and decisions within different SADC countries over the preceding 12 months | At least six documented case studies of influenced policies and decisions within different SADC countries over the preceding 12 months
Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
15% |  |  | InfoHub Database Reports; Civil Society Grant Recipient Monitoring Reports; DFID Annual Programme Reviews; Regional Conference Presentations and Poster Reports |  |  |  | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2010/11) | Milestone 1 (Mid 2012) | Milestone 2 (Mid 2013) | Target (end 2014) | Assumptions
Pharmaceutical market innovations to improve access to medicines identified through private sector engagement and investments made to initiate and scale these up within the region | A Social Impact Investment Fund operational to provide debt financing for scaling up private sector organisations that have the potential to increase access to medicines in Southern Africa | Planned | Draft proposal in place to establish a Social Impact Investment Fund to improve access to medicines | Social Impact Investment Fund operational | Demonstrable evidence of progress of pledged potential investment of more than £ 2 million into a Social Impact Investment Fund within SARPAM timelines. | Social Impact Investment Fund is operational with more than £ 3 million assets under management and providing debt financing for scaling up private sector organisations to increase access to medicines in Southern Africa. | Legal and financial regulations and procedures conducive to the establishment and operation of an impact investment fund. Sufficient investment into the Social Impact Investment Fund. Sufficient quality investment opportunities available in the region to invest into. Investment opportunities want debt financing. Investment opportunities accept loan conditions. No major political or economic instability or volatility. No or very low default rate on the portfolio, or no/low credit risk. Social Impact investment fund is adequately managed. Supported by DFID and SARPAM.
| An Impact Investment Fund is an investment vehicle which seeks to achieve both financial return and social impact. | Achieved
IMPACT WEIGHTING (%) |  |  | Source |  |  |  | RISK RATING
25% |  |  | Quarterly fund fact sheets and annual reports (including audited financials) |  |  |  | HIGH
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)