Pre- Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Family Planning Outreach Programme Phase II, Tanzania
Programme Value: £22,030,000		Review Date: January/February 2015 / (Due 11 March 2015)
Programme Code: 204266	Start Date: November 2014	End Date: December 2018

Summary of Programme Performance
Year	2015
Programme Score	A
Risk Rating	medium

Summary of progress and lessons learnt since last review:
This is the first year of the programme since approval, with the target for contracting two suppliers reached. The programme was tendered in two lots under the Framework Agreement to ensure competition and stimulate innovation. Since there was only one bidder for each lot, the process moved to a negotiated agreement, which allowed for influences on the design and value for money considerations. Marie Stopes International (MSI) and Population Services International (PSI) have been contracted to run 20 and 10 teams respectively to scale-up family planning services with comprehensive post-abortion care (CPAC) and Gender-Based Violence (GBV) services nationwide. This process has been successful in ensuring that another model of service delivery is being rolled out, which has the potential to be more sustainable, and there is the ability to compare between the two models. Both PSI and MSI have started service delivery in January and February respectively; therefore there was not enough project data to analyse at this stage.

Multi-lot tenders provide the opportunity for innovation and comparison: The split tender allowed DFID to obtain bids with very different models, with the entry of a new IP providing a riskier (in terms of something not thought of by DFID), but potentially more sustainable model. This has provided the opportunity to have a joint inception review, to ensure that monitoring parameters are the same to enable comparison between models. Already, this competition has meant that MSI have reviewed their training model to support capacity building of the public sector after PSI shared that they provide intensive supportive supervision.

Milestone-based contracts are challenging for IPs (Implementing Partners) and DFID in-country to understand and manage: While both contracts have now been signed, MSI have asked to re-negotiate the contract to a hybrid fee and reimbursable contract instead of a fully milestone based contract to comply with DFID’s requirement for financial reports. This negotiation process is currently ongoing. MSI were uncomfortable with sharing the financial reports with a fully milestone based contract in case DFID would seek to renegotiate the milestone payments at the contract breakpoints in case the profit margins were seen to be too high. Without this information, it would be difficult for DFID to assess value for money and compare between different models, as part of the learning agenda in family planning globally and within Tanzania. In addition, it was challenging to agree on meaningful milestones that did not encourage coercion or targeting of easy to reach beneficiaries. The milestones have ended up being a compromise between what are seen as tangible deliverables versus what the programme is really trying to achieve; in due course we will monitor to what extent the milestones been appropriate.

Keep dialogue open and ensure IP’s understand the importance of timely communication, as well as DFID coordinating with other donors: PSI has a change in circumstance during the contract negotiation which was not shared in time for DFID to make strategic decisions. DFID were put under pressure to ensure the contract was signed in September 2014, to ensure continuity in funding eight existing teams which were no longer going to be funded by the Dutch (who were withdrawing form the country) and KfW. This changed with KfW-centrally extending support meaning that PSI would have to form ten new teams to stick to their commitments with DFID. DFID were uncomfortable with PSI’s absorptive capacity and ability to scale-up to an additional ten teams with a new model, therefore it was agreed that only four teams would be supported in year one to enable PSI to learn how to implement the new model before scaling up in year two subject to review. It was also agreed that the teams would work in different regions. This change led to the contract being signed in January 2015. If DFID has shared plans with other donors more widely and discussed the new project with existing funders, coordination may have been smoother.

Need for Government leadership and in mapping and coordination of IP’s: During the contracting phase, it was challenging to understand where all the different IP’s are working. Interest in FP has increased, with a number of implementing agencies working in different regions, albeit not at scale. DFID have negotiated with PSI and MSI to cover different regions through this project to minimise risk of duplication and to ensure that there is adequate coverage from the programme support. The technical working group for family planning outreach should be doing this, with MST being the secretariat, there seems to be no ownership of the mapping exercise and sharing of information is poor. Engender, another agency have also mapped activity but there is an ongoing risk of different implementing agencies rotating through the same facilities within a month of the last outreach, resulting in lack of consistent supervision and support in those facilities, whilst others remain unserved. This needs to be addressed by co-ordinated action by government, donors and the implementing partners

Commodities: Last year, there were considerable issues of stock-outs with commodities within the public sector. This resulted in IP’s sorting out their back-up supplies on an ad-hoc basis, which meant that data to support quantification is lacking, which further hinders strengthening of the system. UNFPA (with central DFID support) has played a key role in procuring and storing commodities, which MSI drew significantly from. This year, through DFID in-country support, UNFPA will be using DKT (through four warehouses) to store and track commodities to ensure systematic and appropriate use of a strategic reserve of commodities by the IP’s. Although this was seen as a pragmatic solution, there have been concerns raised by MSI that this mechanism could cost them more than the original mechanism. DFID has learnt that further consultation on this delivery mechanism may have raised this issue earlier, and an appropriate mechanism with all stakeholders on-board designed. This may have been a challenge in itself due to the short timeframe from the release of the quantification results to the cut off time for ordering commodities to ensure that there was continuity in supply.

Inconsistencies in approaches: while DFID encourages and actively seeks for IP’s to do things differently, the review identified that areas such as training, supervision, reporting, monitoring and commodities management need to be consistent to ensure strengthening of the public system. For example, MSI’s model lacks the supervision needed to accredit trained providers by the Government (even though it is a great opportunity for government staff to gain practical expertise for accreditation and maintaining skills). Monitoring indicators also varied in terms of definitions such as new users of modern family planning methods. Furthermore, each IP had different mechanisms for obtaining back-up commodities which were not reflected in any monitoring system making it difficult to use public records to give an accurate picture of actual use of commodities resulting in difficulties in forecasting with outreach and usual family planning activities. The inception review has supported clarifying on issues and was commended by IP’s to be a very useful way to start a programme with multiple delivery partners.

Summary of recommendations for the next year:

Compare the models. Phase I had only one partner with one family planning outreach model. Phase II offers a chance for two IPs to deliver slightly different outreach models and for DFID to be able to compare their strengths and weaknesses, including how much each model costs. In addition, competition between MSI and PSI internationally--as well as in Tanzania--is keen and spurring improvements in each other may be a key product of this programme. DFID has less experience working with PSI on FP outreach and will be seeking to understand the alternative model and its advantages and disadvantages. In addition, PSI is working with other partners—Intrahealth (GBV) and Restless Development (youth).

Mapping. DFID needs to push the technical working group for family planning outreach, especially through MST, (the secretariat), to ensure that this is completed as soon as possible to ensure good coordination and coverage. There appears to be confusion as to where the responsibility lies for this and some work is being led by Engender Health.

Family Planning Donors group: This informal group needs to continue to meet on a regular basis to ensure coordination between donors, which is also linked to issues around FP commodities security.

Commodities security: DFID to ensure effective coordination with USAID and UNFPA to ensure commodities procurement and distribution mechanisms adapt according to need, and that IP’s support strengthening of the public system only pulling on the strategic reserve when absolutely necessary. IP’s need to ensure that the monitoring forms are completed to aid analysis for further quantification and planning for the public system to work.

Training (continued). There are a number of outstanding issues to make public sector provider training consistent and measurable:

GOT Certification. Progress has been made in recognizing GOT FP training requirements (GOT training curriculum, GOT-approved trainers & GOT supervision. IP’s to liaise with Government to ensure Government provide certificates to trainees who have successfully undergone the full training and supervision.

Trainee Supervision. The MST model (passing through many facilities) does not make regular supervision opportunities possible. How MST will supervise their trainees remains a question, and MST need to come up with a response to this to ensure that trainees can become accredited.

Not qualifying trainees who are unready. The IPs are responsible to produce certain numbers of trainees but it is important that unqualified trainees are not approved when they are not ready. The way around this is for the IPs to train roughly 120% of their final numbers, allowing a certain number of trainees to not qualify, if necessary.

Refresher training and how to quantify. The USAID Senior FP Advisor mentioned how useful the refresher training is that MST gives to some of the public sector healthcare providers with whom they work. This is behaviour that DFID wants to encourage— DFID needs to review how to ensure MST continues to carry this work out and receives recognition for it.

Pre- and Post-Training Tracker. The Training Tracker is a system whereby those public sector healthcare workers who have been trained in family planning are tracked. Each worker has a unique number so that repeat training is discouraged. MSI and PSI should check that a potential trainee has not already received this training (pre-) and then enter the names and details of all the people they have trained in family planning (post-). The Training Tracker is currently hosted by CHAI and was funded by USAID.

Youth. Assess the different models being tested by the IP’s to see which is/which combinations are better at reaching youth. Both PSI and MSI should collect the relevant data including qualitative data to share during quarterly reviews as well as the annual reviews.

Gender-based Violence (GBV). This is new work in Tanzania and it helps that the GOT has recently come out in support of reducing GBV. GBV services are the most unpredictable of the services offered by this programme as the demand for these services is extremely hard to estimate. As this GBV work is new to these providers (and to DFID) and the demand is so difficult to predict, these indicators will be the most experimental in this programme’s logframe. Of all the figures in the logframe, these milestones are most likely to change as the IPs gain more experience in the demand for GBV services.

Comprehensive Post Abortion Care (CPAC). This is newly added service to Phase II and IP’s need to learn more about how to strengthen it. This includes supporting maintenance of and resupply of equipment, and supporting in planning for health facilities to have both a trained provider and equipment to ensure services can actually be offered.

Monitoring: adjustments have been made to the logframe including clarity on indicator definitions and means of verification. Recommendations on exit surveys to ensure that sample sizes for indicators need to be actioned by IP’s.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4420192
DevTracker Link to Log frame:	4893523

Outline of the programme

DFID Tanzania is implementing Phase II of a Family Planning outreach programme over 4 years (2014-2018) to continue to increase family planning use in Tanzania. The outcome of the programme will be to increase women's use of family planning and availability of comprehensive post abortion care (CPAC) services across Tanzania. The impact will be to reduce maternal mortality and improve women's lives by giving them control over their family formation.

Phase I, had one supplier, Marie Stopes Tanzania, delivering family planning outreach services only, nationwide over 3.5 years. Funds were channelled through USAID to provide programme management and technical expertise. In this new phase, CPAC and GBV are additional services, with an increased focus on youth as well as capacity building of public providers are different. Two suppliers – MSI and Population Services International (PSI) have been contracted to provide services, in the interest of sustaining a competitive market and fostering innovation and challenge. MSI will deliver services through twenty teams, and PSI through four teams in year one with a view to scaling up to ten teams in year two based on performance. Both providers are expected to mobilise rapidly at scale, i.e. 70% of teams to be fully operational within four months increasing to 90% of teams fully operational within 6 months. Implementation will be in close collaboration with the Government of Tanzania authorities both at the national and district level.

The programme has specifically set out to increase women's use of comprehensive family planning and availability of comprehensive post abortion care (CPAC) and GBV services across Tanzania. Specific outputs were stipulated in the original log frame as follows:
- Private sector family planning outreach services to rural areas (particularly long-acting and permanent methods-LAPM) in consultation with Government public sector services;
- Strengthened national comprehensive post abortion care (CPAC) in both public and private sectors (including policy work);
- GoURT supported to strengthen its family planning programme, including training of public sector providers in LAPM;
- Young people (<20) reached with family planning and CPAC; and
- Integrated RH services for women who are victims of violence (GBV) work in the public or private sectors.

Contextual issues remain the same as in the business case however there has been increasing focus on family planning with other providers such as Engender Health scaling up services. The sharpened One Plan (to accelerate reduction in maternal and newborn deaths) has increasing access to family planning services as one pillar of a three-pronged strategy to reach the MDG’s 4 and 5.

Addressing youth remains a challenge and this programme will ensure that this underserved group are able to access services. This will be an area requiring a lot of testing and learning, ensuring that youth preferences are taken into account in designing accessible family planning services for them.

MSI and PSI were contracted in December and January respectively after a prolonged negotiation process, specifically relating to milestone based payments. MSI were able to continue services from 1st December and retain staff when phase I ended on 30th November. PSI had news during the contracting process from KfW that they will also support eight existing outreach teams which DFID had thought they would be taking over funding of as it was thought that there was no continuity of funding. DFID was therefore concerned that PSI may not have the absorptive capacity to scale up so quickly, and it was agreed that they would start with four new teams for year one, using their new model, which would be assessed by DFID to ensure that they can scale up to the full complement of 10 teams by year two.

Description of each model:

MST’s outreach model involves 20 four-person outreach teams ‘snaking’ through the countryside to continually different public sector health facilities, including dispensaries. Teams include a MoHSW AMO - Assistant Medical Officer and a MoHSW nurse. MST reached over 3000 health facilities in Phase I of the programme, returning to each facility only about every five to six months. DFID has considerable experience with this MST model with its strengths and weaknesses.

PSI’s outreach model is a hub and spoke model and more static than the model of MST. PSI is beginning with only four teams in the first year, increasing to 10 teams in the subsequent years of the programme. Teams include a MoHSW nurse.

Each model has its strengths and weaknesses as shown in the following table.

Strengths and Weakness of the MST and PSI models
	Strengths	Weaknesses
MST model	Full method mix including sterilization / Reaches large numbers of women with unmet need / Reaches many facilities / One organization means better coordination / Able to refresh the training of public sector workers / Incorporates public sector healthcare providers on its outreach teams / Twice the in-team mentoring of MoHSW staff as the PSI model	Less time at facilities leaves less time to build sustainability / Difficult to supervise trained workers / Only able to refer to public sector facilities / Harder to follow up post- operative problems, if any / Not suitable for CPAC / Greater danger of exhaustion of facility commodities, if District Pharmacist does not receive notice of visits and acts to allow appropriate stock accumulation
PSI model	In-depth work in fewer facilities / Better training supervision / Additional partners for new work brings new ideas (CPAC & youth) / Able to refer to its own strengthened services / Leaves sustainable and well trained public sector providers and facilities when leaves	Does not include sterilization in outreach services / Reaches fewer facilities / Reaches fewer women / Model yet unproven
Both	Have a misoprostol product / Offer training in FP to public sector providers / Strong relationships with GOT

The reviewers conducted this inception review as part of the annual review process to ensure that the monitoring parameters were set-up so that at the six month breakpoint and annual reviews, DFID are able to assess and compare the models including costings. The review was done with only two weeks of MSI implementing Phase II. Therefore the narrative in the annual review template below is not an assessment against milestone indicators, as nothing is expected to be achieved apart from contracting and planning, but provides clarification on the indicators, required adjustments, definitions and means of verification as we go forward with the quarterly, breakpoint (at six-months of implementation if things are not working) and annual reviews.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Achievement has been as planned. Contracting of two service providers to deliver family planning outreach services through 20 teams and 10 teams (four in year one) each completed. However, there is some re-negotiation by MSI on the type of contract with PCD to convert it into a fees and reimbursable contract instead of a fully milestone based one. Further explanations are in the commercial section below.

Outcome indicator 1: Couple years of protection (CYPs) delivered by the project.

Nothing to report as implementation has only just started (as planned)

Outcome indicator 2: Proportion of clients who are first time users of modern family planning (FP).

Definition is the same for both partners (MST & PSI). The definition is that the client has ‘never used modern contraception’ and the answer is derived from two questions in the MST exit surveys (and PSI will use the same two questions). In addition, PSI and MST will collect the data from public sector family planning books where ‘new users’ is already a tick box. These two ways of collecting the data will be a check on the other method of collecting this. MST will carry out 800 exit interviews per year and PSI will carry out 500.

The evaluation team have calculated these numbers and they are in the logframe.

Overall output score and description: A

Key lessons

See summary	above

Key actions

See summary above.

Has the logframe been updated since the last review? Yes, the logframe has been updated since the business case design to take into account the tender process.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	FAMILY PLANNING: Private sector family planning outreach services to rural areas (particularly LAPM) in consultation with GOT public sector services
Output number per LF		1	Output Score
Risk:		Low/Medium	Impact weighting (%):	50%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
1.1Number of FP services delivered by the project (long & short term methods/ disaggregated by age)
1.2 Proportion of clients classified as poor
1.3 Cost per CYP (efficiency)
1.4 Client satisfaction with service they received

Key Points

The service contract between MSI and DFID was in place for 1st December 2014, allowing continuity in service delivery and transfer of assets from Phase I (approved by USAID). However, this contract is being re-negotiated as explained below. PSI’s contract was finalised in January allowing for service delivery to start with four teams in February. The two suppliers have about two months difference in starting implementation with PSI also have a smaller number of teams in the first year. The objectives of the tender were met in terms of stimulating innovation in outreach services with PSI’s model being very different. Further details in the commercial section below.

There has been little/no implementation as expected.

The following issues arose with the logframe and the following changes were made:

1.1 MST cannot count clients yet so both partners will report on ‘services’. PSI will adapt their numbers to accommodate this so that the numbers will be comparable. PSI can report on both ‘clients’ and ‘services’. MST will be able to report on ‘clients’ by the end of this programme but it will be necessary to use ‘services’ for this programme for consistency across years and between IPs.

1.2 The source for this will be exit surveys. It was agreed to standardise the exit survey questions on MST’s questionnaire. PSI will adapt the same questions for theirs.

1.3 Costs per CYP. This will be measured without support costs and will include full sector commodity cost (as well as an estimate of MOH cost).

1.4 Client satisfaction. Beneficiary feedback is seen as an important proxy for quality.

Summary of responses to issues raised in previous annual reviews (where relevant)

This is the first review.

Recommendations

Number of exit surveys: MST regularly carries out exit surveys and PSI can also do it. MST proposed carrying out 400, an inadequate number to look at sub-categories such as age. It has now been agreed that there will be 850 exit surveys by MST and at least 500 surveys by PSI, subject to availability of budget.

Output Title	CPAC: Strengthened national comprehensive post abortion care (CPAC) in both public and private sector (including policy work)
Output number per LF		2	Output Score
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
2.1 Number of facilities (public & private clinics) equipped and supplied to deliver CPAC
2.2 Number of public and private health workers trained and certified in CPAC using MVA (80% of these will be public sector providers and will include government certification)
2.3 Number of women accessing CPAC (through this programme of support)

Key Points
As output 1.

2.1 No change. PSI knows source of data. MST has yet to provide source details. Training is done up front with no training in last year.

2.2 MST wants to have this indicator to be looser [+ or – 20%]. This is to ensure that trainees who are not ready are not counted. MST and PSI know they need to train 120% in order to achieve final numbers of certified trainees.

2.3 No change. MST number from proposal logframe; PSI’s number from their proposal.

Summary of responses to issues raised in previous annual reviews (where relevant)

This is the first review

Recommendations

Increase training to 120% of target to take into account those that do not become certified.

Output Title	TRAINING: GOT supported to strengthen its family planning programme including training of public sector providers
Output number per LF		3	Output Score
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
3.1 Number of GoURT health providers trained in LAPM/LARCs and government certified (with supervision in line with Government guidelines)
3.2 Total number of women assessing FP services in public facilities (derived from an aggregation of district data)
3.3 Average QTA score for project teams
3.4 All clinical incidents properly investigated and clearly communicated to Government.

Key Points

As output 1

3.1 MST provides training for full menu of contraceptive methods including sterilisation. PSI provides training for all methods but sterilisation. MSI have proposed a supervision plan and DFID are in agreement. PSI is able to supervise their new trainees easily for three months. We have told IPs to train 120% of the trainee numbers they need.

3.2 We will use DHS 2015 for the baseline for this. (NOTE: We would not have data until 2016.)

3.3 Quality indicator is slightly different between both IP’s but we will track according to their parameters and systems

3.4 This has arisen following learning from the last phase. While these are expected to be a rare event, IP’s are expected to respond quickly and appropriately.

NOTE: We agreed with the IPs that the weight of this output would be on indicator 3.1 as indicator 3.2 is beyond the IPs control.

Summary of responses to issues raised in previous annual reviews (where relevant)

This is the first review.

Recommendations

Increase training to 120% of target to take into account those that do not become certified.

Output Title	YOUTH: Young people (<20 years) reached with family planning including CPAC and GBV
Output number per LF		4	Output Score
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
4.1 Proportion of all services to clients aged under 20 through the outreach teams
4.2 Number of (private) programme staff specifically trained to work with or provide information, education or family planning services to adolescents (<20)

Key Points
As output 1.

4.1 This indicator is changed to ‘services to clients under aged 20’.

4.2 Both organisations are training 100% private sector staff i.e. project staff—no public sector staff involved. The evaluation team has asked both organisations for baseline information.

Summary of responses to issues raised in previous annual reviews (where relevant)

This is the first review.

Recommendations

Update logframe with baseline information once received.

Output Title	GBV: Integrated RH services for women who are victims of violence (GBV) in the public or private sectors
Output number per LF		5	Output Score
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
5.1 Proportion of services to clients that include GBV care
5.2 Number of public (80%) and private providers trained in GBV care and treatment
5.3 Per cent of GBV survivors referred for clinical and non-clinical services

Key Points

As output 1.

GBV services are the most unpredictable of the services offered by this programme as the demand for these services is extremely hard to estimate. The need for the services is well documented but stigma is high and reporting an abusive partner (for example) is potentially extremely dangerous. Work within communities is changing the attitudes toward GBV but those perpetuating the violence still maintain the majority of the power (and continue to misuse it). There is also likely to be a good deal of regional variation in this work—and the areas where GBV is the highest might be the last place where these services are sought. There is simply a lot we don’t yet know.

As this GBV work is new to these providers (and to DFID) and the demand is so difficult to predict, these indicators would be the most experimental in this logframe. In addition, setting the milestones is based on the proportion of women who might need these services and is, in fact, no more than good ‘guestimates’. Of all the figures in this logframe, these milestones are most likely to change as the IPs gain more experience in the demand for GVB services.

5.1 We are estimating that 4% of client services will include GBV care, based on TDHS and IntraHealth data.

5.2 Trained and certified with GOT GBV curriculum.

5.3 Referral for PSI will include hub to spoke. Referral for clinical services estimated at 2-3%; to police 45%; and 7-8% for legal aid. [These numbers based on Intrahealth July-December 2014 data.]

Summary of responses to issues raised in previous annual reviews (where relevant)

This is the first review. See above.

Recommendations

Ensure learn from implementing the GBV programme.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The costing data used for this report is based mainly upon the budgets and planned activities of the two IPs – MST and PSI – itself based on several years of experience of this activity within Tanzania on the part of both organisations.

However, this report is interested in costs incurred not only by the two IPs, but also by other stakeholders in the course of the IPs’ outreach activities. So estimates have been made of the cost of the FP commodities used (procurement, warehousing and distribution), though this will mainly be covered by MoHSW, DFID, USAID or other donors. Also, estimates have been made of the value of the time provided by the MoHSW staff involved in the outreach teams. The IPs pay these staff a per diem, but take no account of the effect of these staff being taken away from Tanzania’s public health system – something which may be approximated by their salary levels.

In order to create a level playing field, costing data needs to be collected from the two IPs in the following categories:

	Cost category	Description
1	Own labour costs	Salaries and per diems for IP operational staff
2	Transport costs	Fuel and maintenance for vehicles
3	MoHSW costs	Per diems for MoHSW staff, and person-day data for application of salary cost
4	Commodity costs	Service delivery data for application of commodity procurement, storage and distribution costs
5	Support costs	Estimates of support provided by both local and international offices of the IPs
6	Other costs	Any other costs related to the FP outreach

MoHSW salaries used are those relating to staff with two years of seniority. Commodity cost estimates are not subject to price increases over the life of the project. The costs of training are excluded from this analysis as they are largely determined by the MoHSW, which decides on training duration, curriculum and trainers. Once the programme is complete, estimates will be made of the residual value of major assets such as vehicles, rather than assuming all will have been fully amortised. This residual value will be subtracted from the estimated cost of the programme.

The budget analysis clarified that the key cost drivers for the outreach programme are the labour cost of IPs and MoHSW, which between them account for more than half of the budget. Commodities account for 16% of the budget and transport costs just 4%.

Model testing: MST v PSI.

To an extent, the VfM analysis can form a part of the comparison of the two outreach models. However, it should be noted that the two models each have a range of advantages and disadvantages which will not be captured by this cost benefit analysis. At present no adjustment is made in either the logframe or the VfM analysis for the slightly different start dates of the two IPs.

# Value for Money indicators, and their ex-ante values
The following tables show key selected VfM indicators and their ex ante values – i.e. those based on budgets and plans rather than any achievements or actual costs – for each IP and the programme as a whole:
MST
	2015	2016	2017	2018	total
Effectiveness
Cost/DALY	£ 5.99	£ 5.21	£ 5.77	£ 5.61	£ 5.65
Cost/maternal death averted	£ 5,228	£ 4,548	£ 5,031	£ 4,890	£ 4,928
Cost/unwanted pregnancy averted	£ 13.30	£ 11.57	£ 12.80	£ 12.45	£ 12.54
Efficiency
Cost per CYP	£ 5.52	£ 4.80	£ 5.31	£ 5.16	£ 5.20
FP services delivered/team/year	15,054	14,399	14,399	14,399	14,563
LARCS per team/year	11,829	11,313	11,313	11,313	11,442
Economy
Cost/team/year	£ 239,052	£ 198,995	£ 220,165	£ 214,037	£ 218,062

Ratio: direct savings: cost	4.11	4.72	4.27	4.39	4.36

PSI
	2015	2016	2017	2018	total
Effectiveness
Cost/DALY	£ 15.38	£ 7.25	£ 5.40	£ 4.95	£ 6.62
Cost/maternal death averted	£ 13,417	£ 6,324	£ 4,712	£ 4,322	£ 5,779
Cost/unwanted pregnancy averted	£ 34.15	£ 16.09	£ 11.99	£ 11.00	£ 14.71
Efficiency
Cost per CYP	£ 15.36	£ 7.24	£ 5.39	£ 4.94	£ 6.61
FP services delivered/team/year	13,214	16,518	20,131	20,579	18,386
LARCS per team/year	6,607	8,259	10,066	10,289	9,193
Economy
Cost/team/year	£ 342,300	£ 197,721	£ 174,527	£ 164,484	£ 198,133

Ratio: direct savings: cost	1.60	3.40	4.56	4.97	3.72

Combined
	2015	2016	2017	2018	total
Effectiveness
Cost/DALY	£ 6.93	£ 5.75	£ 5.66	£ 5.41	£ 5.89
Cost/maternal death averted	£ 6,050	£ 5,016	£ 4,936	£ 4,718	£ 5,139
Cost/unwanted pregnancy averted	£ 15.40	£ 12.76	£ 12.56	£ 12.01	£ 13.08
Efficiency
Cost per CYP	£ 6.43	£ 5.40	£ 5.33	£ 5.10	£ 5.53
FP services delivered/team/year	14,747	15,105	16,310	16,459	15,703
LARCS per team/year	10,958	10,295	10,897	10,972	10,771
Economy
Cost/team/year	£ 256,260	£ 198,570	£ 204,952	£ 197,519	£ 212,118

Ratio: direct savings: cost	3.55	4.28	4.35	4.55	4.18

Ex ante, all indicators suggest that the programme offers good value for money. This is not unexpected, as the LAPMs provision which is at the heart of the programme is an inherently cost-effective intervention, offering many years of protection from a range of costly and unhealthy outcomes at a modest cost. Note that due to differences in how the two IPs accounted for support costs, these have been excluded from the VfM indicator levels. They amounted to 22% of total cost as recorded by the two IPs. However, even if these were added back in, the programme would remain well within the bounds of good value for money. It is hoped that the IPs will provide disaggregated data so that different regions and districts can be compared. This is because a key issue for outreach FP – how much does it cost to reach the poorest? – is very under-researched. Some aspects which could be of great interest, e.g. cost per under 20 year old FP service delivered; discontinuation rates; cost per GBV service and referral delivered, are likely to be too challenging to collect during this programme given current M&E resources. However, consultants will be appreciative of any available information in relation to these issues.

The IPs at present has no geographically disaggregated data available, but they have been asked to produce this in time for the next Annual Review. We hope to be able to address at least some equity considerations – i.e. the important question of varying cost and effectiveness across different parts of Tanzania – at this time.

VfM performance compared to the original VfM proposition in the business case

The ex-ante VfM values and those of the original Business Case are compared in the table below.
The key difference is that while forecast service delivery (and hence CYPs) is similar, the estimated health outcomes that would be associated with this have been modelled in different ways. In the Business Case, an annual impact basis was used (i.e. only those health benefits occurring during the four programme years are counted), whereas in the current analysis a longer term view is taken and the modelling is on a service lifespan basis (i.e. health outcomes resulting from the programme’s activities are included even when they occur in later years).

Note that the current VfM estimates would be 7% higher if support costs were included. They are excluded in order to place both models on an equal basis (as the IPs had different systems for estimating support cost).

Comparison of Business Case and current VfM estimates
	Business Case	Current VfM estimates
Cost/Disability-adjusted life years	10.81	5.89
Cost/Couple years of protection	5.01	5.53
Cost/unwanted pregnancy averted	24.01	13.08
Cost/maternal death averted	9,435	5,139

**Following completion of the review and analysis, the Government per diem rates have increased by 50% which will have an impact on the VFM for the programme.

Assessment of whether the programme continues to represent value for money

This is too soon to assess.

Quality of financial management

Both PSI and MSI have robust financial management systems. Since the IP’s have a number of sources of funding, some for similar activities, we have asked them to ensure open-book accounting with financial reports showing the contribution of funds for major line items. DFID will also check audit reports during the life of the programme.

Date of last narrative financial report	Due in April 2015
Date of last audited annual statement	Due in March 2016

E: RISK (½ page)

Overall risk rating: Low/Medium/High

Medium

Overview of programme risk

The business case (2013) identified a number of risks to the programme. These included issues around sensitivities relating to abortion; the challenge of measuring impact; concerns around having a lower impact as youth are more likely to use shorter term methods; GBV services may be shunned by clients and communities; and parallel service delivery could undermine systems strengthening efforts.
Since the business case, the DFID programme management team have updated the risk matrix in the delivery plan. More information can be found in the delivery plan but the following risks are issues requiring follow up.

Risk Matrix
Scale – Low (1), Medium (2), High (3)
Risk	Prob-ability	Im-pact	Mitigation
Perverse incentives to misreport	1	2	Contract is not based on CYP’s but does include number of trainings. Results audits and monitoring systems will be implemented by the contractors / Triangulate data with Government stats and consumables at the reviews.
Theft of commodities	1	3	Only trained providers can utilise the more expensive commodities
Stock outs of commodities in the Government system	3	3	Implementing an emergency procurement and strategic reserve with UNFPA through DKT in areas of high unmet need.
Lack of sustainability	2	2	Incentivise suppliers to strengthen the Government systems including on reporting, ordering commodities and clinical training of health workers. Suppliers have been asked to provide a mentorship role to public health workers to ensure that they are offering quality FP services to clients. Evidence of this will be required. Monitor district public and private data to ensure public services increasing.
Backlash by Government and CSO’s/FBO’s on CPAC	2	3	Suppliers and DFID to ensure stakeholders are clear at all levels that the CPAC services being provided are legally and ethically permissible in Tanzania and contribute to the reduction in maternal mortality.
Transition from Phase I could result in slippage in results	1	3	Transition phase carefully planned with MSI and USAID, with approvals for transfer of resources in place. Contract in place for Phase II by the end of Phase I (completed).MST have retained core staff to manage the programme.
Transparency – both suppliers have multiple donors which could result in overcharging /duplication of funding the same activities or operations.	1	2	MSI and PSI to provide open budgets and financial reports, as well as audit reports throughout the life of the programme. Review incentives on this during the inception review in Jan/Feb.
Fraud is a major risk, zero tolerance makes partners vulnerable	2	3	Conduct spot checks and remind partners of consequences of fraud on the programme. Seek reassurances regarding adherence to robust systems every quarter during the reviews. Ensure partners identify where there could be fraud and implement measures to close loopholes.

These risks need to be reviewed and revised quarterly and at the Annual Review.

Procurement / Commercial risks

9. Security, political / instability or terrorism / threats – deteriorating to / such a point that / international consultants / cannot travel to Tanzania / and project staffs’ safety is compromised	1	3	Compliance with FCO travel advice and close liaison with DFID where necessary; Security Procedure Manual to be issued to project staff and consultants working on this programme – includes a project Health and Safety Risk Assessment. PSI and MSI have their own duty of care procedures.
10. Suppliers do not deliver agreed / outputs (on time, on / budget, as agreed in ToR / with DFID)	1	3	Active quarterly monitoring and support suppliers to remove bottlenecks where relevant. Good inception review with revised, feasible targets agreed. Effective reporting mechanisms put in place will ensure that the progress of milestones will be visible to DFID and Government; Quarterly review meetings will allow for review of progress against milestones; Activity work plans agreed upon and approved by DFID on a regular basis.
11. Difficult to understand the milestone payments as not clear how they are broken down. We cannot change them according to the contract.	2	2	Suppliers need to provide financial reports with breakdowns. Inception review will also identify key cost drivers we will need to monitor.
15. Programme funds / poorly managed:	1	3	Programme staff is knowledgeable of both DFID and their own institutional systems. An annual audit (commissioned by contractors) will identify and mitigate potential problems.
DFID update required after inception review then quarterly

Outstanding actions from risk assessment

- Conduct regular quarterly meetings with partners including ad hoc meetings in between depending on the need.
- Ensure suppliers comply with their data quality assurance measures and shares report/analysis annually.
- Need to plan audit and obtain asset registers and inventories
- Plan to do one spot check per UK Financial Year.
- Procurement plan prepared by contractors needs to be reviewed

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

It was important to have a smooth transition between Phase I and Phase II to ensure continuity in services, and to ensure that operations continued with almost the same teams and staff. MSI and DFID could not afford for the investment in Phase I to be discontinued as that would have meant disbanding teams, risks of attrition before the new phase started and issues around assets such as vehicles. This would have resulted in higher transaction costs similar to starting up a completely new programme which would have delayed start-up. MSI’s implementation for Phase I was ending on 30th November. PSI also had 8 teams previously funded by the Dutch and then KfW, which were at risk due to the expected discontinuation in funding of these teams by September 2014.

The procurement process started in good time with the aim for contracting to be completed in September 2014 due to the above. It was a restricted tender process open to Framework Agreement partners only to ensure quality technical bids with partners who had already gone through a due diligence process. The tender was run in two lots to ensure greater competition, VFM and spur suppliers to be innovative. Each lot only received one bid, therefore it was permitted to move to a negotiated agreement which allowed for more open dialogue to get the projects right. This took some time, especially as the suppliers interpreted the commercial requirements of the tender as needing a fully milestone based offer. These milestones were negotiated in detail between PCD and the suppliers, particularly PSI, who were having difficulties in formulating appropriate milestones payment projections. This was mainly due to the fact that they were negotiating for funding to enable them to start-up activities and could not take so much risk. Late in the negotiation process, KfW approved funding of 8 PSI teams, which resulted in concerns regarding PSI’s absorptive capacity and ability to scale up rapidly as per the ToR’s. It was agreed that PSI would start with four new teams for year one and scale-up depending on the outcomes of the inception and annual reviews.

The service contract between MSI and DFID was in place for 1st December 2014, allowing continuity in service delivery and transfer of assets from Phase I (approved by USAID). However, this contract is being re-negotiated as explained below. PSI’s contract was finalised in January allowing for service delivery to start with four teams in February. The two suppliers have about two months difference in starting implementation with PSI also have a smaller number of teams in the first year. The objectives of the tender were met in terms of stimulating innovation in outreach services with PSI’s model being very different.

Performance of partnership (s)

The contract negotiations have been protracted due to the change in circumstances for PSI with extra funding requiring an understanding of what DFID and KfW would fund and how there would be transparency and non-duplication in resource allocation. This has been resolved by covering separate regions and open-book accounting. DFID have requested greater transparency and more timely communication of issues affecting the programme.

MST and DFID have a good partnership in-country. However, relationships and programme management competencies need to be strengthened now that there is a direct relationship instead of through USAID. The progress of the programme could be affected as MSI re-negotiate the contract to a hybrid fee and reimbursable contract due to reluctance to adhere to DFID’s requirement for financial reporting to enable due diligence and analysis of the costs involved in the model. MST do not agree with financial reporting with a fully milestone based contract as they have concerns that this could result in DFID re-negotiating the contract at the breakpoints (six months and annually) if it is seen that MST are making too much profit. MST are also concerned regarding our support to commodities through another programme delivered by UNFPA, which they argue is going to drive up the logistics costs of accessing buffer stocks of commodities should the public system fail. This is despite the fact that the commodities will be brought closer to the regions, instead of MST having to arrange and fund logistics and distribution from Europe. Therefore there is potential for fragility in this partnership which needs to be mitigated through open communication.

Asset monitoring and control

IP’s have provided procurement plans and have inventories of existing equipment and supplies (to be shared when new items come in). MSI submitted their inventory to USAID who have transferred assets to Phase II.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The programme does not fund Government directly, but supports Government initiatives. This programme supports increased Government of Tanzania commitments to the rural poor of Tanzania especially women. Through the sharpened One Plan (to accelerate reduction in maternal and newborn deaths), the Government has increased focus on underserved areas to deliver on its commitment to reducing poverty and meet the MDG’s. There has been no evidence of corruption and human rights abuses, and the rights of poor people are protected. Support to women and girls rights to access CPAC and GBV services is also aligned to the commitment to support human rights. The regional scorecards assessing progress on reproductive, maternal, newborn and child health have been successfully implemented by Government over the last six months to increase accountability for results, demonstrating the strong commitment to enhancing domestic accountability.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

International evidence for family planning has not changed, and no new evidence impacts on the project. Lessons learned from Phase I are being used to feed into Phase II. In Tanzania, learning on outreach has been used to influence the design of the outreach models.

Two consultants were hired to conduct the project completion review for phase I and inception and annual reviews for phase II. DFID has contracted the consultants to provide services for subsequent annual reviews (in line with the terms of reference in the tender). This will ensure consistency in comparing the two models especially in terms of costings.

Log frame revision.

As part of the Pre-Annual Review, the logframe has been revised. There has been no change at outcome or impact level and only minor wording revisions at the output level. The indicators, however, have been modified somewhat to reflect new activities, making the two partners comparable, and to accommodate the way the IPs collect their data. A few indicators where data were not available were cut. Overall, these changes have not changed the logframe significantly and should have made the subsequent Annual Reviews data collection much easier and the two IP models more comparable.

In addition to the logframe, the following will be examined during the Annual Reviews:

KAP survey of public sector attitudes
Youth use of condom
Training Tracker before and after
Stock outs (Depo as tracker)
Misoprostol use and availability
MVA main and resupply (logbook of use?)
Training + or – 20% of target
Male attitude
Outreach staff morale and pay scales
Geographical variations

Monitoring progress throughout the review period

The Adviser (SRO) and programme manager are responsible for reviewing quarterly reports and discussing any issues with IP’s during quarterly review meetings within two weeks of the report being submitted. Field visits will be conducted at least annually and beneficiary feedback (especially of youth) will be sought by DFID staff (not necessarily adviser or programme manager, but also other DFID staff interested in the programme e.g. social development adviser).

The Annual Review Process
The annual review process was conducted by two consultants, with the Health Adviser and Programme Officer for Family Planning Outreach. The consultants also completed the inception review for Phase II and project completion review of phase I. The review was undertaken through a document review and discussions with key stakeholders including MSI, PSI, Engender Health, Ministry of Health officials and DFID, especially the HIT team leader, Commercial Adviser and Health Adviser.