Annual Review - Summary Sheet FINAL APPROVED

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Family Planning Outreach II
Programme Value: £22,030,000		Review Date: January/February 2016
Programme Code: 204266	Start Date: November 2014	End Date: December 2018

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A+
Risk Rating	medium	Moderate

Summary of progress and lessons learnt since last review
This programme has just completed its first year of the second phase of DFID-supported family planning (FP) outreach.

Two FP outreach models in one programme is a useful way of adaptive programming. Phase II of the family planning outreach programme brings in a second Implementing Partner (IP) to complement the Marie Stopes Tanzania (MST) outreach model. These two delivery models are being scaled up in parallel with explicit focus on improving access, sustainability and lesson learning. Population Services International (PSI) with subcontractors Intrahealth and Restless Development introduced four family planning outreach teams this year, and has provided a significant improvement on the sustainability aspects of the programme. These models are meant to complement one another as well as to introduce some healthy competition between the two IPs. MST has 20 outreach teams and it is recommended that PSI expand from four to 10 outreach teams in Year 2, as planned. The four teams that PSI has trained were working well and the hub & spokes were proving to be a sound model. The introduction of key performance indicators has been useful in ensuring collaboration, and has improved the quality of engagement (particularly for MST) with Government of the United Republic of Tanzania (GoURT) and other stakeholders.

The programme is working towards a good combination of service delivery, to support GoURT to meet its targets, and capacity building to ensure sustainability. In line with a total market approach to family planning[1] in Tanzania, the current ways of working combine the advantages and current capacity of the public sector and the flexibility and efficiency of the private sector to cover the total market for family planning. In the short to medium term, there is also the need to balance systems strengthening efforts with meeting Tanzania’s policy targets and UK Manifesto commitments.  How this combination will change in the coming years will be based on how much the public sector can increase its capacity to cover family planning at primary level. However, the private sector may continue to be useful in the most rural hard-to-reach areas.  To achieve this total market approach, good coordination and planning between public and private sectors is critical, and effective coordination of donor investments including the large health systems strengthening efforts of USAID, UNFPA, DANIDA and the sector basket.  There is good evidence that this is happening in Tanzania, based on the multiple Technical Working Groups and the active role of GoURT. The timeframe for an effective exit for donor funded service delivery could be around 7-10 years. In the meantime, further efforts are required to ensure that there is domestic resource allocation to family planning. While the main aim of the programme is to give women choice over their reproductive lives, and effective strategy for engaging with the Ministry of Finance would be through messaging on the demographic dividend. Analysis has already been completed by Pathfinder through DFID funding in the commodities programme in 2014.
[1] USAID (2016) Planning Guide for a Total Market Approach to Increase Access to Family Planning

Public sector capacity building leaves sustainable services after the non-sustainable family planning outreach services cease. Training of public sector providers at scale is new to MST, hence the weighting was only 10%. It is also determined by the availability of senior level public sector trainers whom the GoURT require to be present at all training courses. Both IPs are training public sector providers in long and short-term family methods. In addition, the outreach teams are urged to mentor and refresh the FP skills of the providers they find in government facilities. There has been some success with mentoring, and both agencies have been making progress with on-the job training. Both IPs are encouraged to avoid substituting for any family planning services the public sector is already able to provide. A perennial problem, however, is ensuring that trained public sector providers have the equipment and commodities that they need.

Community norms around family planning and GBV need concerted efforts by IP’s to overcome. The teams especially the community-based mobilisers and nurses work closely to address issues raised by women regarding local norms and understanding around family planning and GBV. As part of the programme quality and learning agenda, it would be useful if this was documented and used to improve the responsiveness of the programme for beneficiaries. This qualitative data could also be fed into a wider programme to prevent GBV or focus on a rights based approach to addressing the needs of girls and young women. Possibilities of working with schools should also be considered within parameters of GoURT policy.

Emphasis on youth increases programme costs. Both MST and PSI were challenged by DFID to reach more young people with their programmes and to use innovative ways to do this. Each has risen to the challenge and surpassed their youth milestones in Year 1. MST has greatly exceeded theirs as 13% of those reached by MST were under-20 compared to less than 5% in previous years. This is because of increased youth activities as well as superior measurement of youth participation by collecting youth data along with their routine data collection rather than only at exit interviews. More innovative ways are required to reach youth and their preferences tend to be for injectables and condoms, the latter has the benefit of dual protection against sexually transmitted diseases and contraception, but have lower numbers of couple-years of protection. The costs of reaching youth are high at £63 per couple-year of protection for the Restless Development model. However, the value of a CYP with youth is much higher than for older women, what MSI term a ‘high-impact’ CYP.

New areas beyond FP outreach takes advantage of the opportunity to meet the needs of girls and women. Phase II introduces two new areas beyond family planning: Comprehensive Post Abortion Care (CPAC) and Gender-Based Violence (GBV). CPAC services include treatment of post-abortion complications, counselling, and post-PAC family planning. GBV services include screening, treating and referring survivors of GBV to trained providers or to Government of the United Republic of Tanzania (GoURT, also referred to as public) services. There is much to be learned from the addition of these new services to the FP outreach model, which were a missed opportunity in the previous phase, and there was some adjustment this year to the indicators to better measure them.

Collaboration with GoURT. Collaboration with GoURT during Phase I had some challenges. Phase II has begun smoothly with good evidence of excellent collaboration with GoURT, especially at regional and district levels. At national level, the partners have been actively engaged in the family planning working groups, with MSI acting as secretariat for the outreach working group.

Avoiding overlap with other IPs doing FP outreach. Multiple donors, including USAID and KfW, fund FP outreach, making a careful mapping of FP outreach critical. So far, this has not been a major issue but PSI, in expanding its teams, will need to keep a careful eye to avoiding overlap. Active participation by all partners in the FP outreach Technical Working Group is an additional check and advanced planning is required.

Collaboration and learning between IPs. Cooperation and collaboration between IPs appears to be positive. The PSI model does not include permanent methods and MST doctors were asked to perform tubal ligations in some of PSI’s regions. Communication between partners at DFID-run quarterly meetings is working well and the evaluators would urge that this good practice continues.

Commodities. Both IPs are meant to rely on the GoURT Medical Stores Department (MSD) for the majority of their contraceptive supplies. As this system was not always working, DFID has engaged UNFPA, who have contracted DKT, to maintain contraceptive buffer stocks in warehouses around the country. This year, it was found that PSI used 80% stocks from MSD; for MST, the proportion was even higher at 85%. The IPs need to work better with public sector facilities to encourage forwarding planning of necessary FP commodities; ideally this should be a year in advance, with quarterly detailed planning to ensure stocks are in place at the public health facilities. In addition, MST and PSI could do better at reporting their sources of commodities including strategic reserves and their own buffer stocks to feed into the national monitoring system for commodities. It is also essential that DKT engage more with MSD.

Summary of recommendations for the next year

Both IPs
1. Commodity planning at district level is to be encouraged by both IPs to decrease dependence on the buffer stock. DKT to work more closely with Medical Stores Department (see commodities annual review) IPs should be planning their outreach and communicating this to districts a year in advance. IPs should help facilities in an informal way with their understanding of stock management, minimum stock levels and Report & Requests when they visit in an effort to raise visibility of the level of stock in the government system. Outreach team leader with immediate effect.
2. Improve timely reporting to GoURT/DKT on commodities use by source, and coordinate with the District Reproductive and Child Health Coordinator (DRCHCo) and district pharmacist. Outreach team leader with immediate effect based on a revised reporting requirement by DKT– DFID and UNFPA will monitor this from the next quarterly reporting period.
3. Enhance mentoring for public health providers, especially in FP counselling and service provision. Public sector providers should be encouraged to participate in group & private FP counselling sessions. Outreach teams with immediate effect.
4. Both IPs should put an increased emphasis on both dual protection and on Emergency Contraception (EC), particularly for young people. (Note: USAID is including EC training alongside training in Implanon NXT, the same product with improved insertion and a radio-opaque rod). Dar teams to support outreach teams to deliver on this, by July 2016
5. Ensure that FP is part of the CPAC guidelines as there is a disconnect between policy teams working on CPAC and FP (we were informed at the time of the review that post-PAC FP is missing). Technical teams in Dar to advocate through technical working groups. DFID to work with USAID to push through maternal health working groups. By July 2016
6. IPs should coordinate with Pathfinder and others to avoid duplication of CPAC training. By April 2016
7. IPs should train sufficient numbers of staff to account for attrition. Ongoing
8. Continue to pursue District Health Information System (DHIS-2) data with GoURT and obtain passwords. IP Project Managers by April 2016.
9. Consider seriously whether outreach teams should be able to deliver CPAC (as they currently do not). While cases would be few, it could save some lives. IP clinical directors or equivalent, with formal response to DFID by May 2016 (next quarterly review)
10. IPs to provide requested data for next year to allow evaluators to comment on differential effectiveness, efficiency or economy between different geographical locations and models. MSI were unable to provide the data agreed, and most data was available for PSI. IP headquarters (finance managers, programme quality and research leads) to ensure this happens by next year. DFID will request evidence of data collection by May 2016 to ensure on track.

MST
1. MST needs to carefully keep track of what interventions to reach youth are the most effective. Ongoing
2. Ensure that valuable client data is not lost by using the less complete consent forms to gather it, and consider rationalising the number of times they enter similar data on different forms. By April 2016
3. MST should consider using Association of Gynaecologists and Obstetricians in Tanzania (AGOTA) trainers for CPAC (PSI is already doing this). Response to DFID by May 2016.
4. MST to ensure that costing data is set-up and available to allow for cost-analysis to compare models and types of clients reached. Immediately and available for before the next annual review.

PSI
1. Ensure adequate numbers of intrauterine copper device (IUCD) insertion kits in PSI hubs and spokes. Ongoing
2. Strongly consider adding voluntary counselling and testing (VCT) for HIV/AIDS for GBV survivors in the PSI model. PSI project manager to respond to DFID by May 2016
3. CPAC should be delivered at both PSI hubs and spokes to increase access. PSI to submit costings to DFID by April 2016. DFID to approve by May 2016
4. Integrate community health workers into training on how to reach youth and how to be more youth friendly. Plan by August 2016
5. Ensure the use of the term ‘targets’ per method is not used by Team Leaders, providers or in reports. Ongoing
6. MST has developed a values clarification tool for training providers working with young people and PSI should consider using it as well. Decision and plan for using it by April 2016
7. In the current programme, consider a small programme that ‘cares for the carers’, as in the PSI model, the providers are trained to deal with even serious cases of GBV. This would mean that those working with GBV cases could receive some counselling themselves, if required. Response by April 2016

DFID
1. Consider working further on GBV prevention at the community level either as another component or a larger separate programme, given the complexities. Possible consideration of how this and family planning can be integrated within the broader girls and youth agenda using rights-based approaches. DFID to consider during the bilateral aid review and strategy discussions.
2. Ensure joint monitoring visits with Government and IP’s for learning and peer review to enhance programme quality. DFID adviser and programme manager to schedule twice a year (including annual review).
3. Define an explicit exit strategy including consideration of further systems strengthening to ensure sustainability and ensuring domestic resource mobilisation. DFID during bilateral aid review and by October 2016.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

DFID Tanzania is implementing Phase II of a Family Planning outreach programme over 4 years (2014-2018) to continue to increase family planning use in Tanzania, especially among the rural poor and youth (under 20 years of age). The outcome of the programme will be to increase women's use of family planning and availability of comprehensive post abortion care (CPAC) services across Tanzania, with a special focus on rural and hard to reach areas. The impact will be to reduce maternal mortality and improve women's lives by giving them control over their family formation.
The programme has specifically set out to increase women's use of comprehensive family planning and availability of CPAC and GBV services across Tanzania. Specific outputs are stipulated in the log frame as follows:
- Private sector family planning outreach services to rural areas (particularly long-acting and permanent methods-LAPM) in consultation with Government public sector services;
- Strengthened national comprehensive post abortion care (CPAC) in both public and private sectors (including policy work);
- GoURT supported to strengthen its family planning programme, including training of public sector providers in LAPM;
- Young people (<20) reached with family planning and CPAC; and
- Integrated RH services for women who are victims of violence (GBV) work in the public or private sectors.
Addressing youth remains a challenge and this programme will ensure that this underserved group are able to access services. This will be an area requiring a lot of testing and learning, ensuring that youth preferences are taken into account in designing accessible family planning services for them.

MSI and PSI were contracted in December 2014 and January 2015 respectively after a prolonged contracting process, particularly relating to milestone based payments. MSI continued services from December and retained staff when Phase I ended in November 2014. PSI started with four new teams for year one, using their new model, which would be assessed to ensure that they can scale up to the full complement of 10 teams by year two. PSI has two sub-contractors: Intrahealth (training and GBV) and Restless Development (youth).

Here is a short description of each model:

MST’s outreach model involves 20 four-person outreach teams ‘snaking’ through the countryside to continually different public sector health facilities, including dispensaries. Teams include MST staff as well as a public sector Assistant Medical Officer (AMO) and a nurse. MST returns to each facility only about every five to six months. DFID has considerable experience with this MST model with its strengths and weaknesses (see table below). In addition, MST has been training public sector providers with the GoURT FP curriculum.

PSI’s outreach model is a public sector hub and spoke model and more static than the model of MST. The hub and spoke facilities have considerable training in FP, CPAC, and GBV. PSI outreach teams operate out of the PSI offices nearby and include one PSI healthcare provider and one public sector nurse (recommended by the District Reproductive and Child Health Coordinator - DRCH Co). The outreach teams go to rural areas surrounding their corresponding hub and spoke and refer more complicated cases there. PSI began with four teams in the first year and it is recommended that PSI scale up to 10 teams in Year 2.

It is not expected that one model will necessarily be seen as superior to the other. Each model works best in the areas in which the IPs are working and each model has its strengths and weaknesses as shown in the following table.

Strengths and Weakness of the MST and PSI models
	Strengths	Weaknesses
MST model	Full method mix including sterilization / Reaches large numbers of women with unmet need / Reaches many facilities in remote areas / Also provides voluntary counselling and testing (VCT) / One organization with no subcontractors means single organisation coordination / Able to refresh the training of public sector workers / Sends GBV survivors to strengthened public services where available.	Less time at facilities leaves less time to build capacity / Difficult to supervise public sector trained workers / Only able to refer to regular public sector facilities (with no additional training) / Harder to follow up post- operative problems, if any / Not very suitable for CPAC as few cases would come to an outreach event / Greater danger of exhaustion of facility commodities, if District Pharmacist does not receive notice of visits and act to allow appropriate stock accumulation
PSI model	In-depth work in fewer facilities / Better training supervision / Additional partners for new work brings new ideas (CPAC, GBV & youth) / Static model is able to refer to trained & strengthened public sector services / Leaves sustainable and well trained public sector providers and facilities at end of project / Allows for GBV referral to hubs	Does not include sterilization or VCT in outreach services so does not provide a full method mix / Reaches fewer facilities / Reaches fewer women / Model still being tested at scale
Both	Incorporates public sector healthcare providers on its outreach teams / On the job training of public sector staff / Offer training in FP to public sector providers / Maintains strong relationships with GoURT

Background. Phase I, had just one provider, Marie Stopes Tanzania, delivering family planning outreach services only, nationwide over 3.5 years. Funds were channelled through USAID to provide programme management and technical expertise. Phase II includes CPAC and GBV as additional services, with an increased focus on youth as well as capacity building of public providers. Two suppliers – MST and Population Services International (PSI) have been contracted to provide services in the interest of sustaining a competitive market and fostering innovation and challenge. MST will deliver services through twenty teams and PSI through four teams in year one with a view to scaling up to ten teams in year two based on performance.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Achievement has been almost universally met and, in some cases, exceeded. Both IPs exceeded their CYP outcome milestones and both MST and PSI exceeded their milestones for their promised services. In addition, both IPs delivered more new users than estimated. The most surprising news was that 13% of MST’s clients were under the age of 20—this is a significant jump from 4%. PSI’s new model is working well with good referral systems in place and the requisite public sector providers trained. Both IPs exceeded their training targets as well. Progress on the new components to the programme (CPAC and GBV) continued apace. MST is working closely with the Ministry of Health, Community Development, Gender, Elderly and Children (MOHCDGEC) to prepare CPAC guidelines. They are not yet signed off as some additional training with them was required. In addition, MST is still awaiting GoURT decisions on which regions MST will concentrate CPAC public sector training. GBV services are available in all FP outreach sites and staff are trained. Some of the work on capacity building of public providers has been very successful and supports the move to ensure that services can be delivered through the public sector. Other stakeholders such as USAID and CHAI, are gradually addressing other complementary issues, including commodities forecasting, coordination of trainings and data management and use. There are two big challenges to sustainability: (a). low priority for GoURT given the scarce resources, perhaps due to lack of knowledge by Ministry of Finance on the cost-effectiveness and the demographic dividend; and, (b). continued donor funding due its high VfM.

Overall output score and description: A+

Key lessons

The programme has completed its first year of operation and PSI has yet to scale up to full (10 team) capacity, therefore it is too early to draw too many conclusions or lessons.

The biggest lesson this year is that MST and PSI can reach youth, and effectively measure that they have done it with routine data. The extent to which they have done this has surprised and pleased both MST in particular and the evaluation team. This is absolutely critical because of the demographic and health impact of reaching people early with family planning and safe sex messages and habits they might maintain throughout their reproductive lives. Raising the age of first birth should always be a major development goal as later births are more likely to have healthy outcomes and allow the girl to finish her education.

The evaluation team have also found that we can compare VFM between the two models (although PSI is not yet as efficient yet as it will be once all scale up to ten teams is complete).

Key actions
Give the green light for PSI scale up to the full ten teams with an emphasis on rural areas. PSI is expected to mobilise rapidly at scale, with 90% of teams fully operational within 4 months. Implementation will be in close collaboration with the GoURT at the national, regional and district levels.

Continue buffer stock until the end of the programme and encourage IPs to improve planning at district level so that dependence on buffer stock diminishes over the life of the programme.

Has the logframe been updated since the last review? Yes; further details in the monitoring and evaluation section.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	FAMILY PLANNING. Private sector family planning outreach services to rural areas (particularly LAPM) in consultation with Government public sector services
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		Y from low-medium to moderate	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of FP services delivered by the project (LT & ST methods, disaggregated by age)	MST: 301,071 / PSI: 26,427 (4 teams)	MST: 312,865 / PSI: 29,278
1.2 Proportion of clients classified as poor	MST: 62% / PSI: 62%	MST: 72% / PSI: 60%
1.3 Cost per CYP (efficiency)	MST: £5.52 / PSI: £15.36	MST: £4.48 / PSI: £13.17
1.4 Client satisfaction with the service they received (PSI: would you recommend a friend?)	MST: 90% / PSI: 90%	MST: 92% / PSI: 99%

Key Points
The models have very different method mixes. The vast majority of PSI’s services are long-acting and reversible contraceptives (LARCs), with an impressively high uptake of IUCDs. MSI also offers female sterilisation and offers more services to youth so its method mix is much broader. It should be noted that it is more difficult and expensive to include permanent methods in the method mix however, cost per CYP is reduced.

Outreach clients are already choosing long-acting methods. Outreach clients do not tend to choose short term FP (such as pills, injectables and condoms) because they can already find these options in the public sector. The clients wait for the outreach teams to obtain free long-acting and permanent methods. There were issues around counselling on the full method mix including little emphasis on female condoms and emergency contraception (EC). Teams did not mention or skimmed over these and Government providers are less aware of these methods. This is a missed opportunity in the prevention of unwanted pregnancies, particularly among youth.

Access to equipment limits service delivery. Limited numbers of IUCD insertion kits for teams limits the rate at which services can be offered as time is required for sterilisation between clients. There was also evidence of Government facilities having incomplete and/or inadequate numbers of IUCD kits which needs to be addressed.

Both IPs are active members of the FP Outreach technical working group. MST is the secretariat for the outreach working group in which PSI also participates. This is critical for overall coordination and collaboration with the GoURT.

Collaboration at regional and district level is good and shows improvement from Phase I. The evaluation team heard nothing but appreciation at the regional and district level for the good cooperation and support of both MST and PSI.

MST data collection. MST staff currently collect client data on the consent forms and enter it into the government records later. As the consent forms are less complete, valuable client data is lost. In addition, data is entered several times on several forms.

Commodities continue to be an issue. The DKT buffer stock continues to play a critical role. MST is using 85% of its commodities from MSD; PSI is using 80%. It was agreed that decreasing dependence on the buffer stock would be observed and encouraged. Meanwhile, joint annual review of the DFID commodity support recommended the continuation of the buffer stock for the rest of the life of this project.

PSI model lacks access to VCT for high risk groups. While the MST model includes Voluntary HIV counselling and testing (VCT) for all clients, the PSI model does not include VCT. It may not be necessary to include VCT for everybody; rather a system whereby GBV survivors may be given the option to test.

IPs still struggling to access DHIS-2 data. The evaluators found at least two other IPs who have password access to the GoURT’s DHIS-2 database. MST and PSI have been told that once their M&E people are trained that they will also receive passwords. Persistence is required.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- Commodity planning at district level is to be encouraged by both IPs to decrease dependence on the buffer stock. Districts should be planning at least six months ahead; ideally a year ahead.
- Both IPs should put an increased emphasis on both dual protection and on EC, particularly for young people. (Note: USAID is including EC training with Implanon NXT training for public sector providers.)
- Ensure adequate IUCD insertion kits in PSI hubs and spokes.
- Consider adding VCT for GBV survivors in the PSI model.
- IP’s to continue to pursue DHIS-2 data with GoURT and obtain passwords.
- Ensure that valuable client data is not lost by using the less complete consent forms to gather it and rationalise the record keeping process.

Output Title	CPAC. Strengthened national comprehensive post abortion care (CPAC) in both public and private sector (including policy work)
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Y, revised from medium to moderate	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 a) Number of facilities (public and private clinics) equipped and supplied to deliver CPAC; b) Per cent of facility visits MST makes where CPAC equipment and supplies are present and in good working order [(b) has now been cut]	MST: 80 / PSI: 740	MST: 130 / PSI: 481
2.2. Number of public and private health workers trained and certified (at least 80% of those trained) in CPAC using MVA (80% of these will be public sector providers and will include government certification)	MST: 160 / PSI: 20	MST: 182 / PSI: 16 certified
2.3 Number of women accessing safe post abortion care (through this programme of support)	MST: 4,670 / PSI: 933	MST: Work not begun / PSI: 725

Key Points
CPAC in public facilities is not free. CPAC is not free in public sector facilities so distressed women are forced to pay for life-saving assistance. Also, often the equipment and training in public sector facilities is inadequate to perform the procedure. The RMO in Njombe recognised CPAC as an area where the public sector was weak and welcomed the input of DFID and the IPs.

CPAC Guidelines awaiting GoURT signature. While many IPs participated in the preparation of CPAC guidelines, MST took the lead. The GoURT have not included CPAC using misoprostol in the guidelines, likely out of fear that the spread of the use of misoprostol will increase illegal abortion. The use of misoprostol for CPAC is in the WHO abortion and post-abortion guidelines, along with MVA.

Post abortion family planning is missing in CPAC guidelines. A critical part of ‘Comprehensive’ post-abortion care is their attention to seeing that the client leaves with a family planning method in order to avoid future unwanted pregnancies. One theory about why these are missing is that CPAC falls under the Safe Motherhood department in the MOHCDGEC.

CPAC is currently only offered in PSI hubs. This is a missed opportunity. While CPAC cases at the spokes can be referred to hubs, keeping the services closer to the women and more widespread is essential to reduce complications and lower the risk of mortality.

AGOTA trainers were able to add use of misoprostol for CPAC to their training. As above, the CPAC guidelines do not contain information on the use of misoprostol for CPAC but the trainers from AGOTA were able to include it in their CPAC training to government providers. PSI is using AGOTA trainers and, while they are more expensive, they are finding the high quality of training as well as the addition of misoprostol use for CPAC to be worth it. MST should also consider using AGOTA trainers, who are also government providers.

Misoprostol is widely available ‘on the streets’ and in pharmacies. While the use of misoprostol to induce abortion is illegal, it is a safer method than what women used to use, thereby reducing deaths from unsafe abortion. This is a life-saving commodity.

MST CPAC training being driven by government preference to concentrate in two regions. MST is still in consultation with GoURT on where to carry out CPAC training with the GoURT preference being to concentrate in two regions at scale to demonstrate impact on maternal mortality.

Coordination with other initiatives is essential. Pathfinder, particularly, are working sensitively in this area, with scale-up up to all facilities in Dar es Salaam. There is possible overlap with PSI in Dar.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- Ensure that FP is part of CPAC guidelines (USAID has also been notified).
- CPAC should be delivered at both PSI hubs and spokes.
- IPs should coordinate with Pathfinder to avoid duplication of CPAC training.
- MST should consider using AGOTA trainers for CPAC (PSI is already doing this).

Output Title	TRAINING. GoURT supported to strengthen its family planning programme, including training of public sector providers
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y, changed from medium to moderate	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of GoURT healthcare providers trained and certified in LAPM/LARCS (with supervision)	MST: 300 / PSI: 126	MST: 332 / PSI: 125
3.2 Total number of women accessing FP services in public facilities (derived from aggregation of district data)	MST: To be derived / PSI: To be derived	MST: 823,551 / PSI: 62,903
3.3 Average QTA score for project teams	MST: 90% / PSI: 90%	MST: 91.5% / PSI: 94%
3.4 All clinical incidents properly investigated and clearly communicated to all levels of Government in a timely fashion (within three days)	MST: Yes or no / PSI: Yes or no	MST: Achieved (1 clinical incident) / PSI: None

Key Points

Both MST and PSI have met or exceeded their training requirements. Training public sector providers is a critical piece of this programme’s sustainability strategy. As private sector FP outreach will never be sustainable, it is key that long-lasting FP skills are left in the public sector.

MST has made real progress in the training & full certification process for public sector providers. Initially reluctant to engage with the public sector beyond using their facilities and commodities, MST has been pleasantly surprised at how their training activities have built a much more positive relationship with the GoURT.

Final training numbers affected by a) attrition; b) inability of staff to pass; and c) in the case of CPAC, poor healthcare provider attitudes. The evaluators were reluctant to ask the IPs to train a specific number of extra staff (e.g. 130%), preferring rather to have the IPs determine how many people they need to train in order to ensure that 100% of the training milestone are in post.

MOHCDGEC ready to certify first batch of trained public sector providers. The certificates are awaiting signature of Assistant Director RCHs and Director of Preventive Services sitting at MOHCDGEC’s office
.

Trainee follow-up remains a bigger challenge for MST than for PSI. PSI trained staff reside at the hubs and spokes. MST-trained public sector providers reside in facilities that MST visit only rarely. MST is working hard to carry out follow-up supervision.

Public sector provider mentoring opportunity missed. Both IPs spend time at public sector facilities and should not miss the chance to informally mentor these workers on their FP skills. As the GoURT FP training module is weak on teaching counselling skills, public sector providers are not as good at FP counselling as they need to be. This means that the mentoring opportunity of the outreach teams for the public sector providers is even more important. Similarly, informal mentoring of staff at facilities in commodity management and Report & Request submissions is suggested. It is acknowledged that there is formal secondment of public health workers to the teams, however, other providers should be mentored informally during outreach.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- IPs should train sufficient numbers of staff to ensure that there are 100% in post at the end of the training process.
- Informal mentoring for public sector providers, especially in FP counselling should be encouraged.

Output Title	YOUTH. Young people (<20) reached with family planning (likely to be ST methods) including CPAC and GBV
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y, changed from medium to moderate	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Proportion of all family planning services to clients aged under 20 through the outreach teams [also PSI data on youth attending the hubs]	MST: 5% / PSI: 5%	MST: 13% / PSI: 7%
4.2 Number of (public and private) programme staff specifically trained to work with or provide information, education, or family planning services to adolescents under 20 (no certification)	MST: 55 / PSI: 4	MST: 72 / PSI: 9

Key Points
MST surpassed its youth milestones by far and PSI also slightly exceeded their milestone. Even MST was surprised at how effective their interventions were in reaching youth under the age of 20. This represents a real achievement for MST.

MST changed the way it collected data on youth. Formerly, MST collected its youth data from exit surveys, making the findings less reliable and only available at specific times of the year. In Phase II, MST has begun to collect data on youth as part of its routine data. This has resulted in greater accuracy in youth numbers.

MST is using a variety of interventions to reach youth. MST is working with vocational colleges, attending youth festivals, and ensuring that each outreach site has at least one young community mobiliser. MST has not yet rolled out its two-day outreach model yet. This model includes youth services on day two when all the older clients have received services on day one.

Restless Development (RD) have an effective method of ensuring youth attend the public sector hub facility. RD is running a number of community interventions, including youth groups. RD gives young people who have been counselled on their FP options a referral card which they take to the hub. The card identifies the healthcare provider in the hub by name that the young people seek. RD found that about 77% of the referral cards they passed out were turned in to the hubs, indicating a high success rate. RD has also had success with the involvement of parents at the community level.

MST is leading the international MSI partnership in reaching youth. MST reported that other MSI country partners were coming to MST as they all seek to reach youth better. This is a compelling reason for effective analysis and documentation of the models.

What FP methods do young people use? From the monitoring visits and the data so far, it is clear that youth prefer to use short-term methods, specifically condoms and injectables. The evaluation team will explore this further in the next annual review as MSI and PSI establish their work with youth.

How much does it cost to reach youth? Reaching youth is much more costly, however these services and CYP’s should be considered as very high-impact as there are significant longer-term benefits of preventing pregnancies in youth, including enabling continuation of schooling and better prospects for future children, among others. [See the VFM section for more answers.]

Sustainability of youth interventions. As the programme progresses and the ways to reach youth are better understood, attempts can be made to see that these interventions can be sustainable.

Pregnant girls can now return to school. Girls in school are subjected to pregnancy tests and, up until recently, could never return to school if they were found to be pregnant. A recent policy victory (not funded by this project) has meant that girls can now return to school. This is welcome progress, although operationalisation of this is still limited.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- MST needs to carefully keep track of what interventions to reach youth are the most effective.
- Integrate community health workers into training on reaching youth and how to be more youth friendly.
- MST has developed a values clarification tool for training providers working with young people. This tool should be shared with PSI and they should consider using it as well.

Output Title	GBV. Integrated RH services for women who are victims of violence (GBV) in the public or private sectors
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y, changed from medium to moderate	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (for monitoring not targets)	Progress
5.1 Number of survivors receiving post GBV care services	MST: 4% [to be adjusted] / PSI: As above	MST: No data / PSI: 2644
5.2 Number of public (80%) and private providers trained [with 80%-CUT] with good competency assessed in trainee follow-up	MST: 50 / PSI: 48	MST: 71 / PSI: 54
5.3 Number of survivors referred for clinical and non-clinical services	MST: 50% [to be adjusted] / PSI: As above	MST: No data / PSI: 2,537

Key Points

GBV survivors are more likely to have problems accessing and using family planning and are at a higher risk of an unwanted pregnancy. Recent evidence shows that abortion rates are twice as high for women who have experienced partner violence (Population Reference Bureau, 2015).

MST is linking GBV survivors to local GoURT services. MST has a GBV Government Liaison officer who links survivors with local Government services. This person researches the most appropriate and closest government service available, often the Village Executive Officer. This may be useful for prosecuting or punishing the perpetrator, but will not be able to provide the psychological and social support needed.

PSI refers GBV cases to the hub. Public sector healthcare staffs in the spokes are given the short version of the GBV training to that they can screen, treat and refer the more difficult cases to the hub. In the hub, the GBV provider has received the longer version of the GBV curriculum & can work with the harder cases.

GBV exemption is not always applied. The evaluation team heard of cases where survivors were not properly identified as such and were charged for the services they needed in the public sector. There are GBV exemption forms but the survivors don’t always get identified in such a way that it is clear what they are and what they need. PSI, with Intrahealth, should be considering how to avoid this issue (clearly a wider problem within the Tanzanian health service) and also to bring this to the attention of policy makers and councils.

Work on GBV is new and indicators and milestones have changed. The GBV indicators have been re-worded in the logframe and the milestones will be adjusted for the rest of the programme. These changes were always anticipated, as DFID and IP’s are learning in this new area which has limited data with which to plan.

GBV prevention in the community is not currently built into this programme. Currently the programme screens for survivors and treats them and/or refers them on to other services. There is no prevention aspect of the programme built in. To really address the problem, a GBV prevention component would have to be built into the programme or a completely new programme designed to address the complexities and social norms around GBV.

GBV workers have a high rate of burn-out after seeing many difficult cases. Intrahealth suggested some additional help for the PSI-trained public healthcare providers at the hubs called ‘Caring for the Carers’.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
- In the next phase of this programme, build in GBV prevention at the community level into the programme from the start.
- In the current programme, consider a component that ‘cares for the carers’, meaning that those working with GBV cases could receive some counselling themselves, if required.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The first year of operation should have delivered stronger evidence of the cost drivers for the project than previously (when budgets and plans were used). As part of last year’s Annual Review it was agreed that IPs should place their data in a common format for ease of analysis and comparison:

	Cost category	Description
1	Own labour costs	Salaries and per diems for IP operational staff
2	Transport costs	Fuel and maintenance for vehicles
3	MOHCDGEC costs	Per diems for MOHCDGEC staff, and person-day data for application of salary cost
4	Commodity costs	Service delivery data for application of commodity procurement, storage and distribution costs
5	Support costs	Estimates of support provided by both local and international offices of the IPs
6	Other costs	Any other costs related to the FP outreach

However, only PSI was able to deliver cost information in this format, yielding the following information:

Figure 1: Cost drivers, based on PSI cost data, Year 1

The ‘Other’ category contains some spending which should ideally be moved elsewhere, e.g. all payments to Intra-health and Restless Development; additional consulting fees; etc. But this is still a helpful step forward in understanding the cost drivers of an outreach FP-based programme.

Unfortunately, MST’s cost data remains in categories which challenge external analysis. They were in 13 different categories and hard to translate to the agreed classifications. For example, fuel costs and per diems were within the ‘furniture and equipment’ category; and, payments to village health workers and printing were within the ‘travel’ category.

As set out in the Inception Report, the consultants have included not only the IP’s direct expenditures but also indirect costs. So while the IPs were obliged to contribute the per diem cost of their GoURT outreach team members, the consultants also took account of what GoURT paid to them in salary while they were involved in outreach. And commodities that were free of charge to IPs (because financed by other donor-funded programmes) have also been costed. Costs to clients, such as transport and any foregone income, have not been included, but recent evidence from DFID’s multi-country Preventing Maternal Deaths from Unwanted Pregnancies (PMDUP) programme through suggest that these are minimal.

This initial analysis is close to the projections made at Inception, with the important role of labour costs underlined (some of the ‘Other costs’ is sub-contractors’ labour) and the minimal role of current transport costs. Note that DFID paid the vehicle purchase cost[2].
[2] These are amortised by IPs over 5 years, although in fact some may last twice this, even given their punishing treatment in outreach.
Value for Money indicators and their ex-ante values. The following table shows key selected VfM indicators for each IP and, with their values in the initial Business Case and Inception Report in brackets, for the programme as a whole:

Table 1: Estimates of VfM indicators, Year 1
	MST	PSI	Programme
Effectiveness
cost/DALY	£4.87	£14.16	£5.86 (£10.81; £5.89)
cost/maternal death averted	£4,266	£12,309	£5,132 (£9.435; £5,139)
cost/unwanted pregnancy averted	£10.79	£31.36	£12.99 (£24.01; £13.08)
Efficiency
Cost per CYP	£4.48	£13.17	£5.26 (£5.01; £5.53)
Services delivered/team/year	13,036	7,320	11,804
Economy
Cost/team/year	£199,210	£344,836	£220,013
Amortisation of capital goods	5 years	[?]	n/a

Note: as per the Inception Report, MST is assessed over 13 months in this table and costs included are conservative, including all IP programme costs.

All indicators suggest that the programme offers good value for money. This is not unexpected, as the LAPMs provision which is at the heart of the programme is an inherently cost-effective intervention, offering many years of protection from a range of costly and unhealthy outcomes (e.g. unwanted or risky births) at a modest cost. Note that the marked difference in the effectiveness measures from the Business Case is due the modelling approach of the Business Case which looked only at impacts during the programme years (and not at the protection of long term methods to women in the years immediately after the programme ceases).

There were no specific VfM indicators to cover the programme’s training activity. Such indicators can be problematic because training quality is hard to gauge and because the GoURT has a major influence over training costs (e.g. per diem rates were raised by around 50% by GoURT during Year 1). At present, there is no data available from IPs on differential effectiveness, efficiency or economy between different geographical locations (although this was promised by IPs at the Inception Phase). This information will need to be provided by the end of Year 2 if not sooner.

Model testing: MST v PSI. One of the objectives of the current programme is to compare the two IPs’ FP outreach models. While this is useful for DFID (and for the IPs) it should also be recognized that the two models are also to an extent complementary. MST’s model is better designed to reach rural facilities, far from a facility functioning well enough to serve as a hub. PSI’s model is better designed to engage intensively with a public hub facility, exerting a more strongly positive capacity building influence. With that proviso, both are compared over calendar 2015 (though note that PSI started operations slightly after the start of the year. The basic team/year data clearly suggests greater effectiveness with MST’s model, especially for young people under 20 – 13% of MST’s clients were under 20, compared to 7% of PSI’s.

Table 2: Comparative team/year data, Year 1
	MST	PSI
Services delivered/team/year	12,551	7,320
LARCs per team/year	7,679	6,781
CYPs per team/year	43,192	26,182
Under 20s services/team/year	1,632	507

The following tables control for two factors: MST’s teams are in the field more days per month and that MST teams also contain more members, due to the focus also on permanent methods. Also, the tables show progression over time. It can be seen that per person per day in the field the two models generate very similar numbers of services (though not of young people, as above). Also, encouragingly, it is clear that both IPs are getting steadily better at what they do. This augurs well for the remainder of the programme.

Table 3: Comparative person/day data, Year 1
Services/team-member/day
	Dec-14	Q1	Q2	Q3	Q4
MST	4	6	8	11	11
PSI		7	7	12	12

Youth/team-member/day
	Dec-14	Q1	Q2	Q3	Q4
MST	0.6	0.8	0.9	1.2	1.6
PSI		0.5	0.5	0.8	0.8

Reaching youth: Restless Development. Delivering SRH services to youth is a global challenge, suffering from a lack of consensus about what approaches work best as well as a lack of data. Restless Development’s model of informing youth, issuing them with referral vouchers and recording where those vouchers are redeemed and for which services seems to be an effective one, and it also generates useful data, which may be of interest within this programme but also outside of Tanzania. The consultants have analysed Restless Development’s data, from the start of operations in July 2015 until the end of the year, and summarise it in the following table.

Table 4: Restless Development data on youth FP services, H2 2015
Referrals issued	3,468
Referrals redeemed	2,677
Issue average monthly growth	14%
Redeem average monthly growth	16%
Redeem rate	77%

Of redemptions, FP	1,503

Total cost, H2	£61,000
Cost/redemption, H2	£22.79
Cost/FP redemption, H2	£40.59
Cost/CYP*, H2	£63.75

*approximated method mix

This shows that a large majority (77%) of young people (<20) given referral vouchers do indeed redeem them at MOHCDGEC health facilities within a short space of time. Also the numbers are growing steadily every month. And 56% of the redemptions were for FP services. Although the £41 per FP redemption is the conservative estimate of Restless Development’s cost-effectiveness, this ignores all of the non-FP benefits that clients received (abortion-related, GBV, etc). The £23/redemption all-service figure is also worth consideration and represents a reasonable cost for a hard-to-reach client group. Note that if Restless Development’s youth FP services are added to PSI’s youth FP services in the second half of 2015 then the total would be the equivalent of 15% of all PSI+RD FP services, compared to 7% at PSI alone.

Summary of VFM

The cost per DALY in this programme is £5.86. This includes child DALYs as well as maternal ones; if maternal DALY’s are only counted it could be five times as much. This is good compared to the Tanzanian GNI/capita of around $1,000.

Family planning will always be good value, especially in an environment where cost effective long term methods are used and pregnancy-related morbidity is prevented. Since preventing maternal mortality and morbidity is complex, it is challenging to cost the different services and cost per life saved.
The Tanzania FP programme compares reasonably well against other programmes in the region (See Table 5 below). We expect that VfM will steadily improve over the life of the programme, with more accurate estimates on MSI’s model, when they report more accurately.

Table 5: VfM of other FP programmes in Africa.
	Malawi / 2013-14	Tanzania 2015	Zambia / 2014-15	Ghana / 2014-15	Ethiopia / 2014-15	Zimbabwe / 2014-15
Cost per CYP	£3.87	£5.26	£11.25	£4.59	£3.02	£6.15
% under 20	10%	12%	13%	11%	13%	2%

Sources: Malawi PCR of programme running since 2009; Zambia/Ghana/Ethiopia/Zimbabwe Annual Review of PMDUP programme, running since 2011.

Tanzania’s mid-range cost per CYP is reasonably good, compared to the other programmes which are experienced and on the one hand may train less but on the other (apart from Malawi) are also offering safe abortion. It is also doing relatively well on reaching youth, although the other programmes, although the other programmes have less emphasis on youth.

Quality of financial management

Both PSI and MST have robust financial management systems. Since the IP’s have a number of sources of funding, some for similar activities, DFID have asked them to ensure open-book accounting with financial reports showing the contribution of funds for major line items. While MST has not conformed to the agreed accounting classifications due to the milestone based contract, both they and PSI have been open and cooperative with financial data during consultant field visits. DFID will also check audit reports during the life of the programme.

All financial transactions are centrally managed. Every month, outreach teams prepare their monthly budgets which have to be approved by respective team leaders and project managers before payment is made. Both organisations give a stipend to government health providers in their outreach teams and an allowance to community mobilizers who help them in organising outreach events. These transactions are paid through m-Pesa and recipients acknowledge receipt by signing a form.

Overall the spending pattern of the project is on track. Partners have in some instances delayed submission of their financial forecasts, which affects the financial planning for DFID. MST have also found it difficult to submit their quarterly financial reports as agreed during the inception of the programme, due to the structure of the milestone based contract. This has posed challenges in assessing Value for Money for the programme. MST also had an audit report for their USAID-funded programme, showing lapses in financial management, and has rectified these.

Both organisations have whistle blowing policies. PSI has experienced fraud in the Malaria behaviour change communication programme which was also funded by DFID. PSI immediately notified DFID and have taken actions including suspending staff and strengthening their financial management.

Date of last narrative financial report	31 December 2014
Date of last audited annual statement	31 December 2014

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

MST has been carrying out family planning outreach services for many years and their long experience ensures a reasonably reliable programme. PSI is expanding the numbers of FP outreach teams they are using from four to ten teams. The biggest risk is finding adequate public sector staff of the right cadre to train, hiring and training private sector staff, and continuing to collaborate closely with GoURT (which can slow progress even if the collaboration is good). Commodity risks remain but are managed to a great extent with the buffer stock. However, with the switch to Implanon NXT and roll-out of trainings, care needs to be taken to ensure that the transition is managed carefully to ensure Implanon classic is utilised and those already trained last year have also had Implanon NXT training. Further issues remain regarding Jadelle which has a global shortage, limiting choice between a three and five year implant. These risks are manageable. Work with CPAC, GBV and public sector provider training requires close collaboration with GoURT and sensitive engagement. This has been good so far and regional and district staffs appear to be enthusiastic and grateful for the assistance of the IPs. The national Government would be unlikely to change the FP outreach, CPAC or GBV guidelines but this remains possible as the CPAC guidelines have not been endorsed.

Risks internal to the project need to be managed effectively by DFID and IP’s. Of particular note, is the that MST continues to present contract management challenges and does not comply with the structures for reporting agreed during the inception phase, which will undermine the ability to conduct a proper comparative analysis of models and costs in different geographies, something which would be particularly valuable for the evidence base.

Outstanding actions from risk assessment

None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The transition between Phase I and II was not completely smooth as there were protracted negotiations with each of the IPs to finalise the contracts, as there was a lot to learn on how to set-up performance-based contracts. Neither IP lost staff and services were continued without a break.

The procurement process for vehicles took longer than expected. PSI received their seven vehicles in early 2016. However, delays in the procurement of five MST vehicles, due to the specification being difficult for the manufacturer to fulfil, have required MST to hire vehicles, which have been covered within the existing budget.

Performance of partnership (s)

Overall, the relationships between all partners seem to be positive. The evaluation team did not find evidence of unsatisfactory relationships either between DFID and the IPs or between the two IPs or their subcontractors (Intrahealth and Restless Development). Pointed questions revealed no current issues. DFID should be encouraged to continue its quarterly meetings with the IPs as these meetings appear to be building good relationships, ensuring a lack of duplication, and encouraging joint problem solving (e.g. acquiring access to the government health database DHIS-2).

MST has specific key performance indicators as part of the contract which has incentivised better collaboration and coordination with GoURT and other IP’s, communication and proactive problem-solving. MST has however, had issues with complying with financial reporting and a milestone-based contract, and has required part-payment of milestones. PSI has been more effective at managing it’s milestone-based contract, but both IP’s have performed well in terms of meeting their set milestones.

The partnership with GoURT and DFID could be stronger, as bilateral communications are limited given availability of GoURT. Coordination meetings do not occur regularly, but the IP’s have been requested to support the Government to get these structures to work.

Asset monitoring and control

Both MST and PSI have asset registers at their regional and central offices that are up to date. DFID has procured motor vehicles for both implementing partners. They all have a mechanism for monitoring in place and there are log books for recording distances. Both MST and PSI have fleet management systems which ensure vehicles are efficiently utilised. Each organisation has identified potential vendors to be servicing their vehicles in their regional offices and bills are sent to the central offices.

Both IP’s could improve on their commodities stock management from different sources.

G: CONDITIONALITY (½ page)

Update on partnership principles

Not directly applicable to this programme. However, the assessors have made the following consideration in light of the principles and the fact that the programme works closely with Government.

The programme does not fund Government directly, but supports Government initiatives. This programme supports increased GoURT commitments to the rural poor of Tanzania, especially women. Through One Plan II (to accelerate reduction in maternal and newborn deaths) and Big Results Now the GoURT has increased a focus on underserved areas to deliver on its commitment to reducing poverty and meeting the Global Goals. There has been no evidence of corruption and human rights abuses within this programme, and the rights of poor people are protected. Support to women and girls rights to access FP, CPAC and GBV services is also aligned to the commitment to support human rights. The regional scorecards assessing progress on reproductive, maternal, newborn and child health are no longer being used visibly, but the GoURT are working towards enhancing domestic accountability. The scorecards may not be a priority for the new Government; however there have been strong signals at relevant policy fora that accountability in healthcare is high on the agenda as shown by the recent restructuring of Medical Stores Department and Muhimbili National Hospital.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

FP and CPAC continue to have a strong evidence base with huge public health impacts, as outlined in the business case.

DFID is in the process of commissioning an external data quality assessment for both IP’s, who already conduct internal DQA’s (not yet finalised). DFID is particularly concerned regarding double-counting of clients and ensuring that the number of services are additional to GoURT capacity.

In addition to the monitoring of the log frame, the evaluation team spoke to beneficiaries (see box), examined the main clinical incident (at MST funded by another donor), spoke to other IPs and donors to get a full picture of the FP situation in Tanzania, followed the continued difficulties with misoprostol for CPAC, looking at how much it costs to reach youth (although no full answers yet), examining and contrasting both FP outreach models, healthcare provider pay scales and whether there are problems, carefully examining the new GBV work in order to learn and modify the programme, looking at GoURT data sources and monitoring the IPs success in accessing it, a close look at the economy, efficiency, and effectiveness of both models, and assessing stakeholder collaboration in the SRH sector in Tanzania overall.

DHS 2015 data was not available for this Annual Review. The results should be published by May 2016.

Box. Beneficiary feedback: Naomi / One member of the evaluation team followed one woman through the entire process from arrival at family planning outreach to leaving with her preferred contraceptive method. Her name was Naomi; she was 32 years old and had five children between the ages of 15 years and [a baby of] 4 months. / During individual counselling, the health provider explained to Naomi the different family planning methods. Naomi insisted on receiving an three-year implant (Implanon). Her choice was made because her husband had allowed her to get an Implanon and no other method and she was frightened to go against his decision. In an interview after she had received her implant, Naomi told the team that she would be beaten if her husband found out that she had gone contrary to their agreement [to get that particular implant]. She added that her husband does not have any problem with her use of family planning when a child is younger; the problems begin after the baby stops breast feeding. This is because her husband believes that a woman should get another baby just after she stops breastfeeding. “Men here believe that women should have babies until they run out of ovaries” she added with laughter. / Finally, Naomi shared her story about her previous family planning experience and how many times she was beaten by her husband because she was not conceiving after having their fourth child. She was [secretly] using injectable contraception which enabled her to space her pregnancy for six years before having her fifth child. “For those six years [when I did not get pregnant], I have been beaten, locked out, having several meetings with my in-laws and parents; not to mention how many times my husband threatened me that he was going to get another wife.” She finally decided to have another child because things were getting out of control. “Many women would like to use family planning or have fewer kids, but it is not possible here. Men also need to be educated about family planning for this to happen”, Naomi ended.

Finally, this AR was done in close collaboration with the Reproductive Health Commodities Security Annual Review so both reviews informed the other. Here, the DKT warehouse operations and costs were examined as well as whether the buffer stocks have lowered project risks (they have).

Going forward, it is recommended that joint monitoring visits are conducted with both IP’s during the year and at annual review stage, to allow for learning and peer review to enhance programme quality.

Monitoring progress throughout the review period

The programme team have: had quarterly review meetings with both IP’s; conducted two field visits during the last year; and spoken directly to beneficiaries to learn about the progress of the programme. Observations have been used to improve the quality of programming, particularly in how the needs of beneficiaries are met, commodities management and health worker training. Joint IP review meetings facilitated by DFID have also been fruitful in supporting IP’s in bottlenecks on larger technical, operational and policy issues. This has facilitated collaboration. DFID has also been kept updated and shared learning on developments with other development partners and IP’s through relevant fora, including technical meetings, donor groups and working groups.

Changes to logframe indicators/milestones, including reasons for the change
Original indicator	Revised indicator	Reasons for the change
Outcome indicator 1: CYPs		Do they need ‘resetting at end of Year 1’? Evaluators decided no need.
Outcome indicator 2: new acceptors	IPs using different definitions: PSI is ‘never used’ (minus condoms) or MST is ‘not used in the last three months’ (matching the MSI partnership)	MSI wants to continue using its own MSI definition. / DFID to follow up with MSI to see if there can measure both to enable comparisons.
Indicator 1.4 Client satisfaction	IPs using different definitions: MST uses ‘were you satisfied with the service received?’ PSI asks ‘would you recommend a friend?’	Ok to have different definitions as long as it is clear in the logframe and subsequent assessments and comparisons. There may be respondent bias with either of these questions anyway.
Indicator 2.1 a) Number; and b) Per cent of facility visits that MST makes where CPAC equipment and supplies are monitored and recorded	2b) not required	a)Change to ‘number ‘ rather than %. / Cut 2b) altogether as difficult to measure.
Indicator 2.3 Number of women accessing post abortion care (through this programme of support)	MST still working with GoURT to determine where to train and deliver services. / DATA SOURCE QUERY	Redistribute MST numbers to latter years; access to DHIS-2 also required (although PSI managed to give data)
3.1 Number of GoURT healthcare providers trained LAPM/LARCS with 80% of those government certified (with supervision)	3.1 Number of GoURT healthcare providers trained LAPM/LARCS certified (with supervision)	IPs will train as many providers as they judge necessary to achieve 100% in post.
Indicator 3.2 Number of women accessing FP services in public sector facilities	DATA SOURCE QUERY	Baseline not yet determined. MST has given figures but no figures from PSI. Evaluators have determined baseline and finalised milestones.
Indicator 4.1 Proportion of services to clients aged under 20 through the outreach programmes	Proportion of family planning services to clients aged under 20 through the outreach programmes [PSI: and numbers of referral coupons redeemed into public sector facilities]	Make both changes to master logframe; note that PSI will be delivering two kinds of data in future for this indicator.
Indicator 4.2 Number of programme staff (public or private) specifically trained to work with or provide information, education, or family planning services to adolescents under 20		Reset milestones and change logframe.
Indicator 5.1 Proportion of services to clients that include GBV care	Number of survivors receiving post GBV services	Change logframe and set milestones (which are not targets).
5.2 Number of public (80%) and private providers trained with 80% with good competency assessed in post trainee follow-up	5.2 Number of public (80%) and private providers trained [with 80%-CUT] with good competency assessed in post trainee follow-up	Same as 3.1
Indicator 5.3 Proportion of GBV survivors referred for clinical and non-clinical services	Number of GBV survivors referred for clinical and non-clinical services	Change logframe and set milestones (which are not targets).

Team & Field Visits. The evaluation team was made up of Carol Bradford (Team Leader) and Dan Whitaker (Economist); participation from DFID included Lisha Lala (Health Advisor), Jane Miller (Human Investment Team Leader), Suse Matamwa (Programme Manager), Lesley Miller (Commercial Advisor) and Tom Allan (Deputy Director). The team visited Njombe with Marie Stopes Tanzania and saw outreach at two sites (Ilembula and Chalowe). With PSI, the team visited Dodoma and saw one hub (Makole) , two spokes (Kikuyu & Chamwino), and outreach (Iringa Mvumi) services. In addition, the team visited the RMO and DMO at each field site. Finally, the team visited DKT and MSD in Dodoma. In Dar, the team met with RCHS staff, USAID, Engender Health, DKT, Pathfinder, UNFPA, MSD, as well as all IPs and their partners. The team were unable to meet directly with KfW or DANIDA, but the DFID team have kept in touch regularly. NOTE: At the next AR, the team should also meet with Dr Winani (Safe Motherhood) and Grace Malini (GBV).

ACRONYMS
AMO	Assistant Medical Officer
AGOTA	Association of Gynaecologists and Obstetricians in Tanzania
CHAI	Clinton Health Access Initiative
CIP	Costed Implementation Plan
CPAC	Comprehensive Post Abortion Care
CYP	Couple Years of Protection
DALY	Disability-Adjusted Life Year
DFID	UK Department for International Development
DHIS	District Health Information System
DMO	District Medical Officer
DANIDA	Danish International Development Agency
DQA	Data Quality Assessment
DRCHCo	District Reproductive and Child Health Coordinator
EC	Emergency Contaception
FP	Family Planning
GoURT	Government of the United Republic of Tanzania
IUCD	Intrauterine Copper Device
LAPM	Long Acting and Permanent Methods (of Family Planning)
LARCs	Long-acting and reversible contraceptives
LF	Logical Framework
M&E	Monitoring and Evaluation
MOHCDGEC	Ministry of Health, Community Development, Gender, Elderly and Children
MSD	Medical Stores Department
MSI	Marie Stopes International
MST	Marie Stopes Tanzania
MVA	Manual Vacuum Aspiration
PAC	Post-Abortion Care
PMDUP	Preventing Maternal Deaths from Unwanted Pregnancy
PSI	Population Services International
QTA	Quality Technical Assessment
RCHS	Reproductive and Child Health Services
RD	Restless Development
RH	Reproductive Health
RMO	Regional Medical Officer
GBV	Gender-Based Violence
TDHS	Tanzania Demographic and Health Survey
UNFPA	United Nations Population Fund
VCT	voluntary counselling and testing
VfM	Value for Money