Annual Review - Summary Sheet

Title: Pro-Poor Growth (PPG) Programme 2011-2016.
Programme Value: £13.5m		Review Date: Sept 2014
Programme Code:	Start Date: Nov 2011	End Date: 31 Dec 2016

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A	A	A
Risk Rating	M	H	H

Summary of progress since last review:
The PPG programme is on track and continues to deliver appropriate financial and technical support to agribusiness with innovative and inclusive business models, which is helping to improve access to financial and business development services for Zimbabwean agribusinesses. To date, over 100,000 economic opportunities have been created through the provision of over 9,500 loans and grants to beneficiaries in the Zimbabwean agribusiness sector.

The 2014 review has been conducted internally, with fewer resources than last year’s midterm evaluation. This year’s review concentrated on i) assessing results achieved over the review period; and ii) considering how the logframe could be improved to better capture and communicate the programme’s benefits. This review summarises progress over the last year, and recommends areas of possible work to better target some PPG activities.

A budget extension was approved in September 2014 for the provision of an additional £2.5m (to December 2016) to expand and scale up two components of the PPG, in line with 2013 annual review recommendations:

- A total of £2.1m has been budgeted for Technoserve to: i) support earlier stage innovation; ii) attract more qualified applicants to the existing Agro Innovation Zimbabwe (AIZ) competition; iii) address client growth constraints and DFID compliance risks by strengthening AIZ clients’ financial management systems and controls; and iv) the inclusion of a direct link to the DFID-funded Zimbabwe Microfinance Wholesale Facility (ZMWF) in order to increase the impact that ZMWF has in terms of access to finance for rural farming households
- An additional £400,000 has been approved to expand ZMWF activities in areas including: i) provision for intensive Microfinance Institution (MFI) skills training; ii) the roll out of an internationally recognised Management Information System (MIS) to ZMWF’s beneficiary MFIs; and iii) additional recapitalisation of the facility in order to increase the size of its loan portfolio.

Summary of recommendations from last year’s annual (mid-term) review and responses:
Recommendations that remain relevant from last year’s annual review have been addressed or are in the process of being addressed, the exception being that programme components have not undertaken formal gender audits. In early 2014 DFID worked with Technoserve (implementing partner for the AIZ component) to develop a proposal (including plans for gender audits) that would address the overarching lack of gender focus across the PPG. At the same time Technoserve responded to the 2013 annual review recommendations by developing a proposal to extend in duration and scope their existing AIZ programme. Given the limited time left on some of the PPG components (and thus limited time for the gender strategy to have an impact) as well as a finite budget for these two competing activities, it was decided to proceed to implement the AIZ extension proposal instead of attempting to retro fit ‘corrective’ activity across the PPG such as gender audits. The AIZ extension does however have a strong gender focus, including a focus on addressing the reasons why fewer women owned businesses and business with activities benefitting women in particular have applied to the existing AIZ programme.
For further details on this and other recommendations, please refer to the summary appended to the annual review.
A. Introduction and context

Outline of the programme
DFID Zimbabwe’s Pro-Poor Growth programme (PPG) was approved in November 2011 with a budget of £13.5 million up to December 2016 to (i) provide support to rural businesses with grants and loans and the provision of business development services; and (ii) increase access to affordable finance for the economically active poor, with a particular focus on empowering women. The programme is being delivered through four interventions, as set out in Table 1.

Table 1: Summary of the four components of DFID Zimbabwe’s Pro-Poor Growth programme
	Activities	DFID funds / (Total budget) / US$mn[1]	DFID period of funding / (Total period)	Implementing partner/s	Other funding
Africa Enterprise Challenge Fund – Zimbabwe window (AECF)	Provides grants and loans to support innovative business ideas that impact agribusiness and financial services value chains to catalyze sustainable and inclusive growth in Zimbabwe.	8.25 / (28) / DFID = 29% / All funds go through Alliance for Green Revolution in Africa.	Dec 2011 – Dec 2015 / (2011-2017)	KPMG IDAS	Australian Aid Program, Swedish International Development Agency, Soros Economic Development Fund
Agro Initiative Zimbabwe (AIZ)	Provides grant funds and technical assistance to businesses to encourage innovative ideas in agriculture and agro-processing	2.5 / (2.86) / DFID = 89%	Dec 2011 Dec 2016 / (2011 – 2016)	Technoserve	Delta Corporation, Irish Aid
Zimbabwe Agricultural Development Trust (ZADT)	Provides loans and technical assistance to financial institutions to stimulate on-lending to agricultural market intermediaries that benefit small-scale farmers	3.3 / (35.798) / DFID = 9.2%	Dec 2011 – Dec 2015 / (Started 2010. No fixed end date.)	SNV, Independent Secretariat	Danish Development Agency / (DANIDA), Ford Foundation
Zimbabwe Microfinance Wholesale Facility (ZMWF)	Provides loans and technical assistance to micro-finance institutions (MFIs) to stimulate on-lending to the MFIs’ clients. Promotes development of legislation and regulations to support micro-finance. Supports mainstreaming of HIV/AIDS and gender issues into MFI business models.	6.6 / (8.3) / DFID = 80%	Dec 2011 – Dec 2015 / (Started 2011. No fixed end date.)	ZMWF, HIVOS	DANIDA, German Development Agency(GIZ), HIVOS
[1] Exchange rate of £1 = US$1.65 has been used throughout.

Zimbabwe experienced a 50% decline in GDP between 1998 and 2008, caused in large part by a significant deterioration in the business climate. This culminated in the abandonment of the domestic currency in 2008. At the same time, Zimbabwe experienced the steepest fall in its Human Development Index ranking of any country, falling from 130 out of 174 countries in 1998, to 173 out of 187 in 2011. In spite of a return to positive growth following currency reform in 2008-9, the business climate remains extremely challenging. Key constraints include ongoing financial sector instability and an uncertain regulatory environment (discussed in more detail below).
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Outcome	Improved access to financial and business development services for agricultural value chain actors, Small Medium and Micro Enterprises (SMMEs) and entrepreneurs.

Indicator(s)			Milestone 2 / 31/12/2013	Milestone 3 / 31/12/2014	Target / 31/12/15[2]
1	No. of economic opportunities created (cumulative)	Planned	42,659	54,214	60,645
		Achieved	91,483 / AECF = 280,987 x 0.26[3] / AIZ = 12,418 x 0.89 / ZADT = 26,928[4] x 0.092 / ZMWF = 7,421[5] x 0.66	 106,010 (July 2014) / AECF = [No new data at time of review] / AIZ = 22,839 x 0.89 (August 2014) / ZADT = 34,512[6] x 0.092 (July 2014) / ZMWF = 14,322[7] x 0.66 (July 2014)	 106,010 / (07/14)
2	Average incremental income generated per new economic opportunity (US$ per annum)	Planned	41	66	241
		Achieved	US$9.12mn / 291,644 = US$31.3 / AECF = US$7.0mn / 280,987 / AIZ = US$2.12mn / 10,657	Not enough data available yet to estimate for 2014
3	No. of previously excluded beneficiaries with access to financial services	Planned	4,000	10,000	18,000
		Achieved	4,924 / AECF = 5 / AIZ = 19 / ZMWF = 4,898 / ZADT = 2	Estimated 9,587 (June 2014 for AECF, September for all others) / AECF = 5 / AIZ = 20 / ZMWF = 9,547 / ZADT = 15
[2] Performance assessed against targets set prior to approval of the addendum the PPG business case in September 2014 (which has extended portions of the PPG into 2016)
[3] Attribution calculated by taking total AECF economic opportunities x DFID’s proportion of funding. This calculation applies to results calculations for all 4 components throughout.
[4] Includes unverified beneficiaries.
[5] Includes repeat loans.
[6] Includes unverified beneficiaries. Of this number, 11,007 have been verified (7,000 to Dec 2013, and 7,594 for first seven months of 2014).
[7] Includes repeat loans.

Key points
- The PPG outcome level indicators aim to monitor the overall impact that the programme has had on the Zimbabwean agribusiness sector. To do this the programme monitors the number of loans that PPG partners have created as well as the average size and number of economic opportunities generated as a result of the provision of this credit. Outcome indicators 1 and 3 contribute directly to DFID Zimbabwe’s Operation Plan Headline results and “We Will” commitments respectively.
- Indicator 1 measures the number of economic opportunities created by the PPG programme partners. To date, 106,010 economic opportunities have been created, well above the 2014 target. This is largely due to two ICT projects, one supported by AECF and the other by AIZ, which have large numbers of beneficiaries (approximately 137,000 and 15,000 respectively).
- Indicator 2 measures the average incremental income generated per new economic opportunity. The 2013 actual ($31.3) fell short of its December 2013 target ($40) and not enough data is available yet to estimate the full 2014 actual figure. Missing this target is to some extent the flipside of exceeding the Indicator 1 target: ICT projects have many beneficiaries, but the estimated additional income that each receives is relatively small.
- On indicator 3, data measuring ‘number of previously excluded beneficiaries with access to financial services’ is not available. However, as at September 2014 the PPG programme had created 9,587 new loans / grants against a December 2014 target of 10,000. Using this metric (rather than number of previously excluded beneficiaries with access to financial services) this target is likely to be achieved.
- DFID’s support for AECF and ZADT is due to end in December 2015. As these components make some loans (as opposed to just grants) repayments on those loans will mean that they will have funds available to them post-December 2015. Both of these components also have funding from other sources, for example the AECF ZW is a multi-donor Fund and is due to operate to at least 2019.

Overall outcome score and description
Outcome indicator 1 has over-achieved, Outcome indicator 2 has under-achieved and Outcome indicator 3 is on track (although against a revised metric, as described above). The aggregate amount of economic benefit (as calculated by multiplying the number of economic opportunities by the average incremental income per economic opportunity) is significantly above what would have been achieved if all three targets had just been met. Outputs 1 and 2 have both scored a B while outputs 3 and 4 have scored an A and A+ respectively, which taking into account the weightings of each output (see later section) gives an overall outcome score of A.

Key lessons and actions
- DFID will need to decide if it is going to continue funding the AECF and ZADT beyond December 2015. (Action DM[8], first quarter 2015)
  [8] Dave Mollatt, DFID Zimbabwe Economic Adviser
- For a given amount of total economic benefit, it is arguably preferable for a larger number of beneficiaries to each receive a small benefit, rather than the other way around (a few beneficiaries receiving a large benefit). The economic benefit of all four components needs to be measured, not just AECF and AIZ. ZADT intermediary borrowers could be asked to provide information on contracts that they make with the beneficiaries. Clients of both ZMWF and ZADT could provide information on the interest payments they receive on the loans they make – a simple proxy for the (minimum) benefits their borrowers expect to gain from getting the loans. This will facilitate a more robust VFM analysis of PPG. (Action DM, first quarter 2015)
- A small number of companies have received support from more than one PPG component. In principle there is nothing wrong with this, but it would be helpful to have a central register of borrowers / grantees to which all the implementing partners have access. This will ensure that results reported by partners are not double counted. (Action DM and all partners, fourth quarter2014)
- Outcomes, outputs and indicators at the component level logframes do not always match up neatly with their equivalents in the overall PPG logframe. This should be rectified. (Action DM, first quarter 2015)
- It is not always helpful to have cumulative targets for indicators. This makes calculating annual ratios more difficult, and also means that the impact of one good or bad year of performance distorts annual review scores in the future. The logframe should be amended to reflect this. (Action DM, first quarter 2015)
- The milestones and reporting of the four components and the overall PPG are not all well-aligned. For example, PPG has overall annual targets due in December of each year; AECF produces its annual report for the period July to June; and DFID’s annual reviews of PPG are typically conducted around September / October. Consideration should be given to whether to action an early annual review in 2015. (Action DM, first quarter 2015)

Has the logframe been updated since the last review?
Yes, but it would benefit from further revision and clarification (as would the logframes for the components) in line with the recommendations set out in this annual review.

C: DETAILED OUTPUT SCORING

Output Title	Appropriate financial products accessible to value chain actors
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y. Increased from 30% to accommodate the reduction in weighting of output 3

Indicator(s)			Milestone 2 / 31/12/13	Milestone 3 / 31/12/14	Target / 31/12/15
1.1	No. of tailored financial products developed for and being used by target beneficiaries	Planned	2	3	4
		Achieved	2 ZMWF = 2, ZADT = 0	2 (August 2014) ZMWF = 2, ZADT = 0	-
1.2	Operational self-sufficiency (OSS) for ZADT and ZMWF	Planned	80%	85%	115%
		Achieved	ZADT = 40% / ZMWF = 21%	ZADT = 218% ( August 2014) / ZMWF = 54% (current position at September 14)	-

Key points
- Output 1 aims to monitor i) the extent to which PPG partners are offering financial products that are reflective of the needs of the broad agribusiness market; and ii) how efficiently partners are delivering these products. As such, this output tracks the number of new financial products introduced by the two credit providing components (ZMWF and ZADT) as well as their operational self-sufficiency.
- Regarding indicator 1.1, two new financial products have been developed to date, falling short of the 2014 target of three. ZMWF developed two new products toward the end of 2013, a loan targeting cassava growers, and a credit facility targeting dairy farmers. Both these products have been piloted and rolled out to a small number of beneficiaries in 2014. ZADT recently signed an agreement with Banc ABC to commence delivery of an asset leasing product (to finance assets such as farm vehicles and equipment): if, as expected, Banc ABC disburses funds against this leasing product before year end then the milestone for indicator 1 will be reached. Furthermore the ZADT Board has approved increasing the length (“tenor”) of their existing loan product from 2 years up to a maximum of 5 years) so creating a long-term loan product which in the Zimbabwean context is rare and so arguably a tailored ‘product’.
- Regarding indicator 1.2, ZADT has very significantly exceeded the milestone for operational self-sufficiency (OSS) but at the point of this review ZMWF had not. ZADT’s OSS has increased significantly from 2013 to 2014, principally as a result of a significant increase in the size of its loan portfolio (and so greater interest income) coupled with only a modest increase in operational costs. The large increase in loan portfolio has followed DANIDA’s commitment of an additional $20m to ZADT over the next 3 years. Although ZMWF’s OSS position is currently 54%, it is likely to achieve 100% OSS by the end of the year, exceeding the 85% milestone for 2014.
- The above points imply that both indicators may meet Milestone 3 by the end of this year. Nevertheless, in light of Indicator 1.2 missing the 2013 milestone, a score of B remains appropriate.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations from the 2013 PPG annual review, and progress made in addressing them, are considered in the addendum to this annual review.

Recommendations
- ZADT’s OSS now looks to be significantly higher than ZMWF’s, whose overall 2014 OSS is still expected to be low. However, ZMWF have reported that measured on a monthly basis, they will expect to reach an OSS of 100% by the end of December 2014. This should be monitored, so that remedial action can be taken if this does not happen. (Action DM and ZMWF, fourth quarter 2014)
- The output statement focuses on ‘accessibility’ of ‘appropriate’ financial products. The indicators do not capture this as effectively as they could. Measuring the number / volume of tailored financial products that have been taken up would be more useful: if that is high, it would demonstrate that the products are indeed appropriate and accessible. The logframe should be amended accordingly. (Action DM and all partners, fourth quarter 2014)
- Clarity needs to be provided on what is meant by a ‘tailored financial product’ has been ‘developed’, and what ‘operational self-sufficiency’ means. The logframe should be amended accordingly. (Action DM and all partners, fourth quarter 2014)

Output Title	Financial and technical support to agribusiness with innovative and inclusive business models
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y. Increased from 20% to accommodate the reduction in weighting of output 3

Indicator(s)			Milestone 2 / 31/12/13	Milestone 3 / 31/12/14	Target / 31/12/15
2.1	No. of agribusinesses supported and still operational 12 months post support	Planned	54	78	94
		Achieved	=< 26 / AECF =< 21 x 0.26 / AIZ =< 12 x 0.89 / ZADT =< 111 x 0.092	=< 30 (July 2014) / AECF = 21 x 0.26 (Sept 2014) / AIZ = 12 x 0.89 (Sept 2014) / ZADT =< 148 x 0.092 (July 2014)	-
2.2	Days of technical assistance provided to agribusinesses	Planned	840	1260	1260
		Achieved	AIZ = 1,140	AIZ = 1,560 (August 2014)

Key Points
- On Output indicator 2.1, prevailing economic conditions continue to act as a drag on uptake of funds, particularly for the AECF and ZADT. In light of this, the number of applications received from businesses and the number of beneficiaries selected remains 62% below target, and is likely to remain under target at December 2014.
- On Indicator 2.2 AIZ has provided 1,560 days of technical assistance to date, exceeding the 2014 target of 1,260 by 24%.
- In light of the fact that (i) Indicator 2.1 is under-performing by more than the Indicator 2.2 is over-performing; and (ii) Indicator 2.1 is a more relevant output indicator (Indicator 2.2 measures activity / input), this output scores a B overall.
- It has been suggested that uptake by banks from ZADT could be increased by the loans receiving (in part, at least) the benefit of a guarantee from a third party guarantor. However, introducing a guarantee does not reduce risk, it simply moves it to another party. If under the current arrangement the returns available to banks are too constrained to incentivise them to take risk, an alternative may be for ZADT to reduce the interest rate it charges banks, or to allow them to charge their borrowers a slightly higher rate. DFID Zimbabwe needs to work with ZADT and DANIDA to resolve how to increase loan uptake. The fund absorption study that ZADT has recently commissioned will be useful in addressing this question. (Action DM and ZADT first quarter 2015)

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations from the 2013 PPG annual review, and progress made in addressing them, are considered in the addendum to this annual review.

Recommendations

Although they are representative of the output statement, the indicators are quite process-focussed. A high score can be obtained simply by the supported businesses not becoming insolvent (although under the prevailing economic conditions this is arguably an appropriate indicator of success), and by AIZ providing enough days of technical assistance. It doesn’t measure the quality of any outputs – for example how well the supported companies are doing, or how effective the technical assistance is. DFID Zimbabwe should consider including indicators that are more output-focussed, and amend the logframe accordingly. (Action DM and all partners, fourth quarter 2015)

Output Title	Improved understanding of HIV/AIDS and gender mainstreaming issues by women clients of MFIs
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	11%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y. Reduced from 40% in line with reduced activity against this output

Indicator(s)			Milestone 2 / 31/12/13	Milestone 3 / 31/12/14	Target / 31/12/15
3.1	Proportion of victims reporting to police and/or traditional leaders	Planned	No target	45%	55%
		Achieved	Activity associated with this indicator has been discontinued since the last annual review (indicator is not clear and would not be possible to score).
3.2	Number of females in decision-making positions in the beneficiary enterprises	Planned	No target	60% (900 female clients out of 1,500)	70% (1,750 female clients out of 2,500)
		Achieved	Activity associated with this indicator has been discontinued since the last annual review (indicator is not clear and would not be possible to score).
3.3	Percentage of loan contracts financed through ZMWF projects signed by women	Planned	No target	60%	70%
		Achieved	67%	67% (July 2014)	-

Key Points
- The first phase of the evaluation of ZMWF completed at the end of 2013 found that the gender/HIV training delivered limited VFM. This activity has now been suspended. In light of this reduction in activity, the weighting of this output was reduced from 40% to 10%. At the same time a further 10% weighting was proportionately spread across the 4 outputs[9] to correct for the fact that the weightings previously added up to 90% and not 100%.
  [9] Output 1 (3%), output 2 (3%), output 3 (1%) and output 4 (3%)
- Even had data been available, Indicator 3.1 would have been of limited value. Increased – not decreased – reporting of abuse might actually represent progress, as it would demonstrate that victims were increasingly aware that abuse is not acceptable and also that they had increased confidence that the authorities would take reports seriously and act accordingly.
- Overall, these indicators do not effectively measure the output (and would not, even if data were available).
- Regarding indicator 3.3 the percentage of ZMWF’s micro-finance loan contracts going to women might look low by international standards, but it represents a significant improvement on the baseline of 0%, hence the output score of A.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations from the 2013 PPG annual review, and progress made in addressing them, are considered in the addendum to this annual review.

Recommendations
- This output – both the statement and the indicators – needs to be revised in light of the cancellation of the gender/HIV training. (Action DM and SC[10], Q12015)
  [10] Sam Coope, DFID Zimbabwe Social Development Adviser
- Gender and HIV remain key themes for development interventions in Zimbabwe. Following the cancellation of the ZMWF gender/HIV training, DFID Zimbabwe needs to determine the extent to which it now wants to require a new focus, perhaps with new results targets, on gender / HIV for the PPG components. (Action DM and SC, Q12015)
- Committing significant resources to ensuring PPG has an increased focus on gender / HIV when DFID’s support for most components ends next year might not be the most effective way in which DFID Zimbabwe can promote the gender/HIV agenda. Whether or not this is the case is likely to be informed by (i) how the PPG components are likely to develop once DFID support stops; and (ii) what other activities / plans DFID Zimbabwe has in this area. If, for example, ZADT and ZMWF are likely to continue for a number of years after DFID support comes to an end, this might present a good opportunity for DFID to influence their approach to gender/HIV over the longer term.
- At the very least, all the PPG components need to continue to report on how these themes are taken into account in their activities and in a way that provides some information that helps to track progress (e.g. providing gender disaggregated reporting). (Action DM and all partners, Q12015).

Output Title	Enabling environment for business and microfinance
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	23%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y. Increased from 10% to accommodate the reduction in weighting of output 3

Indicator(s)			Milestone 2 / 31/12/13	Milestone 3 / 31/12/14	Target / 31/12/15
4.1	No. of regulations supporting growth of the MFI sector	Planned	1	1	2
		Achieved	1 (ZMWF)	1 (ZMWF)
4.2	No. of MFIs borrowing from ZMWF that have attained operational self-sustainability	Planned	4 with OSS ratio above 85%	5 with OSS ratio above 90%	5 with OSS ratio above 100%
		Achieved	11	12 ( August 2014)

Key Points
- Output 4 monitors the effectiveness of the lobby and advocacy activates conducted by ZMWF. To do this the programme tracks the number of regulations that have been positively influenced by ZMWF over the life of the programme and the number of MFI beneficiaries that attain operational self-sufficiency over time.
- The theory of change for the ZMWF intervention assumes that concessional rates of funding to MFIs will lead to lower rates of interest on micro-finance products made available to beneficiaries. There seems to be limited evidence for this to date. However the intervention is in only its third year and such an impact is only likely to become clear in the medium to long term.
- Indicator 4.1 remains on track, with ZMWF contributing to the successful passing of the MFI bill in 2013.
- Regarding indicator 4.2, as of August 2014 12 of ZMWF’s clients were reporting operational self-sufficiency (OSS) above 90%. On the face of it this is good news, demonstrating significant sustainability. However, this is arguably only achievable because interest rates on micro-finance loans are currently very high – often 5-10% per month. These rates need to come down to improve the affordability of micro-finance.
- Indicator 4.2 doesn’t measure whether ZMWF’s clients have attained high OSS rates because of ZMWF’s support, or because all MFIs have improving OSS rates. And as explained in the first bullet point, it might be that high OSS rates are being maintained through charging very high rates of interest to poor people.
- A number of ZMWF’s clients are dependent for their survival on ZMWF’s funding. Where this is the case, we need to be particularly confident that these MFIs are having a material, positive impact. Otherwise ZMWF risks simply subsidising the survival of inefficient MFIs, when it might do better to channel funds through better-performing institutions. At the other extreme, five have OSS rates over 120%. In these cases, we need to be confident that ZMWF’s support really is incentivising these MFI’s to reach borrowers they otherwise would not, rather than just inflating their profits.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations from the 2013 PPG annual review, and progress made in addressing them, are considered in the addendum to this annual review.

Recommendations
- The impact that ZMWF’s activities have on their clients, and on the cost and availability of micro-finance products, needs to be measured more precisely. This could be done by measuring how ZMWF’s MFI OSS rates compare with other MFIs, and/or how the range and price of micro-finance loans that ZMWF’s clients offer to target beneficiaries compares with clients of other MFIs. This would help answer the question of whether ZMWF is lending to the MFIs who are likely to pass on the benefits of concessionally priced loans to end beneficiaries. (Action DM and ZMWF, first quarter 2015)
- The first phase of the ZMWF evaluation report that DFID commissioned last year leaned against requiring MFIs to cap their interest rates. However, banks on-lending funds borrowed from ZADT are subject to interest rate caps, so it is not clear why this would be inappropriate for ZMWF. DFID Zimbabwe should work with ZMWF and the authors of the evaluation report to further investigate this issue. (Action DM and ZMWF, fourth quarter 2014)
- An alternative way of incentivising MFIs to bring their rates down could be to ask them to bid for funding (for example, making a US$500,000 loan available every six months with a 2-3 year duration). The loan would be advanced at a concessional rate to the MFI that undertakes to lend the biggest proportion at the lowest rates to rural / women / business borrowers. DFID Zimbabwe should work with ZMWF to investigate this question. (Action DM and ZMWF, fourth quarter 2014)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
- Key cost drivers across the programme are the general costs of doing business in Zimbabwe, with the risks and uncertainty associated with this. Adverse movements in exchange rates and the cost of living have also been cited as significant cost drivers.
- For AECF, the average size of awards in the latest round has been significantly less than in previous rounds, largely because the independent investment committee took a much more risk averse view of beneficiaries. If this view prevails in future rounds, it raises questions about efficiencies and transactions costs over the six year period of this component.
- For ZADT, fund manager’s fees and other fees for SNV and HIVOS for the year to 2013 amounted to around US$520,000, over 100% of interest income. Staff and administration costs for the first eight months of 2014 are approximately US$460,000, but on a much bigger portfolio – so 46% of interest income: this represents improved VFM.

VfM performance compared to the original VfM proposition in the business case
- The business case assessed the value of money of PPG by estimating the costs and benefits of two components, AECF and ZMWF.
- The business case took an optimistic approach in estimating the likely benefits of AECF and ZMWF. Even after some sensitivity analysis, the business case projected an internal rate of return of 148% for AECF and of 115% for ZMWF (leading to returns on investment after ten years of more than 600% for each).
- Table 2 summarizes the costs and benefits of each of the four PPG components. No attempt has been made to discount costs or benefits. In addition:
  - On costs, funding for loans made by ZADT and ZMWF has not been counted as a cost, on the assumption that the money will be returned (although arrears have been counted as a cost). Because AECF’s loans are on very favorable terms (interest free), they have been counted as a cost.
  - On benefits, the numbers reported by AECF and AIZ have been used. In the absence of robust data on economic benefits created by ZMWF and ZADT, the gross interest paid on loans[11] made by the financial intermediaries (MFIs and banks, respectively) has been taken as a proxy of benefit. It should be noted that using the interest paid on these loans as an indication of the benefits will under-estimate benefits and should be viewed as the minimum benefit received.
    [11] As a beneficiary would not take out a loan unless they expected to benefit by more than the interest they expect to pay on the loan

Table 2: Costs and benefits 2011-2014 (total, not limited to DFID’s attribution; no discounting of costs or benefits) All data from August 2014 unless stated

	Grants disbursed / US$mns	Outstanding loans (ex-arrears) / US$mns	TA / training for clients / US$mns	Overheads / US$mns	Total spend / US$mns	No. of economic opps.	Total economic benefits / US$mns	Total economic benefits / total spend
AECF	3.768	6.275	0	2.510	12.553 / (inc. 6.275 soft loans,	280,987 / ( December 2013)	18.4 / ( December 2013)	1.47
AIZ	0.490 / (June 2014)	N/A	0.390 / (06/14)	0.692 / (06/14)	1.572 / (06/14)	22,839	2.95	1.88
ZADT	0.673 / (arrears,	8.989	0.461	1.995	3.129 / (exc. 8.989 loans,)	34,512[12] (July 2014)	1.498 minimum	0.48 minimum
ZMWF	0.458 / (arrears,	2.957	0.581	1.240	2.279 / (exc. 3.506 loans)	14,322[13] (July 2014)	2.025 minimum	0.89 minimum
[12] Includes unverified beneficiaries. Of this number, 11,007 have been verified (7,000 to Dec 2013, and 7,594 for first seven months of 2014).
[13] Includes repeat loans.

Assessment of whether the programme continues to represent value for money
- Table 2 cannot be regarded as a robust assessment of the various components’ VFM, rather it should be considered as a starting point for considering the VFM question. In particular, more work needs to be done in assessing the benefits accruing from the ZMWF and ZADT components.
- On the face of it their negative return implies poor value for money. However, it should be noted that these numbers are simply the aggregate interest payments received to date by ZMWF and ZADT. They are put forward as minimum economic benefits on the assumption that the borrowers must receive benefits at least as big as the size of the interest payments they have to make in order to make it worthwhile for them to borrow. The estimates represent a proxy for the benefit received by the end beneficiary and as such should not be used on their own to judge the return the two components are delivering.
- In aggregate, and subject to the caveats described above, Table 2 implies that the costs of these four components in total have been US$19.5 million against benefits of at least US$24.9 million (benefit cost ratio of 1.27). A significant portion of the PPG’s funding goes to AECF which shows the second highest net benefit in Table 2, suggesting that overall, PPG is delivering VFM, albeit at significantly lower levels than the optimistic forecasts in the business case.

Quality of financial management
- DFID disbursements to AIZ and ZADT have limited over the review period. No significant issues have come to light on their financial management more broadly. It is worth noting that over the last year ZADT has successfully transitioned from being administered by a fund manager to having a secretariat. When ZADT was first set up the trust did not have the technical fund management capacity to manage the fund on a day to day basis, a fund manager was hired to manage the fund. As the fund has grown significantly since 2012, a dedicated secretariat has been put in place consisting of 6 full time employees. The secretariat is responsible for all fund management and monitoring and results management activities and reports directly to the ZADT board.
- DFID’s last disbursement to the AECF was in January 2013, no further disbursements are planned for the AECF component. Although the AECF received an unqualified 2013 audit (for the entire AECF Fund across multiple windows including the Zimbabwe Window), they are currently in the process of reconciling their accounts for each window as there have been a number of incorrect accounting entries in recent years (for example, a large number of expenses from other windows have been posted to the General Window which now shows a large deficit). Donors have commissioned a financial due diligence of the AECF to independently verify the financial position on each window as a result of the poor financial management to date with the final report due on the 15th of January 2015.
- Financial management by ZMWF until Q2 2014 was not satisfactory. In light of this an informal performance improvement plan was set up involving bi-monthly financial meetings with HIVOS to address areas of poor performance. This included emphasis on accurate quarterly forecasting and improving the quality of quarterly narrative updates. The quality of both forecasting and updates has improved although there remains further room for improvement.

Date of last narrative financial report	AECF: 30/06/13 (updated narrative overdue, see point 2 under above heading. Report expected 28/10/14) / AIZ: 14/08/2014 / ZADT: 30/09/2014 / ZMWF: 05/08/2014
Date of last audited annual statement	AECF: 31/12/13 / AIZ: 31/12/13 / ZADT: 31/12/13 / ZMWF: 31/12/2013

E: RISK

Overall risk rating: High

Overview of programme risk
Overall risk continues to be high. This is largely driven by the operating environment in Zimbabwe, rather than the nature of the programme. Key risks include:
- Financial sector instability:, in particular in light of the prolonged liquidity shortages.
- Companies failing: Zimbabwean companies are producing at approximately 36% of what they are able to produce , raising concerns about their long-term sustainability. This risk is exacerbated for companies in the agricultural sector by potential adverse weather conditions in 2014/2015.
- Uncertain regulatory environment: ongoing uncertainty in policy-making (for example indigenisation policy) acts as a drag on investment.
- Political instability / interference: there is the ongoing risk of political instability in Zimbabwe, including political interference on project selection and execution.
- These and other principal risks are summarised in Figure 1.

Figure 1: Risk matrix summary
		IMPACT
		HIGH	MEDIUM	LOW
PROBABILITY	HIGH	Financial sector instability / Companies failing / Uncertain regulatory environment (indigenization policy requires clarification) / Political instability
	MEDIUM	Seizure of bank accounts / Over-optimism by DFID / IPs on timing and volume of results	Land disputes / Beneficiaries regard all donor funds as grants – don’t repay loans / Applicants misuse funds / Re-introduction of Zimbabwe dollar	Lack of good applications / Negative press
	LOW	Negative social /environmental impact / Theory of change wrong / Political violence / Breakdown in law and order / Fraud within IPs / DFID

Outstanding actions from risk assessment
- All implementing partners are aware of the importance of risk monitoring. They should continue to review risks on an ongoing basis, and maintain the adequate risk mitigation process.
- DFID and all the implementing partners should continue to discuss the risks that PPG is facing at each quarterly meeting if not more often.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The key PPG deliverables with milestone targets are captured within the output statements and measured against the output indicators considered above. Overall, PPG has scored on A on the extent to which output milestones have been met to their planned timeframes.

Asset monitoring and control
There are asset registers in place for three of the four components (the AECF programme uses KPMG assets and thus does not have an asset register). The ZADT register needs to be updated.

G: CONDITIONALITY

Update on partnership principles (if relevant)

DFID Zimbabwe undertook a country-level assessment of the UK Partnership Principles in July 2014. This confirmed the DFID policy that no UK aid should be managed by or be under the direct control of the Government of Zimbabwe using its own financial systems and procedures. We only provide direct support to other Governments when they commit to improving the management of public finances, tackling concerns about human rights abuses and corruption, and improving domestic accountability. The assessment highlighted shortcomings in all of these areas. The PPG programme is in line with this policy and does not use Government of Zimbabwe systems. According to the March 2014 Guidance Note, it is therefore not appropriate to undertake an assessment of the Partnership Principles as part of the design and monitoring of this programme.

The Zimbabwe country-level Partnership Principle assessment will be updated in summer 2015 and the outcomes will feed into ongoing management of this programme’s activities and risks. Going forward, experience and evidence generated through the PPG on the impact of policies such as land and empowerment will be fed into the country level assessment on an annual basis

H: MONITORING & EVALUATION

Evidence and evaluation

 AECF
- The AECF Zimbabwe window is adopting the Donor Committee for Enterprise Development (DCED) audit approach which by the very nature of a Challenge Fund relies on self-reporting by the recipients of AECF funding. AECF has and continues to embed the DCED process throughout and in 2015 will have a partial audit by the DCED on eight of its grantees. Independent verification studies on four grantee companies have been finalised to date and submitted to the funding donors. The results of these studies are taken into account by the Fund Manager when future grantee reporting is monitored, and the beneficiary models adjusted accordingly. A further six independent verification studies are being designed currently.
- The AECF produces a Portfolio Impact Report covering each calendar year (provided to all funding donors). As grantee results are independently verified, these numbers are accepted as verified by the DCED Standard.

AIZ
To date all results have been obtained through self-reporting rather than independent monitoring and/or verification.

ZADT
- The key result is the number of beneficiaries. Up to December 2013, only 7,000 out of 27,000 claimed beneficiaries had been verified as such. This has improved for the first seven months of 2014 during which time the majority of claimed beneficiaries were verified.
- To date all results have been obtained through self-reporting with no independent monitoring and/or verification. ZADT has however contracted an external consultant to independently verify the numbers of farmers that the value chain actors report to be associated with. The verification exercise will be done through sampling a representative number of at least 5% of the smallholder farmers.

ZMWF
ZMWF is currently undergoing a longitudinal impact assessment, phase 2 of which commences in October 2014. Phase 1 of the evaluation verified portions of the results reported by ZMWF, particularly around the operational self-sufficiency of a number of borrowing MFIs as well as ZMWF itself.

Monitoring progress throughout the review period
- The PPG programme is rated as medium risk in the overall DFID Zimbabwe programme portfolio and has been monitored as such. This has included quarterly technical partner meetings, quarterly field visits as well as informal monitoring through phone calls and emails with implementing partners and other donors.
- Recommendations from this annual review have been shared with the ZMWF evaluation team with a view to addressing these as a part of phase 2 of the ZMWF evaluation.
- The introduction of further independent monitoring/verification of the PPG results would be valuable. The appointment of an independent evaluation management unit by the AECF will support this process in the context of the AECF Zimbabwe Window.
- The review was carried out over a one week period in-country and a further two weeks’ worth of analysis and report writing. The review team consisted of Rob Probyn (Tem Leader) James Jowa (independent consultant) with support from the DFID Zimbabwe Office (David Mollatt, Angie Dhlakama, Nyasha Mayanga and Sam Coope) The review included technical meetings with all sub-programme managers, and field visits in Domboshawa, Goromonzi and Harare. The draft report was quality assured by the DFID Zimbabwe Results and Evaluation Adviser, the Deputy Head of Office and the Head of Office before sign-off by the latter.