Annual Review

Project Title: GOU/UN Joint Programme on Population in Uganda

Date started: December 2010	Date review undertaken: November 2013

Introduction and Context

What support is the UK providing?
DFID has committed to provide £30,000,000 for implementation of the Government of Uganda/UN Joint Programme on Population (GoU/UN JPP) over four years (2011-14).

What are the expected results?
The Goal of the GoU/UN JPP is to accelerate the onset of a beneficial demographic transition in Uganda between December 2010 and December 2014. The joint programme will support an expansion of the supply of, demand for and utilisation of family planning services primarily through the public sector, to increase reproductive health choice for women and accelerate reductions in fertility in Uganda. At the same time it will support improvement in safe delivery and other maternal health services, a bursary scheme for girls for secondary education and improve the policy environment to increase youth employment. Gender is mainstreamed throughout the objectives of the programme. / The programme, complemented by the DFID and USAID funded Accelerating the Rise in Contraceptive Prevalence rate in Uganda (ARC) programme[1], will contribute to a broader, transformative impact on the Ugandan economy, given the risks to economic and social development posed by the current rate of population growth and the opportunity of social sector savings from lower demands on public services. / The GoU/UN JPP and ARC programmes will contribute to enabling 1.1 million additional women (431,000 attributable to DFID) to voluntarily use modern family planning methods in Uganda and increasing the contraceptive prevalence rate by 2.5 percentage points per year. / DFID attributable planned outputs from the GoU/UN JPP by December 2014: / Fertility reduced in line with the choices of individuals and couples, especially young people. / 15% young people (10-24 years) with accurate information on family planning in the target districts; / 95 health centre IIIs and IVs providing youth friendly services in target districts; / 75% of health facilities in target districts without stock outs of pills, male condoms and injectables. / Prepared, protected and healthy mothers children and youth. / 1,000 girls retained in school through the secondary bursary programme; / 50% deliveries occurring in health facilities in the target districts. / An improved policy context for youth employment and opportunities. / 4 key policy documents developed on youth employment / An adequately resourced, coordinated and managed national population programme. / All target districts allocating and disbursing funds to population issues; / All target district development plans developed based on socio-economic, demographic and other data sources.
What is the context in which UK support is provided?
Uganda has one of the youngest and most rapidly growing populations in the world. With a total fertility rate estimated at 6.2 children per woman, the country’s population growth rate is currently at 3.2%[2]. The population is estimated at 35.4 million in mid-2013 with fertility rates higher in rural areas compared to urban areas at 6.8 and 3.8 respectively. Over half (53%) of Uganda’s population is younger than 15, well above Sub-Saharan Africa’s average of 43.2% and the world average of 26.8%. The resulting very high dependency ratio represents a major challenge for Uganda in the short and medium term. Due to population increases, Uganda’s real income growth per capita has been half its total national real income growth at about 3.4% during the 1990’s and 4% since 2000[3]. The high rate of population growth also creates strains on the country’s natural resources including arable land and public services such as health care. Unemployment and underemployment are serious concerns in Uganda, despite relatively high access to education. / Over 2 million women in the reproductive age group (34%) have an unmet need for family planning[4] and the supply of services needs to be complemented with activities to improve demand for services. About 44% of all pregnancies are unintended, and these account for the deaths of around 3,000 women every year[5]. The burden of unwanted pregnancy and its consequences disproportionately falls on poor women and adolescents. The Uganda Demographic Health Survey (UDHS 2011) found the teenage pregnancy rate to be 24% and that by 15 years of age 30% of young women have had sex and by 18 years of age it has risen to 72%; this suggests that any information on safe sex and family planning is needed early so young girls are able to make informed choices. Uganda’s maternal mortality ratio has remained relatively high decreasing from 505 in 2001 to 438 deaths per 100,000 live births in 2011. Although the proportion of deliveries taking place in health facilities is increasing at an impressive pace, the quality of care provided for deliveries is not able to maximise the opportunity to reduce maternal death rates. / In order to change its population age structure and reduce its dependency ratio faster, Uganda needs to accelerate the demographic transition, namely the shift from high to low levels of mortality and fertility. However, the potential benefits of the demographic dividend are not automatic. The supply of good quality family planning services is a key element to accelerate the pace of the demographic transition. Additionally, there needs to be a strong focus on human capital, with intensive investments in education, particularly girls’ education. Education transforms countries and societies as well as the lives of individuals and it has been shown that an extra year of quality schooling lifts a country’s annual economic growth by 1%[6].
[1] ARC jointly implemented with USAID to increase family planning choices through non-state service providers.
[2] Uganda Demographic Health Survey (2011) Uganda Bureau of Statistics.
[3] Ministry of Finance, Planning and Economic Development, Uganda: Population Factors and National Development, January 2010
[4] Uganda Demographic Health Survey, 2011
[5] Calculated from the Uganda Demographic Health Survey 2011 estimates. As per the UDHS 2011, Uganda experiences 438 maternal deaths per 100,000 live births. This implies that around 6,600 maternal deaths take place per year in Uganda, and 3,000 deaths represents around 44% of all maternal deaths.

## Section A: Detailed Output Scoring
Output 1: Fertility reduced in line with choices of individual and couples, especially of young people
Output 1 score and performance description: B / Output 1 has three indicators of which two met expectation and one moderately did not meet expectation. 1.1 and 1.3 are regarded as fundamental, whereas the evidence of 1.2’s impact if delivered is less clear, and so Output 1 has been awarded a score of B, “Outputs moderately did not meet expectation”. The discrepancy in the sample frames (8 districts in 2012 and 15 in 2013) is also noted, since it raises questions about whether the baseline and achieved rates are comparable. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2013- Dec 2013) Achieved[7] (Jan 2013- Nov 2013) / 1.1 Proportion of young people (10-24 years) with accurate information on use of contraceptive pills, male condoms and emergency pills in target districts. N/A 10% 6.1% / ( 9.6% males – / 3.5% females) / 1.2 Number of HC IIIs and HC IVs providing youth friendly services in target districts. 4 (HC IV) / 0 (HC III) / ( UNFPA report 2011) 10 (HC IV) / 60 (HC III) 20 (HC IV) / 60 (HC III) / 1.3 Proportion of health facilities in target districts without stock-outs of 3 most commonly used contraceptive methods (pills, male condoms, depo-provera) in the past 3 months. N/A 70% 74.5%
Summary of activities / It is not possible to make any judgment on whether knowledge levels have increased because the 2013 Mid-Term Review (MTR) was conducted in 15 districts while last year’s evaluation focused on 8 districts. An analysis of the MTR data for the 8 districts shows knowledge levels at 6.2% suggesting an improvement from 1.3% in 2012. However one of the 8 districts is skewing the data and once that is excluded then the level of knowledge is 3.6%. There is also a large difference in knowledge levels between boys (9.6%) and girls (3.5%), and in girls under 14 the score was 2.3%. Because the UDHS shows that 30% of young girls will have had sex before 15 years of age increasing the levels of knowledge in young girls should be a priority. The programme reached 485,239 of the 1,527,214[8] young people (10 -24 yrs) in the 15 districts through various channels including community outreaches, health facilities and schools. / Healthy Choices is a radio programme which is transmitted only in the 8 districts and yet the MTR found very little difference in the knowledge levels between those districts receiving the radio programmes and those in the 7 districts that are not. Whilst there are undoubtedly other factors involved, it is important to be asking about the added value of this radio programme. A challenge identified during the MTR and that continues to date is that IEC materials targeting young people are not available in local languages at health facilities, schools and in the community; it is imperative that the production and dissemination of the IEC materials in local languages is treated as a priority by JPP. Overall the approach to this output is fragmented with no apparent joined up strategy across the 15 districts. It is very unlikely that this indicator will be met by 2014, if the JPP does not revise its strategy for increasing knowledge in young people, particularly girls. / The number of health facilities providing Youth Friendly Services (YFS) has increased. However there are serious concerns about Youth Friendly Corners (YFC) including the lack of a gender sensitive approach and the poor supervision of YFC at health facilities including the use of peer educators who often do not have a sufficient level of knowledge to provide accurate information. It is therefore very unlikely that the YFC are contributing to increasing knowledge particularly on sensitive topics. In addition there are concerns about the cost–effectiveness and sustainability of this model. / 1.3 Good progress has been made on this indicator as the milestone for 2013 was achieved. Part of the success stems from district health offices (DHOs) redistributing supplies within districts to where supplies are needed. However there is now a problem of excess supplies of certain family planning commodities. There are two supply chain management systems for reproductive health commodities including family planning supplies; the National Medical Stores (NMS) for the public sector and the Uganda Health Marketing Group for the Non-government organisation (NGO) and private sector. These two systems should be aligned and UNFPA whose mandate is ensuring security of FP commodities should take responsibility to facilitate this process. / Progress against recommendations in the 2012 Annual review: / There were 4 recommendations in the last annual review: work has started on 2 (formative research on messages and channels to reach young people and capacity building for health care workers) but has not been finalised. There has been little progress on generating evidence on the relevance of YFC and discussions with NMS/ MOH on reviewing the commodity kits for lower level health facilities to include Long Term Family Planning Methods have not taken place. / Recommendations: / 1. The JPP should radically review its approach to increasing knowledge in young people to develop / a joined up approach between UN agencies and across the 15 districts, including: / finalising formative research to understand the messages and channels for reaching young people at scale with accurate information by June 2014. This should include a review of the impact of the Healthy Choices radio programme. / the production and distribution of IEC materials in local languages by January 2014. / 2. Spending on YFC should be discontinued. Carry out retrospective operational research including Value For Money (VFM) on the various models of YFS/YFC, and use this information to inform future practice on delivering effective YFS in the 15 districts and nationally by June 2014. / 3. UNFPA should work with NMS to improve the quantification and coordination of the procurement of family planning commodities in Uganda and discuss the benefits of distributing long term FP methods to lower level health facilities. / Impact Weighting: 50% / The review found no reason to change the impact weighting. / Risk: Medium / The review found no reason to change the risk rating.
Output 2: Prepared, protected and healthy mothers, children and youth
Output 2 score and performance description: B / Output 2 has two indicators of which one met expectation and the other moderately did not meet expectation. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2013- Dec 2013) Achieved / (Jan 2013- Nov 2013) / 2.1 Number of girls retained in school through the secondary bursary programme 0 / (2010) 1000 1000 / 2.2 Proportion of deliveries occurring in health facilities in the 15 target districts 31% / (HMIS 2010/11) 46% 30.2 %
Summary of activities / 2.1 Since August 2012, 1,000 girls have been enrolled and retained in the bursary programme in 8 districts; 854 of these are in secondary schools and 146 enrolled into Business Technical and Vocational Educational Training Institutes (BTVET). Since the programme started 40 girls have dropped out and been replaced by girls at the same stage of their schooling. Girls that have completed their lower level education have been linked to other organizations to enable them continue with higher education. / 2.2. Data available from the HMIS up to October 2013 shows that 69,431 deliveries (30. 2%) have taken place in public facilities in the 15 districts since January 2013. Extrapolating for the remainder of the year would give approximately 36% coverage, below the JPP target of 46% for 2013. Some of the main challenges around increasing institutional deliveries have been the lack of skilled health workers, the poor attitude of staff towards clients and the indirect costs women incur delivering at health facilities. To increase institutional deliveries, UNFPA supported the training of a total of 253 midwives, 34 of whom have already been deployed to health facilities. In addition, WHO is training health workers on Basic and Comprehensive Emergency Obstetric Care. The distribution of Maama kits to promote safe deliveries and encourage women to deliver in health facilities unfortunately did not take place because of significant delays in the procurement process. In addition there are serious concerns about creating demand for health facility deliveries when insufficient attention is being placed on the quality of health facility deliveries and an effective referral system to deal with the 15-20% expected complication rate. / Progress against recommendations in 2012 AR: / There were 3 recommendations. One has been completed (linking girls graduating from lower secondary to other organisations to continue their higher education); work has begun on the second (WHO started work on training Health Care Workers on Emergency Obstetric Care); and a review of the functionality of the ambulances has not been done. / Recommendations: / 1. Whilst trained human resources are critical, reducing Maternal and Neonatal Mortality is more complex and the JPP strategies need to be more joined up between the UN agencies. Provision of support to health facility deliveries should be organised along a continuum of care to ensure that quality basic and comprehensive emergency obstetric services are provided at the appropriate levels of the health system according to WHO standards. In addition through the continuum of care seek opportunities to integrate FP services to increase uptake of family planning / 2. No further procurement of Maama kits should take place until MOH reaches a decision concerning a revised and sustainable strategy for the provision of Maama kits. / Impact Weighting: 20% / The review found no reason to change the impact weighting. / Risk: Medium / The review found no reason to change the risk rating.
[7] Government of Uganda / UN/ JPP Mid Term Review ( September 2013). Centre for Sustainable Development. Aberdeen.
[8] Government of Uganda / UN/ JPP Mid Term Review ( September 2013). Centre for Sustainable Development. Aberdeen.

Output 3: An improved policy context for youth employment and opportunities
Output 3 score and performance description: C / Output 3 has one indicator which substantially did not meet expectation. Although no policies have been published it is expected that 2 will be finalised in December. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2013- Dec 2013) Achieved / (Jan 2013- Nov 2013) / 3.1 Number of key policy documents developed on youth employment. 1 4 0 / Summary of activities / Following revisions to Output 3 to focus on strategic interventions at national level, the programme set out to support the development of the following policy related documents: National Action Plan on Youth Employment (NAPYE); Labour Market Needs Assessment (LMNA); National Labour Force Survey (NLFS); and the Labour Market Information System (LMIS) framework report. While progress has been made towards finalising these reports none of the reports had been completed at the time of the review. / Both the NAPYE and the LMNA are in draft and will be finalised in December 2013. / The NLFS has been carried out in 2 sectors (hotel and food processing), analysis is underway and the draft will be available by the end of the year. / The LMIS framework report will be released in January 2014. / Recommendation / Activities in 2014 should focus on ensuring functionality of the LMIS which can be benchmarked with implementation in other countries e.g. Rwanda. In addition, the LMIS data should be used to generate future training areas and youth employment creation projects. / Impact Weighting: 10% / The review found no reason to change the impact weighting. / Risk: Low / Given the change in the indicator the risk rating has been revised to low.

Output 4: An adequately resourced, coordinated and managed national population programme
Output 4 score and performance description: B / Output 4 has two indicators one of which met expectation. At the time of the review, the data required to assess the second indicator was not yet available from the Ministry of Local Government and Ministry of Finance. / Progress against expected results: / Indicators Baseline Milestone / (Jan 2013- Dec 2013) Achieved / (Jan 2013- Nov 2013) / 4.1 Proportion of target districts allocating and disbursing funds to population issues N/A 80% Data not available at time of review / 4.2 Proportion of district development plans developed based on socio-economic, demographic and other data sources N/A 80% 87%
Summary of activities / 4.1 According to the MTR, a review of the Budget Framework Papers (BFPs) showed that all the districts had allocated funds to population issues. However the BFP does not provide data on funds actually disbursed and spent on population issues as it is a budgeting tool. This data can only be obtained following the annual local government assessments that produce the Annual District Performance Reports (ADPRs) and data from the Ministry of Finance Planning and Economic Development. Therefore to effectively assess progress on this indicator will require an analysis of the 2012/13 ADPRs and district expenditure reports. / 4.2 This indicator has been met and cannot change in the life time of the project as the DDPs are five year plans. The JPP through the Population Secretariat has initiated work to support the districts in the development of DDP IIs that will inform the National Development Plan II (2015-2020). To enhance use of data at the district level to feed into national planning, a centralised district database to collect aggregated data was established in the 15 districts. However the database functionality is not yet optimal as districts continue to grapple with low human resource capacity, lack of resources for collection of data from primary sources and lack of standardised data collection tools for the different sectors. / Recommendations: / 1. Carry out retrospective analysis of the annual district performance reports for years 2011/12, 2012/13 by March 2014 to assess whether funds allocated to population issues were released and spent. / Impact Weighting: 20% / The review found no reason to change the impact weighting. / Risk: Medium / The review found no reason to change the risk rating.

## Section B: Results and Value for Money.

1. Progress and results
Has the log frame been updated since last review? Yes / Indicator 3.1 was revised to reflect the change of strategy under output 3 from district based to national level interventions. Following this year’s annual review, the following revisions are recommended: / Include an indicator under output 1 on number of new users of FP, a key output of the programme; / Include an indicator under output 3 to reflect new activities in 2014 to establish a functional LMIS. / Change indicator 4.2 because it has been met and will not change over the next year as DDPs are five year plans. Therefore, it is recommended to replace this indicator with a new indicator to assess the utilisation of data in the district planning process in relation to the functionality of the databases. / Overall Output Score and Description: B / While the programme has performed better in 2013, it was insufficient to meet expectation and therefore has been scored B (moderately did not meet expectation). / 1.2 Direct feedback from beneficiaries / The Assistant Commissioner, Reproductive Health is pleased with the JPP programme because it provides coordinated support from the UN in the 15 districts and he would like the programme to expand to other districts. The same message was received from the Population Secretariat team. Overall the support by JPP is welcomed as an improvement to the UN’s normal working practice as they said they could see the UN working together in these districts which they said was not happening in other districts. The Population Secretariat team did say that it was hoped that any future programme would be streamlined as currently the JPP has separate planning and coordination structures which increases transaction costs for Government colleagues. Indeed the review confirmed a disjointed approach in some aspects of programme implementation. / In talking to midwives from two health facilities they were happy with the support provided through the JPP but felt more could be done. One example given was the need to expand electrification so that the level IV health facilities could store blood as post- partum haemorrhage a major cause of maternal mortality. A clearly committed midwife working in a level III health facility complained that she has not been trained to provide long term FP methods and yet many of her clients wanted to use these methods. The midwives in a facility with a YFC had not been trained to provide YFS and felt that they should have been; this is a missed opportunity to build upon the existing knowledge of health professionals on how to address the specific ASRH needs of the youth and to have a joined up approach to YFS. / There was some criticism from the Ministry of Health of UNFPA’s approach to YFS as it was felt that their exclusive focus on YFC was undermining the MOH’s more systematic approach to scaling up the provision of YFS. / 1.3 Summary of overall progress / There has been improvement in many of the indicators in 2013 but insufficient progress to meet expectations. Good progress has been seen in the reduction in stock- outs of FP commodities in the districts but there have not been significant increases in number of health facility deliveries. In addition, there has been limited and disappointing progress in increasing the knowledge of young people on ASRH. While a lot of progress has been made towards producing the relevant youth and employment policy documents, these were still in draft stage at the time of the review. / This is a complex programme with an ambitious goal and purpose and there is a risk of a fragmented approach which does not deliver results in either family planning or maternal health. By re-focusing the programme in 2013 on activities that would deliver results, there has been an improvement in delivery of results. The challenge for the programme in the final year is to maintain the momentum in those areas where the programme has been successful whilst revising the strategies to increase the quality of health facility deliveries and the proportion of young people with accurate information on ASRH. This would be improved through a more joined-up approach to implementation by the UN agencies.
1.4 Key Challenges / Increasing Knowledge on ASRH in young people / The level of knowledge was very low (6.1%). Indicator 1.1 measures the knowledge of youth on 3 family planning methods: the pill, the condom; and emergency contraceptives. This is not the common indicator used and including the emergency contraceptive pill makes it difficult to use traditional methods of communication to transmit the message such as the radio which is one of the major methods of communication. It means using one to one communication but that needs qualified and confident peer educators. In reviewing the Healthy Choices programme it was noted that the emphasis was on safe pregnancy (programme 10) which is off-course desirable, but the focus of JPP is to reduce teenage pregnancy and so we would argue that the sessions on family planning are coming too late at programme 20. What seems clear is that the JPP approach to increasing knowledge is fragmented and not joined up across the 15 districts. A revised strategic approach between the UN agencies across the 15 districts on how they intend to increase knowledge in young people is urgently required. / Youth Friendly Services / The JPP is supporting three different models of delivering Youth Friendly Services (YFS): community outreaches using trained peer educators; youth friendly corners in schools and health facilities; and training existing health workers to provide adolescent friendly services in health facilities through routine care. The MOH policy is to systematically train health workers building on their existing skills and knowledge which has the added value of improving the attitude of health workers to all clients. However there have been challenges with lack of IEC materials and the training and follow up of health workers providing YFS. One major concern in using the peer educators in YFC is often their level of knowledge is not sufficient to provide accurate knowledge on these relatively sensitive issues. It is therefore recommended that support to YFC should be stopped and the resources should be used for scaling up YFS through training health professionals. In addition the approach to YFS and YFC should be reviewed including costing which can then be used to inform future practice nationally. / Quality Maternal Health Services / Encouraging mothers to deliver in health facilities without concurrently increasing the quality of those services and the development of an effective referral system has some inherent challenges. The evidence is overwhelming that a high maternal mortality ratio (MMR) is an indicator of a weak health system. Science in Action[9] argues that to reduce the MMR, support should be provided through a continuum of care[10] (CoC). The programme support to training midwives, providing equipment and training health workers is good but rather fragmented and more should be done to provide an integrated package of support to strengthen the CoC, including FP; otherwise the programme is unlikely to have any impact on reducing maternal and neonatal mortality. / Evidence based decision making / There is insufficient use of data to analyse the successes and challenges in different districts and from that develop district focused approaches. District planning and analysis provides the opportunity to focus on the successful strategies and stop activities that are not adding value. Taking a district approach should also provide opportunities for a more joined – up approach based on comparative advantage between the UN agencies across the 15 districts.
1.5 Annual Outcome Assessment / The overall purpose of the GoU/UN JPP is that “national, community, cultural and issue-based leadership are managing the acceleration of a downward trend in population growth”. The log frame contains two indicators against which this purpose is assessed. / Outcome indicator 1 Baseline Milestone / (Jan 2013- Dec 2013) Achieved / (Jan 2013- Nov 2013) / Contraceptive prevalence rate (modern methods: women of reproductive age) 25.6% / (2011) 31% To be determined through annual panel survey of 2013. The results are likely to be published in 2014. / Although results were not available for 2013 the most recent annual panel survey 2012 shows that the CPR has increased to 30% from 25.6 % in 2011. This is a reasonable increase and shows that nationally progress is being made. / Outcome indicator 2 Baseline Milestone / (Jan 2013- Dec 2013) Achieved / (Jan 2013- Sept 2013) / Teenage pregnancy rate 24% / (2011) 21% No data to access progress / The Uganda Demographic Health Survey (UDHS 2011) shows that 24% of teenagers had begun childbearing, a decline over time from 43% in the 1995 UDHS. There is no new data available to measure this indicator for 2013.
[9] Science in Action: Saving lives of Africa’s mothers, newborns, and children. 2009
[10] Continuum of Care “a core organising principle for health systems that emphasises seamless linkages between health care packages across time and through various service delivery strategies”.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / In 2013 the planned budget was $24,974,097 of which DFID contributed $14,626,761. The most up-to-date report on allocations and expenditure is only available for DFID funds and shows an expenditure of 77% as outlined below. / Table 1: JPP Funds Allocation from DFID and Utilization as of September 2013 and disbursements for Oct-Dec 2013 / UN Agency Work Plan Budget Jan-December 2013 - USD Total funds available for Jan Sept 2013- USD Estimated expenditure Jan-Sept 2013* % spent out of total funds available for Jan-Sept 2013 Funds Disbursed for Oct-Dec 2013 / WHO 2,287,142 1,319,957 1,065,325 80.7% 1,804,566 / UNFPA 7,733,630 5,898,099 4,050,473 68.7% 1,835,531 / UNHCR 386,133 338,385 165,133 48.8% 47,748 / UNICEF 4,118,792 4,110,232 3,774,972 91.8% 8,560 / WFP 280,903 237,139 237,139 100% 43,764 / ILO 224,780 186,684 114,776 61.5% 38,096 / IOM 200,000 166,658 96,147 57.7% 33,342 / UNHABITAT 155,000 97,171 54,285 55.9% 57,829 / UN WOMEN - - - - - / TOTAL 14,626,761 12,354,326 9,558,250 77.4% 3,869,436 / *Inclusive funds committed in contracts for services, etc. / 2.2 Key cost drivers / At the time of submission of the report, data on key cost drivers was not available but an analysis is being conducted to provide an understanding of this aspect of the programme. / 2.3 Is the project on-track against original timescale: No Indicators 1.1 and 2.2 are critical to the achievement of Outputs 1and 2 and therefore the purpose but they have not been achieved. It is looking very unlikely that either indicator will be met by the end of the project unless radical actions as recommended by this review are taken by the JPP.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project. / Whilst the previous Annual Review requested information on evidence of the relevance of the Male Action Groups (MAGs) and YFC to achieving the goal of the programme; and formative research on the messages and channels used to use young people with information on ASRH, the review did not find evidence that this has been done systematically. Despite efforts to improve the operationalization of the Male Action Groups through training and supervision, there is no evidence that this has contributed to expected results. On the other hand it appears that the number of groups has in fact decreased and challenges cited at the end of last year continue to plague the initiative. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation / review commissioned by the JPP took place in September 2013 and some of the data was used in this annual review, although we have significant concerns about the reliability of the survey sued. In addition, an end of programme evaluation is set to take place in 2014 and progress is under way to initiate the process.
4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The GoU/UN JPP programme document contains a set of risk categories against which the overall programme risk can be determined and scored. The team reviewed the risks and is recommending a change to one of the risks. / Description of risk Status and mitigating action Rating / UN agencies are unable to work closely together and cohere around shared objectives The UN agencies are doing well at joint planning and field supervision, however implementation remains very agency focused and not always based on comparative advantage. This is resulting in a fragmented approach which is affecting performance. The JPP needs to move to joint implementation through a joined – up approach across the districts, if outputs are going to be met by 2014. Probability: medium / Impact: high / Recommendation: keep rating as above. In the final year of programme implementation, strengthening the joined up approach to implementation will need to be a priority to ensure achievement of projected milestones. / Participating GoU and national institutions lack implementing capacity There are 8 key sectorial ministries and 2 government agencies involved in the GoU/UN JPP. As co-chair of the steering committee, government is involved at the highest level in decision making for the programme. However weak district capacity and structures pose a challenge to coordination on the ground. District capacity building activities and field monitoring visits are conducted to improve implementation at the district. Probability: medium / Impact: medium / Recommendation: keep rating as above as activities to increase the capacity of the districts to deliver quality services are intensified / Government commitment to programme aims is reduced Government has consistently shown high levels of commitment to the programme and continue to participate actively at steering committee meetings and in joint monitoring visits. Probability: low / Impact: high / Recommendation: keep rating as above / Increasing demand for family planning cannot be met due to supply-side funding gap DFID and USAID together fund approximately 80% of the contraceptive commodities for the country and over the last years there has been a decline in stock outs of key contraceptives though some supply chain management challenges still exist as there are now excess stocks of certain commodities. There is a need to ensure that the health care workers have the right skills to administer FP methods, particularly at the lower level health facilities. Probability: low / Impact: high / Recommendation: keep rating as above as efforts are being made to build the capacity of health workers to provide particularly long term family planning methods.
4.3 Risk of funds not being used as intended / The GoU/UN JPP funds are disbursed directly to and managed by UNFPA, the Administrative Agent. Funds are made available to the participating UN agencies for specific activities through the UN “pass-through” funding modality. The financial accountability for use of the funds is the responsibility of each participating agency. A detailed risk assessment is undertaken to review and identify strengths and weaknesses in the partners’ capacity for financial management and to establish appropriate financial modalities, procedures, and assurance activities. The programme has a full time Financial Specialist, who works closely with UNFPA’s International Operations Manager to monitor financial spend of recipient agencies’ and conduct systematic follow-up to previous quarters’ (and previous audit) recommendations. / Funds are disbursed to implementing partners, in accordance with an annual work plan approved by the Steering Committee and more detailed quarterly work plans, which are agreed with the participating UN agency. Usually advances are only given on a quarterly basis, with a requirement that accountability for the previous period needs to be submitted before the next tranche can be disbursed. Following disbursement a programme officer is assigned to each partner to monitor progress and expenditures. Field monitoring visits with government officials and beneficiaries also provides a checking mechanism to ensure funds are being used for the intended purpose. / 4.4 Climate and Environment Risk / Improved population planning has the potential to make a significant contribution to more environmentally sustainable development. While the design of the GoU/UN JPP does not focus explicitly on aspects of the National Population Policy related to environmental management, through output 4 there is an opportunity to provide better data, evidence and analysis around the impact of the growing population on the rural and urban environment and the environmental benefits of improved population planning. In addition, DFID ensures that approval of work plans takes into account and incorporates opportunities for environmental benefits where possible. Summarised below are the potential detrimental environmental impacts of the programme and the corresponding mitigating action. / Potential detrimental environmental impact Mitigating action / The release of carbon dioxide through transport of the outreach teams and support supervision teams The programme has procured vehicles with modern fuel combustion systems. / Waste generated as a result of used contraceptive commodities and supplies used for deliveries Health care workers have been trained in infection control and medical waste management and disposal.

5. Value for Money
The review team faced significant challenges in accessing information on expenditure broken down to the level of detail and in the format required, to allow a comprehensive assessment of value of money. In this section, we only present our conclusions based on the (incomplete) information availed to us, and in some instances are unable to make conclusive statements on value for money. / 5.1 Performance on VfM measures / 5.1.1. Economy / Procurements of FP commodities / UNFPA procures through the UNFPA procurement services branch at the headquarters. Procurement of contraceptives in Uganda is based on quantification and procurement plans agreed by the members of the national Reproductive Health Commodities Security Committee. Using PIPELINE software, annual supply plans are prepared for all the contraceptives including quantities required, shipment schedule, and costs for the products and handling charges. In 2012, with funds from DFID, UNFPA spent £2,067,527 (approx. US$3.28 million) on procurement of FP commodities. Of this amount, 92% was spent on commodities and supplies and 8% on handling fees. In 2013, about £941,887 (approx. US$ 1.23million) was spent on contraceptives, of which 84% was spent on commodities and 18% on handling fees. The proportion of funds spent on handling fees seems to have increased significantly between the two years. UNFPA advises that handling fees comprise 10% of the cost of the product (cost, insurance and freight) for warehousing and distribution and 2% for National Drug Authority verification and testing; however, based on the information available for 2012 and 2013; the handling charges appear to not be aligned with this guideline. / Analysis of trends in prices at which UNFPA has procured commodities shows that efficiency gains have been made through procuring commodities at lower prices. Specifically, basing on price reductions for only 3 commodities (see Table below) there was a total saving of US $ 2,711,107 made in 2013. / Commodity 2012 Price / US $ 2013 Price / US $ price change / US $ Quantity purchased in 2013 2013 Saving / US $ / Implanon 16.837 8.852 7.98 300,032 2,395,725 / Male condom 0.031 0.028 0.00 92,930,400 312,728 / IUD 0.396 0.361 0.03 77,000 2,653 / 2,711,107 / In the past two years, although procurements handled by UNFPA are considered to be for the public sector, all FP commodities procured by UNFPA are delivered to UHMG (and not NMS). UHMG which is largely accessed by the NGO sector seems not to have direct distribution channels for the public sector. It appears that FP commodities procured by UNFPA may not necessarily go to the public sector. / Procurements of Mama Kits / An expanded kit was requested by MOH and the procurement process for the expanded kit, was handled by UNICEF. Approx. $2.8 million was spent on purchasing 95,472 kits. Having moved from the basic kit to the expanded kit, the unit cost of procuring mama kits has increased from $7.5 to $37 per kit (5 times higher). The actual cost of each kit is $29.84, and approx. $7.2 per kit is the cost for freight and handling (bring the total cost of a kit to $37). The cost of $37 per kit excludes the 7% indirect costs charged by UNICEF. Overall the process of procuring mama kits appears not to have been competitive and efficient, but this may be largely due to the specifications set for the expanded kit. For example, the Child Passport was also printed in China and branded products instead of less expensive alternatives were used which makes the cost of the kit (including its freight) significantly higher. / Administrative Costs vs. Service provision / For the JPP programme, administrative and programme management costs comprise the mandatory 7% that goes to each UN agency headquarters and the costs relating to office and administrative operations of the programme for each UN agency and the implementing partners. For 2012, approximately 79% was spent on service delivery, 12% on administrative and management costs and 9% on indirect costs that go to each UN headquarter. For 2013, we are only able to provide insights based on data from only 3 UN agencies which show that about 87% was spent on service delivery, 7% on administrative and management costs and 6% on indirect costs. Without a full picture of spending by all UN agencies, these results are inconclusive. A more complete picture will be presented in the main VFM report if the information becomes available. / 5.1.2. Efficiency / This concerns the transformation of money into outputs. The key efficiency measures are ratios of costs of delivering services to outputs from those services. / Family Planning services / FP services are delivered through 2 different approaches namely: outreach camps by NGOs (Marie Stopes Uganda and Reproductive Health Uganda) and routine services and camps through the district hospitals. UNFPA supports the provision of services by NGOs through outreach camps (with different durations for the camps run by the two NGOs) while WHO works directly with the districts to increase uptake through district hospitals. (Data required for the calculation of costs of the different modes of services delivery are still not available. As such, it is difficult to comment on efficiency of service delivery. / WHO spent a total of $31,391 and $77,572 in 2012 and 2013, respectively to run camps by district staff. There is considerable differences between the cost per new user in 2012 (i.e. $23.3) and that for 2013 ($64.8) which may suggest inefficiencies in implementation. Information from Marie Stopes Uganda shows the most efficient delivery approach to be outreaches. Unit costs for camps run by WHO compare with the unit costs for services delivered through a static clinic run by MSU. / Cost per new user / (US $) Cost per CYP / (US $) / Institution Approach 2012 2013 2013 / WHO Camps at public health facilities 23.3 64.8 Not available / RHU Camps at public health facilities Not yet available Not yet available / MSU Camps at public health facilities 15.6 2.6 / MSU Clinic 64.2 21.8 / MSU Community 5.8 21.5 / Important to note is that comparisons with overall sector achievements for 2012/13, as reported in the Annual Health Sector Performance Report, show that there may be no significant differences between the 15 JPP districts and other parts of the country, as far as availability of FP commodities is concerned. / Contraceptive use has the potential to have impact through preventing unintended pregnancies which, in turn, avert unplanned births, abortions, miscarriages and maternal deaths. As was the case for the 2012 annual review, detailed expenditure on the different components of the JPP is not readily available. Further, information on Couple Years of Protection (CYP) was requested, and is apparently not readily available and cannot be easily computed because it is not routinely collected. Without actual expenditure on FP commodities and CYP data for 2013, we are unable to assess or comment on the value for money for family planning service delivery through the GoU/UN JPP. / Institutional deliveries / No information is available yet to assess the cost of training of midwives and other activities relating to support for institutional deliveries. There seems to be no significant difference between the 15 JPP districts and other parts of the country, as far as increases in proportions of women delivering at health facilities is concerned. / Girls’ Bursaries / A total of 1,000 girls have benefitted from the programme since 2011 in eight JPP districts. The MTR reports that for 2012 the average annual cost per girl educated through the bursary scheme is £599 (which translates into £2,397 for 4 years per girl). Figures reported for this review indicate an average annual expenditure of £546 per girl in 2012 and £537 per girl in 2013. These reported figures seem reasonable and may be value-for-money. The World Bank points out that an extra year of secondary school increases a girl’s potential income by 15 to 25%. In addition, benefits of educating girls include: faster economic growth, food security, reduced infant and child mortality, among others. Estimation of the full economic impact of keeping girls in schools longer required more analysis that is beyond the scope of this review. No useful literature has been found for comparison purposes. / Male Action Groups, Youth Friendly Corners & Youth Friendly Services / A total of $170,872 has been spent on forming and supporting MAGs in 15 districts over the past 2 years ($65,445 in 2012 and $105,427 in 2013). The unit cost of establishing one YFC at a school is estimated at $5600 while the cost of establishing one at a health facility is $17,232. On the other hand, a total of $77,412 was been spent on training health workers on youth-friendly health services, in 2012 and 2013. Considering the lack of clear outputs associated with both MAGs and YFC, their value-for-money can only be estimated at the end of the programme. / 5.1.3. Effectiveness / This concerns the extent to which the programme is planning to do the right things to achieve its objectives, and delivering on its plans, and is largely discussed above. / Overall, the Programme has been effective in ensuring a steady supply of FP commodities in the country and has made reasonable achievements on the supply-side that relates to service provision. On the other hand, the demand side is still lagging behind, evidenced by poor performance on Output 1.1 (on knowledge of contraceptives) and moderate performance on increasing uptake of FP services. Given the fragmented nature of the programme design, there has been less effectiveness on some components of the programme, especially relating to Output 3 and 4. / 5.1.4. Equity / There seems to be significant difference between the 15 JPP districts, in terms of achievement of targets for key programme indicators. Factors responsible for such differences have not been documented, analyses relating to equity have not been undertaken, and the UN agencies seem not to paying any attention to equity issues. Some of the differences between districts may be as a result of the different implementation approaches used by the different UN agencies. At implementation level, division of labour based on districts, rather than on comparative advantage, accentuates the differences between districts, and seems to contradicting the “delivering as one” principle. / Awareness of efficiency / Although a few stakeholders interviewed made remarks about the adequacy of funding and the efficiency with which funds were released to different agencies, none of them raised the need to maximise achievements within existing resources. The fragmented nature of service delivery within the 15 districts is one of the indicators of a lack of awareness of efficient delivery of services/implementation of activities. Further, the UN JPP is not routinely tracking output data on key outcomes, such as Couple Years Protection, and no attempts have been made by the programme to estimate cost per CYP, as an indicator for monitoring programme efficiency. On the other hand, however, some degree of awareness of efficiency is demonstrated in carrying out joint monitoring visits, and joint planning meetings. / 5.2 Commercial Improvement and Value for Money / There seems to be improvement in procuring some of the FP commodities at lower prices in 2013, which resulted in reasonable savings. Other than that, there is no evidence of efforts to improve implementation or operational efficiency or value for money. The lack of critical output, outcome and expenditure information suggests that very little attention is paid to improving efficiency and value for money. Lastly, administrative costs (including the indirect costs for UN headquarters) are high and are significantly contributing to overall poor value for money of the programme. / 5.3 Role of project partners / Since the programme started there has been progress in the UN working together and “delivering as one”. This can be seen in joint planning and joint field visits to the districts but joint planning does not immediately translate to a joined up approach to implementation based on comparative advantage. The JPP approach to implementation remains agency focused, not based on comparative advantage and fragmented; it is critical that in 2014 the JPP takes the next step and moves away from “Business as Usual” to joint implementation across the 15 districts. It is difficult to assess the inefficiencies associated with the fragmented approach to implementation, but the team believes that potentially joint implementation of activities (with each agency focusing on their comparative advantage) is likely to enhance efficiency in service delivery and reduce inequalities between districts and deliver more results. / 5.4 Does the project still represent Value for Money: Partially. / Processes are in place to increase VFM but there is no collection of relevant data. Further analysis may be possible in the main VFM report if additional information that was requested becomes available. / 5.5 If not, what action will you take? / We recommend that re-programming be done to modify activities around the male action groups and youth corners to achieve high impact for the programme through other activities. / Specific VFM Recommendations: / 1. Joint implementation of activities (with each agency focusing on their comparative advantage) is likely to enhance efficiency and effectiveness in service delivery and reduce inequalities between districts. / 2. Tracking of performance should include Couple Years of Protection, and not just the number of new FP users. Further, estimation of impact of FP services on reduction of unintended pregnancies should be undertaken at end of programme evaluation. / 3. All UN agencies should be asked to routinely report their expenditure by Programme Output, to allow quick reviews of value for money that enable cost-per-output ratios to be developed. This should be made compulsory for 2014, in order to inform the End-Term evaluation of the JPP.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The performance of the programme has improved in 2013 but not sufficiently to meet the agreed milestones for 2013. The challenges for the programme in the final year is to reduce fragmentation, maintain the momentum in those areas where it has been relatively successful whilst revising the strategies to increase the quality of health facility deliveries along a continuum of care and increase knowledge in young people. The annual review team is convinced that fragmentation would be reduced by a district-focused approach building on what is working and with the JPP looking explicitly for more joined-up strategic approaches to implementation across the 15 districts. In addition to the VFM recommendations (section 5) the following actions are recommended to improve the performance of the programme. / 1. Before preparing the 2014 annual work plan carry out analysis of each district using the MTR results identifying successes and challenges, developing joined up strategies between the UN agencies and across the 15 districts that build on what is working and stop activities that are not producing results. 2. The JPP should radically review its approach to increasing knowledge in young people to develop a joined up approach between UN agencies and across the 15 districts. / 3. Spending on YFC should be suspended. Carry out retrospective operational research including VFM on the YFS/YFC and use this information to inform future policy and practice in the 15 districts and nationally by June 2014. / 4. Provision of support to health facility deliveries should be organised along a continuum of care (CoC) to ensure that that quality basic and comprehensive emergency obstetric services are provided at the appropriate level of the health system in all the 15 districts by the end of the programme. / 6. Carry out retrospective analysis of the annual district performance reports for years 2011/12, 2012/13 by March 2014 to assess whether funds allocated to population issues were released and spent.

8. Review Process
The review team was made up of Marilyn Mc Donagh and Charlotte Zikusooka and took place from the 4th to the 22nd of November. It has been difficult to obtain information and data especially as the week the 2 consultants were working together most of the JPP were on field visits which meant no follow up meetings were possible to further interrogate issues. / Methodology / Structured key informant interviews were conducted at national level with Ministry of Health officials, the population secretariat but it was only possible to hold one general meeting with all participating UN agencies. In addition Marilyn Mc Donagh visited Mubende district where interviews were conducted with district health officers, reproductive health focal persons, and health care providers at public health facilities. / The team reviewed documentation relevant to the programme including: / The programme document; / Log frames; / Progress reports 2011, 2012; / Mid Term Review 2013; / Uganda Demographic Health Survey 2011; / Annual Panel Review 2012 ; / Annual Health Sector Performance Report 2012/2013; / Guidelines YFS.