Type of Review: Annual Review

Project Title: Support to the International Centre for Trade and Sustainable Development (ICTSD) 2012-14

Date started:	Dec 2012	Date review undertaken: Dec 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Over a three year period (2012-14), DFID will provide a grant of up to £5.1 million to the International Centre for Trade and Sustainable Development (ICTSD). Up to an additional £50,000 will be allocated for independent monitoring and evaluation. Our support constitutes around 30% of ICTSD’s funding, other key donors being Sweden and the Netherlands. Our support will build on the results achieved by DFID support to ICTSD since 2007. / ICTSD is a Geneva-based independent think-tank and knowledge broker. It plays a critical role in providing information and impartial, evidence-based advice to developing countries, to help them to understand developments in international trade, formulate effective trade policies, and negotiate more successfully in trade talks. Along with contributions from other donors, the funds will contribute to ICTSD’s core costs. They will be used for monitoring events in international trade which affect developing countries, carrying out independent research, and sharing information with partners.

What are the expected results?
Over the period of our support we want to see increased participation in regional and global trade by developing countries. This is essential to drive economic growth, create wealth and jobs for men and women. ICTSD’s work will significantly contribute to this outcome. / Our funding will allow ICTSD to continue and expand its established work-streams which will contribute to delivering the following results : / Increased and more effective participation by developing countries in international trade negotiations, / Better food security for developing countries; / Developing countries better able to advance their development priorities in aid for trade and multilateral trade negotiations; / Developing countries better able to innovate, and access technology; / Domestic policies that promote climate change mitigation and adaptation; / Trade rules that promote the sustainable use and management of natural resources; / Policy makers, negotiators, and others are better able to determine and advance their own interests in regional and international trade policy processes.

What is the context in which UK support is provided?
Trade has the potential to be a major contributor to growth in developing countries. But poor countries are not trading enough to deliver the growth they need to reduce poverty. Despite having 12% of the world’s population, the 48 Least Developed Countries (LDCs) account for only 2% of the $22 trillion-worth of annual global trade. / The challenge facing poor countries in breaking into trade has become more complex over the past decade. The Doha Round, which was meant to solve a host of issues simultaneously – including tariffs and market-distorting subsidies in agriculture – has stalled and there is now no prospect of agreeing a “big bang” trade deal on this model. Part of the explanation for the failure of Doha lies in the rise of the emerging powers. This has made the governments of mature developed economies less willing to extend trade concessions multilaterally to developing countries, which are increasingly seen as competitors. This is driving a trend towards bilateralism – that is, pairs or groups of countries making deals amongst themselves that exclude others. Reinforcing this trend is the fact that the international private sector now sees tariffs as less of an obstacle to trade than “behind the border” barriers – particularly domestic regulations – and it is more straightforward to tackle these bilaterally than multilaterally, particularly given the growth of independent regulation in recent years. / The 21st century trading system is further complicated by the fact that a significant proportion of world trade – some 60% - now takes place either within firms or amongst firms that are part of the same supply chain. There are huge opportunities here for developing countries, but it is crucial that they create the right policy environment to facilitate engagement in these global value chains. / Poor countries need to be able to follow and understand these profound changes to the international system if they are to formulate effective policies and negotiate beneficial trade agreements. But most developing countries lack experienced trade policy analysts and negotiators, have weak institutions that fail to build collective memory, and struggle to access and assimilate external information, expertise or research.[1] This lack of access to information hinders their ability to design informed trade policies and strategies, and to engage successfully in trade negotiations. Buying-in this expertise is not often an option for cash-strapped developing countries. Their ability to influence negotiations in organisations such as the Geneva-based World Trade Organisation (WTO) is therefore significantly compromised[2] [3]. / To try to overcome this, a number of developing country coalitions have been formed, such as the Asian Developing Members and the G-33. However, even within these coalitions, small developing countries still find themselves marginalised if they do not have an informed and persuasive line of argument based on current information and rigorous evidence-based research. / Removing all “trade distorting subsidies” in agriculture could lift up to 26 million people out of extreme poverty (under $1 a day) and 90 million people out of moderate poverty (under $2 a day).[4] Conclusion of the Trade Facilitation Agreement in Bali (Dec 2013) is expected to add $10 billion a year to the GDP of sub-Saharan Africa[5]. But few LDCs have enough skilled staff in Brussels or Geneva to monitor all the negotiations in which they have an interest[6]: the WTO often runs four or more parallel committee meetings per day[7]. This means that: / LDCs find it difficult to follow the evolving policies and actions of richer trading partners, and then feed this information back to policy makers in capitals. / Developing countries find it hard to hold richer countries to account if they breach internationally agreed rules. / Proportionally fewer complaints about unfair trading practices are submitted by small or poor members at the WTO.[8] / Complaints that are submitted are often made only at high level[9], whereas trade policy is largely shaped in earlier, lower-level technical discussions. / At WTO meetings, poorly formulated requests for policy discussions from developing countries have resulted in these being excluded from the agenda[10].
[1] Woods, N. and Deere Birkbeck, C. (2009), Manoeuvring at the Margins: Constraints Faced by Small States in International Trade Negotiations, London: Commonwealth Secretariat; Rollo, J. (2009), ‘Helping Developing Countries Negotiate Bilateral Agreements: a proposal for an Advisory Centre on RTA’, Multilateralising Regionalism, Richard Baldwin and Patrick Low (eds), Cambridge: CUP
[2] Stiglitz J. (1999): ‘Knowledge as a Global Public Good’, in Global Public Goods: International Cooperation in the 21st Century, published for the UNDP, Oxford University Press.
[3] Birkbeck C.D. & Harbourd M. (2011): ‘Developing Country Coalitions in the WTO: Strategies for Improving the Influence of the WTO’s Weakest and Poorest Members’, Global Economics Governance Programme, Working Paper 2011/63, Centre for International Studies, Oxford University.
[4] Anderson, Cockburn and Martin (2010): ‘Would freeing up world farm trade reduce or increase poverty?’
[5] CEPII (Centre d'Etudes Prospectives et d'Information Internationales, the French research centre for international economics), 2011
[6] Khor, M. (2009), ‘Analysis of the Doha Negotiations and the Functioning of the WTO’, Geneva: South Centre, http://www.unep.org/south-south-cooperation/exchangeplatform/Portals/116/ministerial/MK%20paper%20Analysis%20of%20the%20Doha%20Negotiations%20and%20the%20Functioning%20of%20the%20WTO%2025.11.2009.pdf
[7] Chifamba, T. (2007), ‘Multilateral Trade Negotiations: How Sensibly Must African Countries and Trade Negotiators Stand?’, Occasional Paper No. 7, Harare: The African Capacity Building Foundation (ACBF), pp.3-4, http://lencd.com/data/docs/7-Multilateral%20trade%20negotiations_how%20sensibly%20must%20African%20.pdf
[8] Nordström, H. (2003), ‘Participation of Developing Countries in the WTO - new evidence based on the 2003 official records’, Stockholm: Swedish National Board of Trade, http://www.noits.org/noits06/Final_Pap/Hakan_Nordstrom.pdf
[9] 43% of LDC submissions in 2003 were made at the WTO Ministerial Conference, General Council and Trade Negotiations Committee, compared to 30% for developing countries and 8% for developed countries. (Nordström, H. 2003)
[10] Saana Consulting (2010), ‘Background Study of Existing Support for Trade Negotiations to LDCs and LICs’, Final Report, 14 September 2010, London: DFID, p.9

## Section A: Detailed Output Scoring

OUTPUT 1 Regional stakeholders are active in pursuing trade policy issues.
Output 1 score and performance description: A+ output moderately exceeded expectations
Progress against expected results: Preliminary results indicated that these targets have all been exceeded. 18 successful regional dialogues engaging a wide variety of regional stakeholders were held. Fuller data and analysis will be incorporated into the 2013 Impact Assessment report, which will be completed in March 2014. / Logframe Target for 2013: 3 regional dialogues; 55% of partners are regional; 20 regional citations / This output also includes additional indicators related to: / Securing a stakeholder base that is broad, inclusive and incorporates underrepresented groups, such as women; / Developing an integrated knowledge community of stakeholders is developed / Evidence-based analysis increases stakeholder capacity for informed participation / Emerging issues in trade policy are identified and articulated. / Progress against each of the above indicators include: / At the end of 2013, there were a total of 36,815 subscriptions to ICTSD periodicals. From the available data, approximately 58% of subscribers are from developing countries, giving an estimated number of subscriptions from developing countries of 21,353. This is approximately 11% growth since baseline. Preliminary data from 2013 shows that 61% of contributing authors are from developing, transitioning and LDCs. Final data will be incorporated into the 2013 Impact Assessment report, due March 2014. 51% of participants at ICTSD dialogues were from NGOs, academia and private sector (ie non-traditional stakeholders), 46% were from Government and Intergovernmental Organisations and 3% other; At the end of 2013, the ICTSD “Gender and Trade” database contains 21 links to external research and 7 ICTSD articles on gender and trade. / 33% returning visitors to website; 1,115,923 page views (16% drop from baseline); 2,459 LinkedIn Members (54% growth) there has been a shift from standard website-based interactions to social media-based interactions. This reflects changes in global trends of societal behaviour. The exceedingly high growth in social media interaction (54% as opposed to the targeted change of 5%) seems to indicate that in overall terms, the target of increased integration within the knowledge community has been met, and targets will be adapted to reflect the changes in web and other electronic access behaviour / Data for this indicator is not available until the Impact Assessment Report, which undertakes a survey of ICTSD periodical subscribers. This report will not be available until March 2014. / ICTSD has actively contributed to the identification and articulation of many emerging issues in trade policy and provided trade policy perspectives to the global thought leadership on the challenges of sustainable development. Examples include: Active membership and contributions to The Task Force on SDGs, convened under the World Economic Forum’s Global Agenda Council on Sustainability Governance; Two new e15initiative groups expert groups were formed, addressing: / Clean energy and the trade system / Trade and innovation / (ICTSD’s e15initiative is a multi-stakeholder dialogue process aimed at identifying a set of policy options to address critical issues in the multilateral trading system). The development of a new ICTSD project to look at Trade in Services and specifically the sustainable development aspects of TiSA (the stand alone plurilateral agreement on trade in services between the EU and, currently, 21 WTO members). The launch of a new ICTSD initiative (in collaboration with the Inter-American Development Bank (IDB) and the Asian Development Bank Institute (ADBI)) called The "RTA Exchange” – a knowledge and dialogue platform aimed at promoting international dialogue, deeper analysis and information-sharing on regional and preferential trade agreements (RTAs).Participation in an ongoing high-level initiative to look at Climate Change Cooperation called the Green Free Trade Working Group.
Impact Weighting (%): 30% / Revised since last Annual Review? N - This is the first Annual review / Risk: Medium / Revised since last Annual Review? N - This is the first Annual review

OUTPUT 2 Stakeholders engage in dialogue about potential innovations and opportunities for governance and institutional reform of the Multilateral Trading System
Output 2 score and performance description: A+ output moderately exceeded expectation
Progress against expected results: / Logframe Target for 2013: 5 informal discussions among key experts and policy-makers on solutions for governance and/or institutional reform of the Multilateral Trading System / 2013 Results: ICTSD has launched a series of initiatives and innovative responses to identify solutions for governance and/or institutional reform of the Multilateral Trading System. These include the e15initiative – a multi-stakeholder dialogue process consisting of a series of 15 expert groups, each made of roughly 20-25 top thinkers, reflecting a reasonable geographical balance and a wide range of perspectives ranging from private sector, academia, trade practitioners and former policy makers. The various e15initiative expert groups have formally convened more than 10 times over the course of 2013, with many more informal discussions on the side-lines of events such as the WTO ministerial in Bali. / This output also includes an additional indicator related to: Stakeholders and governance systems have capabilities to harness international trade policy and law to the ideals of sustainable development / Progress on the indicator includes: As a result of a two day regional dialogue on Strengthening Legal Capacity in Developing Countries and Managing Trade Disputes (held from 10th – 11th October 2013 in Brasilia, Brazil), Ecuador’s ambassador, Cesar MONTANO, former Director for Multilateral Trade Negotiations of Ministry of Foreign Trade of Ecuador said the event was : “practical and particularly useful to a country like Ecuador which has just established new institutions for its international trade law and negotiation activities. I would be happy to bring back the experience in the region and outside the region, and to share it with my colleagues who had started working in the new institutions.“ The event was also attended by representatives from Argentina, Bolivia, Brasil, Chile, Colombia, Costa Rica, Ecuador, El Salvador, Guatemala, Honduras, Korea, Mexico, México, Nicaragua, Panamá, Paraguay, Perú, Rep. Dominicana, Thailand, Uruguay, Venezuela. / ICTSD organised (in collaboration with MOFCOM) a Legal Capacity Dialogue & Training in Beijing, 18-19 November 2013. (attended by representatives from Australia, China, Brazil, India, Indonesia, Mexico, New Zealand, Japan, Pakistan, Republic of Korea, Malaysia, Philippines, South Africa, Switzerland, Thailand, Turkey, Vietnam). During the event, Mr. Sy Giang LE, Deputy Head of Trade Remedies Investigation Division of Viet Nam Competition Authority, Ministry of Industry and Trade, said: “Viet Nam is having its first ever anti-dumping investigation on foreign products. We are currently at the stage of learning by doing. This event provides a great opportunity for us to get the experience of colleagues from other countries working in the trade remedies field.”. One month after the Beijing event, Viet Nam completed its investigation and issued a decision on application of provisional anti-dumping measures on the said foreign steel products. / Impact Weighting (%): 30% / Revised since last Annual Review? N - This is the first Annual review / Risk: Medium / Revised since last Annual Review? N - This is the first Annual review

OUTPUT 3 International cooperation addresses the negative impact of high food prices and excessive price volatility on consumers in poor net-food importing countries
Output 3 score and performance description: A+ output moderately exceeded expectation
Progress against expected results: / Logframe Target for 2013: 1 example of a specific policy measure put forward in international discussions that addresses the negative impact of high food prices and excessive price volatility on consumers in poor net-food importing countries / 2013 Results: ICTSD helped The Group of Net Food-Importing Developing Countries (NFIDCs) to draft a proposal for a work programme on trade and food security; ICTSD also published analysis on how food security could be improved through new disciplines on ag export restrictions. In a dialogue that ICTSD convened to discuss the analysis, negotiators welcomed the work as ‘excellent’ and ‘very useful’ contributions to international discussions on improving food security, especially in net food-importing countries. In addition, the WTO Ministerial Conference in Bali agreed a work programme on public stockholding for food security purposes / This output includes additional indicator related to: / Agricultural trade policy reforms reduce market distortions / Climate change adaptation and mitigation policies take into account agricultural trade and food security concerns / Progress against each of these indictors includes: / US industry groups warn Congress that trade distortions in the Farm Bill could affect developing countries, drawing on legal analysis based on ICTSD research; EU environment and development groups draw on ICTSD analysis of decoupled farm subsidies to inform parliamentarians negotiating new Common Agricultural Policy; ICTSD analysis of India's Food Security Act informs domestic debate and international negotiations over a new 'peace clause' to shield food stockholding schemes. / During the year, ICTSD held 11 informal discussions with a cross-section of climate negotiators from developed and developing countries and international agency officials that took into account agricultural trade and food security concerns. In addition, ICTSD analysis informed the LDC statement at first-of-its-kind technical workshop on agriculture and climate change at the UNFCCC Warsaw COP19 and ICTSD was asked to join a global research network to inform policy-making on agricultural trade, food security and climate change, initiated by the FAO / Impact Weighting (%): 10% / Revised since last Annual Review? N - This is the first Annual review / Risk: Low/Medium/High / Revised since last Annual Review? N - This is the first Annual review

OUTPUT 4 LDCs enjoy improved market access conditions
Output 4.1.1 score and performance description: A output met expectation
Progress against expected results: / Logframe Target for 2013: 1 additional element of LDC package Operationalised / 2013 Results: ICTSD has worked closely with the LDC group towards the operationalization of the “Services Waiver” element of the LDC package. / Progress against target: Significant progress towards this target has been made in a highly politicised and sensitive environment. In –depth analysis will be provided in the annual impact assessment. / This output includes additional indicators related to: / LDCs are better able to understand how they might integrate into world markets through improved access to global value chains / LDCs have strengthened capacity to negotiate / Progress against these two indicators includes: / The relaxing of market access restrictions for LDCs from various “Global Value Chain” trading partners, such as India. ICTSD research and other inputs have been cited by Indian government officials during presentations on this topic. Another example is how ‘Aid for Trade’ development assistance can be used to connect developing country and LDC firms to value chains. This was the topic of the WTO fourth Global Review which took place in Geneva in 2013. ICTSD organized or co-organised a total of four sessions at the Global Review, participated in a number of events organised by other partners and widely disseminated the findings of its research and dialogue project on Aid for Trade monitoring and evaluation at the country level. / At the WTO ministerial Conference in Bali, the LDC group made public their desire to convene a ‘signalling conference’ on the LDC Services Waiver. The text that the LDC group published in support of this drew upon earlier work done by ICTSD. In early 2013, ICTSD published an information note that targeted the C-4, (the West and Central African group of cotton producing LDCs), including recommendations for the inclusion of Duty-Free Quota-Free access provisions for cotton trading. This was followed by an ICTSD dialogue on the same topic. Later in the year, the C-4 put together a proposal to the WTO in advance of the Bali ministerial which, among other issues, stressed the need for Duty-Free Quota-Free access on cotton. While ICTSD’s contribution must be considered in conjunction with inputs from other stakeholders who were also advocating for Duty-Free Quota-Free access provisions, it is our understanding the C-4 group of LDCs was better able to articulate their position following the ICTSD information note and dialogue. ICTSD also organised a timely dialogue which was said to help LDCs articulate the importance of a deadline extension for the implementing of obligations under the WTO’s Trade-Related Aspects of Intellectual Property (TRIPS) Agreement. Shortly after the ICTSD dialogue, the TRIPS extension for LDCs was granted. / Recommendations: / Impact Weighting (%): 20% / Revised since last Annual Review? N - This is the first Annual review / Risk: Medium / Revised since last Annual Review? N - This is the first Annual review

OUTPUT 5 Development considerations form an integral part of international deliberations on IP
Output 5 score and performance description: A output met expectation
Progress against expected results: / Logframe Target for 2013: 1 example of development considerations forming an integral part of international deliberations on IP / 2013 Results: 1 example / In June 2013, WIPO agreed upon the “Marrakesh treaty” to facilitate access to published works for persons who are blind, visually impaired, or otherwise print disabled. The treaty built upon several years of dialogue and workshops in which ICTSD played very active role. / This output also includes indicators related to: / Technology transfer and innovation policies and agreements enhance the diffusion of technologies to developing countries / IP policies align with development objectives / Progress against each of these indicators includes: / In 2013, WIPO held a series of Regional Consultation Meetings on Intellectual Property and Technology Transfer. ICTSD was invited to present at these meetings and participate in several of the roundtable discussions in panellist and moderator roles. On September 28 and 29, ICTSD held the 6th annual Bridges China Dialogue in Geneva. Founded by ICTSD in 2007, the Bridges China Dialogue is a non-partisan project that is committed to leveraging China's constructive role in crafting a global common future of sustainable development. A key topic this year was Patent laws in Transnational Technology Transfer. / The WTO TRIPS Agreement is an international instrument that reflects a balance of private rights and public interest. In 2013, ICTSD contributed to the negotiation of an extension to this agreement with the timely publication of 2 research papers and a dialogue discussion on this topic. In September 2013 South Africa published a draft National Intellectual Property Policy that contains direct quotes from ICTSD work on Intellectual Property. In October 2013, Brazil published a report titled “Brazilian Patent Reform: Innovation Towards Competitiveness”. The report was developed through a long consultative process including several workshops in which ICTSD participated. The final text of the report directly quoted work by ICTSD. Reforms included: eliminating patent term extensions and data exclusivity, restricting patents on new forms and new uses and tightening the inventive step requirement (following the India example), adopting a government use procedures, and clarifying the role that ANVISA, its drug regulatory agency, plays in the patent examination system. / Recommendations: / Impact Weighting (%): 10% / Revised since last Annual Review? N - This is the first Annual review / Risk: Medium / Revised since last Annual Review? N - This is the first Annual review

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No, this is the first review. / 1.2 Overall Output Score and Description: A+ outputs moderately exceeded expectations / All outputs have either been met or exceeded expectations, showing strong progress in the programme which we recommend is / 1.3 Direct feedback from beneficiaries: Direct feedback from beneficiaries will be available through surveys conducted in the Impact Assessment Report which will be available in March 2014.
1.4 Summary of overall progress: Very good progress overall. ICTSD’s analysis and research is widely used with strong evidence that it has been influencing developing countries trade policies and their participation in the multilateral trade system. The e15 intiaitive in particular has provided a successful forum for debating developing countries issues and the global trade agenda. There are also examples where ICTSD’s analysis has been influential in policy fora such as the Bali Ministerial where the Trade Faciliation Agreement was concluded and LDCs succeeded in securing agreement to an WTO Services Waiver which will provide preferences in trade in services. We will also consider that users of ICTSD social media are increasingly using alternatives to its website include Facebook and Twitter. Usage of these social media have increased substantially, while users appear to be using the website less.
1.5 Key challenges: These include ICTSD’s ability to influence the follow up to the Bali package agreed in 2013, particularly where the agriculture agenda is the most politically sensitive issue and which will bring the biggest gains to the poorest countries. More in-depth data on user information of ICTSD publications will be available in March 2014 which will indicate how useful these are to developing country stakeholders. Maintaining ICTSD’s position as thought leaders on trade and sustainable development will also be critical post-Bali in order to continue to make progress on multilateral trade issues.
1.6 Annual Outcome Assessment: A Outcome meets expectations

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers – Key cost drivers include staffing costs (including associated travel costs) and programme management costs. Analysis on cost drivers will be provided in the Efficiency/VfM report once financial accounts are available in March 2014. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project: No changes except that with the Bali Package agreed in 2013, there will be challenges in progressing the key issues of interest to the poorest countries, especially on agriculture and cotton specifically. In addition, as the Doha agenda progresses ICTSD will have a critical role to play in helping developing countries to determine the shape of the development agenda ‘post-Doha’. / 3.2 Where an evaluation is planned what progress has been made? The Impact Assessment Report, which will provide in-depth information on financial issues andwill provide survey information from beneficiaries including ICTSD publications and web products. This work is on-going and will be completed in March 2014.

4. Risk
4.1 Output Risk Rating: Medium / While the risk rating remains at Medium given the uncertainties around development outcomes on the multilateral agenda following the Bali Conference. / 4.2 Assessment of the risk level / Further detailed data relating to publications, website usage and feedback from beneficiaries will be available in March 2014. We will have the results of the Impact Assessment Report at this time where we will be able to better assess if there are any changes to the risk rating.
Risk of funds not being used as intended - Low / To date there has been no reported case of funds not being used as intended so the financial risk is limited. Regular management updates take place quarterly along where financial status of the project is assessed. Funds are used to provide core funding to ICTSD so the large majority of funds are used directly by ICTSD, who have rigourous financial procedures in place. Rrisk of fraud is therefore assessed as low. / 4.4 Climate and Environment Risk – N/A as the project is focused on policy developments and research/analysis.

5. Value for Money
5.1 Performance on VfM measures This section will be fully provided in our annual Efficiency report which will this year include a VfM analysis. This report will be concluded in March 2014. / 5.2 Commercial Improvement and Value for Money To be provided in March 2014 / 5.3 Role of project partners – not applicable / 5.4 Does the project still represent Value for Money :Given the positive progress in this programme we expect this project to represent good Value for Money. However more in-depth analysis will be provided in March 2014 once the Efficiency/Value for Money report is concluded. / 5.5 If not, what action will you take? If we find that there are issues around VFM in March 2014, we will press ICTSD to examine efficiencies and where costs can be reduced.

6. Conditionality
6.1 Update on specific conditions – n/a

7. Conclusions and actions
ICTSD is on top of the issues, influential with key stakeholders in the global trade agenda. The quality of the programme so far is high. Particular strengths include the quality of stakeholder engagement and empowerment. The programme of environment and climate change (following on environmental goods) is one of increasing importance for ICTSD – and one that is getting more attention internationally given the expected negotiations on the Green Goods Agreement. It can be concluded that the medium level of risk is a combination of the high quality of content and high frequency of events and periodical knowledge dissemination, combined with various risk factors that should be mitigated in the future.

8. Review Process
Assesment using ICTSD data internal information and review by DFID.