Type of Review: Annual Review

Project Title: Private Enterprise Development in LICs (PEDL)

Date started:	Oct 2011	Date review undertaken: Jan 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £14.64 million over 5 years starting October 2011 and completing by December 2016. This funds a research project on private enterprise in developing countries which works by competitively awarding research grants through a series of calls for proposals. The project also includes training and other support for researchers and activities to encourage the uptake and use of the research findings.

What are the expected results?
The programme will deliver a significant new body of evidence on private enterprise development that will help shape policy-making in LICs and fragile states. / The programme will initially focus on four key themes: / Achieving a much more detailed understanding of the impact of constraints to enterprise development in LICs, using newly available data / Understanding how the constraints interact with each other, and how constraints in one industry affect other industries / The dynamics of informal small and medium enterprises and entrepreneurship / The role of export-oriented industries in driving growth. / It is expected that around 33 new long-term research projects on private enterprise development in LICs will be funded under the project and procured through a fully open competitive process. This work will be supported by short term ‘exploratory’ research grants, academic working papers, synthesis reports, policy briefs and discussions with policy makers, and training events. The research programme will both respond to and influence policy as researchers and policy makers are brought together to determine key areas for research and to discuss and apply the research findings. / Two additional deliverables are envisaged: / Enhanced data sets on private enterprise development in LICs which, in line with DFID policy, will be made freely available to researchers as a global public good / The project is envisaged to generate substantially enhanced interest amongst the research community in understanding private enterprise dynamics in LICs and fragile states (as noted above, this is a substantial gap at present).

What is the context in which UK support is provided?
DFID’s primary objective is focused on the achievement of the MDGs, including to reduce by half those living in extreme poverty and hunger. A growing body of empirical work has emphasised the importance of economic growth to poverty reduction outcomes.The Growth Report of the Commission on Growth and Development (2008) concluded that ‘it is impossible for poor countries to lift large populations out of poverty without growth’. To reflect its importance, DFID’s research strategy identifies economic growth research as one of five priority areas. / The growth report (2008) notes the important of a dynamic private sector in driving growth and the creative destruction process of firm entry and exit. However, a recent broad based consultation exercise identified substantial gaps in research about private enterprise dynamics in LICs and fragile states. While data does not seem to be a major constraint, data quality and the ability to integrate data sets on all key different aspects of private sector development (entry, performance, exit and global pressures) remain important gaps. By targeting private sector development (PSD) and in particular research associated with the investment climate (property rights) and small and medium enterprises (SMEs) the programme will focus on an area that is of critical importance to Low Income Countries (LICs), fragile states, the development community and to DFID. An important gap that the programme will look to address is with respect to empirical evidence that can be useful in supporting policy in countries emerging from violent conflict. / Filling such gaps therefore constitutes an important priority and strategic use of DFID resources. It represents an important building block for any future programme of research on economic growth focused on LICs. Enhanced wealth creation, including through substantial development of the private sector, is one of DFID’s current key global policy priorities.

Annual Review status
This is an early Annual Review. Scores awarded are provisional until a more thorough review can be conducted in March when milestone deliverables become due.

## Section A: Detailed Output Scoring

Output 1: High-quality research on private enterprise development in LICs
Output 1 score and performance description:[1] A+ / PEDL is making excellent progress in the commissioning of small grants and is beginning to deliver research papers at a substantial rate. The thematic balance of research activity is improving and the PEDL team has been very active in promoting its profile in the research community through its seminars and training events. The major ongoing challenge is the attraction of larger grants, and it is crucial to address this successfully as these are the grants that will generate the best research outputs in the long run.
Progress against expected results: / Output Indicator 1.1 1st milestone (end 2013) Achieved (end 2013) / Number of Exploratory Research Grants (ERGs) awarded that meet the quality standards set by the Initiative. L = 38, M = 42, H = 46 57 (including 10 + 5 = 15 Special Call awards) / Output Indicator 1.2 / Number of Major Research Grants (MRGs) awarded that meet the quality standards set by the Initiative. L = 13, M = 15, H = 17 10[2] / Output Indicator 1.3 / Number of peer-reviewed articles, reports, working papers and conference papers produced by projects funded under the Initiative. (DFID RED indicator). L = 8, M= 10, H = 12 10 Working Papers (1 not posted) / 4 Research Notes (see Output 2.4n) / Output Indicator 1.4 / Number of peer-reviewed articles (only) produced by projects funded under the Initiative. L = M = H = 0 0 / Output Indicator 1.5 / Research conferences on private enterprise development in LICs attended by at least 20 researchers and rated “successful” or better by at least 50% of attendees. L=0, M=1, H=2 4 / Output Indicator 1.6 / Proportion of outputs under Indicator 1.3 that address each of PEDL’s cross-cutting themes (gender, conflict, environment) L= 2.5%, M= 5% H = 7.5% Gender: 22% (15/67) / Fragile and conflict-affected states: 28% (19/67) / Climate, environment and social compliance: 9% (6/67) / All three: 0% / PEDL is broadly on track in terms of the overall scale and speed of commissioning research in terms of grant commitments (decisions to make awards)[3]. However, the pattern differs from what was planned, greatly exceeding the target for exploratory research grants (57 vs. high case target of 46) and missing that for major research grants (10 vs. low case target of 13). PEDL has a very healthy pipeline of Exploratory Research Grant applications suggesting it will be able to sustain this rate of commissioning, but further outreach activity will be necessary to improve the number of Major Research Grant (MRG) applications. With only 17 MRG proposals received in the 2013 round, it seems that attracting and identifying high-quality large-scale projects has been more challenging than anticipated. The introduction of intermediate grants is also being considered. / On the other hand, there are very encouraging patterns in the balance of research commissioning across themes, with substantial numbers of exploratory grants addressing each of PEDL’s cross-cutting themes (exceeding PEDL’s high case milestone in all cases). / Research results started becoming available in mid-2013, as some of the early rounds of ERG funded projects came to a close. Though we cannot expect peer-reviewed publications from all of the ERG projects, given their exploratory nature (e.g. some are only pilot studies for full-scale RCTs) we have received 10 working papers from the closed grants so far, available here, meeting PEDL’s medium case target. It is however too early in the life-span of MRG grants for publishable results to be released, as all of the MRG projects are still in the implementation stage. Completed and ongoing work from both has been presented across a number of seminars and conferences substantially above PEDL’s high target. / Implementation of 2012 Recommendations: / Complete Major Research Grant selection process in June to avoid delays over the summer period. Selection achieved earlier, but still some delays in grant negotiation over summer. / Review composition of Evaluation Committee. The standing committee (with a fixed membership spread across the globe) has led to unbalanced workloads and participation across evaluators. A more flexible structure will allow evaluators to contribute when and where they are available and so to have a more consistent role. New structure with standing Associate Scientific Co-ordinator and flexible Evaluation Committee agreed but identifying a suitable individual remains a challenge. / Revising logframe indicator 1.3 to distinguish between peer-reviewed and other outputs. Revised. / Revising logframe indicator 1.4 to talk about attendance and feedback as well as the number of events. Revised, but we need to specify exactly how feedback will be collected. / Revising logframe risks/assumptions in line with the Business Case risk register (for all outputs). Risk register revised – logframe will be refreshed again following this review. / New logframe indicators on the proportion of research output relevant to gender (which we are required to monitor by the DFID RED Results Framework) and the other cross-cutting themes. Indicator added. / Recommendations: / PEDL is close to achieving an A++ on this core output. To achieve that it needs to increase commissioning of MRGs, as well as maintaining momentum on the publication of outputs, and ensuring their prompt submission to journals (peer-reviewed products are due next year). The Management Committee has already discussed how to scale-up large grant commissioning and has begun implementing the following key recommendations: / To increase outreach - advertising the call to a greater pool of researchers and across a wider range of audiences (including at the December workshop held jointly with the IPA SME initiative and DFID Growth Research Team’s Twitter account) / The management committee has discussed a proposal to allow successful ERG proposals to scale up more gradually by asking for additional funds under the ERG program instead of being required to jump immediately to a large-scale grant. The MC requested that PEDL staff develop a formal proposal along these lines. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[1] Milestones were not set for PEDL’s first year – see below: section B, 1.2 for details
[2] One other was invited to revise & resubmit in the first round.
[3] There are some issues with grant disbursement discussed in Section B, Part 2.

Output 2: Research use by policymakers in LICs
Output 2 score and performance description: B / PEDL has been somewhat slow to develop an outreach strategy, but the final product is high quality and has begun to be swiftly implemented. DFID needs to clarify expectations about the number of briefing and review products while CEPR needs to ensure that research teams keep in regular touch with decision-makers and other key informants.
Progress against expected results: / Output Indicator 2.1 1st milestone (end 2013) Achieved (end 2013) / Policy-oriented conferences on private enterprise development in LICs L = 0, M = 1, H = 2 0 / Output Indicator 2.2 / Number of research teams that interact regularly with policymakers to discuss the research process L = 12, M = 15, H = 18 5 (2 MRGs, 3 ERGs) / Output Indicator 2.3 / Literature reviews and evidence notes (including book/collected volume) L = 42, M = 46, H = 50[4] 0 (1 Lit Review to be submitted by mid-2014) / Output Indicator 2.4 / Research notes and data notes L = 42, M = 46, H = 504 4 (Research Notes) / Output Indicator 2.5 / Survey of stakeholders - impact perception scores for the Initiative 0 Not applicable for this review – see October MC Minutes, page 6 / In terms of uptake, PEDL was somewhat slow to design an outreach strategy with production delayed by some 6 months. However, the final product was good quality and has been swiftly implemented since the last quarter of 2013. PEDL launched a series of Research Notes in October 2013, which are aimed at research users as well as other researchers. Four have been published so far, and another three are currently in the process of being written up. / In terms of interaction with policymakers, it is too early to hold dissemination conferences and to survey users as the outputs have only just been released. On the other hand it is a cause of some concern that there are not more research teams keeping in regular touch with policymakers to discuss work in progress. / DFID urgently needs to clarify expectations for the number of review and briefing papers to be produced. / Implementation of 2012 Recommendations: / Revising logframe indicators to make them clearer and more specific. In particular, this output would be more appropriately called “Engagement with policymakers in LICs” (as using the research is actually the outcome we hope to achieve) and being explicit about what we mean by stakeholders (policymakers using PEDL products?). Actioned and new indicators agreed, but a mistake was made on the targets for indicator 2.3/2.4 – this should have been split up rather than duplicated. DFID urgently needs to clarify expectations for the number of review and briefing papers to be produced following this review. Management Committee has also noted the need to agree a form of survey in the next logframe revision. / Develop an uptake strategy in the first quarter of 2013 and lay the foundations of the policy network that will engage with PEDL’s findings. Achieved in the fourth quarter of 2013. / Recommendations: / More research teams should interact regularly with decision-makers and other potential users/informants. CEPR should include this check in its grant monitoring / progress reports. / Continue the rapid implementation of the outreach strategy, in particular the commissioning of several review papers this year / Impact Weighting (%): 35% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[4] These targets are incorrect, owing to the fact that indicator 2.4 from the previous logframe (2012) was split into two in the current (2013) logframe: current indicators 2.3 and 2.4. The targets should have been split but were instead copied – this will be rectified by DFID and CEPR immediately on completion of the review.

Output 3: Capacity building in LICs
Output 3 score and performance description: A++ / PEDL is exceeding its medium target for southern research participation; moreover, in terms of Southern-led research projects, PEDL had a grace year with a zero target to recognise how challenging this objective is, but it is actually exceeding even its high target for next year. In recognition of the highly successful Special Call for southern researchers and equally successful subsequent training event, we award an A++ for this output.
Progress against expected results: / Output Indicator 3.1 1st milestone (end 2013) Achieved (end 2013) / Number of southern researchers participating in the programme / * Southern refers to researchers based in LICs and MICs. Northern refers to researchers based in HICs. L = 10%, M = 20%, H = 30% of research conducted with southern research engagement 22% (15/67) / Output Indicator 3.2 / Number of southern-led research projects L = M = H = 0 18% (12/67) / Output Indicator 3.3 / Training workshops involving researchers from LICs L = 0, M = 1, H=2 1 / As well as aiming to generate research on low-income countries, PEDL seeks to involve southern researchers in producing it. Overall, the rate of southern researchers’ participation in PEDL is very healthy, with 11 out of 57 ERGs led by southern researchers, one MRG led by a PI based in a MIC (Mexico), and 2 of the remaining 9 MRGs involving LIC-based co-PIs. / Following PEDL’s objectives for 2013 set out in the last Annual Report, it launched a capacity-building call focused on southern researchers in early 2013 and granted funding to 5 projects from this ‘Special Call’. / It then hosted a training workshop for these grantees and another team of LIC researchers from an earlier round of ERGs, in Warwick on December 8-10. The event was structured to provide as much detailed feedback to individual projects as possible. The SC invited two post-doctoral fellows and two professors to join as faculty for this workshop. They helped to review the projects of the LIC researchers and provide feedback on their project design and the presentations they made to the group during the training workshop. The SC and the two other professors also gave lectures focused on methods of identifying causal effects in empirical research. / This workshop appears to have been very effective in improving these LIC-based grant holders’ capacity to produce rigorous research in the field of private sector development. The feedback from the online survey that we asked the participants to fill out was overall highly positive. / PEDL is exceeding its medium target for southern research participation; moreover, in terms of Southern-led research projects, PEDL had a grace year with a zero target to recognise how challenging this objective is, but it is actually exceeding even its high target for next year. / Implementation of 2012 Recommendations: / Special exploratory research grant call for southern scholars only, linked to a training programme, as this will allow applicants with promising ideas but needs for extra support to begin to contribute to PEDL. Actioned and highly successful. / Discussing a number of ways southern applicants can be encouraged in the normal calls, including those mentioned above Actioned and southern researchers have been awarded grants through the main calls. Nevertheless it will be important to continue to monitor southern participation in the calls. / Revising the logframe indicators to talk about the number of projects that are southern-led and are northern-led with southern participation. Consider striking indicators 3 (because it is input-based and creates some perverse incentives) and 4 (because these workshops should be covered by other indicators). Clarify whether “southern” researchers means based in LICs or MICs and LICs. Revised. / Further outreachto southern research institutions and possible collaboration with IDRC/PEP, AERC etc. to help PEDL reach southern researchers. Not actioned. / Recommendations: / Continue efforts to encourage southern participation through the main calls, including leveraging the growing network of PEDL researchers based in developing countries / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y / Most of the outstanding issues were addressed in the last revision of the logframe but new issues have been raised and a number of issues remain to be clarified. We propose a number of revisions and one correction. / 1.2 Overall Output Score and Description: A / PEDL is commissioning research at broadly the rate planned in the business case, but the pattern differs from what was planned, greatly exceeding the target for exploratory research grants (57 vs. high case target of 46) and missing that for major research grants (10 vs. low case target of 13) – see key challenges, below. There are very encouraging patterns in the balance of research commissioning across themes, with substantial numbers of exploratory grants addressing each of PEDL’s cross-cutting themes (exceeding PEDL’s high case milestone in all cases) and highly successful efforts to engage developing country researchers and PHD students (exceeding PEDL’s medium case milestones for both grant awards and training activities). / The first exploratory grants are now concluding; research papers are now being produced and posted here, meeting PEDL’s medium case target of 10. However, PEDL has been somewhat slow to translate these outputs into outreach activity. Production of the outreach strategy was delayed by some 6 months although the final product was good quality and has been swiftly implemented in the form of the first research notes. DFID urgently needs to clarify expectations for the number of review and briefing papers to be produced. / 1.3 Direct feedback from beneficiaries / We surveyed applicants on how they found the PEDL call process in Annual Review 2012 and concluded that the process established at the outset was basically sound. We may repeat the survey as part of the full review later this year, in particular focusing on adjusting the size of PEDL grants.
1.4 Summary of overall progress / PEDL is making good progress against its commissioning objectives. The grant-making machinery has been set up and is working well, but PEDL needs to attract higher numbers of proposals for large grants and speed up the process of processing grant awards. On the other hand, PEDL deserves particular credit for working with a high number of scholars from developing countries and improving the thematic balance of grant awards. / A healthy volume of research papers are now being delivered as well. Although PEDL has been somewhat slow to translate these into uptake activity, a high-quality strategy has been produced and is being rapidly implemented. Progress on this front and sustained success on the others would make PEDL likely to score an A+ next year.
1.5 Key challenges / Outreach and uptake / PEDL was somewhat slow to design an outreach strategy with production delayed by some 6 months. However, the final product was good quality and has been swiftly implemented since the last quarter of 2013. PEDL should continue the rapid implementation of the outreach strategy, in particular the commissioning of several review papers this year, while ensuring that more research teams interact regularly with decision-makers and other potential users/informants through its grant monitoring process. / Southern participation / PEDL is now exceeding its medium target for southern research participation; moreover, in terms of its new target for Southern-led research projects, PEDL is actually exceeding even its high target for next year. The Special Call for southern researchers was highly successful and it will be a huge credit to the project if it can sustain this rate of success. / Thematic coverage / While we still need to review the balance of thematic coverage across the four main themes, there are very encouraging patterns in the balance of research commissioning across cross-cutting themes, with substantial numbers of exploratory grants addressing each of gender, conflict and the environment (exceeding PEDL’s high case milestone in all cases). / Timescales and costs / While PEDL succeeded in accelerating the call process this year, with grant decisions taken by Summer, significant delays were once again experienced in contracting. These issues are discussed extensively in section 2 and DFID and CEPR need to agree remedial action swiftly following this review.
1.6 Annual Outcome Assessment / It is far too early to assess outcomes, but the outcome indicators of the logframe have been revised since last year to better capture policy influence, even where this does not lead to policy change.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Spending has been a little slow, partly because of the number of Major Grant proposals received, coupled with the maintenance of high quality standards. The result is that only 5 Major Grants each were approved for the first two calls, whilst the project budget had assumed 6 from the first call, and 9 from the second. / The process of grant negotiation/award could be accelerated, but maintaining high quality standards remains the over-riding objective. / Spending has been reduced against the original budget by slowing spending on uptake. Thus in 2013 uptake costs were approximately £107,000, as against a budget of £257,000. This is wise, as the project has too little significant output yet, but we should save resources for later in the project when weighty results come through. / . / Financial Year Admin & uptake Research Total / Total Budget 2,845,487 11,793,984 14,639,471 / Major Grants Exploratory Grants / 2011 176,400 - 87,500 263,900 / 2012 396,000 276,000 346,192 1,018,192 / 2013 435,419 502,000 901,000 1,838,419 / - / 1,007,819 778,000 1,334,692 3,120,511 / 2.2 Key cost drivers / The main costs of the project are research grants. Thus the rate of expenditure is largely determined by the speed with which calls are administered and grants made, and the number and size of grants deemed appropriate for the proposals received. The response from researchers to research calls is not within the project’s control. / 2.3 Is the project on-track against original timescale: N / The first call Major Grants were contracted 4-5 months late. On the other hand, 42 Exploratory Grants and 15 Special Exploratory Grants have been awarded, as against 48 originally planned up to 31 March 2014.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / N/A / 3.2 Where an evaluation is planned what progress has been made? / An evaluation is not planned at this early stage.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / Risk Probability Impact How risks will be minimized/mitigated Comments / revisions / Management Risks / (i) CEPR programme management. This is a new and sizeable programme for CEPR, larger than previous programmes they have managed. Will CEPR be able to respond to the management challenges? / (ii) a good quality candidate for the Scientific Co-ordinator post cannot be found. Low Medium (i) CEPR are aware of the risk and are taking necessary steps to ensure they have the personnel and back-up necessary to deliver this programme. CEPR are recruiting new staff and developing systems to ensure that capacity is supported – ie through internationally recognised back-up support. / (ii) CEPR have already identified a high quality candidate for the SC post. CEPR’s management has successfully run several calls for exploratory grants and one for major grants. The risk of poor management appears to be low. / The size of the research programme on private enterprise dynamics in LICs may be too big for the research community to absorb and respond to effectively. Low Medium CEPR/DFID are aware of the risk and will monitor and adjust the programme as necessary. CEPR have a global network of over 800 research fellows with the likelihood that the programme can be absorbed and will indeed shift research interests toward LICs. Moreover data requirements in LICs will also absorb funds. The response to the calls for exploratory and major grants so far gives cautious grounds for optimism that the research community will be able to respond to a project of this size. The response has been neither particularly disappointing, nor much above expectations. / Research Risks / Research procured fails to have policy relevance. Low High The programme governance structure incorporates users from both the north and south to help identify research gaps and reflect user demand. In addition various methods have been adopted during initial scoping to establish genuine gaps in research and user needs. These activities have informed the shape and initial direction of both research programmes. The design of the project, and the inclusion of southern users in the governance structure provide considerable assurance that outputs will be relevant. / Poor quality research funded Low High CEPR has a strong focus on research excellence and is well regarded for the quality of its research. A sift and peer review process will filter poor quality and unfocused proposals during the early stages. / CEPR’s emphasis on the publication of outputs post award provides researchers with strong incentives to produce quality outputs. Clearly articulating the questions we want addressed within the call specifications will also support the production of quality focused outputs. / Quality of proposals (including evaluating methodology) will form key criteria for project selection. The competitive awarding of grants, subject to peer review and expert appraisal, gives grounds for confidence that research quality will be high. / Researchers do not engage with policymakers Low High As part of CEPR’s procedures, applicants are required to submit a pathways to impact plan which outlines how the research will benefit end users. The impact plan will form part of the peer review and assessment process. The risk that “the research will have no impact on policy-makers” was rated ‘Medium’ probability in the Business Case. / We have split the risk into two and this first element, “researchers do not engage with policymakers” is now rated ‘Low’. / It has been reduced because the mitigating actions (especially ‘pathways to impact’ plans, and ‘policy engagement’ plans) have been quite robust in ensuring that research teams make the effort to reach out – PEDL management has substantial control of this. / Policymakers do not use the evidence made available to them Med High Finding ways to communicate effectively with senior decision-makers who have little time to absorb complex research is a perennial challenge. / The Scientific Co-ordinator will oversee the synthesis of research outputs in policy briefs and PEDL has developed an outreach and uptake strategy which identifies key audiences and the titles of the first briefs. / An independent evaluation of project impact is planned at the end of the project cycle. The risk that “the research will have no impact on policy-makers” was rated ‘Medium’ probability in the Business Case. / We have split the risk into two and this second element, “policymakers do not use the evidence made available to them” is still rated ‘Medium’. / It has been left at medium because it is too early to judge how successful the mitigating actions (especially the new uptake strategy) have been. Much of the innovative comms activity lies in the future, and even then we cannot assume that because research findings have been communicated to policy-makers (Output 2), there will then be an impact on policy-making – this can only be assessed late in the project’s life. / Research findings too disparate and do not add up to a coherent set of findings Low Low Dedicated resources are allocated within the programme for the Scientific Co-ordinator, one of whose principal roles will be to cohere emerging research outputs both within and across the themes. / Southern partners fail to win research grants or where they do are represented only peripherally to the commissioned research. Med Low Pro-active and targeted publicising of growth programme awards in relevant print media and networks was undertaken with ample lead times including developing a pre-call guidance note to provide guidance to prospective applicants on research themes and administrative processes. / Moreover PEDL ran a Special Call dedicated to researchers based in low-income countries to mitigate this risk. We have seen a healthy volume of applications from southern research institutes in response to the calls. However, their more variable quality has led to fewer southern applications being successful. In response, a Special Call was held offering smaller grants with more intensive support to researchers based in low-income countries, which was highly successful. / Nevertheless, the challenges in reaching Southern researchers remain great and it is appropriate to leave this risk at a ‘Medium’ rating.
Risk of funds not being used as intended / The risk of CEPR itself misusing DFID funds is low: CEPR is a known and trusted partner, a registered charity (No. 287 287) and a company limited by guarantee in the United Kingdom (No. 1727026). Moreover this risk will be mitigated through regular financial reporting and external audit. / To limit the risk that grant holders misuse funds, CEPR releases grants in tranches, and will demand to see progress reports before releasing more. / 4.4 Climate and Environment Risk / Unchanged from Business Case: / Climate change and environment risk Climate change and environment opportunity / C B / Although it remains the most challenging cross-cutting theme to address, PEDL has gone from awarding no grants with an environmental aspect in 2012 to 9% of grant awards in 2013 – beating its high case target for the year.

5. Value for Money
5.1 Performance on VfM measures / 1. Competition and peer reviewed selection of research proposals – once an individual research contract has been awarded it is difficult and expensive to monitor. Experience has shown (see Research Council approach) that the best way of ensuring a quality output (and so value for money) is through a competitively and peer reviewed selection process for individual research projects. – The project is doing this. / 2. CEPR contribution to cover a significant proportion of administrative costs. Extensive negotiations with CEPR to ensure 92% of DFID funds will be used for research and uptake. – This is being done. / 3. The project is succeeding in bringing new researchers into work on LICs. / While the project is implementing the VFM measures agreed, we propose developing VFM metrics with the team that can be used to monitor progress going forward e.g. costs per journal article etc. / 5.2 Commercial Improvement and Value for Money / All bids are awarded by a competitive international process. / All bids are peer-reviewed and carefully evaluated for quality and relevance. / Small Exploratory Grants are being used to incubate research ideas, which will promote a wider spread of research proposals for the later calls for Major Grants, thus enhancing competition and value. / The project is introducing a new procedure into the assessment of major grant proposals, a ‘line-item VfM review procedure’. / The project is taking considerable pains to negotiate good value for money before issuing grants. / The future supply of good-quality eligible research proposals is uncertain. The project has the flexibility to adjust to a higher- or lower–than-expected response from researchers. / 5.3 Role of project partners / PEDL is a unique partnership between CEPR and DFID, where CEPR contributes its own resources to the project as well leading implementation. A Memorandum of Understanding (MoU) for competitively procuring research through CEPR’s extensive network is the basis of the partnership arrangement. / 5.4 Does the project still represent Value for Money : Y / It is too early at this stage to judge the effectiveness of the project, but the processes agreed are in place and we will agree metrics that will allow us to assess this once outputs are being delivered. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The review concluded that PEDL is performing well, awarding a healthy number of research grants across its themes to a diverse group of researchers. Challenges remain in commissioning larger projects. Research papers are rapidly coming online and while PEDL was initially somewhat slow to translate these into briefs and other uptake activity, a new strategy is now being implemented. / Here we summarise the key recommendations from the body of the review: / To increase outreach - advertising the call to a greater pool of researchers and across a wider range of audiences (including at the December workshop held jointly with the IPA SME initiative and DFID Growth Research Team’s Twitter account) / The management committee has discussed a proposal to allow successful ERG proposals to scale up more gradually by asking for additional funds under the ERG program instead of being required to jump immediately to a large-scale grant. The MC requested that PEDL staff develop a formal proposal along these lines. / More research teams should interact regularly with decision-makers and other potential users/informants. CEPR should include this check in its grant monitoring / progress reports. / Continue the rapid implementation of the outreach strategy, in particular the commissioning of several review papers this year / Continue efforts to encourage southern participation through the main calls, including leveraging the growing network of PEDL researchers based in developing countries / The Management Committee should discuss urgently how the process of grant negotiation/award can be accelerated / DFID urgently clarify targets for indicator 2.3/2.4 / The Management Committee should agree how future outreach activity will be assessed – including the form any surveys should take – and produce an addendum to the logframe defining any terms that may cause confusion.

8. Review Process
The review was carried out by DFID staff from Research and Evidence. CEPR provided a draft Annual Report while key tasks for the DFID team were: / Output scoring based on a review of project documentation[5]. / Review of call documentation and proposal database queries / Review of financial records etc. to assess costs, risk and VFM. / E-mail correspondence with CEPR staff.
[5] Project proposal, business case, logframe and PEDL’s annual report