Type of Review: Project Completion Review
Project Title: Sustaining Nutritional Assistance in Karamoja
Date started: November 2011	Date review undertaken: 18 January to March 2013
## Introduction and Context
What support did the UK provide?
DFID Uganda provided £2,751,250 in the financial year 2011/2012 to enable WFP and UNICEF to meet a higher than anticipated need for nutritional assistance related to drought and poor harvests in Karamoja. WFP received £1,241,875 and UNICEF £1,509,375. Funding supported WFP’s community based supplementary feeding programme (CBSFP), implemented as part of WFP’s Protracted Relief and Recovery Operation (PRRO), and UNICEF’s Therapeutic Feeding Programme (TFP); water, sanitation and hygiene promotion (WASH) and nutritional surveillance programmes. / DFID support was intended to cover an eight month period (August 2011 - end March 2012). The project started in November 2011, and was subsequently extended to 30 November 2012 due to delays with the UNICEF WASH component.

What were the expected results?
The project aimed to maintain global and severe acute malnutrition rates within safe levels across Karamoja, helping to reduce child mortality rates and avoiding over 1,000 preventable child deaths. / Outcome: reduced levels of global and severe malnutrition, particularly among children under five. Targets for all districts Global Acute Malnutrition[1] (GAM) reduced to 10% and Severe Acute Malnutrition (SAM) to 2.5% by March 2012); / Impact: fewer preventable deaths among children under five in Karamoja (target 160 per 1,000 live births). / Expected results at the output level were: / Output 1 Undernourished and malnourished children and individuals receive appropriate treatment and care. Targets: 5,000 children suffering from SAM identified and treated; 20,000 moderate acute malnutrition (MAM) cases treated; 70% of children discharged from outpatient TFP admitted to CBSFP. / Output 2 Safe water facilities, sanitation and hygiene practices provided and promoted at health centres, schools and in rural communities. Targets: 27,000 households with access to safe water and 2,300 schoolchildren with access to adequate sanitation services. / Output 3 Communities and districts are better able to obtain and analyse timely, frequent and quality data on nutritional vulnerability and to take action accordingly. Targets: 180 Village Health Teams (VHTs) collecting community vulnerability system data; 75 healthcare workers receiving refresher training on community vulnerability system and 120 on food security and nutritional assessments; 2,000 children under five screened for malnutrition and referred to care.
[1] Global Acute Malnutrition (GAM) is the sum of the prevalence of Severe Acute Malnutrition (SAM) plus Moderate Acute Malnutrition (MAM) at a population level. Moderate Acute Malnutrition (MAM) is defined by WHO/UNICEF as: Weight-for-Height Z-score <-2 but >-3 Severe Acute Malnutrition (SAM) is defined by WHO/UNICEF as: Weight-for-Height Z-score <-3; Mid-Upper Arm Circumference (MUAC) <11.5cm; Bilateral pitting oedema; Marasmic-kwashiorkor (both wasting and oedema)

What was the context in which UK support was provided?
Karamoja has the highest prevalence of food insecurity in Uganda. The prevalence of acute under-nutrition for children under five fluctuating between 9% and 12% during the year,[1] with GAM and SAM rates frequently exceeding emergency thresholds. / Karamoja is impacted by periodic droughts - there have been four droughts in the past ten years, each affecting roughly half the population.[2] Variable rains during October-December 2010 resulted in delayed planting in 2011. By mid-2011 OCHA estimated that up to 650,000 people (half the population) faced food insecurity. Nutritional surveillance results in May 2011 raised serious concerns – rates of 12.8 % GAM and 2.8 % SAM were reported in half of the districts.[3] “Pockets” of higher malnutrition rates were also reported in some districts e.g. Nakapiripirit (20% GAM) and Kotido (14% GAM). / WFP and UNICEF were already implementing CBSFP and TFP in Karamoja but faced gaps in funding. UNICEF was assisting the Ministry of Health (MoH) to integrate the treatment of SAM into district and community health services - the Integrated Management of Acute Malnutrition (IMAM) Programme (November 2010 to October 2012). UNICEF’s implementing partners (IPs) included CONCERN Worldwide, Action Contre La Faime (ACF) and Cooperazione e Sviluppo (CESVI). / WFP introduced CBSFP in 2009 to extend the coverage of nutrition programmes beyond health centres. CBSFP is based on village health team (VHT) screening with referral of to the CBSFP rather than to health centres, and is an appropriate response to address the coverage/access limitations of a health facility based SFP. / As a response to the Global Scaling Up Nutrition (SUN) initiative, the Government of Uganda (GOU) has committed to combat malnutrition, developing in 2011 a five year Uganda Nutrition Action Plan (2010-2015). Karamoja is one of the regions identified for the scale up of high impact nutrition interventions which fall into three broad categories: promoting good nutrition practices, improving intake of vitamins and minerals through supplementation and fortification, and the prevention and treatment of under nutrition.[4]
[1] WFP; ACF/UNICEF Nutrition Surveillance
[2] Data source: Center for Research on the Epidemiology of Disasters (CRED)
[3] DHO, ACF and UNICEF Nutrition Surveillance Report May 2011.
[4] This exposition of Uganda’s plans to scale of nutrition interventions was provided by UNICEF.

## Section A: Detailed Output Scoring
Output 1: Undernourished and malnourished children and individuals receive appropriate treatment and care. Targets: 5,000 children suffering from SAM identified and treated with therapeutic feeding in 2012. 20,000 MAM cases treated with supplementary feeding in 2012
Output 1: Final score and performance description: / A. Outputs Met Expectations / Summary / The expected result was that 80% of acutely malnourished children would receive appropriate treatment and care. UNICEF achieved the 80% target of anticipated cases. Actual coverage, based on coverage surveys implemented during the programme, was estimated at 60% The coverage target is 70% for both MAM and SAM in the MoH IMAM guidelines. / Appropriate treatment and care is considered as adherence to IMAM Guidelines and the achievement of specified performance standards/targets Overall adherence has been good and standards met with some exceptions for example the effectiveness of referrals; divergence from the guidelines concerning routine medication, and default rates for the TFP were slightly higher than the 15% target.
Final results / Project target – Treatment & Coverage Moderately Acute Malnutrition (MAM) / WFP aimed to achieve 80% coverage of MAM cases. Coverage was 81% in May 2012. In a few sub-counties in southern Karamoja, where distances to CBSFP sites are greatest, coverage was below 70%. The target was to identify and treat 20,000 children and other targeted individuals. WFP increased this in 2012 to 24,000 based on August 2011 GAM rates and an estimate for the number of malnourished pregnant and lactating mothers, elderly women and other targeted categories. / WFP supplied commodities to extended delivery points (warehouses) for an average of 21,240 beneficiaries per month over the project period[2]. This does not represent a shortfall in commodities against the 24,000 planning figure given variations in the actual caseload. Onward transport to final distribution sites was, however, noted to have been problematic, mainly due to difficulties obtaining trucks to transport commodities, and this did result in some fortnightly distribution rounds being missed. / WFP’s planning figure remained over 20,000 throughout 2012. It would have been expected that the monthly caseload would decline over time, particularly after the peak hunger period in April-May and given that the IMAM targets for discharging children as ‘cured’ were generally met. However the caseload did not decrease because a large number of the children discharged from the programme repeatedly returned. The incidence of children returning to the programme was reported by WFP to be as high as four times per annum. / The high incidence of repeat admissions points to an inefficiency that needs to be addressed in coordination with other stakeholders. This could reflect chronic health and food security problems, or be related to the incentive to maintain access to the programme. The number of repeat admissions needs to be more closely monitored and the underlying causes better understood. How effectively VHTs monitor children discharged from the programme to prevent relapse should also be considered.[5] / Project target – Treatment of Severe Acute Malnutrition (SAM) / The target was to treat 5,000 children (80% of anticipated caseload in Karamoja) over 8 months. UNICEF reached more than 5,000 children, and met coverage targets per the anticipated number of SAM cases. The coverage target was based on the likely incidence of SAM. The estimated caseload on the estimated incidence rate. However, latter coverage surveys reported a coverage rate of 60%.of actual SAM cases, indicating that the case load was higher than originally anticipated. / Recommendations: / UNICEF and WFP should carry out a study to determine the profile of new admissions to CBSFP and TFP including age profiles, home circumstances, etc. The incidence of repeat admissions should also be determined. / UNICEF should consider developing a coverage target in future programmes and undertake a coverage survey to test whether they have reached this target. / Integrated Management of Acute Malnutrition (IMAM) performance standards / These are set out in Table 23 on page 69 of the IMAM Guidelines and include cured rate, death rate, default rate, non-cured rate, average length of stay, coverage and distribution of sites. / Discharged ‘cured’ rate: The discharged as cured rates are important and the results are reassuring, but for the fact of repeated admissions. The standard or target cure rate for both Supplementary Feeding Programme (SFP) and TFP (Outpatient Therapeutic Care (OTC) and Inpatient Therapeutic Care (ITC)) is >75% (by maximum 3 months). WFP reported that the cure rate for SFP (weight gain of at least 10% or with reference to Z-score and MUAC) was maintained at about 90% on average over the project period, well above the target. / UNICEF data obtained during the review indicated that the OTC cure rate (weight gain of at least 20% or with ref to Z-scores) for Karamoja as a whole exceeded the target throughout the project. There are however exceptions when the data reported by UNICEF’s IPs is disaggregated, e.g. the cure rate for: / Moroto District remained below the standard throughout first quarter of 2012 / Napak District was below the standard in January and February 2012 / Kaabong District was below the standard for January 2012. / UNICEF’s final report states the discharged cure rate through 2012 was 82%.[6] WFP report that the cure rate in ITC (only) for which it provides some commodity support was maintained at about 83% on average overall. / Death rate: The targets of < 3% for SFP, < 5% for OTC and < 10% for ITC were achieved overall. Disaggregated data for months and/or districts was however not available. UNICEF reported that the OTC death rate was 2% overall.[7] / Default rate: The default rate is the number of clients who defaulted (missed two consecutive visits) as a percentage of all discharges during the reporting period. The IMAM Guidelines target default rate is <15% for both SFP and TFP. WFP reported that default rates were maintained at an average 7%.[8] UNICEF reported that default rates for TFP were 16% through 2012, slightly higher than the target.[9] Despite the good performance against target, default rates were frequently mentioned as a problem area during the review, particularly for OTC. / Average length of stay: Aggregated data was not available at the time of the review. Data had been collected and reported by IPs. For the purposes of calculating individuals within caseloads, two months out of a maximum of three has been assumed. / Coverage – Therapeutic feeding programmes (TFP): IMAM targets are >70% coverage for TFP. SPHERE standards set a coverage target for TFP of >50% for rural areas. Although UNICEF met the specified a target of reaching 80% of anticipated cases. Coverage surveys of actual cases was 60%”, which is below the IMAM target. / CONCERN conducted a Semi-quantitative evaluation of access and coverage (SQUEAC) survey in Nakapiripirit district in March 2010 (IMAM was first implemented in May 2009) which showed an estimated overall coverage of 58% (47.4% - 68.4%). ACF conducted a coverage survey in Moroto and Kaabong Districts in July 2011 and found that (point) coverage was 37% for Kaabong and 41% for Moroto. Period coverage which includes recovering children produced better results with a greater than 50% coverage rate of 58.5% and 57.5% for Kaabong and Moroto respectively.[10] ACF note in their reporting on coverage that the main obstacles are: distance to the health services including security for women and children, availability of health facility staff at the health facilities and caretaker’s household responsibilities. / UNICEF has invested substantially in increasing the coverage of TFP in Karamoja. With UNICEF support TFP geographic coverage has grown from 33 sites in 2009 to 111 in 2012, including nine health centres offering ITC (HC IV) and 102 health centres offering OTC (HC II and III). As planned, two OTCs were established with support from the DFID grant (Apetolim HC II in Kaabong and Nabual HC II in Moroto) to bring services closer to the communities. Coverage was therefore enhanced, however despite these actions coverage was approximately 60%. / If there is a medical complication SAM cases are referred to ITC, in accordance with IMAM Guidelines. ITC can only be offered in HC IVs and hospitals, which are located in the major towns. This underlines the importance of the early identification and effective referral from communities of SAM cases. Some health centres reported admitting isolated SAM cases with complications despite not having appropriate facilities because the mothers concerned were not prepared/able to go to town and tend their child there (Kakingol HC III in Moroto District and Kacheri HC II in Kotido District). / Coverage and distribution – community based supplementary feeding programmes (CBSFP): IMAM targets are >70% coverage and WFP set a higher target of 80%. The ‘distribution’ target for SFP is >90% of the target population lives within 1 day return walk from the centre. This is essentially a geographic coverage target. / WFP reported that the actual coverage of CBSFP at the time of the surveillance round in May 2012 was 81% (estimated percentage of moderately malnourished children from 6 to 59 months enrolled). There may be weaknesses in the way this is calculated. WFP recognise that a more effective method of measuring coverage is required, and is beginning to monitor coverage by comparing the anticipated under-5 population in each village with the number screened by VHTs. A few sub-counties in southern Karamoja appear to have had coverage of less than 70% due to the disbursed nature of settlement and distance from CBSFP sites. / To achieve its current coverage WFP progressively established 150 CBSFP sites across Karamoja, including a site in 90% of sub-counties. On the basis of this WFP refers to geographic coverage of 90%. However actual coverage is a better measure. / 4) The efficiency of referrals to TFP and from TFP to CBSFP / The efficiency of referrals is not well understood. This includes the efficiency of VHTs referrals of SAM cases to TFP, and the proportion that are actually enrolled in TFP. Ideally data monitoring should enable a comparison of: a) estimated prevalence of SAM, b) the proportion identified and referred to TFP by VHTs or from CBSFP screening and c) the number actually admitted for treatment. This information was not monitored. Data is available: for b) and c) through combining information reported at both ends of the referral system - comparing sub-county VHT & CBSFP referrals with OTC admissions. / There are several factors reducing referral rates to TFP. WFP’s IPs reported that mothers prefer to have their children admitted into CBSFP because they prefer the CBSFP supplement (“family porridge”) to the alternative (Plumpynut) provided under the TFP. Even when mothers are referred to TFP it is reported that many attend CBSFP screening hoping to be admitted. Additional factors include: distance to the health centre and a lack of understanding by mothers’ as to why the child is malnourished. Where health workers are involved one would expect more effective referrals. However, delays in the initiation of treatment were noted in some OTCs as the patient had to wait for OTC opening day. OTC admission should be available on any day, and this is the case in some if not most health centres. / The programme target was that 70% of the children discharged from TFP would be admitted to CBSFP follow up. The reviewer was not able to find any data on performance against this target. In Moroto District referrals from OTC to CBSFP can be problematic. Health staff at Nadunget HCIII said mothers were not always briefed about the continuum of care from TFP to CBSFP because staff were often busy or those discharging were not fully familiar with the nutrition programme. One practical obstacle mentioned is the periodic lack of referral slips. In Kotido District referrals from OTC to CBSFP may be more effective because district health staff attend CBSFP screening and can check that their former OTC clients are present. In Kotido WFP included poor referral to CBSFP on their short list of challenges. / WFP reported that one of the ways of improving referrals would be to have that the same VHTs for both SFP and TFP, and to use the same partners to implement both programmes. WFP and UNICEF are in discussions to ensure that referral mechanisms are improved. / Recommendations: / UNICEF and WFP should work with VHTs and health centre staff to ensure that referrals to TFP and from TFP to CBSFP are effective. Information on referrals of TFP to CBSFP should be available to district nutrition focal points in real time so that any apparent failures in the referral process can be addressed. This information could possibly be incorporated in UNICEF’s Dashboard. For referrals to TFP it would be useful to include a ‘background figure’ of expected SAM caseload i.e. three figures – expected SAM caseload, referred and admitted. / UNICEF should further discuss with District Health Officers (DHOs) the impediments to TFP admission. / 5) Routine medication / Table 3 of the IMAM Guidelines specifies that routine medication should be part of SFPs, which are a key part of the management of MAM. The guidelines are however based on implementing SFPs in health centres. Implementing routine medication in the CBSFP is therefore dependent on the capacity of district health staff to be present at outreach sites, and to be consistently supplied with the relevant medication. / WFP’s IPs have tried to make these links, offering to transport health centre staff to outreach sites and often doing so, where medication and immunisations have been provided. In northern Karamoja health centre staff participated in CBSFP, WFP’s IP Community Action for Health (CAfH) providing an incentive for health centre staff. Medication was however not generally provided on site, but through referral to health centres. In southern Karamoja health centre staff did not typically participate in CBSFP, even when WFP’s IP Andre Food Consult (AFC) offered transport. AFC hired a nurse to help fill this gap. / Vitamin A should be given on admission to SFPs to children over six months who have not received it in the preceding month. This was not occurring routinely in northern or southern Karamoja. In northern Karamoja health centre workers could provide vitamin A, but only refer to the health centre upon diagnosis. Theoretically this means that roughly two thirds of moderately malnourished children are not covered by Vitamin A upon admission to CBSFP (one third would have received Vitamin A on a Family Health Day conducted in the preceding month). / IMAM Guidelines specify that deworming should also be given to all children admitted to SFP if not received in the preceding 4 months. This is not done routinely and deworming is only occasionally available from health workers. Deworming on diagnosis should be available at CBSFP screening but it should not be necessary to provide routine treatment to all those admitted as Family Health Days provide good coverage. / Recommendation: WFP and IPs should discuss with DHOs how to ensure a district health worker is present during CBSFP distributions to screen the children and administer tests and provide medication in conformity with IMAM guidelines. Providing Vitamin A upon admission to CBSFP (if not received in the preceding month) is indispensable. To be effective it needs to be given on site, not on referral. De-worming tablets and iron should also be available on site. / In southern Karamoja this may need to involve synchronising district health outreach with CBSFP although it appears there are not enough health workers conducting outreach to cover all CBSFP screenings. The health workers are also reliant on government PHC funds for their movement. Where it is not possible to have a district health worker present it is suggested that the District Health Officer authorise WFP’s IPs to administer Vitamin A. / Table 6 in the IMAM Guidelines specifies medical and dietary treatment for TFP. Amoxicillin should be given routinely. This was however not followed as the amounts provided to the health centre by the MoH is generally not sufficient. / Recommendation: UNICEF should discuss routine medical treatment on initial visit to OTC with DHOs. / 6) Admission and discharge criteria / Admission to SFP or TFP can be based on either MUAC or Z-scores - both should be taken. Some CBSFP sites and some health centres rely solely on MUAC, which introduces exclusion errors. / Recommendation: WFP should ensure that IPs follow IMAM admission criteria. UNICEF should discuss admission practices in health centres with the nutrition focal persons in each district. Discharge criteria should also be addressed. / 7) Adults and the elderly / The IMAM guidelines allow for the acutely malnourished of any age to be admitted to CBSFP and TFP using an adult MUAC tape (22 cm cut-off). It was found that in Karamoja this qualifies many older adults and elderly (over 60). At one site in 2010 in Kotido District more adults/elderly than children were admitted. The cut-off was subsequently amended to 18.5 cm. Even using this measure one third of those admitted to SFP at the Nakapelimoru Primary School site in Kotido District in November 2012 were adults or elderly (13 of 39 admissions). There were a substantial number of elderly women in attendance on the day of the review visit to that site (26 January 2013). Only one elderly woman was interviewed, who confirmed she also participates in WFP’s Extremely Vulnerable Households feeding programme. Joint district/WFP/CAFH monitoring conducted in August 2012 raised as an issue the “overwhelming number of elderly in the programme who take longer to recover”. / Although the inclusion of adults and the elderly based on a MUAC reading is consistent with the IMAM Guidelines it is doubtful that the elderly will respond physiologically as generally expected and be discharged ‘cured’ within three months. / Recommendation: WFP should request its IPs to monitor and report the proportion of adults and the elderly who are non-respondent at the end of three months. WFP should also consider asking its IPs to use BMI in addition to MUAC for admission and discharge. / 8) Efficiency of supply / WFP’s supply of Supplementary Feeding Programme ration ingredients (CSB, oil, sugar) to its warehouses in Moroto and Kotido was good under the circumstances (well over 90%). / Table: WFP planned vs delivery of CBSFP commodities to final distribution sites (in tons) / Month Planned Actual / November, 2011 191.846 189.108 / December, 2011 191.846 137.388 / January, 2012 191.846 189.625 / February, 2012 191.846 178.976 / March, 2012 191.846 188.744 / April, 2012 191.846 165.547 / May, 2012 191.846 162.855 / June, 2012 191.846 145.744 / Total 1,534.770 1,357.987 / This information indicates an overall shortfall in supply of 11.5%. However, this is based against forward estimates of 24,000 beneficiaries per month, while actual monthly requirements fluctuated below 24,000. Substantial problems were also reported in transporting commodities from warehouses to final distribution sites. / For the Therapeutic Feeding Programme UNICEF’s objective was to support the procurement of supplies (RUTF, F100, F75) to ensure “zero” stock-outs. This was to be combined with strengthened logistics and end-user monitoring systems. A report on planned vs actual deliveries over the project period was not obtained during the review however supply generally appears to have been good, given the support of UNICEF’s IPs. UNICEF did report a delay in procurement at the beginning of the project period. / Recommendation: WFP set a monthly target for making CBSFP commodities available to IPs at final delivery points (FDPs) in good time for their distribution to MAM clients. This should be based on input from WFP’s nutrition and logistics personnel and should be in consultation with IPs. The target could for example be 85% of the time with ‘in good time’ allowing for perhaps a delay of no more than seven days. A related target could be set of no delays of more than a fortnight. Both would be monitored and reported. / 9) Community based supplementary feeding programme (CBSFP) ration size / The appropriate ration for supplementary feeding according to accepted international standards is a daily supplement of 500-700 kcals for a closely monitored feeding programme. If dry take home rations are provided, they should provide 1,000-1,200 kcals to account for sharing at home. / WFP aims to provide 1,140 kcals (within the recommended range). As a fortnightly ration this requires a pre-mix of Corn Soy Blend (CSB), sugar and oil weighing 3.76 kgs. This is the ration provided in northern Karamoja by CAFH. In southern Karamoja the fortnightly ration rate is a little more – about 4 kgs – because it is derived by halving what used to be a monthly ration using a particular type of scoop. / Recommendation: WFP should consider standardising the CBSFP ration and scoop. / 10) Utilisation of take home CBSFP supplement & outpatient therapeutic care (OTC) Ready-to-Use Therapeutic Food (RUTF) / The CBSFP premixed supplementary ration is typically cooked as porridge and shared amongst siblings and / or the whole family. It is frequently referred to as “family porridge”. The amount of sharing of the supplement is known to be seasonal and stress related. / A CBSFP joint monitoring exercise for Kotido District (June 2012) reported: “From the interview with most care givers, it was revealed that food is shared with all family members of the household level since they believe that food is for everybody.” / Post distribution monitoring conducted by CAFH in Abim District (September 2012) indicated that 54% of the CB SFP was consumed by the intended beneficiary, 22% by other household members, 24% shared with kin. This is within the expectations of those designing the supplementary ration size i.e. a little over half reserved for the CBSFP client. However monitoring conducted by CAFH for Kotido District indicated higher levels of sharing. It would be useful to have similar data for peak ‘hunger gap’ months in southern Karamoja. The March 2011 evaluation of WFP’s PRRO reported very high levels of sharing. / Ready to Use Therapeutic Food (RUTF / Plumpy nut) is not shared to the same degree, but anecdotal evidence suggests there is also an issue: / Some health centre staff said it is common for mothers or others bringing a child to start consume the RUTF while walking home. / It can be used in alcohol preparation. / It can be bought in the Moroto market (UGS 500). / It is commonly referred to as ‘odii’ - the Acholi word used in Karamoja for peanut and sesame paste. / Recommendations: / WFP should ensure that post distribution monitoring conducted by its IPs yields a reliable view of the extent of CBSFP supplement sharing over time and over the seven districts. / Following the joint monitoring exercise conducted for Kotido District in June 2012 it was recommended that: “VHTs should monitor how malnourished children are being fed at household level.” VHTs should be encouraged to do so, perhaps on a quota basis e.g. visit, observe and advise 10% of households. / WFP’s IPs should not refer to the RUTF as ‘odii’. The RUTF packaging should be changed to clearly identify that it is intended for consumption by young children e.g. picture of a young child. IPs should continue drama to emphasise the need to restrict the RUTF to severely malnourished children. / 11) Process efficiency / A joint CBSFP monitoring exercise for Kotido District (June 2012) reported late arrival by clients, with the result that clients who came early had to wait for services. Long waiting times acts as a disincentive for mothers to attend, with the result that siblings and grandmothers are often asked to accompany the children. / Recommendation: WFP and its IPs should review the process efficiency of CBSFP screening and distribution. One option would be to have two sessions. / 12) Potential for contamination / In southern Karamoja AFC typically conduct CBSFP under trees, volunteer women preparing the pre-mix in 50 litre drums. The potential for human and/or environmental contamination is considerable. In northern Karamoja CAFH often use primary school buildings as CBSFP sites and mix the SFP ingredients on the day in school stores using wooden mixing paddles. / Recommendation: WFP and its IPs should review the manner in which the supplementary CBSFP ration is mixed bearing in mind the potential for human and environmental contamination. / 13) Promotion of nutrition, health and hygiene practices and other complementary practices / CBSFP screening and distribution is preceded by nutrition and health education directed at mothers and caregivers. It is appropriate to make use of this time for health and hygiene promotion activities, however only a very short period of time is available to disseminate messages - in Kotido CAFH reported taking 10 to 15 minutes; in Moroto AFC reported taking 15 to 20 minutes. It was observed that while the content of the promotion activities is acceptable, the delivery does not necessarily follow sound adult education principles. WFP have noted however that the context does not support other more effective techniques (e.g. drama groups). / WFP planned to undertake complementary activities such as community mobilisation and sensitisation, nutrition and health education, promotion of back yard gardens, creation and support of community support groups such as parental care groups, and the creation and support of parental groups to promote good health and nutrition practices. WFP’s IPs and WFP’s final report refer to some of these activities. It was not possible to verify the extent of promotional and preventative activities. / UNICEF’s proposal refers to intensifying support at the community level for the promotion of nutrition, health and hygiene practices through VHTs, women’s groups and other informal networks.[11] UNICEF reported that this was initiated. In addition to basic training, an add-on module on nutrition was introduced to enhance VHT knowledge and skills on key nutrition messages to pass on to communities. UNICEF also reported that TOT sessions were conducted with over 50 regional trainers, which cascaded the district trainings to the VHTs. / UNICEF was also to train 210 health workers in the Uganda national comprehensive Infant and Young Child Feeding (IYCF) package (30 in each district). UNICEF reported that one round of training on IYCF via district budget support was already in progress targeting about 150 health workers. IYCF promotion materials were also found in health centres. A Knowledge, Attitude and Practices survey will be conducted to determine the effectiveness of these efforts. UNICEF had also planned to assist with two quarterly integrated IYCF/IMAM support supervisions (by the DHTs) and in-service mentoring. / Recommendation: WFP and its partners, in consultation with DHOs and UNICEF, should review the effectiveness of the health and nutrition promotion component of CBSFP, both on site and out in the community. / 14) IMAM related capacity building / UNICEF’s proposal included providing technical support, in-service coaching/mentoring and supervision of 373 health workers in the 66 TFP sites to ensure provision of quality care. This was accomplished - UNICEF’s final report refers to involving 420 health workers and 102 supported TFP sites for the calendar year 2012. Technical support was provided by ACF and CONCERN Worldwide, up to October 2012. Makerere University’s Mwanamugimu Nutrition Unit also trained on the IMAM package. Good performance against IMAM standards (cure rates, etc.) provides some evidence of effective capacity. / UNICEF report that a “critical pool of health workers in the region has been trained on IMAM to ensure continuity of the services considering staff rotations and high attrition rates. However ACF noted in its final report noted that although training targets were achieved challenges remained including high health staff turnover, the need for continued on-the-job training, and health office managerial challenges.[12] Regarding training focused on the effective use of IMAM monitoring and supervision tools ACF reported that the DHOs, medical doctors and Medical Superintendents from the hospitals although invited did not attend training. / UNICEF’s proposal also refers to mobilising all VHTs (2,968) in the catchment areas of the health facilities for case identification, referral and follow up. UNICEF reported that mobilisation took place in July/August 2012 to conduct a mass screening exercise in response to the high SAM rate reported in May. WFP’s IPs provided training and support to VHTs. / Impact Weighting (%): 40% / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A
[2] Based on extrapolating WFP’s planned vs actual tonnages
[5] New admissions provide a means of both estimating the number of individuals remaining in the caseload over time, and provide an indication of the efficiency of CB-SFP. WFP reported that new enrolments per month averaged about 3,700 moderately malnourished individuals (mainly children). This suggests that in any one month, over 80% of children were in the programme in the preceding month. If there were no repeat admissions the number of individuals treated per annum would be 126,000 (assuming 21,000 treated per month and length of stay before discharged cured of two months). The actual number of individuals per annum would seem to be roughly half that – 65,400 – on the basis of treating 21,000 in the first month and then ‘substituting’ 3,700 new entrants each month. However what is not certain is the number of repeat admissions amongst the new.
[6] UNICEF Final Report February 2013 p 12. It is not clear if this is for OTC only or includes ITC.
[7] UNICEF Interim Report to DFID April 2012 and Final Report to DFID February 2013 p 12
[8] WFP End of Project Report to DFID
[9] UNICEF Final Report February 2012 p 12
[10] Coverage Assessment of the Integrated Therapeutic Feeding Program Supported by ACF Uganda, Final report, Kaabong and Moroto districts Karamoja, Uganda
[11] UNICEF proposal to DFID, p 4
[12] ACF Final Report for the period July 2010 to June 2012 p 12, 17

Output 2: Safe water facilities, sanitation and hygiene practices are provided and promoted at health centres, schools and in rural communities: 27,000 households with access to safe water through new facilities in health centres, schools and rural communities and 2,300 schoolchildren and 13,000 others with access to adequate sanitation services.
Output 2: final score and performance description: / A Outputs Met Expectation / Summary / By February 2013 UNICEF’s contractors had completed virtually all of the boreholes to be installed or rehabilitated, benefitting 51,900 beneficiaries and exceeding the target originally set of 30,000. Three town water systems had also been constructed /rehabilitated. The programme contributed to a substantial improvement in water coverage in Karamoja from 2011 to 2012: from 43% to 45% in Kotido, from 32% to 37% in Moroto and from 19% to 27% in Kaabong.[13] / There are indications that operation and maintenance remain a challenge. Not including animal troughs in the scope of work for the new boreholes where mixed human and animal use is anticipated was an oversight acknowledged by UNICEF, which will be reviewed in future designs. / By the end of December 2012, UNICEF had constructed 135 stances of drainable latrines in 17 primary schools benefiting 7,536 pupils and exceeding the original target of 2,300. The target for benefitting people using the health facilities was also met. / UNICEF’s IPs and the districts carried out hygiene promotion in communities, health centres and schools. UNICEF staff reported that 96 out of 1,726 villages (5.56%) in Karamoja have been ‘triggered’ for Community Led Total Sanitation (CLTS) and that to date 22 villages had achieved open defecation free (ODF) status.
Final results / Output Indicator 2.1: Number of households with access to safe water through new facilities in health centres, schools and rural communities (attributable to DFID) / UNICEF’s Intermediate Report of April 2012 refers to plans to: / drill 58 new boreholes (across the 7 districts) / rehabilitate 118 boreholes (across the 7 districts) / construct Kapedo Trading Center Water System (Kaabong district) / construct Mouruita/Chesabuni Trading Center Water System (Nakapiripirit district) / rehabilitate and extend Moroto Water System. / The DFID Business Case (BC) refers only to “new” facilities – new facilities are not specifically referenced in the UNICEF proposal. There was also no reference to water systems in the BC or UNICEF’s proposal, per the last three items listed above. These programmes accounted for over 40% of expenditure on water facilities. The target specified for the number of people to be provided with access to safe water in health centres, schools and rural communities was 27,000. / The drilling, rehabilitation and construction work specified did not commence until approximately six months into the project period. UNICEF reported that this was due to the substantial time spent on identification, assessment and consultation, and the setting up of a competitive bidding process (see Costs and Timescale below). UNICEF reported that by February 2013 53 out of 58 new boreholes had been drilled and 115 out of 118 broken-down boreholes had been rehabilitated benefitting 51,900 people. Although delayed this exceeds the beneficiary targets set. Safe water coverage in schools and health units in Karamoja is now put at over 90%, which is a considerable achievement. The construction/ rehabilitation of three town water systems has also been completed, designed to serve an estimated 20,500 people (Kapedo 3,700, Chesabuni 2,800 and Moroto 14,000). / UNICEF’s proposal refers to the construction of water facilities with the provision of water treatment in the case of surface water (e.g. water from reservoirs) to provide safe water. UNICEF did not access surface water during the programme. The BC also refers to water treatment including at the household level (chlorination) - UNICEF did not treat household water during the programme. / An explicit assumption was that WASH infrastructure can be properly maintained and utilised by communities. It was evident from field visits that operation and maintenance is an issue for boreholes recently provided and rehabilitated. UNICEF recognises that operation and maintenance needs strengthening, particularly in communities (boreholes are better managed in health centres and schools) and that the low level of community participation in the management of water services is a critical challenge. UNICEF has made provision for five years maintenance in its recent contracts for drilling / rehabilitating boreholes, and will use its own resources for this purpose. / There is currently no Ugandan standard to guide the inclusion of animal troughs in borehole design. It would appear to be important however to include them where mixed human and animal use is likely. / Recommendations: / UNICEF should seek funds to complement all the new and rehabilitated community boreholes funded by DFID with animal troughs and ensure operation and maintenance is assured. / UNICEF should convene consultations with other agencies/organisations working in WASH (including Uganda Red Cross) to discuss engineering (hardware) and community mobilisation (software) approaches. / Output Indicator 2.2: Number of households with access to adequate sanitation services (attributable to DFID): target 2,300 schoolchildren and 13,000 others. / UNICEF’s interim report of April 2012 refers to plans to construct 135 stances of drainable latrines in 17 primary schools. UNICEF staff reported that the plans for latrines in schools had been realised by December 2012 benefiting nearly 10,000 pupils in Abim, Kaabong and Amudat districts. Coverage of school children was therefore exceeded fourfold. / Output Indicator 2.3: Number of people reached by messages on hand washing and safe hygiene practices (attributable to DFID) / UNICEF’s proposal refers to promoting safe hygiene practices including hand washing in rural communities, school and health centres. The target of 27,000 reflected the target for output indicator 2.1, indicating that messages would be delivered in tandem with the provision of new/rehabilitated boreholes. / UNICEF’s IPs reported carrying out hygiene promotion in communities, health centres and schools. Villages were not visited during the review to observe these activities and it was not possible to aggregate partner activities to determine if the target of 27,000 had been reached. As part of building of capacity of local government, UNICEF involved the districts together with NGO partners in hygiene promotion. Methods by partners and districts included total sanitation approaches - hand washing, cleaning of the environment, construction of rubbish ditches etc. / UNICEF reported that the methods used by partners and districts included the community led total sanitation (CLTS) approach. UNICEF staff reported that by December 2012 104 (94%) of health units and 224 (84%) of primary schools with approximately 100,000 pupils in Karamoja were supplied with hand washing facilities. The approach to community hygiene promotion changed during the course of implementation from Participatory Hygiene and Sanitation Transformation (PHAST) to CLTS[3]. PHAST includes providing digging kits and sometimes slabs while CLTS does not. UNICEF staff reported that 96 of 1,726 villages (5.56%) in Karamoja have been ‘triggered’ for CLTS and that to date 22 villages had achieved open defecation free (ODF) status[4]. / The BC refers to the provision of critical commodities to promote hygiene practices such as soap distribution to each household and school child alongside promotion messages. This was not implemented. An explicit assumption in the logframe is that messaging on hygiene practices results in behaviour change. The reviewer participated in several discussions with UNICEF, WFP and implementing partner staff regarding cultural and practical obstacles to bringing about behavioural change in Karamoja, particularly in relation to latrine use. Different views were expressed as to the effective application of the CLTS approach in Karamoja, including the need to ensure effective monitoring and evaluation, and that adequate time was spent with communities to inform the development of a Karamoja specific methodology. / Impact Weighting (%): 40% / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A
[13] Sector Performance Reports quoted by UNICEF
[3] THE CLTS approach has been endorsed by UNICEF and the GoU
[4] There is not currently an agreed protocol for declaring ODF.

Output 3: Communities and districts are better able to obtain and analyse timely, frequent and quality data on nutritional vulnerability and to take action accordingly (targets 180 VHTs collecting community vulnerability system data in 2012; 75 healthcare workers receiving refresher training on community vulnerability system and 120 on food security and nutritional assessments in 2012; and 2,000 children under five screened for malnutrition and referred to care as needed in 2012).
Output 3: final score and performance description: / B Outputs Moderately Did Not Meet Expectation
Summary / Training and other activities have been undertaken by UNICEF to strengthen the capacity of districts to obtain and analyse timely, frequent and quality data on nutritional vulnerability. The final score reflects an underachievement based on the fact that this approach is yet to result in district health teams being able to monitor and respond to malnutrition in Karamoja through routine surveillance. The systems UNICEF is developing, including the electronic ‘Dashboard’ in the District Health Office, do not yet present comprehensive information and the District Health Teams do not rely on the information so far available. Moreover it seems the system will need to be redesigned as it may not be realistic to have VHT reporting by SMS directly to the district health office. / The capacity of “communities” is referred to in the output statement however the programme is focused on health services, and the role of VHTs in screening, referring and reporting. Implementation of this output was delayed and continued during the no cost extension. / UNICEF and WFP have developed a common approach to address spikes in MAM/SAM rates. The system and procedures specifying how to respond when the results exceed emergency thresholds needs to be reviewed, and the link with national disaster management planning strengthened. / Final results / Output Indicator 3.1: Number of VHT members collecting community vulnerability system data (attributable to DFID) / UNICEF describes its contribution to routine nutrition surveillance in support of IMAM as a community vulnerability system (CVS). It operates at three levels – community, health centre and district health team. At the community level it includes supporting routine screening by VHTs for GAM and SAM and providing a mobile phone SMS based reporting platform for VHTs to report directly to the district health office (numbers screened each month and MAM and SAM referrals). The UNICEF SMS platform is mTRAC[5]. The information transmitted is available to the district health team as a ‘Dashboard’. / The target was to have 180 VHTs reporting by SMS, originally by end May 2012, latter extended to end November 2012. UNICEF reports that over the period September 2011 to December 2012 a total 248 VHTs were trained to collect CVS data (64 in Kotido, 60 in Napak & 124 in Moroto). This is roughly 17.5% of VHTs in Kotido and Napak Districts and approximately 35% of VHTs in Moroto District[6]. / Although training has been conducted, VHT SMS reporting as a CVS component is not yet fully functional. In Kotido District the DHO stated that they are not relying on the ‘Dashboard’ information due to its limited input base. Although some VHTs have been trained few have mobile phones and few are adept at text messaging. There are also network coverage issues. This has led to second thoughts about the system and VHT level SMS reporting, and training, has been put on hold in Kotido District. For Moroto District the DHO reported that although the system is promising it is not strong because not enough VHTs are reporting. / The BC refers to support for district based monthly analysis of CVS data. It is unlikely this is being conducted. The regular district Quarterly Household Register reporting form that feeds into HMIS includes GAM and SAM cases derived from information aggregated at parish and then health centre levels. In addition UNICEF’s IPs introduced IMAM reporting forms for health centres to report weekly and monthly to the DHO their SAM admissions, deaths and defaulters as well as OTC stock balances (RUTF, F100 and F75). UNICEF regards these as standard MOH reporting tools. Nevertheless they are separate forms, which health centres sometimes do not send off to the district, the central reporting information being considered as more critical. / UNICEF’s IPs have also trained health workers to send the IMAM related information by SMS. Many health centres are perhaps doing so but certainly not all due to gaps in mobile network coverage. / Recommendation: UNICEF and the MoH should consider redesigning the CVS, with data transmitted at the health centre level. The transmission of health data by SMS offers the potential to get information to the district far more quickly, however the question remains whether it is appropriate to seek to establish such a system for nutrition data only. The Dashboard effectively is a parallel system (as noted by the Kotido District Health Officer), as it is not part of HMIS – the HMIS captures numbers screened by MUAC and identified as having GAM or SAM (this information is entered on the Register). / Output Indicator 3.2: Number of health care workers receiving refresher training (attributable to DFID) / The targets were to train 75 healthcare workers in routine nutritional surveillance (CVS) and 120 in periodic surveillance (Food and Nutrition Security Assessments or FNSA) by end May 2012, extended to end November 2012.[7] / UNICEF reported that by the end of December 2012 that 23 out of 55 health workers in Moroto, Napak and Kotido Districts had received refresher training on CVS (conducted by UNICEF’s partner ACTED). This is an under-achievement. UNICEF also reported that by the end of December 2012 120 health workers received refresher training as enumerators during each of the two FNSA surveillance data collection rounds. This aspect exceeded expectations. / The FNSA had been conducted each May, September and December by ACF since 2009 in cooperation with DHOs (the last involving ACF was May 2012). Based on recommendations from a UNICEF consultant UNICEF will henceforth support two assessment rounds, with support from Makerere University’s Institute of Public Health in April/May and December each year. The rationale is that three rounds is expensive, and that if the routine CVS is effectively implemented this will provide an indication that SAM is on the rise to trigger response. / UNICEF also reported on a target not included in the BC logframe - providing refresher training on Infant and Young Child Feeding to 30 health workers per district - 379 health workers receiving training during the period September 2011 to end December 2012. / Output indicator 3.3: Number of children under five screened for malnutrition and referred to care as needed (attributable to DFID) / The logframe specifies a target of 2,000 (2012) – these targets seem very low, even if considered as representing monthly targets. It is unclear how they relate to the targets set for Output 1. UNICEF staff in Karamoja reported a result (July 2012) of a total of 215,272 children screened, of which 10,754 were referred to SFP and 1,842 referred to OTC. / Impact Weighting (%): 20% / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A
[5] mTRAC is an innovative program using SMS to track the health facility stocks of essential medicines. mTRAC allows health facility workers to send government reports by SMS, including real-time data to map facility stocks. The aim is to avoid unnecessary stock-outs and to ensure transparency and accountability for the drugs. Following a pilot program, mTRAC has been taken over and is operated by the Ministry of Health and has sustained a 90 percent response rate for weekly reports via SMS.
[6] The number of VHTs currently reporting by mTRAC was not recorded
[7] DFID’s BC refers to refresher training on FNSA methodology for 140 health workers, 7 district surveillance focal persons and 7 district health officers.

## Section B: Results and Value for Money.
1. Achievement and Results
Has the logframe been changed since the last review? / No. There was no previous review and the BC logframe was not been changed or updated. / There were differences in content and targets between the BC logframe and the agencies’ proposals. Although the BC was developed with input from UNICEF and WFP, the final BC was reportedly not shared with UNICEF or WFP, and the logframe not subsequently reviewed or updated to reflect partners proposals. / DFID’s formal agreement to UNICEF’s request for a no cost extension did not specify which part or parts of the programme were extended. Correspondence indicates the delay was related to the WASH component, however the extension was considered by UNICEF to be for all components. This complicates the issue of the period that should be used for determining results for the therapeutic feeding and nutrition surveillance components. UNICEF’s final report is for the calendar year 2012, which does not capture November-December 2011. UNICEF also implemented activities that were not included in its proposal (e.g. town water supply systems) and also supported some activities included in its proposal with funds from other donors (e.g. household sanitation). There is no documentation indicating that these changes had been agreed with DFID. Nonetheless, it is possible to assess the the programme reached approximately the number of beneficiaries intended, albeit over a slightly longer timeframe. / Recommendations: DFID needs to apply greater oversight and consider quarterly narrative and financial reporting for any further interventions funded in Karamoja through UNICEF and/or WFP. / Final Output score and description: / A Outputs Met Expectations / Outputs 1 & 2 were rated as A, and Output 3 as B. / Based on the impact weighting (80% outputs 1 &2, 20% output 3, the overall output result is A.
Direct feedback from beneficiaries / Feedback was obtained from beneficiaries during the course of CBSFP screening and distribution exercises, including some home visits, and during visits to new/rehabilitated boreholes. The CBSFP was universally praised, but worryingly because it provides “family porridge”- participation in the programme is clearly a household coping strategy. When questioned on the issue of sharing the supplementary ration women stressed that it is needed by the whole family and they are unable to restrict it to the child enrolled in the programme. / The additional water resources were also praised. No concerns were expressed regarding poor operation and maintenance. More reflective feedback from female beneficiaries concerned the injustice of gender roles in Karamoja. Women complained of their work burden and the limited assistance their husbands provide.
Overall Outcome score and description: / B Outcome moderately did not meet expectations / The expected Outcome was reduced levels of severe and moderate malnutrition particularly among children under five (target 10% GAM and 2.5% SAM by March 2012). / Outcome targets were not realistic given that GAM/SAM rates are influenced by several factors / underlying causes outside of the scope of the programme. At most the programme could be expected to stabilize rates and prevent the development of a critical situation (WHO: GAM > 15%). The BC had referred to stabilising the situation by maintaining GAM and SAM within safer levels across Karamoja. It is important that these observations and understanding are translated into the setting of realistic targets for future programmes. / Severe Acute Malnutrition (SAM): The key issue is the persistence of high SAM rates. The project target was 2.5% by end March 2012 against a baseline of 2.8% in May 2011. This rate was not realized. Although not significantly different from the target the May 2012 nutrition surveillance report found an overall rate of 3.1% (2.3-4.1, 95% CI).[14] The rate differed from district to district but the target 2.5% was exceeded in 5 out of 7 districts. Moroto combined with Napak was the highest at 4%. / The DHO/ACF/UNICEF nutrition surveillance report that since May 2010 there had been an increasing trend in the prevalence of SAM within Karamoja, the proportion of severely malnourished children increasing from 20% to 26% of all malnourished children. The increasing trend in the proportion of children with SAM was taken to indicate that the safety nets established to prevent a deterioration of nutritional status in children were not adequate to address the high numbers of children identified with nutritional needs.”[15] However, one of UNICEF’s IPs, CONCERN Worldwide, reported that: “Through the identification and referral of SAM cases to nearby health centres for management, nutrition related morbidity and mortality reduced across Karamoja.”[16] / Active case finding (mass screening) was carried out between June and October 2012 in four districts (Amudat, Nakapiripirit, Abim and Kotido Districts). This was a recommendation made by ACF following the May 2012 surveillance, which identified many acutely malnourished children not on treatment. This would seem to reflect inadequacies in the effectiveness of nutrition interventions, particularly ‘capturing’ SAM cases. / Global Acute Malnutrition (GAM): The project target was to reduce GAM rates to 10% by end March 2012 against a baseline of 12.8% in May 2011. This was not realized. The May 2012 nutrition surveillance report found on overall rate of 11.7% and rates in excess of 10% in all districts except Abim. The report’s authors observed: “Compared to May 2011, there was no significant change (p>0.05) in the GAM rates for the region, however, a slight reduction was registered in the entire region from 12.8% (11.0-14.9) to 11.7% (10.2-13.4), the highest reduction was noted in Nakapiripirit from 20.4% to 13.1% (p<0.05) for the same period as 2011.[17] More broadly it was observed that there was no significant difference in the prevalence rates between May 2010, May 2011 and May 2012 (P>0.05). / It was agreed by UNICEF and WFP staff in Karamoja who participated in the review that it was unwise to include the achievement of specific GAM and SAM rates as targets in the project logframe, given that reduction in these rates requires a holistic approach to underlying causes of malnutrition. Programmes such as the UNICEF and WFP programmes that address malnutrition by treating individually malnourished children have a direct live saving impact, although this impact may be limited to the duration of the programme unless attention is also given to addressing the underlying causes malnutrition and building local capacity and supporting a wide range of livelihood and development programmes. / There was mitigation of GAM and SAM rates, and deaths were averted. SAM and GAM output targets were also realised. Similar interventions in 2010 and 2011 did not prevent GAM and SAM rates climbing by May in each of those years and exceeding acceptable levels. Coverage has been expanding but the underlying causes of malnutrition have remained more or less a constant - food insecurity, disease burden, poor feeding practices, etc. / In terms of design, very little work was done on outlining the assumptions and risks associated with achieving the anticipated outcome. At the outcome level the BC logframe refers to an assumption that climatic conditions do not deteriorate beyond currently envisaged scenarios and that no major natural disasters occur. No internal design assumptions are mentioned, and a more rigorous approach should be adopted in the design of future programmes. / Recommendation: In the short term, WFP and UNICEF should work more closely together to more effectively and efficiently identify and treat acute malnutrition in Karamoja. This should be regarded as ‘core business’ and no other imperatives should detract from this the risks to child growth, mortality, and morbidity rates. More work needs to be done on ensuring an understanding of the use of nutritional data in food security and early warning systems, and in programme monitoring, including the use of this information in advocating for programmes that address the underlying causes of malnutrition / Impact and Sustainability / Impact / The BC refers to maintaining global and severe acute malnutrition rates within safer levels, helping to bring down child mortality rates and avoid over 1,000 preventable child deaths. The impact indicators in the BC logframe are under-5 mortality rates (target: 160 per 100,000 live births against a 2008 baseline of 174) and crude mortality (target: <1). / For under-5 mortality rate used in the BC is an indication of the probability of dying between birth and five years old, per 1,000 births. This is the wrong indictor to use for this programme. The Crude Mortality Rate (CMR) or Under five mortality rates (U5MR), expressed as deaths per 10,000 people per day, would have been a more appropriate emergency indicators. Data collected during nutritional surveillance rounds could have usefully indicated a deterioration or stabilisation of the situation based on standard U5MR or CMR benchmarks[8]. / The calculation in the BC is that 1,143 lives would be saved over 8 months through the WFP and UNICEF supplementary and therapeutic feeding interventions[18], assuming identification and treatment targets were met. This calculation was based on death rates for the severely malnourished, with 70% intervention effectiveness, being almost halved, from 30/100 to 18.45/100. For the moderately malnourished, with 70% intervention effectiveness, death rates are more than halved - from 5 to 2.2 per 1000 per month. [19]. Based on the above a total 950 lives were saved (122 from CBSFP and 828 from TFP). This is based on 43,600 individual CBSFP beneficiaries over 8 months and 6,167 11,480 individual TFP beneficiaries over 10 months (7,175 x 1.6 incidence). / The impact of the programme on the capacity of district health teams to monitor and respond to malnutrition in Karamoja was less than expected given that the primary innovation introduced by UNICEF into routine surveillance (reporting by SMS), however valuable and promising, is yet to deliver a product that the district health teams can and will rely on (the Dashboard). On the other hand all the engagement and training undertaken by UNICEF and WFP’s partners CONCERN Worldwide, ACF, CEVSI, ACTED, CAFH and AFC had a substantial impact on capacity from VHTs to health centre staff to district health teams, although this needs to be effectively measured. Walking into a rural health centre in Karamoja one can’t help being impressed by how well they seem to operate relative to any other institution or service. / Sustainability / The direct benefits to communities are short term only. Lives were saved, and additional water has been provided - operation and maintenance however is problematic. Because vulnerabilities remain, the same or similar interventions will need to continue until such time as there is a sustained change in the fundamental circumstances of Karamoja e.g. food security, health system provision and access. / There is a desire for change by government, donors and agencies, including shifting the emphasis from managing acute malnutrition to addressing under nutrition in the first 1,000 days of a child’s life. However, in the short term it is hard to see new approaches could immediately substitute the need for current range of programmes given chronic food insecurity. / There would appear to have been sustainable changes at the institutional level. Training has had on impact on district health service capacity to identify and treat acute malnutrition in accordance with IMAM. A significant amount of training was provided to VHTs, clinical staff and DHTs. However, it is unclear what further training and level of technical backstopping is still required. UNICEF reported that a critical pool of health workers had been trained on IMAM to ensure continuity of the services considering staff rotations and high attrition rates”.[20] This included over 400 health workers from over 100 implementing sites. All the VHTs (nearly 3,000) have been trained on the nutrition module. / CONCERN reported that the training was successful and knowledge and skill levels in the health centres were sufficient to implement IMAM. CONCERN also noted a number of challenges to effective implementation, these including: high staff turnover, absenteeism, and gaps in management and supervision capacity. During the programme CONCERN provided supervision on a continuous basis, consistently identifying issues and addressing them at site or reporting them to DHOs for action. The key question for the future is whether IMAM services will be able to maintain quality standards without this level of management and technical support. / It appears from the field visit for this review that there are relatively high levels of institutional and individual commitment within the district health services. However immediate challenges include: / The supply chain of essential IMAM supplies (RUTF, essential drugs & F100 & F75 milk) which is now a district responsibility. / The compilation of monthly nutrition reports at the health centre level and their submission to the district (attached to HMIS). / The conduct by district health teams of their quarterly support supervision visits to health centres. / The identification, referral, admission and treated and children suffering from SAM. / These indicate that additional support to existing services is likely to be required to improve management and coverage. This should be designed in a way that supports district health plans and capacity without compromising programme integrity or accountability. / Essential IMAM supplies are not part of the MOH drug /supplies logistics chain and thus fall outside MoH local transportation contracts. The district now pushes supplies to the periphery opportunistically i.e. by any vehicle moving. For example, the Nadunget HC III reported that the ambulance is used to resupply RUTF. UNICEF will step in in an emergency. UNICEF has held discussions with WFP with a view to taking advantage of their wide logistic network to deliver IMAM supplies to the peripheral health centres. / In Moroto District it is evident that the supply of UNICEF printed client cards once provided by ACF is proving a problem and ACTED stock reporting forms are now missing. (The District Health Inspector suggested at one health centre that they include photocopying the forms in their budget.) / The VHTs are an essential element underpinning both CBSFP and TFP. The ability of VHTs to deliver is dependent on many important factors including (but not limited to): lack of a consistent/regular monthly stipend (and dissatisfaction with the low rate vs. cost of living); inconsistency in the provision of materials (IMAM reporting tools, bicycles and other materials); infrequent follow up of their activities; and IPs competing for their services. It would be helpful if the MoH could pay the Ugs 10,000 per month incentive that was promised when they were originally mobilised. Routine nutrition surveillance (CVS) is accepted as a VHT and health centre responsibility (albeit competing with others). The SMS based reporting system introduced by UNICEF is not currently sustainable without on-going support. Paper based IMAM reporting to the district will need to be maintained for now, even if in parallel. / Periodic nutrition surveillance was undertaken up to the May 2012 round by DHO/ACF with UNICEF assistance. This is now to be undertaken with more reliance on the districts with technical support from the Institute of Public Health, particularly in relation to data analysis and interpretation. Nutrition surveillance focal points have been trained in each district in FNSA methodology as well as 120 health workers. Nevertheless periodic surveillance will require on-going support from UNICEF for the foreseeable future.
[14] DHO, ACF and UNICEF Nutrition Surveillance Report May 2012
[15] Ibid p 9. See also p 23.
[16] Concern Worldwide, IMAM Health Facility Assessment, September 2012, p 4
[17] DHO, ACF and UNICEF Nutrition Surveillance Report May 2012, p 9
[8] CMR: 1/10,000/day ‘serious situation’; > 2/10,000/day ‘out of control’ U5MR: 2/10,000/day ‘serious situation’;4/10,000/day ‘emergency out of control’
[18] This assumes 1 child death averted is equal to 33 DALYs (WHO)
[19] Malnutrition and Mortality – the use of epidemiological tools in conflict-affected populations; http://conflict.Ishtm.ac.uk/page_139.htm
[20] Ibid

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / There were no budget revisions. UNICEF’s extension was at no cost to DFID. / 2.2 Key cost drivers / The main cost driver for the nutrition programmes was food costs (1,404 tons of CSB, sugar, oil) budgeted by WFP at $1,204,000 excluding transport and other costs (61% of total costs of these activities). / The main cost of the WASH program was water supply infrastructure budgeted by UNICEF at $989,485 (78% of total). Of this approximately 44% was for three town water supply system installations/rehabilitations, making these the most expensive single investments. / 2.3. Was the project completed within the expected timescale: No / DFID funding was originally intended to cover the eight-month period August 2011 through March 2012. However the project actually started in November to be completed by June 2012. WFP completed its activities within the period specified in its Letter Of Undertaking, having requested a no cost extension to the end of November 2012, which was granted. Work on the WASH component extended into 2013. / In requesting the extension UNICEF reported that as of July 2012 overall progress under the WASH component was assessed at >56% and that the slower than expected progress was explained by exigencies in the identification and verification of location/sites in collaboration with ministry/district officials, the competitive bidding process (which was finalized by mid- March 2012) and UNICEF internal delays caused by the introduction of a new financial transaction system in January 2012 globally. / Unusually heavy prolonged rains contributed to further delays. The planned work was 58 boreholes to be drilled and 118 for rehabilitation. By end December 2012 53 boreholes had been drilled and 115 rehabilitated. UNICEF intended to complete the remaining works by end of March 2013. / It was unrealistic to expect to complete the borehole construction and rehabilitation works within the original 8 month period to envisaged and this probably should have been recognised by DFID, UNICEF and WFP from the outset

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / The evidence in the BC refers to global evidence on the effectiveness of sanitation and hygiene promotion, ranking it higher than any other form of health intervention. It is not clear to what extent this evidence was drawn from contexts similar to Karamoja, and what assumptions were made regarding the effectiveness of sanitation and hygiene promotion interventions. WFP did not reassess its approach in the course of implementation. UNICEF and its IPs made some changes from the PHAST to the CLTS approach to sanitation. / Neither WFP nor UNICEF specified a theory of change for the programme although the intervention logic is fairly straight forward. / 3.2 Set out what plans are in place for an evaluation. This was a short term humanitarian programme which supported existing programmes managed by UN agencies which were subject to the UN’s cycle of programme management and evaluation which this PCR has drawn upon.

4. Risk
4.1 Risk Rating (overall project risk): Medium / The risk rating did not change over the life of the project. / 4.2 Risk funds not used for purposes intended / The BC rates financial risk as low given that WFP and UNICEF managed the funds. This seems appropriate given both agencies have clear financial reporting and management systems. The review however did not consider the application of these standards and systems. / UNICEF previously provided funds directly to the districts for the installation and rehabilitation of boreholes, but now contracts directly. This reduces risks considerably. A remaining area of risk may be associated with the supervision of borehole installation and rehabilitation work. UNICEF however did not rely solely on the district for monitoring these activities, and hired a consultant to monitor and supervise construction work and to certify the completion of work. / 4.3 Climate and Environment Impact / It was not possible to measure the environmental impact of the programme.

5. Value for Money
5.1 Performance on VfM measures / Output 1 – CBSFP and TFP / The BC indicated that that evidence of inputs and efficiency in implementation through WFP and UNICEF could be collected by monitoring unit cost information, including: / Unit cost of nutrition interventions per severely and moderately malnourished child / Cost per DALY (Disability Adjusted Life Year) saved through nutrition interventions. / The unit cost of CBSFP per individual beneficiary (taking into account repeat admissions after being discharged cured) is calculated at approximately £28 (43,600 individual beneficiaries and a budget of £1,241,875). This is on the lower end of global averages estimated by the World Bank - $40 to $80 – and even lower considering the World Bank estimates appear not to factor in repeated admissions.[21] / The unit cost of TFP per individual beneficiary (taking into account repeat admissions after being discharged cured) is calculated at approximately £76 (£469,566 / 6,167). This is well below the global averages estimated by the World Bank - $200 per episode – and even lower considering it includes multiple episodes for half the children. / The number of lives saved by CBSFP and TFP for the relevant period is calculated to be 950, which is equivalent to 31,350 healthy years of life (DALYs).[22] The cost per DALY for these interventions is £50 (£1,711,441 / 31,350), which is cost-effective.[23] / Output 2 - WASH / The BC stated that evidence of inputs and efficiency in implementation through UNICEF could be collected by monitoring unit cost information, including of relevance to WASH: / Unit cost per new borehole or per pit latrine, including cost per beneficiary / WASH costs per household, to include promotion of good hygiene behaviour, sanitation facilities, and water point maintenance. / Water infrastructure was budgeted at $989,485 of which approx. 56% was for new and rehabilitated boreholes ($554,112) and approximately. 44% was for town water systems ($435,373). The cost per beneficiary of the former was approximately $10.68 (51,900 beneficiaries) and the latter approx. $21.24 (20,500 beneficiaries). / 5.2 Commercial Improvement and Value for Money / UNICEF elected to use commercial contractors to install / rehabilitate boreholes - Samadhura and China Geo. In 2011 UNICEF had contracted the Italian NGO Cooperation and Development to install 70 new boreholes and rehabilitate 120. The cost of one borehole drilled by C&D in 2011 was 18,864,200 UGX (£4,621), comprehensive of administration costs, commercial contractors were reported to providing estimates of 18,500,000 UGX (£4532) during the same period. Costs per borehole are now in the region of UGX 20 million (£4,900) due to the increased costs of fuel and materials / WFP has for some years now relied on Ugandan based institutions/organisations to implement CBSFP, with cost savings. / Recommendation: / In future programmes DFID should consider asking UNICEF to conduct a brief cost and efficiency analysis in relation to the use of the commercial contractors, including any quality and other performance differentials with NGOs like C&D. / 5.3 Role of project partners / Effective management of nutrition products is important for the VfM of nutrition programmes. Good supply chain management and effective forecasting would help in minimising the costs associated with procurement, transport and warehousing of food items. / 5.4 Did the project represent Value for Money : Yes / The programme made good progress against key performance indicators in the logframe, suggesting that it had been effective. Further work needs to be done however on developing, agreeing and clarifying appropriate VfM indicators.
[21] Scaling up Nutrition: what will it cost p 11 and pp 21-24
[22] This assumes 1 child death averted is equal to 33 DALYs (WHO)
[23] Cost effectiveness is defined as cost per DALY < GNI per capita which is GBP 300 (2009)

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions
The interventions were expected to maintain global and severe acute malnutrition rates within safer levels across Karamoja, help bring down child mortality rates and avoid over 1,000 preventable child deaths. “Safer levels” was not defined but it would be reasonable to consider this to be below the WHO critical threshold of 15% and/or the serious threshold of 10% GAM. / Acute malnutrition did not increase to critical levels, however nor was it stabilised under the ‘serious’ threshold. GAM/SAM targets were unrealistic in that planned outputs could not deliver these targets in the absence of effective health and food security interventions. This needs to be carefully considered in any new design. The donor community, agencies and government need to find a way to improve the effectiveness and efficiency of nutrition and WASH interventions in the short term, while designing and implementing interventions that both consider and address the underlying causes of malnutrition. / TFP and CBSF are indispensable in Karamoja given the high rates of malnutrition and chronic food insecurity. However, there are inefficiencies in these programmes that need to be analysed and addressed. TFP is not ‘capturing’ an adequate proportion of children suffering with SAM (40% are not treated). This is commonly attributed to weaknesses at the community level and VHT referrals. CBSFP has better coverage but it is inefficient in so far as many children are repeatedly readmitted despite having been discharged ‘cured’. More needs to be known about which children are being enrolled in CBSFP and TFP and how often they are readmitted and why, and which acutely malnourished children are not being enrolled and why not. More needs to be known about effective TFP coverage in particular. / CBSFP is also inefficient in that the pre-mix provided is shared within the household and at times of stress. For those enrolled in the programme this means staying longer in the programme. It is generally assumed that children are continually re-entering the CBSFP because nothing has changed ‘at home’ in terms of food insecurity, hygiene and feeding practices. Furthermore there is an incentive for mothers to maintain a child in CBSFP to keep receiving the “family porridge”. There is a need to undertake research into these, and other related issues. / The Framework for Scaling up Nutrition and Uganda’s Nutrition Action Plan should shape future action on under nutrition and malnutrition in Karamoja. Programmes also clearly need to be strengthened - some of the weaknesses identified including: the effectiveness of referrals, the need to ensure health centre staff are present at CBSFP screening, ensuring routine medication is provided as per the IMAM Guidelines, applying adult education principles to the health and nutrition promotion component, and improving the regularity of commodity supply. / WASH programme are indispensable in Karamoja. However, an increase in the supply of water needs to be translated into better hygiene and sanitation practices. The effectiveness of efforts to promote hand washing or improve sanitation during the programme was not fully assessed. However a number of key informants raised doubts as to the impact of CLTS in Karamoja. It was also noted that new and rehabilitated boreholes faced operation and maintenance issues – this underlined the importance of engendering ownership, and more effectively engaging the Karamojong people in development of these programmes. / The impact of the programme on the capacity of district health teams to monitor and respond to malnutrition in Karamoja was considered to be poor given that routine surveillance had yet to deliver a product that the district health teams could rely on. Training implemented by UNICEF and WFP’s IPs appeared to have had a substantial impact on the capacity of VHTs, health centre staff, and district health teams. Walking into a rural health centre in Karamoja one can’t help being impressed by how well they seem to operate relative to any other institution or service. / Periodic surveillance remains indispensable in Karamoja and UNICEF is trying to establish this capacity as far as possible within the district health service with technical back stopping from the Institute of Public Health. / UNICEF and WFP face overlapping challenges in Karamoja and work quite closely together. The two agencies coordinate their respective nutrition programmes and consult periodically in Kampala on the overall management of acute malnutrition. At the Karamoja level, the two agencies, their partners and the district health offices meet on a monthly basis for district sector working group meetings. Two regional nutrition technical working group meetings were held during the project period. / However, what appears to be lacking is a shared concept and plan for stabilising acute malnutrition in Karamoja, including a common theory of change. Programme objectives and activities are described by the agencies, but more rigorous work needs to be done in identifying and treating assumptions and risks, and describing how and why things will change after many years of fundamentally similar interventions. A common theory of change for stabilising acute malnutrition in Karamoja needs to address first principles and credibly describe how nutrition interventions can be more effective and efficient and how prevention and promotion can bring about real change. In terms of implementation there needs to be a plan for delivering together as a team back-stopped by shared concepts, technical expertise and programme delivery capacity. / Recommendation: WFP and UNICEF should develop a shared concept and plan for stabilising acute malnutrition in Karamoja, including a theory of change. Government and partners should be consulted however the objective should be to have WFP and UNICEF developing a joint plan.

8. Review Process
An independent consultant Bernard Broughton undertook the review for DFID. The stated objective was to review the performance of the project “Nutritional Support to Karamoja” against the objectives set out in the original submission, business case and log frame. The contract was for 14 days commencing 15 January 2013. Before departing for Karamoja the consultant reviewed reports; attended a briefing with DFID in Kampala; and held separate meetings with WFP and UNICEF to discuss their interventions in Karamoja. Some of their IPs were contacted at this time, including CONCERN Worldwide and ACF. The consultant then travelled to Karamoja and based himself in Moroto for 5 days and Kotido for 5 days. The draft report was discussed prior to finalisation with UN stakeholders and partner agencies in June / July, and a final draft document finalised for review in September 2013.