Type of Review: Annual Review

Project Title:DFIDZimbabwe Pro-Poor Growth Programme

Date started:	December 2011

Date review undertaken: 1 – 12 October 2012

## Introduction and Context

What support is the UK providing?
Up to £13.54 million until 2015 to: / Provide support to rural businesses with grants and loans and the provision of business development support services. / Increase access to affordable finance for the economically active poor, with a particular focus on empowering women. / The programme is delivered through four interventions: / £2 million for the Zimbabwe Agricultural Development Trust (ZADT), a Zimbabwe trust which includes the $15 million CREATE fund, which provides support to financial institutions to on-lend to agricultural market intermediaries that benefit small-scale farmers / £2 millionto help strengthen the microfinance sector through establishing the Zimbabwe Wholesale Microfinance Facility (ZMWF),a trust which will provide wholesale funds to MFIs and other microfinance organisations, including SACCOs, which in turn will provide credit and other microfinance to their clients; introducing a microfinance act and regulations; and mainstreaming HIV AIDS/ Gender issues into the microfinance provider business models / £1.54 million to the Agro Initiative Zimbabwe (AIZ), a facility to encourage innovative ideas in agriculture and agriprocessing, providing grant funds and technical assistance to grow the ideas / £8 million to the Africa Enterprise Challenge Fund (AECF), a programme of the Alliance for Green Revolution in Africa (AGRA). AECF is an Africa-wide challenge fund, and the DFID funding contributes to the Zimbabwe window of the AECF. / The interventions are supported by a variety of other donors and implemented in part by consultants and donors: / ZADT. Donor partners- SNV (Netherlands Development Organisation), Hivos (Humanist Institute for Development Cooperation), DANIDA; implementers - SNV and Sabi Consulting / ZMWF. Donor partners-Hivos, DANIDA, GIZ (German Agency for International Cooperation); implementers – Zimbabwe Microfinance Wholesale Facility (ZMWF) Zimbabwe Association of Microfinance Institutions (ZAMFI), Hivos / AIZ. Donor partners – Nduna Foundation, Delta; implementer TechnoServe / AECF. Zimbabwe Window (round 2, 3 and beyond) Donor partners - Soros Economic Development Fund (SEDF) , SIDA, AusAid. Implementer - KPMG IDAS

What are the expected results?
The four sub programmes have the following expected results, based on the business case (2011). Some of these results will be revised, as the logframe is being amended as a result of the analysis and conclusions of the review team. In addition to this the logframe indicators have been more closely aligned with DFID Zimbabwe’s We Wills and Operational Plan results Full details of these revisions are provided in the aide memoire to this review document. / ZADT – / The main expected outcome of the intervention is improved access to finance for intermediaries in the rural agriculture and food value chains. This is expected to lead to improved input supplies and market access for small producer commodities thus contributing to an increase in small holder productivity, incomes, employment opportunities and ultimately to improved livelihoods of poor rural families. / The outcome, measured in terms of job creation, for the trust’s overall operation is 78,500 by December 2015, according to the current logframe. Additionally, the activities of the fund will significantly improve the agricultural output of beneficiaries. In terms of maize, the average household’s productivity is expected to increase from 700kg per hectare to 2,000kg. Participating intermediaries will grow by 10% per annum and financial institutions will devote 10% per annum more in resources for agribusinesses. / At the output level it is anticipated that the fund will: / Provide 70% of intermediaries applying to the facility with appropriate capacity building that lowers their business risk and allows access to funds / Experience no greater than 5% loan defaults by intermediaries / Target to ensure that 70% of beneficiaries are women-owned / Develop 4 tailored financial products for beneficiaries / Commit 97.5% of the available funds to intermediaries within 12 months / ZMWF – / The fund will have provided financing to a number of microfinance providers that have attained operational self sufficiency / Access to finance for 62,000 economically active poor people, 70% of whom to be women / A microfinance act and regulations approved into law and enacted, influenced and enabled by ZAMFI (Zimbabwe Association of Microfinance Institutions) / A number of innovative microfinance products introduced into Zimbabwe by 3 microfinance providers / MFIs mainstreaming HIV/ AIDS and gender issues and providing 500 of their clients with training, with an impact on reported GBV and HIV prevalence / AIZ – / DFID funding for technical assistance and DFID seed capital of £480,000, provided over three years, combined with corporate sponsorship, isenablingAIZ to award prizes to 21 grantees that demonstrate the potential to create outgrower/contract farming opportunities, with an average anticipated annual revenue of about £313 and an impact such that : / 4,200 sustainable jobs/opportunitiescreated / £2.3 million incremental small farmer revenue generated within the programme lifetime / £2.87 million income generated by the grantees within the programme lifetime / It is anticipated that the scaling up of some of the pilots will occur within the program timeframe, and the implementing partner would hope to help raise additional finance for the most successful model to enable additional growth opportunities. / AECF– / AECF’s Zimbabwe Window aims to provide 34 grants totalling $27 million by the end of 2014 that contribute to the rehabilitation and regeneration of agri-businesses and rural financial market systems that benefit in particular, 350,000 rural households by the end of 2014 by at least $100 per household per year, and create 5,000 direct jobs in businesses and related supply chains over the course of the programme. / The Pro-Poor Growth programmelogframe, and the individual component logframes, have been revised and expected results will be recalculated in line with this.

What is the context in whichUK support is provided?
Zimbabwe has experienced a staggering economic decline in the last decade. There has been a significant deterioration in the business climate and cumulative decline in GDP. Despite a return to positive economic growth, the rural economy remains depressed through a combination of limited agricultural financing, input/output market constraints and diminished service industries. Lack of liquidity and high perception of risk are critical barriers to the economically active poor’s ability to access finance that would help them to start or grow their businesses and better cope with shocks. On certain measures of empowerment, women do badly in Zimbabwe. They face significant barriers to accessing affordable finance, levels of gender based violence are high and are disproportionately affected by HIV. / DFID’s intervention will contribute to and help to consolidate emerging donor efforts to revitalise the agricultural sector and to catalyse private sector innovation in Zimbabwe, drawing on a proven track record of support to business challenge and prize funds and to create two sustainable trusts (agricultural development and wholesale microfinance) that can provide focussed products and finance that directly or indirectly encourage income growth for small farmers.

## Section A: Detailed Output Scoring

Output 1:
Commercially viable business ideas to demonstrate clear poverty impact especially for women / Score: A
Measures: / Number of MFIs borrowing from ZMWF that have attained operational self-sufficiency (OSS) – exceeded / ZMWF reports that it has approved 7 MFIs and SACCOs (Savings and Credit Cooperative Organisations) of which 5 have operational self-sufficiency above 85%. It is expected that, in a high interest environment, the injections of loan finance will enable self-sufficiency ratios to increase, although there is a real risk that, should interest rates be regulated significantly downwards, or reduce through market forces, that the performance of the OSS measure may deteriorate. / Number of projects including agribusinesses that are profitable and sustainable – too early to tell / It is too early to say whether funded projects will be sustainable. AECF indicator measures profitability 36 months after receiving the grant, but report that the August 2012 indicator of 35% of business projects profitable has already been met.AIZ will collect incremental revenues by prize-receiving business from round 1 by end December 2012. Selection processes for projects look at these issues at the outset and select those with the most positive potential, however the outcome in a challenging operating environment is uncertain. / Percentage of women owned businesses accessing financial services – exceeded / To date ZMWF has disbursed $50,000 to the Women’s Development Savings and Credit Union (WDSCU) the entire amount has been distributed as loans to its members (an average loan amount of $416) all beneficiaries are women (100%). As such, although actual loan disbursements are low the milestone for this indicator has been exceeded. Approximately 99% of WDSCU historical loans are made to women borrowers. This indicator has been re-worded in the new logframe to “percentage of loan contracts financed through ZMWFT wholesale loans signed by women” / A number of indicators from output 1 and output 4 have since been swapped to ensure better grouping of gender indicators (under output 1) and enabling environment indicators (under output 4). Given the gender focus attached to this project the existing weighting (40%) remains appropriate for this output. Risks associated with the forthcoming elections push the risk rating to HIGH from MEDIUM. Specifically, political disruption could affect all business operations in Zimbabwe, and an increased focus on the constitution and elections could result in policy makers according a much lesser priority to other issues such as microfinance.

Output 2:
Appropriate financial products accessible to value chain actors
Score A / Measures / Number and types of financial products – on track/ exceeded / This indicator should be refined in the revised logframe to provide greater clarity on the definition of types of financial products. AIZ does not provide financial products and hence should be removed as a source. / ZMWF provides information on new and innovative microfinance products. Here, ZMWF is engaging with three MFIs to introduce new microfinance products based on assessed needs. The selection criteria for engaging with MFIs includes openness to new products. ZAMFI has provided four sensitisation events for MFIs on innovative products, including mobile banking, agricultural value chain finance and micro insurance. / ZADT introduced the 50% guarantee in its engagement with qualified banks as an incentive to provide under collateralised borrowers with finance. ZADT is encouraging lending to associations. / Productive utilisation of disbursed funds: on track but weakattribution to DFIDfunding / Three interpretations of “productive utilisation of disbursed funds” has been made by the implementing partners. Firstly, that funds provided by ZMWF are provided to MFIs who must report on the loans made from the proceeds of the loan, and that such MFI loans are for productive, rather than consumption purposes. Secondly, that DFID funds are used productively by the sub programme managers. Thirdly, that the overall loan portfolios of MFIs borrowing from the facility are used productively. The final interpretation reflects the policy intention behind the measure most closely. / ZMWF reports that most MFI new loans are salary based loans (87% and primarily for consumption) and only 12% for microenterprise loans, and 1% agriculture loans, and their portfolio provides 66% in salary based loans. All DFID money channelled through ZMWF is to be used for productive as opposed to consumptive uses – but the proportion of DFID funding to MFIs compared to overall funding is small and not possible to track, and so attribution is not possible (for example ZMWF’s loan commitment to Micro King is 0.5% of Micro King’s whole portfolio). / Due to the problems surrounding consistent definition of the measure and attribution of results, this measure will be removed from the revised logframe. Also, the policy intention to steer the market towards productive loans and away from consumptive loans may not fit the microfinance market as it currently stands in Zimbabwe, and this policy issue requires further discussion with partners. / Operational self sufficiency of the funds: - on track / The measure has been reworded in the revised logframe to “Operational self-sufficiency for ZADT and ZMWF”, and the definition of OSS provided in the Aide Memoire. OSS will arise in ZADT when additional funds are provided to the programme, as operating costs will remain relatively flat compared to funds under management, which attract an arrangement fee charged to banks. DANIDA’s planned further injection of funds will provide a significant boost to OSS.ZMWF has less funds to work with, and interest income at 11% is insufficient, even if the wholesale funding is totally absorbed, to cover current operating costs. Again, further capital injections would have a large positive impact. / At 30% the weighting for this output remains appropriate new product development and organisational self-sufficiency are key attributes of a long term financial sector intervention. Continued financial sector fragility and risks associated with the forthcoming elections push the risk rating to HIGH from MEDIUM.

Output 3:
Financial and technical support to agribusinesses with innovative and inclusive business models
Score A / Measures: / Number of agribusinesses supported -exceeded / AIZ has already approved support through grant awards to 12 enterprises and AECF to 9 enterprises (round 2 of the Zimbabwe window) so the measure at the first milestone (12) has been exceeded. / Incremental agribusiness revenues – on track / AIZ’s expected outcome measure is £2.87 million, equivalent to the final result under this output measure. AIZ report that it is “on track” (£109,000 at review date) and based on the evidence of the project visited, DFID expect that the end 2012 will reach target. ZADT do not currently track incremental business revenues as part of their logframe measures, but will be doing so under the revised logframe. AECF do track incremental business revenues, but it is too early to see the impact, especially where investments are still to be made by the grantees. / Days and types of technical assistance provided to agribusinesses – met / AIZ has already provided 420 days of TA to date. The types of TA include capital raising, market linkages, financial modelling and extension support. AECF does not measure days of TA as part of their logframe, but this is not central to their programme given the different types of businesses receiving grants.The inclusion of the word ‘type’ in the indicator causes confusion and we recommend that this be removed. / Weighting of 20% for this output remains appropriate.Risks associated with the forthcoming elections push the risk rating to HIGH from MEDIUM.

Output 4:
Enabling environment for business and microfinance
Score: A / Measures: / 1. Number of regulations supporting the growth of the financial sector – on track / The process of enactment of the Microfinance Bill is underway and, after numerous consultations, the Bill was laid before Parliament on 31 August 2011, and is expected to be passed later in 2012 or early 2013. ZAMFI carried out numerous interventions to facilitate this progress, including conducting consultations with ZAMFI members, meetings with the Reserve Bank and the Ministry of Finance, and through membership of a core working group comprising ZAMFI, the Ministry, the Reserve Bank and the Attorney General’s office. However, the political environment is focused on early preparations for elections, expected in 2013 which may put this timetable at risk. Regulations will follow the passing of the Act. The risk of eventual non-approval has reduced following the gazetting. / 2. The number of GBV/ IPV reported to the police and local traditional leaders– output indicator data not available, inputs/activities on track / Hivos contracted IMAGE South Africa to replicate their similar programme in South Africa. 3 MFIs/ SACCOs (WDSCU, Zubo and Micro King) have been identified to apply the model and a study tour is planned for those officers of those institutions. The baseline survey for clients of the ZMWF client WDSCU is completed and for two other clients (Microking and Zubo) is expected to be completed soon. IMAGE has already trained facilitators who trained local level trainers in September. Training of credit clients had not started at the time of the review but was imminent. The M&E system has been adaptedto Zimbabwe circumstances. IMAGE is confident of achieving its first year milestone (March 2013), and does not believe that there are any insurmountable obstacles to achieving its overall goal, although there is a risk of political unrest before and after the elections. / It should be noted that the issues around Gender Based Violence / Intimate Partner Violence impact women in the same communities as MFI borrowers who are in the minority in terms of numbers. There is therefore likely to be a relatively weak connection between the training of women (the output measure in the ZMWFlogframe) and the chosen measure in the PPG logframe which covers the whole population. The logframe is therefore being adjusted based on measures to be agreed with Hivos which have a stronger connection to the intervention (a GBV index is under discussion). / 3. Number of females in decision making positions in beneficiary enterprises. – too early to tell / The ZMWF programme targets MFIs with a positive gender bias in their borrowing plans, and as such targets lending to women-led enterprises. Figures for ZMWF lending are detailed under output 1. / At the moment, all of the borrowers accessing loans through ZMWF lending are female and so it has been taken that all of these are in decision making positions as they are the loan signatories. However ‘decision making’ has not been defined beyond this, which may lead to confusion in future. Decision making within female headed households may still lie with men, even if the borrower is female. There is no baseline study, and ZMWF is not tracking impacts on decision making within the household at present. For all of these reasons, the logframe indicator measuring women’s economic empowerment is being revised. Hivos are developing an economic empowerment index as part of their M&E which will provide the baseline and will be incorporated in the revised logframe. / As mentioned in the discussion under output 1, gender indicators have been grouped under output 1 and enabling environment indicators under output 4 going forward. The 10% weighting for output 4 is sufficient to emphasizes the importance of ensuring that the enabling environment facilitates the development of business and microfinance. Risks associated with the forthcoming elections push the risk rating to HIGH from MEDIUM.

## Section B: Results and Value for Money.
1. Progress and results
Has the log frame been updated since last review? / No, but has been revised as part of the review mission, in order to provide a clearer logical structure, to review indicators using the SMART technique, and to confirm the links to the subproject logical frameworks to ensure logical structure and identify gaps in data and evidence collection. Two logframe sessions were held with partners at project approval and shortly before the annual review. Further sessions were held during the review. Given that in 3 out of 4 cases the PPG sub programmes are being implemented jointly with other partners, the results that feed in from the sub programme have been suitably apportioned to ensure that only results attributable to DFID funding are captured. / 1.2 Overall Output Score and Description: / All outputs have been provided with an A, as progress has met expectations and, where available, measures have been met or are on track. There are instances where data has not been available and /or it is too early to tell. There are also instances where programmes have reported under spend / disbursement against budget, this is due in part to the fact that this review was conducted in early October 2012 and that the milestone targets are set against a December timeline. In such instances implementing partners have provided comfort around progress made to date and the likelihood of achieving milestones. / All subprojects are underway and making satisfactory progress, although there are issues detailed further in the review reportfor DFID and partners to consider in order to improve the implementation and potential outcomes on all four of the subprojects. / 1.3 Direct feedback from beneficiaries / The review team was able to meet with a number of beneficiaries, including intermediaries (grantees, prize winners, MFIs borrowing from the wholesale facility, agriprocessing companies) and end beneficiaries, including MFI borrowers and small farmers. The details of the visits are provided in the Aide Memoire. / ZADT – / NicoOrgo - (seed supplier and fertiliser manufacturer) – received a $200,000 loan from the facility as working capital for its retail shop consignments. It has been successful to date, although it is noted that NicoOrgo could probably have received bank finance at the market rate. The review team met with three retail outlets benefitting from consignments, who reported increased sales. The sales increases were due to fertiliser stock availability in store and the lower retail prices for fertiliser bags. There is strong evidence that farmers were able to increase production as a result / Mr Mazivire – Increased his turnover from potato farmer offtake from $90,000 to $200,000 a month and increased his staff levels from 3 to 10 through accessing a ZADT supported loan. The major constraint to further growth is the working capital required to finance potato farmer’s inputs. / ZMFW – / Micro King – a successful microfinance institution financing the expansion of its activities. The loan amount of $100,000 is relatively small, given its overall borrowings of $18 million. / Women’s Savings and Credit Union (WDSCU) – a SACCO (Savings And Credit Co-operative) able to qualify for the facility as it has adequate collateral in the form of buildings. The ownership of the buildings enabled it to survive the currency collapse. The loan is insufficient to meet all the demand of its members, but is clearly welcome. A visit to its branch in Honde Valley suggested that there are issues faced because of lack of finance for lending. The high rate of interest charged to borrowers is reflected in a large percentage of loans which are past due. The lack of funding means that loan demand cannot be met, and this impacts the ability of the credit union to attract new members, and the ‘first in, first out’ model used for loan rationing does mean that loan needs are not current. A visit to an MFI borrower (a woman running a retail store in a small community) demonstrated that a $500 loan to finance an increase in the range of items stocked increased sales significantly and increased profits over the cost of the loan. / UNTU– A relatively new MFI that requires wholesale finance as it cannot take deposits yet. The funding will allow expansion in the Gokwe area. Again, the amount of financing is insufficient to meet heavy demand, but is welcome. / In all three cases, the high rates of interest (ranging from 40%-80% per annum) charged to the end borrowers is a concern. This is balanced against the need for strengthening key MFIs by moving towards operational and financial sustainability. / AIZ – / Better Agriculture – the scale up of a model for chilli contract farming to serve strong markets. Chillies provide a good cash crop that increases farmers’ incomes, with one farmer, managing a nursery patch, reporting an additional $400 in income. Two other farmers providing support to the chilli nursery were also interviewed, both expressing satisfaction with the crop and the support provided from the company. Questions were asked around how innovative this project is given that the company already was in its third year of tabasco chilli contract farming on the Honde Valley, where chillies were semi-processed before export to the USA. TA provided by the project had created a linkage to an important local chilli consumer (Nandos) for production in another area of the company’s operations. / Peak Trading - Peak Trading’s business model is to buy commodities from the farm gate and achieving transparency in the trading business by using digital scales to weigh grain purchased from smallholders-with farmers being paid on the spot, ensuring that farmers are not short changed as normally happens when traders use the bucket system. Peak Trading is still a small company and their capacity to procure large quantities of grain from smallholder farmers in operational areas is still low. So far they only have one truck (which was procured using funds from the competition) and their target is to have 4 trucks. It is possible that prices paid to farmers do not reflect fair competition, given that there is no factoring in of the capital costs of the truck, and the farmer’s benefits might not be sustained. However the more favourable prices offered to farmers are likely to last only in the short term, with the marginal competitive edge allowing Peak Trading to consolidate its position in the commodity supply chain. In the long run other competitors will enter the market and prices will trend toward a market equilibrium level. / AECF – / Sondelani – a grant to provide tomato processing capability in Bulawayo to create additional demand for tomato production in the Matobo area. The processing facility is yet to be built. An impressive business model that deserves to work. The review team met with teachers, students and graduates of Ebenezer College, a post school facility that creates community farming leaders, as well as company field managers, and a number of tomato growers in the Matobo area, who are all capable of extending advice to others farming in their communities. The contract farmers are benefitting by about $40-$200 a month through planting on up to 0.1 ha. Cropping 3 times per annum, in an area where there are no alternatives to growing tomatoes as a cash crop. In 2008 the inhabitants of this area were starving and unable to cope for themselves according to one woman interviewed. She manages a small plot providing financial return for her and her grandchildren’s subsistence. She still needs to walk 1 km for water, and water availability is the constraining issue for most farmers in the valley. Sondelani is running a 8 km pipe to serve farmers close to the road. Despite this constraint, there was visible evidence that the number of farmers growing tomatoes in the valley had increased substantially in 2012 with five farm plots identified by the Sondelani manager as we drove through the valley that were not there on his previous visit. . / A round table meeting with 6 other AECF grantees demonstrated high innovation of their ideas, and respect for the challenge fund model and fund managers. / 1.4 Summary of overall progress / The overall progress reported here supplements that provided in each of the four subprogrammeself-assessments. / ZADT– DFID has provided £2 million to an existing initiative, the CREATE Fund, of Danida, Hivos and SNV which became operational during 2012. £1.6 million is applied to the fund’s capital, and £400,000 reserved for monitoring and evaluation and capacity building. The total funds available for investment is now $15 million. During the last year, the fund manager was appointed, governance agreed, the modality for operating with banks established, three participating banks selected, and the first loans made. At the time of the review, funds disbursed totalled $3.6 million to 41 borrowers, some of whom were already known to SNV Technical assistance, 200 agro dealers have attended information sharing sessions organised by the programme. 1,390 agro dealers have been selected for linkage to suppliers, and all have been provided with business training. Banks have been conducting training needs assessments and are finalising their training plans with SNV. A study of the financial needs of value chain actors has been commissioned by SNV and is expected to inform the design of innovative products to be shared with banks. / The fund’s donor commitments have grown faster than disbursements, and the major constraining factor has been the qualification of participating banks, as a number have been proscribed by the donors and the initial period of qualification was longer than anticipated. The selection of the fund manager also ate into time. The quality of banks has led to quite strict procedures for loan qualification to be applied, and the model is quite conservative. The product offered to banks does not provide leverage. The banks benefit through matching funding, 50:50 risk sharing, and a low interest rate, allowing loans to be passed though at an affordable rate. The level of application acceptance is quite high, suggesting that banks are trained to identify opportunities against the funds’ objectives. The fund takes insurance from a local insurance company to guarantee the repayment of certain loans where the borrower has inadequate collateral at a very acceptable rate (1.7% per annum up to $2 million of loans). / There are tensions between what the input and off take commercial actors need in terms of financial resources – the need is large and urgent – and the disbursement to date has been restrained, it is also clear that the risks in the banking sector do justify a cautious start and robust fund processes and procedures to ensure that losses are minimised and that the fund is able to recycle loan repayments in the future. / Through discussions with DFID officers in Harare it is clear that the caution of the fund is supported in the initial decision for DFID to provide its financial support to build the fund as a sustained institution and not to place its funds at higher risk – for example, a graduation from the current model of 1:1 funding to loans can in time be replaced by a portfolio-based facility which allows for leverage of donor funds. The precursor for leverage would be an increased liquidity of the banking sector, a reduction in real interest rates, continuing economic recovery and flawless bank performance as the fund’s partner. These preconditions are not met at the time of the review. / ZMWF / The fund has been designed, established and is now operational, through a 5-person secretariat which provides management services. Hivos has committed EUR 1.7 million, DFID £2 million, Danida £111,000 for operational costs and GIZEUR 14,000. ZMWF designed 4 loan products and provided awareness raising road shows attended by 85 MFIs prior to announcing calls for proposals. To date, 6 MFIs and one Sacco were selected from 30 applications received from two calls for proposals. The MFIs have under 20,000 clients in total but the facility is expected to provide for significant client growth. Total loans approved to date are $595,000 and $50,000 had been disbursed at the time of the review. / As described elsewhere, the MFI bill has been gazetted but progress here may be hampered if parliament prioritises other issues pre-election. The HIV/AIDS and gender mainstreaming work is progressing according to plan, but is dependent on the ZMWF’s actions to qualify MFIs and SACCOs to receive wholesale funds and the eventual disbursement of funds. / The fund has been correctly structured with expert technical assistance, but has been constrained in approving loans to qualifying institutions. The main reason is that there are few residual MFIs who were not wiped out during the currency crash, and even fewer remaining in good financial health as measured by their current balance sheets. Those that are financially healthy can be characterised by ownership of buildings many of which have been revalued to current values, or those that have started with a solid capital base since the currency crash. None of the MFIs are particularly big as measured by numbers of branches. The selection of MFIs has been cautious as a result and qualified MFIs generally have a strong business model. The purpose of the loans from the facility support rural lending, although not all are targeted in their main business to the needs of small-scale farmers, or women borrowers. / The processes for lending are rather slow, mainly because the loans are collateralised. The fund requires that the collaterals should be perfected before loan approval, which adds significantly to the time taken to process an application, and this has slowed disbursement. / . / The review team noted that the Apex has limited funding available currently to start to provide finance to MFIs with limited additional funding capacity. These MFIs in some cases are trying to rebuild their balance sheets. However, there is a huge demand for microcredit in the country, and this combination of factors means that the interest rates charged to clients, which are some of the highest in the world (given that the loans are denominated in US dollars), are unlikely to drop in the near future, as long as there is the supply/demand inequality. This occurs despite the low rates charged by the Apex on DFID’s grant funds to the accessing MFI’s. Balanced against this, the expectation of a 12% default rate on MFI loans is a direct effect of the high interest rate environment. / AIZ. / DFID has committed £1.54 million to TechnoServe’s programme to support medium-sized Agribusinesses. Nduna Foundation also provides financial support. The funding allows prize grants of $50,000 for innovative ideas for engaging with small scale farmers coupled with technical assistance to enable the ideas to become commercially operational. TechnoServe has conducted two out of three expected competition rounds, over which the number of applications has been less than expected (110 applications received against a milestone of 200). Of these applicants, 12 were selected for prizes and 420 days of technical assistance has so far been provided, primarily on capital raising, creating market linkages, financial modelling and extension service support. 19 direct jobs have been created to date, and 802 small scale farmers have generated $212,000 in additional revenue to date, most through a grant to Peak Trading. DFID spend is lower than anticipated, but this is likely to increase substantially during the next 6 months. / The Zimbabwean context is such that small and medium sized businesses are facing immense challenges, and AIZ believe that the milestone of 200 applications was not realistic. It has also been reported that the term ‘innovation’ has discouraged potential applicants to apply for the Fund. Based on these observations and lessons, AIZnow uses the term “initiative” instead of “innovation” to describe the funding instrument. Further ,AIZ stress that they are looking for creative ideas that make business sense or are commercially viable, with emphasis on developmental impact rather than focus solely on innovation. / Technical assistance is likely to be an issue as the AIZ portfolio grows unless the Business Development Advisors staff compliment is beefed up. Contrasting this, the technical assistance provided to one grantee visited did appear to be of good quality. If the recommended changes are made, the fund has a chance to sharpen its focus. Other elements of the pro-poor growth deal with scale-up of existing initiatives. / AECF / From July 2011 to June 2012, AECF conducted the second round of the Zimbabwe Window, resulting in 9 new grants, to add to the 10 selected in round 1. DFID is part funding round 2 (US$3.3 million) with the Soros Economic Development Fund. Round 3 will be co-funded through this programme (US$2.1 million), Sida and AusAid. The programme will support further rounds to the extent of US$4 million. Round 3 is underway. / AECF has been professionally run for a period of time and the projects selected have met or exceeded expectations. AECF’s reporting to its stakeholders is clear concise, appears accurate and is transparent. A number of important processes, including DCED measurement, have been adopted for the Zimbabwe window. / AECF is slightly behind in its planned cash disbursement, although this is attributed to difficulties faced by grantees, and this is a common issue in developing countries, and no real concerns have been identified. / The review team raised some concerns around the repayable grant feature of the AECF. This is effectively a non-recourse loan to the grantee, and the in the Zimbabwe context can be seen as an alternative to working capital funding which is difficult to obtain currently given the liquidity issues in commercial banks. / The review team suggested three potential adverse impacts which may occur as a result of the repayable grant. Firstly, although there is no legal obligation to pay the loans back, the beneficiaries who value their reputation will pay back the loans even if it means that it will worsen their overall financial ‘health’. Repayment may also act as a brake on growth that might otherwise have been achieved had the monies been granted outright, and therefore limiting the effectiveness of the grant. Finally, the grant repayment monitoring and reprocessing require additional administration and adds to the management cost, so is therefore arguably less effective from a VFM economy point of view than simply providing grants. / However the rationale for repayment of part of the grant is that it encourages a greater degree of financial control, discipline and responsibility, and evidences good VFM from an economy point of view as a result. Less money is spent than otherwise would have been the case. The repayable grants also provide finance in the absence of availability of working capital finance from the financial sector. Finally, projects requiring further financing to complete can apply outside of future competition for funding, (although this process also incurs management costs). / The AECF policy on repayable grants is being examined by the combined AECF donor group, and these points will be considered as part of this exercise. / 1.5 Key challenges / All projects will face challenges around the forthcoming elections in Zimbabwe which will adversely affect not only the ability to monitor projects countrywide, but can also be expected to limit the business opportunities for grantees for the same reasons as transport will be limited and business interruptions increase. / Another key challenge is the current rationalisation of the banking sector, where capital requirements have increased significantly (commercial bank capital requirements have been increased from $12m to $100m) Although the compliance period has been staggered (to June 2014) it is possible that during this time banks will be focused inwards on mergers and acquisitions rather than lending. This might be expected to slow projects such as ZADT which are dealing directly with banks. There are real concerns around the financial standing of some key banks which might be expected to have a significant impact on the availability of bank credit in the system in the short term, with particular impact on the ZADT and ZMWF programmes. The regulatory move by the Reserve Bank, has however been broadly welcomed as a positive step toward the long term stability and recovery of the fragile financial sector in Zimbabwe. / All of the grant recipients and small scale farmers face an uncertain time based on whether the rains fall in a way that provides for good quality harvests. The weather patterns in Zimbabwe appear to be impacted by climate change, with longer droughts and heavy rains. / ZADT-The major challenges will be for the fund to meet is expected target of 67% disbursement by end 2012 given the expected increase in disturbances in the near future given the key challenges faced in the short term by the banking sector mentioned above. The restriction on qualifying banks is also a challenge, especially if DANIDA provides a further large tranche of funding. / ZMWF–The major challenge here is to determine which MFIs and SACCOs receive credits, given the poor state of the sector. The challenge is exacerbated through high interest rates charged in the sector, which, when reduced in more normalised times or by regulatory actions, may place the current business models of the MFIs in jeopardy. The passing of the microfinance bill and the regulations is in the hands of politicians, who may have more pressing business and hence the timeframe is uncertain. The gender and HIV/AIDS aspects face the challenge of finding an effective working model where beneficiary women form a small percentage of women at risk in a community. / AIZ - .Faces the challenge of staying focused to fund innovation. Its current grant projects might face problems if TA cannot be provided because of travel restrictions. / AECF–There is a high level of unmitigated risk in many of AECF’s projects, especially the insurance ones, which has the potential to adversely affect the combined results of the programme. However this has to be considered in context: the Fund is set up to support innovation which, by its very nature, is risky, and these programmes also present opportunities for great success. Some risks mentioned in the self-assessment can be managed by applying a different business model (for example monitoring). / 1.6 Annual Outcome Assessment / The programme calls for improved access to financial and business development services for agricultural value chain actors, SMEs and entrepreneurs, with outcome indicators that measure the number of jobs and opportunities created, the average income generated per new job opportunity, and the growth of agribusiness and financial sector in Zimbabwe. / All four components have made progress since inception, and all are managed professionally by enthusiastic delivery teams. In the case of ZMWF and ZADT, progress has been slow compared to original plans and this is partly due to a risk-averse approach and the desire to create lasting institutions to serve Zimbabwe. / All four subprojects report that the outcome targets, reflected in their logframes, are on target. From a results reporting point of view targets and performance figures presented below reflect the performance of the sub programmes in total, DFID attribution (according to contribution) is then apportioned accordingly in the global log frame. / ZADT (DFID attribution current 13% / forecast 3%[1]) – Report that 42 agrichain actors are benefitting 9,979, beneficiaries (small holder farmers), against a milestone 1 target of 80 agrichain actors benefitting 16,000 beneficiaries, through access to new or improved contract farming arrangements, new or improved wholesale distribution networks and output marketing arrangements. They note difficulties in their measure of job creation not only in theory but that the job conversion metric should give rise to a much smaller number. / ZMWF (DFID attribution 100%)–its outcome is “expanded access to financial services for the economically active poor, especially women and a reduction on GBV/IPV, through capitalisation of MFIs”. The first milestone is likely to be missed because of the slow disbursement issue, however, ZMWF management are confident of delivery of the outcome with pace now picking up now that the procedures are fully embedded. Further speed up should be possible if the recommendations in this report are taken forward. There are also additional risks to achieving the final end of project outcome, centred on sustainable business models of MFIs, should interest rates fall sharply through regulation or market forces. / AIZ (DFID attribution 100%) – Notes that job opportunities target at the milestone have already been exceeded, with 821 jobs opportunities compared to 700 targeted at the first milestone and smallholder incremental revenues also above target. / AECF(DFID attribution 27%) – The AECF Zimbabwe Window outcome is to contribute to the rehabilitation and regeneration of agribusiness and rural finance market systems in ways that benefit the rural poor. Its measures assume that the market system improvements and investments stimulate the effectiveness of private sector, government and donor interventions, and this is yet to occur at significant scale. AECF notes that the Window is delivering very good results. Outcomes maybe impacted because of the very high risk profiles around grant investments and slower than expected implementation.
[1] Assuming 1) forecast fund growth to $50m by 2015 and 2) DFID contribution remains unchanged

2. Costs and timescale
2.1 Is the programme on-track against financial forecasts: / DFID allocation of funding to implementing partners in on track, but channelling of these resources to grantees and intermediaries has been slow. All sub programmes are slightly behind track. In the main, this is a temporary state of affairs and programmes are expected to get back on track imminently. / ZADT –ZADT has not spent much of DFID’s grant to date, but plans to do so when its other earlier commitments from other donors is exhausted. It will take until early 2013 to get back on track. / ZMWF – DFID money is already provided to Hivos and unspent funds are kept offshore. The fund is behind in its on-lending commitments and at the time of review has only disbursed $50,000. Although the rate of disbursement is expected to increase, ZMWF needs to rationalise processes and agreements if it is to disburse for effectiveness, perhaps by considering the use of loan portfolios as collateral and considering the timing of collateral perfection. DFID and ZMWF will consider how to address these issues through future implementation of the programme, and make adjustments accordingly. / AIZ –is provided under an accountable grant arrangement and spending is behind target (£126,523) against a budget of £360,242. Spend to date has been complicated through the co-funding arrangement with Nduna (essentially, DFID funding to date has been spent on TA for the first round winners, and it is only for the second round that DFID funding is actually going into grants).Spend is expected to pick up in the 4th quarter of 2012 and early 2013 primarily through heavier TA and paying out of second round awards. / AECF –Disbursements to grantees are behind schedule because of a variety of factors, relating to the progress on the grant projects themselves. / 2.2 Key cost drivers: / Project costs / All projects are impacted by the foreign currency risk where DFID contributions are denominated in pounds sterling, whereas most pass-through costs, comprising grants, prizes, loan instruments etc. are denominated in US$. This will cause projects to act with some caution in ensuring there is adequate management over the risk that the pound significantly deteriorates against the US$. / ZADT – Consulting costs are quite expensive in the Zimbabwean environment, but essential for capacity building in banks. Costs of monitoring and evaluation are quite high, reflecting the need to collect nationwide information on use of funds and impact. / ZMWF – ZMWF management costs are subject to Zimbabwean inflation and cost of living. The market for locally qualified consultants in very specialised areas is not large, and occasionally international resources much be used. The cost of provision of TA is similar in most respects to the management costs. / AIZ – Consulting costs are a large component of non-prize expenditure and can be expected to increase in the coming year as projects are implemented. It will be critical to ensure a clear linkage between the cost and quality of TA and the expected benefit of the TA. TechnoServe has a good model of using relatively low cost, but skilled, volunteers to provide TA. / AECF – the management of AECF consider the main cost drivers to be project scope “creep”, where additional burdens are placed by donors after implementation commenced. Extra funding has been provided to ensure more robust M&E through the introduction of the DCED monitoring approach. For grantees cost drivers include the costs of doing business in Zimbabwe, and the associated risks and uncertainties in the environment. / 2.3 Is the project on-track against original timescale: / All projects are slightly behind track including on project spend, as explained above.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Generally it is too early in most of the subprojects to determine changes in evidence. / ZADT–Have recommended to replace transporters as a class of borrowers with input manufacturers, given that transport providers are not applying for loans. / ZMWF–It is becoming clear that there is a pressing demand for MFI wholesale funding which is not being met. Interest rates to borrowers will not decrease unless significantly more funding is provided to the Apex (and even then a clear message provided to MFIs to reduce interest rates) and/ or DFID insists that the Apex make this a requirement for access. / AIZ–AIZ recommend that no deviation in project assumptions is recommended as it is too early in the project. A sharper focus on innovation and a move away from upscaling existing operations is also recommended. / AECF–The major change has been the embedding of the DCED monitoring process. / 3.2 Where an evaluation is planned what progress has been made? / No overarching DFID evaluation of the PPG programme has been planned, but evaluation plans are underway for each of the four separate components. / ZADT–DANIDA carried out a review separately from DFID during the same time period – they are due to share the results imminently. / ZMWF–Hivos recently commissioned an annual review of ZMWF which is being finalised before distribution. The recommendations provide further strengthening of governance arrangements to prepare for growth in the organisation and the fund and for distinguishing the roles of CBZ, ZAMFI and ZMWF. Hivos will provide the financial support for the organisational strengthening in line with the recommendations. / AIZ–An internal evaluation is planned in early 2013 for early grant winners when data and evidence will cover 1 full year. / AECF–AECF has been subject to AusAid annual reviews since inception and in April 2013, AusAid will undertake an MTR. The AECF Committee is also putting an overarching M&E system in place covering all of the Windows.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / The overall risk is now rated as high, primarily because the risks of operating in Zimbabwe continue to be high. The situation can change dramatically and quickly and the prognosis for the next 12 months is for a higher risk profile than experienced in the first year of operations, especially those relating to political stances and political decisions in advance of the general elections, and the potential for general public unrest related to election issues. The latter may impact the activities of sub-programmes adversely during the period up to and for a period after the elections. A number of the risk indicators have been revised upwards as a result, which has changed the overall assessment from medium to high. / 4.2 Assessment of the risk level
The key risks that could threaten the successful delivery of the intervention along with the corresponding mitigating actions to minimise these risks are summarised below. / (H – high, M – medium, L- low) / Table 1: Key Risk Identification and Mitigation / Risk Probability Impact Mitigation Strategy Review observations / 1 Political interference on project selection and execution H H no political interference to date, however the risk remains for future selection and existing execution / 2 Insufficient capitalization of the Fund – presumed to be the AECF, but in reality also ZMWF and ZADT L (was M) H Additional donor support Fund appears to have adequate funding for the Zimbabwe window of AECF. Danida is expected to provide $35 million to ZADT. / 3 Collapse of GNU H H Cancellation of process, cut-off points, delay of transfer of money to projects GNU has survived to date but this can quickly change. / 4 Escalation of political violence H H Business will be affected if political violence matches or exceed that in 2008, and donor’s positions will be very sensitive to this, Delays in transfer of funds possible, postponement of project activities. Political violence is on an increasing trend following a relatively quiet time. / 5 Occupation of farms that are part of AECF/AIZ project M M Mediation via govt. Institutions, dialogue with local organization, include local smallholders as stakeholders in project No evidence that this has been an issue to date, but change can happen quickly. The emphasis on small holder farms has mitigated the risk. / 6 Breakdown of Law and Order H H Cancellation of process, delay of bids, cut-off points, delay of transfers No evidence that law and order has broken down to date, but this may change in the next year. / 7 Re-introduction of ZIM Dollar L M Mitigation would be: cancellation of process, cut-off points, delay of transfer of money to projects. No evidence that there are plans to introduce a new currency. MoF has announced that the multicurrency regime will remain in place until at least the end of 2013. / 8 Persistent illiquidity leading to failure to mobilize cash contribution M H Make use of advance payments, allowance of delays in paying own contribution DFID has responded positively to challenges here by allowing advance payments. / 9 Project on disputed land M M Mediation via MOF and other govt. Institutions, dialogue with local organization, include local smallholders as stakeholders in project, DD of each project at business plan stage No evidence of this impacting projects to date. / 10 Low number and quality of applications M (was L) M (was L) Marketing and PR-efforts have created huge response from private sector. There should be a good depth of bankable projects Generally response has been good across the 4 windows, although AIZ received less applications than planned. / 11 Negative social or environmental impact; climate vulnerability L H Applicants implement the projects themselves, so the risk is always there. Needed actions include: strict M&E on the spot (done), closer liaison with Donor embassies and local NGO’s (ongoing) and enforceability of contracts (ongoing), environment/climate due diligence process and related M&E. These aspects do not appear to have become issues on any of the projects / 12 Negative press M L Very low incidence. Can be handled ad-hoc, based upon careful examination if critique is justified. No evidence of negative press to date. Care must be taken on two issues where negative stances can be easily taken. Risk mitigation should be considered. / 13 Seizure of bank accounts M H Risk is particularly big at grantee level. Off shore bank accounts. Adapt payment procedures accordingly. No issues to date. / 14 Fraud and disappearance of funds L L Communication lines are short because of in-house EM, AGRA management open to complaints, motivated and professional staff, Annual independent audits done Subprogramme procedures are strong. No evidence to suggest that there are problems in this area. / 15 Fraud and misuse of funds by applicants M L Each component’s financial control and accounting procedures are sufficient. Procedures and management of this risk appears quite strong on all 4 projects. / Table 2: Risk Matrix Summary – Changed assessment of risks shown in [square brackets] / IMPACT / H M L / PROBABILITY H 34 6 1 / M 2 8 13 5 9[10] 12 15 / L [2]11 7 10 14 / Risk of funds not being used as intended / The risk that funds are not utilised as intended is quite low, given strong governance and adequate financial procedures in each subproject and high reputation of subproject partners. / ZADT–a highly complex governance process ensures separation of duty between donors and managers, with one donor acting as payment agent. Management boards and team are staffed with experts in various fields. SNV, whose systems have been tested by a number of donors, will provide the fund with this system. / ZMWF–The risk in ZMWF is also considered low, with expert services provided for all fiduciary processes, including at trustee, management and payment agent levels. / AIZ–AIZ has recognised that the main risk to funds not being used as intended relates to use of prize money by the grant recipient. The risk is mitigated by providing the money in instalments, separate project bank account, regular monitoring visits, and expert assessments of the systems and accuracy of financial and project reporting. / AECF–The implementing agent has introduced a monitoring system against four major criteria, project financial viability, development impact, AECF reputation and reporting from the grantee, to ensure that funds are used as intended. / 4.4Climate and Environment Risk / ZADT: The project encourages loans where sustainable agricultural practices are used or introduced, primarily organic fertilizers against inorganic, but also sustainable wood lots. It is likely that increased farming activity will result from lending activities, but farming activities are at historically low levels. A constraining factor will be access to water supply, which appears to be a constant issue for small holders wishing to expand. / ZMWF: As an onlender to the MFI sector, ZMWF is unlikely to know the impact on the environment of activities funded by the MFI. Given the size of loans made by the MFIs, individually they are likely to not have a significantly harmful impact, although in total they could, especially if loans are to purchase harmful products. ZMWF should reconsider this risk and assess against the policies of the MFIs it makes loans to. / AIZ: Requests an impact assessment from all would-be grantees. Judges are mindful of these impacts in the selection of the winners. AIZ carries out environmental assessments as part of grant due diligence. / AECF: Recognise that agriculture can have an adverse impact on the environment but it is already impacted by climate change, which compromises low technology farming. Adaptation through new technologies and better management techniques is a positive outcome in this situation. AECF carries out due diligence on this issue before grant award.

5. Value for Money
5.1 Performance on VFM measures / Of the four projects, only the AECFhave attempted analysis of VFM using the ICAI recommended 4 E’s approach. Because none of the subprogramme management contracts were awarded under a DFID-run competition, a VFM economy opportunity was foregone or the process left to others. The existence of other donors, and in the case of ZADT and AECF significant donors closer to the projects, DFID’s influence on VFM discussions is more limited. The following, albeit with the above caveat – represent opportunities for VFM over and above those found by other VFM audits. / Against the DFIDVFM Framework scoring methodology – markings are as provided in the table below, with a summary of the detailed justification for the markings provided in the aide memoire that supports this project review document. The projects have been scored against a VfM framework, with 1 representing poor VfM and 5 representing excellent VfM. The assessment criteria are also included in the aide memoire / Table 3: VfM Scoring on scale of 1[poor] to 5[excellent]) / Economy / (Unit costs) Economy / (Procurement) Efficiency TOTAL / ZADT 3 3 2 8 / ZMWF 2 3 1 6 / AIZ 2 3 3 8 / AECF 3 4 2 9 / ZADT / The ZADT intervention is broken down into 2 main channels – the Create Fund (Managed by Sabi Consulting), and the provision of technical assistance and training to current and potential beneficiaries of the Create Fund (managed by SNV). For donors wishing to contribute to the program the split in contribution is a predetermined 80% Create Fund: 20% Technical Assistance and M&E. From an efficiency perspective the fund has fallen short of its disbursement target, but this is as much an issue of the funds available growing in volume as it is issues faced by identifying and engaging suitable end beneficiaries. The Trust acknowledges that the top heavy management and governance structure needs to be streamlined [2]. Fund management costs are included in the 11.5% overall interest charged to access funds, this rate is significantly below the market average are low which keeps unit costs low [3]. SNV’s procurement process and Sabi Consulting’s procurement of bank partner services is satisfactory [3] / ZMWF / Due to stringent application procedures only $50,000 of the $595,000 worth of loans approved has been disbursed, 120 micro loans had been made at the time of review. Training and awareness has also proceeded slowly, with the first round of 500 credit clients currently undergoing training (October – December 2012). It is thus too early to make a full efficiency and economy assessment, with a preliminary rating of [1] and [2] given respectively. HIVOS-based procurement processes are viewed as satisfactory, yielding a score of [3] / AIZ / From a VfM perspective overall overhead costs are relatively high (35% of budget), this drives the unit cost score of [2]. The cost of TA provision to beneficiaries is relatively low (at $270/day), and includes the subsidy provided through the use of volunteer consultants, efficiency score is a [3]. Procurement of a vehicle following a formal procurement process and coming in under budget drive the procurement score of [3]. / AECF / DFID supports the AECF at an Africa wide level, with funding for the programme coming centrally from DFID UK as well as various country offices providing funding to specific country windows. AECF has overall been rated as providing VfM from DFID’s perspective[2]. Despite the initially slow disbursement of funds via the AECF Zimbabwe window, results achieved to date have exceeded milestones indicating an efficient delivery of services to beneficiaries [3]. Management fees fall toward the high end of the spectrum (The combined KPMG IDA and AGRAmanagement fee totals 20% of funds provided over 6 years) this drives the unit costs score [2]. KPMG’s procurement cycle conforms to international procurement standards [4] / 5.2 Commercial Improvement and Value for Money / DFID is at a distance from the decision-making relating to procurement under the sub-programmes, resultant from its decision to fund existing initiatives. There is evidence that local procurement practices on the four sub-programmes are of an acceptable standard. / ZADT – The selection of participating banks was based on a competitive bidding process, although the selection of banks was hindered as a number are proscribed. SNV provides good quality processes around the selection of consultants and local capacity builders. SNV withholds a percentage of the contract based on the need to demonstrate the quality of the deliverables. / ZMWF – the purchase of goods and services is carried out through competition and there are procedures, including separation of duties in the procurement process, based on purchase limits that were set by the ZMFW board. / AIZ – grant prizes are paid in tranches based on meeting performance targets. AIZ uses relatively low cost, but high quality volunteers to supplement the core of paid advisers. / AECF –the grant control procedures ensures that funded projects stay on budget at a line item level, with approvals for variations made requiring justification. Changes above 20% require the approval of the investment committee. Checking of invoices includes assessment of grantee financial control and spot checks of accounting records and vouchers. / 5.3 Role of project partners / As lead donors, DANIDA can be expected to provide VFM audits of ZADT and AusAidofAECF. The findings of this annual review in relation to VFM will be discussed with donor partners. / 5.4 Does the project still represent Value for Money : / In general yes, but VFM needs to be properly documented in the 3 E’s framework. Only AECF provided an appraisal off in their self-assessment working to this standard although ZADT subsequently provided this analysis. / 5.5 If not, what action will you take? / The managers of all four sub-programmes should provide a VFM economy and efficiency plan to show how project management overheads can be reduced as projects mature.
[2] DFID Research and Evidence Division, January 2011

6. Conditionality
6.1 Update on specific conditions / N/a

7. Conclusions and actions
The actions are aimed at providing positive recommendations on all four sub-programmes to provide for improved utilisation of DFID funding. / ZADT / Governance of the trust is generally regarded as top heavy and can be rationalized without loss of impact of effectiveness. One of the ZADT board members has been tasked with disentangling the governance structure. / The fund should be preparing for potential leverage of its funding to increase impact (greater efficiency/effectiveness) and potentially increase its appetite for risk, if and when the bank liquidity crisis eases. / The programme needs to provide a clear M&E plan . / The programme managers should provide a VFM Economy and Efficiency plan / ZMWF / DFID will consider supporting a review by the Apex designer to review collateral types (in order to allow more MFIs to qualify); speed up the process of collateral processing (in order to accelerate the use of DFID finance to MFIs for on-lending) and to consider speeding up the disbursement of commitments through faster tranche mechanisms, all within the boundaries of good banking practice. / DFID and ZMWF to consider whether its funding should be passed through to the end user at aspirational rates of interest rather than current market rates, which are currently very high – and how this issue may be addressed through amendments to the programme’s implementation. (improved equity) / The programme managers should provide a VFM Economy and Efficiency plan / AIZ / AIZ and DFID to discuss the potential for encouraging greater innovation through the remainder of the grant prize rounds, for example through revision of the selection committee’s processes. / The programme managers should provide a VFM Economy and Efficiency plan / AECF / DFID are working with the AECF donor group and AGRA to consider policy on repayable grants. / The manager should provide a VFM economy plan to show how it will manage lower cost inputs and a lower level of inputs as the programme matures / DFIDandAusAID will continue to consider how best to align review and reporting processes. / DFID Zimbabwe / DFID Zimbabwe will continue to work with the sub programme managers on a common framework for VFM build around the 4E’s, and for the measurement of jobs as part of the outcome indicator in the revised logframe. / Gender analysis has been largely restricted to the ZMWFprogramme for the purposes of this annual review, given that it is the only sub-programme explicitly addressing gender issues. However analysis of the impact of the programme by gender should be conducted (perhaps at mid-term review stage), which will inform donors and partners regarding any possible programme adjustments. / The PPG programme global logframe has been revised following the review of the 4 subprogrammelogframes. The indicators have been agreed with programme partners at a subprogramme level. The programme team will aggregate and incorporate the targets for these indicators into the global PPG logframe, a copy of which is appended to this annual review. / A key discussion point throughout the review has been the measurement and calculation of the job creation indicator. A note on suggested measurement is appended to this review, with the recommendationbeing that, for practical purposes, the programme reports on incremental income earned in combination with the number of economic opportunities created, rather than the number of jobs created.

8. Review Process
The review was carried out over a 2 week period in-country. The review team comprised Robert Smith, Principal Consultant, Oxford Policy Management as team leader;TonderayiMakumire, Independent Consultant; and David Mollatt, Economic Adviser, DFID Zimbabwe. / The work of the review included technical meetings with all sub-programme managers, and field visits in Harare, the Eastern Highlands, Midlands, and Bulawayo/ Matobo.