Type of Review: Annual Review	ARIES 203668

Quest docs: 3744994 (project document) & 4318727 (logframe)

Project Title:
Monitoring and Evaluation of the UK’s Framework for Results for Malaria (“Breaking the Cycle: Saving lives and protecting the future”) and RMNH (“Choices for Women: Planned pregnancies, safe births and healthy newborns”)

Date started:	April 2013	Date review undertaken: January 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK will provide up to £4.5m to evaluate the implementation and outcome of the two Frameworks for Results which were published in December 2010: / • Breaking the cycle: Saving lives and protecting the future. The UK’s Framework for Results for malaria in the developing world and / • Choices for women: Planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world. / This funding includes up to £205,000 to review the 2011 HIV Position Paper Towards Zero Infections. There are important linkages between HIV and reproductive, maternal and newborn health (RMNH), which DFID aims to strengthen.

What are the expected results?
The funding will provide evidence and better data on how the UK has supported efforts to save and improve the quality of the lives of children and women worldwide by: / preventing, treating and controlling malaria; and / giving women the chance of a planned pregnancy, safe birth and healthy newborn baby. / This will be achieved through delivery of the following: / 1. An Evaluability Assessment of the malaria and reproductive, maternal and newborn health programme portfolios to clarify evaluation questions, assess the complexity and evaluability concerns, assess relevant evaluation approaches, budget implications and availability of data sources. / 2. A Mid-term review covering activities under the Frameworks for Results up to 2013 to take stock of progress in their implementation, advice on how to improve progress monitoring and evaluability and actions to improve achievement of results. Conducting a mid-term review (MTR) by end December 2013 was one of DFID’s Strategic Reform Plan commitments. / 3. In-depth case studies on a select number of Framework interventions and thematic areas. / 4. Final evaluation and evaluation report: The evaluation of the Frameworks for Results will cover the period up to Dec 2015. The scope of the evaluation will be clarified following the results of the initial evaluability assessment and production of the mid-term review. / 5. A contribution to the evidence base for malaria control and the improvement of reproductive, maternal and newborn health outcomes for DFID and the wider global community. / 6. Effective dissemination of the findings and lesson learning to key partners and stakeholders. / In addition, the programme will deliver a review of the progress DFID has made towards the commitments laid out in the 2011 HIV position paper. This will improve the synergies between DFID’s response to HIV, malaria and RMNH.

What is the context in which UK support is provided?
The UK government is committed to reduce poverty in poorer countries, in particular through achieving the Millennium Development Goals (MDGs), including MDG 4 (Reduce child mortality), MDG 5 (Improve maternal health) and MDG 6 (Combat HIV/AIDS, malaria and other diseases). While progress is being made towards attainment of the MDGs, the rate of progress is insufficient to attain the MDG targets in some countries, with particular challenges in reaching the poorest and most disadvantaged. / To support attainment of the MDGs, in December 2010 DFID published Frameworks for Results on malaria and Reproductive, Maternal and Newborn health. These set out frameworks for delivering on UK Government commitments to: / • help halve deaths from malaria in at least ten high burden countries by 2015; / • provide access to modern methods of family planning for 10m additional women, including 1m young women aged 15 – 19 by 2015; / • prevent more than 5m unintended pregnancies by 2015; / • ensure at least 2m safe deliveries, particularly for the poorest 40% by 2015; and / • save the lives of at least 50,000 women during pregnancy and childbirth and 250,000 / Together these two frameworks committed up to £7 billion (up to £4.4 billion for women’s and children’s health and up to £2.5 billion for malaria). / Why was an evaluation needed? / The UK Government is committed to making British aid more effective by improving transparency and value for money and, as part of this, building more and better evaluations into DFID programmes. To honour this commitment the Frameworks for Results describe 5 processes that will be used to inform progress, performance and impact as follows: / • Routine programme monitoring; / • Routine project and programme level evaluation; / • Mid-term review (2013); / • Global and partner monitoring and evaluation process; and / • Final evaluation (2015-6). / Learning lessons from the activities under the Frameworks is important because of the scale of spend across multiple DFID delivery channels and the innovative approach taken by the Frameworks for Results. There has been substantial interest from civil society and donor partners in the Frameworks and the 2011 HIV Position Paper, and an expectation that DFID will carefully review and assess its new approach to these critical agendas in order to better meet our commitments. / In the 2011 HIV position paper Towards Zero Infections the UK Department for International Development committed to review progress against results and reassess strategic priorities in 2013. / Independence and quality / The reviews and evaluations within this programme will be conducted in line with OECD DAC guidance. / The mid-term review and final evaluation of the Frameworks will be conducted independently of DFID. The contract was awarded to e-PACT, a consortium led by Oxford Policy Management through a competitive process. / Quality assurance of the inception report was provided through DFID’s Specialist Evaluation and Quality Assurance Services (SEQAS) process. Independent experts were contracted by DFID to provide impartial advice (see below) and the e-PACT consortium had their own quality review process. / Management / The consortium has been managed by a DFID Internal Management Group (IMG) consisting of a core management team (Malaria, RMNH, Evaluation, Results and Programme Management). / A Monitoring and Evaluation Group (MERG) was established to oversee the evaluation of the Frameworks. Its membership covers a wide cross-section of DFID Departments. In order to ensure independence, two external members have been co-opted on to the MERG: an evaluation expert and an RMNH expert. The MERG has been consulted at important decision points during the progress of the Evaluation. / The review of the 2011 HIV was conducted as a self-assessment by DFID with a call-down contract awarded in April 2013 to a consortium led by Oxford Policy Management including STOPAIDS (formerly known as the UK Consortium on AIDS and International Development) under the PEAKS Health Education and Nutrition Framework Agreement. Oxford Policy Management and STOPAIDS supported DFID in the analysis of programme documentation, an online survey, and three consultative stakeholder workshops - one held in the UK and two regional workshops in Asia and Southern Africa.

## Section A: Detailed Output Scoring

Output 1: Availability of evidence on effectiveness and relevance of Frameworks for Results
Output 1 score and performance description: / B. The final outputs have been delivered to time and acceptable quality as specified by the TORs. However first drafts were of poor quality and required substantial comments from DFID and external experts.
Progress against expected results: / Output indicator 1.1: Concise reports delivered as specified by TORs on the evaluation of the FfRs on time, with only 2 drafts needed before final version and with limited comments from external reviewers. / Planned milestones: Delivery of inception report by June 2013 and delivery of mid-term review (MTR) report by end 2013. / Progress / Partly achieved. Three products were delivered under this output: / The inception report was split into two reports: 1) Evaluability assessment and 2) mid-term review approach paper. / Mid-term review report. / First drafts required substantial comments from the Internal Management Group (IMG). Three or four revisions were needed before the final version could be signed off. The first draft of the mid-term review report lacked analysis and triangulation of evidence from different sources. External reviewers confirmed these views. / OPM consistently missed agreed deadlines, although only by a few days each time. The first draft of the inception report was delivered broadly to time. It was subsequently split into two separate reports. The evaluability assessment report was finalised in November 2013, much delayed from the original timetable. However this did not delay the conduct of the mid-term review which was completed to time. / It should be noted that timing was short to deliver the evaluability assessment and mid-term review. This was driven by an SRP commitment to conduct a mid-term review of the RMNH Framework for Results by end December 2013. / It was complex to review jointly two high level strategy documents and assess both whether the documents and the activities carried out under them have achieved the expected aims. / The consortium faced considerable difficulty in accessing information on progress against the Frameworks. The programme coding structure and quality of coding meant that it was difficult to identify a sample of malaria and RMNH programmes. Annual Reviews were not always available. There was not coherent information at country level on progress against the Frameworks. However, since the consortium had undertaken the evaluability assessment, they should have been aware of the complexities and availability of evidence, and ensured that their proposed approach to the mid-term review was feasible. / The programme was brought back on track by clear communication from DFID on what was expected to be delivered, robust management of timescales and very detailed comments from DFID staff on several versions of the report. Following the comments on the first draft of the MTR report an OPM director was brought in to lead the MTR process. This addressed the issue of lack of co-ordination across the consortium. / The final MTR report was delivered to time by end of December, thus meeting the SRP commitment. It contained important findings and recommendations. These have implications for future DFID strategies (eg that targets need to be incorporated into DFID systems), for the post MDG agenda (on disaggregated data), for the policy teams (on evidence underpinning the strategies) and for DFID’s monitoring and VfM systems. / Output indicator 1.2: Deliverables as specified in the terms of reference for the review of the 2011 HIV Position Paper, completed on time to publish DFID review paper by World AIDS Day 2013 / Planned milestone for end of 2013: Review of results, facilitation of 3 workshops, report on findings and knowledge management system delivered. / Progress / Achieved. More time was required than originally anticipated for the organisation of the 3 workshops, the consultative process and DFID staff input to assist OPM with the collection of data and ensuring the required quality of the narrative report was met. This resulted in delays to the indicative target dates of outputs outlined in the terms of the reference. However, despite the challenges , including acquiring programme data from DFID corporate systems, the work done by OPM and STOPAIDS was delivered in time for the review to be published on the external website by 28 November 2013. / Output indicator 1.3: Number of products reviewed externally with comprehensive comments delivered within agreed deadlines. / Planned milestone for end of 2013: 2 / Progress / Achieved. Three documents were reviewed by external experts who provided valuable comments within agreed deadlines. / The evaluability assessment and the MTR approach paper were reviewed by an external evaluation expert under DFID’s SEQAS process. Timely and comprehensive comments were received within agreed deadlines. / In addition the MTR report was reviewed by two external experts: Paul Balogun a highly respected evaluation expert and Jeremy Shiffman, an RMNH expert and professor at American University. Both were co-opted onto the Monitoring and Evaluation Reference Group (MERG) and provided valuable comments on the draft reports within the required tight timescales. In addition Paul Balogun provided some dedicated support to the consultants during the production of the MTR report. / Lessons learnt: / It is not feasible to aim to evaluate the impact of the Frameworks as a modality in themselves as evidence on their impact does not exist. It is more realistic and productive for the final evaluation to focus on the activities under the Frameworks and whether DFID has met its commitments. / It is also likely to be most productive to focus the final evaluation of the Frameworks on specific evidence gaps, through a phased approach rather than relying on one product in 2015/16. / Complex evaluations of high level strategies are resource intensive especially in view of the limitations of DFID’s data systems. / The involvement of external experts was valuable, in providing an impartial view on the quality of the products and constructive ideas on how the issues should be addressed. / Recommendations on output 1: / The approach for the final evaluation of the Frameworks should be fundamentally reconsidered, including revising the TORs. The IMG should clarify the purpose and scope of an evaluation and its evidence needs and, in discussion with the MERG, agree a revised approach and revised logframe by March 2014. / Impact Weighting (%): 80% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? Y

Output 2: Strengthened accountability for malaria and RMNH across DFID
Output 2 score and performance description: / A. Although the MTR process had limitations and did not build accountability in the way envisaged, a wide range of health advisers and other DFID staff were involved in the MTR both during the inception meeting and during subsequent MERG meetings. The MTR report contains useful recommendations. It provides a basis for internal discussions that should strengthen understanding of the malaria and RMNH portfolios across DFID and build ownership for action that needs to be taken to strengthen oversight and accountability.
Progress against expected results: / Output indicator 2.1: Number of health advisers contributing to the gathering of evidence. / Milestone by end 2013: 15 health advisers contribute (75% of countries with significant activities under the Frameworks). / Progress / Achieved. As part of the MTR evidence gathering, the consultants conducted an e-survey of DFID’s country programmes. It was sent to health advisers in 20 of the 27 DFID priority countries. These were agreed with DFID to be the countries where significant activities are being undertaken against the Frameworks. Responses were received for 16 countries for the Malaria Framework survey and 19 for the RMNH survey. / Two other MTR processes built awareness and accountability for the Frameworks and enabled DFID staff to contribute views. Key Informant Interviews were held with representatives from 12 DFID Departments. In depth case studies were conducted in three DFID priority countries (Ethiopia, India and Nigeria). / Output indicator 2.2: Number of DFID Departments or country offices involved in discussions on implementing the recommendations from the MTR and evaluation. / Milestone by end of 2013: 10 DFID Depts/country offices. / Progress / Achieved. Many of the findings have implications for DFID’s systems for monitoring, evaluation and value for money. These have been discussed with DFID’s Finance and Corporate Performance Division (FCPD), the ARIES team and the Chief Statistician. It is clear that the MTR findings on DFID systems resonate and have been useful in highlighting the key issues and providing concrete recommendations. In addition the findings and recommendations were discussed with the Development Policy Committee on 10 December 2013. / The MTR contains recommendations which are, in the main, helpful to DFID. These are more focused on process and implementation than policy course corrections. This reflects the conclusions from the mid-term review that the Frameworks are important strategic documents and have contributed to increasing DFID’s profile and international influence. The recommendations on monitoring and value for money will be useful in informing FCPD’s plans to strengthen systems and build the case for investment in these areas. The issues of accountability in DFID’s decentralised structure highlighted in the MTR have implications for other DFID strategies. There are, in addition, useful recommendations to update the evidence base and learn lessons from innovative programming. / However, the poor quality of initial drafts eroded internal stakeholders’ confidence in the MTR. It is important now to communicate the key findings clearly and widely, and gain senior management support to address the recommendations. A session has already taken place with the Statistics Cadre at which 14 DFID Departments and country offices were represented. / It will also be important to consult widely on the DFID response to the MTR report. / Output indicator 2.3: % of health advisers aware of MTR and evaluation findings. / Milestone by end 2013: No milestone as MTR only just concluded and had not been communicated. / Recommendations on output 2: / The IMG should develop a communication plan to share the findings from the MTR and rebuild the confidence of internal stakeholders in the report. This should be based around the consultation process for the MTR response. The communication plan should also include external communication. By end January 2014. / The IMG should consult widely on the DFID response to the MTR including with senior management to ensure there is support for the commitments made. By end February. / Impact Weighting (%): 20% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? Y

## If the project involves more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / The logframe indicators have been amended to improve their relevance and measurability. The new logframe was peer reviewed by a statistician external to the Internal Management Group. / 1.2 Overall Output Score and Description: / B (but calculated automatically) / All written products have been produced to an acceptable standard within the required time frame. However, this was not a straightforward process. On the Frameworks for Results, draft document required much input from DFID and robust management of timescales. Input from external experts supported this process. / On HIV, much effort was expended by DFID technical advisors to ensure that the report submitted by OPM, that was the basis for the published paper, was robust and technically sound. The input from STOPAIDS to organise the consultative workshops was invaluable. / 1.3 Direct feedback from beneficiaries / The review processes involved external stakeholders. The MTR of the Frameworks for Results included interviews with a range of organisations, including the AUSAID, Netherlands MFA, UNFPA, Global Fund to fight Aids, TB and Malaria, the Bill and Melinda Gates Foundation, the Children’s Investment Fund Foundation, Roll Back Malaria, IPPF. Country case studies included interviews with government representatives. / The review of the HIV Position Paper consultation process comprised three workshops and online survey involving CSOs, academia, multilateral organisations, people living with HIV and other development partners. / The main points raised from the consultations are included in the reviews. It is too early for any feedback on the usefulness of the products, but DFID will be sharing and inviting feedback from key partners.
1.4 Summary of overall progress / Overall the programme is only slightly off track, due to robust management from DFID. / Both the mid-term review of the Frameworks for Results and the review of the 2011 HIV position paper were delivered on time, despite challenges. Both involved consultations with internal and external stakeholders. / Financial progress has been according to budget apart for slight slippages in the final months.
1.5 Key challenges / It was challenging to meet the TOR requirements and ensuring that the outputs were delivered on time to acceptable quality: / Complexity. The MTR of the Frameworks for Results in particular was conceptually complex as it aimed to assess progress due to the Frameworks themselves as well as the activities completed under them. / Time constraints. The MTR of the Frameworks had a fixed deadline and challenging timeframe due to DFID’s Strategic Reform Plan commitment to conduct the MTR by end December 2013. / Availability of DFID monitoring data. DFID monitoring systems and its decentralised structure mean that it is difficult to track progress on programme activities and performance. / Performance by consultants. First drafts were of poor quality and teams did not work effectively together. Analysis and triangulation of evidence was lacking in some areas. / A key challenge for the future is to raise awareness within DFID of the key findings from the MTR and engagement for addressing the recommendations.
1.6 Annual Outcome Assessment / Outputs have been achieved, with considerable input from DFID. The outcome is ‘improved effectiveness and value for money of DFID and partner RMNH and malaria programmes’. It is too early progress on this as the MTR has only just concluded. The communication plan recommended above will be critical in influencing staff in DFID country offices to implement the findings. / Given the MTR finding that DFID’s corporate focus on value for money does not translate to programme level, there will need to be a particular focus on supporting programmes to improve VfM assessments in order to meet the outcome. / Recommendation / During 2014 the IMG should work with country offices to incorporate VfM explicitly into programmes and share lessons, also working with Human Development Department (HDD) colleagues to share lessons from relevant HDD programmes. / DFID’s Aids and Reproductive Health Team should explore other tools for assessing programme performance to maximise value from other investments, for example the LIST tool, by September 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / The project is currently spending very slightly behind the agreed financial forecasts. The majority of the spending forecast for December 2013 will be dispersed during January 2014. The slippage is due to delay in the delivery of the mid-term review report to the required standard. This is a fixed price milestone contract with 90% fees payable on acceptance of scheduled product to acceptable standard and the 10% remainder paid upon completion of final version including DFID comments. Both payments for the midterm review report were withheld until the final version had been approved. / The contract for the review of the HIV position paper was a similar fixed price staged/milestone contract with the final product due in October 2013. The final report was delivered on time but the stages needed to be re-defined to incorporate additional activities. This was receipted in December but the final payment was not made until January 2014. / It should be noted that the initial estimate for the Evaluation costs (£4.5 million) in the business case proved to be more than was needed. Following a mini-competition under the DFID Global Evaluation Framework Agreement (GEFA), the successful bid to undertake the mid- term review and evaluation of the Frameworks for Results was won by Oxford Policy Management (OPM) Group for £1m (plus VAT). This was accepted by DFID after commercial and technical assessment. / A call-down contract for the review of the HIV position paper was awarded in April 2013 to the consortium led by Oxford Policy Management including STOPAIDS (formerly known as the UK Consortium on AIDS and International Development) under the PEAKS Health Education and Nutrition Framework Agreement. The price of £105,000 which was accepted by DFID after commercial and technical assessment. / The contracts with the two external experts to provide expert and independent advice to the evaluation were call-down contracts limited to 15 days. / 2.2 Key cost drivers / These fixed price contracts were agreed under Framework Agreements established by DFID to provide efficient access to pre-selected and assessed suppliers. / As the evaluation costs for both contracts were above the EU threshold of £113k, Procurement Group (PrG) ran a mini-competition from the GEFA suppliers according to the Terms of Reference. For the Evaluation of the Frameworks the successful bidder was the 2nd cheapest bidder but considered technically the best. Contract negotiations also reduced the cost. / The key cost driver is the ability of the selected consultants to deliver the products outlined in the terms of reference within the agreed fixed price envelope. / 2.3 Is the project on-track against original timescale: Y/N / Yes. The reports were delivered on time while financial payments slipped by about one month. This has required a lot of input from DFID Advisers and staff to ensure that OPM met the TOR product requirements. It also required a few days of additional evaluation specialist consultancy support to advise the consultants and improve the product.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no new evidence that challenges the theory of change and rationale for evaluation. However the difficulties in obtaining monitoring and evaluation evidence during the MTR has implications for the proposed approach for the final evaluation. This is being reviewed. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation is planned.

4. Risk
4.1 Output Risk Rating: Medium / The risk log has been reviewed, see table below. / Risk Impact Like-lihood Direction / of travel Action to mitigate risk / MERG members do not have commitment or capacity to conbribute, or authority to take decisions and implement required decisions. M H ↗ Develop communication plan to build awareness of MTR findings (action 2). / Insufficient expertise and capacity within IMG to maintain momentum over time. M M → Ensure there remains an evaluation expert on the IMG. Include responsibilities in job objectives of members of the IMG. Keep relevant team leaders in HDD up-to-date on progress. / Portfolio of individual project and programme evaluations insufficient to generate new evidence to inform policy and programme design. L M → Review with EvD the DFID portfolio of relevant evaluations. / External evaluator has sufficient expertise to conduct MTR and final evaluation. H H ↗ Reconsider approach for final evaluation by reviewing requirements for final evaluation and amending TORs to focus on specific evidence requirements (action 1). / Mid-term review findings not acted on. M M ↗ Ensure there is senior management backing for MTR findings by consulting widely on response to MTR report (action 4). / Insufficient reliable DFID monitoring data available to monitor performance. H M → Consult FCPD on the commitments on monitoring in the MTR to ensure feasible and integrated into work plans. (action 4). / Evidence generated is not disseminated to external stakeholders. M L → Develop communication plan for internal and external stakeholders (action 2). / Partners do not act on evidence generated. M M → HDD teams identify opportunities to influence for change through global forums. / 4.2 Assessment of the risk level / The risk is assessed as medium overall. The key challenge going forward is achieving DFID buy-in to the findings and recommendations from the MTR report and developing a robust and feasible way forward for the final evaluation.
Risk of funds not being used as intended / Risk of misuse of funds is low. All 27 eligible bidders under the GEFA have been subject to stringent financial checks. The risk of fraud is being mitigated through the use of fixed price milestone contract with detailed budgets. / Funds are only directed to OPM (and via them to associates) mainly based in the UK. Very limited funds directed to overseas consultants for country studies undertaken and consultative workshops. OPM is an international organisation of repute and funds are only directed to OPM against invoices received when workplan milestones are achieved according to workplan or reimbursable expenses Expenses are actuals and only reimbursed upon presentation of receipts. / 4.4 Climate and Environment Risk / The main climate and environment risks that derive from this programme are related to international travel by the evaluation providers. Although the evaluation will mainly involve the analysis of secondary data supplied to the evaluation provider, some primary data will be collected. Where possible this will be through telephone, VC or e-surveys. / Six country case studies are planned. Three have already been carried out for the MTR which involved some air travel. However where possible the evaluation provider used existing in-country staff to collect data. / There are substantial potential benefits from improving DFID and global effectiveness on RMNH, especially family planning and the associated reductions in population numbers.

5. Value for Money
5.1 Performance on VfM measures / The programme will deliver value for money by generating evidence products that improve the way DFID and its partners manage their malaria and RMNH programmes. / Economy: The contract to deliver a MTR review and final evaluation was agreed at just under £1m, rather than £4.5m as envisaged by the Business Case. / Value for money was one of the criteria for selection of the preferred provider. Measures to minimise the cost included assessment of the proposed methodological approach and data collection methods to minimize unnecessary travel, workshops or meetings. The assessment of bids also considered the expertise, salary and length of effort of staff assigned to the project, other direct costs such as per diems, consumables and indirect costs of the provider and any additional costs incurred with a consortium arrangement or proposal for a sub-contract agreement. / The OPM bid was also the most competitive with regard to costs and was let on a fixed cost basis on the advice of Procurement Department. With 90% of costs payable upon completion of acceptable draft and remaining 10% upon final acceptance. DFID achieved savings through its contract negotiations with the preferred bidder. / Efficiency: Efficiencies have been achieved through proactive project management and transparency about DFID approach to consultancy fee rates, travel costs and incidentals. This has raised awareness by OPM of the need to demonstrate VfM and to reduce unnecessary costs. As a fixed price contract, there was flexibility within the contract envelope regarding the deployment of resources (ie: people) as the project developed. The original estimates of consultant daily inputs had to be re-assessed on a regular basis from the original assumptions, as the actual requirements regarding inputs required became clearer. This was undertaken at no additional cost. This led to the most efficient mix of inputs to obtain the required result, within the original fixed price. Early planning and use of DFID country office facilities has allowed workshops and meetings to be held at minimal expense. / Effectiveness: The effectiveness of the overall programme will be maximised by ensuring that the findings are incorporated into DFID programmes and the work of our partners. The communications plan for the MTR report will be crucial for building awareness and confidence in the findings. / 5.2 Commercial Improvement and Value for Money / Much of the scope for commercial improvement and VfM has already been pursued during initial contractual negotiations. DFID took a robust approach to addressing the poor performance by the consultants, signalling strongly that the first draft did not meet the requirements of the terms of reference. This was successful in bringing the MTR back on track, with the personal involvement of an OPM director to oversee the process. DFID also strongly signalled its unwillingness to consider cost- or time extensions. / 5.3 Role of project partners / OPM and its partner organisations are the implementing partners for this project. / 5.4 Does the project still represent Value for Money : Y / The project does represent Value for Money, but it is clear that, given the complexities of the activities being carried out under the Frameworks and the difficulty of accessing monitoring information, the approach envisaged for the final evaluation needs to be amended. / 5.5 If not, what action will you take? / DFID is considering its requirements and the implications for the Terms of Reference.

6. Conditionality
6.1 Update on specific conditions / None.

7. Conclusions and actions
The Framework for Results MTR was completed to time, thanks to robust management of performance by the consultants and considerable input from DFID staff. / The MTR has identified useful findings for DFID and these now need to be communicated widely across DFID and with external stakeholders. / The HIV review was also completed to time, but involved similar challenges and the need for extensive input from DFID. / Summary of recommended action / The approach for the final evaluation of the Frameworks should be fundamentally reconsidered, including revising the TORs. The IMG should clarify the the purpose and scope of an evaluation and its evidence needs and in discussion with the MERG, agree a revised approach and revised logframe by end March 2014. / The IMG should develop a communication plan to share the findings from the MTR and rebuild the confidence of internal stakeholders in the report. This should be based around the consultation process for the MTR response. The communication plan should also include external communication. By end January 2014. / The IMG should consult widely on the DFID response to the MTR including with senior management to ensure there is support for the commitments made. By end February. / During 2014 the IMG should work with country offices to incorporate VfM explicitly into programmes and share lessons, also working with HDD colleagues to share lessons from relevant HDD programmes. / DFID’s Aids and Reproductive Health Team should explore other tools for assessing programme performance to maximise value from other investments, for example the LIST tool, by September 2014.

8. Review Process
The review was carried out by the Internal Management Team (Penny Innes, Nichola Cadge, Gillian Mann, Anna Henttinen and Scott Hardie). The team consulted with Human Development Department team leaders. / Advice on the logframe was provided by Sarah Hennell from DFID’s Education Policy Team, who confirmed that changes made were appropriate. / Next year the Annual Review will capture views from DFID country offices.