Type of Review: Annual Review

Project Title: African Enterprise Challenge Fund (AECF) -South Sudan Window

Date started: September 2011
Date review undertaken: Nov/Dec 2013 (fieldwork 10-15 Nov 2013)

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Please note that the review below was carried out prior to the onset of civil unrest in South Sudan in December 2013. The recommendations within the review document will therefore need to be reviewed in the light of the changing context. / DFID has committed £6m to the Africa Enterprise Challenge Fund South Sudan Window (AECF SSW) to provide support to selected enterprises in the agribusiness and agriculture sector that will have an impact on the rural areas of South Sudan. / An Accountable Grant of £6m was signed between DFID and the Alliance for a Green Revolution in Africa (AGRA), a non-for profit organisation based in Nairobi with effect from October 2011 until December 2014. AECF is a special partnership initiative of AGRA. / The Fund Manager (FM) of the AECF SSW is KPMG International Development Advisory Services Africa, based in Nairobi. A dedicated adviser with the right experience was recruited by the Fund Manager to lead the SSW and has been in place for the majority of this current reporting period (took maternity leave in Sep 2013). She has been replaced by a similarly qualified, dedicated adviser. The AECF SSW Team is based in Nairobi at AECF Head Office and has travelled extensively in South Sudan for the marketing, relationship management, assessment of the Business Plans, and monitoring of supported businesses. In the three months from Sep – Nov 2013, the incoming DFID South Sudan Food Security and Livelihoods Adviser has met with the incoming KPMG adviser three times in South Sudan. This is indicative both of the frequency of the FM team’s visits, and of DFID and KPMG acting on the recommendations of the previous annual review (of November to December 2012) which strongly suggested increasing the frequency of face to face contact between DFID and FM staff. / AECF SSW was launched in October 2011 with a series of well-attended events, with the Minister of Agriculture of the Government of South Sudan (GoSS) in London (with DFID Secretary of State) and Johannesburg at a regional agriculture conference. It was accompanied by a promotion campaign in South Sudan and in the Region targeted at potential investors. / The second year of operations has focused on finalising grant contracts with the selected Agri-businesses whose Business Plans were approved and transferring the first tranches of the approved grants. By the end of the year, 5 out of the 6 selected businesses had signed contracts and 4 of them had received funds from AECF.

What are the expected results?
The Africa Enterprise Challenge Fund South Sudan Window supports private enterprises that will contribute to the expansion of an innovative and commercially viable agricultural and agribusiness sector that benefits the rural poor in South Sudan. / This programme expects to: / Benefit 50,000 farmers/out-growers and clients directly and approximately 325,000 beneficiaries when their family members are included. The average household size in South Sudan is 6.5 (National Baseline Household Survey 2009); / Achieve a total annual benefit to 50,000 rural households of US$ 20 million by 2016 ; / Establish 6 new businesses in the same [agricultural] sector using new technologies and business models; / contribute to increased lending by commercial banks to the agri-business sector. / These are the objectives set out in the logical framework revised three months after the previous annual review following an iterative process of modification between DFID, Fund Manager and AGRA based on the recommendations contained in the previous annual report. / It is to be noted that following a DFID-commissioned mid-term review of the overall AECF programme, the AECF is moving towards a results framework based on the recommendations of the DCED (Donor Committee for Enterprise Development), to capture better AECF wider impact. The development of a more generic monitoring and evaluation system for the AECF is currently a live discussion at AECF board level. / Monitoring: A monitoring mission is currently planned for the end of January 2014 to assess the current monitoring framework of the AECF and assess the strength and VFM of implementing DCED across the portfolio, particularly retrospectively. The Mission will provide recommendations for the design of a new monitoring system for the portfolio (whether it is DCED or not). The Committee will make a decision on the new monitoring system one the monitoring mission has been completed and reported the findings and recommendations. / Evaluation: DFID is currently tendering to conduct a Mid-term Evaluation next year which will include an evaluation of the new monitoring system as well as following the DAC evaluation criteria.

What is the context in which UK support is provided?
The context has not changed significantly since the 2012 Annual Review. / 1. South Sudan is a new country with vast opportunities to tap, especially in the agriculture sector. / - South Sudan can rely on abundant natural resources, especially in the southern provinces; it is not densely populated and land is available for new ventures. Currently less than 5% of arable land is cultivated. / - GoSS is “keen to cultivate and nurture a conducive investment environment in the country”.[1] Private sector investors are protected under The Investment Promotion Act of South Sudan of 2011. Agriculture has been identified as a priority sector for investment and the importance of generating growth in this sector was stressed at the Dec 2013 Investment Conference held in Juba. / - South Sudan can attract the type of investors who want to benefit from the first mover advantage and have an appetite for high risk/high reward. / - It is close to the neighbouring countries of the East African Community (EAC). The Government of South Sudan has signalled its commitment to join the EAC and accession talks are underway. / 2. However challenges remain immense and the analysis done in the DFID Submission remains valid. / Despite progress since the Comprehensive Peace Agreement (CPA) signed in 2005, the economy remains very much “post-conflict” in its nature and, confirmed by surveys such as the World Bank Doing Business in Juba 2011, is affected by: / weak private sector capacity; / lack of infrastructure, and especially poor road and transport network to serve agriculture areas; / incomplete regulatory framework. GoSS has low capacity to put in place the policies and institutions that will create an enabling environment for private sector investors and owners. / Conflict risk remains high in South Sudan (and post-review has again erupted). This risk includes internal localised conflict, internal widespread civil and military conflict and conflict with elements of the state of the Republic of Sudan including localised conflict across national borders or inter-state conflict. / However there has been progress supported by the IFC in the last year to improve this and an active South Sudan Business Forum that is supporting development of the regulatory framework. / The 2014 World Bank Doing Business Report ranks South Sudan 186 out of 189 countries on ease of doing business. The financial sector is under-developed, road density is the lowest in Africa, and the literacy rate is just 27%. / To these well-rehearsed factors must be added the negative perception about farm work amongst the population, especially the young, and the low productivity of the labour force. Semi-skilled labour from neighbouring countries is still being imported to fill this gap. South Sudan labour costs are significantly higher than its neighbours. / 3. DFID and GoSS agree as well as major donors that the agriculture sector is key to development and poverty alleviation and that the private sector has a unique role to play to drive a development strategy - 85% of the population live in rural areas and work in agriculture, however the great majority of farming is low-tech, subsistence level production. Agricultural productivity is extremely low: in 2011 South Sudan produced about 600,000 tonnes of cereals compared to more than 4 million tonnes in Kenya and about 3.5 million tonnes in Uganda[2]. The poverty ratio is 55.4% (2009 World Bank data); / - Agriculture has been recognised by the donor community and GoSSas a sustainable alternative to the oil sector which, prior to the shutdown in 2012, represented 70% of the GDP and 98% of government revenues. Oil production from existing fields is expected to decline gradually from 2014 until it ceases around 2035. - The country is affected by severe food shortages and a vibrant agribusiness sector is one obvious exit strategy to short term emergency and humanitarian aid. / 4. However the Investment Climate has significantly deteriorated since the appraisal of the Programme by DFID and its partners / Although the oil pipeline between South Sudan and Sudan is now open again the potential for it to continue to be used as a political bargaining chip between both countries remains, and this uncertainty contributes to overall uncertainty in the investment climate. / Some regions continue to experience insecurity and local conflict detrimental to free movement of goods and people, and to long term investors’ confidence.
[1] Annual Review SSW Nov-Dec 2012
[2] FA O - W F P S p e c i a l R e p o r t , 2 0 1 2 : C r o p a n d F o o d S e c u r i t y A s s e s s m e n t M i s s i o n t o S o u t h S u d a n | A c c e s s e d o n N o v. 2 0 , 2 0 1 3 v i a www.fao.org; http://bit.ly/1aIbmO9

## Section A: Detailed Output Scoring

Output 1: Innovative Agri-business provided with finance and credit facilities required to get off the ground
Output 1 score and performance description: B: Output moderately did not meet expectation
Progress against expected results: / One competitive round has been completed. Up to the date of this review: / 41 concept notes were accepted / 15 Business plans developed / 6 Business plans approved in 2012, / 5 agri-business companies have signed contracts with AECF in order to commence operations. / These are: / Century Seed Company Ltd- for maize seed replication and national distribution and sale / Honey Care Africa Ltd-honey collection, refining and sale (largely export) / South Farmers Company- commercial crops production and integrated poultry venture / Garden of Eden Company Ltd- Maize Production, value added services and Market Access for small holder producers in Central Equatoria State / Frontier Finance- Provision of microcredit to micro-enterprenuers in the Agriculture value chain / A sixth business that passed successfully through the selection process has still been unable to sign the financing contract with AECF (Dryland Seed Ltd) There is doubt as to whether this contract will be finalised. This will of course have an impact in reducing the overall funds disbursement. Another selected business, Frontier Finance, has only received a relatively low proportion of allocated funds ($50,000) to date, as they have not yet been able to confirm that they have secured sufficient external longer term investment. Full disbursement will occur when that confirmation is received. / The original number of contracts intended was 11. To date only 5 out of that 11 have been finalised, and funds disbursed. / There is a question over defining ‘innovative’ agri-business in the context of South Sudan. In a more general context, none of the businesses selected could be regarded as particularly innovative. However in the specific context of South Sudan, where agri-business has been unable to get established due to years of protracted conflict, all business is essentially innovative. Therefore using the South Sudan context as unique, the agri-businesses supported can be said to be ‘innovative’. The Fund manager (KPMG) noted in their Contract completion note to companies selected that ‘Most companies are new, small and informal according to AECF standards and would not have been considered for funding in any other competition’. This is indicative of the new and very fragile business environment in South Sudan. Definitions, and to an extent rigour, has had to be relaxed or there would be no eligible companies that would qualify under AECF. / There is also an issue around how we define a business ‘getting off the ground’. So far, this programme is still at a very early stage with contracts only signed within the last 6 months and businesses still in the process of establishing their operations (Honey Care still constructing their office and processing facility and South Farmers still constructing their hatchery). Realistically these businesses have not yet ‘got off the ground’ and so assessing them against this Output target is premature. One agricultural season also does not prove a viable operation for businesses dependent on a reliable and sustainable supply of agricultural products, be they seed, grain or young chicks. Viability can only be proven after successive successful seasons. / Recommendations: / A rapid decision is needed from the Fund Manager on completion of contracts with the remaining selected company (Dryland Seeds) and if this will not be completed a revised budgetary forecast will need to be produced quickly. This will relate to available unallocated funds under the AECF SSW in terms of making decisions on alternative options for reallocation of those funds. This also applies to the uncertainty surrounding the full allocation for Frontier Finance still pending. / Impact Weighting (35%): / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? Yes. / Note that the previous annual review recommended a revision to ‘high risk’ due to the lower than average quality of proposals compared to quality in AECF’s more ‘average’ portfolio, plus the relative lack of providers of finance and credit facilities. Given that just 5 businesses of an original intended 11 have achieved the output, this review concurs that risk level on this output alone be raised to high.

Output 2: Increase in commercial private sector investment in agriculture and agri-business
Output 2 score and performance description: / A: Output met expectation
Progress against expected results: / At this stage this must be read as matched funds secured from selected companies. The AECF South Sudan Window requires private companies to commit at least equal to or greater than 50% of the total cost of the venture from their own sources. It is too early to expect any measurable private sector investment in agriculture and agri-business in non-AECF business ventures as a comparator or multiplier effect as the original businesses have not yet had an opportunity to become sufficiently established to provide a replicable example and there are no targets against this in the revised log-frame until 2015. / There is a wide variation in the amount of matched funding pledged from the selected companies as few of them had significant liquid capital they were able to commit. The business environment in South Sudan means that very few small companies have as yet been able to accumulate significant liquid capital. However they have been able to negotiate successfully with the fund manager a valuation of capital assets that would be used in their ventures to be accepted as contributing to the matching commercial funds. There are questions though over that valuation, including whether a consistent valuation of capital assets has been applied across all supported companies, and which assets individual companies have been able to negotiate as constituting valid capital equipment that can be regarded as an in-kind contribution. / Overall the following matching funds have been committed by selected companies with a breakdown between cash and in-kind assets: Currency is USD$ / Company Cash contribution In-kind asset contribution valuation 3rd Party equity investment AECF grant/loan amount Total / Century Seed Co. Ltd 200,000 300,000 500,000 1000,000 / Honey Care Africa Ltd. 1,561,000 1,128,295 1,250,000 3,939,295 / South Farmers Company 150,000 861,502 150,000.00+ / 150,000 (bank loan) 800,000 2,111,502 / Garden of Eden Company Ltd. 375,000 760,300 750,000 1,885,300 / Frontier Micro-Finance Ltd 820,000 500,000 1,320,000 / Dryland Seed Ltd. Not yet committed 584,869 584,869 / So far over 22,000 businesses have been registered in South Sudan (including 260 foreign companies). The International Finance Corporation (IFC) and the South Sudan Business Forum are cautiously optimistic about an improving business environment in South Sudan. There have been incremental improvements in the legal and regulatory framework.19 private sector laws have been enacted to ease business development. A one-stop shop has been established in the Ministry of Commerce, which can in theory allow a business to be registered within 2 days and helps investors navigate through relevant business regulations. However, significant barriers to investment remain including defining and agreeing what counts as collateral for a business e.g. cattle (which are a significant capital asset in South Sudan) are not acceptable as collateral. The definition of land as collateral is also still unresolved. The result of this is that it is extremely difficult to access credit on the domestic market. An insurance bill is still under preparation but at present there are no clauses that cover losses due to conflict, natural disaster etc. The security situation, lack of infrastructure, low capacity in the workforce and an ineffective legal system all further negatively impact investor confidence. Recommendations: / Clarify and standardise the definitions of matching funds across the portfolio and maintain consistency in this through the life of the programme. Consider using financial auditors to value capital assets being used as collateral / matched funds. Inconsistency in this area will make tracking difficult and in establishing a level playing field to measure progress. / Impact Weighting (35%): / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No / Note, last AR recommended considering increasing the risk rating to high. However, given output met expectation, that there are small but positive signs that the broader business environment is improving, and that the recommendation is more around methodology of valuing assets, this AR suggests leaving this rating intact. For more on risk, see section 4.1 below.

Output 3: New business models developed
Output 3 score and performance description: A: Output meets expectation. / However, it is still very early days and although all the ventures are in effect (in South Sudan) new business models, there is no firm indication at this stage whether they are likely to be successful business models and whether there will be any replication by non-AECF funded enterprises.
Progress against expected results: / There is no specific indicator at this stage of the South Sudan window as it was expected to be too early to see firm and lasting results. This assumption has proved to be correct. / However all investments in agri-business in the specific context of South Sudan, are ‘new business models’ and will provide an indication of what may work in this context, whether there is a sufficiently attractive and lucrative market and will provide pointers for future investments in terms of market gaps and opportunities. / AECF expects that all projects will create systemic change. This is change in systems, such as markets, government, or civil society. However at this stage this expectation is premature. / Recommendations: / The last Annual Review recommended that future Annual reviews will assess the use of the £158k budget that has been ring-fenced to disseminate case studies, best practice to communicate on the AECF impact. However given slow progress in implementation this is still a task for the future – but an important one for consideration over the coming year. / Impact Weighting (30%): / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Yes / Amendments have been made to the indicators language and to give numerical milestone targets against indicators. These include: / Changing the Outcome indicator and in particular subdividing it into three indicators: direct beneficiaries, total annual and cumulative benefits, number of new businesses initiated. The indicator for ‘jobs created’ has been removed as this is better captured in total benefits. / The indicator for ‘Number of policy/regulatory changes influenced by evidence provided by the SSW’ has also been removed / Under Output 1 the indicator for ‘capitalisation of funds’ has been removed / These amendments were made following the first Annual Review and in full consultation and agreement with AGRA and KPMG. / 1.2 Overall Output Score and Description: / Overall, the programme scores an A (outputs met expectations) based on the relative weighting of the outputs: / Outputs 2 and 3 scoring a (qualified) ‘met expectations’ (A) with a combined weighting of 65%; / Output 3 scoring a ‘moderately did not meet expectations’ (B) with a weighting of 35%. / Although this represents an improvement from the last annual review, this relative success is marginal and fragile and should not be accepted complacently. / 1.3 Direct feedback from beneficiaries / Three of the businesses supported by AECF were visited during this review mission and these therefore provide all of the beneficiary feedback into this report. We were not in a position to visit the primary producers and include their feedback. / Century seeds in Yei / Century Seeds is working with farmer’s outgrower groups in Yei, Kajo Keji and Morobo to multiply maize seed for national distribution and sale. It is difficult to separate out and attribute the inputs and impact of the AECF assistance from that of the similar USAID funded FARM programme which works with many of the same farmers as under AECF support. / For example FARM provides farmers with extension advice which impacts on their agronomic practices, which may alter the success or otherwise of their agricultural production techniques. The next stage of the FARM project will build marketing skills of farmers. / There is also no clear boundary between farmers in the AECF maize out grower scheme and farmers benefiting from the FARM project. Honest attribution therefore is very difficult. / Erratic weather this year has had an impact on success. There was an unusual drought in April and May when rains were expected which delayed seeds distribution and planting. Planting was therefore delayed and harvest results were still not complete by the time of this annual review. It was therefore not yet possible to give figures for this year’s harvest and therefore to make an evidence-based judgement on achievements. Farmers are reporting changed weather patterns but there is insufficient evidence over a long enough period to ascribe this to any provable changes in weather or to climate change. / Securing farm labour from the local area has proved difficult for Century Seeds and they have had to import labourers from Kenya at increased cost to their business. / Century seeds is working with163 farmers in outgrower schemes organised into 9 Farm-based Organisations / Honey Care Africa in Juba / Honey Care Africa is a Kenyan company who have registered in South Sudan to conduct business in honey collection, production, processing and marketing. The majority of the honey produced will be for export, initially to the Kenya market but also possibly later to more distant markets including Dubai and north America (European certification requirements make export into the EU more challenging). / Presently their South Sudan operation is very small with only three staff. They have established a small office and processing unit in Juba although it was still under construction at the time of the review. Their community development officer was on his first buying trip to honey collectors and as such harvesting figures were not available. These, when available will include number of suppliers, quantity collected, buying price and commercial value. Without those figures it is not yet possible to provide any quantitative assessment of the success or scale of this new operation in South Sudan. / Initial feedback from the Honey Care South Sudan manager highlighted several constraints. These were the lack of any rural financial services, which means that payment for honey has to be through physical cash transfers. This has obvious security implications in a country where banditry is becoming more common. Business documentation delays means that although honey is physically being collected Honey Care has yet to receive an export licence to export it to Kenya. Fortunately the shelf life of honey can accommodate moderate delays in this. These challenges highlight the difficulties of doing business in such a fragile environment as South Sudan and why, as yet, the number of business investments in the country remain modest. / Honey Care was on their first buying trip during the Annual Review. So far this season Honey Care has mobilised 74 suppliers in the Mang'alotore Boma-Payawa area. However as of mid-December they have not completed a successful collection. Expected sellers had sold their honey cross-border to Uganda instead of to Honey Care. This was due to delays in reaching the sellers due to flooded roads in the southern areas around Kajo Keji. Honey Care was still hoping to find alternative sellers in the region of Yambio and Iba. / South Farmers in Juba / South Farmers is a new company established by a South Sudanese former emigrant to Australia who returned to South Sudan to use his business skills to contribute to national economic growth. He is young but very enthusiastic and energised. / South Farmers is working with farmers in Kajo Keji primarily in maize production. A positive element of the business model being developed by South Farmers is a link to supply the UN World Food Programme with maize. Indeed the entire harvest from the first year of this programme is contracted to supply to WFP allowing farmers to retain enough for home consumption. As this is a guaranteed market it will not yet prove the viability of the maize marketing model in the open market in South Sudan. South Farmers need to be able to demonstrate that they can sell maize on the open competitive market as well as to supply humanitarian interventions. That notwithstanding it is a good example of the Purchase for Progress scheme (which is globally supported by DFID) where WFP purchase locally rather than import grain for humanitarian distributions. / South Farmers though could not give any estimation of harvest quantities or yield from this year’s harvest as yet. Maize has been collected but not yet shelled so grain quantities are still not yet calculated. The drought in April and May also delayed planting times and the first planting prior to the rains failed. / South Farmers has established a nucleus farm and have registered 450 farmers to supply maize, although their expectations are that only 225 of them will be actively producing this season. / South Farmers is also establishing a poultry hatchery in Juba to supply chicks to the South Sudan market for broilers and layers. They are estimating production of 45,000 chicks per week. Construction is still under way and is expected to be completed in January and to be producing by the end of January.
1.4 Summary of overall progress / Progress is incomplete with 5 out of 6 businesses having signed grant contracts. A delay in the agricultural season due to early season drought has impacted on harvests and no harvest or production figures were available at the time of the review. Where production or processing facilities are required these are largely still under construction and not expecting to be able to operate as planned until at least December or possibly into the new year 2014. / Although the business climate is improving in South Sudan significant challenges remain and there is continuing uncertainty over the political stability of this country in its fragile post-conflict state and in investor confidence and business capacity and skills. It is too early to predict whether current investments will succeed and whether as yet they provide a business model that will inspire confidence and replication. / What is clear is that there is an enormous demand for the type of primary products being offered by these businesses but that this demand is still almost exclusively being met by import from surrounding countries. / The Theory of Change for this programme states that ‘Supporting private sector initiatives in South Sudan has the potential to tackle poverty, hunger and vulnerability, support wealth creation and contribute to longer term stability and conflict reduction’ The programme must ensure that monitoring captures all of those aspirations. The potential for the better off farmers and those more market-ready to capture the opportunities presented by this programme is still strong although the extent to which the programme he question will really tackle poverty, hunger and vulnerability amongst the most vulnerable remains to be tested. Also there is no clear mechanism for how this programme will contribute to longer term stability and conflict reduction beyond a hope and an aspiration.
1.5 Key challenges / State of business environment and enabling legislation / Although there are positive indications, from IFC and from the South Sudan Business Forum (SSBF) that the business environment in South Sudan is improving there are still significant challenges. In principle the processes required for business registration and start-up are improving. However investor confidence in South Sudan is still low. The Fund Manager has stated that South Sudan is the most challenging country in the entire AECF portfolio and the most difficult in which to do business. This partly reflects prior and some existing bureaucratic hurdles but also a wide range of other factors including lack of skills, lack of infrastructure, ongoing conflict and instability, weak and inexperienced government. It was only in 2012 that the Bank of South Sudan Act established commercial banking in South Sudan. Major investors are still reluctant to invest in the country although the IFC has shown that business-enabling legislation is improving (19 private sector laws enacted) and registration is increasing (22,000 to date). / Conflict and instability / Outside of Juba many regions of South Sudan are still plagued by conflict and instability. This is most pronounced in the border areas with north Sudan, but is also significant in Jonglei, and the borders with DRC and increasingly CAR, which itself is descending into chaos. This instability is a significant disincentive to the growth of business and also holds up investment in vital infrastructure, including roads, bridges and telecommunications. / Poor state of infrastructure / During the review period, Juba was experiencing major shortages including of fuel and foodstuffs. This was due to the roads from northern Uganda being impassable due to flooding. South Sudan is almost completely reliant on importation of non-subsistence food and basic materials, from surrounding countries. While this provides an incentive for business to start to produce more locally, until that production reaches a significant level, the reliance on imports will remain. Importation depends on all-season roads, including trunk roads and feeder roads. Without that access business within South Sudan and into and out of South Sudan will be continually curtailed. / Land tenure and ownership uncertainty / While there is still no clear legislation on land tenure or ownership this acts as a disincentive, both to investors and to farmers. / At the moment the GoSS has no agenda on this beyond ‘Build awareness on access to land, land acquisition and utilisation’. [3] / Lack of skills / We met the NGO SPARK for an overview of capacity issues in South Sudan who run two projects in South Sudan, the Agri-Business Creation (ABC) and the Youth Engagement Programme (YEP). ABC focuses on job creation for youth through agricultural business and agricultural value chain development, while YEP is aimed at improving the socioeconomic position of youth, in particular through entrepreneurial opportunities. They confirm other assessments that critical business skills are in short supply in South Sudan. The only faculty of higher education as yet offering training in these areas is the Catholic University of Juba which runs courses in Business Administration. / Many of the business skills in South Sudan are coming from the return of the diaspora including those who lived in (north) Sudan. / There is therefore an essential need for development of these skills as without them the viability of indigenous businesses will suffer. Many investors are still employing more skilled staff from regional neighbours including for example Century Seeds who employ Kenyan farm labour. / Reaching the poor and most vulnerable / From conversations with the three businesses visited in the AR a picture emerges of a programme which is already reaching farmers who are to an extent already entrepreneurial and attuned to a market economy. It was not clear how this programme will extend beyond this group to reach the more poor and vulnerable farmers. / There were indeed frequently expressed informal opinions related to this group indicating a lack of confidence and belief in their willingness and capacity to become engaged in a market-led economy. With an economy so new and fragile although it is important to provide stimulus at levels where it is most likely to have immediate returns, there is a risk of leaving those less capable and motivated behind and in doing so create societal divisions which may sow the seed for future conflict and instability. The programme does perhaps need to address this more self-critically in line with the original Theory of Change and propose how it may achieve more than cherry-picking the better endowed at the expense of the weaker and more vulnerable.
1.6 Annual Outcome Assessment / The AECF is set up to provide support to business-ready enterprises. It has no current function to build capacity of businesses. However this assumption must be challenged in the context of South Sudan. The level of existing capacity in the country is very limited. This is a country emerging from decades of conflict, with minimal human development outside a few small urban centres. There has been no history or tradition of private entrepreneurship. Private enterprise in South Sudan predominantly means livestock herding. / The main skills in business management are coming from a returning diaspora, including from Sudan to the north. These are mostly petty traders and farmers rather than anyone experienced in managing large enterprises. A few enthusiastic entrepreneurs such as the Director of South Farmers exist but even they are relatively inexperienced.
[3] SOUTH SUDAN BUSINESS FORUM (SSBF) Report of the INAUGURAL BUSINESS SUMMIT 29TH - 30TH October 2013

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / As of the 31st October the Fund Manager has disbursed $956,089 from a round one commitment of US4.4 million. It is uncertain now whether even that full $4.4M will be disbursed as there are doubts as to whether one of the selected companies (Dryland Seeds) would in fact be able to sign a contract. This would reduce the overall disbursal further to a potential total of $3.8 million from an original planned figure of $7 million committed by AECF or 54.3% of the original total committed funding. / 2.2 Key cost drivers / The key cost drivers are still (a year on from the last Annual Review) establishment costs as the programme has not progressed greatly from establishment phase to operational phase. / Several partners are still establishing their operational and production capacity and their main investments presently are in getting that up and running. / Uncertainty around harmonisation of the official and black market exchange rates (SS£ and the US$) were causing worries for the business community in Juba, and are likely to continue to affect business confidence (as well as provoking some social unrest). / 2.3 Is the project on-track against original timescale: No. / The last Annual Review suggested that the original timetable was unrealistic but it has not since been amended. / By 31st October 2013 21.8% of the funds had been disbursed against an original target of 25%. The shortfall was due to failure to sign a contract with Dryland Seeds and the reduced first payment to Frontier Finance. / There is grounds for optimism that with 5 ventures funded and production underway that the delays can be made up, although this is largely dependent on a range of external risk factors including factors affecting the agricultural season, the ability of roads to remain open for movement of inputs and produce, and the potential for localised conflict to erupt. / Harvest and production figures from the first season (still awaited) will indicate how realistic an expectation of getting back on track is, and whether it is reasonable to expect more predictable progress against targets from now on. A post-conflict country such as South Sudan is never going to provide an environment of perfect predictability and expectations of success must be tailored against this reality.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / As already discussed the SSW programme was designed to ‘tackle poverty, hunger and vulnerability, support wealth creation and contribute to longer term stability and conflict reduction’ / These were ambitious expectations and it is becoming apparent that measuring success against those criteria will be challenging. The logframe is designed to measure quite tangible outcomes and outputs including numbers of beneficiaries, benefits accrued, new businesses initiated. / Those very quantitative indicators will not capture the more qualitative goals articulated in the original project submission note. None of them directly measure reducing poverty, hunger or vulnerability which are seen to be more indirect and longer term impacts. There is no evidence being collected either which will show how this programme will ‘contribute to longer term stability and conflict reduction’. / Given that these aspirational targets are not being captured or, so far, being measured in any way, it may be an appropriate moment to consider this and to look beyond the readily measurable to the qualitative to consider how the programme may achieve its original goals. / 3.2 Where an evaluation is planned what progress has been made? / Not applicable at this stage for SSW specifically, but to note the comments on page 3 regarding Mid-Term evaluation for AECF portfolio as a whole.

4. Risk
4.1 Output Risk Rating: Medium / This programme was assigned an original overall risk rating of Medium. The last Annual Review queried the rating, given the multiple challenges to the business environment in South Sudan. However positive signs in the last year cause this review, with a degree of caution to continue to support the medium risk rating. / The regulatory environment has improved somewhat in South Sudan easing the process of Business registration and licencing. The GoSS is more open now to the private sector and through the South Sudan Business Forum actively encouraging investment, both internal and external. There are still regulatory and bureaucratic hurdles to overcome and issues such as land tenure and ownership, as well as establishing clear guidance on insurance to establish. Some of the earlier risks seem to be in the process of mitigation. / There are still myriad obstacles, most notably very poor infrastructure, continued localised conflict, and the potential for the oil pipeline between South Sudan and Sudan to continue to be used as a political bargaining chip between the Governments, which heightens political tensions and impacts on economic and investor confidence. / 4.2 Assessment of the risk level / Annex: Risk Matrix / This was reviewed in the last Annual Review and suggested changes made. It is not clear whether those changes were accepted and formalised and immediate institutional memory has been lost on this due to changes of all key staff engaged on the programme in the summer of 2013 (the Food Security and Livelihoods Adviser, Economist and Team Leader for the Response, Resilience and Wealth Creation were all new in post during the summer of 2013) . Most of those suggested changes make sense so they have been retained here with a few additional amendments based on changes or progress in the last year. / Risk Suggested / Revised Probability Suggested Revised Impact Why? / 1. Global market conditions deter investment in South Sudan L Last AR recommended move to Medium. Agree this re-rating H MNCs and their financiers are cautious and look at country risk in a holistic way. South Sudan is not a “must have” country. / It seems that alternative strategies such as a regional processing presence with a light trading subsidiary is the favourite model. / However it can shift quickly for those believing in the “first mover advantage” thesis. / 2. Political situation in South Sudan deteriorates, and conditions for doing agribusiness in Africa worsen M H Use WB DoB progress (and donors) / Political situation has remained fraught over the last year with complete restructuring of GoSS. Political implications of this are uncertain / 3. Conditions for doing agribusiness in South Sudan worsen L tending to M H With improvements in the Business registration process in the last year and active engagement of SSBF in supporting that process, conditions are improving and as such the overall risk is decreasing / 4. Loss of credibility by AECF deters applicants from business for new competition L – keep low as blame remains subdued so far H AECF brand is strong through extensive marketing and PR efforts. Response from private sector to previous competitions has been immense. The AECF will market the new competition including calling on its extensive contact list/pipeline of potential business applicants / 5. Poor management by successful companies leads to poor results of AECF projects M – tending to H M Fund Manager’s due diligence of business proposals includes rigorous assessment of capacity of company to deliver initiative successfully. / Fund Manager’s M&E system combining grantee self-reporting validated by Fund Manager’s field sites, picks up difficulties at an early stage. / FM and AGRA as well as DFID are worried by the sheer week financial culture of grantees. First year’s progress indicates that this weakness is still inherent / 6. Business idea fails to be financially viable or have development impact anticipated M M Fund Manager and Investment Committee assessments of business proposals probes fully the feasibility of proposal achieving financial viability and achieving development impacts. / No worsening in terms of development impact potential. Too early to be sure of the business viability or the development impact. / 7. Fraud and misuse of funds by applicant L L – agree that this should be moved to M AGRA’s financial controls and accounting procedures are sufficient as are the Fund Manager’s. In addition, agreed sum to be set aside for more in-depth due diligence of certain investments and full investigative audits of 10% of the projects
Risk of funds not being used as intended / An assessment was made with the Fund Manager of corruption risk. / The following processes are underway and integral to the management process: / Due diligence exercises were carried out by the Fund Manager with all business partners but were described as ‘light touch’ and looked at 20 key questions around financial management, capacity and accounting systems. These included sample-based testing, bank reconciliations, HR processes and contracts. Checks were made on whether partners already had a functioning Board, whether Board meeting minutes were recorded and kept, whether they had an operational manual, and also whether they had their own fraud prevention systems and procedures. / Following this process if the FM assessed that further more detailed due diligence is required they would notify AGRA. However current funding does not accommodate the provision for further due diligence actions. / As AGRA is also USAID funded they have to satisfy US Government checks on bribery, corruption and anti-terrorism. / The Fund Manager also conducts on site visits to partners every 6 months to check financial records, the audit trail and to conduct sample testing of systems and processes and progress claims. / AGRA also has an internal audit unit which conducts sampling of 10 projects across the AECF African portfolio every 6 months. However if the South Sudan Window is tested it will only be for a small sample of the total window portfolio. If AGRA uncovers suspicion of fraud or corruption they will undertake more detailed investigations. / AGRA recommends transferring funds into a separate account in a local bank, rather than directly transferring to commercial partners. Release of funds is controlled by the fund manager from that account rather than directly from the fund manager to the partner. As an alternative to releasing funds after receipt of audited reports, AGRA recommends release by the FM to the partner once both have agreed and verified that milestone targets have been reached. This should reduce the time delay caused by the wait for an audit. / We can be satisfied that there are sufficiently robust and rigorous processes in place with the Fund manager and with the EM to protect the programme against corruption risk. However there is no option at the moment for the DFID South Sudan office to probe the performance of the Fund Manager and oversight should ideally occur at all levels. / 4.4 Climate and Environment Risk / The main risks related to this programme are from the environment rather than in terms of impacting on the environment. / The submission highlighted: / Vulnerability of agricultural production to climate change and promotion of practices that reduce environmental impact: / Agricultural productivity has already been impacted by early season drought this year. There is no evidence beyond farmer’s subjective assessments that this drought is part of a changing climatic pattern. Sparse meteorological records in South Sudan do not allow that kind of interpolation. Drought has been followed by flooding this year but again flooding in this region is not uncommon. Flooding impacts on access and infrastructure as was seen during the review period when road access between South Sudan and Uganda was disrupted due to flooding in the border regions. In visits to partners there were indications that this is being incorporated into production processes, for example through promoting grain varieties that had greater resilience to climate extremes, but this was not a strong feature of the production plan. South Sudan normally has a conducive climate for agriculture, although the experience of drought followed by flooding this year indicates that land preparation and land management needs to ensure that resilience to these extremes are built into the production process. / Promoting investments that enhance environmental sustainability and avoid adverse environmental impact / The programme will contribute to some moderate environmental impacts including increasing emissions from vehicles, from industry and from promoting more mechanised agricultural production and processing including greater use of energy water and agro-chemicals. / Potential infrastructure improvement to improve market access can have adverse environmental impacts. An increase in roads construction will inevitably lead to clearing of land for road construction and along road corridors. Increased road traffic will lead to an increase in greenhouse gas emissions from road vehicles, although in a global context the contribution of South Sudan to global GHG quantities will remain negligible for the foreseeable future. / New and improved roads, while contributing to opening up legitimate market access opportunities can also act as an increased opportunity for illegal and uncontrolled movement of wildlife and natural resources products within and out of the region including bush-meat, charcoal and tropical hardwoods. / South Sudan will for a long time remain a country at the mercy of the environment until the economy, the infrastructure and the society in general becomes robust and resilient enough to withstand environmental challenges. All interventions must be designed to withstand climatic extremes and to build resilience to them.

5. Value for Money
DFID measures value for money based upon the principles known as the three ‘E’s of Economy, Efficiency and Effectiveness. Using that as the first level of analysis: / Economy: / AGRA and KPMG have a global reputation as effective and professional development actors. The choice to select them in the overall roles of Executive Manager and Fund manager respectively remains the correct decision. / Efficiency: / There have been some doubts concerning the use of Farm Africa in supporting original applicants to complete applications at Concept note stage. In principle this was a sensible choice, and in practice the output delivered was of good quality. However the process may have over-sold weak partners to the selection board, as their weaknesses in preparing applications (and hence their potential organisational weakness) did not come through. It could also have resulted in selection bias as possibly stronger candidates were excluded in favour of weaker candidates who had received this external support. It did not create a level playing field. AGRA recommend contracting a specialist agency to provide structured and targeted support to weak enterprises, plus possibly seed capital. They also propose buying in specific technical assistance to cover areas like building accounting skills, as an alternative to longer term ‘hand holding’. / The assumptions underpinning AECF must also be challenged. These are that private sector partners must already be business-ready to qualify. This is erroneous in the case of South Sudan and severely limiting as the pool of business-ready partners is very small. A more efficient use of funds would accept that the special conditions of South Sudan should allow enough flexibility to support and mentor weak, but high potential partners through an initial stage of business growth providing business and financial management skills to develop their capacity until they are strong enough to operate fully independently. Simply giving funds to a range of weak enterprises and expecting them to sink or swim is not an efficient use of funding. Either the initial underpinning assumptions and procedures need to be accepted as non-negotiable (meaning in effect that there would be no South Sudan Window of AECF) or flexibility needs to be introduced to better support business development in a very weak and fragile economic and business environment. / An extended due diligence process for successful applicants while time consuming and responsible for delays in implementation was nevertheless necessary. The noted weaknesses of selected partners and their limited business track record to date made this a vital step in ensuring that selected partners met all fund requirements. / The recommendation to alter the funds transfer mechanism to transfer into a local account rather than directly from KPMG to the partner, should be carefully considered. / Effectiveness: / It is too early to judge effectiveness as the businesses have yet to prove the validity or viability of their business models. Effectiveness must be measured against jobs created, incomes and livelihoods (at household level) improved and ultimately the amount of business competition that this process creates by stimulating rival businesses to make similar investments because they have seen the value and commercial potential. This will be measurable in the latter stages of the programme only. / 5.2 Commercial Improvement and Value for Money / No additional comments / 5.3 Role of project partners / The relative roles and capacity of the EM and FM should be re-examined. The EM, AGRA has a team of two people who have overall oversight and management responsibility and for funds release. The Fund Manager(KPMG) has 60 people allocated to supporting this programme. There is hence a clear management imbalance between the EM and the FM and an impression of a tail wagging the dog. / AECF is working with AGRA to reform the EM and to improve alignment between the Board and the Managers. AGRA, while welcoming in principle the diversification of a General AECF into separate windows has noted though that this has made the whole management operation much more complex. AECF/AGRA would ideally prefer a return to a General Africa Window and recommend ring-fencing proposals from weaker countries to ensure that the capacity issues that need to be addressed in those countries are addressed separately and under special conditions. / The continuing inclusion of new donors also adds new layers of complexity to management and reporting. / 5.4 Does the project still represent Value for Money : Y / With qualification, so far, yes. / The qualification to this is that until the businesses start to produce tangible measurable returns we have no way of assessing the true value of the intervention. The deliverables define the value, in particular achievement of the milestone indicators; the number of jobs created, improvements in household income and livelihoods, levels of commercial investment, replication of business models. / The true ‘value’ of this programme is how many poor people will be lifted out of poverty through these ventures in particular and an improvement in the business climate in South Sudan in general. / Assessing value for money when the businesses are so new and have not yet reported their returns is premature. / However given that the original investment of £6M was designed to support 11 businesses and to date less than half of that number are being supported is a cause for concern. Although the unspent balance can potentially be reallocated, the initial design and selection process was based upon achieving what turned out to be a failed target, and will impact on a final vfm assessment. / The failure to reach the original intended target of 11 projects, is disappointing, but cannot as yet be regarded as a programme failure. The viability and success of the businesses supported will provide that judgement. It is disappointing that as of the review date only 5 businesses are being supported but those businesses also need to be given time to prove themselves. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Progress has still not matched original expectations. With only 5 grant contracts signed by the end of this review period this has fallen short of the more modest targets set a year ago which was to have 6 contracts finalised , businesses financed and operational. / Fears of the capacity of South Sudan business to be able to satisfy the implementation standards of AECF still remain. The management and operational capacity of business partners is low and there is a particular need to support and guide these businesses through the early stages of development. The context in South Sudan is radically different enough from the normal AECF environment to justify this. Although the Government of South Sudan is now more pro-actively engaging with the business community and creating a more amenable investment climate many barriers still remain and overcoming most barriers remains aspirational rather than actual. Issues of land ownership and tenure are unresolved and are critical to promoting agriculture and agri-business. / The Developmental impact remains uncertain. Jobs are being created, although some of them are being contracted out to labourers from surrounding countries, rather than South Sudanese. The businesses are too new and recently operational to provide any incentive for replication or scaling up. / Environmental and infrastructural challenges remain immense as proven by the impact of drought and flooding this year and the inability to keep roads open due to excessive rains. / The risk remains of the opportunities for employment being captured by the more market ready and the poor and the vulnerable being excluded by virtue of their poverty and vulnerability. / Partners and the Fund Managers are still lacking the basic data to allow us to measure success this year, particularly with regards to the development impact related to number of jobs created and livelihoods enhanced. This is due to those figures not yet being available at partner level. / However, 5 agri-businesses are now contracted, funding and operational. We do not yet have the figures to prove their success this year, and the only evidence given is anecdotal. KPMG did conduct a monitoring visit in October 2013 and are able to confirm that field operations have been underway this season, that crops were being harvested, that employment was being created and products for markets being sought. / AGRA/AECF made one plea that if every Annual Review continues to recommend major structural and procedural changes in the programme it creates problems rather than solves them. The recommendations therefore are fairly light touch, rather than deep and structural. / Remaining priorities for this year are: / To complete the final contract with Dryland Seeds, or failing that to exclude them from the process. Budgets and financial forecast will need to be rewritten to account for that reduction in partner numbers if the latter option is chosen. / Work with Frontier Microfinance to confirm additional co-financing to allow the release of the full grant, rather than the partial and conditional grant that has been released. / Collect harvest and production data from partners. Without that there is no basis upon which to measure success and achievements. Where partners are experiencing difficulties in collecting this data provide further support to enable this after determining the cause for the blockage. / DFID to make a decision on reallocation of the unallocated balance of funding. This can only follow steps one and two above related to finalising existing contracts and disbursements. At this stage the most relevant opportunity would appear to be through the AECF conflict window. / Consider AGRA proposal to change the funds transfer mechanism through a dedicated local bank account rather than by direct transfer to partners. / There is no present justification or sufficient evidence to consider the AECF SSW either a success or failure. It is simply too early to make that decision. Agricultural production success cannot be judged on one season alone, which may be affected by a wide range of external factors beyond the control of the farmer. This programme needs longer to become established and prove its workability. Another year should at least provide quantifiable evidence for production and for marketing which so far is impossible. / The viability of the businesses selected still remains to be proven, although the initial analysis selected ventures where the local demand for primary foods does exist and is substantially unmet. The opportunity to meet that market and the capacity of the businesses to achieve viable production and processing scale is still in the future. / With business and financial management skills being in such short supply in South Sudan and not being supported through the current AECF process it is recommended that: / AECF is prepared to be more flexible in supporting young inexperienced businesses though their earlier stages of development. The assumption that there would be sufficient market ready businesses was proven wrong in the selection process and still is evident as the businesses commence operations. Capacity building and support is needed for an extended period, not to cushion them against the hard realities of working in a competitive market environment, but to recognise the special conditions of South Sudan, and that there is no prior history of significant business development in the country. / Support is provided for external agencies (such as SPARK) that are providing skills training in these areas and/or for building the more formal institutions such as the University of Juba to develop faculty capacity in these areas.

8. Review Process
The review was performed by an Internal DFID Livelihoods Advisor based with the Food and Nutrition Security Team of Policy Division in East Kilbride with a good knowledge of DFID systems, and the South Sudan environment and context. The in-country DFID South Sudan Livelihoods Advisor accompanied the reviewer to the majority of meetings attended in South Sudan and Nairobi. / The time allocated to this review was one day of preparation in the UK prior to departure, three days in South Sudan and one and a half days in Nairobi. UK writing up time took an additional approximate 4 days of work. This was undertaken through the 10% process which is an internal DFID process that allows Advisors to do discreet pieces of work which are outside their main discipline and area of work in order to provide a service to other departments and country offices and as corporate learning opportunity. On reflection, the time available for an Advisor under their 10% time may be insufficient on its own, in terms of the time required to undertake a full Annual Review, which is a more lengthy and time demanding process. It seems such a process to be undertaken thoroughly requires roughly 3 weeks of staff time. / The review was prepared by brief meetings in the UK with the Africa Regional Department and background reading supplied from DFID Juba. The reviewer met a sample of actors in this field when in Juba (IFC, SSBF, Century Seeds in Yei, Honey Care Africa in Juba and South Farmers in Juba) and in Nairobi with AGRA ,KPMG and Farm Africa.