Type of Review: Annual Review

Project Title:	Low Carbon Support to the Ministry of Finance (203123)

Date started:	1 February 2013

Date review undertaken: 13-30 January 2014
## Introduction and Context

What support is the UK providing?
1. In May 2012, a business case was approved to provide technical assistance and capacity building to the Government of Indonesia to support it in its efforts to promote low carbon development and reduce the growth of emissions to meet its international targets. / 2. The assistance, called the Low Carbon Support (LCS) Programme, is focused on the Ministry of Finance. It has been designed to be highly responsive. It is established in the spirit of partnership between two G20 nations and it is intended that the programme should reflect the needs of the Government of Indonesia and the often changing political and institutional circumstances in the low carbon development sector in Indonesia. / 3. LCS started in February 2013 and will be completed by March 2015. Support is delivered through a £3.8m contract awarded through an open competition to a consortium of UK, Indonesian and international expertise, which is managed by Oxford Policy Management (OPML). The consultancy team mobilised on 4 March 2013 in Jakarta. The team are based in two parts of the Ministry, in the Centre for Climate Change Financing and Multilateral Policy of the Fiscal Policy Agency (hereafter PKPPIM) and the Indonesian Investment Agency (hereafter PIP). / 4. LCS followed a smaller earlier phase of UK support to the Ministry of Finance. Accordingly at the start of the project there was a good degree of clarity about the context and needs of the Ministry of Finance. This enabled the LCS team to embark immediately on an interim work plan aimed at addressing a range of tasks considered to be important and urgent by the Ministry.

What are the expected results?
5. The expected direct results of the programme are: / that Indonesia has a policy environment that is much more conducive to low carbon development compared to when the programme started, particularly in the energy sector; / that the government central budget is more directly promoting low carbon development, as evidenced by a greener budget strategy and visible changes in budget allocations towards low carbon development; and / increased allocation of resources (at least $200m) towards and development of pipelines of low carbon investments by the Indonesian Investment Authority in renewable energy and energy efficiency. / 6. Indirectly, supporting the Ministry of Finance with technical assistance, capacity building, outreach to wider stakeholders and communications will enable it to have built sufficient political and stakeholder support to enable it to take forward low carbon policy reform in Indonesia and be able to tackle some of the real barriers to moving to a low carbon pathway such as in energy subsidies and feed-in-tariffs for renewable energy. / 7. The review was prepared before the first logframe milestones become due. This annual review provides a best estimate of progress in advance of the 2014 milestones.

What is the context in which UK support is provided?
Importance of Climate Change / 8. Climate change is a global problem, but its impacts will be felt disproportionately by the world’s poorest people. HMG’s vision for low carbon development (LCD) is for all countries to adopt low carbon pathways that improve economic development and reduce poverty by avoiding or reducing emissions. / Indonesia’s significance and political commitment / 9. Indonesia is centrally important to the world's efforts to mitigating the impact of climate change. With estimated greenhouse gas emissions of 1.7Gt (billion tons) in 2005, Indonesia is recognised as being amongst the top ten emitters of CO2e. Its emissions, under a “Business as Usual” scenario are projected to grow to 2.95Gt CO2e by 2020. / 10. In a meeting of the United Nations Conference of the Parties (COP) 15 in Copenhagen, December 2009, the President of the Republic of Indonesia committed Indonesia to reducing emissions by 26% below business as usual projections by 2020 (or up to 41% with international assistance). / Huge challenge of moving to low carbon trajectory / 11. Emission reductions will only be politically and economically sustained if Indonesia is able to move onto a low carbon growth path, that generates employment, growth and poverty reduction. The dual achievement of low carbon growth and emission reduction targets will be a huge challenge. A major part of that challenge is the development of viable alternatives to “business as usual” carbon-intensive investment patterns that can genuinely provide prosperity and employment and are supported by Indonesian decision makers. / 12. Renewable energy will play a huge role in any future low carbon pathway. However, the current investment in real low-carbon sectors falls well short of the sums required to achieve national targets on emission reductions. / 13. The national target for renewables, currently contributing less than 3% to Indonesia’s current energy mix, is a 17% contribution to the national energy mix by 2025 with 5% of total energy from geothermal power. To put this figure into context, the Indonesian Ministry of Energy and Mineral Resources estimates that power generation requirements in the country will increase from around 36,000 MW in 2009 to as much as 187,000 MW in 2027 – a more than 5-fold increase. To meet the energy mix target, energy from renewables will need to increase from 1,080 MW in 2009 to 37,790 MW by 2027 a more than 36-fold increase. / Importance of working with the Ministry of Finance / 14. There is a strong body of evidence from around the world to show that fiscal policies can be both, the most effective driver (eg, via feed-in-tariffs) or the single biggest obstacle (eg, via fossil fuel subsidies) to low-carbon development. Unless Indonesia is able to design and implement a comprehensive and consistent approach to fiscal policy which directly prioritises low carbon development, the prospects for Indonesia being able to break-out of its future “business as usual” emission trajectory is very low. / 15. There is little doubt that responsibility for overall “climate change” policy is Indonesia is complicated and diffuse. A number of institutions have a role, including the Planning Ministry (BAPPENAS), National Council on Climate Change (DNPI) and Presidential Delivery Unit (UKP4), the Ministry of Forestry and the Ministry of Environment. The UK is also attempting to support Government of Indonesia (GoI) coordination on climate change through its on-going programme of support to BAPPENAS.

## Section A: Detailed Output Scoring

Output 1: High quality technical assistance to the Ministry of Finance.
Output 1 score and performance description: A+
OUTPUTS MODERATELY EXCEEDED EXPECTATION: / Progress against expected results / 16. This output aims to: / improve the technical basis upon which policies are formulated and generate policy recommendations that result in real policy change; and / improve the skills and knowledge of staff who are formulating and implementing policy so that by the end of the programme they are in a position to formulate future policy with less intensive donor support. / 17. The first year targets for this output are that it would have: / produced at least 4 major policy papers with recommendations by March 2014 to be considered by the Minister of Finance; and / deliver at least three capacity building initiatives to the Climate team in the Ministry of Finance (MoF) and relevant wider MoF departments by June 2014. / Actual results / 18. The project is meeting expectations and is on track to moderately exceed these. Three major policy recommendations have been completed so far: / Estimating emissions reductions from kerosene to gas program with a view to scaling the program to non-participating provinces (May 2013); / Policy advice and analysis for designing the energy efficiency revolving fund (June 2013); and / Policy assessment of scope for scaling up the bio-diesel industry (November 2013). / 19. Two further policy recommendations are expected to be completed before the first year target date of March 2014. They include: / Review of fiscal policy incentives for solar energy promotion (February 2014); / Development of policies for bio-mass / waste to energy credit scheme (February 2014); / 20. For the three completed studies, the following changes to regulations and budgets have been observed. / Policy Ministerial Sign-off Budget changes / Scaling up GoI Kerosene to Gas conversion programme The Minister for Finance wrote to Ministers of Bappenas, Environment and Energy in September 2013 requesting inclusion of further funds in RAN-GRK (national plan on mitigation and adaptation) for 2014 budget to allow expansion of the conversion program in non-participating regions, particularly including support to distribution of 3 kg LPG cylinders. RAN-GRK program allocations (DIPA - i.e. into the budget) for 2014 still being finalized by Bappenas and line Ministries but likely to include significant growth in provisions to support conversion to LPG through cylinder distribution. / Energy efficiency revolving fund Following a Nota Dinas from PKPPIM to the Minister of Finance, it was agreed to: (i) allocate IDR 500 billion (£25m) in the Fund in the 2014 Budget; (ii) to undertake work on a Ministerial Regulation further defining procedures of the Fund to be managed by PIP. / The LCS Team is currently supporting MoF on this regulation. Will be more formally allocated its own budget line of RP 500 billion in mid-term budget review (May / June 2014) following completion and execution of the Ministerial Regulation. / Scaling up of bio-diesel Package of technical reforms announced in the Government’s economic statement of September 2013 to increase minimum levels of bio-diesel in diesel to 10% in 2014 and 30% by 2025 (for bio-ethanol from 0.5% to 20% over the same period). Further economic / fiscal reforms are likely to be targeted at domestic / international market arrangements for supply of raw materials for bio-fuel and not to budget expenditures / incentives as such. Comparative study to Singapore currently being arranged to review relevant trade, market and industry policies. / 21. Under this output, a number of strategic think-pieces and internal/process focused studies have also been undertaken. These include: / Institutional analysis for informing policy development (July 2013) / Policy options and recommendations for PKPPIM work priorities (July 2013) / 22. These studies do not make a direct contribution to policy change, but are vital for the Ministry of Finance to position itself internally and across government in terms of focusing on priority issues that will support future policy change. Three further studies that are scheduled to be completed by the target date for year 1 that will also support policy work are: / Strategy paper for promoting green planning and budgeting (March 2014); / Strategy paper for coherent renewable energy policies (March 2014); / Strategy paper for coherent energy efficiency policies (March 2014). / 23. The target for year 1 on capacity building was to deliver at least 3 technical low carbon training events by June 2014. In preparation for delivering support – the LCS team has undertaken a training needs analysis to identify skill gaps and areas that are necessary for development. / 24. LCS has already met and exceeded this target and is well on track to deliver the end of project targets in this area. Capacity building conducted to date is as follows: / 1. Cost benefit analysis for climate change, phase 1 by University of Indonesia (October 2013) – 24 Ministry of Finance / PIP participants over 3 days ; / 2. Cost benefit analysis for climate change, phase 2 by University of Indonesia (November 2013) – 30 Ministry of Finance/ PIP participants over 3 days; / 3. Introduction to Low Carbon, Green Planning and Budgeting and Sustainable Development (December 2013) – 25 Ministry of Finance / PIP participants over 2 days / 25. Ten staff from the Ministry of Finance and PIP have been supported to attend external training courses, relevant conferences and study trips. Thirty ministry staff have also been on a two-part tailor-made course on cost benefit analysis and climate change. This training has equipped staff with skills and knowledge to present evidence-based policy options to Ministers. A training evaluation exercise will be undertaken by LCS/UKCCU in April 2014 to determine what type of training is the most effective and use this evaluation to inform training plans for the remainder of the project. / Recommendations: / A key task for the project in its second year will be to ensure that the high quality advice and support being provided by the LCS consultants are used to produce actual changes to regulations, demonstrable reallocations of the budget towards supporting low carbon development and fiscal policies that support the Government’s own emissions reduction targets. / Given (i) the limited absorptive capacities of the two principal counterpart institutions of PKPPIM and PIP; (ii) limited time available to implement policies developed especially bearing in mind that 2014 is an election year; and (iii) high administrative and policy work-loads within LCS itself; with the exception of urgent short-term support, no new major policy studies should be added to the already detailed project work-plan following the January Working Committee. / All major policy studies should be timed to be completed by no later than the end of December 2014. Allowing the period between January 2015 and March 2015 (end of the project) to finalise follow-up actions associated with them. / Impact Weighting (%): 35% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N / Key policy achievement - energy efficiency revolving fund / LCS supported the Ministry of Finance by undertaking detailed policy analysis, using evidence from over 500 energy audits, to design a scheme for promoting energy efficiency in SMEs. Rupiah 500 billion (£25m) is expected to be included in the 2014 Budget revision in April 2014 for this. / The initial idea for the fund came from the Ministry of Energy (Directorate of Energy Conservation). PIP was given a new mandate to start work on energy efficiency through the revolving fund. PIP has advertised that it is opening a line of finance for energy efficiency. KfW and AFD may well also add funds and be involved in the implementation. / LCS is working on the final details of the revolving fund, including looking at a guarantee scheme option and on the ministerial regulation to confirm the funding and operation.

Output 2:.
Output 2 score and performance description: A+ / OUTPUTS MODERATELY EXCEEDED EXPECTATION: / Progress against expected results / 26. This output aims to: / Encourage and support the Ministry of Finance to consult with wider stakeholders to ensure that policies gain support and insights from other key sources (wider government, academia, private sector, Parliament, NGOs, etc). / 27. The first year targets for this output are that it would have helped PKPPIM and PIP to have: / undertaken at least two formal outreach events; and / issued at least two low carbon development publications. / Actual results / 28. The communication and outreach output was initially to have been a formal programme designed by one of the consortium partners in the first few months of the project and then implemented throughout. In practice, the project has approached the communication and outreach output in a less structured, albeit successful way. Communications and outreach have been embedded in relevant activities rather than being driven by an over-arching communications strategy. / 29. This less formal approach has delivered the required outreach, indeed in the last year PKPPIM and PIP have undertaken extensive outreach as part of delivering their work-programmes. A selected listing of outreach events (and dates) is as follows: / • Broad consultations / focus group discussions for institutional review study (July 13); / • LCS program launch event (July 2013); / • Donor partner mapping and coordination event (October 2013); / • Formation and initial workshop of inter-ministerial working group to work on green budgeting and planning (December 2013); / • Stakeholder consultations / focus group discussions on policies for solar (October 13). / • Broad consultations and 2 focus group discussions on bio-mass / waste to energy study (October – January 2014); / • Broad consultations and 2 focus group discussions on bio-diesel fuel study (November / December 2013); / • Support to PKPPIM National Seminar event (October 2013); / • PIP workshop on hydro / energy efficiency financing (Sept. 13); / • Various PIP consultations / Focus Group Discussions (FGDs) with regional governments on energy efficiency financing (October 2013 to January 2014); / • PIP comparative / networking study to Australia (December 2013). / 30. To ensure focus and structure for the remainder of the programme, the Steering Committee will shortly consider approval of a communications strategy – this strategy will not only focus on outreach associated with technical policy – but also on capacity building for PKPPIM and PIP in communications. This is essential to ensure that when outreach is conducted that the Ministry of Finance is able to do this in a professional and effective way. / Recommendations: / Maintain the approach of including communication requirements in each piece of work. / Ensure that capacity building on communication skills is done as early as possible in 2014 to ensure it can be helpful for the project in its second year of implementation. / Ensure that the proposed longer-term communications support (currently being recruited by the LCS team) covers both PKPPIM and PIP requirements. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Low carbon investment objectives fully incorporated into the operations of the Indonesia Investment Authority (PIP).
Output 3 score and performance description: A+ / OUTPUTS MODERATELY EXCEEDED EXPECTATION: / Progress against expected results / 31. This output aims to: / Develop Standard Operating Procedures (SOP) for PIP to support low carbon investments (in renewable energy and energy efficiency). / Support PIP’s institutional reform and capacity building programme with a particular emphasis upon being able to finance renewable energy investments. / 32. The first year targets for this output are that it would have: / elaborated and finalised the SOP for the mini-hydro sector by June 2014; and / supported a legal and institutional review and made recommendations that were approved by PIP by December 2013. / 33. The ultimate goal of this programme’s support to PIP is to enable it to be ready and able to disperse finance for low carbon investments. This requires budget allocations, PIP’s mandate being approved to lend for low carbon and for it as an institution to have the capacity to build pipelines and then ultimately finance the resulting projects. / Actual results / 34.The LCS project has invested considerable effort and expertise to work with PIP on a first SOP for mini-hydro. An initial version of the SOP has been extensively tested on a real project (Cicatih) and it is now in the process of being revised for wider applicability. It is on track to be ready for the target deadline of June 2014. It had been hoped that the Cicatih mini-hydro project would, after testing with the SOPs be ready for financing. This is still not the case and PIP needs to consider further whether this particular project is suitable to be the first mini-hydro project supported by PIP. / 35. Plans are well underway to support PIP directly and in coordination with other donors to develop other manuals / SOPs during 2014 on: / geothermal, / energy efficiency; / bio-mass; and / waste. / 36. It is expected that these manuals will closely follow existing manuals / SOPs for Provincial Government and Independent Power Producers financing to ensure that they can be used in a practical way. / 37. In advance of these manuals being produced, the Government of Indonesia has already announced allocations to : / a Geothermal Fund in PIP that now total IDR 3.1 trillion (£154.2 million) at January 2014) / IDR 500 bn (£25m) in the 2014 Budget for the energy efficiency revolving fund. / 38. The LCS team deployed a range of international and domestic consultancy support to assist PIP with its strategic review. Legal and institutional review studies were completed in September 2013. These have been accepted by PIP. PIP is using the reviews in its on-going discussions with the Ministry of Finance on its future institutional arrangements. / 39. We expect decisions on the future of PIP to be finalised in the first quarter of 2014. LCS consultants will be invited to support PIP in presenting findings and options to the Supervisory Board of the Ministry of Finance as well as a broader audience of senior ministry officials. The projects has provided support so that PIP now has high quality legal advice: / in relation to “no loss” provisions in the PIP regulatory framework; and / the legal scope for PIP to undertake equity investments. / 40. It is clear that the project has been invaluable to PIP as it prepares itself for its future institutional status and role in Indonesia. That future will require continuing support under the LCS programme as it can be expected that further follow up legal work in the following areas will be required: / regulatory clarifications under existing BLU status (a BLU is an arm’s length agency of the Ministry of Finance) – no losses, mandatory provisions, SOPs etc.; / formation of a subsidiary PT Company to give focus to green financing initiatives; and / longer term restructuring to a full State-owned Enterprise (PT Persero status).
Recommendations: / The continuing priority is to support PIP to operationalise the budget allocations that it has been allocated for geothermal and for energy efficiency. Particular barriers to overcome will be the mandate and ability of PIP to take on more risk and to have the managerial capacity to finance projects for which it has limited technical knowledge. The practical solution that is most likely to emerge would be for PIP to co-finance with agencies that are better placed to appraise technical projects (eg KfW, AFD, etc). / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.
1. Progress and results
1.1 Has the logframe been updated since last review? Yes / Output level / 41. After the first five months of implementation and following the finalisation of work programmes for PKPPIM and PIP, the indicators and targets at output level were updated in July 2013. These now better reflect the detailed workplan of the project and have improved upon those used at the design stage. / Impact level / 42. During the annual review, PKPPIM asked for the Impact level milestones to be revised to better reflect the wider political situation on fuel subsidies. 2014 is an election year and officials have said that they do not expect there to be any movement on fuel subsidies until 2015. The request was to make the following changes: / LCS Programme Logical Framework / Impact - Low carbon development is shown to be viable and able to deliver results. / Indicator - Energy pricing and feed-in tariffs supportive of low carbon investment / Baseline – Energy/fuel subsidies running at $27 bn per year (2011). / Milestone 1 (December 2014) - Subsidies as a percentage of government expenditure reduced by 10% (change to 6%). / Milestone 2 (March 2015) Subsidies as a percentage of government expenditure reduced by 15% (change to 8%). / 43. These are reasonable changes – since they better reflect the current political and economic situation (the Rupiah has fallen 30% since May 2013, so the Rupiah cost of imported fuel is much higher than it was and so achieving the original milestones will be virtually impossible). / 44. It is recommended that these changes are made following the sign-off of this Annual Review. / 1.2 Overall Output Score and Description: A+ / 45. The overall score is moderately exceeding expectations. / 46. Both PKPPIM and PIP have engaged in a very constructive partnership with the programme. Resources have been used in an effective way. The governance of the programme, which involves a monthly working committee meeting and a quarterly steering committee meeting, is working very well. Decisions are made by consensus which ensures that there is buy-in and agreement on priorities. / 47. The scale of policy-related work has been impressive as has been the willingness of PKPPIM and PIP to embrace communication and outreach. There are clear work-plans in place for both agencies until the end of the project. / 1.3 Direct feedback from beneficiaries / 48. Both PKPPIM and PIP are pleased with the LCS Team and the delivery of the programme. The flexibility and responsiveness of the programme to meet evolving and changing needs has been a key feature of its success so far. IN the preparation of this review, one to one meetings with the Head of PKPPIM and PIP were undertaken. / 49. A large number of consultants have been used. All of the work produced has been regarded as high quality, with the exception of two deliverables: / the work to support PIP in the application of Standard Operating Procedures in relation to a mini-hydro project in Cicatih has been subject to a number of delays. PIP has expressed dissatisfaction with several aspects of the work by the consultants. The LCS team are working with PIP and the consultants to resolve the issue and move forward with the project; and / the first communications and stakeholder outreach strategy report was rejected by PKPPIM and PIP. The report was rejected because it did not address the issues of importance to PKPPIM/PIP/LCS, was not aligned with the available resources and therefore was considered to be unworkable in an Indonesia setting. The report was rapidly revised using other expertise to produce a strategy that was then acceptable. / 50. The project has been very successful at securing Indonesian expertise – this has certain advantages – not least that it allows follow-on support over time. This is important as the policy formulation process often takes time, involving many stages of review and by different parts of the government. It is likely that the preference for Indonesian consultants will continue into the final year. / 51. The Ministry is aware that the project is due to end in March 2015. With elections in Indonesia that will produce a new Parliament and President (by the latest in September 2014). It was agreed that discussions on extending end dates or potential future UK support should take place in September 2014. / 1.4 Summary of overall progress / 52. The programme is well on track to meeting its Outputs. Spend is on target and management arrangements are working well. / 1.5 Key challenges / 53. The following are key challenges for the remainder of the project: / Staffing / 54. The LCS team is now firmly established within the Ministry of Finance, occupying space in both agencies. There is a very large volume of work to be managed. Additional long-term junior project staff were agreed as it was clear that more support was needed. Whilst the LCS team have requested further long-team support, this has been rejected by the UKCCU as the budget for project management is already at its limit. To address the work-load, it will be important for the LCS team to: / to spread more evenly the remaining tasks in the programme. A more measured pace of implementation of the current large number of activities would reduce current workloads; / stay focused on the agreed work-programme and not agree to take on additional commitments (unless they are short-term (no more than 5 days) and urgent); / if longer-term unplanned work is requested, these new tasks must only be undertaken if some existing planned work is dropped from the work plan; and / confine major written programme reporting requirements to quarterly reports and largely reserving reporting for monthly Working Committee meetings to decision making matters and “exception reporting”. / Deliverables / 55. Providing policy support to enable the Ministry of Finance to deliver on its own low carbon targets will remain central to the coming year. / 56. It will be important to really focus support in areas where the project can deliver real change (eg new ministerial regulations, new budget allocations, new planning processes) so by the end of the project there are tangible outcomes that can be measured. / 57. The LCS team should ensure that it regularly assesses that there is traction in the areas where the project is working and that there will be real change resulting from the work. If the prospects for any particular piece of work having a real impact look to diminish, then the LCS team should advise the Working Committee and a decision on the future effort into that work should be determined. / 58. At times it will be necessary to turn-down work requested by the Ministry of Finance to ensure that the above focus can be maintained. / 1.6 Annual Outcome Assessment / 59. The outcome of the programme is that there is: / A supportive environment for low carbon investment established in Indonesia. / 60. Measured by: / New low carbon incentives & regulations introduced and implemented. / Funds available in PIP for low carbon investment / 61. There are no milestones in the logical framework for the Outcome level to be delivered by January 2014. However we have noted that to date the following new incentives and regulations are well underway to being finalised: / Ministerial Regulation on the Energy Efficiency Revolving Fund; / Ministerial Regulation on Credit Subsidy scheme for bio-mass / waste to energy; / additional incentives funding in 2014 RAN-GRK budget for conversion of kerosene to LPG. / 62. Also, to date the following new funds are now available in PIP for low carbon investment: / IDR 3.1 trillion (£154.2 million) available as at January 2014 for investment in geothermal. It should be noted that this amount already exceeds the final milestone of $200m additional public finance for low carbon investment for the entire programme. / A further IDR 0.5 trillion (£25m) is expected by mid-2014 with the formal start-up of the Energy Efficiency Revolving Fund. / 63. Finally it is worth noting that the following initiatives are well under way and will form a core of the work of the programme in 2014: / PKPPIM strategy paper for medium term green development planning and financing (including private sector framework) / Support to developing policy priorities and a Financing Strategy for RAN-GRK 2015 -2020 / Contributions to Government Work Plans; Budgets; President’s budget speeches; and Nota Keuangan (principally for the 2015 budget) / Contributions to greening the 2015 – 2020 Five Year Plan (RPJMN) and to developing higher level targets and indicators for the 2015 budget, including inter-governmental financing. / Study on Fiscal Policy Framework on land based sector. The objective of the study is to develop a strong medium term fiscal policy framework on the land based sector. / 64. Given this progress at the Outcome level and the overall performance at the Output Level (see above, we conclude that the project is on track at the Outcome level and delivering as expected. / 65. Wider uncertainty on the economy, the government budget and upcoming elections, means that the hoped for impact has some uncertainty. However, the Finance Minister is very clear that low carbon development provides a range of potential solutions to the current economic difficulties. The future security flowing from diversified energy sources, the potential to offset imports with bio-diesel, and the benefits of reducing demand for vehicles and fuel are well understood and will directly contribute to lower government expenditure on energy subsidies. In the event that government policies and commitments change dramatically, then all partners will review whether the programme should continue implementation. Clarity on future commitments and policies to climate change under the new government should emerge by October 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes. / 66. According to projections as of end December 2013, the project is expected to meet forecasts. / 67. There is a requirement to shift resources from the component covering the special fund to the short-term consultancy budget to allow consultancy-related expenditures on outreach and communication to be properly recorded under the special fund output. The purpose of the special fund is to largely fund the communication and outreach elements of the project. As a first step, it is recommended that all activities related to green planning and budgeting be recorded under the Special Fund. Further steps, if necessary, can be determined later in the year. / 2.2 Key cost drivers / 68. The key cost drivers are the technical consultancy inputs. These form the vast majority of programme expenditure. / 69. These costs have been contained by agreeing fee rates at the start of the programme and fixing these for the duration (two years) of the project. Any work that has to be delivered outside of the OPML-led consortium, is always subject to competitive tender, requiring at least three bids. Records of these tenders and their evaluations are kept by the OPML local and UK office. / 70. In terms of other costs, at least three quotes are obtained for all asset purchased under the project to ensure that costs are minimised. / 2.3 Is the project on-track against original timescale: Y / 71. The project is on track to deliver on the current timescale.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / 72. The broad evidence base that supported the rationale of the project has not changed. / Starting point / Low carbon development is not happening quickly enough in Indonesia because the policies that would encourage this to happen are either not in place or if they are in place, they are weak and do not create strong enough incentives. / In the climate change arena, Indonesia, not unlike a lot of countries, has confused and conflicting mandates for different institutions.[1] / The Ministry of Finance is by far and away the most important ministry in setting the framework and incentives for low carbon development which other actors then respond to. / But the Ministry of Finance lacks the capacity and resources to push through policy reforms. In particular it needs to be much more networked with outside stakeholders, it needs to use more evidence and it needs to build support for its policies across other ministries and with parliament. / Change needed / More evidence, more outreach, more input from external experts would enable the Ministry of Finance to identify and develop economic and fiscal strategies to reduce emissions and promote a more efficient use of Indonesia’s resources for sustainable development. / For any policy change to be successful it needs to be properly researched and have a solid evidence base. / Wider stakeholders (other ministries, think-tanks, politicians) need to be involved in policy formulation from the start, for this to happen the Ministry of Finance needs to open-up its policy making process more than it has traditionally done. / Policy needs to be disseminated properly to other ministries and agencies, it needs champions and supporters outside government. / Policy, especially when it is in very sensitive areas, needs to have very strong ministry ownership. / Communication needs to be improved so that wide support can be gained. / 73. However, the context in which investment decisions are being made have changed. The devaluation of the currency (down by 30% since May 2013) and a worsening macro-economic environment have all increased risk levels for investment in Indonesia, particularly for foreign investors. These conditions have also increased the cost of investment for the Government of Indonesia and domestic investors, particularly when foreign currency based loan and imported materials are used. PKPPIM has been actively responding to this situation by looking at policies and packages that can drive down the import of fuel and promote energy efficiency (to reduce the fuel subsidy and improve the trade balance). The LCS team have been very active in helping PKPPIM to respond. / 3.2 Where an evaluation is planned what progress has been made? / 74. No evaluation is planned. The UKCCU is considering an independent review in September 2014.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / 75. The overall risk level assigned to the Business Case was medium. This has not changed. / 76. The assessment of risk at the Outcome level is medium. The risks at this level are: that MoF is unable to gain cross government support for new regulations and Parliament does not agree to any new laws or regulations proposed by the Ministry of Finance. The programme is addressing these risks by helping to transform the approach to consultation: / A large number of cross Ministry of Finance meetings have taken place, enabling the PKPPIM to build strong links with for example, DG Budget and DG Treasury . These links are essential for building support to the fiscal policies that will drive low carbon development. / PKPPIM and PIP have undertaken a number of focus group discussions with other government agencies and the private sector. Whilst more is needed, the first year has shown the growing commitment to the Ministry to engaging with wider stakeholders. / In 2013, a major green growth conference was held – the target audience for this was the Government of Indonesia. / 77. And by: / Working very closely with the Heads of PKPPIM and PIP and with Finance Ministers – preparing speeches, briefings, and draft regulations to ensure that there is political buy-in from the Parliament. / 78. These risks have not gone away and the programme will need to continue supporting efforts to address these for the remainder of the programme. / 79. The assessment of risk at the Output level is also medium. The risks identified in the Business Case were that: / MoF does not engage fully with the LCS Team and it is unable to quickly establish its reputation with policy makers in MoF. / PIP is not committed to working on low carbon development and it fails to introduce institutional changes to enable it to develop a pipeline of projects and disperse finance. / 80. The LCS team has done an excellent job of establishing its credibility with the Ministry. There is now little risk that the LCS Team is not seen as valuable and supportive. In terms of PIP’s commitment and ability to support low carbon - essential changes to PIP’s mandate are still under discussion, so the risk that it may not be able to develop a pipeline and disperse finance remains. / Risk of funds not being used as intended / 81. Funds for the programme are managed in the UK and locally by the LCS Team. The governance structure of the programme allows for UK approval of all contracts that are let. The LCS team always obtains three quotes or more for all asset expenditure over £100. Records and documents are maintained on all contracting. There is low risk of funds being misused. / 82. There will be an independent audit of the programmes accounts in the first quarter of 2014.
4.4 Climate and Environment Risk / 83. There are no direct or indirect risks to Climate and the Environment from this policy-based programme.

5. Value for Money
5.1 Performance on VfM measures / 84. The key indicator for measuring value for money is the additional finance that the programme secures for deployment into low carbon development - principally the level of public finance that is newly allocated as a result of the LCS Programme. This indicator also contributes to the overall indicator for the UKCCU and for the International Climate Fund. The target leverage for this programme is $200m of new public finance by the end of the project / 5.2 Commercial Improvement and Value for Money / 85. The business case was subjected to open competition. The result of the procurement was that the deliverables for the programme were secured at a cost below the value of the business case (at £3.8m). As part of this procurement, key cost drivers such as fee rates have been fixed for the entire duration. / 86. All fees for short-term consultants are subjected to benchmarking by the UKCCU throughout the programme, with negotiations seeking to ensure that all rates are competitive. / 87. If consultancy support is required that goes beyond the expertise of the original consultants in the consortium, at least three bids are obtained to deliver this work when it is over £25,000. For contracts under £25,000, any fees are benchmarked against the market and the fees agreed for equivalent expertise in the consortium. / 88. International consultants are used sparingly to ensure that resources can secure the maximum amount of consulting days. / 89. The project introduced written guidance on project funds being used for travel, subsistence, hotels, venue hire, etc. All these are clearly written to minimise costs and avoid any extravagant expenditure. These guidelines have been strictly adhered to so far in project implementation. / 5.3 Role of project partners / 90. The Deputy Heads of PKPPIM and PIP are very active in the programme and sit as members of the Working Committee and lead advisers to their respective Heads on the Steering Committee. There are excellent personal relationships which allow for very effective management and oversight of all project activities. / 91. A Working Committee (comprising the Deputy Heads of PKPPIM, PIP and UKCCU) meets every month to review programme progress and to approve future work. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions / 92. There are no formal conditions attached to this project. / 93. As part of the partnership the Ministry of Finance has provided excellent office space in both PKPPIM and PIP to enable the LCS Team to fully integrate with government officials. This arrangement is working very well.

7. Conclusions and actions
94. The LCS Team has worked really well to build relationships with Government of Indonesia officials and add considerable value in terms of short and long-term policy development, ministry outreach and capacity development. The team sits within the Ministry of Finance, providing direct access to project beneficiaries. Extensive work across all outputs have helped keep the project on track, with the result that all outputs are moderately above expectations. The budget is on track and at this stage. Outputs are expected to be delivered on time. / 95. Elections in April and July mean that the UK should review the project again in September 2014. This would allow a determination of continuing commitment by the Government of Indonesia as well as an opportunity to review the project budget and timelines for the key deliverables being developed for the project. / 96. The key recommendations arising from the Annual Review are: / Focus on areas most likely to produce actual changes to regulations, demonstrable reallocations of the budget towards supporting low carbon development and fiscal policies that support the Government’s own emissions reduction targets. / Given (i) the limited absorptive capacities of the two principal counterpart institutions of PKPPIM and PIP; (ii) limited time available to implement policies developed especially bearing in mind that 2014 is an election year; and (iii) high administrative and policy work-loads within LCS itself; with the exception of urgent short-term support, no new major policy studies should be added to the already detailed project work-plan following the January Working Committee. / Maintain the approach of including communication requirements in each piece of work. / Ensure that capacity building on communication skills is done as early as possible in 2014 to ensure it can be helpful for the project in its second year of implementation. / Ensure that the proposed longer-term communications support (currently being recruited by the LCS team) covers both PKPPIM and PIP requirements. / The continuing priority is to support PIP to operationalise the budget allocations that it has been allocated for geothermal and for energy efficiency.

8. Review Process
97. This review was undertaken by Mark George, Deputy Head of the UKCCU and Lead Adviser on the LCS Programme. The review process undertaken was as follows: / 1. Review of project documentation, partnership agreement, outputs and progress reports / 2. Interview with PKPPIM, PIP and the LCS Team (January 2014).