Annual Review – Summary Sheet (2018)

Title: Investments in Forests and Sustainable Land Use
Programme Value £: £93.5m (plus £19.4m funding from the Department of Business, Energy and Industrial Strategy)		Review Date: 09/12/2018
Programme Code: GB-1-202745	Start Date: 09/12/2014	End Date: 09/12/2023

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020	2021	2022	2023
Score	A	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business case
DevTracker Link to Log frame:	Log frame

A. Summary and Overview

Description of programme
Conversion of forests to grow a small number of agricultural commodities, including palm oil, soya, beef, cocoa and coffee, accounts for over 70% of tropical deforestation in recent years. This contributes to global greenhouse gas emissions and environmental degradation, with negative impacts on large numbers of poor rural communities and indigenous peoples.

Over 470 businesses have made voluntary commitments to reduce or eliminate deforestation from their supply chains for these commodities. This provides an important opportunity for transformational change, but realising these commitments in practice is challenging.

While companies can have a significant impact through changing their purchasing and growing policies, lasting change also requires governments to enact policy and regulatory reforms and enforce laws. Support and finance is needed to help millions of smallholder farmers, who account for a significant share of total global production, change their practices. Efforts are also needed to encourage major emerging markets for commodities to adopt a greater focus on sustainability.

Investments in Forests and Sustainable Land Use (IFSLU) was established to accelerate the opportunity presented by these commitments. It contributes to a new vision for sustainable land use through developing sustainable business models, which support development, promote growth and livelihoods, and protect forests.

The programme is delivered through two complementary interventions:
- The Tropical Forest Alliance (TFA) (£4m), which mobilises action by industry, governments and civil society to tackle deforestation caused by agricultural commodities.
- Partnerships for Forests (P4F) (£56.5m), which supports public-private partnerships, providing support to develop new sustainable business models, which support development, jobs and livelihoods, without causing deforestation.

DFID confirmed an extension of three years and £33.5m to IFSLU in September 2018, extending operations to 2023. Operations of Partnerships for Forests commenced in Latin America (Brazil and Colombia) in 2018, with funding from the Department of Business, Energy and Industrial Strategy (BEIS), building on operations in Southeast Asia, East Africa, West and Central Africa funded by DFID.

Summary supporting narrative for the overall score in this review
All quantitative targets in the logical framework have been met or exceeded and results have been achieved in all output areas. Progress has also been made against the outcome-level key performance indicators ahead of schedule, providing the basis for a 2018 annual review score of A+.

Support to the secretariat of the Tropical Forest Alliance has played an important role in building an international community for action of over 150 governments, companies and civil society organisations working together to address deforestation associated with agricultural commodities. Partnerships for Forests has established partnerships at all levels of supply chains for palm oil, cocoa and rubber, with potential to support a shift towards more sustainable forms of production over the lifetime of the programme.

These partnerships cover: (i) demand (sustainable sourcing commitments by governments, encompassing approximately 75% of the European market for these commodities); (ii) enabling conditions (new industry sustainability standards, policy reform and regulation in producer countries); and (iii) public-private partnerships with companies to develop and test new and sustainable ways of doing business without causing deforestation. Figure 1 illustrates how this applies in the cocoa sector.

Figure 1: Cocoa supply chain partnerships

Partnerships for Forests has also achieved the first results against outcome level key performance indicators, mobilising private sector investment of £68.4m and bringing 88,000 hectares (ha) of land under improved management (see Output 3 below). This helps to provide proof-of-concept for the programme approach, demonstrating that grant funding and technical assistance can be used to increased private investment in businesses based on more sustainable land use practices.

Recommendations for the year ahead
Accelerate programme delivery and work to identify strategic opportunities to demonstrate impact to key audiences (DFID, BEIS and P4F programme team).

Increase focus on learning, collaboration and leadership outputs, as the programme shifts from building a portfolio to delivering results (DFID, BEIS and P4F programme team).

Develop an ambitious strategy to scale-up and increase impact through programme extension period (DFID, BEIS and P4F programme team).

Increase efforts to align other donors and agencies around the public-private partnership approach pioneered through IFSLU (DFID, BEIS and P4F programme team).

## B: DETAILED OUTPUT SCORING

Output Title	Demand-side measures: An enhanced market for sustainably sourced products through public and private commitments to sustainable sourcing
Output number per LF		1	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 number of cases where P4F has supported policy change and development, at public (sub-national, national or international) or multi-corporate level, that enhance forests and sustainable land use investment.	1 case by 2018 / 2 cases by 2019 / 4 cases by 2020	On target: 1 case in 2018 / (Amsterdam Declarations Partnership).
1.2 number of cases where P4F has supported policy change and development at the individual corporate level that enhances forests and sustainable land use investment.	1 case by 2018 / 4 cases by 2019 / 7 cases by 2020	On target: 1 case in 2018 / (Touton cocoa sourcing).

Key points
This output is focused on building stronger markets for sustainably produced commodities. A relatively modest share of the programme budget is attached to this output (£2m), reflecting the fact that funds are used in ways that catalyse effort by others (such as companies implementing sustainable sourcing policies, governments implementing sustainable procurement policies), and build wider coalitions for change. Milestones are based on case studies which describe the support provided and present evidence describing the role of the programme in securing the result achieved.

The Tropical Forest Alliance has undertaken analytical work on emerging markets for deforestation-linked commodities, identifying that major emerging market importers (China and India) and major emerging market producer-consumers (Brazil and Indonesia) together account for around 40% of global demand for soya, beef, palm oil and wood products, with their share is set to rise further by 2025.

A workshop held in Beijing in May 2018 identified anecdotal evidence suggesting that governments, consumers and producers in emerging markets are increasingly interested in sustainably sourced products, but barriers such as the cost of complying with sustainability standards, higher cost of sustainable products, and challenges associated with standards, traceability and compliance are preventing wider uptake. Further work to build on this analysis is now being considered.

The UK 25-Year Environment Action Plan, published in January 2018, has set out an ambition to reduce deforestation caused by the UK’s imports of agricultural commodities. The plan sets out a commitment to establish a Global Resource Initiative (GRI) to “work with businesses, NGOs, producer countries and intermediary countries, to identify actions across supply chains that will improve the sustainability of products and reduce deforestation”.

Partnerships for Forests provided technical and logistical support to consult on the GRI with key UK stakeholders and prepare and convene a high-level meeting during Green Great Britain Week in October, attended by ministers from the Department for Business, Energy and Industrial Strategy (BEIS), the Department for Environment, Food and Rural Affairs (Defra) and DFID. Further support is anticipated in the year ahead, focused initially on establishing a task force to advise on the scope of the initiative.

Indicator 1.1
The Amsterdam Declarations Partnership (ADP) builds collaboration between governments in support of strengthened demand for sustainable agricultural commodities. Current members are the UK, Netherlands, Germany, Norway, Denmark, France and Italy. Engagement with the Amsterdam Declarations Partnership by officials in DFID, BEIS and Defra, along with support provided for the ADP secretariat through Partnerships for Forests, has helped to ensure effective cooperation on policy between the seven signatory countries. This included a joint intervention at the Environment Council in March, led by France in its capacity as ADP chair from January – June 2018, helping to build the case for action at a European-level to address the impact of agricultural commodity imports on deforestation.

Countries in the Amsterdam Declarations Partnership also continue to promote cooperation around national sustainable sourcing initiatives, seeking opportunities to raise ambition and align on targets, standards and reporting. In this context, Denmark hosted a meeting of European sustainable soya sourcing initiatives in November 2018 under its role as ADP chair from July-December 2018.

This responds to growing support for action on sustainable soya in many European countries, including the UK. The UK officially launched a UK Roundtable for Sustainable Soya in July 2018, drawing together retailers, agricultural industries and traders under a commitment to source soya that is ‘legal and cultivated in a way that protects against conversion of forests and valuable native vegetation’. Technical support for the roundtable is being provided through Partnerships for Forests.

Indicator 1.2
Securing demand-side policy change at an individual company level is also key part of the programme approach, which works at all levels of value chains to secure change. A case study has been completed to document this in the Ghanaian cocoa sector, where Touton, a French cocoa trading company, is working to encourage deforestation-free cocoa production in the Juaboso-Bia area. As part of its commitment to this work, Touton has introduced corporate-level changes to its business model, increasing supply chain control through becoming a licenced buying company and applying a climate smart, deforestation-free sourcing policy to help improve land-use management in the region.

Lessons identified
Programme support can enhance the impact of policy processes with well-targeted technical, advisory and logistical support. There is a complementary association between the engagement of UK government officials in relevant public policy processes, such as the Amsterdam Declarations Partnership and the Global Resource Initiative, and programme operations. This is helping to enhance the impact of demand-side interventions and reflects a close alignment between the policy agenda programme operations.

The growing influence of major emerging consumer markets (China and India) and emerging producer-consumer markets (Indonesia and Brazil) make it essential that these countries move towards sustainable sourcing. This will be needed to effectively address the deforestation crisis and the accompanying risks to the climate, ecosystems and planetary health.

Recommendations
Continue development of relationships with Amsterdam Declaration Partnership countries to strengthen markets for sustainable agricultural commodity supply chains, including palm oil, soy and cocoa (DFID);

- Ensure DFID support’s delivery of the UK’s 25-Year Environment Action Plan, through working with BEIS and Defra to design an ambitious Global Resource Initiative. Ensure that effective support to the GRI is provided through Partnerships for Forests;
- Deliver enhanced engagement on demand-side measures and communications as UK withdrawal from the European Union takes place, working in collaboration with Defra, BEIS and the Department for International Trade (DIT).

Consider how to ensure effective engagement with major emerging consumer markets (China and India) and emerging producer-consumer markets (Indonesia and Brazil), to shift global markets and supply chains towards sustainable production (DFID).

Output Title	Enabling conditions: Improved business environment for investments in forests and sustainable land use
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 number and description of cases where P4F has supported national / international multi-partner initiatives designed to enable private investment in forests and sustainable land use.	3 cases by 2018 / 6 cases by 2019 / 9 cases by 2020	On target: 3 cases in 2018 / (High Carbon Stock Approach (HCSA); / Cocoa and Forests Initiative (CFI); and / TFA Africa Palm Oil Initiative (APOI)
2.2 number and description of cases of Forest Partnerships that have benefitted from an enabled business environment as a result of P4F support.	2 cases by 2018 / 5 cases by 2019 / 12 cases by 2020	On target: 2 cases delivered in 2018. / (Cemoi cocoa production and PT Royal Lestari Utama rubber production).

Key points
This output is focused on creating the conditions required to enable private investment in forests and sustainable land use. Support is provided to address barriers to investment, such as the development of standards, provision of finance and policy and regulatory reform. Milestones are based on case studies which describe the support provided and present evidence describing the role of the programme in securing the result achieved.

The Tropical Forest Alliance has supported a series of dialogues in Southeast Asia and Latin America, focused around provincial and state-level sustainable development plans. These dialogues are intended to draw companies with sustainable sourcing commitments towards jurisdictions with clear plans in place to develop their agricultural industries in ways that minimise deforestation. Interest from the market in sourcing from these jurisdictions should provide further impetus to the implementation of provincial and state-level sustainable development plans.

Partnerships for Forests is providing targeted support helping to develop standards, mobilise industry-wide commitments and support policy and regulatory reforms for specific commodities, including palm oil, cocoa and rubber.

Indicator 2.1
A lack of operational standards has been identified as a significant barrier preventing palm oil companies from implementing zero-deforestation growing policies. Companies producing other commodities, including rubber, have faced similar a similar challenge. The High Carbon Stock (HCS) Approach has been developed to address this. Support provided has allowed the HCS Approach to develop a unified methodology and set of principles to help implement corporate zero deforestation commitments, agreed by a broad set of major companies as well as social and environmental NGOs.

Application of the HCS standard by palm oil companies has now resulted in the assessment of over 2.4m ha of land in West Africa and Southeast Asia, with over 0.55m ha of high carbon stock forest identified for conservation. Future support to the HCS Approach is likely to focus on developing solutions for the sustainable management of these conservation areas, so that forest set aside from palm oil developments is protected and managed sustainably over the longer term.

Following a decision taken at the 15th General Assembly of the Roundtable on Sustainable Palm Oil (RSPO) in November 2018, the High Carbon Stock Approach has now been integrated into the RSPO’s updated certification standard. This is a significant development which will ensure further uptake. It will also help to ensure that the RSPO – the benchmark international standard for sustainable palm oil – is now able to certify palm oil to a deforestation-free standard. High social requirements within the HCS Approach will also help to ensure positive impacts for communities, balancing sustainable livelihoods and poverty reduction with the need to conserve, protect and enhance ecosystems, and respect land users’ rights.

Further progress has also been recorded through the Cocoa and Forests Initiative (CFI). The Cocoa and Forests Initiative was launched in 2017, when 34 cocoa and chocolate companies (representing 80% of global cocoa usage) set out a commitment to end deforestation associated with cocoa production. Under the grant from Partnerships for Forests to support Phase I of this initiative, the cocoa and chocolate industries negotiated and agreed Joint Frameworks for Action with the Governments of Ghana and Cote d’Ivoire, which together account for over 60% of global cocoa production. The Joint Frameworks for Action set out plans for implementation, policy and regulatory reforms and monitoring and reporting arrangements. The frameworks have the potential to increase mutual accountability and could serve as a model for future work in other countries and commodities.

As support through the programme has transitioned into a second phase, the P4F team has played an important role in enabling greater representation and participation of local civil society organisations (CSOs) in the CFI process and the implementation of the Joint Frameworks for Action. This has been documented as a case study under Indicator 3.6 below. The closer engagement and participation of local CSOs should help to strengthen the implementation of the Joint Frameworks for Action, as these organisations hold some of the strongest relationships with farmers and communities in Ghana’s cocoa-growing areas.

Lessons identified
Support for enabling conditions is a key aspect of the IFSLU programme strategy. The business environment for companies seeking to operate sustainably is highly challenging. Policies and regulations often discourage sustainable practices, but securing change is challenging in the context of the political economy around land use in developing countries. Finance is hard to access and rarely offers any price incentive for sustainable practices as an alternative to unsustainable business-as-usual practices. A strong set of enabling interventions has now been established across all programme regions, addressing these challenges. The expansion of the programme into Latin America offers an opportunity to build on this further.

Finance is one of the most important (and most challenging) enabling conditions required to unlock investment in sustainable land management at scale. Good progress has been made towards building up a set of interventions (both through enabling conditions grants under Output 2 and support to partnerships under Output 3) which will allow the programme to start working on this issue.

In East Africa and West Africa, the Climate Smart Lending Platform (CSLP) is working to provide finance to help smallholder farmers through a transition to more sustainable land-management practices, including increased on-farm tree cover. In Southeast Asia, the Sustainable Commodities Conservation Mechanism (SCCM) is aggregating payments which palm oil companies owe for historic deforestation and investing these funds to support community forestry projects and restore ecosystems. These platforms have the potential to be financially sustainable, replicable and scalable across large numbers of smallholder farmers and communities. Opportunities to accelerate and scale-up these activities should be given consideration in the year ahead and in the programme extension period.

A new arrangement to collaborate with New Forest, an equity fund manager operating in Southeast Asia, will also help to the programme to improve understanding about how best to cooperate with impact investors and other mainstream fund managers. The collaboration is based on the development of pipeline for the New Forest fund, with Partnerships for Forests support focused on achieving additional environmental and social benefits through the fund managers’ investments.

Recommendations
Explore opportunities to accelerate and scale-up enabling conditions interventions focused on smallholder and community finance for sustainable land management practices (DFID, BEIS and P4F programme team);

Consider opportunities to enhance the impact of support for enabling conditions interventions in the programme extension period (DFID, BEIS and P4F programme team);

Continue support to enabling conditions interventions focused on the palm oil, cocoa and rubber industries (P4F programme team);

Work with BEIS to develop a complementary approach to supporting enabling conditions in Latin America as P4F expands into the region, adding value to the existing portfolio.

Output Title	Partnerships and investments: Partnerships between private sector, public sector and communities that seek to deliver investment in forests and sustainable land use
Output number per LF		3	Output Score	A+
Impact weighting (%):		60%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 number of concept notes that are accepted into the programme.	35 by 2018 / 40 by 2019 / 40 by 2020	Exceeded target: 36 projects accepted into the programme.
3.2 number of partnerships with a partnership agreement as a result of P4F support (Decision Gate 1).	16 by 2018 / 23 by 2019 / 23 by 2020	Exceeded target: 18 partnerships with partnership agreement.
3.3 number of partnerships with a business plan as a result of P4F support (Decision Gate 2).	10 by 2018 / 20 by 2019 / 20 by 2020	On target: 10 partnerships with business plan.
3.4 number of partnerships ready and prepared for a pilot as a result of P4F support (Decision Gate 3).	4 by 2018 / 10 by 2019 / 13 by 2020	Exceeded target: 6 partnerships ready for pilot or trial.
3.5 number of partnerships prepared for commercial scale-up as a result of P4F support (Decision Gate 4).	0 by 2018 / 3 by 2019 / 9 by 2020	No milestone: 1 partnership prepared for commercial scale-up.
3.6 number of interventions with new or enhanced stakeholder engagement planning (including gender and social inclusion) as a result of P4F support.	2 by 2018 / 4 by 2019 / 8 by 2020	On target: 2 cases in 2018. / (Civil society participation in Cocoa and Forest Initiative, Ghana; and gender analysis to support Africa Palm Oil Initiative, Ghana)

Key points
This output is focused on supporting public-private partnerships. Grant funding and technical assistance is provided to support partnerships which have commercial potential and deliver strong climate and development benefits.

Programme support is focused on moving partnerships through a series of steps presented in Figure 2, beginning with entry into the programme and then on through a set of decision gates leading from agreement of an MoU between parties (DG1 MOU), through the development of a business plan (DG2 Business plan), pilot testing (DG3 Pilot) and on to commercial scale-up (DG4 Scale-up). Partnerships which pass through the final decision gate should be financially viable businesses that no longer require support, providing the programme with an exit strategy. Partnerships which do not fulfil their potential to become financially sustainable will drop out of the programme at an earlier stage.

A strong portfolio of 36 partnerships has been established across the programme regions. To achieve this, a total of 349 ideas were identified, 193 ideas were screened and 143 subject to a more detailed assessment. This competitive process is an important feature of the value-for-money focus within the programme, ensuring that only the strongest partnerships with the potential to deliver the greatest impact and value for money are accepted into the programme. Further information about the partnerships and portfolio is available at https://partnershipsforforests.com/.

Eighteen partnership agreements have reached Decision Gate 1, with MoUs between parties; 10 have reached Decision Gate 2 and established business plans; six have reached Decision Gate 3 and commenced piloting; and one has reached Decision Gate 4 and embarked on commercial scale-up (see below). The rate of progress through the decision gates has accelerated considerably over the past year. A rate of progress through decision gates which was slower than expected had been identified as an area for management attention at the 2017 annual review. In the year ahead, it will be important to maintain a focus on progress of partnerships through decision gates, particularly Decision Gate 3 (piloting) and Decision Gate 4 (commercial scale-up). Taking partnerships through these gates will test the rationale for the programme and ensure that Outcome level targets are met.

Figure 2: P4F portfolio progress against logical framework targets

Portfolio overview
In West and Central Africa, the strategy is focused on partnerships around key commodity supply chains in the region, particularly palm oil and cocoa. A good alignment between support for improved enabling conditions and partnerships for deliver change on the ground has been achieved.

In the cocoa sector (Figure 1), industry engagement takes place through the Cocoa and Forests Initiative (CFI) (see Output 2 above). This supports a sector-wide effort to halt deforestation associated with cocoa production. This is complemented by partnerships with leading cocoa traders, including Cemoi, Touton and Olam, to develop and test new approaches to achieve this aim in practice. This includes innovative approaches to implement a climate smart approach to cocoa growing, working with farmers to improve growing stock, productivity, use of shade trees, conservation of forests to maintain healthy and productive landscapes, and the establishment of innovative landscape-scale management boards. The latter involves governments, companies, communities, farmers and civil society, in managing landscapes for production and conservation, thereby supporting more inclusive and sustainable development.

In East Africa, an important focus of the strategy is securing greater value for local communities from forests. A partnership to build a value chain around forest coffee is a key part of this effort. Coffea arabica – the plant from which all arabica coffee is derived – is indigenous to the forests of Ethiopia’s southwestern highlands. Forest coffee grows wild and regenerates spontaneously in its natural habitat. It is currently sold as cheaper, commercial grade coffee due to variable quality and lack of traceability. The forests in which the coffee grows are also under threat from agricultural expansion and demand for fuel.

P4F is providing support to create a premium brand and traceable supply chain. A business plan for the partnership has been developed and piloting is now underway. The business plan seeks to secure the export of 6,030 metric tonnes of forest coffee by 2020, with an associated investment of £70m, benefiting up to 10,000 farmers and providing an incentive to protect 150,000ha of forest.

To help prepare the business plan, a consulting firm, Boot Coffee, was engaged to assess whether the coffees were of high enough quality for the specialty coffee market. Around 30% of samples tested showing high potential, which could be marketed at specialty coffee level with small quality improvement practices during harvesting and processing. Boot Coffee also conducted a survey of international specialty buyers to gauge their knowledge and interest in the product, with initial positive responses.

The pilot to take this forward is now underway. Support is being provided to build farmers’ capacity to meet the harvesting and processing standards required to access the specialty coffee market, alongside marketing and branding assistance. Initial engagement with buyers in Ethiopia and internationally has resulted in positive interest among mid-size importers and exporters, and large coffee chains. Sales contracts for the pilot are expected to be concluded after completion of the 2018 harvest in December.

If the pilot is successful, further benefits could be achieved through scaling and replication. Forest coffee covers a total production area of approximately 600,000 hectares, an area twice the size of Kent. At least 23,000 farmers depend on forest coffee for their livelihoods, of which 20% are women. Many more people are employed in other parts of the coffee value chain, in activities such as sorting, in jobs which are predominately undertaken by women.

In Southeast Asia, the portfolio is focused on supporting pioneer businesses based on sustainable forest products, and supporting sustainable practices in established commodity value chains, such as palm oil and rubber.

An important milestone was achieved in 2018, through support for a sustainable rubber plantation development in Indonesia, working with PT Royal Lestari Utama (PT RLU) and WWF Indonesia. This is the first partnership to reach the stage of commercial scale-up. The scale-up will help to create 16,000 jobs and improve 50,000 livelihoods, while protecting key protected areas and wildlife habitat. Building on support provided through Partnerships for Forests, the rubber plantation attracted commercial finance of £68.4m, bringing 88,000 ha of land under improved management. This marks the first results against Outcome-level key performance indicators.

A second important result was achieved with agreement around the first transaction under the Sustainable Commodities Conservation Mechanism (SCCM). The SCCM has been set up to aggregate compensation payments which palm oil companies owe for historic deforestation and invest these funds to restore ecosystems and support community forestry projects. The compensation payments are a requirement under the Roundtable on Sustainable Palm Oil RSPO, a certification scheme which is essential for market access in European and other developed markets. Total potential deforestation liabilities across the palm oil industry are estimated at approximately $250m.

The first transaction will result in the investment of funds which Cargill, an agribusiness company, have committed to the SCCM, to compensate for historic deforestation on palm oil plantations which they acquired in the province of West Kalimantan. The funds committed by Cargill will be invested into forests under management by local communities in the province, supporting sustainable economic growth and local livelihoods. Negotiations to finalise the contract for this investment are in their final stages. Conclusion of the first transaction has helped to accelerate negotiations with other palm oil companies. SCCM has received letters of intent and interest from a range of corporate clients to support conservation compensation credit purchase to the value of at least £20m.

Lessons identified
Experience of programme delivery has led to an improved understanding of the time and resources needed to move projects through decision gates. This has helped to allocate staff time and resources more effectively and strengthen the overall management of the portfolio with a view to meeting indicator targets. The impact of this work can be seen in the accelerated movement of partnerships through decision gates. Continuous efforts to ensure speed up programme processes and ensure smooth operation across all regions is still required.

With the project portfolio on track to meet planned targets, and current programme resources now close to being fully committed, pipeline development for Output 3 has now been significantly reduced, except in Latin America, which is at an earlier stage of development. The focus is now on developing a small number of project concept notes for possible entry to the later stages of the decision gate process, and implementation of existing partnerships to achieve results and impact. This marks an important turning point for the programme. This will continue to be a key focus in the year ahead, to ensure that programme spending reaches the targeted levels.

The sustainable rubber project in Indonesia has generated significant insights into how public funds can be used to catalyse private investment, but has also highlighted challenges around replication. While many companies have public commitments around zero-deforestation and sustainable supply chains, the difficulties in getting companies and investors to commit to projects cannot be underestimated, especially within challenging operating environments.

Companies in dialogue with the programme have faced challenges in relation to securing concessions the required operating licences and permits, while securing board-level sign-off for innovative approaches can also be challenging. Investor perceptions of risk remain high and finance for sustainable practice is priced at the same level as finance for business-as-usual operations, which weakens the incentive to adopt more complex sustainable approaches. This highlights the need to continue working to engage developing country governments around this agenda, maintaining pressure for internal change within companies, and continuing to seek ways of changing practices in the financial services industry.

Recommendations
Manage shift in focus of the partnership portfolio from expansion to progressing projects through decision gates and implementing activities to achieve results and impact. Maintain a close focus on decision gates for piloting and commercial scale-up in the final years of the programme (DFID and P4F programme team);

Maintain close management of the grants to ensure milestones are monitored and achieved and spending reaches target levels (P4F programme team);

Strengthen financial forecasting around partnerships to support DFID’s financial planning and ensure efficient interactions between Partnerships for Forests and programme partners on financial reporting and disbursement of grant payments (P4F programme team);

Continue to work with BEIS to support the development of a portfolio of public-private partnerships in Latin America.

Output Title	Leadership, collaboration and learning: Models, learning and leadership that support collaboration and investment in forests and sustainable land use
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Annual report demonstrating understanding of portfolio dynamic and progress through decision gates.	2 by 2018 / 4 by 2019 / 6 by 2020	Target met: reports completed.
4.2 number and description of P4F knowledge products published and communicated	4 by 2018 / 13 by 2019 / 26 by 2020	Target met: 4 knowledge products completed.
4.3 number and description of initiatives with enhanced or high value collaboration from P4F	0 by 2018 / 5 by 2019 / 10 by 2020	No milestone: 3 examples of high-value collaboration delivered in 2018.
4.4 number and description of events with a distinct contribution from P4F	12 by 2018 / 25 by 2019 / 38 by 2020	Exceeded target: 14 events with distinct contribution in 2018.

Key points
This output is focused on learning, collaboration and leadership to inform a wider community of stakeholders, with the aim of accelerating the replication and scale-up of sustainable business models. A strategic partnership has been formed between the Tropical Forest Alliance and Partnerships for Forests, focused on advocacy and learning across the growing international community of practice working to address deforestation associated with agricultural commodities. Partnerships for Forests has also developed a revised strategy for Output 4, focused on strategically important collaboration.

The programme helped a successful DFID-led communications campaign through UK-based media around the Illegal Wildlife Trade Conference, hosted by the UK government in September 2018. The conference marked a significant commitment by the UK government on an issue which has strong and widespread public support. The programme provided the content, as well as essential support on communications, for a high-profile visit by the Secretary of State to London Zoo. The visit highlighted efforts to protect the Sumatran tiger and other endangered wildlife species in Southeast Asia and West Africa and attracted coverage in national television and print media.

Indicator 4.1
Analysis of the portfolio is an important element of programme learning. This analysis shows that it typically takes over 300 days to take a project from initial conception to a concept note that meets the P4F investment criteria. Time is required to develop the idea, undertake due diligence and assess risk and negotiate to ensure value for money. While these steps are essential to effective programme management (and contractual requirements from DFID), it does mean that the programme is at times not operating at a speed which is commensurate with the expectations of external stakeholders, particularly programme partners in the private sector.

A thematic study was undertaken by the Independent Evaluation and Learning Manager, on the ‘Effectiveness of the Forest Partnerships Assessment Framework, Grant Making and Incubation Processes.’ It produced some useful recommendations and P4F has adapted elements of the pipeline process to improve efficiency and reduce the project development time. However, balancing the need to move quickly and innovate with the need for effective programme management and prudent risk management is an ever-present tension that requires constant management oversight to ensure the right balance.

Other findings of the portfolio analysis show that Partnerships for Forests processes result in the rejection of a high rate of projects at early stages and the rejection rate reduces as a project develops. Only 15% of identified ideas progress to the point of concept note development. Early filtering helps to remove projects that do not fit the investment criteria and strategy of the programme to minimise developing concepts that will ultimately be more likely to be rejected.

Indicator 4.2
A second important area of focus is the provision of knowledge products for target audiences. This included a video for Ethiopian Wild Coffee, aimed at industry, investors and donors. It illustrated the potential impact of this value chain on forest conservation, protection of biodiversity and livelihood benefits. This was shown at various events in 2018, including the Seattle Coffee Expo, as a way of raising the interests of potential buyers in the product.

The Ethiopian Wild Coffee partnership aims to create a premium brand and traceable supply chain and ensure that Ethiopian farmers increase their returns from wild coffee to create greater incentives to conserve the forests in which it grows. Marketing efforts are a key part of this intervention and pitches to the coffee industry, including through the Seattle Coffee Expo and other fora have successfully raised interest from coffee buyers and roasters in the product.

Indicator 4.3
Enhanced collaboration with strategic initiatives has been demonstrated this year, notably through the strategic partnership with the Tropical Forest Alliance. In Southeast Asia, this helped to identify opportunities for public-private collaboration around the Bukit Tigapuluh National Park and the Rimba Corridor conservation landscape in Indonesia, while in West & Central Africa it focused on significant collaboration around a successful TFA General Assembly in Accra in May 2018. This included hosting two field visits to flagship public-private partnerships (Benso Oil Palm Plantation and Touton cocoa landscape) to showcase the approaches to zero deforestation production which the programme is supporting, as well providing significant content for the General Assembly agenda.

Indicator 4.4
Partnerships for Forests hosted an inaugural Partner Exhibition in the UK in July. This brought together 12 project partners, to support cross-regional and cross-project learning and enabled partners to pitch their projects to wider participants which included members of the investment community. The format for the event supported effective interaction. Building on this experience, a follow-up Partner Event is being considered for 2019, which will be more explicitly focused on pitching projects to investors.

Lessons identified
Advocacy, communication, learning and collaboration are vital to ensure commercial scale-up of successful business models. Tracking and reporting on the impact of this work will be important and challenging and this should be given further thought in the year ahead.

Partnership for Forests needs to be opportunistic but also strategic to ensure effective use of limited resources. Regular discussion, including in the weekly management call, could be used to help identify the most important opportunities.

Use different channels to ensure that new and different audiences are effectively reached and engaged. An example of how this was achieved successfully this year was at the Seattle Coffee Expo, where the audience reached was from within the coffee industry, rather than an audience engaging through corporate social responsibility or sustainability interests.

Recommendations
Effectively prioritise new strategic opportunities for learning, collaboration and leadership over the next year, such as the UNSG 2019 Climate Summit and the Food and Land Use Coalition Global Report. Effective interventions should aim to provide ‘proof of concept’ to audiences already engaged on how to deliver commitments, as well as reach new audiences to demonstrate the value of the model (DFID, BEIS and P4F programme team).

Continue to foster a cooperative relationship between the P4F delivery team and the Independent Evaluation and Learning Manager to develop an enhanced learning focus and implementation of key learnings within the programme (P4F programme team and evaluation manager);

Continue to build the programme presence in key international, regional and national platforms for learning and developing collaboration, including a strong focus on collaboration with the TFA to maintain momentum for delivering on 2020 commitments (P4F programme team).

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

IFSLU aims to shift private sector incentives and practices, and catalyse private sector investment in forests and sustainable land use. Changing business-as-usual practice in land use change is challenging. The programme business case identifies opportunities to shift private sector incentives and practices through market-driven approaches to sustainable sourcing of forest products and agricultural commodities (demand-side measures); support to improve the enabling conditions for responsible and sustainable investment; and support and finance for such investments (supply-side measures). The programme theory of change assumes that a focus is needed across each of these areas (Figure 3).

Partnerships for Forests is the major element of the IFSLU programme. It provides grant financing and technical assistance against the following areas to deliver against the theory of change:

Demand-side measures: to accelerate public and private commitments to create a more valuable market for timber and agricultural commodities from sustainable sources;

Enabling conditions: to improve the business environment for investments in sustainable forestry and agriculture;

- Partnerships and investments: to develop public-private partnerships and investments in sustainable forestry and in sustainable agriculture.
- Leadership, collaboration and learning: to accelerate replication and scaling-up of successful sustainable business models.

Figure 3: Summary theory of change

Annual outcome assessment
The programme outcome is: Increased private investment in forestry and ‘reduced-deforestation’ agriculture support economic growth, improved livelihoods and reduced poverty, measured against outcome-level indicators of private investment mobilised (£); area of land under improved (sustainable land use) management (hectares); and number and description of cases where there has been a change in livelihoods and/or employment and/or reduced poverty.

Figure 4: Risk-weighted modelling of the portfolio against programme outcomes

The portfolio of 31 active partnerships has the potential to significantly exceed the outcome targets. Current projections indicate that the portfolio has the potential to bring 3.02m hectares under sustainable management (against an outcome target of 1.22m ha) and to mobilise £352m of private investment by 2020 (against a target of £183m) (Figure 4).

Outcome forecasts are subject to considerable volatility, given that many partnerships may not lead through to the anticipated investments. The first results against these targets have been banked this year (£68.4m investment and 88,000 ha of land under improved management), giving some confidence that the overall targets can be achieved. The programme is also set to achieve significant livelihood and employment outcomes, to be documented through case studies in later years of the programme.

Changes to the log frame
The log frame was updated in 2018 following a comprehensive review based on the experience of the first two years of programme operations. Revisions include:

Revised and extended Demand Side Measures (Output 1) and Enabling Conditions (Output 2) indicators to recognise results in these areas being embedded in a number of partnerships and addressing the need for some intermediate output indicators;

Revised Output 4 indicators and targets;

Increased output targets where existing targets have already been met, to ensure that the programme has realistic but challenging targets and provides maximum value for money;

Improved indicator verifiers and definitions to ensure clarity of what constitutes successful delivery of results;

Adjusted targets and milestones to ensure that administration and payment by results delivers appropriate incentives and risk management for all parties;

Revisions to all results areas to allow for the Latin America expansion of the programme to be effectively managed within a single, programme-wide, results framework.

Further log frame changes will be introduced in 2019 to reflect the extension of the programme to 2023.

## D: VALUE FOR MONEY

Value for money assessment
Within the programme portfolio, value for money has been identified as a key issue for the replicability of public-private partnerships. A framework focused on economy (buying inputs of the required quality at the lowest price); efficiency (producing outputs of the required quality at the lowest cost); effectiveness (how well outputs produce outcomes); cost-effectiveness (producing outcomes at the lowest cost); and equity (ensuring development results are targeted at the poorest) is applied.

Economy: The main cost driver in Partnerships for Forests is the need to engage specialist expertise to work effectively with businesses, governments, industry associations and non-government organisations. This is used to design and structure innovative public-private partnerships, which are financially viable, and deliver social and environmental benefits, while meeting DFID’s standards for risk management.

Specialist expertise is provided directly through the programme or through third parties. Costs relating to the former are managed through an output-based contract which defines payments against milestones in the logical framework. Costs for the latter are managed through competitive procurement, negotiation of rates, and sourcing of expertise in local, rather than international markets, where appropriate.

Efficiency: Match funding greatly enhances value for money. Grantees are encouraged to match at least 25% of project costs. This has been exceeded and the match funding achieved currently meets around 50% of project costs, or a ratio of 1:1 (as of September 2018). This means that grantees and their partners are contributing £1 for every £1 provided by P4F. Match funding commitments are subject to stress testing and due diligence prior to the approval of grants. Success in securing match funding suggests a high degree of ownership and commitment, helps to ensure that costs and risks are shared fairly between the programme and the partnerships, and ensures P4F targets support only in ways where additionality can be achieved and development and climate benefits secured.

A focus on additionality further strengthens the value for money framework. Each project considered for support is reviewed against additionality criteria. Additionality has been defined as the ‘net positive difference that is expected to result from a P4F supported partnership. The extent to which activities (and associated results) are larger in scale, at a higher quality, take place quicker, take place at a different location, or take place at all as a result of a P4F intervention’. Evidence to support additionality is documented for each partnership supported and broader analysis of this data helps to better understand the role and the value of the P4F programme. This helps to design and target assistance more effectively as needs become better understood for different business models and partnerships.

Effectiveness: Mobilisation of private investment through use of DFID’s grant funding ensures that the programme achieves a strong value-for-money outcome. Programme support is geared towards helping partners secure the commercial finance required to become financially viable businesses, providing the programme with an exit strategy from the partnership. To date, programme funding has secured £68.4m (US$95m) in commercial ‘green’ private sector investment. The projected level of investment mobilised over the lifetime of the programme is up to £350m.

Cost-effectiveness: Budget scrutiny is an important part of programme delivery, and occurs at three levels: ongoing negotiation by the regional teams during project concept note development; compliance and value for money quality assurance by the grants team when project concept notes are in final draft and ready for submission to the P4F approval committees; and ongoing scrutiny of planned and actual project expenditure by both the regional teams and the central grants teams.

Partnerships for Forests also applies strict cost management to its own operations, for example through achieving better value on office rental, vehicle leasing and flights, which has also secured considerable savings. Savings from negotiation and cost management are documented in programme reports.

Equity: Equity is addressed through due diligence procedures which ensure partnerships supported provide strong benefits to local communities, through improved livelihoods and jobs. Often, support provided is designed to enhance the social impacts of private sector investment. A Gender and Social Inclusion Strategy is applied across programme activities ensure issues of equity are addressed systematically across the programme. Programme impacts on livelihoods and equity will be documented through case studies.

Value for money to support continuation of the programme (own merits and wider portfolio)
IFSLU contributes to important HMG priorities. It provides a strong example of UK global development leadership, focused on finding new, sustainable solutions to key global challenges – how to secure enough food for a growing population while protecting the environment and forests on which we depend, improving the resilience of local people, and reducing carbon emissions to help meet our climate goals.

UK leadership on this issue is shaping the agenda internationally. The UK’s 25-Year Environment Action Plan flagged the importance of sustainable supply chains and set out commitments in this area. IFSLU is providing a key means to deliver on HMG’s aims.

A new approach to sustainable land use needs to be at the centre of efforts to realise the Sustainable Development Goals and the Paris Climate Agreement. Neither can be achieved without a shift to more sustainable patterns of land use, which produce sufficient food for a growing population, reduce greenhouse gas emissions and protect the ecosystems and natural resources (fresh water, fertile soil, biodiversity, wildlife habitats) which sustain life. IFSLU is at the leading edge of international efforts to find a new approach.

The programme also has the potential to support the UK’s leadership role on resilience for the 2019 UNSG summit. Experience of working with companies to develop public-private partnerships around climate smart agriculture and sustainable land use will inform the UK’s wider approach to engaging business in the resilience agenda.

The year 2020 is the deadline by which many companies have committed to remove deforestation from their supply chains and operations. This is unlikely to be met, but good progress has been made and further efforts beyond 2020 need to be sustained, given the crucial influence of this issue on global deforestation rates.

Successful demonstration of public-private partnerships which provide solutions to this challenge, across different countries, with different commodities and involving a range of businesses, are required. This would help to demonstrate that commitments can be achieved, leading to the possibility of a transformation in global markets and impact at scale. IFSLU has an important focus on accelerating ambitious industry-led efforts to source and produce commodities like palm oil, cocoa and soya without causing deforestation, and is ideally placed to contribute to this challenge.

E: RISK

Overall risk rating
Moderate

Overview of programme risk
The programme operates in a complex risk environment. Simultaneous management of risks associated with programme delivery and meeting results targets, provision of support to incubate start-up businesses and the sharing of associated risks, and risks associated with political and reputational issues arising through supporting private sector-led innovation has the potential to result in a tension between innovation and risk-taking on the one hand, and the delivery of results in a challenging environment on the other. This is a continual feature of the programme which requires ongoing management oversight, to ensure the programme strikes the right balance between innovation, delivery of results and risk management.

Key delivery risks relate to the assumption that technical assistance and grant funding can take sustainable businesses through a transition to commercial finance, as well as wider challenges relating to the political economy and operating environment for forest and land use investments in developing countries. The broad portfolio of partnerships, encompassing different types of businesses, commodity value chains, countries and regions, helps to mitigate this risk.

There are also reputational risks associated with private sector collaboration which require continuous monitoring and mitigation, particularly around the need to avoid providing an excessive subsidy for private sector activity, ensuring the right balance in sharing of risk and up-front costs, and demonstrating additional value arising from the use of public funds.

Systems have been designed to ensure that fiduciary risk is low. Programme funds are disbursed through an external service provider with strong due diligence and financial management systems. Downstream mapping of the supply chain has taken place for Tier 2 and Tier 3 partners.

Risk mitigation includes due diligence; the integration of gender and social equity considerations into appraisal and decision-making, to ensure that partnerships deliver strong development benefits; and a programme focus on developing shared value through public-private-people partnerships. Realising shared value is a vital element of sustainable business models, which retain a social licence to operate, in remote, rural regions of developing countries.

Safeguarding has been a particular focus of risk management this year. Due diligence procedures have been updated to include a strengthened focus on safeguarding, focused on partner organisations internal policies and procedures, such as codes of conduct, grievance mechanisms and whistle-blower policies, questions on contractual equity (such as contracts between companies and farmers), as well as safety, security and duty of care. This augments existing due diligence procedures, which include a strong focus on land issues and the social impacts of operations. Programme staff have also been provided with safeguarding training, focused particularly on due diligence, social performance of partner companies and the safeguarding of programme beneficiaries.

Initial experience with applying these policies has been broadly positive. Managing complex environmental and social issues is an important requirement for companies operating in the agricultural and forestry sectors, and many large companies do have such policies in place. Applying such policies across companies with extensive and dispersed operations can be challenging, and careful monitoring of such risks is applied. Smaller companies and start-ups may not yet have a full set of adequate policies in place, and the programme has provided advice on required and recommended improvements.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery against planned timeframe
The programme is on track. All deliverables during this period were of high quality and submitted either on time or ahead of schedule.

Performance of partnership(s)
The Tropical Forest Alliance is jointly funded by the UK, Norway and the Netherlands. The UK is a member of an international multi-stakeholder steering committee, which has been established to guide the operations of the alliance. The donors also meet on a six-monthly basis with the TFA secretariat. This ensures effective input to the strategy of the alliance and strong oversight of activities.

Partnerships for Forests is outsourced to a consortium comprising Palladium, McKinsey and Systemiq. Within the consortium, regional teams are responsible for identifying partnerships with the potential to contribute to programme outcomes. Potential partnerships are developed and moved through a series of review steps. Decisions to provide funding are taken ultimately by the Senior Leadership Team, comprising the responsible directors of Palladium and McKinsey and DFID’s Senior Reporting Officer.

A strong and collaborative working relationship has been established between DFID and the Partnerships for Forests management team, including through strategy workshops, regular management meetings, joint outreach and engagement with partners, and field visits. BEIS has also been successfully introduced into the established programme management arrangements.

Palladium, McKinsey and Systemiq, have formed a strong partnership, combining Palladium’s development experience and business advisory experience on sustainability and finance held by McKinsey and Systemiq. Secondment of staff between the different programme regions is helping to ensure that all programme offices have access to these different skills, helping to promote a common approach across the different regions which draws on the strengths of the different consortium members. Strategic roles have also been identified for other partners in the consortium, particularly Efeca, a consortium partner specialised in advising governments and companies on demand-side policies.

Monitoring of the delivery chain continues to be applied to ensure early identification of reputational, political and fiduciary risks which may arise in relation to Tier 2 and 3 partners in activities supported through the programme.

The P4F annual audit was conducted by an independent assessor, covering the period April 2017-March 2018. The audit review process was designed to determine whether activities conducted were in accordance with the contractual requirements for the P4F programme. Recommendations arising focus on improving the supporting documentation of regional office finances; agreeing a cut-off date for charging historical expenses between the consortium; and demonstrating compliance with the updated DFID terms and conditions. Work to address these recommendations is ongoing.

Date of last narrative financial report(s)	November 2018
Date of last audited annual statement (s)	October 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring
Monitoring is focused on implementation of processes and systems, including assessing ideas and proposals for inclusion in the programme, criteria for moving through decision gates, modelling and risk-weighting of project and portfolio outcomes, tracking change and attribution, supporting individual projects to develop results frameworks and theories of change. Project management systems generate good data which enables portfolio analysis and adaptive management of the programme. Portfolio-level monitoring has also been used to focus resources efficiently, such as prioritising projects which contribute the greatest potential results, or offer strategic value to the programme.

Monitoring has been enabled by the development of innovative information management systems, including a portfolio tracking tool, which facilitate effective working of a dispersed team, operating from Bristol, Sau Paulo, Accra, Addis Ababa and Jakarta, as well as other locations. Remote working is complemented by visits to programme regions on a quarterly basis by senior managers.

Evidence
The evidence base supporting the programme is continually evolving. The community of practice brought together by the Tropical Forest Alliance is providing a strong body of first-hand experience associated with implementing different approaches to implementing zero deforestation production and sourcing commitments. Evidence is often blurred with advocacy and promotion of individual projects and approaches, so a lack of credible and impartial evidence can still present a challenge. The time between changed practices and changed outcomes on the ground also presents a challenge relating to evidence.

Partnerships for Forests is at the forefront of programmes generating primary evidence and it is important that this is shared widely. An important area topical evidence is being generate relates to landscape approaches to manage production of commodities and protection of forests.

The programme is supporting landscape-scale interventions in West Africa (cocoa production and forest conservation), East Africa (tea production, smallholder dairy farming and forest conservation), and Southeast Asia (rubber development, non-timber forest products and forest conservation). Important lessons are being generated, highlighting the need to work at this scale to reconcile development and conservation priorities, as well as the challenges of developing and sustaining the management institutions required to accommodate a range of stakeholder interests and manage trade-offs which arise. A key challenge relates to the financing of these management arrangements over the longer term and it may be opportune for the programme to undertake specific work on this issue in the year ahead.

Learning
The Independent Evaluation and Learning Manager has conducted a comparative analysis of programmes focused on incubating public-private partnerships, implemented by both public and private sector organisations. Key lessons identified include:
Results take time – 2020 may be too early to see significant outcomes from P4F activities. As the P4F programme is responsible for delivering ‘market ready’ partnerships, expected impacts will occur beyond the life of the programme and is influenced by many different contextual factors.

The incubation process is core to the P4F programme but could be improved through evaluation and learning (improvements are now being introduced, following a detailed case study undertaken by the Evaluation and Learning Manager in early 2018).

Consideration of balance between innovation and meeting targets. There is tension between meeting programme outcome targets and supporting initiatives that may be riskier or could take longer to develop but which might eventually lead to more systemic, transformational change.

The regional strategies and identified projects are highly relevant given the different starting point contexts in each region. There is variation in the regional approaches because of differences in current forest cover and potential forest transitions, the primary drivers of deforestation, and current governance contexts in each of the countries.

The P4F results are driven by a probabilistic modelling approach that is reasonable as it is widely used in the private sector. This is a reasonable approach but could warrant further review as projected outcomes are subjective and assumptions should be clearly communicated.

Progress on recommendations from previous reviews
A comprehensive review of the programme strategy was undertaken following the 2017 Annual Review, both to take stock of the portfolio and related targets after two years of implementation, and to accommodate the entry of BEIS into the programme and the mobilisation of operations in Latin America. This has resulted in an updated programme strategy and a revised log frame.

Steps were taken to bring the different regions together around a shared vision. This has been achieved through a review and discussion of the programme strategy, a retreat and training sessions for regional teams, regular regional visits by members of the senior management team. Opportunities for staff secondments have also helped to promote a shared vision, as well as offering team members an important development opportunity and helping to ensure a good mix of skills across all regional teams (for example, seconding a team member with strong business analytical skills to work with a team with more experience in development programme delivery for social impacts).

Attention has been focused on improvements to the development of the portfolio, including improved understanding of the time and resources needed to move partnerships towards impact. This has resulted in prioritisation of resources and accelerated progress of partnerships through programme decision gates over the past year.

A strengthened approach to identifying and engaging with demand-side measures opportunities has also helped to bring a stronger focus to this area of the programme and greater coherence to the portfolio. Steps have been taken to address gaps in the portfolio around enabling conditions, which will help to enhance the impact of public-private partnerships supported by the programme.