## Annual Review

Project Title: Fair Trade, Employment and Poverty Reduction Research
Date Project Started: 2009 Date Review Undertaken: December 2013

Introduction and context

What support is the UK providing?
Originally, DFID was providing an accountable grant of £692,958 to the School of Oriental and African Studies (SOAS) over 4 years (2009/10-2012/13). / The closing date of the grant was extended to 31st March 2014 through two no cost extensions which have been granted since the last Annual Review was submitted in 2012. The first was granted on 29/01/13 (EDRM 3839646), in response to a request to extend the project completion date from 31/08/13 to 31/12/13 to allow the research team to carry out workshops in Uganda and Ethiopia that would provide comment on preliminary findings from the research data and analysis. The second was granted on 10/12/13 (EDRM 4272237) in response to a request to extend the project end date to 31/03/14 to allow the research team to provide feedback to workshop respondents and further test their findings with peers after the draft technical report is submitted by end 2013. / The grant is used to fund quantitative and qualitative (including some longitudinal) research to provide a better understanding of the prevalence of waged work and the comparative benefits and disadvantages (especially for women workers) of agricultural certification schemes compared to non-certified production. The research was implemented in Ethiopia and Uganda and focuses on two commodities in each country: coffee and cut flowers in Ethiopia, and tea and coffee in Uganda. / The Project Completion Report (PCR) for this accountable grant will be submitted by 31st March 2014, therefore covering the findings of the final technical report (draft received 01/01/14) and any dissemination activities. This AR is light-touch and will cover the period of September 2012 to December 2013 (the period since the last AR was submitted). This review incorporates a desk-based review of relevant documents and a face-to-face meeting with the research team (13/12/13).

What are the expected results
If results are successfully achieved, the SOAS research project should enable companies, certification bodies, governments and donors (including DFID) to have a better understanding of the income effects of fair and ethical trade for poor people engaged in wage labour. / The expected impact, outcome and outputs are: / Impact: Poverty reduction policies, company decisions and certification standards are shaped by high quality evidence of the impact of agricultural produce certification on poverty. / Outcome: Relevant stakeholders have a better understanding of comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification and non-certified production. / Output 1: Appropriate research methodology to assess effectiveness of certification schemes on poverty reduction among women and men is available. / Output 2: Longitudinal assessment completed of the comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification schemes and non-certified production. / Output 3: Research results and policy messages disseminated to donors, certification bodies and business. / Milestones in the logframe are timed for the original contract period. The relatively short extension period (5 months) did not merit the introduction of a further set of milestones. At the date of this Annual review, we have therefore used targets specified in the logframe, and identified our degree of confidence in achievement of each target within the revised timeframe of the project.

What is the context in which UK support is provided?
Millions of poor people in developing countries are involved in exporting agricultural commodities, as wage workers on both large and small farms. Fairtrade and other certification schemes are based on theories of change that suggest, directly or indirectly, that they reduce poverty. / There has been little research on the results for the poorest households of certified production, relative to non-certified production, on waged workers compared with smallholder producers, or on the living standards of women dependent on wage employment in agricultural commodity production. / The June 2007 International Development Committee report on Fair Trade and Development concluded “we believe there should be more systematic analysis of the impact of Fair Trade on poverty and would urge DFID to contribute to this process”. In response, DFID supported this research by SOAS and provided an accountable grant to the Natural Resources Institute (NRI) for Assessing the Impact and Governance of Sustainability Certification and Labelling Schemes (EDRM 4209728).

Detailed Output Scoring
Output 1: Appropriate research methodology to assess effectiveness of certification schemes on poverty reduction among women and men is available.
Output 1 score: A (Outputs met expectations) / Performance against target: / Target: positive peer review of literature on methodology as part of final report. This target is on track for completion by the Project Completion Review due on 31/03/14 and we have a high degree of confidence that peer review will include positive comment on the methodology used. / A paper on methodological approaches was written in 2012 (http://ftepr.org/wp-content/uploads/how-to-do-fieldwork-draft.pdf) and has been peer reviewed and accepted for publication in the Canadian Journal of International Development (expected online publication date January 2014). / SOAS have continued to present on their methodology at workshops with standards organisations (e.g. ISEAL June 2013) and academic conferences (e.g. Lisbon June 2013). The draft technical report (received 01/01/14) includes a comprehensive overview of the approach to selecting research sites, sampling, longitudinal studies and the inclusion of life work histories. The draft technical report has been submitted to the Advisory Group, Fairtrade Foundation, Fairtrade International and key DFID colleagues for fact-checking ahead of the report’s finalisation at the end of January 2014 / Target: positive review of field report as part of final report. This target is on track for completion by the Project Completion Review due on 31/03/14. Discussions with the research team indicate that they received positive feedback from workshops held in Uganda and Ethiopia in November 2013. They were able to provide detailed explanations of how their data are generated, in response to challenges that their findings are controversial. The draft technical report (received 01/01/14) includes analysis of the field reports. The draft technical report has been submitted to the Advisory Group, Fairtrade Foundation, Fairtrade International and key DFID colleagues for fact-checking ahead of the report’s finalisation at the end of January 2014.. / Recommendations: Ensure DFID technical staff and relevant stakeholders are aware of the SOAS article, when published in academic journal. / Impact Weighting (%): 25% Revised since last Annual Review? No / Risk: Low Revised since last Annual Review? No

Output 2: Longitudinal assessment completed of the comparative benefits and disadvantages (especially for women) – from a labour market and poverty reduction perspective – between special certification schemes and non-certified production
Output 2 score: A (Outputs met expectations) / Performance against target: / Target: completion of sex disaggregated data set with methodological and technical notes. This target has been achieved. The data set was generated through 1700 survey responses, with 401 longitudinal follow up survey responses. The sample was generated from 8349 GPS census data points and 4743 initial household survey interviews. The methodologies paper records that the research respondent data set has been disaggregated (p30, http://ftepr.org/wp-content/uploads/how-to-do-fieldwork-draft.pdf), and that the research samples were representative of the wider population sample. The data set has been analysed for sex disaggregated correlations between a number of characteristics. Further regression analysis and propensity score matching has been applied to key labour market data. Findings include daily wage rate levels for women and men in each sector. / Target: peer validation of research findings through academic conferences and workshops. This target has been achieved. The research team presented their methodology and an initial research finding at the Research Network session with standards organisations in the ISEAL conference on 11/06/13. The SOAS team reported that the audience was impressed by the methodology, including use of GPS technology to track farmworkers in each survey round of the longitudinal study, and the number of qualitative ‘life histories’ – a relatively large sample (more than 100 work history interviews). Fairtrade International expressed their concern that SOAS had not provided them with an indication of their findings, as a courtesy, before presenting an initial finding that shows a negative correlation between wage levels and certification in Ethiopian flower production sites. In June 2013, the SOAS team co-organised a seminar in Lisbon at the European Conference for African Studies and presented methodology and preliminary findings, which were discussed by academic peers. The research team also held three workshops to report their research findings and test their assumptions with stakeholders in the research countries; one in Uganda (04/11/13) and two in Ethiopia (07 & 08/11/13). One of the Ethiopia workshops was particularly targeted at a government audience. Participants in the Kampala workshop became very engaged in a debate on child labour, which is not an issue that the research can inform systematically (although it was clear at each survey site that children below the age of 15 are engaged in waged work). / The methodology purposively does not include engagement with the standards organisations as part of the implementation process to ensure there was no research partiality, but Fairtrade Foundation and Fairtrade International have been asked to fact-check the draft final report. In the longer term (beyond the lifetime of this project) the research team will also produce articles on their findings for publication in academic journals and other outlets. / Recommendations: / None. Further peer validation, through workshops and conferences will happen beyond the period of this accountable grant. / Impact Weighting (%): 60% Revised since last Annual Review? No / Risk: Low Revised since last Annual Review? No

Output 3: Research results and policy messages disseminated to donors, certification bodies and business
Output 3 score: B (Outputs moderately did not meet expectation)
Performance against target: / Target: implementing research dissemination strategy. This target has not yet been achieved. Dissemination activities are planned when the technical report is finalised. Discussion will be needed between SOAS and DFID to agree appropriate forums and formats for dissemination (e.g. summaries, rather than full reports). As the findings of this research are controversial, more time may be needed to identify and implement dissemination plans, than was originally envisaged in the initial project design. Activities that contribute to preparation for dissemination will be undertaken during the lifetime of this accountable grant, assuming that the fact-checking exercise with stakeholders runs to schedule. These activities include making datasets available publicly, preparing a photograph exhibition and preparing educational materials for use in secondary schools. The Project Completion Review will provide a more complete assessment of achievement by 31/03/14. / Results and messages / There is little doubt that findings from this research will generate debate and, potentially, controversy. Results indicate a strong correlation between certification and lower wage levels than in non-certified production sites. The research team note that, while there were clear differences in wage levels, the great majority of the workers surveyed are low paid. Furthermore, the poorest group in each sample are female manual waged workers with no formal education. They will present some possible causal explanations for findings, and some policy recommendations, in the final report. At this stage, they think that size of enterprise is causally related to wage levels and other conditions of employment; investment in and institutional organisation around higher product quality may be causally related to higher wage levels; and characteristics of workers (sex, age, length of experience) do not explain different wage levels between certified and non-certified producers. In flowers, different forms of certification correlate with different wage levels. However, location specific, idiosyncratic factors are clearly important to variations in wage levels and working conditions across all commodities, research sites and individual employers. / Policy messages from the SOAS research team may include that more infrastructure investment is needed to improve product quality (e.g. coffee washing stations). The research does not provide evidence about the mix of public or private investment, but does suggest that investment in labour intensive, export-oriented sectors is important. Direct labour market regulation may be effective in certain circumstances; however, it is difficult for governments, let alone international certification bodies and their auditors, to enforce such regulations where there are large numbers of small and widely dispersed producers/employers. Change may more effectively be achieved through ‘indirect’ policy areas e.g. public policy on schooling not only benefits children themselves, but also potentially increases wages for adults (through tighter labour markets). There are some specific conclusions for the flower sector in Ethiopia. / Dissemination process / In February 2013, the SOAS team drafted a dissemination strategy (EDRM 3855206) which was discussed by the advisory group. The dissemination strategy provides a scoping of a wide range of dissemination opportunities. It includes analysis of stakeholders at the level of country governments/producers, fair trade practitioners, donors, corporates, campaigners, academia and the general public. The Advisory Group felt that the draft document provided a scoping of a wide range of potential dissemination opportunities and encouraged the SOAS team to prioritise and focus down their planned dissemination activities. Dissemination activities to 31st March 2014 will concentrate on the following areas: taking results back to respondents; further testing of results with peers; and some activities in preparation for future public dissemination (such as preparing a photograph exhibition and educational materials, and making the datasets publicly available). / Recommendations: / DFID officials to continue to ensure appropriate use of DFID funds on dissemination activity up to 31/03/14, and engage the research team in internal dissemination activities such as a brownbag lunch and a photo exhibition within DFID. / Impact Weighting (%): 15% Revised since last Annual Review? No / Risk: Low Revised since last Annual Review? No

Results, cost, risk and value for money

Progress and results
Has the logframe been updated since last review? No. / Overall output score and description: / A (outputs met expectations) / Direct feedback from beneficiaries / The SOAS team are planning to return to research sites in Uganda and Ethiopia to provide feedback on the research findings as part of the dissemination activities to be completed by 31/03/14. / Annual Outcome Assessment / SOAS are on track to complete the programme outcome by the deadline 31/03/14, as long as the fact-checking exercise runs to schedule and the planned dissemination activities are achieved.

Cost and timescale
Is the project on-track against financial forecasts: Yes / Is the project on-track against original timescale: No (see comments about no-cost extensions).

Risk
Output risk rating: Low / Assessment of the risk level / The outputs are considered low risk as the SOAS team have submitted robust papers on their methodological approach and dissemination strategy. Researchers are in regular contact with DFID officials regarding the progress of research and dissemination. / DFID is a committed funder of research, to inform evidence-based policy making. We expect that the findings from supported research may be controversial and generate robust debate. / Climate and environment risk / The SOAS research project is expected to have a low impact on the climate and environment beyond the impact of researchers’ air travel, as the sole outputs are research papers and knowledge transfer activities.

Value for Money
In the context of this project, value for money is best understood in terms of how effective and efficient the project is in delivering its intended results. / Research is one effective way of informing evidence-based decision making. DFID has a strong commitment to commissioning world class research, and ensuring that it is readily available to those who can use it around the world. DFID uses research such as this to inform its own programming on responsible business. / The research team identified weaknesses in existing approaches to study in this field, namely: largely qualitative, case study-based studies that collected data from producers rather than directly from waged or self-employed workers, with weak rationale for selection of study sites and use of inaccurate official household lists and often a lack of adequate research independence. By addressing some of the weaknesses that have characterised earlier approaches, the research team believe that they have developed a mixed methods fieldwork methodology that will be replicable in other research studies focusing on rural development economics research, and in particular in research on labour markets in developing countries. They have contributed to capacity building of local and international researchers by training them in how to apply the methodology. Evidence of this includes the training of enumerators in both Ethiopia and Uganda, and sharing the fieldwork methodology amongst SOAS PhD and MSc students as a learning tool (for example, a seminar for Economics Department and Development Studies Department PhD students in November 2010, two seminars to MSc Economics and MSc Development Studies students on research methods in 2011 and 2012). / A number of efficiencies have also been realised in the project that have improved the value for money of the research. For example, the project team was able to build on a tried and tested approach based on their previous experience of including life histories (‘nested’ in a quantitative survey sample) in rural labour market survey-based research in Mozambique and their many years of experience in designing rural labour market surveys in a number of African and other countries. They drew on research expertise from other disciplines and adopted new technological methods that included the use of GPS and hand-held computers for sampling. This increased the efficiency and significantly reduced the inputting and search costs of large scale data collection and will also potentially increase the value for money of future research. It is expected that the use of easily accessible visual representation of data sampling and collection methods will also add value when demonstrating the impact of the project. See, for example, use of Google maps and Google earth (http://ftepr.org/research-sites/). / The research team also note that the high proportion of time spent in the field increases value for money, as it improves research quality, enables the team to adapt to circumstances and ensure good data collection, and increases the transfer of research skills to local researchers. / The total budget for this project is allocated as follows: / Staff time - £317,222 / Travel - £27,000 / Fieldwork - £193,325 / Other (dissemination) - £41,000 / Contingency - £28,927 / Additional funding (request of Nov/Dec 2010) - £85,484 / DFID reimburses SOAS for expenditure in quarterly arrears, in line with the arrangements set out in the Accountable Grant letter.

Conditionality
Not applicable

Conclusions and actions
The SOAS programme has made strong progress as the research comes to a close, and the research team are on track to achieve the outputs and outcome by the programme deadline of 31/03/14. / The no cost extensions reflect the complexity of the research and findings, and therefore revisions by the research team of their peer review, fact-checking and dissemination approach. / DFID officials will ensure that SOAS develop a dissemination strategy that contributes to the wider body of evidence on the impact of standards systems.

Review process
This review was conducted by staff in PSD’s Business Engagement Hub. / This review draws on the logframe (EDRM 3678809), the 2012 annual review (EDRM 3676705), no cost extension documents (EDRM 3839646, EDRM 4272237), the draft technical report (EDRM 4302463) and the SOAS dissemination strategy (EDRM 3855206).