Annual Review - Summary Sheet

Title: Building Empowerment and Accountability in Malawi (BEAM)
Programme Value: £20,457,729		Review Date: 31/03/2014
Programme Code:	Start Date: 7/12/2010	End Date: 30/06/2016

Summary of Programme Performance
Year	FY 2011	FY 2012	FY 2013	FY 2014
Programme Score	NA	A	A+[1]	A+
Risk Rating	NA	Medium	Medium	Medium
[1] The FY 2013 Annual Review was scored A by the review team, however, according to the Aries calculations the output scores added up to an overall A+.

Summary of progress and lessons learnt since last reviewThis Annual Review covers the fourth and penultimate year of operation of the Building Empowerment and Accountability in Malawi (BEAM) programme. From featuring 14 components in its original design, the programme has gradually been rationalised and was this year able to focus on the three components that deliver the greatest contribution to the BEAM objectives: the Tilitonse civil society governance fund, the Kalondolondo score-carding programme, and the support to Public Financial Management (PFM) reform through the World Bank’s PFM Multi-donor Trust Fund (MDTF).

2014 was a challenging year, and the high risk environment in which BEAM operates has continued to make its mark on the programme. The PFM work has had to negotiate a lack of clarity on the Government of Malawi’s plans for PFM reform following the Cash-gate scandal, and the discovery of a number of instances of fraud in the Tilitonse fund has sharpened the attention on managing fiduciary risk. Despite this, the programme has continued to perform well and is overall on track to meet its targets for next year. As in previous Annual Reviews, it is noticeable that the civil society components of BEAM are producing stronger results than those focused on supporting the Government of Malawi (GoM) to deliver reform. It is also of note that some of the key impact indicators – for instance indicator 1 which measures citizen’s satisfaction with democracy in Malawi – are moving in the wrong direction. This is a sign of the scale of the challenges that BEAM is looking to address, and may suggest a limited ability in BEAM to contribute to change at the macro level, despite its good work.

As the programme is moving closer to its last year of implementation, the focus on learning to inform the future design of DFID Malawi’s empowerment and accountability (E&A) programming has increased. Central lessons revolve around anchoring the work with civil society more firmly in the local context, and the need to underpin PFM reform with efforts to strengthen integrity in public life. A number of reports on different aspects of BEAM’s work have provided useful insights and will feed into the development of BEAM’s successor(s).

Summary of recommendations for the next year
Recommendations covered in more detail below include:
- With one year left of BEAM, DFID should clarify the future design of its E&A programming. Based on the BEAM experience, delivery of different aspects of E&A work through separate programmes that are linked to a shared macro Theory of Change - as opposed to BEAM’s multi-component model – is emerging as a sensible approach.
- DFID should work with BEAM partners to continue improving delivery, in particular by working with the World Bank to improve oversight and accountability for results for the PFM MDTF.
- In light of recent fraud cases, DFID should continue to strengthen anti-fraud measures to safeguard DFID funds.
- DFID should increase efforts to build linkages between stand-alone E&A programming and its sector work, and share learning on E&A through regular engagement between DFID Malawi programme teams and beyond with partners.
- Following the Annual Review, DFID should further revise the BEAM logframe to ensure it is aligned with component logframes and captures key results.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-200469/
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4429218.xlsx

Outline of the programme
The Building Empowerment and Accountability in Malawi (BEAM) programme was launched under a Programme Memorandum in 2010. It combines work on the ’demand side’ of governance - supporting citizen and community based projects that promote better information, monitoring and influencing of Government policies and programmes – with work on the ‘supply side’ – supporting selected Government or quasi-Government institutions to improve service-delivery and increase transparency and accountability. The total UK commitment to BEAM is £20.5 million from 2010 to 2016.

The expected impact of the programme is ‘more accountable, responsive and inclusive governance in Malawi able to support progress on off-track MDGs.’ The outputs are:

1. Civil society fund strengthens local organisations’ ability to promote access to information and monitor and influence policy
2. Government public financial management policies, procedures and practice strengthened
3. Capacity of National Integrity System assessed and civil society and ACB capacity strengthened
4. Civil society community based monitoring strengthened

Since the launch of BEAM in 2010, the context has changed several times. In its first year, the programme operated in an environment of sharply declining governance with President Bingu Wa Mutharika’s government increasingly limiting the independence of accountability institutions and restricting the ability of citizens to exercise rights and freedoms. This changed with Bingu Wa Mutharika’s sudden death in April 2012 and transfer of power to Vice President Joyce Banda. As Head of State, Banda moved quickly to address concerns around economic management, political governance and human rights. Increased space for civil society and more freedom for the media to speak out returned, and relative stability ensued. However, during 2013 Banda’s leadership was increasingly being questioned and her position was weakened by the revelation of grand scale fraud and corruption involving public finances, popularly known as Cash-gate. Malawi held tripartite elections in May 2014 and Peter Mutharika emerged as the winner of the presidential ballot. So far his new government has retained the progress made under Joyce Banda and made a strong commitment to following through on corruption.

BEAM is a portfolio programme bringing together a total of 14 planned components. Some components were in-design at its approval stage, some were short extensions to existing projects, and others were still to be fully defined. Throughout, BEAM has had to adapt to the changing circumstances while staying committed to achieving the overall impact of the programme. By the start of the current annual review period, the BEAM portfolio had been rationalised to concentrate on its three main components:

Component	Description	Contributing to output	Operational dates
Tilitonse	A multi-donor Civil Society Governance Fund (Tilitonse) combined with an Independent Impact Evaluation Agent (IIEA). The fund aims to strengthen civil engagement to support efforts to achieve greater public accountability and faster progress on development outcomes while at the same time contributing to the institutional development of civil society organisations (CSOs). This is a £14,654,267 programme with a DFID contribution of £9,617,857.	1	23/02/2011 – 31/10/2015
Kalondolondo	An Accountable Grant to a consortium of Plan Malawi, CONGOMA and ActionAid for a community based monitoring programme. The purpose is to ensure community participation in planning and budgeting processes at local district and national levels so that plans and budgets are more evidence based and reflective of the real needs of rural service users. The programme is solely funded by DFID with a budget of £2,480,015.	4	01/09/2011 – 31/10/2015
Public Financial & Economic Management (PFM) Reform	Contribution to a World Bank managed PFM Multi-donor Trust Fund (MDTF) supporting the Malawi Government’s Public Financial and Economic Management (PFEM) Reform Plan. The target budget for the PFM MDTF is $40 million and DFID’s contribution is £5,174,000. Contributing to the PFEM RP objectives but outside the MDTF, DFID is also funding a Cash-gate related forensic audit and support with the investigation of the corruption cases, with a total contribution of £976,000.	2	01/07/2011 – 31/03/2016

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome for BEAM is ‘Greater citizen voice and participation in governance with improved management of public resources’. It is measured by four indicators which combine results from the three main BEAM components, as set out in the table below. During the review period the programme’s progress at the outcome level has met expectation on the basis that:
- the milestone for Outcome Indicator 2 was exceeded;
- there has been reasonable progress against the milestone for Outcome Indicator 3: Tilitonse is reporting that by the end of December 201489,700 people had been supported to have choice and control over their own development and hold government to account while Kalondolondo figures are still being clarified; and
- Outcome Indicators 1 and 4 could not be measured at this stage.

	Outcome indicators	Milestone FY 2014	Result FY 2014
1	PEFA scores in priority areas (WB PFM MDTF)	NA - no PEFA assessment	NA – no PEFA assessment till 2015
2	Number of documented cases of influence at national and decentralised levels on government and non-government actors achieved by BEAM programme partners / Tilitonse / Kalondolondo	1. 70 2. 118	1. 804 / 2. 127
3	Number of people supported to have choice and control over their own development and hold government to account (Kalondolondo and Tilitonse)	233,000	89,700 for Tilitonse to the end of December 2014. Kalondolondo figures being clarified.
4	Quality of cooperative activity (Tilitonse) / Extent to which cases demonstrate a strategic approach to partnerships / % age of funded project respondents that say they have a ‘strong’ working relationship with Govt officials / No. of cases that demonstrate improved collaboration between CSO/ citizens, government stakeholder and/or private sector actors	1. Some (ca. 1/2 of cases) / 2. 31 (OC1), 5 (TH), 33 (OC2) / 3. 0	NA – cannot not be measured yet as the Independent Impact Evaluation Agent End-line Survey data is not yet complete

Notes: The very significant uplift in the results for Outcome indicator 2.1. is due to the large number of CBO grants that have come on stream in Tilitonse which were not envisaged when the programme was designed. The milestone and target for this indicator should be brought in line with current expectations. The results for Outcome indicator 2.2 are based on 17 cases of self-help projects, 43 instances where communities have influenced change through demanding fair application of rules governing access to services, 44 instances where CSOs have exerted influence on duty bearers, and 23 instances where resource allocation has changed as influenced by score carding process.

Overall output score and description

The output score of the programme is A+ on the basis that:
- Output 1 with an impact weighting of 40% scored A+
- Output 2 with an impact weighting of 30% scored A
- Output 3 with an impact weighting of 10% scored B; and
- Output 4 with an impact weighting of 20% scored A++

Output 1 ‘Civil society governance fund strengthens local organisations’ ability to promote access to information and monitor and influence policy’ scored A+: The achievement of the milestone for Output indicator 1.1 narrowly missed expectation with Tilitonse grantees developing 146 information products against a target of 150. For Output indicator 1.2, a total of 1,144,820 were informed about their rights to public services, exceeding the milestone of 1,000,000. The achievement for Output indicator 1.3 also exceeded expectation by surpassing the number of representations to duty bearers by 22 against a milestone of 200. For Output indictor 1.4, a total of 12 innovative practices developed by Tilitonse grantees were adopted by other CSOs or agencies outside Tilitonse, against a milestone of 10.

Output 2 ‘Government public financial management policies, accountabilities, procedures and practice strengthened’ scored A: The achievement of the milestone for indicator 2.1 fell short of expectation. While the proposals for legislative changes to strengthen the independence of the National Audit Office have been accepted by the GoM, the legal process is yet to commence and the timing will depend on what other constitutional changes are being scheduled for presentation to Parliament. In terms of indicator 2.2, GoM has increased the level and quality of in-year budget reports and they now also publishes quarterly budget updates on the GoM website. The milestone for indicator 2.3 has been achieved in as much as the GoM in December 2014 made a decision to upgrade or replace the current IFMIS software. However, the sources of funding for the new software have not been agreed and this is holding up the launch of a tender. The milestone for indicator 2.4 was achieved when 53 case files and the final forensic audit report were submitted to the authorities in September 2014. However, the milestone underplays the very significant impact the forensic audit has had in supporting stakeholders inside and outside government to respond to Cash-gate, which pulls up the overall score for this output.

Output 3 ‘Capability of National Integrity System assessed and civil society and ACB capability strengthened’ scored B: This Output was completed in 2013 and the score of B has been transferred from last years’ Annual Review.

Output 4 ‘Civil society community-based monitoring strengthened’ scored A++: During the year 76,770 citizens participated in Kalondolondo score-carding, exceeding the milestone of 35,000 for Output indicator 4.1 by over 100%. In terms of Output indicator 4.2, there have been 67 instances where the allocation of resources has changed as a result of the programme, against a milestone of 42. For output indicator 4.3, 128 agreements have been recorded between service providers and service users to improve service delivery, exceeding the milestone of 100 by 28%.

Key lessons

For the demand-side accountability components of BEAM, we have learned a number of important design related lessons:
- Our programmes are delivering good results at the community level but are less effective in elevating this to advocacy at the national level to achieve policy change. Going forward, there is a need to support a strong national advocacy and mass media approach that builds on evidence gathered at the local level.
- Strengthening voice alone is not enough to achieve accountability. Our programmes need to facilitate the interface between the demand and supply side to be effective and should consider supporting supply side actors to make this happen. As part of this, DFID should consider the role of Parliament and its committees in demanding accountability.
- While still relevant, the Political Economy Analysis approach we have been promoting with our Tilitonse grantees needs to be simplified and made practical through mentoring, and the Theory of Change should be contextualised within the local governance setting and the capacity of CSOs.
- Standardised training is not adequate to address the capacity challenges faced by Tilitonse grantees. The new capacity development strategy which is based on CSOs doing a self-assessment and receiving mentorship over the life of their grant is proving more effective in addressing specific needs of partners, particularly CBOs.
- In our social accountability work with Kalondolondo there is a need to temper community expectations in order to avoid counter-productive frustration. While being supported to demand better service delivery, communities should also be helped to understand the resource limitations of local governments.
- The gap between initial scorecard meetings with district officials and the follow up meetings to assess whether actions plans have been implemented is almost a year. It needs to be reduced so important issues are not lost and communities recall what they had identified and communicated to council officials.
- The coming in of Ward Councillors is changing the advocacy landscape in the districts. Encouraging their participation in community assessments is a quick win to bring the supply side to interface more with the demand side.

PFM related lessons include:
- There are strong links between the issues affecting PFM reforms and civil service reforms. Technical fixing of the computer systems is not sufficient to ensure full implementation of internal controls and checks. For instance, there is evidence that technical assistance in the Accountant General’s office to improve internal controls and checks within the central payment system have resulted in limited behaviour change in the workforce. Linking the PFM reforms closely to the civil service reforms will help deal with the incentive and sanction issues that shape the behaviour of civil servants.
- The Integrated Financial Management Information System (IFMIS) has been at the centre of the Cash-gate scandal. The GoM needs to avoid the pitfalls that characterised the procurement, installation and implementation of the current system by following a rigorous, transparent, credible and systematic process of selecting and rolling-out an upgrade or new software.

Key actions and recommendations

BEAM post 2015/16
After this Annual Review, BEAM is entering into its last year of operation. Its multi-component design has served it well and allowed it to respond flexibly to changes in the context, but the ‘omnibus’ approach has had costs in terms of clarity of design, objectives and reporting. In 2013 DFID’s Internal Audit Department looked at BEAM and noted the challenge of reporting adequately on progress when annual reviews and progress reports for a large number of individual components are amalgamated into a single annual review.

Going forward we recommend dismantling BEAM and instead delivering different aspects of our E&A work through separate programmes which are clearly linked into a shared macro E&A Theory of Change. It is envisaged that there will be a programme supporting supply side reforms encompassing PFM and Public Sector Reform, a separate programme on anti-corruption which may include elements of E&A work, and a programme focused on demand side accountability that will absorb Tilitonse and Kalondolondo which should continue as separate but complementary approaches to support social accountability. Specific recommendations for the future of three current BEAM components include:

1. There is a need to reach a final decision on the options post 2015 for Tilitonse. While there seems to be agreement on an extension of the current programme by both funders and the Board, there is need to clarify the future of the current structures such as the Management Agent and the Independent Impact Evaluation Agent. Fundamentally there is also a need to clarify the purpose of Tilitonse, taking into account the design lessons listed above and evidence coming out of the Independent Impact Evaluation. This is the preserve of both donors and the Board. As Board chair and lead donor, DFID should endeavour to influence speedy conclusion to this issue, with a view to submitting a Business Case for a programme on demand side accountability in June 2015.
2. While Kalondolondo is expected to seek a no cost extension to its existing grant, an early start on the design for the new programme is desirable to ensure coherence across the E&A portfolio and enable proper resourcing. DFID should work with Kalondolondo to carry out an assessment of its future options, building on the design lessons set out above but also learning from other similar programmes such as DFID Ethiopia’s work on social accountability where communities access budgets in their Waredas (Wards) and are able to engage with councils in a meaningful and realistic way.
3. As DFID thinks about how best to support the GoM’s recently published plans for Public Sector Reform, it will be important to ensure strong linkages to the work on PFM for the reasons already set out. A shared programme would facilitate this and is recommended.

Continue to improve the delivery of the current BEAM programme
Coming into its last year, there is still scope to refine the delivery of the three main BEAM components to ensure expected results are achieved. In particular, there are issues relating to the PFM MDTF which need to be addressed:

1. The governance arrangements for the PFM MDTF need to improve. There is a need for more oversight from the World Bank and greater accountability for results. The latter will require better reporting on programme outputs, outcomes and impact, moving away from the current focus on reporting on activities. DFID should work with the World Bank to set out clear performance indicators for the next 12-18 months, linking the achievement of these to our remaining disbursements.
2. DFID should continue to influence the World Bank as MDTF manager to facilitate a national PEFA assessment in Malawi. This will help stakeholders ascertain the state of the public financial management system and practice and update the shared understanding of fiduciary risk. A PEFA assessment is also needed to measure progress for this component at the Outcome level of BEAM.

In the Kalondolondo programme, delivery can be strengthened by:

shortening the gap between the initial scorecard process and the follow-up meetings with District Councils to ensure that action plans agreed between communities and officials are followed up in time and critical issues are dealt with without delay.

Strengthening anti-fraud measures
The last year saw the discovery of a number of fraud cases in Tilitonse, affecting 4 of 73 grants (5%) There were also issues with GoM-led procurement in the PFM MDTF which have been dealt with by not allowing any DFID funds to go through GoM accounts. For the civil society components - although the number of fraud cases is relatively small and their detection demonstrates that the controls are working ‑ the following measures are recommended to further strengthen the response to fraud:

1. The Tilitonse Secretariat should ensure that the Tilitonse Anti-Fraud Policy is disseminated widely, and the launch of the new Whistleblowing Facility should be supported by a strong promotion plan. Simultaneously the Fund should enter into binding agreements with partners to ensure any partners caught up in fraud return misappropriated project funds.
2. As noted in the Tilitonse Due Diligence Assessment report (2015), the Tilitonse Secretariat is stretched and finds it challenging to deliver the support needed to improve grantees’ programme management. Additional staff is required, especially in the finance area, to strengthen scrutiny and deal with fiduciary risks. As the Board Chair and lead donor, DFID should exert its influence to ensure extra human resource is agreed in the April 2015 Board meeting.
3. DFID should consider whether to carry out a Due Diligence Assessment of Kalondolondo to be reassured that its systems and processes provide adequate safeguards against fraud.

Improve learning on E&A and linkages across DFID programmes and beyond
There is work on E&A in many of DFID Malawi’s programmes outside BEAM. This includes the sector programmes as well as those with a more targeted E&A focus such as the Elections Programme. DFID should continue to ensure these programmes are coordinated and share learning through regular engagement between the respective programme teams. This could be done by realising previous ambitions to bring sector advisers together under an Accountability Committee in DFID to share work on accountability issues, including sector work done by BEAM partners and sector programmes. Looking beyond DFID, there is also scope for DFID to facilitate learning among the key external partners engaged in E&A work.

Further revise the BEAM logframe
Following this Annual Review, DFID should further revise the BEAM logframe to:
- bring it in line with any changes to the Tilitonse logframe to be agreed by the Tilitonse Board in April 2015;
- potentially relate indicators and milestones for the PFM component more closely to the new PFM Action Plan
- capture the results of the new Cash-gate related technical assistance by the International Centre for Asset Recovery (ICAR) to the Anti-corruption Bureau (ACB) and Director of Public Prosecution (DPP) through BEAM’s PFM component; and
- clarify targets for FY 2015/16 for the Kalondolondo component.

Has the logframe been updated since the last review?
The BEAM logframe was updated in November 2014 to reflect changes in the programme context as recorded in Quest document number 4842229. The revised logframe was approved by DFID Malawi’s Head of Office on 5 January 2015 and has been used for the scoring of results in this annual review.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Civil society governance fund strengthens local organisations’ ability to promote access to information and monitor and influence policy (Tilitonse)
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones for 2014	Results
Number of information products developed in funded projects	150	146
Number of people informed through funded projects about their rights to public services	Men - 500,000 Women - 500,000 Total – 1,000,000	Men - 457,928 Women - 686,892 / Total – 1,144,820
Number of representations based on monitoring initiatives made to traditional leaders, officials responsible for public service delivery, MPs.	200	222
Number of practices and issues promoted by CSO grant partners that are adopted by other CSOs and development actors	10	12

Key Points
The achievement of the milestone for Output indicator 1.1 narrowly missed expectation. Over the year, grantees from Open Call 1, Open Call 2 and Thematic Call projects developed 146 information products. The failure to meet the target was due to the late submission of data by grantees from the CBOs Call. This data is expected by the end of March 2015.

Output indicator 1.2 is a headcount measure of the number of people informed through funded projects about their rights to public services. During the year, 1,144,820 people were reached, exceeding the milestone of 1,000,000. The majority accessed information through radio programs (Zodiak, Maziko and MIJ), the FUKO newspaper and by attending community meetings and other outreach programmes.

Output indicator 1.3 counts the number of representations based on monitoring initiatives made to traditional leaders, officials responsible for public service delivery and MPs. This year there has been 222 representations, exceeding the expectation for the milestone by 11%.

Output 1.4 measures innovative practices by funded partners that are adopted by other CSOs or agencies outside Tilitonse. This year recorded 12 innovative practices, surpassing the milestone by 2. For instance, NICE has adopted CCJP’s formation of District Multi-stakeholder dialogue committees in Thyolo, and the Forum for African Women Educationalists in Malawi (FAWEMA), the District Education Network (DEN) and the Youth Network and Counselling Organisation have replicated World Vison’s Citizen, Voice and Action concept.

Summary of responses to issues raised in previous annual reviews (where relevant)
Last year’s Annual Review highlighted concerns from donors over the administration burden Tilitonse places on them, despite the outsourced management arrangements. There was also a concern that the Board set-up does not offer donors sufficient voice and decision power. Both issues are still being discussed and there is agreement to change the Board set-up in the next phase of the programme.

The review also noted that the results captured in the Tilitonse logframe focus on the local rather than the national level. It recommended a better mechanism for capturing results at the national level to ensure that progress at that level is clear. The revised Tilitonse logframe, which has received approval at sub-committee stage and is expected to be approved by the Tilitonse Board meeting in April, combines national level and local level results, leaving a need to ensure that national level results can be extracted separately from the Grants Management Information System (GMIS) for results monitoring and lesson learning purposes before the Impact Evaluation is finalised and published.

Recommendations
- At the forthcoming Board meeting in April 2015, the Tilitonse programme logframe should be formally approved to ensure that all parties use a version that has the support of the Board. Following this, the BEAM logframe should be revisited and adjusted accordingly. This will include a revision of the milestones and target for BEAM Outcome indicator 2.1, as discussed in the Annual Outcome Assessment section of this review.
- As part of the Board discussions on the logframe, DFID should explore how national level results for Tilitonse are documented on the GMIS and how examples of influence at this level can be disseminated lesson sharing sessions.
- To guard further against fraud, the Tilitonse Secretariat should disseminate and promote the Tilitonse Anti-Fraud Policy and the new Whistleblowing Facility. Partners should be asked to enter into binding agreements to ensure that anyone caught up in fraud returns misappropriated project funds. As the Board Chair and lead donor, DFID should exert its influence to ensure extra human resources for the Tilitonse Secretariat to boost its ability to manage fiduciary risk.

Output Title	Government public financial management policies, accountability, procedures and practice strengthened
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones for 2014	Results
Independence of the National Audit Office	Approval of full range of legislative proposals for an independent NAO	Legislative proposals have been accepted by GoM but the legal process is yet to commence
Quality and timeliness of in-year budget reports	Reports published and accessible for the public	Budget reports and updates are published on the GoM website
IFMIS roll-out and update	Clear GoM decision and process for upgrading or/and replacement of the current IFMIS software	By the end of 2014, the GoM made a decision to tender for a software upgrade or replacement of the current EPICOR software. The decision is subject to the confirmation of funding.
Scale and nature of Cash-gate fraud and corruption established (covering April to September 2013)	Submission of final forensic audit report and 53 case files (cumulative) handed over to investigation agencies	53 case files and the final forensic audit report were submitted to the authorities in September 2014.

Key Points
The GoM faces significant challenges in reforming both its public financial management and accountability systems and the civil service administration. In principle and on paper, the new GoM of Peter Mutharika has committed itself to a twin programme of tackling both. To address the PFM part, it has received technical assistance from the International Monitory Fund (IMF) and other Development Partners to set out the Action Plan on PFM, building on previous assessments and all current and past reform actions with a view to bringing all stakeholders together under one clear framework with GoM leadership. Agreeing this plan, however, has taken considerable time and was only achieved by the end of February 2015. For the majority of the review period, this left the PFM MDTF with a degree of unclarity on the way forward which has made planning a challenge. The Action Plan runs till June 2015 but provides opportunities to be scaled up to longer-term PFM reforms. A number of the actions in the plan are already underway but coordination and systematic monitoring of progress remains a challenge. There is also a need for further clarity on how to manage the interface between the Action Plan and the PFM MDTF.

The PFM component of BEAM has had to navigate these challenging circumstances and performance across the output has been mixed. As for the indicators measuring progress for the PFM MDTF (2.1, 2.2, 2.3), the technical work has been done but the achievement of the milestones has been affected by the GoM’s ability to use the technical input to deliver change. On the other hand, the direct support to the Cash-gate effort in the form of the forensic audit (indicator 2.4), has been a low cost, high quality and high impact intervention which has provided evidence for stakeholders inside and outside government on which to base decisions on their response to the corruption scandal. Taken in isolation, the PFM MDTF work would have scored a B. However, in a year where the focus was firmly on dealing with Cash-gate, the high impact of the forensic audit pulls up the overall score for the output to an A.

More detail on progress against Output 2 indicators:

The achievement of the milestone for indicator 2.1 fell short of expectation. The proposals for strengthening the independence of the National Audit Office have been accepted by the GoM and the Cabinet Paper for amending the law is ready, awaiting the legal process to begin. Because some of the proposals require constitutional changes, the timing of approval will depend on what other constitutional amendments are proposed.

The milestone for indicators 2.2 a was successfully met and the quality of the information has exceeded expectations. GoM has worked hard to increase the level and quality of in-year budget reports and they now also publish quarterly budget updates on the GoM website for citizens, civil society and professional bodies to access in an easy and timely fashion.

The milestone for indicator 2.3 has been achieved in as much as the GoM in December 2014 finally made a decision to upgrade or replace the current IFMIS software. This was done with MDTF support to develop business process requirements. GoM launched a limited tender in January, then withdrew it, and is currently planning an international competitive tender. However, the sources of funding for the new software have not yet been agreed and this is holding up the re-launch of the tender, all of which is illustrative of the circuitous route the decision on IFMIS and its implementation has taken since Cash-gate. Meanwhile, although the decision to upgrade or replace the current software provides a degree of clarity on the future of IFMIS, the state of the current EPICOR remains an issue. There is need for remedial actions to patch weaknesses and improve its connectivity to ensure it remains operational until an upgrade or replacement is fully rolled out. GoM has established a committee to oversee this work and a work plan has been developed to keep the current system running.

The milestone for indicator 2.4 was met when 53 case files and the final forensic audit report were submitted to the authorities in September 2014. However, the achievement of the milestone does not fully capture the very high impact this work has had. The forensic audit report has become the most authoritative source of data about the Cash-gate scandal and is being cited by both GoM, its prosecution arms, Parliament and Donors as a basis for demanding accountability and justice for those involved.

Summary of responses to issues raised in previous annual reviews
In the 2013 annual review, DFID undertook to lobby for the World Bank to move their PFM specialist from his base in Zambia to Malawi in order to deal with the day to day interactions with the GoM. Working with other Development Partners, this was successfully achieved with effect from July 2014. Having a real time trouble shooting resource available in-country has helped a great deal in moving the programme forward and timely reports are now being produced.

Recommendations
- In February 2015, the GoM published its plans for Public Service Reform which have a strong link to PFM. DFID will work alongside other Development Partners in influencing the direction and quality of the reforms, ensuring there is complementarity between the two reform areas.
- DFID will influence the World Bank as the MDTF manager to facilitate the commissioning of a national PEFA assessment or equivalent in Malawi in order to ascertain the state of the public financial management system and practice. This will update our understanding of fiduciary risk since the last PEFA assessment in 2011 and the DFID Fiduciary Risk Assessment in 2012, both of which concluded that the level of fiduciary risk was substantial. The PEFA assessment is also the basis for measuring progress on PFM at the outcome level of BEAM.
- The governance arrangements for the PFM MDTF need to improve. There is a need for more oversight and greater accountability for the GoM Programme Implementation Unit, and donors contributing to the MDTF should play a more active role in supervising the World Bank. More and better reporting on programme outputs, outcomes and impact is needed, moving away from the current focus on reporting on activities. DFID will work with the World Bank to set out clear output and outcome indicators for the next 12-18 months, linking the achievement of these to our remaining disbursements.
- With the agreement of the PFM Action Plan, DFID should consider whether indicators and milestones for Output 2 should be revised to bring them more line with expectations in the new plan.
- In December 2014 DFID agreed to fund the International Centre for Asset Recovery (ICAR) through BEAM’s PFM component to provide technical assistance to the ACB and DPP on the Cash-gate investigations. Following this Annual Review, the BEAM logframe should be revised to include an indicator capturing the results of this work.

Title	Capability of National Integrity System assessed and civil society and ACB capability strengthened
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target (by end of 2013 Annual Review period)	Results
National Integrity System Assessment	Assessment completed and results disseminated with key actions agreed by the National Integrity Committee (NIC)	Assessment completed and report launched in November 2013. Agreement of the key actions by the NlC was still to be reached.
Civil Society Platform	Platform operational with transparent governance structures and membership	Terms of Reference and membership agreed and steering committee constituted by end of 2012. Platform operational since then.
ACB project implementation	ACB programme completed with 90% of key objectives met	2 of the 8 key objectives completed, representing 25%. However, most objectives that had not been completed had gone beyond 50% of what was expected.

Key Points
The two components which contribute to this output – the National Integrity System (NIS) Project and the Support to Anti-Corruption Bureau (ACB) – were both completed by the end of the 2013 Annual Review with a final score of B. As the output carries an impact weighting of 10% in the BEAM logframe, the score has been carried over to this year’s Annual Review. The results are reproduced for reference only.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2012 Annual Review recommended finalising the anti-corruption work within BEAM and instead developing a new Business Case to house DFID Malawi’s work on anti-corruption and integrity. The 2013 Annual Review noted the need to build findings from an external review of the ACB funding and lessons from Cash-gate scandal into the design of this new programme. The external review of the ACB funding will report in March 2015 and work is now underway to develop a Business Case with a view to agreeing the new anti-corruption programme in July 2015.

Recommendations
None for the current review period

Output Title	Civil society community-based monitoring strengthened
Output number per LF		4	Output Score	A++
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Results
Number of people participating in score-carding	35,000	76,770
Number of instances where the allocation of resources within district and sector budgets has changed as a result of the score-carding process	42	67
Number of agreements between service providers and communities to jointly improve service delivery	100	128

Key Points
The achievement of the milestone for Output indicator 4.1 exceeds expectation by over 100%. During the year 76,770 citizens have participated in the score-carding process and received information about their entitlements against a milestone of 35,000. Increased visibility and communication on the programme through ‘Kalondolondo Corner’ in the Nation Newspaper and on Times Television has helped get more people interested in the programme. The demonstration of results and increased responsiveness of service providers to the needs of rural citizens has also helped improve participation.

Output indicator 4.2 measures instances where the allocation of resources has changed as a result of the programme. This year has seen 67 of such instances, exceeding the milestone of 42. For example, thanks to Kalondolono, in Nkhotakota district 70 bags of cement were provided to Kauye and Mwalawatongole primary schools to complete Local Development Fund (LDF) teachers’ houses which stalled in 2011. The allocation of 310 solar sets by the Ministry of Energy to CHAM and government hospitals also represents a change in allocation of resources that was influenced by the programme.

For Output indicator 4.3, there have been 128 agreements recorded between service providers and service users to improve service delivery, exceeding the milestone of 100 agreements by 28%. These range from agreements between citizens and councils to follow a more inclusive and transparent procurement processes for LDF projects, to commitments to deal with issues of ghost workers in 18 districts and the formulation of bye-laws in 4 districts to guide girls’ education for self-boarders. There has also been agreement to resolve the 2013 suspension of FISP beneficiaries in the Mzuzu peri-urban district, resulting in 1000 peri-urban poor people now benefitting from FISP.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2013 Annual review noted the difficult relationship between District Councils and the Kalondolondo project which affected information sharing. As a result of efforts by Kalondolondo to explain the value of community service delivery assessments, this has changed and there is now a lot of demand from councils for Kalondolondo to facilitate service delivery assessments.
The last Annual Review also recommended that a third indicator be added to Output 4 to ensure Kalondolondo results were adequately covered in the BEAM logframe. As a result, Output indicator 4.3 was added in the last BEAM logframe revision.

Recommendations
- The Kalondolondo programme should shorten the gap between the initial scorecard process and the follow-up meeting with District Councils to ensure that action plans agreed between communities and officials are followed up in time and critical issues are dealt with without delay.
- DFID should consider whether to carry out a Due Diligence Assessment on Kalondolondo to get reassurance that the programme has the necessary structures and procedures in place to guard against mismanagement of funds.
- The BEAM logframe contains no milestones and targets for FY 2015 for Kalondolondo yet Kalondolondo’s work continues to October 2015. DFID should work with Kalondolondo to clarify expectations for next year and revise the BEAM logframe accordingly.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The annual financial targets for the three BEAM components are back on track following a period of stagnation with the PFM MDTF. The expenditure rate for this component started out in slower pace than anticipated, largely due to lengthy World Bank procurement processes and the weak capacity of the Government’s PFM Project Management Unit (PMU). Since November 2013 this was compounded by the freezing of all funding though government systems as a result of Cash-gate, which affected DFID’s ability to make payments to the PFM MDTF. Meanwhile some of the funds originally planned for the PFM MDTF were reallocated to support Cash-gate related activities that were aligned with the PFM MDTF’s objectives. These took the form of a forensic audit and technical assistance to the Malawian investigation agencies. In October 2014 the World Bank was finally in a position to confirm that no DFID funds would be paid though GoM accounts but instead exclusively be used to pay suppliers directly by World Bank from its Washington account. This has facilitated the resumption of payments to the PFM MDTF and all BEAM components are now in line with originally anticipated expenditure.

As the BEAM programme is based on a Programme Memorandum and not a Business Case, specific cost drivers were not identified and therefore cannot be assessed. However, the following items have accounted for the majority of the expenditure:

Tilitonse:	Grant funding to sub-grantees
Kalondolondo:	Implementation of score-cards, including capacity building of subgrantees and hosting of interface meetings after assessment
PFM MDTF:	Procurement of IT hardware and software

VfM performance compared to the original VfM proposition in the business case
The BEAM programme was designed and approved prior to the introduction of the business case format and therefore has no established VfM metrics.

Assessment of whether the programme continues to represent value for money
Although the BEAM design lacks VfM metrics, considerable effort is put into ensuring the programme delivers value for money. In its original design, the programme was envisaged to comprise 14 components which would all contribute to increasing empowerment and accountability in Malawi in different ways. While this provided flexibility, the administrative burden and impact on the clarity of delivery were considerable. Coming into the current review period, the portfolio has been rationalised to focus on the three main components that deliver the greatest contribution to the BEAM objectives. Below are some of the key VfM considerations for individual components.
As the lead donor for Tilitonse, DFID is leveraging funds worth £5 million from other donors[2] with its £9.6m investment. The fund manager was recruited using the OJEU process with financial criteria increased to emphasise the desire to see good value for money, and the competitive grant making process allows the fund to ‘test the market’ and select those partners that are best placed to deliver results and value for money. However, in its 2013 report on DFID’s programming on Empowerment and Accountability,[3] ICAI questioned whether the desire to control cost and reap the benefits of economies of scale with a large programme impacts negatively on effectiveness because of the need for standardised procedures and the limited scope for individualised support to grantees. Although asked to consider value for money, the Tilitonse Mid-term Review (MTR), which followed ICAI’s report, was not able to draw any firm conclusions on these points.
[2] Irish Aid contributes £1,816,985 and the Royal Norwegian Embassy £3,219,425.
[3] http://icai.independent.gov.uk/2013/10/11/independent-commission-for-aid-impact-publishes-report-on-dfids-empowerment-and-accountability-programming-in-ghana-and-malawi/
Kalondolondo has been set up on the basis of a direct grant to a consortium of established CSOs who in turn operate through local CSOs who receive small sub-grants on a non-competitive basis. In the same report referred to above, ICAI notes that Kalondolondo has delivered some significant development impact for modest expenditure and suggests that the Kalondolondo delivery model may provide better value for money than competitive grant-making for local interventions.
DFID was the first donor to contribute to the PFM MDTF and has helped mobilise approximately £8 million from other donors.[4] Beyond that, the delivery of value for money in the PFM MDTF is largely dependent on World Bank procurement procedures and the institution’s ability to provide oversight for performance in the PFM reform process. A concern raised by DFID and other donor partners with the latter has resulted in the World Bank recruiting an in-country PFM specialist. There continues to be scope for improvement, including on procurement where DFID would like to play a greater role in the sign-off process.
[4] The EU contributes EUR 7m, Germany EUR 0.4m, Irish Aid EUR 0.5m and the Norwegian Embassy NOK 15m.

Quality of financial management
During the review period DFID has continued to work with BEAM implementing partners to strengthen financial management. The discovery of a number of fraud cases in the Tilitonse component has been the main cause for concern in the portfolio. To get reassurance on the quality of the Tilitonse Secretariat’s financial management of down-stream partners, donor partners collectively carried out a Due Diligence Assessment (DDA) in November 2014. The DDA confirmed that the Tiliitonse Secretariat has good systems in place for financial management of downstream partners but lacks the resource to undertake the frequency of financial monitoring required given the risk profile of many grantees. To address this, DFID will work through the Tilitonse Board to agree additional staff for the Secretariat’s accounts section.

Date of last narrative financial report	Tilitonse: Report for January 2015 / Kalondolondo: Report for the quarter ending 31/12/2014 / WB MDTF: Report for the quarter ending 31/12/2014
Date of last audited annual statement	Tilitonse: March 2014 / Kalondolondo: August 2014 / WB MDTF: December 2014

E: RISK (½ page)

Overall risk rating
The overall risk rating for BEAM is at the high end of medium.

Overview of programme risk
During the review period the overall risk level for BEAM has remained unchanged, however, there has been changes within individual components and some risks have materialised and become issues the team is now managing.

In terms of the civil society components, the arrival of a new government has not seen an impact on the space for engagement as could have been feared, and political risks remain medium. On delivery, risks associated with managing a funding gap in Tilitonse have been removed with the formal agreement by donor partners to provide additional funding. There continues to be a risk that the investment required in managing donor and Board relationships takes the focus away from delivery on the ground, although the risk remains low. The single biggest issue has been the discovery of 4 instances of fraud among Tilitonse grantees, in itself a result of proactive risk management and increased controls by the Tilitonse Secretariat. The discovery of irregularities also poses a reputational risk for DFID which is being managed by clearly demonstrating a zero tolerance for fraud and corruption.

On the PFM work, there have been risks arising from the time it has taken Government to agree a PFM Action Plan. The lack of clarity on the way forward during the majority of the review period has made it challenging to plan the implementation of activities in support of the reforms, and without a strategic and technical framework it has been difficult for donor partners to engage. The agreement of a PFM Action Plan in February is welcome step forward but there are risks around coordination and monitoring of implementation which will need to be monitored. On partner delivery, the World Bank MDTF has improved its level of oversight with the arrival of a PFM expert who is based in-country, but risks associated with inadequate accountability for delivery of results remains and issue that the DFID team is addressing.

Outstanding actions from risk assessment
There is a need to continuously monitor government and civil society relations and use political influence and funding to ensure the civil society voice is heard. Further instances of fraud in our civil society funding may be uncovered as the controls are further tightened. At the same time the discovery of fraud cases and our firm response sends a strong signal to grantees of our zero tolerance for fraud and corruption that we need to continue to reinforce. On PFM, we will need to maintain our effort to support government decisions on reforms and priorities in a positive direction and work with the World Bank to develop a strong results framework to facilitate our continued collaboration.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Tilitonse and Kalondolondo are on track to deliver against the agreed timeframe and both components will finish in October 2015. After its approval in 2012, the PFM MTDF was slow to start up and its first project only went live in March 2013. The weak performance of the Programme Implementation Unit has been compounded by lack of clarity on planning as a result of Cash-gate. The Government has recently asked for a two-year extension of the arrangements with the PFM MDTF, taking it to July 2018, which has been granted by the World Bank. DFID has clarified to the World Bank that under our current arrangement, DFID financial support will come to an end in March 2016.

Performance of partnerships
The Tilitonse and Kalondolondo partnerships are performing well. As the lead donor for Tilitonse, it can occasionally be a challenge to negotiate the conflicting interests that can play out amongst the donor partners. We are working proactively to strengthen donor relationships to ensure that efforts to reach consensus on the management of the fund do not have an adverse effect on delivery. On the PFM MDTF, the arrival of a Malawi-based PFM expert has had a positive impact on the World Bank’s oversight of the project but there is further scope for improvement. DFID is working proactively with other donors partners demand better accountability for delivery of results.

Asset monitoring and control
DFID maintains registers of assets purchased by BEAM implementing partners who in turn are responsible monitoring assets purchased by down-stream partners. With the exception of the PFM MDTF, capital investment is modest. During the first half of the review period, the BEAM team was stretched on programme management resources and this has impacted on the ability to carry out systematic asset spot checks. As a new dedicated BEAM programme manager gets upskilled, this aspect of monitoring and control will be strengthened and physical asset checks will be carried out on all components by June 2015.

G: CONDITIONALITY (½ page)

In November 2013, DFID froze all funding thorough the Government of Malawi’s systems and there is currently no financial aid provided through any of the BEAM components. The World Bank has formally agreed that no DFID funds will be disbursed through GoM accounts, even though the PFM MDTF arrangements in principle allow for this. On this basis, the use of the Partnership Principles does not apply in the detailed management and monitoring of any part of the BEAM programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
There is no evaluation planned for the BEAM programme as a whole, largely because the numerous components included in BEAM since its inception would make it challenging to provide a single, coherent assessment of achievement. An impact evaluation has been contracted for the Tilitonse Fund and is carried out on an on-going basis by an Independent Impact Evaluation Agent (ITAD). It is on track to produce an impact evaluation in 2015.
In response to the 2013 ICAI review of DFID’s E&A programming, DFID’s Policy Division has updated the global theory of change (ToC) and evidence summary on E&A. Although the evidence base for this ToC is still moderate to limited depending on the type of accountability (political, social or economic), it is growing and will be fed by evaluation of the work of Tilitonse.

The 2013 ICAI E&A Review, the 2013 Tilitonse MTR and the 2014 Tilitonse Options Study have all provided evidence about the strengths and weaknesses of the Tilitonse design. A common observation is that the management structure is confusing and affects speedy decisions. The Political Economy Analysis and Theory of Change are seen as academic and need to be contextualised within the local governance setting and the capacity of CSOs. All reports, however, note that Tilitonse is achieving meaningful results, especially at the local level, but needs to strengthen the collection of evidence of its national and policy level impact. Many of these findings are being addressed, and the post 2015 design will be further guided by this body of evidence.

Similarly, both the 2013 ICAI E&A Review and the 2013 Kalondolondo MTR have provided important evidence relating to the effectiveness of the Kalondolondo programme and its overall direction. The ICAI report observed a number of strong design features such as teaching communities that government services and development projects are an entitlement, generating knowledge of government programmes and processes, and helping communities to identify and resolve barriers in the delivery of particular services. The MTR noted that Kalondolondo has improved service delivery as a result of duty bearers now knowing that if they misappropriate resources meant for public service delivery, they will at some point be held answerable. However, the MTR also questioned Kalondolondo’s relationship with duty bearers who have been suspicious about the programme’s intensions and reluctant to give out information for fear that it will be used against them. Kalondolondo has worked to explain the programme benefits and there is change of attitude and greater cooperation.
On PFM and specifically related to the Malawi context, the DFID funded forensic audit report has provided the single most comprehensive evidence of the extent to which the PFM system failed during the Cash-gate scandal. It provided evidence of inadequately installed computer systems, widespread collusion among the people trusted with controls and those operating the system. The audit report has become a key source of evidence for public prosecutions and related trials of those responsible for fraud and corruption in the GoM. Further to that, the EU funded technical assistance in the Accountant General’s Office provided evidence of weak managerial oversight and reluctance to enforce existing control systems. The World Bank quarterly supervision missions provided evidence of where the GoM was making progress and where more needs to be done to address PFM inadequacies. The IMF mission reports and related Technical Assessments provided systematic scoping of the PFM reforms needed and the sequencing options. In the next 12-18 months, DFID will work alongside other development partners to measure the changes that are occurring as a result of the reforms and technical assistance provided. Part of this evidence will be linked to a proposed new PEFA assessment.

Monitoring progress throughout the review period
The DFID team working on BEAM monitors partners through rigorous scrutiny of reports submitted on finances and activities. This information is triangulated through field visits and meetings with stakeholders to double check on what partners have reported. The team holds regular meetings with each partner to look into programme and corporate issues. These meetings are complemented through the governance structures put in place for each component. For instance, the Tilitonse set-up comprises a Board with donor and non-donor representation which reviews the funds’ progress on a quarterly basis with input from three sub-committees (the Grants Committee, the Research, Monitoring and Evaluation Committee, and the Audit and Finance Committee), all of which have DFID representation. Monitoring of progress on the PFEM Reform Plan which is supported by the PFM MDTF is elevated from the technical level in the meetings of the Group on Finance and Economic Management (GFEM) which brings together Heads of Cooperation with the Minister of Finance and his senior civil servants.

This review was carried out by members of the Governance and Security Team with the input and close collaboration of the BEAM programme partners. The process has included individual reviews of the three BEAM components which were operational between April 2014 and March 2015. These combined a review of project documentation and input from project partners with field visits and interviews with grantees and beneficiaries conducted mainly in December 2014 and January 2015. In addition, the Annual Review has drawn on:

- The Tilitonse Mid-term Review (2014)
- The Tilitonse Options Study (2014)
- ICAI’s review of ‘DFID’s Empowerment and Accountability Programming in Ghana and Malawi’ (2013)
- An Internal Audit of BEAM carried out by DFID’s Internal Audit Department in November and December 2013

The Annual Review was peer-reviewed by the DFID Results Adviser and colleagues from other DFID Malawi teams before being submitted for approval by DFID Malawi’s Head of Office.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process