Type of Review: Project Completion Review

Project Title: Improving the effectiveness of the delivery of humanitarian programmes in South Sudan (project ID: 202301)

Date started: 01/04/2011	Date review undertaken: 15/08/2013 & updated December 2013

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
DFID provided a contribution of £7,025,464 to RedR to improve the effectiveness of delivery of the humanitarian programming in Sudan and the Republic of South Sudan over the period April 2011 to December 2013.[1] The allocation made for South Sudan was £3,211,253, which reduced to £3,098,887 by the final no cost extension to the grant in 2013. / The project was initially conceived and implemented across Sudan prior to the South voting for autonomy and forming the Republic of South Sudan. In March 2012 it was agreed that the programme should be split between Sudan and South Sudan.[2] This project completion review is for the South Sudan project only.
[1] This includes two no-cost extensions
[2] See Submission: Improving the Effectiveness of Delivery of the Humanitarian Programme (RedR): Split of the Programme between DFID Sudan and DFID South Sudan, 13 March 2012.

What were the expected results?
It was expected that the project would improve humanitarian assistance and protection for populations in South Sudan by enabling humanitarian organisations to operate effectively and safely. This was to be achieved through preparing staff and agencies to identify, mitigate and effectively manage risks linked to their work by improving the skills and knowledge of relief workers to ensure they have the right competencies to address the needs of humanitarian response and recovery programmes. It was expected that the intervention would contribute to UK government priorities in responding to humanitarian disasters and focus on building the skills of humanitarian workers and organisations to be able respond to the humanitarian needs of populations affected by conflict-driven crises in Darfur and Southern Sudan. There was a concern that continued delivery of humanitarian assistance would be difficult in many parts of Sudan and South Sudan without this type of project.

What was the context in which UK support was provided?
Context at project commencement / At the time the project was conceived, South Sudan was facing a dynamic humanitarian situation at the same time as undergoing major political change. Continuing inter-tribal conflict was exacerbated by poor development of rural and urban areas and significantly degraded infrastructure following the conflict with northern Sudanese states and continuing raids by the Lords’ Resistance Army (LRA). / In all, an estimated 87,800 southern Sudanese had fled their homes as a result of LRA attacks since late 2008. Displaced communities had sought refuge in larger towns, including Juba, but faced regular demolitions, eviction and destruction of cultivated lands. Over 90% of the population lived on less than $1 per day. The outskirts of Juba were overcrowded, posing serious health and sanitation risks such as cholera outbreaks. Levels of insecurity were high, with many households reporting they were fearful of leaving their houses at night. Assessments indicated that the outlying residential areas of Juba city were more violent than during the war and were too insecure for cultivation. / Changes in the situation during 2012 and 2013 / Since the project started, much has changed in South Sudan, but there have continued to be significant humanitarian needs. As of June 2013, up to 4.5 million people needed basic humanitarian services. of these, an estimated 4.1 million people were food-insecure, down from the original estimate of 4.6 million at the beginning of the year. One million people were expected to remain severely food-insecure.[3] / The refugee flows from Blue Nile and South Kordofan that escalated in 2012 have continued albeit in much lower numbers in 2013, moving the refugee operation from a crisis to a more stable situation. Despite this the caseload continues to be vulnerable, particularly those accommodated in Unity State. Internal insecurity has continued to cause displacements and deaths; Jonglei has remained the centre of violence where fighting continues to displace communities. / At the time of the completion of this review the situation in South Sudan had deteriorated significantly following the conflict which broke out after 15 December 2013. Around 865,000 people have been displaced, some 740,000 of them within South Sudan, and 123,000 to neighbouring countries. It is estimated that 7 million of South Sudan’s 11.5 million population – nearly two-thirds – have been put at risk.
[3] Source: OCHA (2013) South Sudan Consolidated Appeal: Mid-term review

## Section A: Detailed Output Scoring

Output 1: Filling of Critical Gaps in skills needed to respond to the humanitarian crises in South Sudan are addressed
Output 1: final score and performance description: / A+ - Output moderately exceeded expectation / Final Results: / Overall, sound progress has been made in achieving and, in some cases, exceeding the RedR project indicators. This is particularly true of the quantity of training delivered the indicator for which has been exceeded by over 50%. These results are supported by consistently good feedback, which over the entire project term has exceeded the indicator set (90%), reaching on average 91% at project completion. This suggests that there is both a demand for the training courses offered (albeit some more than others) and satisfaction with the content and approach taken by RedR. / Indicator Target Achieved end-June 13 Achieved at project close / 1. Learning Needs Assessment undertaken annually and used to develop training 2 2 2 / 2. Number of participant training days disaggregated by sex, nationality and organisation type 4,500 6,333 6,710[4] / 3. % of participants indicating a significant improvement in skills, knowledge or confidence immediately after the training event 90 87 91[5] / Indicator 1: Learning Needs Assessment (LNA) / Two learning needs assessments have been undertaken since the project was launched in 2011. The first was conducted in April 2011 to provide a baseline and the second was undertaken in December 2012. The reflections of the RedR team were that participation in the exercise and the quality of the analysis has understandably improved over time (83 organisations participated in the second LNA). / Issues of note arising from the most recent Assessment include the following;[6] / Juba was the favoured training location. Despite the focus on moving the locus of training to field locations in recent months, 90% of the respondents indicated that Juba was their favoured location for training (only 57% of the agencies that responded had activities in Juba). / Satisfaction levels with RedR’s services are extremely high. Of those participating 92% had prior knowledge of RedR and over half of international NGO respondents and a third of national NGO respondents had sent their staff for training courses. Of these, over 90% were satisfied or very satisfied with the training provided. Over three-quarters said that as a consequence they had seen an improvement in staff skills, policies, procedures or staff working practices. / Despite logistics and staff welfare training courses being the most poorly attended/having the least demand, the courses were considered by the LNA participants to be where the greatest skills gap exists (78% and 80% respectively). / Organisational capacity in terms of budget provision and qualified staff emerged as a constraint for all agencies that responded in meeting training and learning needs for their humanitarian staff. While over 70% of international NGOs has a budget for staff training, only 18% of national NGOs had access to financial resources and as a consequence, 90% of national NGOs considered costs as the biggest constraint to staff development (for international NGOs time was the biggest constraint with over 70% of agencies highlighting this). / The LNA showed that over three-quarters of International NGOs saw an improvement in staff skills, policies, procedures or working practices as a direct result of RedR training, while 100% of National NGOs reported an improvement. Specific improvements were noted in the following areas: / The quality of staff reporting; / management of staff and staff performance; / improvements in organisational security, communication around security and staff confidence in working in insecure environments; / management of stress and support for staff affected by trauma; / overall planning of humanitarian projects, and; / integration of humanitarian principles in project design and implementation. / Indicator 2: Training Courses / RedR initially offered four core training courses on a three-month calendar which included (i) Logistics and transport (ii) Staff welfare (iii) Staff safety and security, and (iv) Humanitarian principles and practice. While these have had significant uptake, it took time for RedR to become established in South Sudan as they had to set up the operation at the same time as marketing their training products. After the set-up, there was a period during which training courses were confined to Juba which proved successful as there was considerable demand, but interest has waned somewhat over time and so RedR has increasingly moved to offering tailored courses to meet organisations’ needs in the field. These have become more popular as agencies knowledge of RedR’s capacity and performance as a training provider has grown. New and bespoke courses have included needs assessments in emergencies, disaster risk reduction, hostile environment first Aid and team building in a humanitarian environment (see table below) / Courses conducted per subject area (by end-Nov 2013) / Courses conducted by RedR/number No. of courses / Humanitarian essentials 20 / Staff welfare 50 / Staff safety and security 81 / Project cycle management 39 / Logistics and technical training 12 / Disaster risk reduction 9 / Total courses offered by RedR 211 / One reason for the limited interest in attending Juba-based trainings was considered to be the gradual move of staff from Juba to field locations linked to the high cost and limited availability of transport between locations. For this reason, RedR changed their strategy to adopt a field-based approach to training. For field trainings, the cost of subsistence and accommodation for RedR training staff is covered by the client agency as part of a cost-sharing agreement. This change in emphasis has allowed RedR to address very specific skills or knowledge gaps within organisations. By adopting this approach RedR was able to significantly improve the impact of its training by focusing on teams rather than individuals. For example, during October 2012 – March 2013, 60 World Vision staff in Jonglei and 30 South Sudan Red Cross staff in Eastern Equatoria were trained on hostile environment first aid and ground search and rescue, and 26 Oxfam staff in Upper Nile received two week long WASH training. / Between October 2012 and March 2013 almost half of the courses (31 out of 68) were provided outside Juba including locations with the highest humanitarian need such as Yida, Maban, Agok, Fangak, Bor, Malakal and Bentiu all in Upper Nile, Unity and Bor.[7] Other courses were delivered in Northern and Western Bahr El Ghazal, Eastern Equatoria and parts of Central Equatoria. / While RedR initially levied a training charge of $50 and $30 per person per day for international and national NGO participants respectively, it was felt that this cost was too high, particularly for the national NGOs (as the LNA shows). In light of this RedR decreased its costs to $30 and $15 per person per day.[8] This change was made with a view to maximising participation of agencies. The cost is justified by the need to supplement the budget and to ensure that agencies own and engage in the training process which might not have happened if a free service was offered. The reduction in costs hasn’t changed the fact that some national NGOs still find them prohibitively expensive and hence are unable to benefit from RedR’s services. / Feedback from discussions with international and national NGOs in Juba that had sponsored staff to attend the training underlined this disparity with international NGOs considering that the costs were affordable particularly as many had dedicated funds for capacity development. Some national NGOs on the other hand still considered $15 per person per day to be beyond their reach, although many of the larger national NGOs had used the RedR service and felt that it was effective in key areas of need, particularly in areas of proposal writing and logistics where they felt they had significant skills gaps. / Overall, the number of people who have received training has been encouraging and has justified the changes that RedR has made to its approach and fee structure. The number of participants who had received training under the DFID programme were as follows:[9] / 1,776 Total international NGO / 589 Total national NGO / 70 Total UN / 249 Total Government / 67 Total other / RedR records show that by end June 2013 they had trained 2,751 participants. We are still awaiting final figures to February 2014, but this shows good progress against the target by of 3,250 by project end.[10] A further 695 participants were trained through initiatives funded by other organisations however these activities would not have been possible without the established presence, experience and training materials developed under this DFID-funded programme. / RedR has considerably exceeded targets of both number of courses and number of training days. By Nov 2013, 211 courses had been delivered under the DFID programme (compared to a target of 179 by project-end). Similarly, the target of 4,500 participant training days has been exceeded over 40%, with RedR having successfully delivered 6,710 participant training days by Nov 2013 with final project-end figures expected to be higher. While this has been achieved over a longer timeframe than initially planned, the achievement is within the original budget allocation, which is impressive. / Training participant figures trained under DFID programme by RedR course by year (2011 – June 2013) / Course/year 2011 2012 2013 / Humanitarian principles and practice 80 503 531 / Staff safety and security 65 530 456 / Staff welfare 58 356 87 / Logistics and transport 0 38 47 / Final figures covering the whole of 2013 are expected to be higher. / Indicator 3: Feedback from training participants / Courses are evaluated by participants after each event and these figures have been collated by RedR with a target of 90% of participants indicating a significant improvement in skills, knowledge and confidence immediately after the training event. Cumulative responses from the commencement of the programme to end-Nov 2013 show an overall satisfaction rating of just over 91% which is a very impressive achievement. / Feedback from international and national NGOs during the PCR endorsed RedR’s statistics with the majority expressing satisfaction with the quality and effectiveness of the training provided. / Feedback from course participants (2011 – end-Nov 2013) / Area of feedback/feedback received Excellent Good Adequate Limited / Improvement in knowledge and skills 41 52 6 1 / Relevance to humanitarian work 50 39 10 1 / Effectiveness of humanitarian training materials 47 35 14 4 / Effectiveness of facilitation 50 38 11 1 / Worthy of note is that 92% of the participants rated their improvement in knowledge and skills as being excellent or good with similarly high scores for the effectiveness of training materials (84% excellent/good) and facilitation (87% excellent/good). The figures suggest that RedR’s training programme has been of a very high standard.
Impact Weighting (%): 30 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
[4] This only includes training that has been directly funded by DFID. Substantial additional training has been provided through other projects as a result of this DFID support in setting up the programme
[5] Based on adjusted results for improved knowledge and skills across each year of the project
[6] Source: RedR, Learning Needs Assessment, South Sudan, December 2012
[7] Source: RedR 6-month narrative and financial report, October 2012 – March 2013
[8] Source: PCR meeting with RedR Country Representative, July 2013
[9] Source: RedR, PCR Meeting with RedR Country Representative, July 2013 and training statistic records
[10] Source: RedR update on outputs, personal communication, July 2013

Output 2: Organisations use knowledge gained from RedR to fill critical gaps in the ability to respond to humanitarian crises.
Output 2: final score and performance description: / A - Output met expectation / Final results: / There is evidence that the RedR training courses have been used widely by both international and. to a lesser extent, national NGOs; and post-training evaluation suggests that in some cases this has led to organisational change and improvement (although the evidence is weaker). / Indicator Target Achieved end-June 13 Achieved at project close / 1. Numbers of organisations served disaggregated by location and organisation type 100 137 150[11] / 2. % of organisations indicating a significant improvement in the understanding or use of systems, processes etc. 80 60 by end-March 2013 71[12] / Indicator 1: No. of organisations served / Altogether 137 NGOs have used RedR training to build capacity of their staff which significantly exceeds the target of 100 agencies. The total proportion of national NGOs has increased over time as a consequence of better marketing with national organisations and more strategic identification and planning of the activities that are in greatest demand. / Indicator 2: % organisations indicating an improvement in systems / As part of their follow-up interview, participants have demonstrated that in one way or another their organisations have benefited from the RedR training through new policies and procedures; awareness of specific standards or know-how; success in fundraising; improved communication within the teams or with their external partners and beneficiaries; better security measures; and knowledge sharing with other colleagues in their organizations. While the evidence provides a helpful indicator of the relevance of training, follow-up only targets 5-10% of training participants and so this figure is likely to under-represent the actual number.
Impact Weighting (%): 30 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
[11] Based on last quarterly report to end of September 2013
[12] Based on last quarterly report to end of September 2013. Analysis based on 57 follow ups conducted with participants from all courses – 71% indicated specific examples of improvements in coordination or operational systems and processes such as HR, team working, planning, disaster management, logistics, procurement, vehicle management

Output 3: Humanitarian staff have the competency to remain effective and operate safely in South Sudan
Output 3: final score and performance description: / B - Outputs moderately did not meet expectation / Final results: / In setting such a challenging output, RedR has been a victim of its own very high standards. While the advisory services have proved much slower to become established and win the trust and respect of NGO partners, performance is now beginning to make up for lost time. Similarly the Peer Support Network took a long time to establish and has only really been used effectively for agencies that are part of it. It will likely take time and demonstration of added value for agencies external to the Network to start to use it. Post-training self-evaluation provides some evidence of the readiness of agency staff to operate effectively in South Sudan and the large numbers of staff that have been trained in security management goes some way to meeting the output. / Indicator Target Achieved Achieved by project close / 1. Number of training and advisory services provided (including support with Security plans, SOPs, info sharing events, simulations etc.) 30 20 by end-March 2013 20[13] / 2. Number of responses to critical incidents conducted within 48 hours by beneficiary organisations 50 5 by end- March 2013 5[14] / 3. % of participants indicating improved understanding of security concerns and awareness of their own security as a result of the RedR activities 80 82.36 by end-June 2013 88[15] / Indicator 1: Number of Advisory services provided / RedR assisted several organisations (e.g. JEN, CAFOD) to undertake security assessments either of the areas where they operate or their offices around South Sudan. By working closely with the management and security advisors RedR provided guidance on development and implementation of security policies, plans and procedures. RedR has also provided assistance to Samaritan’s Purse in security situation analysis which improved the organisation’s awareness of the present risks and has strengthened its ability to make informed decisions on security-related issues. / Indicator 2: Number of responses to critical incidents / After a long period of preparation, in February 2013 the first Peer Support Network (PSN) meeting was organised with an aim to create a regular platform for aid workers to share their experience and seek advice on various staff wellbeing aspects. The PSN now meets relatively regularly and its key priorities have been refresher trainings for network members, critical incident tracking and case study discussions. RedR has identified 17 members (12 male and 5 females) representing 6 NGOs (1 from an international NGO and 5 from national NGOs) and 1 Government (from the Relief and Rehabilitation Commission) who have previously attended RedR staff welfare training.[16] In March 2013 the second PSN meeting was organized which focused on refresher training on Psychosocial first aid based on the World Health Organisation (WHO) model. / There have been several challenges with launching the Network which includes, for example, the recruitment of network members, attendance at meetings, finding a location to meet as a group (many potential/interested network members are based outside Juba), and timings for meetings. However, with the new Training Team Leader on staff welfare in post since January 2013 progress is beginning to be made. / By the end of March 2013 there had been only five responses, which is a small proportion of the target.[17] It is noteworthy that these have been from agencies that have provided staff and have received training. There are concerns that it will take time for those agencies without trainers on their teams to sufficiently trust and understand the facility and to make best use of the services it offers. / Indicator 3: % of participants indicating a better understanding of security concerns / This indicator is measured directly after participants have been trained as part of the course evaluation. By end-Sep 2013 the percentage total was above the target, with almost all participants (88%) recording an improvement according to follow-ups with participants over the course of the project who undertook security training. RedR training has made an impact both on individual aid workers through changed behaviour, awareness or ability to identify risks, and on organizations through improved day-to-day practice and procedures.[18]
Impact Weighting (%): 40 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No
[13] Achieved by 10 December 2013
[14] Achieved by 10 December 2013
[15] Based on documented follow ups with participants from security related trainings
[16] Source: RedR 6-month narrative and financial report, October 2012 – March 2013
[17] Source: PCR meeting with RedR Country Representative, July 2013
[18] Ibid

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? Yes / The project was split between Sudan and the Republic of South Sudan in August 2012 and the logframe was changed to reflect this. A no cost extension was also agreed in August 2012 to reflect an increase in the number of participants trained. A second no cost extension was agreed in July 2013 to extend the programme until the end of the calendar year 2013, to allow for the scaling down of the RedR operations in the transition from existing funding and securing other funding sources from 2014. Importantly the extension period was still within budget. / 1.2 Final Output score and description: / A: Output has met expectations / RedR has been effective in identifying skills gaps and seeking to fill them through the provision of high quality training. In making the move to South Sudan, not only have efficiencies been achieved, but the training programme appears to have been more responsive to the context and to the expressed needs of operational organisations. In responding to these needs and in showing adaptability in decentralising their training programme, RedR has demonstrated an ability to adapt in order to maximise their effectiveness which has been impressive.
1.3 Direct feedback from beneficiaries / A discussion with agencies whose staff had participated in RedR training (during a meeting with international NGOs and a separate meeting of national NGOs hosted by the South Sudan NGO Forum) highlighted general satisfaction with the effectiveness of the courses offered. Beneficiary agencies spoke of the limited opportunities that existed to train staff in South Sudan; the considerable skills gaps that exist, particularly with their South Sudanese staff; and the professional approach that RedR has maintained both in terms of the skills and knowledge of the trainers, and the course content. / There was some scepticism about the fees that RedR levies. As revealed by RedR’s own learning needs assessment, the $15 per person per day mean that the courses are unaffordable to some national NGOs and this was confirmed in the discussion (although it is important to note that a number of national NGOs have found resources to use RedR services). There was also some concern about the high cost of some of the bespoke courses held outside Juba.[19]
1.4 Overall Outcome score and description: / Anticipated Outcome: Humanitarian organisations in South Sudan are able to respond to the evolving humanitarian situation more effectively. / A - Outcome met expectation / RedR has made an important contribution to realising the outcome. This was strengthened by DFID’s willingness to grant successive no cost extensions thereby lengthening the period of training provision. While the investment that DFID made was considerable it was also timely as it was made at a time when there was rapid change occurring in South Sudan. While expectations were that moderate insecurity would continue, few people imagined that independence would come at such a high cost and DFID’s investment in training has certainly provided an important source of knowledge and skills that are in scarce supply and significant demand. / That said, even with an extended timeframe the project period is too short to provide an assurance that humanitarian organisations will be able to respond more effectively to the humanitarian situation in South Sudan for any length of time. The rapid turnover of humanitarian staff in the country and the relatively short institutional memory that exists makes this a challenging outcome to achieve. The nature of the diverse challenges in South Sudan also makes it an extraordinarily tough context to deliver effective (timely, relevant and quality) programming in. Despite these retention and continuity challenges there is no doubt that RedR has strengthened both the knowledge and practice of many staff and organisations and in so doing has made an important contribution towards achieving the outcome. / 1.5 Impact and Sustainability / Beyond the training figures it is only possible to get a partial sense of what has been achieved by the project. There is a process of follow-up, but this happens with only 5-10% of the trainees. RedR had developed written case studies but these do not explore the outcomes and impact of the training systematically. / An impact evaluation was initially recommended in the Business Case. However, the original budget only included provision for an external Mid Term Review. This was conducted midway through the project. Whilst an impact evaluation could have offered significant learning and helped to strengthen RedR’s ability to advocate for follow-on funding, budget was not allocated and an evaluation framework was not established during project design. / Sustainability is a more complex issue. At the time of the completion of this PCR no alternative funding had been identified and there were no plans to continue the training. While the nature of training lends itself to sustainable knowledge transfer, particularly where the new skills are being put into use, the high staff turnover in humanitarian agencies means that the organisations that pay for the training may not fully benefit from it in the long-term as staff move between agencies. Looking more broadly at the skills gap that exists across South Sudan, then RedR’s focus on national staff (even those working for international agencies) is a good investment and one that will likely provide benefit in the longer-term.
[19] In response to this issue RedR provided a breakdown which provides an insight into the costs associated with conducting training outside of Juba. It was noteworthy that Associate Trainers (international consultants) were used in the specific example discussed with DFID which increased the total cost considerably.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / There has been good budget management albeit in the context of slow spend throughout the life of the programme. The fact that underspends have been proactively managed with the submission of no cost extensions at appropriate times suggests that a satisfactory level of budget scrutiny is being maintained by RedR. / 2.2 Key cost drivers / By end-Sep 2013 (the most recent date for which consolidated accounts are available) the key cost drivers include the following:[20] / The cost of staffing accounts for the greatest proportion of line item costs to date with international and national staff salaries and associated expenses accounting for 30% of spend. RedR have sought to manage these costs through reducing reliance on both Nairobi-based staff and associate trainers and by passing on costs of associate trainers to agencies wherever possible. / Rental of the RedR house and office rates account for 17% of the total budget. The proportion was reduced after the move to a single autonomous programme as Nairobi office costs were no longer borne by the programme but this has likely been offset by the need to move to a larger office to accommodate the larger team with an on-site training facility. / The cost of RedR Associate Trainers has been a considerable cost driver in the past but has been reduced in recent months as RedR has endeavoured to reduce reliance on consultants and draw on its in-country staff. A reduction in recent quarterly international flight costs may also reflect the reduction in the use of Associate Trainers. / 2.3 Was the project completed within the expected timescale: No / The project was not completed in the expected timescale; a six-month no-cost extension was submitted and agreed which extended the project from 31 March 2013 until 30 September 2013. A second no-cost extension was submitted and agreed by DFID in July 2013 to extend the project by a further three-month’s until the end of the year to complete training activities and scale down operations. The review considers this a positive outcome since RedR’s services are highly valued. A short extension period 1 January 2014 to mid-February 2014 was granted to enable RedR to close down their operations under this project including disposal of assets which has all now been completed and agreed by DFID
[20] Source: REDR 6-month narrative and financial report, October 2012 – March 2013

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / The evidence presented in the Business Case included the dynamic security situation which was implicitly linked to the skills gap in security management and the limited options for capacity development. During the course of the project, the security situation has ebbed and flowed but there has not been a significant improvement. While the RedR training assistance has gone some way to beginning to fill the skills gap, this remains a work in progress. The lack of alternative options for security training is also little changed. / 3.2 Set out what plans are in place for an evaluation. / Although a mid-term and final evaluation were referred to in the Business Case, a final evaluation was not completed (see impact and sustainability section). That said a mid-term review was completed. The reporting and quarterly financial monitoring has been extremely good and has provided a detailed overview of project achievements.

4. Risk
4.1 Risk Rating (overall project risk): Low/Medium/High / Low / Did the Risk Rating change over the life of the project? No / There has not been a considerable change in risk over the life of the project although the risks have changed throughout the duration of the project. The move to de-link the South Sudan office from Sudan and Kenya had potential risks but also gave the team greater autonomy and capacity which is a benefit. Staff recruitment and turnover has been troublesome at times but the team is currently fully staffed. / The risk of insecurity in South Sudan has continued throughout the programme albeit with periodic changes for better and worse. The re-focusing on training in the field has been affected by issues of access on several occasions which has led to training events being postponed or cancelled but this risk has been offset by an associated reduction in the reliance on participants flying into Juba from field locations. / 4.2 Risk funds not used for purposes intended / The risk is also low. The funds are being spent directly by RedR and much of the expenditure is being made in Juba. Financial reporting has been strong and reports have been sent on time each quarter. Financial management procedures are in place and are being implemented. / DFID commissioned an external financial review of the RedR project in May 2013 for the period 01 April 2012 – 31 December 2012 which provided the following reassurances:[21] / Controls are in place for avoiding duplicate workers, courses, payments and participants. / Quarterly physical checks are conducted of fixed assets and assets on the ground are verified with records and their working condition is examined. / Quarterly management reports are submitted in which a budget analysis is undertaken. / The development of a cash policy in 2013 for cash adequacy levels and petty cash limits. / 4.3 Climate and Environment Impact / With the full training team in place, International Associate Trainers (consultants who are flown in from the UK or Europe) are now used only in exceptional cases when the training requests are very specific. During a six-month period (March – October 2012) only two international Associate trainers travelled to South Sudan delivering 15 days of training outside Juba. From April 2013 the RedR Nairobi office became independent of the South Sudan programme and as a consequence there was a significant decrease in international flights between Juba and Nairobi as all the South Sudan team were based in Juba. While the change in focus of the training to field locations required greater travel by the RedR trainers, this was still a significant reduction in the total number of flights compared to the large number of flights to Juba by training course participants before the change was made.
[21] Ernst & Young, Report on RedRUK – South Sudan project: Improving the effectiveness of the delivery of humanitarian programmes, July 2013

5. Value for Money
5.1 Performance on VfM measures / The project budget included the financial cost of supporting an office and staff in Juba, as well as office set-up costs in Nairobi and as a consequence had extremely heavy front-end costs. These were appraised as being offset by the training taking place in-situ. / Economy / DFID-attributable unit costs per person trained are estimated by RedR to be $1,027.57[22] against a RedR target of $957. Over time, RedR have been able to decrease their reliance on comparatively expensive Associate Trainers and replace them with country-based international and national staff reducing the cost of training significantly. / Timeliness / There is little doubt that RedR’s training services are timely. Given the dearth of skills, the escalating humanitarian needs and the challenges of staff turnover, the ability to provide high quality (see below) training to front-line (mainly national) staff has strengthened much-needed capacity in the humanitarian sector. / Quality/Effectiveness / RedR has done extremely well in consistently delivering a quality training product in addition to proving to be able to diversify their training courses to meet prevailing needs and agency demands. The feedback given by participants provides strong evidence that training needs are effectively being met. / The external financial review of the RedR project commissioned by DFID concluded that the design of the controls around ensuring value for money was good in all cases. / 5.2 Commercial Improvement and Value for Money / By centralising the South Sudan office in Juba from Nairobi and recruiting a full team to be based there. RedR have potentially reduced costs associated with regional flights while at the same time permitting the Juba team to be much more responsive to the environment in South Sudan (with the caveat that now the South Sudan office is autonomous, the initial investment by DFID in the Nairobi office no longer contributes to the RedR programme). / 5.3 Role of project partners / Through decentralising their training to field locations and passing on costs to agencies, the change in focus has been cost-neutral and while the partners bear the cost of transport, subsistence and accommodation for the training staff, this represents an important efficiency in comparison with flying field staff to Juba. / 5.4 Did the project represent Value for Money : Yes / Although the change in the location of the management of the South Sudan programme has led to heavy initial costs, efforts have been taken to reduce these including through a strategy of increasing the autonomy of the Juba office and staffing it appropriately. The high quality training product that RedR delivers linked to the comparatively favourable cost per beneficiary provided by an in-country training programme (as opposed to flying staff out of the country) means that the project has delivered good value for money.
[22] Note that RedR’s calculations do not include the fee that they levy to each person per day which goes to pay overhead costs

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions
Investing in RedR at the birth of the Republic of South Sudan was a shrewd move by DFID. Through RedR’s professional approach to delivering its programme, not only were learning needs identified, but significant steps have been made towards meeting some of the most important gaps. While the separation of the South Sudan office from Sudan and from Nairobi took time and energy, it was also an important step towards having an autonomous team that is well-placed to understand the context and adapt to the changing environment. / There are caveats to the successes of the programme and it is unfortunate that the fee-for services made the training beyond the reach of some national NGOs; the slow start made to some aspects of the programme as a result of human resource constraints also made it challenging for RedR to achieve all of its aspirations. But overall very good progress has been made towards achieving RedR’s ambitions and delivering much-valued training services to the humanitarian community in South Sudan.

8. Review Process
Document review / An initial document review was undertaken which included internal DFID documents (the BC, log frame and budget) and RedR literature (financial and narrative quarterly reports, No Cost Extension (NCE) supporting documents, learning needs assessment). / Documents reviewed include: / RedR quarterly reports / RedR quarterly report / RedR approach to monitoring / RedR Learning Needs Assessment, 2012 / DFID RedR Business Case / No cost extension documentation / DFID annual review for 2012 / Ernst & Young, Financial review on REDR, July 2013 / Interview of RedR staff / A PCR meeting was conducted with a group of RedR staff which included the following: / Country Representative / Head of Programme / Monitoring and Evaluation Officer. / A series of follow-up email exchanges were conducted with the UK-based International Programmes Director. / Interview of course attendees/agencies / Several agencies were visited in Juba during the review process and this was complemented by 2 focus group discussions. / NGO focus group – People in Need, Care, Relief International, International Rescue Committee, Norwegian Refugee Council, Medair, International Medical Corps, Mercy Corps, Mines Advisory Group, World Vision International / INGO focus group – UNIDO, The Health Support Organisation, UNKEA, MACDA, SSUDA, CMD, Nile Hope / Ivor Morgan, NGO Forum, Policy Focal Point / Emma Drew, Oxfam Humanitarian Programme Manager