Annual Review
Project Title: Accelerating the Rise in Contraceptive Prevalence in Uganda
Date Started: October 2011 Date Review Undertaken: 11August 2013
Introduction and Context
What Support is UK providing
DFID has committed to provide £35,000,000 for implementation of the Accelerating the Rise in Contraceptive Prevalence in Uganda (ARC) programme over four years (2011-15) in partnership with USAID and Government of Uganda (GoU). USAID has committed to provide approximately £12,500,000 to the ARC programme between 2011 and 2015.

What are the expected results?
The goal of the ARC programme is to prevent an estimated 650,000 unwanted pregnancies between 2011 and 2015 in Uganda. DFID support through this programme will enable at least 300,000 additional women to voluntarily use modern family planning methods of their choice. These results will contribute to a broader, transformative impact on the Ugandan economy, given the risks to economic and social development posed by the current rate of population growth and the opportunity of social sector savings from lower demands on public services. / DFID attributable planned outputs between October 2011 and September 2015 are: / Better information about family planning choices. / 300 community health workers to be trained to provide information and referral. / Targeted radio campaigns to reach rural communities in 45 more districts, double the number reached prior to October 2011. / Fewer barriers to accessing family planning services. / 200,000 more women to redeem vouchers at accredited family planning service providers. / 5 types of family planning products to be available through subsidized social marketing compared to 3 types prior to October 2011. / A better supply of quality family planning services. / 370 more family planning providers to be accredited to Marie Stopes Uganda (MSU) and Marie Stopes International’s (MSI) global standards, / The number of MSU outreach teams working in Uganda to increase from 8 to 20. / 500 shops and clinics will provide socially marketed family planning products through the expansion of activities of the Uganda Health Marketing Group (UHMG). / More choice of family planning methods. DFID-funded services to provide over: / 130,000 Inter Uterine Devices (IUDs). / 260,000 Implants.
What is the context in which UK support is provided?
Uganda’s fertility and population growth rates are among the highest in the world.[1] 34% of women have an unmet need for family planning; only 26% of women are using modern contraception.[2] About 44 % of all pregnancies are unintended, and these account for the deaths of around 3,000 women every year[3]. The burden of unwanted pregnancy and its consequences disproportionately falls on poor women and adolescents. High fertility is undermining the potential for per capita income growth, and creating additional costs for public service provision.[4] / This programme will make possible a major uplift in the provision of the most cost-effective family planning services through partnership between state and non-state actors. The programme focuses on improving the access to and quality of a range of modern contraceptive methods and ensuring that the poorest groups benefit the most from the UK support. The ARC programme complements the DFID-funded GoU-UN Joint Programme on Population[5] (GoU-UNJPP) and the USAID funded reproductive health programme in Uganda. While the GoU-UNJPP focuses on service delivery through the public sector, the ARC programme works through the non-state sector to increase access to quality family planning services. The ARC programme uses all proven private sector family planning service delivery channels such as outreach, social marketing and social franchising with and without vouchers. / Half of the contraceptive users in Uganda get their contraceptive supplies from the non-state sector; condoms and pills from shops and pharmacies, and injections and IUDs from NGOs/for-profit providers. A large percentage of sterilization’s and implants are administered in public health facilities. Therefore, partnerships between the state and the non-state actors are important for increasing uptake of family planning services in Uganda. / GoU recognizes the importance of collaborating with non-state actors to provide family planning services. It has established an alternative mechanism/distribution channel through UHMG to make available family planning commodities to the private sector/NGOs. The GoU at the 2012 Family Planning Summit in London committed among other things to increase funding for family planning from $3.3m per year to $5m per year. / Through this programme, DFID is working with USAID who have extensive experience working with non-state providers of family planning services in Uganda. USAID and DFID are funding MSU (the leading provider of long term family planning in Uganda) and the UHMG (the leading social marketing organization in Uganda) to expand their existing operations. DFID is directly procuring contraceptives and other family planning products for these organizations to ensure best value for UK funds.
[1] A woman in Uganda is likely to give birth to around six children; Total Fertility Rate is 6.2: Source: Uganda Demographic Health Survey (UDHS) 2011.
[2] Uganda Demographic Health Survey, 2011
[3] Calculated from the Uganda Demographic Health Survey 2011 estimates. As per the UDHS 2011, Uganda experiences 438 maternal deaths per 100,000 live births. This implies that around 6,600 maternal deaths take place per year in Uganda, and 3,000 deaths represents around 44% of all maternal deaths.
[4] Decrease in number of pregnancies, births and children will decrease pressure on public resources. Less crowded hospitals and schools would be able to provide better quality health care and education.
[5] The UN Joint Programme on Population aims at improving public systems to achieve an increase the contraceptive prevalence rate (CPR) by 2.5 percentage points annually–a rate nearly 50% more than the current rate. DFID is providing £30m to this programme over 2010-14. v Barberis, M. and P.D.Harvey. 1997. “Costs of Family Planning Programmes in Fourteen Developing Countries by Method of Service Delivery.” Journal of Biosocial Science 29(2): 219–33.

Section A: Detailed Output Scoring
Output 1: Women and men have better information to make healthy reproductive choices
Output 1 score and performance description: A / Output 1 has three indicators of which one has substantially exceeded expectation, another met expectation and the third substantially did not meet expectation. / Progress against expected results: / Output Indicator Baseline / (Oct 2011) Milestone 2013 Achieved / (Oct 2012-August 2013) / 1.1 Number of new DFID supported private facilities providing FP services 0 90 36 / 1.2 The number of family planning radio spots and talk shows on local radio in social marketing project area (attributable to DFID) 0 4,000 (radio spots) / 100 (radio talk shows) 21,600 (radio spots) / 201 (radio talk shows) / 1.3 Percentage of the population reached nationally with DFID supported messages on family planning Not available 70% 65% / Summary of activities / 1.1 Activities in the second year of implementation focused on strengthening the supervision of private providers accredited in the first year of the programme. This included support for business skills development and improved quality of care. Additional activities were undertaken to accredit new private providers. However this year’s target was not achieved because most of the identified providers did not meet the required minimum standards for accreditation. In addition 67 facilities were dis-accredited from the franchise for failing to maintain agreed standards for quality of care. Therefore the total number of providers in the franchise is 275 against a cumulative target of 370. / 1.2 UHMG supported the national demand generation campaign – The SMART CHOICES campaign, to increase adoption of modern family planning methods across the country. This multimedia campaign focused on promoting informed choice for contraceptive methods and improving perceptions and attitudes towards modern family planning. / 1.3 UHMG used a media research company IPSOS synovate to carry out independent media and awareness tracking of the DFID funded communication campaign. The tracking was conducted among 15-54 year old radio listeners across the country. The results of the tracking showed that by June 2013 65% of radio listeners had been exposed to the SMART CHOICES campaign. / Recommendations: / While there has been a lot of work done through mass media campaigns, there is a need to strengthen interpersonal communication at community level. These should include efforts to enhance the capacity of community health workers to effectively give advice on family planning. / Impact weighting: 20% / The assessment team finds no reason to change the impact weighting. / Risk: Low / The assessment team finds no reason to change the risk rating.

Output 2: Women and men face fewer barriers to accessing family planning services
Output 2 score and performance description: B / Output 2 has two milestones of which one moderately did not meet expectation and the other met expectation. / Progress against expected results: / Output Indicator Baseline (Oct 2011) Milestone 2013 Achieved / (Oct 2012- August 2013) / 2.1 Number of LAPM vouchers redeemed through accredited service delivery points (attributable to DFID) 0 59,000 49,995 / 2.2 Number of subsidized family planning products being offered through the UHMG social marketing (attributable to DFID) 3 5 5 / Summary of activities / 2.1 There has been an improvement in the redemption rate of vouchers from as low as 22% at the end of July 2012 to 63% in August 2013. This is attributed to the use of behaviour change communication officers in the communities close to the facilities and strengthening of the voucher tracking system. Despite this, the volume of services through the Blue star clinics, under MSU’s social franchising network, is less than optimal and it is not clear whether the vouchers are effectively increasing uptake among the poor. In addition, the number of cash clients for the Blue Star clinics remains low having increased from approximately 5% in the first year to 11% of the total number of clients in the second year. / 2.2 In the first year UHMG was able to expand the range of socially marketed family planning methods to include IUDs and implants. Since their introduction in September last year, there has been a significant increase in the demand for these products that could be attributed to UHMG’s communication campaigns and expansion of their Good Life Clinics (GLCs) network. / Recommendations: / As the network of Blue Star Clinics increases, a roadmap needs to be developed to sustain them, including a strategy to increase their cash client base. Also, efforts to increase the synergies between the Blue Star Clinics and GLCs need to be enhanced. / Significant effort needs to be put into understanding the less than optimal service delivery through the Blue Star clinics and come up with strategies to increase the efficiency of this service delivery channel. / More effort is needed to systematically collect information on the socio-economic profile and the ability to pay of clients accessing services through the Blue Star Clinics and other service delivery channels. This will provide evidence for investing in the most cost effective service delivery channels in an environment of changing family planning utilization patterns. / Impact weighting: 20% / The assessment team finds no reason to change the impact weighting. / Risk: Medium / The assessment team finds no reason to change the risk rating. However it will be important to track the indicator on redemption on vouchers to ensure attainment of programme goals.

Output 3: The supply of quality family planning services and products in Uganda is expanded
Output 3 score and performance description: A / Output 3 has four milestones of which two have substantially exceeded expectation and two moderately did not meet expectation. / Progress against expected results: / Output Indicator Baseline / (Oct 2011) Milestone 2013 Achieved (Oct 2012- August 2013) / 3.1 Number of LAPM services provided by outreach services at public sector facilities (attributable to DFID) 0 72,000 104,361 / 3.2 Number of FP services providers trained in delivery of LAPM according to the MSU global standards (attributable to DFID) 0 310 114 / 3.3 Number of UHMG Good Life clinics offering Implants and IUDS in 90 districts (attributable to DFID)[1] 0 (in additional 45 districts; a total of 200 in 90 districts) 200 158 / 3.4 The number of short term hormonal family planning methods sold through social marketing (attributable to DFID) 0 1,450,000 (injectables) 750,000 (pills) 820,017 (injectables) 657,741 (pills) / Summary of activities / 3.1 With DFID funding, the programme supported 14 outreach teams to provide family planning services at public health facilities across the country. By strengthening the mobilization of clients through community discussions, distribution of information, education and communication materials, radio talk shows and working with district officials, the outreach teams were able to exceed the target for this year. However, the involvement of public health workers in the outreach camps remains a challenge despite the importance of their role in sustaining provision of family planning through routine care in the public sector. / 3.2 MSU in collaboration with trainers from the Ministry of Health trained 114 private providers from accredited Blue Star Clinics using training materials adopted from the Ministry of Health family planning training curriculum. This number is less than the annual target because most of the providers were trained in 2012. Cumulatively, the programme has trained a total of 674 providers against the target of 560. / 3.3 The GLCs were provided with sterilizers and equipment for delivery of long term family planning methods. In addition, 83 clinics were supported to conduct integrated outreaches in collaboration with trained good life promoters (community health workers). However, there are concerns over the quality of the services provided at GLCs and the current capacity of UHMG to quality assure the GLCs appears inadequate. / 3.4 There have been challenges achieving the annual targets for short term methods distributed through social marketing. One of the factors influencing this is the increased availability of free short term methods through other programmes. As a result, the demand from the market in some areas for the socially marketed short term methods has declined. / Recommendations: / There is need to consider a quality related indicator relevant to the GLCs to provide assurance on services provided through these clinics. As part of the broader agenda on increasing synergies between the Blue Star Clinics and GLCs, it will be useful to explore potential benefits of collaborating with MSU to use the MSI international standards guidance and approach or other tested approaches (such as PACE/Population Services International’s operation in Uganda) in the GLCs network. / There is need to review the current marketing strategy for the socially marketed short term methods particularly information on market segmentation that profiles the clients ability to pay. This may provide useful data that will inform the marketing approach. / Innovative capacity building efforts, with a big focus on follow up supervision and mentoring as opposed to training alone, should be implemented to strengthen the role of public health workers in routine provision of family planning services. / Impact weighting: 40% / The assessment team finds no reason to change the impact weighting / Risk: Medium / The assessment team finds no reason to change the risk rating
[1] DFID funding for LAPM in Good Life Clinics in 45 additional districts

Output 4: A better choice of family planning methods is available and being used
Output 4 score and performance Description: B / Output 4 has three indicators of which one met expectation; one moderately did not meet expectation and one that substantially did not meet expectation. / Progress against expected results: / Output Indicator Baseline / (Oct 2011) Milestone 2013 Achieved / (Oct 2012- August 2013) / 4.1 Number of implants and IUDs provided by MSU programme (attributable to DFID) 0 (IUDs) / 0 (implants) 45,000 (IUDs) 90,000 (Implants) 29,048 (IUDs) / 105,201 (implants) / 4.2 Number of Implants and IUDs provided through UHMG social marketing activities (attributable to DFID) 0 (IUDs) / 0 (implants) 3,500 (IUDs) 6,500 (Implants) 3,957 (IUDs) / 6,020 (Implants) / 4.3 Number of tubal ligations/vasectomies performed by MSU programme (attributable to DFID, cumulative) 0 (V) / 0 (TL) 3,100 (V) 28,000 (TL) 769 (V) / 22,451 (TL) / Summary of activities / 4.1 There was a significant increase in uptake of IUDs and implants in the second year of the programme. This was mainly because of efforts to improve community sensitization including the introduction of IUDs days where satisfied users share their experiences and correct myths and misconceptions about IUDs. Information, Education and Communication materials on long term methods in 6 languages were produced and distributed across the country. In addition, MSU partnered with USAID funded HIV implementing partners to provide family planning services through integrated outreaches. / 4.2 A total of 177 private providers were trained and equipped with supplies, equipment and commodities for the provision of long term methods. These included equipment for infection control and waste management such as sterilizers, autoclaves, safety boxes and waste bins. / 4.3 Uptake of permanent methods remains less than optimal because of social and cultural barriers. In addition, the limited availability of medical doctors particularly in rural areas poses a challenge to the uptake of permanent methods. MSU has been at the forefront of efforts to advocate for implementation of the national policy that allows clinical officers to conduct tubal ligations and vasectomies. Based on research conducted by MSU and advocacy through the Family Planning Consortium, the Maternal and Child Health technical working group has recommended scale up of the implementation of this policy. It is hoped that following training and mentorship, the number of clinical officers that can carry out these permanent methods will increase significantly. / Recommendations: / There is need for continued efforts to increase uptake of IUDs. DFID support through the GoU-UNJPP programme to build capacity on IUD insertions should be synergized with the ARC programme to enhance achievement of results. / Impact weighting: 20% / The assessment team finds no reason to change the impact weighting. / Risk: Low / The assessment team finds no reason to change the risk rating.

Section B: Results and Value for Money
Progress and Results
Has the logfame been updated since last review? Yes / The following changes were made to the logfame in consultation with both MSU and UHMG: / The baseline on the contraceptive prevalence rate (CPR) was revised to reflect data from the 2011 Uganda Demographic Health Survey that was not available at the beginning of the programme. In addition, the milestones were revised to reflect a 1.5% increase in CPR per year following revisions to DFID Uganda’s overall target on CPR. / The reporting period was changed from the calendar year to the reporting period under the contract with USAID, October to September. / The milestones were revised from cumulative to annual targets. / The milestones for Couple Years of Protection were revised upwards based on achievements of the first year that superseded expectations. / Output indicator 1.3 was changed from percentage of the population in the 45 districts aware of UHMG socially marketed products to percentage of the population nationally reached with DFID supported FP messaging. This is because measurement of awareness can only take place through an in-depth survey conducted bi-annually. / Overall target for milestone 3.1 was increased based on progress in first year and projected increase in uptake of family planning through outreach services. / Indicator 3.3 changed to reflect GLCs offering long term family planning methods as opposed to short term family planning methods. This is because DFID support through this programme is procuring long term family planning methods. / Overall targets set for indicators 4.1 and 4.3 were increased based on a discussion with MSU on demand generation activities to increase uptake of long acting and permanent methods. / Overall output score and description: A / Based on the progress to date the programme has met expectation. / Direct feedback from the beneficiaries / Direct feedback from beneficiaries was mainly collected through interviews and discussions with Government officials at the central and district level, donors supporting family planning, the implementing partners and other stakeholders. In addition field visits were conducted to meet with health workers and clients to get feedback on the benefits and challenges at the peripheral level. It also provided an opportunity to observe the delivery of services through the Blue Star franchise, GLCs and outreaches at public health facilities. / It was clear from the discussions with the government officials that ownership of the programme at the district level was good. The district officials recognize that the ARC programme has contributed significantly to the uptake of quality family planning services in the districts in an environment of constrained resources from the public sector. In addition, efforts to work with private providers that the district officials have minimal resources to supervise and quality assure has significantly improved the quality of family planning services in the private sector, particularly through the Blue Star franchise. There has also been a significant improvement in availability of long term methods through this programme. The programme has also included district officials in the implementation of communication campaigns including radio talk shows which has increased uptake of family planning services. It was clear that ownership of the programme at the district level is very strong. However district officials observed that there is still a gap in the knowledge and skills of health care workers in the public sector on provision of particularly long term family planning methods significantly affecting the provision of quality family planning services through routine care in public facilities. In addition, integration of data generated through the outreaches and the private clinics into the Health Management Information Systems needs to be enhanced to improve district reporting and also improve integration of the programmes activities into the district work plan. / In discussions with the new assistant commissioner of reproductive health it was clear that while he was aware of the implementation of activities under the programme such as the outreaches and support to private providers, the linkages between DFID and GoU funding to build public sector capacity could be strengthened. The Ministry is aware of the enormous impact the outreach services are having on communities and the contraceptive prevalence rate. The Government fully supports the policy to increase access to family planning services through public/private partnerships. It was reported that the alternative distribution mechanism through UHMG and UHMG’s communication campaigns have contributed significantly to increased awareness on family planning and availability of the commodities in both public (through outreaches) and private facilities. He also noted that the GoU with support from the World Bank is in the initial stages of designing a voucher programme for reproductive health services and will be drawing on some of the experiences of the Blue Star voucher scheme to implement this programme. / UNFPA recognizes the huge contribution of support from DFID to increased availability of family planning commodities in both the public and private sectors. From discussions with UNFPA and others it could be inferred that, DFID support for procurement of contraceptives through ARC and GoU-UN JPP has contributed to increased availability of these commodities in country. The quantification and forecasting for contraceptives is done through the reproductive health commodities security committee with several stakeholders including the Ministry of Health. However, it was not clear the extent to which this was becoming more professional or at least forecasting becoming more evidence based or to what extent service information from both the public and the private sector was being used to generate forecasts. / Private providers reported that they felt more confident providing family planning services following the training they have received. However, the quality of services varies significantly. From the discussions held with several clients at facilities, it could be inferred that most clients appreciated the services received through outreaches and considered the outreach teams to be highly competent in some cases preferring to wait for outreach teams than come for services through routine care. Long waiting lines during outreaches were however reported as an inconvenience. / Summary of overall progress / The project is making an important contribution towards increasing the supply of (services, commodities) and demand for (information, vouchers) family planning in Uganda; a country where contraceptive use is still low (CPR of modern methods at 26%; and 15% among the poorest) and 43% of women discontinue use within a year mainly due to fear of side effects (UDHS 2011). Funding through this joint DFID-USAID programme has significantly improved availability of a wider choice of modern contraceptives to rural women and men. Progress against all four outputs has been good (two outputs meeting expectation while two moderately did not meet expectation) with more people in Uganda having correct knowledge about family planning methods as a result of communications campaigns, an impressive expansion of service delivery sites through outreach clinics and two social franchising networks and the availability of socially marketed commodities, in particular long term methods. / 1.5 Key challenges / The project has been designed predominately to drive volume – in terms of the numbers of private clinics providing family planning services, the number of outreach sites, the number of vouchers, the number of products and the reach and volume of messaging on family planning. Progress has been good and it could perhaps be argued that given the context in Uganda at the start of the programme, a focus on volume was appropriate in order to reach a critical mass of people accessing family planning. However, in the next two years the programme could focus on quality and Value For Money (VFM) issues along with driving volume. In particular, the programme could focus on (1) quality and professionalization of service delivery; (2) VFM and monitoring of unit costs in particular; (3) peer to peer behaviour change communication and (4) approaches to particular target groups including the youth. Some of these areas for future focus are discussed in more detail below: / Quality and professionalization of service delivery / MSI has global standards for quality which are clearly reflected in MSU’s Blue Star franchise where quality is monitored with regular exit interviews, mystery clients and follow-up of a selection of clients. However, UHMG started off as a social marketing organization and its organizational strengths are primarily in communications, social marketing of commodities and supply chain management. It is not supported with the level of international expertise that MSU has, does not have the same experience of clinic based service provision as MSU and the lower level of quality is therefore reflected in some of the GLCs. The ARC programme has also not really resourced UHMG to provide this kind of support to the franchise and a strategy needs to be worked out for either developing UHMG’s capacity and/or contracting-in an organization to provide this support to the GLCs. / There are now three reasonably well developed social franchising organizations in Uganda – MSU, UHMG and PACE, which have regular meeting to share information under the umbrella of the Family Planning consortium. Work is being done, using GIS mapping, to better understand the coverage and reach of these different franchises to develop a more coordinated approach to private sector delivery. Over the next few years it will be important to consider how franchising could be made more professional and how under the Ministry’s leadership social franchisers could move towards developing accreditation and associated standards, quality assurance and monitoring, pricing standardization and a more formal relationship with government. This should be part of the development of a total market approach referred to in section 7 below. / MSU is considering how the outreach model could be strengthened to enhance government ownership and capacity with approaches such as the dedicated provider. There are other models of strengthening government outreach, such as working with the regional hospitals to ensure they provide support to the delivery of long acting and permanent methods in lower level facilities, or integrating the delivery of family planning into other maternal and child health programmes such as child health days, which MSU and indeed the GoU- UN JPP should be tasked with to consider. / Value for Money / The different steps in the DFID value for money framework were considered (see relevant section) and provided assurance that this programmes continues to offer value for money. However, there are no VFM measures in the logframe and there was limited VFM data available on a routine basis to undertake regular VFM analysis. This not only complicates DFID programme oversight but also, more importantly, undermines wider strategic planning for the sector as a whole. Given the importance of this issue, it is therefore recommended that routine monitoring of selected VFM indicators be introduced for the remainder of the programme – ideally through the addition of a new VFM output to the log frame or alternatively in the form of additional reporting. / The key VFM indicators concern the ‘efficiency’ of the programme (i.e. transformation of money into outputs). The key efficiency measures are costs of service (including the cost of the commodity) through the different channels. An indicator should be included to the monitor unit cost of procurement and delivery of various contraceptive methods through the different channels. / Approaches to target groups / The project is designed to focus on reaching the poorest with outreach services in Government clinics, reaching those who can pay through highly subsidized socially marketed commodities and services (vouchers). This focus on delivering to the poorest quintiles is welcome but needs to be better monitored, particularly in Blue Star and Good Life franchises. MSU are considering providing vouchers for free in Northern Uganda which provides an opportunity to further develop the evidence base in this area (i.e. use of free vouchers as a demand creation tool) and should be resourced accordingly so that appropriate data on effectiveness can be collected. / Given the structure of the population in Uganda with a large number of youth, and data showing that 23% of girls had sex before 15 years and 64% by 18 years (UDHS 2011), the project should have a stronger focus on youth and adolescents. It will be important to consider what kinds of approaches need to be developed to reach a larger number of young men and women. / Annual outcome assessment / The overall outcome of the ARC programme is increased use of modern contraception in Uganda. The log frame contains two indicators against which this outcome is assessed. These include; / Outcome indicator 1 Baseline (October 2011) Milestone 2013 / (Calendar Year) Achieved / Contraceptive prevalence rate (modern methods: women of reproductive age) 25.6% 30.6 % To be determined through the annual panel survey of 2013 and FP mid-term survey 2014. The results of these surveys are likely to be published in 2014. / According to the Annual Panel Survey 2012 the contraceptive prevalence rate (CPR) for modern methods of contraception is 30.2%, an improvement from 25.6% in 2011. The increase in CPR in 2013 will be determined through another panel survey whose results will be available in 2014. / Outcome indicator 2 Baseline / (Oct 2011) Milestone 2013 Achieved (Oct 2012-August 2013) / Couple Years of Protection delivered through ARC 0 1,323,988 1,029,417 / The Couple Years of Protection (CYP) achieved 77% of the target. Therefore this outcome moderately did not meet expectation. While the outreach service delivery channel has continued to reach large numbers of clients uptake through the other delivery channels needs to be enhanced. Implementation of remedial actions recommended in this report should enable attainment of the overall outcome.

Costs and Timescale
Is the project on-track against Financial Forecasts? Yes / The annual budget planned for the year Oct 2012- Aug 2013 was £7,130,874. / Implementing Partner Funds Planned Oct 2012- Sept 2013 Funds Received / Oct 2012-Aug 2013 Funds Spent / Oct 2012-Aug 2013 Percentage expenditure / UHMG £1,243,272 £1,100,001 £927,287 75% / MSU £5,887,602 £5,378,643 £5,205,969 88% / Total funding £7,130,874 £6,478,644 £6,133,256 86% / The expenditure against planned budget registered impressive performance. MSU achieved an 88% and UHMG a 75% spend as of August 2013. It is projected that all the funds will be expended before the end of the fiscal year. Overall the programme budget forecast is on track as it registered an 86% spending in 10 months over the allocated funds for the year. / Key Cost Drivers / Overall the costs of implementation of the programme remained within the anticipated budget. / Is the project on-track against original Timescale? Yes

Evidence and Evaluation
Assess any changes in evidence and implications for the project / There is a growing body of evidence on the use of vouchers which could be bought to bear. MSI have 17 social franchises in the world and 9 of these have vouchers and need to be encouraged to bring this experience into the MSU programme. The relevance of simultaneously investing in free services for all and in subsidized services through social marketing and franchising needs to be critically examined in the context of Uganda. A strategy for Uganda on how to promote a total market approach to family planning could be worked out by the end of this programme. This will be important in planning the future of family planning programming by all stakeholders of family planning in Uganda under the leadership of the Ministry of Health. / Where an evaluation is planned, what progress has been made? / Terms of reference to undertake an evaluation of the delivery of family planning through various channels has been finalized and is in the procurement process. The mid-term survey is envisioned to start in January 2014. This evaluation will not only measure the extent to which the use of modern family planning methods has changed between 2011 and 2015 in Uganda but also ascertain the relative contribution of each intervention (delivery channel). It will also assess the extent to which each of these interventions (delivery channels) has reached the poor in Uganda.

4. Risk
4.1 Output Risk Rating: L / 4.2 Assessment of the risk level / The ARC business case contains a set of risk categories against which the overall programme risk can be determined and scored. An assessment of these risks to the delivery of expected results and an assessment of whether the mitigation actions directly address the identified risks is contained in the table below; / Description of risk Probability Impact Comments / (August 2013) / Lack of national political support. Ugandan government policy is supportive of family planning, but there is also quite a strong pro-natalist sentiment in the statements of some politicians. There is also some religious opposition to family planning in general, and to MSI in particular because of its association with abortion. Low Medium With Uganda’s commitment at the FP2020 Summit in July 2012 and the participation of the president and other high level government officials, the probability attached to this risk is judged to remain low. / GoU engagement. In particular, MSU’s outreach services are delivered mainly in MoH facilities, so the outreach programme is heavily dependent on MSU achieving and maintaining a good working relationship with the MoH. Low Medium MSU has done well in collaborating with MoH and particularly at the district level. GoU capacity – including at the MoH remains weak though and this is a risk for long-term coherence and effectiveness of FP service delivery. In addition, there are still challenges with the capacity of health workers to deliver particularly long term family planning methods through routine care. The probability attached to this risk remains the same. / Impact of the voucher programme. MSU has experience of vouchers in Uganda and MSI has experience elsewhere, but such a large voucher scheme may have unpredictable effects on demand and supply in the overall market. Medium Low These questions remain important and will be studied in detail by the evaluation to take place later in the year. / Changes in US legislation. The reinstatement of the Mexico City Act could prevent USAID channeling DFID funds to Marie Stopes Uganda. Low High Risk reduced following the US election of November 2012. / Implementation management capacity. The ability of MSU to achieve the rapid scale-up proposed in this programme has not been proven. UHMG are a relatively new organisation still in the process of developing full management capabilities. Medium Medium MSU has been able to set up the Blue Star franchise. However accreditation of more facilities in the second year declined to focus on quality as opposed to scale up. While UHMG have demonstrated strength in social marketing, it is a priority for them to strengthen their social franchising capacity – particularly on quality of care. In addition, MSU needs to enhance their efforts to manage clients from their large outreach operations that may experience side effects and complications. / 4.3 Risk of funds not being used as intended / The ARC programme funds are managed and disbursed through the USAID robust financial procedures to the implementing partners. The close monitoring of funds by USAID and the various checks and balances minimize the risk of funds being misused. The implementing partners MSU and UHMG put in place systems to check spend and ensure accountability of funds received. However the findings of an ongoing audit on MSU due to be released this month will provide additional information on the current risk to the programme. / 4.3 Climate and Environment Risk / Many of the service sites that were visited had good waste disposal at the facility but the disposal of waste for the outreach services was left up to the Government facility and in the social franchises to the various providers. In both situations there was varying quality in the waste disposal systems ranging from well managed incinerators to poorly managed pits with sharps littered around the pit. DFID Uganda needs to work with partners to consider how waste management can be properly managed and disposed of. / Potential detrimental environmental impact Mitigating action Rating / The release of carbon dioxide through transport of the outreach teams The programme has procured vehicles with modern fuel combustion systems. “B”: medium/manageable potential risk, with good opportunity for improvement. / Recommendation: Upgrade rating from last year from low up to medium. / Waste generated as a result of provision of family planning MSU and UHMG have provided training on infection prevention which include strict protocols on disposal of domestic and clinical waste as well as procedures for disinfection, cleaning and sterilization. / However based on findings in the field, DFID Uganda needs to work with partners to consider how waste management can be improved.

Value for Money / 5.1 Performance on Value for Money indicators / There are no VFM measures in the log frame and there was limited regular availability of VFM data to undertake analysis. Given the importance of this issue, it is recommended that routine monitoring of selected VFM indicators be introduced for the remainder of the programme – ideally through the addition of a new VFM output to the log frame or alternatively in the form of additional reporting. The VFM section in the Business Case sets out a number of indicators and benchmarks which provides a good starting-point. The VFM monitoring should be structured in line with DFID’s ‘three Es’ value for money framework as the section below is. Under each heading indicators to be monitored for the remainder of the programme are proposed. / Economy: This concerns the process of turning DFID money into inputs. Going through the different elements in turn: / Procurement of commodities: This is managed by the International Procurement Agency (IPA) through a direct contract with DFID. IPA uses a competitive process to procure the commodities. Given the importance of implants in the methods provided under the programme, the recent agreement to reduce the price of both Jadelle and Implanon by over 50% has generated significant savings. It is anticipated that approximately $3,096,630 will be saved over the next year in procurement of implants through IPA. / Delivery of services through MSU and UHMG: Assurance is provided by the application by MSU of MSI’s standards and procedures as well as oversight by USAID to ensure compliance with USAID procedures. / For the remainder of the programme an indicator should be established to monitor the unit cost of commodities procured. / Efficiency: This concerns the transformation of money into outputs. The key efficiency measures are costs of delivering service through the different channels. Data was not available during the review but implementing partners should be asked to calculate these figures and report on progress periodically for the remainder of the programme. This information will also be generated during the evaluation of the different service delivery channels set to begin in January 2014. / It is to be expected that costs per Long acting and permanent method (LAPM) service through outreach would be the highest since service to more remote communities is included and MSU bears the cost of staff, vehicles and fuel. The unit costs for GLCs would be much lower since: (i) the non-commodity costs are not subsidized by DFID but paid by clients; and, (ii) the services delivered are overwhelmingly for short-term methods for which the price of both commodity and underlying service costs are much lower. / Effectiveness: This concerns the transformation of money into outcomes. The log frame outcomes concern total CYPs delivered under the programme together with the overall national CPR. CPR data in Uganda is not routinely available on an annual basis. The key effectiveness measure is therefore cost per CYP under the programme. Based on total CYPs and funds used, the estimated average cost per CYP is £6. However it is important to note that this does not include some of the costs incurred during the provision of services e.g. costs to government facilities at which outreaches are conducted. The appraisal in the Business Case suggested that the cost per CYP across the whole programme would be £11. Therefore it can be inferred that implementation of ARC programme provided good value for money.
5.2 Commercial Improvement and Value for Money / DFID has been procuring contraceptives for this programme directly through its framework agreement with IPA. IPA was procured following a competitive international process that followed European Union procurement guidelines. IPA uses competitive bidding to select suppliers following World Health Organisation guidelines and agreed upon specifications with the MoH and the National Medical Stores. Using the framework agreement with IPA enables DFID to benefit from pre-negotiated economies of scale on management fees and their vast knowledge in procurement and project management. In addition, IPA is well versed with market changes, have a big negotiating power and have mechanisms to drive down costs. / Role of project Partners / The performance of MSU is considered to be strong in most areas, except for building capacity of the public health system. MSU will remain an important player in the family planning landscape in Uganda in coming years. A key challenge that will need to be resolved is a potential tension between its role as a player in the FP market and a potentially wider ‘public good’- type policy function in the system. Already MSU is supporting a hotline that is available to all FP users in Uganda free of charge. In the event that the vouchers currently used just for Blue Star clinics became transferable for use in other providers or if MSU took on a role in training and accreditation beyond Blue Star clinics then conflicts of interest would arise that would need to be addressed. / UHMG has also performed strongly in its areas of strength namely social marketing and communications/behaviour change. There is concern over its level of competence as a social franchiser particularly around its capacity for effective training, accreditation, reporting and quality assurance of clinical services in the GLC network. This is not just an issue for FP – but for the other services such as HIV, malaria and maternal health that the GLCs provide. UHMG recognizes this issue as a strategic priority and is committed to addressing it. However this does not represent a significant risk for this programme’s objectives because the share of LAPM delivered through GLCs is significantly small by those delivered through other channels. The vast majority of the CYPs delivered by the GLCs are through short-term methods (i.e. pills, injectables). Nevertheless, a key recommendation of this review is that working with UHMG to strengthen its quality assurance function should be made a priority for monitoring over the coming period. / USAID has worked effectively to manage and implement DFID resources in this programme. Strong results are being delivered on DFID’s behalf through the social marketing and outreach services. The ‘delegated authority’ arrangement represented an effective model when the programme was launched in 2011 given (i) DFID’s limited technical advisory capacity and (ii) the priority of finding channels for rapid scale-up of services. That said, the policy landscape has changed since 2011and DFID has significantly increased it’s in country technical capacity on health and is playing a leadership role in policy dialogue with government, implementers and other stakeholders. However, the current model at times dampens that function for DFID. In the event that DFID were to consider designing follow-on support for FP in Uganda after the end of this programme, it will be important to consider the possible delivery models that enhance DFID’s comparative advantage while avoiding duplication and strengthening the host country’s capacity to provide improved and integrated health services including family planning. / Does the project still represent Value for Money? Yes / If not, what actions will you take

Conditionality / N/A

Conclusions and Actions
Short term recommendations (within the life of the programme) / 1. Log frame revisions: There is need to re-organize some indicators and where applicable add new indicators particularly in light of the proposed additional funding to expand service provision. / Output 1 is essentially about better information and awareness and yet there is an indicator on the number of new DFID supported private facilities, which is really a measure of service delivery. This indicator should be moved to output 3 as it is a measure of supply. In discussions with UHMG a new indicator around changes in awareness through the provision of better information may be included. / Indicators for quality that are more relevant to the GLCs network should be considered. Indicators to reflect any new proposed activities should also be included. / Monitoring of costs and VFM should be more systematically considered. / 2. hould also be included. y new proposed activiteis MSU has developed some interesting ideas about how service delivery through Blue Star Clinics and the outreach could be improved and it would be useful to have this captured more formally in a short paper in order to better help define the longer terms strategy. / Long term recommendations (beyond the life of the programme) / As the FP landscape matures, with the development of both the public and private sectors and more partners and resources, higher level strategic and policy dialogue, in particular with the Government will become important. Over the next 18 months, it will be important to see to what extent a more strategic approach to FP can be nurtured that builds consensus and agreement about ‘a total market approach’ with the Ministry in the lead. This essentially means assessing the characteristics of existing and likely future markets and to define the comparative advantages of the commercial, social marketing, NGO and public sector in terms of ability to deliver a range of FP products for different clients or market segments. It would mean moving towards better and more coherent use of the public and private sectors and the professionalization of both. The impact evaluation of the family planning service delivery channels that is planned for later this year will be useful for developing a total market approach. DFID, along with USAID and UNFPA, could more systematically engage with the MoH to develop this approach.

Review process
The review was conducted by Ms. Natasha Maesko and Mr. James Droop, DFID health advisers with support from the DFID Uganda MDG team and Mr. James Duworko the reproductive health adviser at USAID. / Period of Review: 5th August 2013 -31st August 2013 / Methodology / Structured key informant interviews were conducted at national level with Ministry of Health officials, USAID, UNFPA and the implementing partners (MSU and UHMG). The team visited 2 districts to assess implementation of the programme on the ground. At district level interviews were conducted with the respective district health officers, reproductive health focal persons, health care providers and clients at public health facilities and the Blue Star and Good life Clinics. / The team also reviewed documentation relevant to the programme including; / The programme Business case / Logframe / Quarterly reports from implementing partners / Uganda Demographic Health Survey 2011 / All conversion rates for CYP, DALYs, Total Cost Saving, Environmental impact and Welfare gains were calculated using the MSI Impact Calculator. / Citation: Corby N, Boler T and Hovig D. The MSI Impact Calculator: methodology and Assumptions. London: Maries Stopes International,2009 / The table below shows key stakeholders interviewed. The list of stakeholders interviewed at district level is available. / No Name Title Organisation Email contact / 1 Edward Zzimbe Operations Director MSU edward.zzimbe@mariestopes.or.ug / 2 Awundo Milton Director Medical development team MSU milton.awudo@mariestopes.ur.ug / 3 Barbara Katende Director Technical services and innovation MSU barbara.katende@mariestopes.ur.ug / 4 Senior M&E manager MSU / 5 Alex Bagora Senior Manager-projects MSU alex.bagora@mariestopes.ur.ug / 6 Christine Namayanja Director Private Sector partnerships MSU namayanja.christine@mariestopes .or ug / 7 Jon Cooper Country Director MSU jon.cooper@mariestopes .or.ug / 8 Espilidon Tumukurate Director programmes UHMG etumutkurate@uhmg.org / 9 Ron Hess JHU/CCP JHU/CCP rhess@jhuccp.org / 10 Emily Katarikawe Executive director UHMG ekatarikawe@uhmg.org / 11 Phillip Apira Director Product facility UHMG papira@uhmg.org / 12 Joy Tamale Finance director UHMG jtamale@uhmg.org / 13 Dr. Collins Tusingwire Assistant Commissioner Health Services –RH division Ministry of Health drtusingwire@yahoo.com / 14 Dr. Zainab Akol Head of family planning programme Ministry of Health zainabakol@gmail.com / 15 Dr. Janex Kabarangira Deputy health team leader USAID jkabarangira@usaid.gov / 16 Jyoti Tewari Health Adviser DFID ss-tewari@dfid.gov.uk / 17 Robinah Lukwago Health Adviser DFID r-lukwago@dfid.gov.uk / 18 Catherine Kawamara Programme Officer DFID c-kawamara@dfid.gov.uk / 19 Grace Namata Deputy Programme manager DFID g-namata@dfid.gov.uk / 20 James Droop Health Adviser DFID j-droop@dfid.gov.uk / 21 Natasha Maesko Health Adviser DFID N-Mesko@dfid.gov.uk