Type of Review: Annual Review

Project Title: African Risk Capacity (Start-Up Support)

Date started: February 2010	Date review undertaken: January 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
African Risk Capacity (ARC) provides an innovative approach to manage the risk of food insecurity caused by extreme droughts; slow onset disasters that can often overwhelm the capacities of African governments and do not attract humanitarian aid early enough. / ARC is a pan-African mechanism to pool drought risk and provide African Governments with timely and reliable contingency funding in the event of a severe drought. It should complement, but not replace, current national and international efforts to address food security needs. A risk pool is a mechanism where individual risks are transferred and combined. Countries participating in ARC will commit to pay small, regular premiums in return for reducing the risk of spikes in drought assistance costs as a result of an extreme event. / DFID provided £2.5 m for the design of African Risk Capacity (December 2010 to July 2013), and a further £1.3m in October 2013 to cover the period to December 2014. Other donors have also contributed (see section 5.1). The design is led by the African Union, with the World Food Programme housing a Secretariat that provides administrative assistance and coordination on the technical, legal and institutional mechanisms of ARC.

What are the expected results?
The expected results from DFID’s support to the start-up of African Risk Capacity include: / Impact – Sub-Saharan countries better able to manage extreme drought risk (by Dec 2014): / 10 drought vulnerable countries covered by contingency plans linked with access to regional contingency finance; / $365 million ($200m, plus baseline of $165m) extreme weather contingency funds available to sub-Saharan countries. / Outcome – ARC, an African-owned disaster risk pool for sub-Saharan Africa, in place providing a contingency funding mechanism for planned responses to extreme climate emergencies (by Dec 2014): / 6 national governments drought response contingency plans linked to regional contingent funds agreed by ARC; / 100% of required funds pledged against ARC donor appeal (by Dec 2013). / Output 1 – Capacity and understanding built for African governments to take a fully informed decision on participating in the ARC pool (by Dec 2014): / 18 countries that are (or have been) in dialogue with ARC and actively considering ARC participation; / 20 Africa RiskView and ARC training workshops held for stakeholders (400 people); / Economic rationale for ARC participation established and plan for monitoring benefits of participation developed (by Dec 2013) / Output 2 - Detailed design study for a feasible ARC risk pool architecture approved and agreed on by key stakeholders (by Dec 2014): / Governance structure in place and operating for ARC Ltd ; / All guidelines and procedures in place and review conducted. / 14 independent reviews of discrete technical portions of the ARC Project complete. / Flood modelling completed / Output 3 - Consultation and political engagement carried out (by Dec 2014): / 125 consultations (bilateral meetings, presentations, seminars) held with representatives from countries, RECs, donors, NGOs, IOs, private sector and leading thinkers consulted on ARC concept; / 10 different actors financially supporting, or have pledged to support, the ARC initiative (donors, private sector, Member States etc.); / 25 Positive mentions of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments. / 30 countries have joined CoP / Output 4 - Plan for the creation of the legal and organizational structure of ARC entity fully defined (by Dec 2014): / ARC up and running.

What is the context in which UK support is provided?
Extreme weather events across Africa regularly place the lives and livelihoods of the most vulnerable at risk. Droughts are particularly significant and often lead to food crises with significant humanitarian impacts and longer-term economic costs. Climate change is leading to more frequent and intense extremes in weather, increasing the longer-term risk of greater humanitarian need and economic impacts. / As the Humanitarian and Emergency Response Review (HERR)[1] showed, the current system of response to drought is not as timely or equitable as it needs to be. The International system is trying to address the need for fast and predictable responses to emergency situations; for example through the Crisis Response Window (CRW) of the International Development Association (IDA) and the United Nations Central Emergency Response Fund (CERF). However, such funds are generally only available on an ad hoc basis in the immediate aftermath of a disaster and only then can relief be mobilised for the people who need it most. This results in a time lag between the onset of a crisis and the availability of resources to deal with the consequences. In the meantime, lives are lost; families sell or consume their assets and undertake other strategies with detrimental consequences, such as taking children out of school and reducing food consumption. / The HERR showed anticipation and the early provision of relief can stop a crisis becoming a disaster. This is particularly important for slow-onset events, such as the impact of drought of food availability. Analysis undertaken during the current design of Africa Risk Capacity found that the cost of delaying relief for three months after a failed harvest had negligible impact whereas delaying the response for six months led to losses of $1,200 in assets per household. Loss of assets reduces families’ future income potential, but too often the cost of delay is also in lives.[2]
[1] Available from: http://www.dfid.gov.uk/what-we-do/key-issues/humanitarian-disasters-and-emergencies/how-we-respond/humanitarian-emergency-response-review/
[2] The final report by D Clarke (University of Oxford) and R V Hill (IFPRI) is at: http://www.foodsecurityportal.org/could-weather-indexed-insurance-replace-food-aid-africa-cost-benefit-analysis-africa-risk-capacity?print

## Section A: Detailed Output Scoring

Output 1: Capacity and understanding built for African governments to take a fully informed decision on participating in the ARC pool
Output 1 score and performance description: / Output score: A++ Outputs substantially exceeded expectation / Two of the indicators for this Output have greatly exceeded their targets for this year and the other has achieved as much as possible given the pace of the political process, completing its aims.
Progress against expected results: / Milestones for this Annual Review and results to date are reported below: / 1.1 – Fifteen countries that are or have been in dialogue with ARC and actively considering ARC participation. The ARC Project Team had initially exceeded this target through scoping missions and workshops, engaging 23 countries. This number has since risen to 41 countries with the conference of plenipotentiaries on 19-23 November 2012 in Pretoria attended by 41 AU Member States, 18 of which then signed the Establishment Agreement, provisionally establishing the ARC as a Specialized Agency of the AU. Since then, 4 more countries have signed the treaty. / 1.2- Fifteen Africa RiskView and ARC training workshops held for stakeholders, including government and their partners, and regional body representatives (15 workshops or 350 people). Target for 2013 had already been reached by 2012 Annual review. 2013 therefore saw a slowing in momentum in country engagement as the Secretariat started to focus work with its existing MOU countries and on ARC Ltd establishment. Four additional training events took place in 2013, and to date there have been 24 workshops reaching 700 people. / 1.3 – Economic rationale for ARC participation established and plan for monitoring benefits of participation developed; M& E frameworks developed to monitor the impact and benefits of contingency funding proved by ARC. Completed. The Secretariat developed Standards and Guidelines for ARC Contingency Planning during this reporting period. The ARC Agency Governing Board adopted these standards and guidelines provisionally at their meeting in Abuja in June 2013, with the intent of testing them through the first round of activities in ARC, reviewing the process this year and improving the guidelines and process as necessary in the future. / The Standards and Guidelines for ARC Contingency Planning were tested for the first time in August-September 2013 with the review of the first six operations plans submitted to the Peer Review Mechanism (PRM) of the ARC Governing Board as part of the country applications for a Certificate of Good Standing. The ARC Secretariat has also commissioned an independent review of the overall ARC contingency planning process including its M&E component. / Recommendations: / The Project Team need to continue to capitalise on this excellent progress and turn this momentum into creating strong initiative and ownership in as many countries as possible. No changes needed to milestones. / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Detailed design study for a feasible ARC risk pool architecture approved and agreed on by key stakeholders
Output 2 score and performance description: / Outputs Score: A – Outputs Met / The progress demanded by targets are being met, in one case where target is quantitative, it was met ahead of time.
Progress against expected results: / Milestones for this Annual Review and results to date are reported below: / 2.1 – ARC financing strategy and institutional structure defined, agreeing core technical content of the design proposal by sufficient stakeholders. Completed. The Secretariat designed and negotiated a new model with donor partners on behalf of the ARC member states. In this new model, as opposed to the traditional donor model, funds can be deployed as ‘returnable capital’ which DFID and KfW could make capital available interest free over a 20 year term in order to establish the ARC mutual insurance company, after which time it would be fully owned by the ARC Member States. / At the end of thes reporting period, the ARC Secretariat had provisionally secured in excess of USD 200 million from DFID, KfW and SIDA in capital and guarantees for ARC Ltd, which has established in Bermuda in November 2013and has now received its provisional insurance licence. The Secretariat has also been responsive, supporting initiatives to ensure funds classify as ODA and that they meet BMA and IFRS requirements. The subscription agreements are now being negotiated. / 2.2 – Agreement on operational manual by stakeholders sufficient for initial operation of the entity, developing M&E guidelines, ARC participation and operation. Completed. An ‘ARC operational manual’ can take on a multitude of definitions. The Conference of the Parties (COP) have taken several strategic decisions to guide the institutionalisation and operationalization of the new Agency including on the structure of ARC country contingency planning standards and the sanctions policy. For ARC Ltd, a provisional policy handbook – which can be considered as an “operations manual’ for the company – was drafted by the Secretariat in November 2013 for consideration by the company Members at their first meeting in December in Dakar. Draft key interim policies were agreed (eg Directors appointment and remuneration, and procurement) and all are being refined for final agreement as the Founding Policies in April 2014. / 2.3 – 10 independent reviews of discrete technical portions of the ARC Project e.g. Africa RiskView, dynamic finance analysis, institutional structure, M&E, climate change stress tests. 13 reviews completed. By the end of the Second AR Period, the ARC Project Team (at the time) had already exceeded the original target of 10 reviews by June 2013. This reporting period two additional independent reviews on technical portions of the ARC have been conducted. / The customisation, continual review and use of Africa RiskView has constituted an ongoing review,as does country engagement with ARC, although this is not counted against the target. TheSecretaria has been open to sharing its work and receiving and implementing constructive feedback, including through the intense donor engagement with them on the governance and institutional structure of ARC.. / 2.4 Development of products for risks other than drought – funding for flood modelling achieved. Achieved – SDC (Switerzerland) has agreed to fund this modelling work on flood risk, which is now being put out to tender. / Recommendations: Solid progress. The only change needed to a milestone is Indicator 2.4, where funding for flood modelling has been secured from Switzerland (this year’s milestone) but it will take 18 months and so cannot be completed befpre December 2014 (the current target). We will agree a more suitable milestone with ARC Secretariat. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 3: Consultation and political engagement carried out
Output 3 score and performance description: / A+ : Targets moderately exceeded expectations.
Progress against expected results: / 3.1 – 100 consultations (bilateral meetings, presentations, seminars) held with representatives from countries, RECs, donors, NGOs, IOs, private sector and leading thinkers consulted on ARC concept (Baseline: 25). Over 200 consultations have been held. By the end of the Second Annual review Period, the ARC Project Team (at the time) had already exceeded the original target and has continued to make progress on this indicator as the ARC Secretariat in 2013. / 3.2 – 10 different actors financially supporting, or have pledged to support, the ARC initiative (donors, private sector, Member States etc.) Completed. To date, ARC has six grant-giving donors: DFID, Rockefeller Foundation, SIDA, SDC, WFP’s internal Saudi innovation fund and IFAD. / In addition, the project received in-kind support from the World Bank’s GFDRR at the start of the project for the initial ARC feasibility study. The Republic of South Africa supported some of the costs associated with the plenipotentiary conference in November 2012 and the Government of Senegal supported some of the costs associated with the first COP in February 2013. KfW supported the costs of the BCG cost-benefit analysis and hosted the ARC donor meeting in August and ARC Agency Board meeting in September 2013. / In addition to DFID, KfW and SIDA, Kenya, Malawi, Mauritania, Mozambique, Niger and Senegal are expected to contribute to ARC Ltd through premium payments in 2014, although these countries are not included in the count above. / 3.3 – 20 positive mentions of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments (baseline 3). 27 positive mentions achieved. As the newest ARC Specialized Agency, ARC continued to receive positive mentions in AU documents and African interactions. Building on the 24 mentions in the previous reporting periods, during this period ARC was mentioned in several documents including a number of higher-profile publications. / Recommendations: Again, excellent progress has been made against objectives, and no changes are needed to milestones. / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 4: Plan for the creation of the legal and organisational structure of ARC entity fully defined
Output 4 score and performance description: / A – Outputs met expectation
Progress against expected results: / 4.1 – Legal structure of ARC defined and finalised, vetted by the AU, donors, potential Member States, and legal experts. Completed. The ARC Specialized Agency Establishment Agreement has been adopted by countries, representing the culmination of a year-long design and expert, donor and member state consultation process by the ARC Project (as it was then) on the legal and institutional structure of ARC. / 4.2 – Process for establishment of the ARC facility defined, and establishment process agreed upon by ARC stakeholders. Completed. In late November 2013, ARC Ltd was created in Bermuda, with the aim of becoming operational in early 2014. / Recommendations: Solid progress. No changes needed to milestones. / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y/N / Yes - an additional set of milestones and revised targets have been included to reflect the costed extension to Dec 2014. / 1.2 Overall Output Score and Description: / A+ - outputs have moderately exceeded expectations / 1.3 Direct feedback from beneficiaries / The ARC Secretariat continues to operate effectively, working consistently to try to deliver ARC on schedule and budget. All feedback from Class A members has been appreciative of the considerable support they have received from the Secretariat to familiarise themselves with Africa RiskView and ARC. The main point for improvement was the need for more timely circulation of documents before meeting to allow enough time to read and seek comments from headquarters. Our impressions as a Class C member mirrors this - the team has worked very hard to deliver ARC has been receptive to comments, questions and requests where we have felt systems needed to be strengthened, but they must try to everyone informed in a more timely and consistent way.
1.4 Summary of overall progress / Project progress so far has been impressive – this is a complicated, innovative project, requiring a huge amount of technical support, which the Secretariat has delivered with great energy. Formal targets are being met, often ahead of schedule, and the ambition remains to launch ARC in Spring 2014. The financial affiliate, ARC Insurance Company Ltd, has been established and registered, granted a provisional insurance licence and has a high calibre, engaged Board of Directors.
1.5 Key challenges / Most of the key challenges going forward are on the actual implementation of ARC for the first time- the need to finalise Class A policy purchase and Class B and Class C support, engage the private sector to provide reinsurance, ensure the technical quality of Africa RiskView and strong financial and other management and oversight of contingency planning and any responses. This will require continued diligence and hard work, with the spotlight firmly on ARC to show results..
1.6 Annual Outcome Assessment / Excellent progress has been made in the past year towards the achievement of the Outcome: ARC, an African-owned disaster risk pool for sub-Saharan Africa, in place providing a contingency funding mechanism for planned responses to extreme climate emergencies. The structures of the ARC Agency are in place, as is the financial affiliate, ARC Insurance Company Ltd, which has been established and registered, granted a provisional insurance licence and has a high calibre, engaged Board of Directors. Six countries have indicated their desire to purchase insurance in the coming months, and several donors have also indicated that they are willing to support, subject to prerequisite conditions being met. ARC is expected to be up and running in 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Yes – a costed extension is underway, and those funds are being spent according to schedule. / 2.2 Key cost drivers / Key cost drivers for the project remain as anticipated - staff time and consultancy inputs and advice, as well as a lot of travel associated with agreeing country participation in ARC, raising awareness and supporting the Board and Governing Body. / 2.3 Is the project on-track against original timescale: Y / The establishment of ARC is making good progress towards the logframe milestones for this costed extension and expected timescale (to be complete by Dec 2014).

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Evidence is being gained all the time from stakeholders, country members, academics and others, for example during the customisation and review process as Africa Risk View is tailored for individual country use. It is also being widely shared for technical review (eg by Swiss Re). This evidence is being used to strengthen the programme (eg as new country data sets and evidence is added). Globally, lessons from parametric insurance and risk pooling (eg the Caribbean Catastrophe Risk Insurance Facility and the World Bank’s Pacific Insurance Pool Pilot) are also feeding into design, as well as DFID inputs (for example, lessons learnt from our CCRIF review). / 3.2 Where an evaluation is planned what progress has been made? / ARC’s operations and rationale will be subject to extensive evaluation when the organisation is up and running. No evaluation is planned though of this start-up phase.

4. Risk
4.1 Output Risk Rating: Low-Medium / 4.2 Assessment of the risk level / Low – Medium remains correct. The project start-up is being delivered by a competent team who are expected to deliver, the medium risk elements though relate to the innovative and complex nature of the insurance pool itself and whether all the elements will come together as expected to allow insurance cover to start in the next few months.
Risk of funds not being used as intended / This support covers just project development and start-up managed by a team procured and administered using UN World Food Programme (WFP) procedures. The risks of funds being misused are very low. / 4.4 Climate and Environment Risk / Low risk, mainly related to carbon emissions from air travel (with alternatives such as conference calls being used where possible to mitigate this). As a whole, the project is designed to bring huge climate and environment benefits as it will promote contingency planning and provide a new way to help cope (thought risk transfer) with the risks of extreme weather (drought) faced by African member countries.

5. Value for Money
5.1 Performance on VfM measures / The consultancy for this project has offered good value for money. The consultants are high calibre, extremely engaged and hard-working. / 5.2 Commercial Improvement and Value for Money / Consultancy and staff inputs costs are agreed, travel by consultants (though not WFP staff) is all in economy class and many of the staff work from home so there are no office costs. Little scope for additional efficiency savings at this time. / 5.3 Role of project partners / WFP provides the administrative oversight and management systems for the project. Six African countries (Mozambique, Kenya, Malawi, Senegal, Niger and Mauritania) plan to join as Class A members, as well as SIDA (Sweden) as a Class B donor and KfW (Germany) as a Class C donor. Other donors such as the Rockefeller Foundation, SDC (Switzerland) and others have provided grants towards programme development and start-up costs. / 5.4 Does the project still represent Value for Money : / Yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / No specific conditions.

7. Conclusions and actions
Excellent progress has been made towards the establishment of ARC. The next few months will be crucial, as final structures and procedures become implemented and the first insurance pool is formed. We will continue our extremely close engagement with the ARC Secretariat on all elements of ARC to ensure it meets the high technical, fiduciary and governance standards necessary for the UK to join. Currently, the country contingency plans are a “weak link” which we are working to strengthen. Whilst this start-up work has been intensive and is meeting its objectives, ARC as a whole remains high risk.

8. Review Process
The review was written by Oliver Charkham, based upon the ARC Secretariat’s Narrative Report covering the period November 2012 to November 2013, supplemented by additional information from Nicola Jenns. Richard Dewdney, Head of ARD, had final sign-off.