# ARC Project Logical Framework[1] Costed Extension Agreed May 2013
[1] The ARC Project logframe has been revised in line with the recommendations of the annual review that took place in December 2011. The main change is a 6 month no-cost extension of the project to June 2013 to allow for in-country capacity building activities to continue for the 12 months (as originally envisaged) after the ARC project becomes operationally active in-country in order to enable full achievement on Output 1. This will also allow for enhanced achievement, and also provide a contingency buffer, across all other outputs. Given a design project of this size, scope and political sensitivity, it faced several challenges and constraints in its first year, many beyond the project's control. In particular delays in signing the WFP-AU Special Agreement, which has anchored the project firmly with the African Union Commission (AUC), took 6 months to secure. Delays with the World Bank supervised study also prevented effective movement on country consultations and some aspects of the technical work required. Subsequent milestones and timelines have been adjusted accordingly and should be considered in each of the changes detailed below.
Updated with progress as of Dec 2013

IMPACT			Impact Indicator 1			Baseline / Dec 2010	Milestone 1 / Dec 2012[2]				Milestone 2 / Jun 2013[3]	Milestone 3 / By Dec 2013[4]			Target / By Dec 2014
Sub-Saharan countries better able to manage extreme climate risk			No. of drought vulnerable countries covered by contingency plans linked with access to regional contingency finance		Planned	2	At least 3 countries in negotiation for ARC finance				At least 10 countries in negotiation for ARC finance	6 countries covered			10 countries covered
					Achieved							6 country drafts submitted
						Source
						ARC Secretariat and ARC Ltd Reports
			Impact Indicator 2			Baseline / Dec 2010	Milestone 1				Milestone 2 / Jun 2013	Milestone 3 / Dec 2013			Target / 2014
			Value of extreme weather contingency funds available to sub-Saharan countries		Planned	$165 million[5]					$50 million pledged	$100 million financing available to ARC Ltd			$200 million
					Achieved							$260m pledged (some of which already received)
						Source
						ARC Secretariat Reports and ARC Ltd Annual Reports

OUTCOME			Outcome Indicator 1			Baseline / Dec 2010	Milestone 1 / Dec 2011				Milestone 2 / Dec 2012	Milestone 3 / Dec 2013			Target / Dec 2014		Assumptions
ARC, an African-owned disaster risk pool for sub-Saharan Africa, in place providing a contingency funding mechanism for planned responses to extreme climate emergencies			No. of risk pool participation requests received by project from national governments[6]		Planned	0	ARC dialogue process raising understanding of climate risk management underway with at least 4 governments				Draft detailed proposal for ARC risk pool	At least 6 countries requesting participation in ARC / (PPAs)			An additional 4 countries participating for a total of 10 and at least 4 more requesting participation in 2015 (PPAs)		Governments use these funds to protect human, social and economic development and reduce the short- and the long-term costs of assistance. / Governments, donors and international partners continue to focus on disaster preparedness to deal with climate risks and develop effective national disaster risk management and disaster risk reduction plans. / Donors pledge support to regional contingency funds to make country engagement credible / Additional risk capacity from the market and/or international financial institutions can be secured by ARC to leverage donor and country contributions to the pool.
					Achieved							12 pre-participation requests received, six countries ready to join first pool.
						Source
						ARC Secretariat Reports
			Outcome Indicator 2			Baseline / Dec 2010	Milestone 1 / Oct 2012				Milestone 2 / Mar 2013	Milestone 3 / Aug 2013			Target / Dec 2014
			No. of countries with developed drought response contingency plans linked to regional contingent funds[7]		Planned	0	In dialogue with at least 3 countries on contingency planning for contingent funds				3 draft contingency plans developed and in dialogue with at least 3 additional countries	At least 6 national contingency plans developed for contingent funds			6 plans approved by ARC Board
					Achieved							6 draft planssubmitted
						Source
						ARC Secretariat and Governing Board Reports
			Outcome Indicator 3			Baseline / Dec 2010	Milestone 1 / Dec 2012				Milestone 2	Milestone 3 Dec 2013			Target / Dec 2014
			Percentage of funds pledged against ARC donor appeal[8]		Planned	0	Required capitalisation envelope determined by the number of countries					100% of required funding envelope to establish ARC			n/a
					Achieved							Achieved
						Source
						ARC Secretariat Reports
INPUTS ($)			DFID ($)			Govt ($)	Other ($)				Total ($)					DFID SHARE (%)
			7,867,377			0	8,993,555				16,860,932[1]					47%
INPUTS (HR)			DFID (FTEs)

OUTPUT 1		Output Indicator 1.1				Baseline / Dec 2010	Milestone 1 / Dec 2011				Milestone 2 / Jun 2012	Milestone 3 Dec 2013			Target / Dec 2014		Assumptions
Capacity and understanding built for African governments to take a fully informed decision on participating in the ARC pool		No. of countries that are or have been in dialogue with ARC and actively considering ARC participation[9]			Planned	0	4				10	15			18		Donors support country participation financially if required (subject to all country participation requirements being met and participation aligned with other in-country activities). / Assumptions for All Outputs / Governments and regional organisations throughout Africa open to new approaches to weather risk management and are willing and able to consider such mechanisms and make necessary changes in national planning and policy, where appropriate / Political and macroeconomic stability across most countries in Africa. / Countries have access to, and receive technical assistance on, other risk management tools and strategies in order to developing comprehensive risk management and risk reduction programmes.
					Achieved							41 countries considering,18 have signed Establishment Agreement, 12 pre-participation agreements and six ready to join first pool.
						Source
						ARC Secretariat Reports
		Output Indicator 1.2				Baseline / Dec 2010	Milestone 1 / Dec 2011			Milestone 2 / Jun 2012		Milestone 3 / Dec 2013			Target / Dec 2014
		No. of Africa RiskView and ARC training workshops held for stakeholders, including government and their partners, and regional body representatives[10]			Planned	Workshops: / 2 / (40 people)	Workshops: 4 or / People: 100			Workshops: 10 or / People: 200		Workshops: 15 or / People: 350			20 or People: 400
					Achieved							24 workshops held,reaching approx 700 people.
						Source
						ARC Secretariat Reports
IMPACT WEIGHTING		Output Indicator 1.3				Baseline / Dec 2010				Milestone 1 / Jun 2012		Milestone 2 Dec 2013			Target / Dec 2014
25%		Economic rationale for ARC participation established and plan for monitoring benefits of participation developed[11]			Planned	0				Study written by leading experts on the cost benefits of contingency financing mechanisms as offered by ARC and other alternatives		M&E frameworks developed to monitor the impact and benefits of contingency funding provided by ARC			n/a
					Achieved
						Source											RISK RATING
						ARC Secretariat and Governing Board Reports											Medium
INPUTS ($)		DFID ($)				Govt ($)	Other ($)			Total ($)						DFID SHARE (%)
		3,131,292				0	2,001,905			5,133,197						61%
INPUTS (HR)		DFID (FTEs)

OUTPUT 2		Output Indicator 2.1				Baseline / Dec 2010	Milestone 1 / Jun 2012			Milestone 2 / Dec 2012		Milestone 3 / Dec 2013			Target Dec 2014		Assumptions
Detailed design study for a feasible ARC risk pool architecture approved and agreed on by key stakeholders		ARC financing strategy and institutional structure defined[12]			Planned	None	Draft ARC financing strategy developed and institutional structure defined			Final draft developed and dialogue on-going with required stakeholders* to finalize ARC financing strategy and institutional structure		An agreement on core technical content of the design proposal by sufficient stakeholders*			Governance structure in place and operating for ARC Ltd		All relevant actors identified in the risk pool are able in practice to satisfy the requirements of participation that are outlined in the design.
					Achieved							Done
						Source
						ARC Secretariat and ARC Ltd Reports
		Output Indicator 2.2				Baseline / Dec 2010	Milestone 1 / Oct 2012			Milestone 2 / Dec 2012		Milestone 3 Dec 2013			Target Dec 2014
		ARC participation, operation and M&E guidelines developed[13]			Planned	None	Process for approving contingency plans, paying premiums and monitoring ARC payouts drafted and under discussion with stakeholders			Draft of ARC operational manual completed for consideration and revision by ARC stakeholders*		Agreement on operational manual by stakeholders* sufficient for initial operation of the entity			Review conducted of guidelines
					Achieved							Basic structures agreed for ARC Agency and ARC Ltd, and in place, including key policies for ARC Ltd which will now be refined and formally agreed by the new Board of Directors. Contingency planning standards remain a weak link in need for further work.
						Source
						ARC Secretariat and ARC Ltd Reports
		Output Indicator 2.3				Baseline / Dec 2010	Milestone 1 / Dec 2011			Milestone 2 / Oct 2012		Milestone 3 / Dec 2013			Target Dec 2014
		No. of independent reviews of discrete technical portions of the ARC Project e.g. Africa RiskView, dynamic finance analysis, institutional structure, M&E, climate change stress tests[14]			Planned	0	3			7		10			14
					Achieved							13
						Source
						ARC Secretariat and Government Coordinator Reports
IMPACT WEIGHTING		Output Indicator 2.4				Baseline / Dec 2010	Milestone 1 / Dec 2011			Milestone 2 / Oct 2012		Milestone 3 / Dec 2013			Target Dec 2014
25%		Development of products for risks other than drought			Planned	None						Flood modelling funding secured			Flood modelling completed
					Achieved							Yes – SDC to fund
						Source											RISK RATING
						ARC Secretariat Reports											Low
INPUTS ($)		DFID ($)				Govt ($)	Other ($)			Total ($)						DFID SHARE (%)
		2,228,274				0	3,667,086			5,895,360						38%
INPUTS (HR)		DFID (FTEs)

				*This will be defined in the design process, and will depend on the governance and establishment requirements of the proposed entity structure and location of ARC
OUTPUT 3		Output Indicator 3.1				Baseline / Dec 2010	Milestone 1 / Aug 2011			Milestone 2 / May 2012		Milestone 3 Dec 2013		Milestone 4 Dec 2014			Assumptions
Consultation and political engagement carried out		No. of consultations (bilateral meetings, presentations, seminars) held with representatives from countries, RECs, donors, NGOs, IOs, private sector and leading thinkers consulted on ARC concept			Planned	25	55			80		100		125			Global macroeconomic stability, enabling new resources for ARC to be prioritized. / Donors and other institutional partners can take the ARC initiative on board and incorporate it into their programming, planning, policy making and budgets, as appropriate.
					Achieved							Over 200 complete
						Source
						ARC Secretariat Reports
		Output Indicator 3.2				Baseline / Dec 2010	Milestone 1 / Dec 2011			Milestone 2 / Dec 2012		Milestone 3 Dec 2013		Target / Dec 2014
		No. of different actors financially supporting, or have pledged to support, the ARC initiative (donors, private sector, Member States etc.)			Planned	3	5			7		7		8
					Achieved							10
						Source
						ARC Secretariat Reports
		Output Indicator 3.3				Baseline / Dec 2010		Milestone 1 / Aug 2011			Milestone 2 / May 2012		Milestone 3 Dec 2013	Target / Dec 2014
		Positive mention of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments			Planned	3		6			10		20	25
					Achieved								27
						Source
						ARC Secretariat Reports
IMPACT WEIGHTING		Output Indicator 3.4				Baseline / Dec 2010	Milestone 1 / Dec 2011			Milestone 2 / Dec 2012		Milestone 3 Dec 2013		Target / Dec 2014
25%		Number of countries that have joined ARC CoP (i.e., establishment treaty signatories)			Planned	None	n/a			n/a		26		30
					Achieved							18, with others in progress
						Source											RISK RATING
						ARC Secretariat Reports											Low
INPUTS ($)		DFID ($)				Govt ($)	Other ($)			Total ($)						DFID SHARE (%)
		1,863,796				0	1,483,350			3,347,146						56%
INPUTS (HR)		DFID (FTEs)

OUTPUT 4[15]			Output Indicator 4.1			Baseline / Dec 2010	Milestone 1 / Feb 2012			Milestone 2 / July 2012		Milestone 3 Dec 2013			Target / Dec 2014		Assumptions
Plan for the creation of the legal and organizational structure of ARC entity fully defined			Legal structure of ARC defined, and vetted by the AU, donors, potential Member States, and legal experts		Planned	None	Legal structure designed and produced to stakeholders for input			On-going dialogue with stakeholders regarding legal structure and incorporate input		Legal structure of ARC finalized			Legal structure established and in operation		Successful completion of Outputs 1-3 / Donor, AUC and AU Member State buy in.
					Achieved							Achieved
						Source
						ARC Secretariat Reports
			Output Indicator 4.2			Baseline / Dec 2010	Milestone 1 / Mar 2012			Milestone 2 / Dec 2012		Milestone 3 Dec 2013			Target / Dec 2014
			Process for establishment of the ARC facility defined		Planned	None	Confer with AU legal team and outside legal experts regarding the process for ARC establishment			Review of the most appropriate jurisdictions and venues for the establishment of ARC completed		Establishment process agreed upon by ARC stakeholders and underway			n/a
					Achieved							Achieved
						Source
						ARC Secretariat Reports
IMPACT WEIGHTING			Output Indicator 4.3			Baseline	Milestone 1			Milestone 2		Target			Target / Dec 2014
25%					Planned
					Achieved
						Source											RISK RATING
																	Medium
INPUTS ($)			DFID ($)			Govt ($)	Other ($)			Total ($)						DFID SHARE (%)
			644,015			0	1,841,215			2,485,230						26%
INPUTS (HR)			DFID (FTEs)
[2] Impact Indicator 1, Milestone 1: Added as a new intermediate milestone
[3] Impact Indicator 1 & 2, Milestone 2: Date changed to reflect the six month no-cost extension to enable the full 12 months of capacity building in each country, a critical component of the project as it moves towards its envisaged outcome and impact.
[4] Impact Indicator 1 & 2, Target by 2014: This final target has been adjusted down, over a shorter time horizon however, to be more realistic. After a year of operation, the ARC team has a better context with external factors and the reality of navigating the institutional bureaucracies and structures of multiple political organs in a regional initiative and, following initial country consultations, at the national level.
[5] Impact Indicator 2, Baseline December 2010: Values used in the original logframe were incorrect. The values have now been revised to accurately reflect currently available contingency funding in Africa for drought: Ethiopia (US $160 million) and Malawi (US $5 million), a total of US $165 million. The target for the overall ARC design phase remains at raising US $300 million in additional contingency funding.
[6] Outcome Indicator 1: The delays in country consultations and a rescheduling of country outreach at the request of the AU led to shift in timeline that in particular affected progress on Indicator 1 and Indicator 2. The revised indicators are now more realistic in terms of milestones and timelines, and reflect the new country outreach strategy and the no-cost extension to allow for full completion of capacity building.
[7] Outcome Indicator 2: As above for Indicator 1.
[8] Outcome Indicator 3: Initially, this was an indicator in the original Output 4. Further review of the logframe suggested this indicator is better posited as an outcome indicator rather than an output indicator, as fundraising is not directly under the ARC project’s control, but is important to reflect in the design process. Last two assumptions have been added to the outcome section as a result.
[1] This includes 1 Mil USD from the Rockefeller Foundation and 1 Mil CHK from the Swiss Agency for Development and Cooperation (SDC) currently undergoing confirmation.
[9] Output 1, Indicator 1.1: The original version of the logframe had very specific language on ARC in-country working groups for this indicator. Initial country outreach has showed the project needs to be more flexible in how it engages with countries and how it describes that engagement. Text referring to establishing ARC working groups within countries could be misleading as so many active groups already exist – as identified during the initial scoping missions – that can already be used to consider ARC participation.
[10] Output 1, Indicator 1.2: Numbers of milestones and the target were revised downward, as workshops have evolved to be regional and more comprehensive. Initially, workshops were envisioned to be frequent, small sessions for specific countries. Delays in country consultations also prevented progress against Indicator 2. The timeline and milestones are now consistent with the revised country outreach strategy.
[11] Output 1, Indicator 1.3: Indicator definition has been broadened to capture the ultimate aim of the cost benefit analysis studies originally outlined for this indicator, namely providing the rationale and economic evidence to countries for participating in ARC. The three cost benefit analysis studies initially envisaged in the original indicator have now been combined into one larger final report, which is due by June 2012.
[12] Output 2, Indicator 2.1: Due to World Bank engagement delays, technical work was delayed however since September 2011 good progress on the financial strategy has been made by the team. New milestones and timelines have been redefined to be more realistic, in particular regarding the process for defining and finalizing the institutional structure of ARC. Work with the AUC over the past year has allowed the team to understand these requirements and timelines better.
[13] Output 2, Indicator 2.2: Strict language on completion of operational manual was changed: the operational manual is a living document and cannot be finalized in the design phase of ARC. Final approval is something a newly established ARC Board must do after the design phase has been completed. The dates of milestones and the target of this indicator have also changed to reflect the timeline of Output 2 Indicator 1 above and the delays in the country outreach. Softer, flexible aspects of ARC’s design, such as the contingency planning component reflected in this indicator, will be further refined through interactive consultations with countries and stakeholders throughout 2012. The milestones reflect the reviews already carried out and those planned in the project’s lifetime.
[14] Output 2, Indicator 2.3: Currently, monitoring “active” ARV online users is not possible. In addition, ARV online access has been restricted by the project team due to the political sensitivities surrounding drought need estimates. The team has decided to limit ARV online access primarily to countries and their stakeholders working towards ARC participation, thus reviewing and customizing the model, and those who have received training on the tool. The original indicator to capture external user feedback has thus been substituted with a baseline that indicates ARV and ARC transparency in a different way: through peer reviews of all technical components of the project’s work programme.
[15] Output 4: As per the DFID feedback following the annual review, language of Output 4 has been changed to be one that is completely within the ARC project’s control. This revised output aims to complement the processes entailed in Outputs 1-3 and to complete the ARC design phase with an establishment roadmap. This output reflects a more comprehensive and robust design phase, contributing to the outcome and impact even if full operation of ARC is not achieved by the end of the project. Milestones and timelines have been chosen to reflect the two processes needed for define ARC establishment as an entity: the legal process and the political process with the AU. For example, July 2012 was chosen for Indicator 1, Milestone 2 because dialogue with ARC stakeholders must come after AU approval for moving ahead with ARC establishment is secured at the annual AU summit in June. December 2012 in Indicator 2, Milestone 2 reflects the required meetings to establish an AU specialized agency, following an AU process, to enable the potential establishment of an ARC entity by June 2013.