## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline |  |  | 2018-01-01 |  | Target (date) 2020
Strengthened national research systems, and nationally led research for development in East Africa. | Growth index of scientific production in East Africa | Planned | 1.17 (2010) |  |  | Growth index remains unchanged or increases. |  | Growth index remains unchanged or increases.
Achieved
Source
The data for the baseline and the project's end (2020) will be documented by political economy studies commissioned by the SGCI in 2016-17 (phase 1) and 2019-20 (phase 2). Sources include: African Innovation Outlook (AIO) Chapter on Assessment of Scientific Production in the African Union, 2005–2010 (using data from the Scopus database) by Africa Observatory on Science, Technology and Innovation, and Thomson-Reuters. AOI reports are published every 2 years and so data is expected in 2017 and late 2019 or early 2020. These are summarised in the SGCI Annual Report
| Impact Indicator 2 |  | Baseline |  |  | 2018-01-01 |  | Target (date) 2020
| Government investment in research and development in East Africa (GERD) | Planned | Burundi (0.8, 2011); Rwanda (n/a); Tanzania (7.6, 2010); Kenya (19.8, 2010); Uganda (7.1, 2010) |  |  | GERD unchanged or increases |  | GERD unchanged or increases
Achieved
Source
Political economy studies will document Gross Expenditure in Research and Development (GERD) per capita (current PPP$) for baseline and the project's completion. Main sources: African Innovation Outlook (AIO) Reports, UNESCO Institute of Statistics (UIS) Reports, National S&T Councils or Commissions, National Statistical Offices; Ministries of S&T or Planning and Economic Development (For example, Kenya National Bureau of Statistics). AIO and UIS reports are produced approximately every 2 years and so the data will most likely be available in 2017 and late 2019 or early 2020. GERD values are unlikely to change significantly over the project period. These are summarised in the SGCI Annual Report
OUTCOME | Outcome Indicator 1 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020 | Assumptions
More effective research investments and strengthened research leadership for development in East Africa. | Case studies to show how evidence, exchange and support has informed research allocation and grants management by science granting councils. | Planned |  | CTAs prequalified and final selection criteria agreed. SGCI MEL consultant in place | SGCI MEL Framework in place. First phase of political economy case studies (baseline) commissioned | 3 national political economy case studies completed (baseline). 2 SGC examples of how evidence, exchange and support has informed research allocation and grants management | All 5 national political economy case studies completed (baseline). Second phase of political economy case studies commissioned. 4 SGC examples of how evidence, exchange and support has informed research allocation and grants management | Second phase of political economy case studies completed (n= 5). 4 rigorously documeted case studies show how evidence, exchange and support has informed research allocation and grants management. | Evidence-informed policy and change requires engagement with the research system. Research system change requires a broad range of individuals and organisations that work together in different ways within the wider regulatory, legal and funding research environment The supply, demand for and application of research within each country is dependent on these individuals and organisations working together in a range of different capacities as producers, communicators and users of research Donor funding can provide specific support depending on the level (individual, organisation, environment) or area of the research chain (supply, broker, use) but requires wider buy in and politicalcommittment to effect change to the wider research system.
|  | Achieved |  |  |  | At least 3 national political economy case studies completed (baseline) At least 2 SGC examples of how evidence, exchange and support has informed research allocation and grants management
Source
Political economy case studies reports (first and second phases); Jan 18 & Jan 19 - SGCI Annual report will provide documented examples from the CTA technical reports. Jan 2020 - Rigorous case study reports on how evidence support has informed research allocation and grants management. These reports will document changes for at least 4 SGCs based on evidence from political economy analyses and the Evaluative Learning Framework (ELF)
| Outcome Indicator 2 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
| Case studies to show how high quality reseachers have been developed and are engaged with policy and how to promote equitable career pathways for internationally competitive African researchers including women and other under-represented groups | Planned |  | Independent learning on the DELTAS/AESA programmes commissioned | Independent learning completes inception and formative stage | Independent evaluation concludes mid term report & recommendations | Independent learning data collection and interim reports | Independent learning concludes final report & case studies
|  | Achieved |  |  |  | Independent evaluation concludes mid-term report & recommendations
Source
Independent learning commissioned across the DELTAS portfolio
| Outcome Indicator 3 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
| Case studies document how learning outputs have been taken up by science granting councils and research leaders in East Africa | Planned |  | CTAs prequalified and final selection criteria agreed. SGCI MEL consultant in place | CTAs contracts in place. SGCI MEL Framework in place and reporting agreed. | 2 SGCs take up learning outputs | 5 SGCs take up learning outputs | 4 rigorously documeted case studies show how leanring outputs has informed research allocation and grants management.
|  | Achieved |  |  |  | At least 2 SGCs take up learning outputs
Source
Jan. 18 and Jan. 19 SGCI Annual reports document examples of the influence and use of learning outputs from CTA technical reports submitted every 6 months and political economy study reports. Target outputs are cumulative. 2020 - Rigorous case study reports on the uptake of learning outputs (i.e. on themes from Annual Fora & the specially commissioned papers) . These reports will document changes for at least 4 SGCs based on evidence from political economy analyses and the SGCI MEL Framework
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020 | Assumptions
More effective research investments by Science Granting Councils in East Africa | Number of high quality research competitions | Planned |  | CTAs prequalified and final selection criteria agreed | CTA contract in place; work plan developed. At least 1 training event completed | 2 participating SGCs conducts a high quality research competitions | 3 participating SGCs conduct a high quality research competitions | 5 participating SGCs conduct a high quality research competitions | National governments have multiple roles as both a producer and user of research as well as having a major influence in the composition of the wider regulatory and funding research environment Evidence informs the effectiveness of research allocations Governments reflect their commitment to STI through budget allocation and support to the science granting councils.
|  | Achieved |  | As the monitoring and evaluation plan is still in development the definitions of the indicators have not been agreed (this is the same across all indicators).There is no mention of the completion of the benchmarking process in any report to date. | 2 contracts issued to SARIMA by NRF (June) and IDRC (October); Harmonized work plan has been developed after a detailed needs assessment. 1 training event (August, Kigali) has been completed | 2 SGCs (Kenya’s National Research Fund and Uganda’s National Council for Science and Technology) have been supported by SARIMA to conduct high quality research competitions using the ‘good practice' guidelines.
Source
CTA reports detail the number of SGCs conducting high quality competition through benhcmarking of key features such as transparency, expert panel review, merit-based awards, efficency of grant process. These are summarised in the SGCI Annual Report. Target outputs are cumulative
| Output Indicator 1.2 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
| Documented examples of SGCs adjusting research programmes and prioritising investments based on evidence and robust indicators | Planned |  | CTAs prequalified and final selection criteria agreed | CTA contract in place; work plan developed. 4 training events completed | 2 SGCs change approach to budget and allocation analysis and adjust research programs and prioritising investments based on evidence and robust indicators | 5 SGCs have modified their data collection instruments/ tools and received training on data collection, analysis and use for the design of research programs and budget allocation analysis | 7 SGCs have modified their data collection instruments/ tools and received training on data collection, analysis and use for the design of research programs and budget allocation analysis 4 SGCs adjust research programmes and prioritise investments based on evidence and robust indicators
|  | Achieved |  | There is no mention in the inception report of agreement on the budget and allocation approach. Funds for programme activities are currently underspent and it is not clear how these will be spent in the coming months. | IDRC issued 1 contract to NEPAD in August 2016. Harmonized work plan has been developed with other CTAs. 4 SGC training sessions were conducted in Namibia (October), Zimbabwe (October/ November), Senegal (November/ December) and Uganda (December). | 2 SGCs, Rwanda and Uganda, plan to use modified instruments/tools to begin collecting and analysing micro-level datasets in April and September 2018, respectively. This data can then be used to prioritise programmes and allocate resources.
Source
To include budget tracking of allocation and analysis of investment on STI . CTA reports detail the SGCs programmes and investments. These are summarised in the SGCI Annual Report. Target outputs are cumulative
| Output Indicator 1.3 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
| Documented numbers and examples of strategic partnerships with private sector: | Planned |  | CTAs prequalified and final selection criteria agreed | CTA contract in place; work plan developed. 2 SGCs confirm willingness to co-fund private sector partnership projects | Strategy for private sector engagement and monitoring in place. 2 participating SGCs engage in new partnerships with private sector | 4 participating SGCs engage in new partnerships with private sector | 5 participating SGCs engage in new partnerships with private sector
|  | Achieved |  | An overall strategy is not yet in place for the programme. | IDRC is finalizing 1 contract with ACTS (December 2016) but they have started work. 2 SGCs (Ghana and Kenya) have agreed to co-fund private sector partnership projects with the SGCI. | Strategy in place and 2 SGCs have involved the private sector to design their calls for proposals. Uganda’s National Council for Science and Technology (UNCST) has partnered with the East African Business Council (EABC), while Ghana’s Directorate of S&T is working with the Association of Ghana Industries (AGI).
Source
CTA reports documenting partnerships including financial contribution to projects by the private sector, student internships, involvement in project selection, utilisation of research results. These are summarised in the SGCI Annual Report. Target outputs are cumulative
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
30% | Numbers and examples of increased coordination activities between science granting councils in East Africa. | Planned |  | CTAs prequalified and final selection criteria agreed | CTA contract in place; work plan developed. 2 SGCs confirm interest to enter into new cooperation agreements | Strategy for supporting cooperation agreements in place. 2 new cooperation agreements for joint activities signed by participating SGCs | 4 new cooperation agreements for joint activities signed by participating SGCs | 5 new cooperation agreements for joint activities signed by participating SGCs
|  | Achieved |  |  | IDRC is finalizing 1 contract with ACTS (December 2016). 8 SGCs (Senegal, Zambia, Malawi, Ethiopia, Côte d'Ivoire, Uganda, Kenya and Rwanda) have agreed to enter into new cooperation agreements for joint activities. | Strategy in place and 2 new cooperation agreements were signed during the reporting period as follows: Namibia and Mozambique (September 2017); Malawi and Zimbabwe (November 2017).
|  | Source | [6 empty] | RISK RATING
|  |  | CTA reports detail cooperation agreements and joint activities such as collaborative projects and peer-to-peer support and learning. These are summarised in the SGCI Annual Report. Target outputs are cumulative | [5 empty] | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020 | Assumptions
Capacity built for research leadership in collaborating partners | Number first author publications in peer-reviewed journals (with % by women researchers) by collaborating partners | Planned |  | common monitoring system established across all grants | common monitoring system established across all grants | Number publications (with % women) | Number publications (with % women) | Number publications (with % women)
|  | Achieved |  | A common set of indicators and reporting processes have been agreed between grantees and the grant making mechanism. The system captures a range of routine monitoring indicators. The first reports from this system are yet to be produced. A system of data quality reviews has yet to be outlined. | Common reporting system in place and will be reported in March (2017) | 81 first-author publications (17 (21%) by women) in peer-reviewed journals by DELTAS research fellows in 2017
Source
| Output Indicator 2.2 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
| Numbers of (i) post doc (i) Masters (ii) PhDs (iii) graduate internships supported (with % of women) | Planned |  | common monitoring system established across all grants | Numbers of (i) Masters (ii) PhDs (iii) post docs enrolled & supported (with % women) | Numbers of (i) Masters (ii) PhDs (iii) post docs enrolled & supported (with % women) | Numbers of (i) Masters (ii) PhDs (iii) post docs enrolled & supported (with % women) | Overall programme targets of (i) >220 Masters (ii) > 170 PhD and (iii) >95 post docs of which 11.5% of each attributable to DFID
|  | Achieved |  | A common set of indicators and reporting processes have been agreed between grantees and the grant making mechanism. The system captures a range of routine monitoring indicators. The first reports from this system are yet to be produced. A system of data quality reviews has yet to be outlined. | Common reporting system in place and will be reported in March (2017) | Cumulative enrolment as of December, 2017: 154 Masters (82 women (53%)) 218 PhD (112 women (51%)) 85 Postdocs (39 women (46%)) 15 Senior Researchers, (7 women (47%))
Source
Numbers of trainees will be cumulative up to target by end of programme. Figures are takes as enrolled due to different lengths of training times. Total numbers graduating vs enrolled will be documented at the end of programme. 11.5% of overall results will be attributable to DFID in line with DFID's share of funding to this component.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
30% | Joint platform to support research leadership established and on sustainable financial footing | Planned |  | Platform established, with staff in place and governance structures operational | Open DELTAS call for proposals developed and run | DELTAs transferred to platform | Additional donor funding secured for granting. | Platform successfully transitioned from core start-up funding
|  | Achieved |  | The platform that houses the grant making programme for researchers has been established. | DELTAS consortia selected and awards made. DELTAS formally handed over to AESA | DELTAS Platform transferred to AESA in October, 2016
|  | Source | [6 empty] | RISK RATING
Minor
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020 | Assumptions
Increased research capacity in collaborating partners in Somalia | Number of training sessions/events delivered | Planned | 0 | contracts in place with M&E framework | 45 training participants (disagregated by gender and training type) | 45 training participants (disagregated by gender and training type) 30 learners graduating from newly developed HE courses (disagregated by gender) |  |  | Operating context provides stability for programmes to influence institutional change.
|  | Achieved |  | On track: Both contracts are in place with partners now nearing inception period for monitoring and evaluation frameworks to be in place. | 26 (7 female) mid-career researchers trained in research methodology. The training package delivered included three stages i.e. Training, Mentorship and Internship for all trainees 38 participants (8 female) received one 10 day training course (introduction to research methods) | 48 participants (10 female) completed three social research methodology training of trainers sessions 30 (5 female) mid-career researchers trained in research methodology. The training package delivered included three stages i.e. training, mentorship and internships for all trainees
Source
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
10% | Number of policy dialogue events (with documented examples) | Planned | 0 | contracts in place with M&E framework | 5 events such as (I) Policy forums (II) Curriculum reviews (III) Conference Presentations held or participated in | 10 events (cumulative) such as (I) Policy forums (II) Curriculum reviews (III) Conference Presentations held or participated in
|  | Achieved |  | On track: Both contracts are in place with partners now nearing inception period for monitoring and evaluation frameworks to be in place. | 12 Public forums were held by the two universities during 2016, the forums were used to present research and publications on pressing issues within Somaliland and Puntland. Some of the forum topics include transparency within government institutions, famine, the role of zakat in Somalia’s development. These forums were held at the universities, and attracted a wide range of panellist and audience members. IPCS within the University of Hargeisa held a curriculum review for all their Masters programmes. This activity was part of a large university reform that took place following a management reshuffle during the first 6 months of 2016. | 15 policy dialogue forums were held, including 8 events at Puntland State University and 7 events at University of Hargeisa 7 research validation and dissemination workshops were held, during which findings from research projects conducted by trainees were presented to relevant stakeholders in Somaliland and Puntland
|  | Source | [6 empty] | RISK RATING
|  | This output will continue to end FY 18/19. No targets are reflected for 2019 & 2020 | [6 empty] | Minor
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | DFID SHARE (%)
100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020 | Assumptions
Learning on what works and what does not in strengthening research systems particularly in East Africa | Number of knowledge outputs on research system strengthening in East Africa (e.g. political economy analysis; research synthesis; commissioned studies) | Planned |  | CTAs prequalified and selection criteria agreed | SGCI: 1 knowledge output produced | SGCI: 2 knowledge outputs produced Independent research commissioned on knowledge systems | SGCI: 4 knowledge outputs produced Independent research interim reports for 3 countries | SGCI: 8 knowledge outputs produced Independent research final reports and at least 1 papers and 3 country policy briefs | Evidence informs implementation of partnership programmes.
|  | Achieved |  | Embedded monitoring and evaluation frameworks have been agreed for outputs 2 and 3. Output 2 has also initiated an in-depth learning exercise. The monitoring and evaluation and learning agenda is still being developed under Output 1. | SCGI: A research paper “Research Excellence in Africa: a discussion paper on perceptions and measurement” was commissioned in October 2016 and presented at the annual forum in Maputo (November 2016). The paper is being finalized based on feedback from the forum prior to submission for publication. | Completed: 1 paper “The political economy of science granting councils in sub-Saharan Africa: defining a role for science funding in low and middle income countries” has been prepared and submitted to Science and Public Policy. 1 short correspondence article “Grant winners: track social impacts of grant types in Africa” has been published in Nature 550 7–8, 2017 Completed: The tender process has been finalised and the contract awarded to a consortium led by the Natural Resources Institute (NRI), University of Greenwich, with a start date of April 4th, 2018
Source
Knowledge outputs will be rigorous peer reviewed papers suitable for publication in a peer reviewed academic journal or similar. A list of papers and progress with submission will be summarised in the SGCI Annual Report. Target outputs are cumulative
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020
20% | Number communication (i) outputs and (ii) events on what works on research system strengthening | Planned |  | SGCI: launched and first forum held AESA/DELTAS: launched and first forum held | SGCI: 3 communication events held AESA/DELTAS: Annual Forum held and at least 2 events | SGCI 4 communication events held and at least 1 policy brief produced AESA/DELTAS: Annual Forum held | SGCI 5 communication events held and at least 2 policy briefs produced AESA/DELTAS: Annual Forum held | SGCI 5 communication events held and at least 3 policy briefs produced AESA/DELTAS: Annual Forum held
|  | Achieved |  | Embedded monitoring and evaluation frameworks have been agreed for outputs 2 and 3. Output 2 has also initiated an in-depth learning exercise. The monitoring and evaluation and learning agenda is still being developed under Output 1. | SGCI: Inception/ launch (Nairobi, September 2015); SARIMA Annual Meeting (May 2016); Annual Regional Meeting (Kigali, August 2016); Annual Forum (Maputo, November 2016); 1 press release (Kigali); 1 press release (Maputo); and 1 TV interview AESA/ DELTAS: Annual DELTAS Meeting – July 2016 Building a Strong Research Ecosystem for Sustainable Development – part of Gates Foundations Grand Challenges Conference in London 23-26 Oct 3 DELTAS Consortium Meetings IDeal Science Open Day , 26th September | Completed: SGCI convened the Annual Forum Meeting in Livingstone, Zambia in November 2017. 1 policy brief “Perspectives on research excellence in the global South” was produced Completed: DELTAS convened the Grantees Annual Meeting in Dakar, Senegal in July, 2017
|  | Source | [6 empty] | RISK RATING
|  | SGCI: CTA reports providing information on communication events and outputs, political economy studies report. Communication events include major meetings such as the annual regional meetings, annual forums and specialized meetings organized by the CTAs. Policy briefs refer to formal published briefs for policy and decision makers. These are summarised in the SGCI Annual Report. Target outputs are cumulative | [6 empty] | Minor
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) | DFID SHARE (%)
100%
INPUTS (HR) | DFID (FTEs)
Notes
The Business Case set out the selection process for partner organisations for each of the sub programmes. The primary focus of the programme is in East Africa but other organisations in sub-Saharan Africa could also be selected under two of the three sub programmes. Following the selection phase, the geographical representation of organisations in the programme is as follows: (i) Science Granting Councils Inititiative - 4 of 5 councils purposively selected within East African Community (Kenya, Tanzania, Uganda and Rwanda) plus Ethiopia. Other councils selected across West, Central and Southern Africa based on expression of interest and capacity. (ii) AESA and DELTAS: AESA platform established in Nairobi in headquarters of pan-African institution, African Academy of Sciences. Open competition for DELTAS grants. East African institutions represented in 10 of the 11 successful consortia, and representing half of all African partner organisations. (iii) Somalia Stability Fund focussed exclusively on research capacity building in Somalia. The commissioned research on knowledge systems (under Output 4) will focus on Kenya, Tanzania and Rwanda in East Africa.

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.

## Sheet1
Calculation for number of fellowships | 5 years | DFID contrbution (1/41)
Post doc | 28 | 0.68293
PhD | 112 | 2.7317
Masters | 140 | 3.4146
Graduate internship | 448 | 10.9268
Total | 728 | 17.7561
Number of awards | 7 | 0.17073