Project Completion Review

Title: Somaliland Development Fund Phase I
Final Programme Value £ (full life): DFID contribution £25.3m. Overall value of the Fund £ 52.3m includes contributions from Denmark, Netherlands and Norway	Review Date: November 2018
Programme Code: 202946	Start Date: December 2012	Final End Date: September 2018

Summary of Programme Performance

Year	2013	2014	2015	2016	2017
Programme Score	A	A	A+	A+	A
Risk Rating	Medium	Medium	Medium	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/

A. Summary and Overview
Description of the Somaliland Development Fund
The Somaliland Development Fund (SDF) is a multi-donor fund led by the UK. This PCR covers the first phase of the SDF which is now entering into its second phase. The programme’s intended impact was a more stable and prosperous Somaliland with an outcome of improved, and better resourced, state functions for the people of Somaliland. Programme interventions were to be aligned with Somaliland’s Development Plan 2013-2017. The SDF started in 2013 and finished in September 2018 after a 6-month time extension. Over the life of the programme, total spending was £52.3m, of which approximately half (£25.3m) was the DFID investment and the rest came from Denmark, the Netherlands and Norway. BMB Mott Macdonald was the Fund manager, contracted via an open tender process.

The SDF has become a well-known brand in Somaliland which has given it a strategic importance beyond its results and achievements: it is the Somaliland authorities’ preferred instrument, the UK’s flagship programme in Somaliland, is often the first issue raised in discussions with the President and is well known throughout government and the population at large for the results it has delivered. The SDF ensures access to the highest levels of government and cements the UK’s close relationship with the authorities in Somaliland. Its successes indicate that it is possible to deliver results – including the rehabilitation of 155km of road rehabilitation and making 5,858m3 of water available per day – even in a complex environment and provides potential demonstration effect for other parts of Somalia. Learning from the SDF is being used in other donor investments in the infrastructure sector.

SDF Achievements
Results: The SDF has delivered physical infrastructure and associated services that is changing people’s lives in a challenging and dynamic context. The SDF has achieved these results in a limited market place that had little to no experience of international tender processes, alongside mixed levels of government performance and capability. Over 90% of contracts went to Somaliland companies using international procurement standards, therefore making an additional contribution to private sector capacity, jobs and the economy. Past Annual Reviews have rated the programme from A to A+. Over its five-year lifetime, the SDF has reached:
- 1,438,000 people through interventions in agriculture, livestock, water supply, road rehabilitation, and basic social services. That is almost half of the population of Somaliland.
- According to the October 2018 SDF citizen perception survey, 72% of the sampled citizens reported improved service delivery in roads, water supply, and agriculture. 88% of the citizens reported improved journey time in the 156km of roads that were rehabilitated under SDF.
- The programme helped conserve 32,700 hectares of land through various conservation and integrated natural resources management initiatives: 740km of erosion control/soil conservation structures, reforestation/reseeding, and 89km of fencing for a livestock holding ground.
- When Somaliland experienced the 2016/17 drought, areas where land had been rehabilitated were the last to feel the effects; whilst this was not an explicit outcome of SDF it has shown how this type of investment can play an important role in building resilience and has informed our thinking about considering climate sensitivity and resilience early on in future investments given Somaliland’s vulnerability to climate shocks.
- Prior to the SDF no donor had implemented development projects in the two eastern regions of Sool and Sanaag (which make up half of the land mass of Somaliland) beyond humanitarian assistance. The SDF by contrast has delivered health, education, and water results in these regions and provided lessons for the future support in these remote and hard to reach regions.

Achievements in relation to State capacity: The SDF business case appraised three options and chose the second option which was to use government plans, implement using an external fund manager, and integrate into government planning and budgeting and eventual transfer of control of funds on the proviso that public financial management and revenue targets were met. Progress on both public financial management and revenue targets was slower than planned and delivered below expectations, and the gradual phased handover of the SDF to government control did not take place beyond the use of government planning systems. We will use the external review of the SDF – on-going – to relook at our approach to state capacity for SDF2.

Contextual Challenges Affecting Achievements
Political Economy, Inclusion and Conflict Sensitivity: The SDF political economy analysis in 2013 concentrated on who had influence, focused on finding ways to work within the existing government administrative system, but did not extensively consider private sector interests or seek to explore in detail issues facing citizens holding less power such as pastoralists, women and youth. For future programming and purposes of inclusion, the SDF and government of Somaliland needs to undertake inclusive participatory analysis and purposefully map people with less obvious official sources of power and support their ability to take decisions about projects that will affect them. The SDF, its donors and government partners should be continuously mindful of decisions that might reinforce systems that strengthen inequality – highlighted as a programme risk in the design. Similarly, the way that conflict was assessed relied too heavily on the initial analysis in 2013 and subsequent conflict sections embedded in the 11 project delivery documents. Experiences with the water projects in the east of Somaliland and the livestock holding ground project on the outskirts of the capital city Hargeisa, demonstrate the need for constant ‘everyday’ political, inclusion and conflict analysis. More positively, we have seen an appropriate approach to ‘doing no harm’, where the SDF secretariat immediately stopped work when concerns were raised and informed the Joint Steering Committee (JSC) for advice – this approach should be continued. Further thinking should go into how SDF works in the marginalised and conflict prone east of Somaliland, where SDF 1 projects faced the most delivery challenges.

Donors: DFID is the lead delegated partner for the SDF and takes on the administrative burden for the SDF secretariat. This works well with Denmark – that helped shape the original design of the SDF – which is the only donor agency with in-country presence in Somaliland and finances an adviser in the Ministry of Planning and National Development. As the SDF delivered both Norway and the Netherlands co-financed the SDF as silent partners. The UK has agreed to be lead partner again and the SDF2 business case was signed off by UK Ministers in May 2017. With contracting complete, a managed transition process from SDF1 to SDF2 is now taking place. An external review is providing further lessons and an expectation that SDF2 will take a slightly different approach across its implementation arrangements. The original donors are positioned to support SDF2, as is Sweden for the first time.

Governance: The SDF had an inclusive governance structure with the JSC focused on the strategic, decision-making issues. It met every quarter. The JSC comprised the Minister of Planning and State Minister of Finance and Donor representatives. Mott MacDonald acted as the secretariat. The SDF was initially poorly understood by some government ministries and engagement was limited. However, with the successful delivery of the first round of SDF projects, the wider government started paying more attention to the prioritisation process and are now heavily engaged in the latest round of prioritisation for SDF2 financing. The SDF increasingly became recognised and owned as a government initiative. Several lessons (at programme, governance and operational level) have been captured during the life of the fund and are included against each output in this PCR.

SDF2 project concept notes are now under development and taking account of lessons from this report.

## B: DETAILED OUTPUT SCORING

Output Title	Improved water and road infrastructure to promote economic and socially equitable development.
Output number per LF		1	Output Score	A+
Impact weighting (%)?		35%	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Overall Target	Achieved	Progress
Output Indicator (OI) 1.1: Quantity of water per day available for distribution in urban water systems with SDF support.	N/A	8,505 m3/day (69%)	5,858 / m3/day / (69%)	Rated B: The cumulative water made available is 5,858 m3/day against a target of 8,505 m3/day representing a performance of 69% of the overall target.
Output Indicator 1.2: Number of rural water points constructed or rehabilitated with SDF support.	N/A	165 water points	141 / (85%)	Rated B: Cumulatively, 141 water points have been constructed against a target of 165 (85% of overall target).
Output Indicator 1.3: % change in travel time on roads rehabilitated with SDF support.	N/A	37%	47% / (127%)	Rated A++: The overall change in the SDF road portfolio resulted in a 47% travel time reduction against a target of 37%.
Output Indicator 1.4: Length of roads rehabilitated to all weather condition with SDF support.	N/A	119.2km	155.9km / (131%)	Rated A++: The cumulative length of roads rehabilitated to date is 155.9km against a target of 119.2km.

Supporting narrative for the score
This has been one of the strongest outputs of the SDF and the most visible in Somaliland. Prior to the SDF, Somaliland’s war-torn infrastructure was in the main falling apart, with major trade and transit arteries impassable in places. The Government – through its national planning commission – directed the SDF to upgrade major urban water systems, rural water points and a major upgrade of the road network. The SDF has delivered an impressive set of results against this government direction. The SDF has invested in a laboratory in the roads development authority to support a sustained effort by the authority to maintain its network. Increasing water for all citizens of Hargeisa will address a key equity issues where sections of the city have been excluded from cheaper public water supply.

OI 1.1: The SDF activities with the Hargeisa Water Agency (HWA) changed significantly during implementation. Initially activities were focused on the drilling new boreholes on the outskirts of Somaliland’s main city, Hargeisa, and extending the in-city water system. However, as design started on the city distribution system the financing for a new water pipeline from the new boreholes into the city failed to materialise and the JSC responded by shifting the focus on the SDF work to replace the main water pipeline into Hargeisa and only design (not implement) the extension of the in-city water system which was passed on to KfW to deliver. This flexible response was applauded by the HWA. The cumulative amount of water delivered at this PCR is 5,858 m3/day through drilling of Hora Hadley boreholes, construction of Ayaha 1 & 2 water supply system, construction of Berbera springs and expansion of Burao town water supply system through 14km and connection of one of the constructed 100 m3 tanks. The milestone represents 69% of the overall target of 8,505 m3/day. However, work to meet this target in full is well underway and once the well field collector is installed in 2019 an additional 3,411 m3/day will become available for around one third of the population of Hargeisa (300,000 people). The SDF has already procured the well field collector contractor and implementation will start in early 2019.
OI 1.2: 141 water points against a target of 165 were installed and functioning. This represents 85% completion rate. The target was missed because of localised conflict and contractual challenges in two sites in the east of Somaliland. Insecurity in both sites meant that contractors could not access the sites. Both sites remain incomplete and have been handed over the Ministry of Water to complete once tensions reduce.
OIs 1.3 and 1.4: One of the SDF’s strongest and most consistent results. The cumulative length of roads rehabilitated was 155.9 km against a target of 119.2 km. This represents 131% completion rate. The reduction in travel time across the roads rehabilitated under SDF was 47% against a target of 37%.

Lessons and Recommendations
- Instil a clear understanding across the SDF teams about the time it takes to design appropriate programmes in Somaliland. Approaches in project design should recognise complexity of project delivery across Somaliland and allow adequate time for planning and addressing challenges.
- Re-design the conflict analysis in project formulation. The water projects in the east of Somaliland were the most challenging to implement, and two projects will not be finished because of resistance and conflict. The SDF2 inception phase is considering how to improve its local conflict analysis before starting further implementation.
- Focus on fewer, larger infrastructure projects. Some of the SDF prioritisation led to a long list of unrelated projects which do not contribute to the achievement of the SDF outcomes (e.g. rural water projects and a number of regional government offices whose occupancy rates are low). Experience has shown that a greater quantity of development activities does not increase overall programme quality but pulls overall results downwards. The JSC has already agreed with this recommendation.
- To continue with the policy to rehabilitate infrastructure and not build new infrastructure. A policy choice was taken early in the SDF to only rehabilitate existing infrastructure rather than to build new. This was taken because of pressure (rejected by the JSC) to invest in the new Erigavo road which runs from the city of Burao to the eastern city of Erigavo and is more than 250 kms.
- Consider different project team structures to deliver future projects in the eastern regions. Consideration should be made of splitting the project management teams – for example a project manager in the implementing Ministry and a project manager in the region. This could ensure better community engagement, better understanding of land issues, and better delivery.
- Engage in Somaliland annual budget formulation to track whether sufficient financial and human resources are provided for infrastructure maintenance. SDF investment in the Roads Development Authority laboratory has been a good investment. Contractors, as a result, bought the same testing equipment knowing full well the SDF secretariat would be spot checking their work. Understanding the budget allocation for the Roads Development Authority will help taking a possible decision under SDF2 to support regional mobile road maintenance teams.

Output Title	Improved productive sectors enhancing incomes, food security and livelihoods.
Output number per LF		2	Output Score	A
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Overall Target	Achieved	Progress
Output Indicator 2.1: Productivity of staple food (Sorghum) in Marodijeex Upper Catchment.	1.0t/ha	0.9 t/ha	0.7 t/ha / (78%)	Rated B: The average sorghum production from 2014 to 2017 in Maroodijeex according to FSNAU data was 0.7 t/ha. The target was 0.9 t/ha.
Output Indicator 2.2: Number of hectares of land conserved or rehabilitated (for both agricultural and livestock).	0	32,688 hectares	32,783 ha / (103%)	Rated A: Cumulatively 32,783 ha of land have been conserved against a target of 32,688, which is 3% above the overall target.
Output Indicator 2.3: Number of Animals accessing Aroori livestock holding ground and services.	0	30,000 animals	22,323 / (74%)	Rated B: The number of animals (camels and shoats) accessing water and veterinary services was recorded as 22,323 per month against a target of 30,000.
Output Indicator 2.4: Quantity of cubic meters of water per annum available in rural areas for livestock	0	158,399 m3 per year	217,083 m3 / (137%)	Rated A++: A total of 217,083 m3 per annum of water has been availed for livestock against a target of 158,399 m3; representing 37% above target. 43,000 livestock benefitted from water pans.
Output Indicator 2.5: Number of cold storage and ice making facilities constructed.	0	3 facilities	3 / (100%)	Rated A: 3 cold storage facilities were installed in the sites of Maydh, Hiis and Lasurwayn. The tonnage of fish per day processed by the facilities is 1.5 tonnes.

Supporting narrative for the score
Activities in the livestock and agriculture sectors have delivered in the face of challenges. The agriculture investments in the Marodijeex upper catchment – near the largest population of Hargeisa which is the largest market for agricultural products – have supported traditional water catchment techniques but fell short of the sorghum productivity target. This can be partly explained by two years of serious drought across Somaliland in 2016/17. Livestock remains the backbone of Somaliland’s economy but has been devastated by the drought. The livestock holding ground in Aroori is starting to function, but monitoring must be retained to ensure the full use of this facility occurs over the next few years. SDF work in the fisheries sector has been limited and questions the appropriateness of pushing the SDF into too many sectors.

OI 2.1: The average sorghum production of Maroodijeex was found to be 0.7 t/ha (78% against the target). The prolonged drought affected both the Gu and Karaan rainy seasons for 2017 which negatively impacted crop growth. Despite the lower than expected yields in 2017, 2018 has (so far) received above average rains and there is a positive outlook for better crop yields.
OI 2.2: The cumulative land conserved with SDF support was 32,783 hectares, 103% against the target. Land conservation increased forest cover in five forest reserves and rehabilitated grazing areas in four locations. Reforestation, construction of soil bunds, seeding of rangelands resulted in reduced rain water runoff, grass rejuvenation, fodder production, increased water retention and increased soil moisture. During the 2016/2017 drought, the SDF intervention areas were the most resilient in the face of the long dry spell.
OI 2.3: The rehabilitation of the livestock holding ground livestock is a major result with 25,000 hectares of land now fenced in (89km of fence). However, the drought in 2016 and 2017 significantly reduced the numbers of livestock and only 22,323 animals per month were able to benefit from veterinary services which represents 74% against the target and pulled the overall scoring down to a B. Two tonnes of grass seeds were purchased and reseeded, and six hectares were prepared for fodder production. The full potential of livestock holding ground – as a quarantine facility – cannot yet be realised because the other proposed livestock holding ground in the west of Somaliland was halted in the face of localised concerns about land rights.
OI 2.4: Water interventions far exceeded the target 137% and will benefit approximately 43,000 heads of livestock in Aoori (near the major city of Burao) and Maroodijeeh and Qool Caday (near the capital city Hargeisa). The 43,000 figure is for all livestock in the areas of intervention and based on the land’s carrying capacity. Project level feedback stated that this intervention increased the resilience of the interventions areas significantly, but a more robust review should take place in SDF2 to confirm these statements.
OI 2.5: Three cold storage and ice making facilities were installed in the coastal sites of Maydh, Hiis and Lasurweyn. The tonnage of fish per day processed is 1.5 tonnes which meets the target at 100%.

Lessons and Recommendations
- Consider additional financing for feeder roads to connect agricultural productive areas to markets. As production increases in the Maroodijeeh upper catchment area (on the outskirts of the capital city Hargeisa), and as other donors provide additional support in the Maroodijeeh area, thought should be given to the construction of access roads to enable market connectivity for rural agriculture producing areas. Coordination with DFID’s project that has provided value chains analysis across six sectors is improving our understanding and will help inform any future interventions under SDF2.
- Resume work on the Maydh jetty in the east of Somaliland. The major investment in the fisheries sector – Maydh Jetty– was put on hold because of the Danish decision to suspend SDF financing after the second delay of the Somaliland Presidential election in early 2017. This project is fully designed, and tender documentation prepared. The first SDF2 JSC approved the resumption of this project.
- Re-consider how the SDF2 might further support the Qool Qaday (on the outskirts of the capital city Hargeisa) livestock holding ground concept. Many in the livestock sector still see the rehabilitation of the Qool Qaday livestock holding ground as an essential part of support for the sector. The challenge is to manage the tension between the need to ‘set aside’ pasture for difficult years with the resistance from communities who see the land as a common asset they’ve used for centuries. Fencing in of land brings back memories of the Sayed Barre regime.

Output Title	Enhanced citizen perception of Government priorities, activities and expenditure
Output number per LF		3	Output Score	A
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Overall Target	Achieved	Progress
Output Indicator 3.1: % of people who report improved access to potable water in Hargeisa	5%	50%	65%	Rated A+: The percentage of residents that perceived improved access to water improved from 5% (Baseline) to 65% against a target of 50%.
Output Indicator 3.2: % of people who report improved journey time on SDF rehabilitated roads	0	95%	88%	Rated B: The percentage of respondents in the SDF supported project areas of Hargeisa, Berbera, and Dilla reported improved travel time from 5% (Baseline) to 88% against a target of 95%.

Supporting narrative for the score
The SDF established a communications hub in the Ministry of Planning from 2015-17. The outputs from that hub and wide-ranging press coverage that the SDF has received such as Presidential visits and project openings have ensured that the SDF brand is well known in Somaliland. Both public perception milestones have increased year on year as citizens benefit – in these project cases – from better quality roads and cheaper bus fares. These perception interviews focused on the largest SDF interventions, close to Hargeisa, where results were expected to be felt by users soon after the interventions were complete. The interviews were based on a random selection and do not claim to be fully representative. The interviews are project focused and not intended to be a sample of increased state legitimacy. In 2015, SDF and MoPND carried out a nationwide perception survey which was to be used partly to refine the communication strategy, however this coincided with two presidential election postponements and as such the results could not be used.

OI 3.1: This activity reached 65% against a target of 50%. The cost of water remains high at $6-7 per cubic meter for areas that are not receiving publicly provided water from the HWA, but the additional water from the boreholes is dependent on the completion of the well field collector so once that is completed (mid-2019) this public perception should increase markedly. With hindsight the original baseline was set too low and a better attribution concept could have been developed with an increasing number of donors working to support the Hargeisa water system. The HWA coordination mechanism is working well.
OI 3.2: The perception survey results on improved travel journey time started from a baseline of 5% in 2015, then peaked at 92% in 2016 when all roads had been completed, dropping to 87% in 2017 and most recently rated at 88%. It is possible that this final rating can be attributed to people getting used to the new road and identifying other areas of the road which should be upgraded. Maintaining 88% against a target of 95% implies that the quality of the roads is good and public perceptions are remaining significantly positive. Qualitative interviews of different road users show that most respondents were experiencing reduced travel times, less expenditure on transport, and decreased cost of doing business especially the transporting of goods.

Lessons and Recommendations
- In SDF 2 improve the disaggregation of citizens perceptions to better understand whether SDF results increase citizens perception of government. The SDF started to consider communications and public perceptions of its work too late in implementation. The low baselines and very high targets show a lack of engagement with recipients of SDF projects. Further thought should be given to this essential feedback loop in SDF2. The SDF2 might consider a communications officer sitting at the secretariat and working with different Ministries and media outlets. This is under consideration.
- Further contextualised consideration of road safety. More attention needs to be paid to road safety by passing requisite legislation and purchase of speed monitoring equipment. The SDF has invested in road signs and speed bumps but a culture change is required to prevent accidents.
- Engage with local and regional governments in programme design. The SDF programme design learned more about engagement with national authorities and less with regional governments or local authorities. This is often the missing link to bridging the gap between bottom-up planning (based on real and / or perceived needs) and top-down planning (and the need to elicit feedback from the communities). The SDF secretariat now has better feedback on what was working and needs to be changed and whether the local governments were aware of the planned interventions.
- Expand the remit of communications and citizens perceptions beyond the areas close to the capital city of Hargeisa. This current focus reflects the pressing needs in the capital for water distribution networks. Future citizens perceptions need to be gathered from other parts of Somaliland.
- Link citizens engagement with the sustainability of SDF interventions. Creative ways to cross check SDF interventions are best sustained via citizen engagement. Future communications activities under SDF2 should include better indicators to inform the JSC of sustainability issues.

Output Title	Improved government capacity to prioritise development objectives and to plan and budget development activities under the SDF programme expenditure
Output number per LF		4	Output Score	A+
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Overall Target	Achieved	Progress
Output Indicator 4.1: SDF Programme average aggregate disbursement deviation from forecasts.	5%	11%	9%	Rated A+: The average programme disbursement deviation stands at 9% which is better than the 11% target.
Output Indicator 4.2: / SDF Programme average time from approved concept note to approved project proposal.	0	180 days	124	Rated A+: The average duration to design and approve projects was much faster at an average of 124 days against a target of 180 days.
Output Indicator 4.3: Number of SDF projects executed on time and within budget by PMTs.	0	6	6 / (100%)	Rated A+: 6 projects were completed successfully.

Supporting narrative for the score
The SDF is the first multi donor fund established in Somaliland, and one that uses the planning country system. Setting up the SDF with all of its systems and operating procedures took the best part of the first year of operation. Once the results of SDF started to be realised significant attention started up from across government. This output tracks the improvement in the SDF secretariat’s systems and meeting the challenge from government to speed up implementation.

OI 4.1: Achieved.
OI 4.2: Achieved. With enhanced guidance, and using tried and tested SDF partners, project lead time could be further reduced to 90 days for some Somaliland partners.
OI 4.3: Achieved. Those Somaliland partners that completed their projects on time and on budget were: Ministry of Livestock, Ministry of Environment, Ministry of Education. Roads Development Authority, Communications Hub in the Ministry of Planning, Land Policy developed by the Rift Valley Institute, and the Ministry of Fisheries. Since this indicator was agreed and being tracked 5 new projects were approved and this indicator should have been amended to capture these additional 5 project’s project execution.

Lessons and Recommendations
- Allow sufficient time for participatory planning. Despite the SDF secretariat undertaking fragility, conflict and social impact analyses and contracting community-based NGOs, unforeseen issues with the recipient community led to misunderstandings and in some cases the cancelling of projects. With respect to the livestock holding ground project, and the rural water supply projects in the east of Somaliland, localised conflict occurred because of limited engagement with the local community. Some of these complications relate to legal authority and jurisdiction, and others to (lack of) participation and insufficient engagement with local communities. SDF2 partners must allow sufficient time for participatory planning and the SDF secretariat should plan for more consultation with recipients.
- Monitor and track the project execution of the five SDF1 projects that will be completed under SDF2. Delivering projects on time and in budget is difficult to achieve in Somaliland where project scope and context tends to change. These dynamics affect contractual performance for downstream partners, specifically the ability to deliver on time which has a knock-on effect with financial disbursements as well as ability to make accurate forecasts.
- Continue to rely on Somaliland’s planning systems. A key part of the SDF was to start drawing on an incentive fund to gradually make greater use of country systems. The SDF already started by using the Government’s planning system and partially its human resource system for setting up the project management units. The on-going external review of the SDF systems and modus operandi is explicitly considering a range of options across Somaliland country systems to clarify where the SDF2 can gradually make use of some country systems and where further strengthening is required.
- Increase the skills of crosscutting issues in the Somaliland civil service: Future training of civil servants involved in project management should include conflict, gender, environmental management and inclusion as key programming principles.

Output Title	Improved health and education facilities to provide social services (secondary health care and education)
Output number per LF		5	Output Score	A+
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Overall Target	Achieved	Progress
Output Indicator 5.1: Number of School buildings renovated / constructed and equipped in Sool and Sanaag	0	40 buildings	48 / (120%)	Rated A+ Cumulatively 48 school buildings in Sool and Sanaag have been completed and equipped with desks, kitchenware supplies, and beds against a target of 40.
Output indicator 5.2: Number of hospital buildings renovated / constructed and equipped	0	30 buildings	43 / (143%)	Rated A+: Cumulatively 43 hospital buildings have been completed - but not fully equipped - against a target of 30.
Output indicator 5.3: % of girls enrolled compared to total enrolment in the two secondary schools of Sool and Sanaag	0	25%	23%	Rated A: The initial girl ratio enrolment was 33% in February 2017 but dropped to 23% by October 2018 against a target of 25%. The drop in the enrolment ratio percentage is because more boys are enrolling compared with girls.

Supporting narrative for the score
This output is the result of a national planning commission request for $5 million to be allocated for basic services in the eastern regions of Sool and Sanaag. As water projects were already under design, implementation in Sool and Sanaag this output focused solely on health and education. The original design was to rehabilitate the two main referral hospitals in the regions – Erigavo and Las Anod, and establish two boarding schools, one in Sool and one in Sanaag. The targets in this output were exceeded significantly and represent an A++ scoring, however, the additional qualitative rationale for this project was the sustainable development of these facilities alongside a medium term recurrent budget for the management. In the absence of a recurrent budget for the schools and hospital the score provided is an A+.

OIs 5.1 and 5.3: Two secondary school level teaching facilities have been operational since the beginning of 2017 but using hired facilities in both Las Anod and Erigavo. The overall construction and equipping of school buildings stands is now 99% complete in Las Anod and 97% in Erigavo. The plan is to move to the rehabilitated schools by the beginning of 2019. The initial enrolment was 209 students with 69 girls (33%). However, the latest data in October 2018 shows that student enrolment has doubled to 409 but with fewer percentage of girls (94 girls are now enrolled which equals 23% against a target of 25%). Infrastructure is clearly not solely the causal link with girls’ education enrolment. In this case the installation of new infrastructure made local citizens send more boys to school relatively. This result shows the need to work in a sectoral approach in the education sector so that other social dimensions are considered in the design of education projects alongside infrastructure.

OI 5.2: Construction across all hospital facilities is almost complete. 48 school buildings renovated / constructed against a target of 40, and 43 health related buildings renovated / constructed against a target of 30. Management and new staff are in place but only in Erigavo. The Las Anod component was put on hold because of the freeze in Danish finances in early 2017. Several training sessions have been undertaken including: ICU, basic anaesthesia management and orthopaedic/surgical and trauma management. In 2016 the Ministry of Health informed the JSC that they were unwilling to work with UNICEF to provide the essential drugs supply and equipment. DFID and the SDF secretariat started conversations with the organisation DPSA and the first batch of essential drugs were delivered in May 2018 (18 months late).

Lessons and Recommendations
- Use UNICEF services for essential drugs supply in Somaliland health projects. The decision by the Ministry of Health not to use UNICEF for the provision of essential drugs supply and the delivery of equipment lost our health projects almost two years in time. UNICEF has the only reliable cold chain facility to cater for essential drugs and the capacity to support storage and stock out systems.
- Medical procurement is high risk. Drawing on the SDF to engage in the health sector met considerable implementation challenges. The experience from Erigavo hospital support is that health systems need long term support and are probably better suited to a medium to long term sector wide approaches that include: systems, cold chain, recurrent costs and quality of services. Any additional health projects that are proposed by the Somaliland government in SDF2 should be considered first under DFID’s health project SHINE.
- Test and monitor the original design of the SDF education and health projects to ensure the government allocates recurrent costs to sustain the facilities the SDF has refurbished. The concept to annually reduce the recurrent costs for the Erigavo hospitals and two boarding schools has yet to be tested. It will be under SDF 2. It is essential that recurrent costs are gradually taken up by the national budget. Having the new Minister of Finance on the JSC is key to making this happen.
- Support the equity debate and future policy formulation in Somaliland. The political decision to allocate $5million for Sool an Sanaag basic services was made in the absence of a policy to support government services in the eastern regions. Under SDF2 consider support for a coherent policy of supporting the eastern regions before designing new projects. The external review of the SDF is considering this issue and will be making recommendations around equity issues for SDF2.
## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Assessment of whether expected outcomes and target impact(s) were achieved

Outcome / Indicator 1	Baseline / (2013)	Overall Target	Achieved (2018)	Progress
Number of beneficiaries of services attributable to SDF supported projects		1,655,024	1,438,321	Rated B: Target not met. Reduction in available resource envelope following withholding of funding arising from delayed national elections in 2017, foreign exchange rate losses and project delays related to procurement and community conflict impacted on the provision of services.
Outcome Indicator 2	Baseline / (2015)	Overall Target	Achieved (2018)	Progress
% of citizens reporting improved service delivery in government sectors supported by SDF.	33%	55%	72%	Rated B: Target not met. Lower perceptions were registered because the Hargeisa Water System is still on-going. Cumulatively, citizens’ perceptions on three services (urban water in Hargeisa, roads and agriculture) have changed from 33% in 2015 to 47% in 2016 to 50% in 2017. In 2018, 72% reported improved service delivery in Roads, Water supply and Agriculture.
Outcome Indicator 3	Baseline / (2014)	Overall Target	Achieved (2018)	Progress
Average effectiveness and efficiency of SDF-supported GoSL MDA	4.0/6.0	5.0/6.0	5.1/6	Rated A+: – Target exceeded. A limited ex-post survey conducted in November 2017 reported an overall rating of 5.2/6.0 which exceeds the target. This score demonstrates improved capacity to prioritize development objectives. (6 as highest score).

The overall outcome score is an A. The outcome of the SDF did lead to “improved and better resourced core state functions for the people of Somaliland”. However, this is best explained by reviewing the actual programme outputs against the Original Theory of Change (below):

State Capacity, Country Systems and Phased Handover to GoSL
The SDF’s design was rooted in an understanding of the processes by which stability and prosperity can be effectively achieved in fragile environments and informed by best practice in operating pooled donor funds in such contexts; the key lesson from which is that the greater a government’s level of responsibility and ownership of a fund is, the more likely it is to have long-term sustainable impact. The Theory of Change assumed the following, some of which held true, and some did not:
- On plan and on budget: This was central to sustaining the strong government ownership. Improvements in decision-making by the GoSL were delegated at the sector level to the national planning commission, and at a project level to the ministries and in some cases parastatals. Here the evidence is mixed. The first round of sector prioritisation in 2013 (with some external support) produced a selection of sectors and partners that delivered the lion’s share of the SDF results to date. The government and parastatal partners also delivered consistently across the design and implementation phases of the project cycle giving the SDF, as an instrument, significant confidence to deliver more. Improved government capacity to prioritize, plan and budget development activities – there is partial evidence of this from some Ministries and parastatals – but there is a concern over the higher-level prioritisation process led by the national planning commission. There is collaborative decision making on day to day operations of the fund with GoSL, however planning for investments remained largely ad hoc. As further priorities were sought in 2014 and 2015, the tendency of the national planning commission was to extend the SDF into new sectors rather than consolidate around what the SDF was delivering best. The assumption in 2014 and 2015 was that the national planning commission would always make sound development and poverty related decisions. The weaker set of results from the second and third rounds of decision making show that assumption to be flawed. The decisions in the main were politicised.
- Public Financial management (PFM): PFM reforms stalled just as the SDF was starting but five PFM bills are now enshrined in law and work on the IFMIS is progressing. The design of a system that used Somaliland’s financial systems for local payments was designed but not implemented. The GoSL engaged in all procurement boards and the national tender board invited as an observer.
- Revenue reform: DFID continues to be the lead donor on revenue reform. Initial reforms struggled to apply a range of analytical work. However, the second phase is now registering the largest taxpayers, introducing customs reforms, and widening the reform conversation to the private sector, elders, academics and the Presidency.
- Somaliland budget expenditure and analysis: An indicator in log frame for 2015 and 2016 assessed the SDF investments against wider national spending on development. However, in the total absence of data about the budget, and the stalled PFM reform process, this indicator was removed. The World Bank’s last public expenditure review for Somaliland was 2013 making any formal judgement on PFM, or working with the budget, challenging.
- Government capacity: The SDF invested in a significant civil service training programme with the civil service institute to deliver a 9-month training programme for key staff in the SDF’s partners ministries and parastatals. However, budgeting processes for development priorities, increases in transparency, and accountability in the Government, have not yet delivered as expected.
- Supply-side communications technical assistance. Perceptions from some service users have been measured and improved as SDF projects were delivered. The Communications Hub in the Ministry of Planning supported SDF branding and external products.

Increased state capability was correctly pegged to the establishment of PFM to prove that that key Somaliland institutions had the capability to increasingly manage and account for external aid finance. This meant that the gradual transfer – notably over financial and procurement controls – did not take place and the fund continued to be delivered by the SDF secretariat in support of the prioritized activities with full procurement and financial control. This protected the delivery of results and fiduciary risks. However, the ToC remained to some degree valid without fulfilling PFM benchmarks or handing over more responsibilities to government. The ToC has partially fulfilled Outputs 1, 2 and 4 above. And despite the absence of reliable data, Somaliland is more stable and prosperous in 2018 than it was in 2013. Its political settlement is changing but the private sector continues to be the engine behind Somaliland’s state building success. A major caveat continues to be the poorest – especially those vulnerable to drought and those consistently affected by conflict – mainly the eastern regions of Somaliland where the SDF has struggled to make an impact. Arguably the Theory of Change should have been changed once the key PFM reforms stalled in 2016.

Explain major changes to the logframe in the past year

No changes took place in the past year.

## D: VALUE FOR MONEY

Whether the programme continues to represent value for money?
The SDF remains excellent VfM based on the its Results: Output scores have ranged from B to A+. The original TOC logic remains sound but warrants some refinement in the light of the changing context. Key constituent parts of a revised ToC would include: promoting political resilience, including through increased consultation and participation; Building Capability in the public sector in priority areas, including competence in policy making to solve problems and macroeconomic management; and building Equitable Systems of laws and institutions. Overall Risks: remained stable at Medium. The ultimate confirmation of the SDF’s VFM is Ministerial approval of SDF2.

The results of SDF delivery against the 2013 business case VFM analysis is as follows:

ECONOMY:
Performance against the 2013 economy metrics (below) was strong and consistent during SDF delivery:
1. Costs incurred by the fund manager. Metrics to include the costs of TA.
2. Costs incurred in implementing SDF projects. Unit cost of the delivery.
3. Procurement methodology employed and sub-contracting.

- Fund Management Costs: reduced from 21.3% to 16.9% despite the fund portfolio doubling from the initial business case value. Project delivery costs for the various projects averaged at 9.8% benchmarked against a 15% threshold. The major SDF key cost drivers have been accommodation, security, local support staff, travel, and vehicle rentals.
- Office Costs: in 2016, Mott MacDonald started the implementation of another DFID funded project in Hargeisa (ESRES) operating from the same premises as the SDF Secretariat. Mott MacDonald developed a transparent cost-sharing mechanism (75% - SDF, 25% - ESRES) for the two projects (e.g. security, rent, etc.) reducing its operational costs, and benefitting from economies of scale.
- Procurement and Unit Costs: the SDF Secretariat has consistently undertaken a comparative analysis of the market rates e.g. SDF infrastructure delivery benchmarked against tender proposals’ costing. The standardization of procurement procedures and policies has ensured that procurement is transparent, fair, timely and competitive. Where projects had similar activities like construction of soil bunds in MoA and MoERD and boreholes in MoA, MoWR and MoL; similar unit rates were adopted with a slight variation to cater for location differentials. Unit cost inputs for various project activities reduced significantly against the planned inputs, this was achieved though standardization of procurement procedures. This resulted in unit costs for some activities reducing by more than 20% and the savings were used to produce more project activity outputs. A payment by outputs approach adopted for the SDF programme ensured good VFM with savings in some contracts. With the principles of engagement being output focused, payments were made based on satisfactory delivery of agreed outputs. Where budget revisions were analysed and potential savings identified, more outputs were planned for. The table below presents analysis by the SDF secretariat of unit costs across project deliver:

			Units	Outputs		Unit Cost (USD/unit)		% Variance
Project		Sub Project		Planned	Actual	Planned	Actual
RDA		Hamas -Berbera - Sheikh Road (1st Project)	km	75	99	$85,365.32	$64,475.32	24%
		Kalabaydh - Dilla Road (2nd Project)	km	19	21	$108,125.00	$97,742.88	10%
		Hamas -Towards Hargeisa Road (3rd Project)	km	30	36	$73,333.33	$55,982.42	24%

HWA		Supply of Ductile Iron material pipes DN600 for Geed Deeble Transmission Mains & associated fittings	m	23,000	23,000	$313.39	$313.39	0%
		Construction of Ayaha 1&2 Water Supply System	m	5,100	5,100	$86.45	$79.06	9%

MoWR		Burao Water Supply Expansion Project	m	12,900	14,000	$46.11	$37.15	19%
		Hadaftimo Mini Water Supply System	m	3,783	4,583	$53.24	$48.38	9%
		Gargooray Mini Water Supply System	m	3,367	3,367	$70.25	$72.46	-3%

MoA		Construction of soil bunds constructed (Large soil bunds in farms)	m	415,000	415,000	$1.13	$1.06	7%
		Cost of Unlined Earth Dams	m3	51,480	59,905	$1.26	$1.15	9%
		Cost of Lined Earth Dams	m3	109,880	109,880	$2.17	$2.06	5%

MoL		Aroori LHG Fencing (Woven wire + Concrete Pillars)	m	89,000	89,000	$15.73	$9.66	39%
		Drilling of Boreholes - Aroori	m	450	626	$489.67	$352.00	28%
		Drilling of Boreholes - Qool Caday	m	450	400	$473.89	$366.33	23%

MoERD		Hectares of Land & Forest Conserved	Ha	1,400	1,926	$336.37	$160.14	52%
		Cost per m of soil bunds constructed (Large Soil bunds)	m	326,000	343,200	$1.20	$1.00	17%

- Somaliland Business Opportunities: out of the 478 contracts, 377 contracts were awarded to Somaliland consultants / companies which is a 79% engagement rate. Engagement of local contractors created local employment.
- Vehicle Rentals: the SDF Secretariat ensured reliable and competitive transport services from local service providers following a competitive bidding process.
- Donor Financing: the UK pound sterling reduced in value against most of the major currencies in 2016 – critically for the SDF against the US dollar. This had a major impact on SDF finances as the UK is the major donor to the SDF and led to: a re-organisation of inputs in some projects and reducing the scope of other activities. Converting other donor contributions to US dollars in real time cushioned the SDF against foreign exchange volatility.

EFFICIENCY:

Performance against the 2013 efficiency metrics (below) was strong and consistent during SDF delivery:
1. TA and training costs associated with the achievement of each output.
2. Citizens perception surveys to measure awareness of government priorities and expenditure.

Delivery Cost Ratios: programme management costs were estimated at 21.3% over the lifetime of the SDF. Experience from other suppliers – e.g. the United Nations – is in the region of 30-35%. The figure below illustrates the management delivery costs trends over the life of the SDF. Delivering a programme of this size below 20%, in such a complex environment, offers good value for money.

- Indirect Cost Ratios: analysis of project delivery costs (indirect costs as a ratio of total budget) shows planned project delivery cost at 8.4% – 3 outlier projects of the 11 were above 15%. Projects with infrastructure components had ratios as low as 4% and a maximum of 9%. Livelihood projects had quite high cost ratios, as high as 26% in one case, because they required similar levels of technical assistance despite lower activity costs. High cost ratios were also caused by the reduction in donor finances.
- Programme Management Teams: implementation, overseen by Project Management Teams in ministries and agencies, and mostly using private contractors and NGOs, has been pragmatic and has in most cases worked well. Mott MacDonald conducted a needs assessment for each SDF partner to develop quality proposals and programme management arrangements. This resulted in the design of a capacity building programme.
- Capacity Building: key staff across the partner Ministries and parastatals was undertaken in both Hargeisa and the major city on the east of Somaliland, Erigavo. The majority of the training was delivered by international trainers at the Civil Service Institute; and Civil Service Institute staff trained as understudies. The training took place over a nine-month period.
- Somaliland Staff: Mott MacDonald employed local staff in key positions which enabled constructive in-country relationship with the Government partners and better understanding of the local context and political economy across all project sites.
- Due Diligence: due diligence of suppliers’ procurement processes reduced waste, for example the water pipes the Hargeisa and Boroma water projects were inspected by certified engineers in China before importation and inspection on arrival. Mott certified engineers reviewed the Hargeisa technical designs before tendering to ensure the high quality of purchased goods and works was maintained.
- Programme Governance: the SDF Secretariat has actively managed relationships with all stakeholders ranging from the JSC, line ministries, and contractors.

EFFECTIVENESS:

Performance against the 2013 effectiveness metrics (below) was consistent during SDF delivery:
1. Effectiveness of spending on the projects financed by the SDF.
2. GoSL prioritisation of projects and effective budget management.
3. Subsequent extent of transfer of management and control of funds from the SDF to GoSL.

- Government Ownership: to ensure ownership and buy-in of all SDF project activities, sectors and project activities were selected from the list prioritised by the national planning commission based on the national development plan.
- Government Capability: the programme invested in building capacity of the technical staff at partners implementing SDF projects. The SDF integrated itself within government structures – for example, SDF budget allocations are part of national budget; the budget is approved by Parliament; and the SDF’s financial management system has the ability to report against the Government’s Chart of Accounts. Audits are, however, commissioned by the JSC and all payments are executed by the Secretariat through the SDF Main Account
- Citizens perceptions: in 2018, the SDF perception survey indicated that 72% of citizens reported an improved service delivery in sectors supported by the SDF. This is compared with only 33% at the start of the programme. SDF1 generated evidence, for the first time in Somaliland, on citizen perceptions of government priorities, activities and expenditure. This reflects a good start but was too limited an approach which needs to be broadened under SDF2. In part this reflects a weak communications in government that the SDF supported but could address more systematically.
- Private contractors: an important area of achievement is that private contractors were strengthened by the SDF’s effective procurement system. Approximately 100 contracts were let by the Secretariat for civil works. Of these, only two are regarded as having failed, an impressive success rate. Two major contractors interviewed as part of the November 2018 SDF review, reported that, never having previously taken part in international-standard bidding, they were originally unfamiliar with preparing bidding documents and also with some of the technical demands of the SDF. They reported that they benefitted considerably both in terms of being able to bid for a wider range of projects and in terms of improving their technical performance (e.g. pressure-testing water schemes). Other development partners have adopted similar procedures to the SDF, so it would be potentially possible to claim benefits both in terms of improving donor practice and in terms of harmonisation.
- Sustainability: there are concerns that attention to the sustainability of SDF investment has not been sufficient. Sustainability should be better understood at the start of SDF2 along four dimensions: financial sustainability (whether operations are funded by customers or through the government budget); organisational (the human resources and the administrative and management machinery, whether in government, the private sector, PPPs or NGOs); political economy (that is that assessments should be made to ensure that influential actors nationally or locally should have a real interest in sustaining the flow of benefits); and social (notably that clan elders and social groups (such as women’s organisations) should be supportive.

EQUITY:
Equity was not considered explicitly in the 2013 business case. However, this issue became a central part of SDF delivery.

- Equity thinking came late: Strategies and work plans were developed with local stakeholders to ensure local ownership and buy-in. The SDF made significant progress to ensure an equitable (geographically) distribution of development initiatives across Somaliland. The equitable distribution of projects was delivered through clear instructions from the national planning commission – regions shown in the table below. SDF2 needs to better internalise resource allocation, geography and clan. Ideally aligned with a Somaliland equity approach / strategy.
- Regional benefits: Through the capacity building project and the contracting of local consultants and suppliers, the SDF is building the capacity of local civil servants and private sector partners to deliver better services across all six regions of Somaliland.
- Gender and Clan: Where the SDF arguably failed was to fully consider the issue of gender. As the SDF2 gets closer to the government’s national budget the issue of gender and youth budgeting should be grasped as a core part of the planning and deliver agendas.

E: RISK

Overview of programme risk during the past year and over the life of the programme
The business case referred to international evidence on engagement in fragile states, highlighting it as inherently risk-taking. As such, SDF delivery was expected to incur a relatively high-risk profile and the likely need for experimentation. The overall risk rating for the SDF was Medium for 2013-2015 and 2017 and was Moderate for 2016 – with election delays and weak performance across government reforms driving that increase. The SDF secretariat, donors and implementing partners mitigated the main risks by investing heavily in understanding the political context in Somaliland in relation to delivery / implementation and using project design and regular donor-government engagement to consider the local environment and fragility. Proactive monitoring of programme risks and updating of the risk register on a quarterly basis with strong oversight from the JSC helped minimize most of the risks. The following table details the risks in the 2013 business case and how these risks were mitigated and managed during SDF delivery.
Risks	Probability	Impact	Risk Management During SDF 1
Government Ownership / There is limited ownership of the NDP across government. This obstructs a clear GoSL steer for national development. There is the risk that, by supporting the NDP the SDF is potentially be captured. This jeopardises the effectiveness of its activities and prevents the enabling aspects of the design.	Low/Medium	Medium	The SDF is referred to as the GoSL’s “preferred aid instrument”. Political changes – especially ministerial changes – often led to delays and new rounds of orientation and briefing by the SDF secretariat. Government ownership of the SDF is one of its most significant achievements and engagement in the on-going SDF sector prioritisation process is testament to that.
Political risk around recognition / As a pooled fund designed to support the GoSL’s development agenda, the SDF risks the perception that the UK and Danida are taking steps towards recognition of the government as the legitimate authority in Somaliland, especially under options 2 and 3, which lead to an incentive fund, which could be seen as budget support.	Medium	High	This risk did not emerge during the SDF implementation. Two additional donors – Norway and the Netherlands – co-financed the SDF from 2014 onwards, and this did not raise this risk, nor did the GoSL attempt to pressurise donors into the recognition issue.
Fiduciary Risk / Inadequate financial controls lead to the loss of funds and assets.	Medium	High	The SDF secretariat retained full control over SDF finances. The JSC considered using government systems to approve local payments but this concept was not taken up by the Ministry of Finance in 2016.
Non-delivery by implementing partners / The phased approach proposed under options 2 and 3 is dependent on the progressive success of World Bank and UNDP PFM and revenue reform programmes. If they fail to achieve their reforms, or are slower than anticipated in doing so, the fund will necessarily continue to implement projects largely independently of government systems, with no GoSL involvement except for the choice of sectors and the prioritisation of actions.	Medium-High	High	Slow progress on PFM – and the wider Government reform strategy – hampered the expected improvement in Government staff financial capability. As predicted in the business case the SDF secretariat implemented projects largely independently of government financial systems, although the annual expenditures were on plan and on budget. The SDF secretariat also experienced a limited availability of local goods and services which led to imports, resulting in slower delivery times and procurement delays. The slow pace of establishing a new portfolio for SDF 2 – which is slowing down the intensity of the Fund – may have repercussions on the SDF brand.
Non-delivery by the fund manager of the SDF, or by implementing agents / The success of the SDF is dependent on the employment of a competent SDF fund manager with skills including project management, M&E, and financial management, and on successful sub-contracting to implementing agents.	Medium	High	Mott MacDonald has consistently scored highly against DFID’s contract performance review. During the 2016 review Mott had a score of 83% - rated as “proactive, innovative, and delivering with superior efficiency”. The SDF review in 2018 recommends the secretariat increases its “capacity for appraisals in economics, social science and political economy, along with public administration, may need strengthening within the limits of what is affordable under SDF2.”
Government staff leaving positions, once trained, for development partner programmes / This negates the intention of said programmes to sustainably and durably build the skills and capacity of the government.	Medium	High	This risk did not materialise beyond the expected retention of civil servants. The 9-month training of civil servants was explicitly focused on young – male and female – civil servants to support the tenure of future talent.
Insecurity / Insecurity, e.g. insurgent attacks on UN and international agencies resulting in evacuation or potential harm of personnel, could significantly prohibit programme implementation.	High	High	Localised clan conflict has continued in Sool and Sanaag during the SDF. This has not led to the harm of any SDF staff or contractors. Localised conflict also altered the shape of the proposed livestock holding ground in Qool Qaday – which is just outside Hargeisa. Parts of the eastern region of Sool have been off limits for all of 2018 as conflict risks increased with neighbouring Puntland.
Development partner coordination / Inadequate development partner coherence and coordination carries the risk of undermining the SDF’s work, leading to duplicating, overlapping and counterproductive activities.	Medium	Medium	Development partner coordination has been strong throughout the SDF and co-financing donors encouraged to find an appropriate fit within the SDF governance arrangements. This coordination was put under pressure by the Danish decision to freeze part of their SDF contribution because on delays to the Somaliland Presidential election.
Political Economy of Somaliland / Somaliland’s political economy is complex and multi-faceted, consisting of multiple allegiances of political party, business and clan. Each group overlaps to a significant extent with the others, alliances and rivalries exist both across and within all of them, and all are to some extent dependent on geography. Without sufficient caution, the SDF runs the risk of being captured by a single group or small number of groups within the government, affecting the governance balance in ways that are unanticipated and jeopardising its operations. This is especially pertinent when it comes to the allocation of funds and procurement.	High	Medium	The national planning commission’ first round of prioritisation was sensitive to political realities and potential capture – by political and clan-based elites – and allocated a list of sectors and projects that delivered significant results. The second round of prioritisation became politicised arguably because government saw how effectively the SDF was delivering and internal pressure led to capture by some elements within government. Project design was the key area where this risk was mitigated, and some priorities were re-designed and, in a few cases, rejected.
SDF Exit Strategy / As the fund progresses in time, the ability of the fund to support long term interventions is diminished.	Medium	Medium	The SDF 2 business case was approved by UK Ministers in May 2017. Denmark, Norway and the Netherlands have confirmed future co-financing. Sweden is also considering joining the SDF for the first time. SDF2 is designed to do more of what SDF1 did well, refining its model to focus more sharply on economic development results including infrastructure and job creation. In parallel Government capability, PFM reform and shifts towards a medium-term expenditure framework are all expected to contribute towards an exit strategy after SDF2.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Mott MacDonald has delivered strongly against delivery, commercial and financial benchmarks. The SDF review – on-going – makes a number of recommendations about the changes that the Mott team will be considering during the SDF 2 inception period.

MOTT MACDONALD PERFORMANCE
- DFID’s Contract Performance Review (CPR) – Mott has continuously scored highly on the CPR which is conducted bi-annually. The CPR is a review of key DFID suppliers. During the last review in June 2016, Mott scored 83% (rated as proactive and innovative, delivering with superior efficiency and the effectiveness above Contractual expectations).
- Relationship with Government and Key Partners – Mott’s relationship with the Somaliland Government and SDF development partners including DFID has been extremely good and managed through DFID’s Key Supplier Management mechanism.
- Political Economy, Gender and Inclusion – as detailed in the output sections the Mott team has learnt lessons from the political economy, gender and inclusion analysis from the SDF inception. This analysis should have been updated during the SDF implementation phase and focused on informing project delivery.
- Monitoring – the SDF Secretariat continues to effectively manage the programme supported by robust monitoring systems, good governance and proactive communication.
- Delivery Partner Relations – the governmental ministries and agencies involved in the SDF have shown high motivation to support and lead the implementation of the programme, with respective programme management teams actively engaging to coordinate the implementation of planned activities.
- Big Picture: Mott has been heavily involved in procurement and contracting during SDF implementation. This has meant less time for comprehensive updates and information about SDF implementation and their impact on the citizens of Somaliland.

DELIVERY AGAINST PLANNED TIMEFRAMES
- SDF Started Slowly In 2013: with hindsight, an acceptable pace to ensure the standard operating procedures were fit for purpose and well understood.
- The Pace of Delivery Picked Up In 2014 and 2015: against its original mandate, the Theory of Change and Results Framework. The pace of delivery continued to increase as systems and processes became established.
- Activity Completion Was Good: of the 119 broad activities planned in 12 projects under the SDF, 116 are on track to be completed on time representing a 95.8% completion rate. Delays were properly identified and where possible projects and related activities have been rescheduled and all time and cost extensions approved by the JSC.
- Delegated Cooperation Worked Well: DFID continues to take on a large administrative burden for management of the Mott MacDonald contract. Other donors have doubled the size of the SDF making this transaction cost good VFM.
- Drought: The prolonged drought slowed down programme implementation, particularly in improving productive sectors to enhance incomes, food security and livelihoods.
- Elections: The final Danish contribution was withheld following the delayed Presidential elections ‘freezing’ some project delivery. Interaction with the Government officials in the election period was reduced and access to project sites was limited. Both affected decision making and delivery.

FINANCIAL MANAGEMENT
- Reporting: the SDF Secretariat adhered to contractual arrangements on financial reporting. SDF quarterly progress reports provided individual project summaries and the spend position as well as a quarterly finance management report. With the programme ending, monthly progress updates were agreed upon including financial reporting updates to track implementation.
- Forecasting: the SDF Secretariat has been consistent in preparing yearly budget forecasts which it shares with SDF donors and the government for discussion. The forecast is monitored regularly during the quarterly JSC meetings.
- Audit: annual external financial audits for the SDF programme have been carried out in accordance with international standards. The final audit of the SDF programme following its closure is scheduled to take place in February 2019.
- Standard Operating Procedures: the SDF Secretariat has a Financial Management and Accounting Manual, the provisions of which were adhered to. The quality of financial management is good and has steadily improved since the start of the programme. The SDF Secretariat adheres to contractual arrangements on financial reporting. SDF quarterly progress reports provide project summaries, spend position, and a quarterly finance management report.
- Exchange Rates: Mott MacDonald developed a tracking system for all donor contributions including potential exchange rate losses / gains. As donor contributions in various currencies have depreciated against the USD a considerable exchange rate loss was incurred on available programme funds in USD. The impact of this deficit was reduced scope of some projects.
Date of last narrative financial report	05/12/2017
Date of last audited annual statement	12/06/2017

The table below outlines the overall financial position of the SDF:

Original Value	£31.9 million, rising to £52.3 million after extensions (see below)
Extensions and Amendments	DFID’s original contribution to the project was £20 million with an original end date of April 2018. Cost and no-cost extensions as follows: / Cost Extensions: / 12 May 2014: A cost extension (Contract Amendment No. 1) of £3.6M was made to reflect new Norwegian funding to SDF increasing total to £35.5M / 23 July 2014: A cost extension (Contract Amendment No. 2) was made to include additional money towards capacity development work. This increased the SDF funding to £35.9M; / 7 March 2016: Cost and time extension (Contract Amendment No. 3) from £35.9M to £52.6 to reflect fresh contributions by DFID (£5M), DANIDA (£8.5M) and Netherlands (£3.2). / 30 November 2017: Cost reduction (Contract Amendment No. 4) of Mott’s fund management contract by £209K to facilitate the drawing up of DPSA call down contract to facilitate the procurement of essential drugs for the Erigavo hospital. This reduced the SDF funding managed by Mott to £52.3M. / No cost extensions: / February 2018: A 6-month no-cost extension (Contract Amendment 5) to allow to allow us adequate time to complete the procurement process for SDF2. The end date was extended from March 2018 to September 2018.
Total Programme Spend	£ 49M[1]
[1] This includes all payments made as at 10 November 2018. Additional payments, linked to this PCR, are scheduled before 31 December 2018 to address commitments entered before the closure of the SDF programme on 12 September 2018.

ASSET MONITORING AND CONTROL
- Asset Register: the SDF Secretariat maintains an asset register. All programme assets are systematically recorded and reported in a comprehensive asset register, maintained by the SDF Secretariat. The asset register is reviewed and shared with DFID Somalia every six months. The asset register was last updated in August 2018 in preparation for programme closure. DFID intends to use the LAMPS team, DFID Somalia’s third-party monitoring team, to carry out an asset check of several projects with assets currently in storage.
- Vehicles: are the major SDF asset. With partner line ministries and parastatals, the secretariat put in place vehicle use guidelines and tracks usage. A policy is in place for all project vehicles (except the ambulances for Erigavo hospital) to be returned for use in SDF 2.
- Closure: with the completion of the programme the SDF secretariat, in partnership with development partners, has developed robust handover guidance to facilitate programme closure and ensure a seamless transition to the SDF2 programme.

G: MONITORING, EVIDENCE & LEARNING

The SDF has developed a strong internal M&E system and been subject to a number of external reviews, over the course of the programme, notably by ICAI and an ODI evaluation of the New Deal. Consistent feedback, usually via the JSC, has ensured that sound monitoring has been converted into robust evidence and learning. The original (2013) SDF business case split the monitoring requirements into three tiers. Details on these tiers, how M&E was done under each tier, and overall results by 2018 are as follows:

Tier 1 M&E: What progress is Somaliland making towards being stable and prosperous?
Three external reviews – by ICAI, ODI and the UK’s Policy Practice – considered the SDF’s impact on Somaliland’s stability and prosperity. The most recent external review of the SDF by the UK’s Policy Practice in 2018 was undertaken in 2018 and reviewed this question with several stakeholders and sources. The team agreed that the SDF is one of the best-performing aid instruments in Somaliland, and that “if there is a balance to be struck between getting development done fast, and building government systems and institutions, SDF1 got it about right”.  The review team also stated that “SDF2 needs to be more ambitious in line both with Somaliland’s changing circumstances and the likely increase in funding under SDF2. The original theory of change for SDF1 was based on the equation that a more stable Somaliland would lead to a more prosperous Somaliland, and vice versa. To promote stability and prosperity required a better resourced and more capable state. This broad logic remains sound but warrants some refinement in the light of the changing wider context.”

Tier 2 M&E: How does the SDF contribute to Somaliland’s development?
- The SDF developed a strong M&E system, guided by the logframe and the SDF M&E manual and framework.
- The secretariat and partners in GoSL have monitored the implementation of the SDF projects and submitted quarterly progress reports. These reports highlighted progress towards achieving the logframe milestones / results, funding financials, risks and value for money.
- The secretariat undertook monitoring visits to project sites to assess implementation progress.
- Members of the JSC have periodically visited field sites jointly to assess progress and understand the operating environment.
- The secretariat facilitated quarterly programme steering committee meetings (JSC) to monitor progress on activities and make strategic decisions. With the imminent closure of the programme, the JSC agreed to monthly progress reporting and meetings to ensure better management of the transition process from phase one of the SDF programme to SDF2.
- The secretariat conducted a perception survey annually to monitor Somaliland citizens’ opinions/perceptions of the extent to which support interventions including provision of water, roads and agricultural improvements have impacted on their productivity and livelihoods. In a recent survey done in October 2018, beneficiary interviews indicated a positive outlook of the SDF projects and have expressed optimism on how funds are being spent. Improved travel time, less money spent on car repairs and improved agriculture yields where tillage was provided by both the SDF and GoSL complimented with rehabilitation of small earth water dams were some of the responses from the beneficiaries.
- The SDF programme has been formally reviewed through annual reviews which included field visits, stakeholder interviews and desk-based analysis. Since inception in August 2013, five (5) Annual Reviews with recommendations have been undertaken with recommendations implemented and lessons learned shared to inform future programming.

Tier 3 M&E: Does the SDF manage itself and its operations efficiently and effectively?
1. As part of the SDF2 business case development in 2016 and 2017 DFID commissioned two independent reviews of the SDF programme. The first asking a series of in depth question about the results and management of the SDF. The review was generally positive but cautioned against rushing into making further use of country systems based on SDF delivery and experience. The second review drew on the Evidence on Demand resource to assess evidence on the gradual handover of management responsibilities of multi-donor funds in fragile and conflict affected states. The review concluded that there was little evidence on handover of multi-donor funds to host governments. The review stated that in any multi-donor fund the vision is always for government to gradually take on delivery with stronger management and financial systems. The review also cautioned against driving the handover of management responsibilities too quickly, and to protect the delivery of results in the earlier years of delivery.
2. ODI undertook a review of the New Deal and referred to the SDF as a “model fund in FCAS”.
3. ICAI also reviewed the SDF and made specific mention of the SDF’s enhanced approach to managing risk.
4. The JSC agreed on an external review of the SDF to support the transition between SDF1 and SDF2. The objective of this review was to identify lessons from the first phase of SDF1 and make recommendations to improve the delivery and governance of SDF2. The terms of reference were jointly agreed between the GoSL and donor partners. The results of this review will be reviewed at the next JSC in January 2019.

Third Party Monitoring
A third-party monitoring firm, (a consortium of private sector organisations procured under the OJEU procedure) provided third party monitoring/verifications and M&E technical assistance support. To date, 40 SDF verifications have been carried out with findings being communicated against five criteria; relevance, effectiveness, inclusivity and gender, efficiency and sustainability. LAMPS reporting has been helpful in ensuring that projects are completed or implemented in an efficient manner and that the quality of work meets the technical quality standards and contractual requirements. The SDF had 40 reviews undertaken of which 32 were satisfactory, and more recently 8 required urgent follow up. The urgent follow up recommendations below will be addressed within the next three months:
- 4 red flags against Ministry of Water projects. These concerns have been formally submitted to the Minister of Water and relate to tensions in the east of Somaliland where a project has not been completed and a number of other technical challenges.
- 1 red flag against the Ministry of Health. This is a concern around the maintenance of the payroll at the Erigavo hospital the SDF is supporting, and conversations are on-going with the Ministry of Finance to gradually take on these recurrent costs.
- 1 red flag against the Ministry of Fisheries. Follow up is confirming the functionality of one of the cold storage units.
- 1 red flag against the Ministry of Agriculture. Follow up on-going around the construction of one of the nurseries.
- 1 red flag against the Ministry of Livestock. This project has now been completed.

Learning

The key lessons have been highlighted in section B under the specific outputs as well as recommendations. As part of learning and ensuring that lessons learned from the previous Annual Reviews were followed up, there was a quarterly review/tracking of progress of the recommendations and lessons. The on-going review of the SDF presented the following learning to the JSC in November 2018 and will be embedded in SDF2 delivery.

Multi donor funds such as the SDF can deliver impressive results in Somaliland: “The SDF is one of the best-performing aid instruments in Somaliland”. The SDF got the balance right between getting development done fast and building government systems. Large-scale measurable benefits were achieved. The SDF had a learning and adaptive approach. Strongest results were in infrastructure, not health and education.
Government ownership remained strong: the SDF was among the first to use New Deal principles. Government’s prioritisation was supported within the framework of SDF broad priorities. SDF developed ways of Ministries implementing, mostly through private contractors.
Private contractors can be strengthened: by using international bidding processes.
Sustainability is key. Some projects may be sustainable (e.g. water revenues).  But lack of budget for recurrent costs, and weak systems for operations and maintenance are a concern for some projects. Embed sustainability more strongly: financial, human resources; political; and social.
Lack of coherence: some projects were not anchored in a coherent approach (lack of complementary inputs, supportive policy). SDF2 to be more focussed.
The SDF has started to help government develop a strategy for the east of Somaliland: need projects that both (a) support national stability and (b) make sense developmentally and can be sustained.
Project management teams performance was variable: most but not all worked well, and were strengthened (training, systems) with enduring effects.

Progress on recommendations from annual reviews

Recommendations from annual reviews were captured in tracking sheets and reviewed on a quarterly basis to ensure their implementation. Below are some key recommendations from previous annual reviews that will inform the design and implementation of SDF2 projects:

1. There should be an integrated approach to WASH interventions to secure better health outcomes as opposed to just providing water supply systems without accompanying hygiene promotion and sanitation.
2. The SDF partners to devote additional time to improve donor coordination in support of the Hargeisa Water Authority (HWA), agreeing on common international standards for equipment and construction. Although HWA is an experienced implementer, SDF2 should not underestimate the time required to manage projects of this scale.
3. All future projects related to land restoration, rangeland and watershed management projects should be at least three years in implementation to allow for full participation and buy in by the communities which will foster community-based sustainability of the interventions.
4. The conservation and environment restoration projects are quite thinly spread. This makes monitoring and quality assurance a challenge. Future support should consider linkages, clusters and more concentrated project locations to validate impact.
5. Engagement with the Minister of Finance (a JSC member) to ensure that SDF annual allocations are clear to both the Council of Ministers, and the budget committee, so that these SDF allocations are integrated into budgetary debates in both the Executive and Parliament and are on plan and on budget.
6. In future, a comprehensive study on status of roads in Somaliland (all classifications) should be conducted and a road sector development and maintenance strategy developed and implemented.  The RDA have this in their plan and wish to have a software-based pavement management system to assist this process.